## Annual Review Template

Title: Strengthening Africa’s Science Granting Councils (SGCI-2)
Programme Value £ (full life): up to £11.2m	Review date: 03.02.2026
Programme Code: [AMP ID#] 301049	AMP start date: March 2021	AMP end date: December 2026

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	A	A+	A+	A+
Risk Rating		Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-301049/documents
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005663.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

The Science Granting Council Initiative (SGCI) is a multi‑donor partnership supporting equitable and sustainable development by strengthening nationally led research and innovation systems. It is funded by the UK’s Foreign, Commonwealth and Development Office (FCDO), Canada’s International Development Research Centre (IDRC), South Africa’s National Research Foundation, the Swedish International Development Cooperation Agency (Sida), the Norwegian Agency for Development Cooperation (Norad) and the German Research Foundation.
Since its inception in April 2015, SGCI has strengthened the capacity of Science Granting Councils (SGCs) in 17[1] sub-Saharan African countries. Over the past decade, it has supported councils develop and deliver research excellence, using a systems approach that promotes women’s inclusion in research, strengthens evidence‑based policymaking, and increases private‑sector engagement. SGCI brings together governments, researchers and development partners to build science partnerships around shared priorities and values.
[1] Participating countries are: Kenya, Rwanda, Uganda, Tanzania, Ethiopia, Côte d’Ivoire, Burkina Faso, Senegal, Ghana, Zambia, Mozambique, Malawi, Namibia, Zimbabwe, Botswana, Nigeria, and Sierra Leone.
Building on the strong foundation established under SGCI-1 and SGCI-2, and leveraging the ongoing interest and momentum, FCDO, Norad, Wellcome[2] and IDRC have agreed to a third phase of the Initiative (SGCI-3), from 2026 to 2030 with an estimated investment of approximately £30M. SGCI-3 will continue to strengthen capacity but include a greater focus on supporting high-quality research and innovation, institutionalising capacity building efforts, advancing STI policy leadership, and deepening African ownership for its long-term sustainability. The current phase has received a one-year extension to continue implementation until December 2026. This is intended to ensure a more sustainable transition to SGCI-3.
[2] Welcome will be joining SGCI-3 as a core funder.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]
The programme is performing strongly, with an A+ rating given all outputs are achieved or exceeded. The programme has delivered systemic improvements in how national research systems are governed, funded and used to inform policy. Research systems have been modernised at scale: grants management is now digitised in 12 countries, supported by a central Helpdesk and peer technical teams that are already being replicated in other programmes such as CHINNOVA[3]. Financial integrity has also been strengthened through adoption of Good Financial Grant Practice (GFGP), demonstrating growing confidence in council systems. Councils are increasingly shaping national and continental science policy. Eleven countries now use Research and Innovation Frameworks to guide national research priorities and evidence‑based decision‑making, with Côte d’Ivoire and Kenya showing strong application in practice. Councils are also contributing to national committees, continental dialogues and the implementation of the Science Technology and Innovation Strategy for Africa (STISA-2034).
[3] CHINNOVA is one of five regional hubs established under the Advancing Research for Climate and Health (ARCH) initiative, jointly funded by IDRC and FCDO. The initiative aims to strengthen research capacity, especially in the Global South, and support local/regional leadership in climate-health research.
Engagement and capacity strengthening remain high, with councils participating in 43 training events (34 in‑person and 9 virtual). Progress extends beyond governance: SGCI has advanced gender equality through the co‑creation of the From Principles to Practice Gender Equality Inclusivity and Intersectionality (GEII) framework with 13 councils; strengthened research quality and ethics; and supported commercialisation, including Tanzania’s COSTECH Intellectual Property (IP) audit uncovering dozens of patents and training over 220 researchers.

SGCI strategic communications have also been revitalised, reaching over 183 million people. Strategic convening has positioned the UK as a trusted partner for science across Africa, leveraging our local staff to unlock 11 new bilateral and multilateral research partnerships.
Taken together, these results demonstrate a programme that is performing consistently, building credibility, and laying strong foundations for SGCI‑3, where the focus will be on sustaining impact, deepening partnerships, and maximising value for money.

Major lessons and recommendations for the year ahead [1/2 page]

As SGCI-2 reaches its final year of implementation, the programme has generated several recommendations based on important lessons that will directly inform the design of SGCI‑3.

Feedback from Councils has underscored a strong desire to have greater influence and agency in shaping SGCI’s implementation. SGCI-2 introduced the Councils Committee (CC) as part of improvement to SGCI’s governance structure. The CC was intended to align SGCI activities with the priorities of participating Councils and to support the initiative’s long-term sustainability. However, over time, it became evident that the CC, comprising Heads of Research Councils (HORCs) convened only once annually, was not as effective as initially envisioned. As a result, for SGCI-3 the SGCI Alliance will be implemented to provide a more robust Council-led structure that reflects the growing maturity and complexity of Africa’s STI ecosystems. The Alliance will foster deeper ownership, enhance collaboration, and facilitate mutual learning among Councils and a broader network of stakeholders. It marks a significant evolution in SGCI’s governance, ensuring that Councils are not only participants but also strategic drivers of the Initiative’s future

- SGCI-3 has decided to move to a pooled funding agreement between development partners to reflect the maturity of the programme and maximise impact, coherence, and value for money. SGCI-3 is moving from capacity building to system leadership and global influence for African science granting councils. This requires partners to work from one agreed theory of change, results framework, and governance model, rather than parallel or donor specific approaches. Pooled funding ensures all partners are aligned around shared priorities, standards and outcomes and will reduce fragmentation and transaction costs. It will also strengthen African ownership, shifting the SGCI away from donor‑led programming towards a council‑led, collective model, consistent with SGCI‑3’s emphasis on: African leadership, equitable partnerships, and longer‑term sustainability.
- Leverage the SGCI Alliance and STISA-2034 implementation to amplify impact and diplomatic influence
Structured engagement between FCDO Posts and SGCI continues to provide meaningful influence over national science and technology policy. In Ghana, sustained collaboration with MEST contributed to the operationalisation of the Ghana National Research Fund- demonstrating how coordinated platforms can align national priorities with continental agendas and donor priorities. As SGCI‑3 introduces the new SGCI Alliance, FCDO country offices can leverage this mechanism to deepen bilateral collaboration, promote coherence with UK investments, and strengthen alignment with the implementation of STISA‑2034.

Deepen Institutional Capacity Strengthening for SGCs at Different Maturity Levels: Councils across Africa vary in maturity, capacity, and funding. Larger, established councils have more resources and systems, while newer/smaller councils require more support and capacity building. Mapping of council activities and needs is underway, with a database proposed for targeted technical assistance. SGCI‑3 should provide tailored institutional support to help councils operationalise governance frameworks, support emerging councils to build foundational structures and capabilities, and sustain peer-learning and South–South mentorship across councils.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

SGCI-2 remains underpinned by a coherent and credible Theory of Change developed jointly by the four core funders (IDRC, Norad, Sida and FCDO). In 2023, funders agreed to consolidate previously separate frameworks into a single multi‑donor model, integrating the FCDO ToC to strengthen alignment and collective impact. The overarching impact and outcome indicators from the original business case remain valid and continue to provide a sound basis for tracking progress.

Evidence from the 2025 reporting period confirms that the core logic of the ToC is functioning effectively. The link between capacity strengthening, improved institutional systems, stronger policy influence and increased research investments is supported by implementation results. Most outcome and output targets have been met or exceeded, with notable progress in Research Excellence (15 Councils), evidence‑informed policy making (11 Councils), and public–private partnership initiatives (14 Councils), which are now operating above expectations for this phase.

While no new evidence challenges the programme design, delivery trends indicate that SGCI is operating at a more advanced level than anticipated in the SGCI-2 business case. Significant achievements in digitised grants management systems, MEL capacity, gender equality and inclusivity integration, and knowledge production reflect a maturing cohort of Councils. These developments justify the shift proposed for SGCI-3 toward deeper institutionalisation, cross‑country coherence and long‑term sustainability through the new Alliance model.

Key assumptions within the ToC have largely held. Councils continue to value technical assistance, peer learning and digital tools. Policymakers remain receptive to evidence-informed decision making, and external partnerships have broadened Council influence and capability. Some adjustments, however, are required. Variability in staffing and internal processes has had greater influence than expected on contracting and proposal quality. Political or structural changes within individual Councils created uncertainties, although none significantly disrupted implementation. Persistent data gaps, particularly in national STI statistics, continue to constrain the ToC’s ambitions around evidence-led advocacy.

SGCI’s Gender Equality and Inclusivity (GEI) and MEL workstreams demonstrate that Leave No One Behind (LNOB) principles are increasingly embedded in Council systems. Councils now regularly report gender‑disaggregated data, integrate GEI considerations into competitions and, in some cases, apply affirmative measures. Fourteen Councils report increased leadership roles for women and nine exceed the 30 percent benchmark for women-led projects. Further attention is needed on age, disability and geography. Strengthening MEL dashboards and data governance systems under SGCI-3 presents an opportunity to address these gaps.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

SGCI‑2 is largely on track, with most outcome and impact targets met or exceeded. At the impact level, 14 countries reported Gross Domestic Expenditure on Research and Development (GERD) trends—above the target of 12 and 10 countries increased patent activity, signalling gradual strengthening of national innovation systems. At the higher‑outcome level, Councils supported 261 research and innovation projects, far surpassing the target of 150, and generated 57 solutions and knowledge products, including climate‑smart agricultural tools, clean‑energy innovations, and health‑related technologies.

Progress in research and innovation management has been substantial. Seventeen Councils conducted high‑quality research competitions, and 15 integrated research‑excellence standards such as RQ+ and ethical frameworks. Councils are increasingly using evidence for decision‑making, for example, Rwanda introduced new grant schemes for female PIs and academic‑industry collaboration, Policy influence has grown as 12 countries reviewed or updated STI policies, and Malawi, Ethiopia and Ghana, and Côte d’Ivoire embedded MEL findings into its financial and strategic planning.

Knowledge translation and partnership outcomes also exceeded expectations. Councils took up 28 knowledge products, including IP audit manuals, commercialization frameworks, and MEL toolkits. Private‑sector engagement expanded significantly, with 76 projects involving business and industry, such as Côte d’Ivoire’s award‑winning biogas innovation. Cross‑country collaboration remained strong, with 14 active agreements and 14 external initiatives leveraged, including STISA‑2034 and the Belmont Forum, broadening global engagement.

Planned Actions for the Year Ahead

As SGCI-2 concludes, preparations are underway for SGCI-3, launching in 2026. Activity over the coming year will focus on ensuring a smooth transition, including establishing a central Capacity Strengthening Hub, strengthening grants management, MEL and data governance, and providing preparatory support to new and existing agencies. Priorities also include deeper GEI integration, improved policy coherence, enhanced strategic communications, more effective use of diplomatic influence, and strengthened risk and efficiency measures to support a resilient rollout from 2026.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

Continuation of SGCI is justified on both performance and strategic grounds. To date, the programme has supported 17 national science granting councils, strengthened African led S&T investment, and built enduring UK–Africa research partnerships. During the reporting period, Togo and Angola joined SGCI, and South Africa’s NRF will participate as a council in the next phase, bringing total membership to 20. SGCI aligns with the UKs evolving approach to development, notably shifting to supporting systems development rather than delivering services. It also supports FCDO priorities on women and girls and sustainable growth, by strengthening national S&T systems that generate evidence and support innovation. FCDO investment will leverage around £5m in partner government financing and £26m from development partners. In its next phase, SGCI will shift from capacity building to positioning councils as regional and global S&T leaders, exemplified by South Africa’s NRF co-chairing the Global Research Council in 2026. A key innovation is the Councils-led SGCI Alliance, transferring ownership and asserting African leadership over research agendas, reflecting the growing maturity of Africa’s S&T systems.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Improved understanding of research excellence and emerging scientific practices by the SGCs
Output number: 1.1		Output Score:		A+
Impact weighting (%): 10%		Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Number of SGCs trained on research excellence and emerging scientific practices	At least 16 SGCs receive training on research excellence and emerging scientific practices.	Target exceeded by 1. One (1) new Council (in Botswana) received training on research excellence and emerging scientific practice, over the baseline (6) and 16 reported in 2024. This means that all 17 Councils have received training on research excellence and emerging scientific practices

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Performance exceeded targets. SGCI‑2 strengthened SGCs’ understanding of research excellence by supporting the adoption of the Research Quality Plus (RQ+) framework[4], research ethics guidelines and open science practices, enabling Councils to assess and manage research with greater rigor and contextual relevance. These advancements have improved the ability of SGCs to recognize, support and govern high quality; innovative research aligned with national and regional development priorities.
[4] See IDRC, Research Quality Plus: A Holistic Approach to Evaluating Research, 2016. The RQ+ framework is a multi-dimensional tool including multiple indicators and contextual factors that can be adapted by agencies to design, monitor and evaluate their programming in research for development and capacity building
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes have been made to this output since its introduction to the consolidated SGCI theory of change and log frame in 2023. The target for 2025 was increased from 14 to 16 given that 16 SGCs had been trained by October 2024.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

There are no recommendations from the previous AR.

Output Title	Increased adoption of online digital grant management systems by the SGCs
Output number: 1.2		Output Score:		A+
Impact weighting (%): 10%		Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Documented numbers and examples of SGCs supported to adopt online digital grants management systems (GMS)	At least 10 SGCs are supported to adopt digital grants management systems	Target was exceeded by 1. One (1) new Council (Boswana) implemented digital GMS in the current reporting period, in addition to the 10 SGCs reported in 2024 (Ghana, Burkina Faso, Côte d’Ivoire, Kenya, Malawi, Namibia, Senegal, Sierra Leone, Uganda, and Zimbabwe). This brings the total to 11 SGCs.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Targets were exceeded. During the reporting period, Councils in eleven countries were operating digitised grant management systems (DGMS), improving transparency, efficiency, and accessibility. Bostwana implemented digital GMS in the reporting period. Peer‑to‑peer technical support models and standard operating procedures introduced during the year strengthened sustainability. The programme further strengthened adoption by introducing a Helpdesk for real-time user support, enabling ICT specialists from Uganda, Namibia and Sierra Leone to provide peer technical assistance, accelerating uptake and troubleshooting across Councils.
Remaining challenges relate to interoperability with national finance and data systems, which will require longer‑term investment and will be a key focus in SGCI-3.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes have been made to this output, and none is planned based on the current review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Capacity strengthening under SGCI has relied on several approaches such as group training courses (both physical and virtual), on-site coaching, peer-to-peer mentoring and learning, exchange visits, and a Helpdesk system to provide real-time user support, system troubleshooting, and training assistance. The approach selected depends on the subject matter of the training, the number of participants and the preference of target SGCs. While most SGCs prefer physical meetings, the CTAs have combined these with virtual engagements to enhance accessibility and impact.

To ensure targeted and effective participation, most SGCs have designated focal points and experts for key areas such as MEL, gender, STI policies, and communications. Each SGC has appointed a coordinator to support the Head of Research Councils (HORC) in implementing SGCI activities. This structure has ensured that appropriate personnel attend relevant training sessions. The HORCs have participated in selected training events especially those touching on STI policies.

Several measures have been put in place to embed the capacity built through CTAs, including practical templates, manuals, toolkits, and standard operating procedures shared with all SGCs. Many of these resources are also available on the SGCI website for wider access by councils and partners. In the next phase, SGCI will take a more coordinated approach to sharing and using these materials.
.

Output Title	Improved understanding of good financial grant practices (GFGP) by the SGCs
Output number: 1.3		Output Score:		A++
Impact weighting (%): 10%		Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Documented numbers and examples of SGCs that receive technical support about assessment of GFGP	At least 15 SGCs receive technical support about assessment of GFGP	15 / Target met. Note that the target for 2025 was increased from 6 to 15. No additional training on GFGP was provided in 2025. The focus in 2025 has been on supporting 8 councils to complete GFGP self-assessment documentation. As reported in 2024, Ghana, Mozambique, Namibia, Uganda, Zambia, Zimbabwe, Burkina Faso, Cote d’Ivoire, Ethiopia, Kenya, Nigeria, Malawi, Sierra Leone, Senegal, and Tanzania have so far received technical support on GFGP.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output target has been met. The training enabled fifteen Councils to complete GFGP self‑assessments, with several leveraging additional external funding to progress towards full certification. GFGP is increasingly used both as a resource‑mobilisation and credibility tool, helping to reduce fiduciary risk and strengthening donor confidence. Notably, the training has enabled Zimbabwe’s RCZ and Kenya’s NRF to receive additional funding from the African Population and Health Research Center (APHRC) to support full GFGP certification.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The target for 2025 has been increased from 6 to 15 given that a total of 15 SGCs had been trained by October 2024.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

There are no recommendations from the previous AR. The main lesson learnt in the current period is that the SGCs’ interest in GFGP continues to increase. However, the high cost of certification has limited the number of SGCs that can achieve full GFGP certification. Despite this, many SGCs have benefitted from the self-assessments that have helped them to introduce changes to their internal financial and administrative systems. Other SGCs have leveraged funding from partners to support full GFGP certification.

Output Title	Increased support to establish new Councils
Output number: 1.4		Output Score:		A
Impact weighting: 10%		Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Documented numbers and examples of SGCI countries that receive support to strengthen or establish new Councils.	At least 7 countries receive technical support to strengthen or establish new Councils.	2025 results: / Target met. The 7 countries listed in 2024 (Senegal, Côte d’Ivoire, Sierra Leone, Botswana, Ghana, Ethiopia and Nigeria) continued to receive technical support to strengthen or establish Councils.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

SGCI‑2 met milestone for supporting the establishment or strengthening of national Councils. By 2025, new Councils were operational in Ghana, Sierra Leone and Ethiopia. Ghana formally launched the Ghana National Research Fund (GNRF) in early 2025 following sustained SGCI and FCDO engagement. SGCI-2 also contributed to major reforms in Botswana and Nigeria, where policy processes, legal frameworks and institutional arrangements advanced significantly, laying the groundwork for establishing new national research funding bodies. Through technical support from ATPS, ACTS and AAU, countries benefited from policy guidance, legal drafting support, institutional design, and peer learning from more established Councils across the continent.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Under the FCDO extension, SGCI will leverage evidence and tools from SGCI-2 to support Nigeria’s ongoing establishment of a National Research and Innovation Council by strengthening policy dialogue, mobilising research governance expertise, and aligning with complementary efforts such as the FCDOs Sankore initiative to advance a coherent, coordinated national STI system.

Output Title		Increased understanding of the use of data and evidence in policy and decision-making among SGCs.
Output number: 2.1			Output Score:		A+
Impact weighting (%): 10%			Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review			Progress
Documented numbers and examples of SGCs trained on the use data and evidence in policy and decision-making	At least 17 SGCs are trained on the use of data and evidence in policy and decision-making			Target met. / All 17 Councils continued to engage in training that supports their ability to use data and evidence for improved policy and decision-making through the work of multiple CTAs.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

SGCI trained all 17 participating Councils on the use of data and evidence in policy and decision making during the current reporting period through Evi-Pol 2 and strategic communication projects led by University of Johannesburg and ScDev.Net/ CABI, respectively. The training and technical support enhanced Councils’ capacity to integrate data and evidence into decision‑making. For example, FONSTI in Côte d’Ivoire applied its MEL framework to restructure its financial budget and inform strategic planning, while Rwanda’s NCST used its innovation and R&D survey findings to design two new grant schemes in direct response to identified gaps. These examples demonstrate how Councils are applying the training provided by the Initiative.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

During the year, the output on increasing SGCs’ use of data and evidence in policy and decision‑making advanced significantly. Councils strengthened their MEL systems, adopted new data governance toolkits and improved their use of R&D survey findings to inform national priorities. Capacity-building support through the Evi‑Pol 2 project further enhanced Councils’ understanding of STI indicators, data management and evidence uptake, resulting in wider application of monitoring data in policy dialogues and organisational reforms.

Output Title	Strengthened MEL and data management systems and procedures.
Output number: 2.2		Output Score:		A
Impact weighting (%): 10%		Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Documented numbers and examples of SGCs supported to develop/ update robust MEL plans and review their data management systems (DMS) and procedures.	At least 15 SGCs are supported to develop/ update robust MEL plans and review their data management systems and procedures	2025 results: / Target met. Note that the target for 2025 was increased from 13 to 15 in 2024. Work in 2025 by the Evi-Pol 2 project team focused on consolidating support to Councils, notably those in French-speaking West Africa and Tanzania, on MEL, together with NSTC in Zambia, UNCST in Uganda, and DGRI in Senegal on R&D surveys. A total of 15 SGCs have so far been supported (Tanzania, Burkina Faso, Uganda, Senegal, Kenya, Malawi, Botswana, Ethiopia, Sierra Leone, Cote d’Ivoire, Uganda, Namibia, Zambia, Ghana, and Mozambique).

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

SGCI-2 met the target for the output. Under the EviPol-2 project, fifteen Councils reviewed and enhanced their MEL frameworks, improving their ability to track performance, streamline processes and use evidence in decision-making, e.g. FONSTI embedding MEL findings into policy briefs and dissemination activities.

The programme also advanced data governance and measurement capacity, with 13 Councils supported to develop and implement a comprehensive Data Governance Toolkit that strengthened data reliability, accessibility and use. The toolkit, alongside the Digital Transformation Roadmap and the R&D Survey Toolkit (developed with AUDA-NEPAD and partners), has begun to improve national STI data ecosystems. Several countries, including Rwanda, used improved data systems to shape targeted funding schemes, demonstrating how strengthened data capability is beginning to influence policy and programme design.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The target set for 2025 was increased from 13 to 15 SGCs given that a total of 15 SGCs had already been trained by the end of 2024.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Support for establishing data management systems is part of the discussions for SGCI phase 3.

Output Title
Output number:		3.1	Output Score:		A++
Impact weighting (%):		5%	Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Output indicator 3.1.1: / Documented number of peer-reviewed publications	At least 45 peer-reviewed publications	2025 results: / Target exceeded by 32. Note that the target for 2025 was increased from 40 to 45 in 2024. / .
Output indicator 3.1.2: / Documented number of other knowledge outputs	At least 65 knowledge outputs	2025 results / Total exceeded by approximately 61. Final output numbers are: 126 knowledge outputs + 248 media outputs.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The programme recorded significant growth in the production of knowledge outputs, reflecting the Initiative’s strengthened role in supporting research uptake, knowledge translation and visibility across Africa’s STI landscape. During the reporting period, the Initiative generated 77 publications, 126 knowledge outputs and 248 media products all of which were disseminated through SGCI’s expanding digital knowledge ecosystem. These outputs demonstrated SGCI’s ability to create actionable tools that support policy, innovation, and scientific collaboration across participating countries.
In addition, SGCI partners produced numerous publications, impact stories, policy briefs and case studies, which were widely shared through the SGCI website, SciDev.Net platforms and international science news channels. Strategic communication efforts resulted in over 183 million cumulative views across web, social media, broadcast and newsletter channels, significantly amplifying the reach of these knowledge outputs and enhancing the profile of SGCs globally. These efforts brought visibility to emerging research innovations -including award winning‑ work from Côte d’Ivoire, Uganda, Malawi and strengthening the link between funded research and its societal impact.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The target set for 2025 was increased from 40 to at least 45 given the number of peer-reviewed publications was expected to increase sharply in the programme’s final year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

A comprehensive SGCI strategic positioning plan was developed to enhance coherence in SGCI messaging and coordination to reach a more diverse audience. In the next phase, the SGCI website will evolve into a comprehensive virtual hub with expanded social media engagement. Beyond the extensive readership, analysis of the needs of different categories of audience will continue, integrating interactive content to amplify Councils’ voices, enhance collaboration among researchers, expand funding partnerships, and shape and influence policy. By curating results, elevating success stories and making data discoverable, SGCI’s communications function will become both a dissemination channel and a key asset for partnerships building.

Output Title	Increased exchange of experiences, lessons, and best practices among SGCI partners
Output number: 3.2		Output Score:		A+
Impact weighting (%): 5%		Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Documented number of dissemination/ networking events involving SGCs and other STI systems actors	At least 30 dissemination/ networking events are held	2025 results: / Target exceeded by 2: Note that the target for 2025 was increased from 28 to 30 in 2024. The 4 events for the current period are: All Partners Forum in October in Ghana, the 2025 GRC meeting and SGCI Academic Symposium in November in Zimbabwe, 2 sessions at the Evidence for Development Conference in May in Kenya. Other events reported in 2024 were: 1 Annual Forum, 1 reflection and learning workshop, 1 meeting for Councils to engage with the new STISA-2034 and SGCI-GEI hosted a virtual parallel session, Finding Focus: Towards a Funding Agenda for Gender Transformation in African Science at the 2024 Gender Summit.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

The target was exceeded. SGCI-2 significantly expanded opportunities for Councils and partners to exchange experiences, lessons, and best practices across the Initiative. Peer learning was strengthened through hands-on mentoring arrangements, an effort that benefited 11 Councils and served as a practical model of South–South technical support. Councils also shared learning through multistakeholder dialogues, with 18 national- and regional-level engagements convened in nine countries to exchange insights on STI policy development, funding mechanisms, gender integration and commercialization pathways.

Knowledge exchange was further amplified through SGCI’s international engagements, including participation in the Global Research Council meetings, the Canadian Science Policy Conference, peer-learning visits to the German Research Foundation and the University of Johannesburg-led evidence-for-policy sessions. These platforms allowed Councils to learn from global research funders while showcasing African research excellence, innovations and governance practices. The SGCI All-Partners Forum, which brought together 170 participants in 2025, served as a major hub for sharing lessons from SGCI-2 and codesigning the SGCI-3 Alliance and delivery model. Strategic communication efforts, including widespread dissemination of impact stories and knowledge products through SGCI and SciDev.Net channels, further promoted cross-country learning and visibility.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The target set for 2025 was increased from 28 to 30 because 28 dissemination/networking events were already completed by the end of 2024.

Output Title	Increased development of frameworks and structures for commercialisation of research results
Output number: 3.3		Output Score:		A+
Impact weighting (%): 5%		Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Documented numbers and examples of SGCs supported to develop frameworks and structures for commercialization of research results.	At least 10 SCCs supported to develop frameworks and structures for commercialization of research results	2025 results / Target exceeded by 3. A total of 4 new SGCs have developed frameworks for commercialising research results in this reporting period (Burkina Faso, Côte d’Ivoire, Mozambique, and Kenya). The final list of 13 countries is: Botswana, Burkina Faso, Cote d’Ivoire, Ghana, Mozambique, Namibia, Nigeria, Rwanda, Tanzania, Uganda, Zambia, Zimbabwe, and Kenya.
Documented numbers and examples of SGCs trained on intellectual property audits, IP policies and strategies, private sector engagement, commercialization and sharing of resources/ facilities with private sector actors.	At least 15 SGCs are trained on intellectual property audits of projects and sharing of resources/ facilities with private sector actors	2025 results: / Target met. Note that the 2025 target was increased from 14 to 15 in 2024. The same countries listed in 2024 annual report have continued to receive support during the reporting period (Zambia, Mozambique, Senegal, Kenya, Uganda, Tanzania, Ethiopia, Malawi, Namibia, Zimbabwe, Sierra Leone, Burkina Faso, Cote d'Ivoire, Ghana and Botswana).

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

This output is on track and exceeds key indicators. SGCI-2 made steady progress in strengthening the frameworks and institutional structures needed for research commercialization across participating countries. Tanzania’s COSTECH completed a comprehensive intellectual property audit of NFAST funded projects, identifying 37 patents, 7 utility models and 59 trademarks while training more than 220 researchers in core IP and commercialization practices. Several Councils also advanced commercialization planning through new tools and frameworks. Ghana’s MEST developed a Research Commercialization and Technology Transfer Framework, and SGCI produced a Private Sector Engagement Framework along with the TechnoMart Platform, which supports access to research infrastructure and enhances readiness for technology transfer. Councils in Mozambique, Malawi, Namibia and Kenya continued to strengthen technology development and private sector linkages, contributing to more structured pathways for moving research outputs toward market use.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The target set for 2025 was increased from 14 to 15 given that 15 SGCs had already been trained by the end of 2024.

Output Title	Increased funding of research projects involving private/ social sector actors
Output number: 3.4		Output Score:		A++
Impact weighting (%): 5%		Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Documented number of research projects involving private sector actors.	At least 52 projects involving private sector actors	Target exceeded by 24. Note that the target for 2025 was increased from 50 to 52 in 2024. A total of 29 projects were funded under the Sida-IDRC partnership; 22 projects under IDRC- FCDO partnership; and 25 projects under Norad-IDRC partnership.
Documented number of research projects involving social sector actors.	At least 34 research projects involving social sector actors	2025 results: / Target met. Note that the target for 2025 was increased from 8 to 34 in 2024. No new projects involving the social sector were funded in 2025. / Another 9 projects are supported under Norad-IDRC partnership.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Performance significantly exceeded targets. Research projects involving private and social sector actors increased in both number and quality, with strong examples in agri‑processing, health technologies, clean energy and circular economy solutions. Engagement is now structural rather than ad hoc, contributing directly to inclusive growth objectives.

Councils also increased opportunities for researchers to work directly with private sector actors through sector aligned research calls and policy dialogues. New Council led initiatives in Malawi, Mozambique, Côte d’Ivoire and Burkina Faso brought together government, civil society and private sector representatives to shape funding priorities and support research that responds to development challenges. SGCI funded projects across areas such as green technologies, climate-smart agriculture, food processing and public health further demonstrated the Initiative’s role in directing resources to research with clear societal and market relevance. These activities contributed to a measurable expansion of partnerships and funding flows involving private and social sector actors within the SGCI network.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The 2025 target set for the number of projects involving social sector actors has been increased from 8 to 34 given that 34 projects were already reported at the end of 2024. No new projects were funded in 2025.

Output Title	Increased awareness of Gender Equality and Inclusivity dimensions
Output number: 4.1		Output Score:		A
Impact weighting (%): 5%		Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
Documented number of SGCs trained on various GEI dimensions including the processes necessary to create change	At least 15 SGCs are trained on GEI dimensions	2025 results: / Target exceeded by 1. One (1) new SGC (Sierra Leone) included GEI indicators into its R&I framework as reported in the GEI Synthesis Report, 2025. This was in addition to the Councils that received support from the HSRC GEI team (in 2023 and 2024) bringing the total to 16 (Sierra Leone, Tanzania, Namibia, Uganda, Kenya, Mozambique, Zambia, Malawi, Botswana, Burkina Faso, Cote d’Ivoire, Zimbabwe, Ethiopia, Senegal, Ghana, and Rwanda).

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Target was exceeded. SGCI-2 significantly increased awareness and understanding of gender equality and inclusivity across participating Science Granting Councils through targeted capacity strengthening, policy development support and participatory learning processes. Councils engaged extensively with the GEII framework “From Principles to Practice,” cocreated by 13 Councils, which helped recognise practical entry points for integrating gender and intersectionality into grant making, institutional policies and monitoring systems.

Several Councils, including UNCST in Uganda, RCZ in Zimbabwe, NCST in Malawi, MEST in Ghana, FONSTI in Côte d’Ivoire and FNI in Mozambique, implemented tailored GEI activities such as gender-responsive evaluation criteria, affirmative action measures, gender integration workshops and women innovator initiatives. These activities improved institutional awareness of gender barriers and increased understanding of how inclusive practices strengthen research quality and impact.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

The target for 2025 was decreased from 16 to 15 in 2024 since the number of SGCs involved in this workstream was not expected to change in the programme’s final year.

Output Title	Facilitating government to government dialogues on STR&I
Output number: 5		Output Score:		A++
Impact weighting (%): 15%		Weighting revised since last AR?		[If Yes, up or down?]

Indicator(s)	Milestone(s) for this review	Progress
No. of events organised, trainings provided, or technical assistance offered with local partners.	At least 5 SGCs are supported to conduct policy dialogues and 3 FCDO Mission science diplomacy events are funded.	ACTS (a consortium member of the Evi-Pol 2 project) was contracted in March 2024 to lead this work in close collaboration with the University of Johannesburg. This team was selected to ensure synergy with the Evi-Pol 2 project that has been supporting other dialogues related to STI policies. Four FCDO projects have been funded. / 12 FCDO Mission projects have been funded, exceeding the target of 3.

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

SGCI-2 strengthened government to government dialogue across Africa’s STI landscape by supporting Councils to convene and participate in national and regional multistakeholder engagements that brought together ministries, statutory agencies, and policy-level decisionmakers. Through FCDO supported platforms, 18 dialogues in nine countries enabled peer exchange on national STI policies, research funding mechanisms, commercialization, evidence-informed policymaking and gender responsive STI governance. These engagements helped governments review or validate national STI policies, as seen in Malawi and Mozambique, and informed high-level coordination efforts such as Ghana’s development of a National Research Fund.

The Initiative also facilitated cross-country learning among senior government actors through international forums, including the SGCI All Partners Forum, the Global Research Council meetings, the Evidence for Development Conference and peer learning missions to Germany and South Africa. These interactions strengthened relationships between governments, improved awareness of continental STI priorities and SGCI contribution to STISA-2034, and elevated SGCs as credible intermediaries linking national policymakers across countries.

The Convening Fund which complements SGCI strengthened the programme responsiveness by enabling timely engagement on 12 initiatives leading to emerging partnerships and technical collaboration on thematic areas such on AI, Space governance, Higher Education.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No change is planned.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

SGCI has consistently enabled councils to collaborate with other government agencies such as finance and planning ministries, statistical offices, innovation agencies, universities and the private sector, to strengthen national STI systems. Examples include Uganda working with their Bureau of Statistics to integrate STI into economic planning, Namibia and Tanzania linking research to innovation and industry, and Botswana promoting research commercialisation through private sector partnerships. In the next phase, these links will be deepened through the new Policy Hub which will bring together national, regional and continental stakeholders together with development partners and diplomatic missions to continue to advocate for robust and well-funded science systems across Africa.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance
Training, capacity building and grant management remained the primary cost drivers during this period, reflecting continued support to strengthen Council systems and improve delivery. Additional expenditure was linked to strategic engagement and GEI activities, including policy consultations and efforts to integrate gender, youth and disability considerations into programmes.

VfM performance compared to the original VfM proposition in the business case

SGCI-2 Programme Narrative

Economy
BC Commitment:
Use existing delivery channels, limit unnecessary travel, and promote open competitions for efficiency.

Reported Performance:
The programme delivered strong economies by combining in‑person and virtual training, reducing travel and accommodation costs for Councils and CTAs. Joint training sessions and consolidated meetings further lowered transaction costs and freed resources for priority activities. Open calls for proposals enabled benchmarking against market rates and ensured value for money in the recruitment of CTAs. Additional savings were achieved through rigorous scrutiny of budgets and financial reports by IDRC’s grant administration and programme teams, which strengthened cost discipline across the portfolio.

Efficiency
BC Commitment:
Efficiency was to be achieved by maintaining clear objectives for engaging targeted SGCs and using experienced technical agencies or consultants to deliver timely and impactful results. Monitoring and financial controls were to ensure optimal resource utilization.

Reported Performance:
Efficiency was strengthened through structured grants management procedures. Disbursements were linked to milestone completion, ensuring funds were released only when progress was demonstrated. Regular technical and financial reporting from CTAs and Councils enabled close oversight by Programme Officers and Grants Officers, who reviewed outputs and participated in monitoring activities both virtually and in person. This approach safeguarded resource use and supported timely delivery.

Effectiveness

BC Commitment:
Effectiveness was to be achieved by building strategic partnerships established in SGCI Phase 1, enhancing synergies at national, regional, and global levels. It also sought to position Councils as key drivers of policy influence and strengthen their roles in research commissioning and management.

Reported Performance:

SGCI‑2 expanded its strategic partnerships, recording 14 collaborative agreements and 14 leveraged initiatives, surpassing targets. Councils adopted new policies and practices with CTAs’ support and strengthened engagement in regional and global STI spaces, including the Global Research Council and STISA‑2034 processes. These efforts enhanced visibility, collaboration and influence beyond national boundaries.

Equity

BC Commitment:
Gender, youth, and disability considerations were to be mainstreamed across the programme, with disaggregated data collection and consultation with vulnerable groups to ensure inclusivity.

Reported Performance:
A context‑sensitive approach enabled tailored GEI support across Councils. Sustained in‑person engagement and capacity building strengthened gender mainstreaming in grant management. Progress on MEL systems and data governance improved Councils’ ability to report on LNOB dimensions, although further work is required to strengthen disability and geographic disaggregation.

Convening Fund VFM Narrative

1. Economy
The Convening Fund has demonstrated strong economy by leveraging UK Government, African partners, and local institutions platforms rather than establishing parallel structures. By aligning activities with ongoing HMG initiatives and national priorities. The fund has minimized duplication while enabling coordinated engagement across multiple actors. Partnerships build around UK Tech Hub ecosystem enabled catalytic engagements such as the 2026 Tech Run delivered through pooled resources hence reducing duplication and maximising impact.

2. Efficiency
The Fund has improved delivery efficiently by enabling targeted collaboration that would otherwise require longer funding cycles. The UK-Ghana Science Journalism initiative strengthened national STI reporting capability through focused engagement while AI strategy support aligned with existing UK-Ghana partnerships and private sector actors, reducing programme startup costs and accelerating implementation timelines.

3. Effectiveness
The Convening Fund enhanced the programme effectiveness by unlocking partnerships beyond SGCI’s core intervention packages. The Trilateral Research, Innovation, and Entrepreneurship Partnership has strengthened institutional collaboration across the UK, India and East Africa supporting youth innovation pipelines, commercialisation pathways and cross regional knowledge exchange. Those outcomes would not have been achievable within core programme architecture alone.

4. Equity
The fund has broadened participation by enabling underserved stakeholders to engage in collaboration opportunities. The UK-Botswana-Kenya renewable energy initiative has supported government institutions and regulators to strengthen in inclusive energy planning through peer learning and institutional exchange.

The convening fund has functioned as a strategic accelerator for partnership led delivery across the UK-Africa science and technology ecosystem.

Assessment of whether the programme continues to represent value for money
The programme continues to represent strong value for money by delivering system level impact while leveraging complementary mechanisms to enhance responsiveness through established SGCI structures and regional S&T partnerships.
E: RISK [½ to 1 page]

SGCI’s overall risk appetite remains CAUTIOUS (Moderate), reflecting the complexity of operating across diverse and often challenging political and institutional environments. IDRC continues to apply proportionate mitigation measures throughout programme delivery supported by FCDO’s oversight and risk management mechanisms.

IDRC’s Risk Management Approach

IDRC manages risks through structured partnerships and delivery relationships. Programme risks are monitored through regular updates to the risk register by the Initiative Management Team (IMT), alongside continuous oversight from CTAs and participating Councils. Familiarity with IDRC systems has improved across partners, strengthening compliance with financial, reporting and safeguarding requirements. Institutional risk assessments, transaction sampling and compliance reviews are applied to ensure consistent standards. FCDO funds are channelled through CTAs rather than directly to Councils, reducing the risk of diversion or fraud.

Risk Trends and Lessons from the Year
Safeguarding and SEAH. Safeguarding mitigation measures have improved following targeted interventions. The joint SEAH training delivered by SGCI and FCDO in March 2025 equipped CTAs with stronger safeguarding procedures. Agencies such as ACTS have since adopted revised Ethical Standards frameworks and a Whistleblower Policy, improving organisational readiness. Safeguarding risk has therefore reduced, although continued support will be required under SGCI-3 to ensure that SEAH policies are fully implemented and systematically monitored across all Councils and CTAs.
Strategy and Context Risk. Structural and political developments within some Councils did not disrupt programme delivery. IDRC’s political economy analyses and ongoing engagement with Councils helped anticipate challenges and maintain stable implementation conditions. Residual context risk remains cautious but manageable.
Financial and Fiduciary risk. Financial risk fluctuated during the year, largely due to exchange rate movements affecting forecasts. IDRC and FCDO mitigated this through closer communication and timely adjustments to funding flows. No financial misconduct was recorded. A key lesson has been the importance of strengthened financial forecasting and early warning of delivery pressures.
 FCDO’s Risk Management
FCDO complements IDRC’s efforts through a multilayered risk oversight system, including:
- Strategic oversight by the SRO and PRO
- Regular governance meetings to monitor risk and financial performance
- Quarterly review meetings with IDRC, where risk is a standing agenda item
- Engagement with partners through annual forums
- Co-delivery oversight of the convening fund
- Targeted spot checks on convening fund activities.

Due Diligence and Assurance
Due diligence assessments continue to inform the programme’s overall risk posture. Councils and CTA compliance with IDRC’s systems has improved across the year. Including financial reporting, and procurement practices aligned with GFGP standards. The IDRC’s broader due diligence refresh across FCDO is underway, with oversight from the SGCI SRO and PRO.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Delivery across SGCI and the Convening Fund remained consistent throughout the reporting period. The Convening Fund, a flexible and demand‑driven instrument designed to support UK Missions across Africa, strengthens SGCI’s operational agility by enabling timely engagement on partnership and technical collaboration opportunities that cannot be addressed through longer‑cycle programme mechanisms. The 2025 call for proposals was promoted regionally through the Kenya, Ghana and South Africa Research and Innovation Hubs and generated 15 applications, with 12 projects selected on the basis of strategic relevance, value for money and alignment with country priorities.

The Fund continues to play an important role in advancing UK research, science, technology and innovation objectives by enabling Posts to build partnerships, support localisation agendas, and help strengthen national and regional STI systems. The funded portfolio spans a wide range of themes, including artificial intelligence, space, media, governance, higher education, entrepreneurship and broader STI priorities across Africa. Delivery has been supported through a combination of MoUs, accountable grants, contracts and GPC mechanisms, ensuring flexibility while maintaining compliance with FCDO commercial and assurance requirements.
Programme management, governance and financial stewardship remained strong. The programme has achieved full CDEL expenditure each financial year, supported by accurate forecasting, regular re‑profiling where required, and clear communication of variances, including interest gains and underspends. Quarterly review meetings with IDRC ensured continuous oversight of risks, delivery chain changes and operational developments. Asset monitoring and downstream risk assurance continued to improve through strengthened systems at IDRC and targeted safeguarding and SEAH training for implementing partners.
Narrative reporting from IDRC met required standards, with improved analytical quality and clearer links between outputs, financial performance and risk. Recommendation: There is scope to strengthen cross‑cutting analysis, including gender equality and inclusivity, LNOB, safeguarding and data transparency, particularly as SGCI moves towards a more integrated Alliance model under Phase 3. Looking forward, the report could more deliberately foreground sustainability pathways. SGCI-2 has achieved important gains in institutionalisation, but the long-term viability of these gains especially beyond SGCI-3 requires clearer articulation. A short section outlining the intended trajectory toward regional anchoring, diversified funding, and strengthened national commitments would demonstrate strategic foresight and reassure funders that SGCI remains committed to reducing reliance on external support over time.
FCDO management contributed effectively through joint oversight of the Convening Fund projects, close engagement with Posts, and timely approval of the SGCI programme addendum. The one‑year programme extension to December 2026, positions SGCI to consolidate gains from Phase 2, support South–South collaboration opportunities, enhance engagement with continental bodies and contribute to the implementation of STISA‑2034. This extension also provides a strategic bridge to SGCI‑3.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

Throughout the review period, a range of MEL activities were carried out to assure delivery quality, value for money, and adaptive management:
Beneficiary insights were collected through engagement with councils, implementing partners and grantee organisations at the all-partner forum, informing ongoing programme design and adjustments

The evidence for the annual review was drawn from
- IDRC annual report, partner feedback, and field-level verification.
- Inputs were sought from outside the core programme team, including with colleagues implementing various convening fund projects and narrative reports.

Learning

Learning processes over the past year have been, driven by the All Partners Forum, MEL and Learning & Reflection workshops, CTA synthesis reports, and ongoing funder engagement. These generated clear lessons: the need for more simplified and coherent governance arrangements, stronger R&D and STI data systems, deeper operationalisation of GEI and SEAH commitments, and improved alignment of research funding with national priorities. These findings also reinforce wider lessons for FCDO on supporting locally led systems strengthening, designing equitable partnerships, and sustaining multi-donor coordination platforms.
Date of last narrative financial report	23 September 2025	Date of last audited annual statement	5 November 2025