Evaluation Report for Programme Name: Evaluation Quality Assurance and / Learning Service 2 (EQUALS2)

Response to Evaluation Quality Assurance and Learning Service 2 (EQUALS2) Evaluation Report

Overall summary: / This report presents the findings of the independent evaluation of the Evaluation Quality Assurance and Learning Service (EQUALS2), commissioned by the UK Foreign, Commonwealth and Development Office (FCDO). / EQUALS2 is a five year, £4.7 million service (2022–2027), delivered by IOD PARC together with consortium partners, providing expert technical assistance (ETA), independent quality assurance (QA) of evaluation products, and Evaluation Insights (EI) to strengthen the quality, credibility and use of evaluation across the FCDO. The service operates as an external mechanism complementing internal evaluation capacity within a decentralised evaluation system. / Objectives and methodology / The evaluation served accountability and learning purposes. It assessed whether EQUALS2 delivered its intended services and represented value for money, and explored how and under what conditions different service components have been effective, to inform both final year delivery adjustments and future service design. A mixed method, theory-based approach was used, drawing on document review, interviews, a survey with evaluation suppliers, case studies and management information, and applying a behavioural lens grounded in the COM‑B model to assess contribution. / Key findings / The evaluation finds that EQUALS2 has made a meaningful but uneven contribution to evaluation quality, with impact varying by service component and level of institutional embedding. / QA emerges as the strongest and most consistently effective element. Evidence indicates that QA has improved the clarity, evaluability, coherence and usability of evaluation products, particularly when applied early, and has strengthened commissioners’ ability to uphold quality standards through credible, independent challenge. Some challenges remain around proportionality and timing. / ETA is widely valued and fills important capability and opportunity gaps, particularly at early design stages and in resource constrained contexts. Its influence, however, is highly context dependent and strongest where support is embedded in decision-making processes, closely aligned to specific needs, and reinforced through continuity of engagement. / The Evaluation Insights component has achieved weaker results relative to ambition. While some products have informed organisational discussions where aligned with strategic priorities, overall awareness, uptake and applied use remain limited, and pathways from insight generation to learning are insufficiently supported. However, it is important to note that many EIs were not explicitly designed to inform routine decision-making across a broad user base. / Overall, EQUALS2 is most effective where its services are structurally embedded in accountability and decision-making systems, and least effective where uptake is voluntary or reliant on diffusion. QA demonstrates strong value for money, while ETA delivers high additionality but at higher cost. Evidence on the value for money of Evaluation Insights is currently limited. Differences in impact across QA, ETA and EI reflect how strongly each service is embedded in and able to influence FCDO systems, rather than differences in delivery quality. / Future effectiveness will depend less on expanding delivery and more on strengthening the conditions that link support to decision making, accountability and learning.

Evaluation Report Title: Evaluation of the Evaluation Quality Assurance and Learning Service 2 (EQUALS2)

Recommendations: FCDO	Accepted or Rejected	If “Accepted”, Action plan for Implementation or if “Rejected”, Reason for Rejection

General recommendations: / EvU should have a strategic discussion on the future priorities of EQUALS2 / EQUALS2 should place greater emphasis on building FCDO’s capability to undertake evaluative thinking and lighter-touch evaluative work, particularly in areas affected by ODA budget reductions / EQUALS2 should make more structured use of service-wide learning during the remainder of the contract, and FCDO should decide whether this should become a core feature of any future model. / EvU/FCDO should clarify how ‘quality’ is defined and assessed in the current and future evaluation system, particularly as evaluative activity diversifies	Accepted	The evaluation report provides a strong basis for strategic discussions to guide priorities for the final year of the programme implementation, and design of the new Business Case. A series of discussions are planned with the Governance Panel, key internal stakeholders, and IOD-PARC. / A key priority for the final year is building on work to date to plan the EQUALS2 contribution to a wider capability building offer for non-specialists and MEL Advisers. This goes beyond areas impacted by ODA budget reductions to supporting the implementation of the Evaluation Strategy across FCDO priorities. This will include ways to make more use of learning and data from the programme. / As part of the refresh of the FCDO Evaluation Policy, FCDO Evaluation Unit is leading work to refresh quality standards and approaches to a diversity of evaluative activity.
Evaluation Technical Advice related recommendations: / 2.1 EvU and IOD PARC should consider reviewing how ETA is expected to operate with regards to PMEL – and how it can and should support PMEL - whether conducted in-house or via contracted suppliers / 2.2 EvU should consider greater focus on improving how non-ODA and non-traditional users understand and access the existing ETA offer / 2.3 EQUALS 2 should strengthen guidance at the point of requests so that FCDO staff can make better informed ETA requests, particularly on likely Level of Effort (LoE) and the type of support required	Accepted	Work is underway by Evaluation Unit and EQUALS2 Management to review the quality assurance (QA) approach to PMEL Terms of Reference, Inception Report and PMEL products, including criteria, templates and process. / Whilst ETA support is flexible and available to teams undertaking PMEL activities, Evaluation Unit and EQUALS2 Management will articulate the range of technical assistance that is available to support PMEL. / A refresh of the communication materials for EQUALS2 will be undertaken to support access to ETA, particularly amongst non-traditional users. This will draw from service data to clearly detail the range of ETA support and include short case studies, expected LoE, and key learning points for FCDO staff to ensure the support is well targeted.
Quality Assurance related recommendations: / 3.1 EvU and IOD PARC should consider developing a more proportionate framework that maintains consistency while better matching the types, scale and risk profile of the evaluative product. / 3.2 EvU and IOD PARC should improve guidance on when to initiate QA and how to build enough time into the process for feedback to be used meaningfully	Partially accepted	As part of the Evaluation Policy refresh, Evaluation Unit is examining quality standards and approaches, recognising there is an increasing diversity of evaluative activity and QA approaches must be both robust and proportionate. / This will include clear guidance for when an adapted EQUALS2 template could be used. This must balance potential increased complexity for EQUALS2 reviewers in using a less detailed template, and risks to the QA process. / As part of the refresh of communications materials for EQUALS2 guidance will be included on practical considerations for ensuring that the QA process is timely and most useful.
Evaluation Insights related recommendations: / 4.1 EvU should review the commissioning model for Evaluation Insights so that topics, intended users and outputs are defined more clearly at the outset and aligned more explicitly to demand and ultimate utility / 4.2 EvU and EQUALS 2 should take into consideration diversifying EI outputs beyond standalone reports and place more emphasis on practical dissemination and use.	Partially accepted	A key purpose of Evaluation Insights at the design stage was to support Evaluation Unit in the delivery of its mandate within the organisation, and not all were designed to have wide awareness and uptake. / We will reconsider the future of Evaluation Insights within the context of the new FCDO Evaluation Strategy and wider priorities for the programme for its final year.