Evaluation of the Evaluation Quality Assurance and Learning Service (EQUALS2) Final Report
Prepared by Chemonics UK for the UK Foreign, Commonwealth and Development Office
April 2026

# Table of contents

# List of figures
Figure 1: Overview of the total number of requests over the period of analysis per quarter	13
Figure 2: EQUALS2 ToC	16
Figure 3: ETA pathway COM-B model	19
Figure 4: QA pathway COM-B model	21
Figure 5: Revised EQUALS ToC	23
Figure 6: Evaluation approach	26
Figure 7: Updated ToC with strength of evaluative evidence integrated	75
# List of tables
Table 1: Overview of number and type of requests categorised by department in the time period	12
Table 2: Evaluation questions	24
Table 3: List of final sampled evaluations	27
Table 4: List of stakeholders interviewed	28
Table 5: Unit cost and total expenditure on EQUALS2 products (up to January 2026)	68
Table 6: Strength of evidence criteria for Theory of Change causal pathways.	72

# List of acronyms
AI	Artificial Intelligence
ATIP	Africa Technology and Innovation Partnerships
BHC	British High Commission
BR	Baseline Report
COM-B model	Capability, Opportunity, Motivation, Behaviour model
CV	Curriculum vitae
DESNZ	Department for Energy Security and Net Zero
DV	Developed Vetting
EQUALS 2	Evaluation Quality Assurance and Learning Service 2
EI	Evaluation Insights
EPM	Expert Panel Members
EQM	Evaluation Questions Matrix
ER	Evaluation Report
ETA	Expert Technical Advice
EvU	Evaluation Unit
FCDO	Foreign Commonwealth and Development Office
FMEL	Fund-wide Monitoring, Evaluation and Learning
GEDSI	Gender Equality, Disability and Social Inclusion
GEMFA	Global Evaluation and Monitoring Framework Agreement
HMG	His Majesty’s Government
IR	Inception Report
ITT	Invitation to Tender
IOD PARC	A name not an acronym: IOD PARC is a stakeholder and provider of the EQUALS 2 service
KEVAL	Thematic Evaluation of UK Support to Kenya’s 2022 Elections
LOE	Level of Effort
MEL	Monitoring, Evaluation and Learning
MI	Management Information
ODA	Official Development Assistance
OECD DAC	The Organisation for Economic Co-operation and Development's Development Assistance Committee
OGDs	Other Government Departments
PMEL	Portfolio Monitoring, Evaluation and Learning
QA	Quality Assurance
REMIT	Revenue Mobilisation, Investment and Trade Programme
REINVENT	Reducing Insecurity and Violent Extremism in Northern and Coastal regions of Kenya Programme
RSH	Resource and Support Hub
SC	Security Clearance
SOR	Statement of Requirements
SRO	Senior Responsible Officer
TA	Technical Assistance
TEFOS	Territorios Forestales Sostenibles Programme
ToC	Theory of Change
ToR	Terms of Reference
UNDP	United Nations Development Programme
VfM	Value for Money

# Executive Summary
This report presents the findings of the independent evaluation of the Evaluation Quality Assurance and Learning Service (EQUALS2), commissioned by the UK Foreign, Commonwealth and Development Office (FCDO). EQUALS2 is a five-year, £4.7 million service designed to strengthen the quality, credibility and use of evaluation and evaluative activity across the FCDO and, to a limited extent, other ODA-spending government departments. Delivered through IOD PARC as contracted supplier, and operating through a helpdesk that quickly deploys experts, the service provides expert technical assistance, independent quality assurance of evaluation products, and evaluation insights intended to strengthen the quality, credibility and use of evaluations across the FCDO. EQUALS2 operates as an external support mechanism that complements internal evaluation capacity within the FCDO. The service launched in April 2022 and is due to end date in March 2027.
The purpose of the evaluation was to serve both accountability and learning objectives of the FCDO. From an accountability perspective, it assessed if EQUALS2 delivered its intended services and contributed to improved evaluation quality in a way that represents value for money. From a learning perspective, it explored how and under what conditions the different EQUALS2 service components have been effective, where they have been less effective, and how the delivery model could evolve to remain relevant in a changing context. Findings are intended to inform both near-term adjustments in the final year of delivery, and longer-term decisions regarding the design of any future quality assurance and learning service.
The evaluation adopted a mixed-methods, theory-based design structured around a Theory of Change (ToC) that integrated behavioural analysis, to examine how EQUALS2 influenced practice (or not) within a decentralised evaluation system. The analytical approach placed emphasis on contribution and used a behavioural lens grounded in the Capability, Opportunity, Motivation, Behaviour (COM-B) Model to interpret patterns of uptake and use. Evidence was drawn from:
- A structured document review of a sample of evaluations assessed by EQUALS2;
- Semi-structured interviews with the FCDO Evaluation Unit (EvU), IOD PARC, EQUALS users and members of the EQUALS2 expert panel;
- An online survey of external evaluation providers;
- Selected case studies tracing quality across the evaluation lifecycle;
- Management information and financial data.
Evidence was triangulated across sources to support reasoned judgement, and the analysis reflects transparently on constraints related to document availability, sample size, and reliance on self-reported perceptions.
Key Findings
The evaluation finds that EQUALS2 has made a meaningful but uneven contribution to strengthening evaluation quality across the FCDO: its influence varies by service component and delivery mechanism, rather than being uniformly spread across the different components
The contribution of expert technical assistance (ETA) is conditional. ETA is widely valued, perceived as relevant, and clearly fills important capability and opportunity gaps, particularly in contexts where time, resources or specialist expertise are constrained. It supports evaluative thinking and enables a wide range of evaluative activities, especially at early design stages. ETA’s influence is highly context‑dependent and strongest where it is embedded in ongoing processes, aligned with specific decisions, and supported by continuity of panel expertise.
The evaluation finds that behaviour change is less likely where key preconditions are not met: where users lack resources or time to engage with ETA, where advice is not sufficiently tailored or reinforced to build understanding in how to apply it, and where there is limited ownership to act on guidance. In these conditions, ETA is more likely to remain a stand-alone advisory input and the causal chain from outputs to sustained behaviour change weakens. However, this is reflective of the episodic nature of ETA delivery, as well as methodological constraints during the evaluation, rather than ineffectiveness of ETA per se. The evaluation shows that ETA operates most effectively as a catalytic and situational intervention rather than as a mechanism for driving durable change at scale.
The quality assurance service is the strongest and most consistently effective element of the programme. There is robust evidence from multiple sources that Quality Assurance (QA) has contributed to improvements in the clarity, evaluability, coherence and usability of evaluation products, particularly when applied early in the evaluation lifecycle. Beyond technical refinement, QA plays an important institutional role by providing evaluation commissioners with credible, independent authority to challenge suppliers and enforce quality standards within a decentralised system. QA has strengthened credibility and publishability of FCDO-commissioned evaluations and is therefore a core pillar of EQUALS2’s overall contribution and value. However, evidence also points to challenges related to proportionality and timing, including cases where QA is perceived as arriving too late in the evaluation framing stage to support meaningful revisions, and where a single approach is applied across products of varying scale and complexity.
The evaluation finds that the Evaluation Insights component has achieved weaker results relative to its stated ambitions. While some insights have informed organisational discussion and discrete initiatives where they aligned closely with strategic priorities, overall awareness, uptake and use remain limited, and the pathway from insight generation to applied learning is insufficiently supported. However, it is important to note that many EIs were not explicitly designed to inform routine decision-making across a broad user base.
Conclusion
The evaluation concludes that EQUALS2 is most effective where its services are structurally embedded in decision‑making and accountability systems, and least effective where they rely on voluntary uptake or indirect diffusion of knowledge. Differences in impact across QA, ETA and EI reflect how strongly each service is embedded in and able to influence these systems, rather than differences in delivery quality. From a value for money perspective, the available evidence suggests that QA offers relatively strong value due to its consistent delivery profile, moderate unit costs and demonstrable quality gains, while ETA is more resource‑intensive but delivers a high level of additionality due to capacity constraints within the FCDO. Evidence on the value for money of EQUALS2 is more limited. While management costs are proportionate, opportunities to use management information and panel expertise more strategically for learning and service development are underexploited. Evidence on the VfM of evaluation insights is currently weaker and less clearly evidenced.
The findings and conclusions of the evaluation should be interpreted in light of several limitations. Evidence on quality improvement at portfolio level is constrained by limited access to evaluation products, resulting in a smaller document review sample than originally envisaged. This limits the generalisability of findings drawn from documentary analysis and case studies. The evaluation also relies heavily on self‑reported perceptions from interviews and surveys, which may be subject to recall bias or social desirability bias, particularly in relation to perceived usefulness and behavioural influence. While triangulation across data sources mitigates this risk, the evaluation does not attempt to measure impact or sustained behaviour change systematically, nor does it assess the substantive quality or outcomes of the programmes being evaluated through EQUALS2. The system‑level nature of EQUALS2 means that observed changes cannot be attributed to the service alone, and the evaluation therefore advances contribution‑based judgements rather than causal attribution.
Recommendations
The evaluation proposes a set of priority recommendations aimed at strengthening the remainder of the current contract period and informing future service design. These focus on:
- Clarifying strategic priorities for EQUALS2;
- Placing greater emphasis on capability‑building for evaluative thinking in a context of reduced evaluation budgets;
- Improving the proportionality and adaptability of the QA framework;
- Strengthening guidance and scoping at the point of ETA requests; and
- Revisiting the commissioning model, purpose and outputs of Evaluation Insights.
Taken together, the evaluation finds EQUALS2 to be a credible and valued service that has strengthened evaluation quality within the FCDO, but whose future effectiveness will depend less on expanding technical delivery and more on strengthening the conditions that link support to decision‑making, accountability and learning.
Introduction
This document is the Evaluation Report for the evaluation of the Evaluation Quality Assurance and Learning (EQUALS2) service. Chemonics UK was appointed as the evaluation partner in January 2026 following a competitive procurement exercise under the Evidence Fund. The evaluation was commissioned by the Foreign, Commonwealth and Development Office (FCDO) to assess the performance, contribution and added value of EQUALS2 in strengthening evaluation quality, evaluative practice and the use of evaluative evidence across the FCDO.
This final report synthesises evidence generated over the course of the evaluation to respond to the agreed evaluation questions and meet the FCDO’s learning and accountability objectives. The evaluation has examined how, for whom and under what conditions EQUALS2 has contributed to improved evaluation commissioning, delivery and quality assurance, as well as to broader evaluative thinking. It also considers the extent to which observed changes are likely to be sustained and what implications these findings have for the future evolution of the service.
The evaluation has been guided by a theory-based and behavioural approach, drawing on a refined Theory of Change (ToC) for EQUALS2 developed during the inception period and further tested through the evaluation evidence. This approach recognised that improvements in evaluation quality and use are shaped not only by technical inputs and services but also by changed capabilities, opportunities and motivations among different actor groups.
The evaluation has drawn on multiple sources of evidence, including document review, interviews with key stakeholders across the FCDO and delivery partners, a survey of evaluation providers, case studies, and available management, monitoring and financial data. Evidence has been triangulated to strengthen the robustness of findings and to support reasoned judgements about contribution. The evaluation also reflects transparently on methodological and evidentiary limitations, and on what these imply for the strength and interpretation of conclusions.
The report is structured to guide readers from context and programme design through findings, synthesis and conclusions, and to a set of recommendations for both the remainder of the current contract period and any future successor service. Overall, the report is intended to support evidence-informed decision making within the FCDO, contribute to organisational learning on how evaluation quality and evaluative practice can be strengthened in constrained and evolving contexts, and inform future investments in evaluation quality assurance and learning across government.
Context, purpose, scope and objectives
EQUALS2 OVERVIEW
EQUALS2 is a five-year, £4.7 million programme funded by the UK Foreign, Commonwealth and Development Office (FCDO). It provides independent technical support and quality assurance to strengthen the quality, credibility and use of evaluations.
While originally designed to focus on evaluative activity related to the FCDO’s Official Development Assistance (ODA) spending, over time demand grew from other ODA-spending government departments and from broader spectrum of FCDO activities, including in non-ODA eligible countries. The programme launched in April 2022 and is due to end in March 2027.
EQUALS2 provides a portfolio of services designed to strengthen the quality, relevance and use of evaluations and evaluative activity across the FCDO and other ODA spending government departments. It was originally designed to work in close partnership with the FCDO, particularly the Evaluation Unit, to support delivery of the FCDO Evaluation Policy and Strategy through a flexible, demand-led approach. EQUALS2 was designed as a responsive service to adapt to departmental needs by providing timely quality assurance, expert technical advice, learning and data management support across the evaluation cycle. Its design emphasised alignment with existing FCDO systems, evolving priorities and user needs, recognising that improvements in evaluative activity depended on EQUALS working alongside wider governance and capacity within FCDO.

‘Evaluative activity’ encompasses a wide range of advisory and analytical activities that apply evaluative thinking to support decision‑making, learning, and accountability, without necessarily meeting the formal standards of a full evaluation. This can include identifying evaluation priorities during business case development; conducting evaluability assessments; interrogating or designing theories of change to identify evidence gaps and design risks; and supporting the selection and design of appropriate evaluation questions and approaches (among others).

EQUALS2 achieves this through the provision of short-term Expert Technical Advice (ETA), independent Quality Assurance (QA) of evaluation products and the generation of Evaluation Insights (EI) to inform learning and methodological development:
- Expert Technical Advice is provided to those planning, managing and supporting evaluations and includes (but is not limited to) activities such as assisting with the development of Theories of Change and undertaking evaluability assessments to determine if a programme can be evaluated in a reliable and credible manner, and to ensure that any evaluation will be useful, feasible and cost effective.
- Quality Assurance is provided on a range of evaluation products throughout the evaluation lifecycle including terms of reference, baseline, inception and evaluation reports (and as such, any one programme may draw on EQUALS2 QA at several stages in its lifetime, in line with independent QA requirements of the FCDO’s Evaluation Policy[1]).
  [1] https://www.gov.uk/government/publications/fcdo-evaluation-policy-2025
- Evaluation Insights provide guidance and practical learning on evaluation, designed to drive the uptake and use of evaluation across the FCDO and others implementing programmes.
The service is managed by the FCDO Evaluation Unit and delivered through a contracted supplier, IOD PARC, which is responsible for overall coordination and delivery. IOD PARC maintains and manages databases of evaluation experts who can be drawn on to provide ETA, QA and EI support when requests are received from the FCDO and other government departments. IOD PARC leads a consortium of six partner organisations, structured to provide breadth of expertise to deliver on the varied needs of service users. Delivery operates through a three-tier model comprising a core management and coordination function responsible for oversight, systems and consistency; a panel of senior and principal experts providing quality assurance and expert technical advice; a wider pool of specialist consultant brought in flexibly to meet specific methodological or sectoral needs. Requests for EQUALS2 support are logged by users either via an online helpdesk function or through a dedicated email address, both managed by IOD PARC.
Once a request is formally approved, an appropriately qualified reviewer or consultant is assigned within 48 hours for QA requests, or selected for ETA/EI based on a review of requirements. Expert selection is led by the IOD PARC Helpdesk Manager, in close engagement with the commissioner. The selection is based on fit with thematic, methodological, geographical needs, and management of conflicts of interest. For ETA and EI services, the Helpdesk provides commissioners with a shortlist of expert CVs, from which the commissioner makes the final selection.
CONTEXT
The primary recipients and beneficiaries of services delivered through the EQUALS2 service are the FCDO and other UK government departments that conduct, manage, and/or commission evaluations. Analysis of service requests indicates that EQUALS2 is overwhelmingly supporting ODA-related activity. Of the 449 total requests received during the period of analysis (Q4 2021-2022 until Q4 2025-2026), 405 (91%) were explicitly ODA-related, with a further 30 requests (7%) non-ODA related and 9 requests (2%) classified as blended ODA/non-ODA. This distribution highlights that demand for EQUALS2 services is strongly driven by the needs of ODA-funded programmes and the associated requirements for robust evaluation, quality assurance, and learning.
EQUALS2 supports a broad ecosystem of stakeholders involved in the design, delivery, and oversight of evaluations. Key user groups include:
- Monitoring, Evaluation and Learning (MEL) advisers and evaluation specialists within the FCDO.
- Programme managers responsible for commissioning and managing evaluations.
- Senior FCDO decision-makers.
- Other government departments (OGDs) with ODA responsibilities.
- External evaluation suppliers and contractors.
- Independent consultants supporting FCDO programmes.
These groups engage with EQUALS2 at different stages of the evaluation lifecycle, from early scoping and Terms of Reference (ToR) development through to final evaluation reporting and quality assurance. This reflects role of the service as both a technical advisory function and a quality gatekeeper, helping to ensure that evaluations meet required standards and generate credible, decision-useful evidence.
While EQUALS2 is available as a cross-government service, the pattern of demand indicates that it operates primarily as an FCDO-focused service, in line with its original design. Of the 449 requests, 415 (93%) originated from the FCDO. In comparison, uptake from other departments is relatively small:
- 17 requests (4%) were submitted by the Department for Energy Security and Net Zero (DESNZ)
- Seven (<2%) by the Department of Health and Social Care (DHSC)
- Five (1%) by the Department for Environment, Food and Rural Affairs (DEFRA), and
- Two (<1%) by the Home Office.
A breakdown of the proportion of requests generated across HMG is presented in Table 1.

Table 1: Overview of number and type of requests categorised by department in the time period
	FCDO	DESNZ	DHSC	DEFRA	Home Office	Total
QA Baseline	100% (11)	0%	0%	0%	0%	11
QA Evaluation Report	89.2% (99)	7.2% (8)	2.7% (3)	0%	0.9% (1)	111
QA Inception Report	90.5% (67)	5.4% (4)	1.4% (1)	1.4% (1)	1.4% (1)	74
QA ToR	93.8% (122)	3.8% (5)	1.5% (2)	0.8% (1)	0%	130
ETA[2]	96.3% (104)	0%	0.9% (1)	2.8% (3)	0%	111
Evaluation Insight	100% (12)	0%	0%	0%	0%	12
[2] In the MI data, while 111 requests were recorded in the period for ETAs, when filtered by department, the sum results in only 108. This suggests 3 requests have been uncategorised by department

The 449 requests equate to an average of approximately 28 requests per quarter. Request volumes did not follow a steady upward or downward trend but instead fluctuated around this average, with distinct peaks and troughs, as illustrated in Figure 1 below. The most notable feature of the time series is a pronounced peak in Q2 2024–25, during which 57 requests were submitted, more than double the quarterly average. This spike represents a temporary surge rather than a sustained increase, as volumes subsequently return closer to the long-term average in subsequent quarters.
Number of requests
31
14
32
37
35
57
43
37
30
30
30
27
12
1
17
16
Figure 1: Overview of the total number of requests over the period of analysis per quarter
The peak observed in Q2 2024–25 is largely attributable to a sharp increase in QA reviews of Terms of Reference (ToRs), which rose from ten requests in Q2 2023–24 to 23 in the same quarter the following year. This suggests a significant increase in early-stage evaluation commissioning activity during this period, with more programmes seeking support at the design phase – this is consistent with the reductions in ODA spend post-Covid and resumption of FCDO spend after re-prioritisation of ODA spending. A different pattern is evident for QA of Evaluation Reports, which show a more gradual upward trend in the second half of the time period reflecting a growing number of evaluations reaching completion and entering the final QA stage from 2024 onwards.
EVALUATION PURPOSE AND OBJECTIVES
The purpose of the evaluation was to serve both accountability and learning needs of the FCDO. As EQUALS2 approaches the final year of its current contractual period (ending March 2027), the evaluation made an independent assessment of the programme’s performance, value for money, and contribution to improving the quality and use of evaluative activity across the FCDO. From an accountability perspective, the evaluation assessed whether EQUALS2 delivered its intended outputs, outcomes, and impacts in line with its ToC, and if public resources have been used effectively. For learning, the evaluation generated practical insights into how and why EQUALS2 contributed (or not) to improvements in evaluation quality, what aspects of the service model have worked well, and where adaptations may be needed.
The findings are intended to inform decisions about the future evolution of EQUALS2 or any successor service, ensuring that it remains fit for purpose in a changing context, with reductions in ODA spend across HMG and reduced FCDO evaluation resources. In addition, and in line with the FCDO Evaluation Strategy 2026-2030[3], a renewed focus on outcomes and portfolio reporting is anticipated to lead to increased demand for technical assistance and quality assurance. Hence, the evaluation was designed to inform the design of any subsequent service to contribute to high quality evaluations and evaluative activity across the FCDO.
[3] https://www.gov.uk/government/publications/fcdo-evaluation-strategy-2026-to-2030/fcdo-evaluation-strategy-2026-to-2030
The primary intended users of the evaluation are FCDO senior leadership, the Evaluation Unit, programme managers and evaluation advisers responsible for commissioning and overseeing evaluations. Secondary users include EQUALS2 delivery partners and evaluation suppliers, who may use the findings to refine service delivery and evaluative practice.
SCOPE AND FOCUS
The evaluation focuses on the EQUALS2 programme over the period from its inception in April 2022 through January 2026, when the evaluation was commissioned. It examines EQUALS2 as a portfolio of services designed to strengthen evaluation quality, relevance and use, with particular attention to its core components: ETA, QA and EI.
For ETA, the evaluation assessed the type, quality and perceived usefulness of technical advice provided, and how well this support has responded to evolving FCDO needs in areas such as theory-based design, evaluability and methodological robustness. For QA, the evaluation examined EQUALS2’s contribution to the quality of evaluation products across different stages of the evaluation lifecycle, including terms of reference, baseline, inception reports and evaluation reports. The EI component is covered in a lighter-touch manner, focusing on stakeholders’ perceptions of its relevance, accessibility and contribution to learning and methodological development.
The evaluation does not assess the substantive findings or outcomes of the individual programmes and policies being evaluated with EQUALS2 support, nor does it attempt to conduct a full counterfactual impact evaluation of EQUALS2. The focus was on contribution rather than attribution, recognising that changes in evaluation quality are influenced by multiple interacting factors.
TIMING AND UTILITY
The evaluation was conducted at a strategically important moment, with EQUALS2 approaching the final year of its current contractual period, and at a time of reduced ODA budgets and constrained evaluation resources within the FCDO. This timing created an opportunity to reflect on performance and assess if the current service model remains appropriate. Conducting the evaluation before the end of the contract end date enhances the utility of findings as they can directly inform design and procurement decisions for any successor service.
INFLUENCE AND COMMUNICATION APPROACH
The evaluation was designed with influence and use in mind. Findings are intended to feed into internal FCDO decision-making processes related to evaluation strategy, service design and resource allocation. The report places emphasis on practical lessons and actionable recommendations to inform both delivery of the service in its remaining twelve months, and design choices for any successor programme.
Emerging findings and recommendations were discussed in two separate validation workshops prior to the submission of the Final Report – one with the delivery partner, IOD PARC, and another with a group of staff from the FCDO Evaluation Unit.
The primary communication product is this final Evaluation Report, supported by a PowerPoint presentation highlighting the main findings and recommendations. Findings were presented by the evaluation team to the EQUALS2 Governance Panel in late April 2026.
Theory of change and evaluation framework
The evaluation adopted a mixed-methods, theory-based approach designed to assess if and how EQUALS2 contributed to improved evaluation quality, strengthened evaluative practice and enhanced use of evaluative evidence across the FCDO. The approach is grounded in the EQUALS2 Theory of Change (ToC), which provided the central analytical framework for exploring how and under what conditions EQUALS2 contributed to evaluation quality, strengthened evaluative practice, and enhanced evaluation use across FCDO. The original Theory of Change is reproduced below (Figure 2):

Figure 2: EQUALS2 ToC
To capture the influence of behavioural and organisational factors in evaluation quality, the approach integrated behavioural analysis throughout, drawing on the COM-B (Capability, Opportunity, Motivation, Behaviour change) model to identify the behavioural mechanisms that shape how users engage with and use EQUALS2 support.
During inception, a dedicated workshop was held with the FCDO to refine the theory of change and explicitly integrate these behavioural considerations. The refined ToC articulates how EQUALS2 is expected to contribute to the production, visibility and use of high-quality evaluative products through the provision of ETA and QA in particular. The ToC reflects the decentralised nature of FCDO’s evaluation system, in which commissioning responsibility is widely distributed and capability, opportunity, and motivation to engage with evaluation vary substantially across teams. This ToC has been further refined based on the evidence gathered during the course of the evaluation.
This section provides an overview of the refined intervention logic of the updated Theory of Change and identifies links between the causal pathways and the evaluation questions.
REVISED THEORY OF CHANGE
The key updates made to the Theory of Change included the following:
1. “Produces” has been removed from the impact statement, as “production” is already an aspect of the outcome statements. Instead, the impact statement focuses on sharing and application of evaluative products.
2. A new outcome has been added related to delivering high-quality evaluative activity (“small e”), as opposed to publishing credible, rigorous and credible evaluations (“big E”). This also becomes the outcome level change of the ETA pathway.
3. Specific actor groups have been called out where relevant rather than the broader use of the term “teams” in the previous version. For example, the ETA pathway is based on the behavioural change of “EQUALS Users”, the QA pathway of both “Evaluation Suppliers” and “EQUALS Users”, and then EI pathway references “FCDO teams” given the broader goals around organisational learning.
4. The intermediate outcome level is now exclusively based on behaviour change of key EQUALS2 actor groups. Given the causal jump from outputs to behaviour change, two capability, opportunity, motivation – behaviour (COM-B) models have been developed based on evaluation evidence, to unpack the causal pathways from output to behaviour change and provide additional nuance. The first COM-B model[4] unpacks the ETA pathway, with EQUALS Users as the main actor group; and the second model[5] articulates the QA pathway, with both EQUALS Users and Evaluation Suppliers as the main actor groups.[6] Please see Figures 3 and 4, respectively, in the relevant parts of the “Intervention Logic” section below. These COM-B models articulate causal pathways for each actor group at a more granular level than the Theory of Change, to provide additional nuance and unpack how EQUALS2’s goals are realised. Given EIs were not the main focus of the evaluation, the COM-B analysis focuses on QA and ETA pathways.
  [4] Referred to as “COM-B 1” in the Theory of Change.
  [5] Referred to as “COM-B 2” in the Theory of Change.
  [6] Please note that these actor groups have been selected due to their relevance to and significance for the Theory of Change. Other actor groups including EvU and IOD PARC are still considered in this evaluation’s wider analysis, but they are less relevant to the behavioural change pathways articulated in the Theory of Change.
INTERVENTION LOGIC
At the impact level, EQUALS2 seeks to contribute to a context in which the FCDO shares and uses high-quality evaluative products that have already been produced. Quality is understood not only in technical terms, but also in relation to credibility, ethical standards, and relevance for decision-making. “Use” is conceptualised as evaluative evidence informing decisions over time, rather than as a single discrete act.
Three outcomes sit below this impact:
1. “FCDO delivers high quality evaluative activity”, which is the outcome level goal associated with the ETA pathway, aligning more with the production of “evaluative thinking” products as they are referred to in FCDO’s 2026-2030 Evaluation Strategy.
2. “FCDO publishes credible, rigorous, ethical evaluations”, which is the primary goal of the QA pathway.
3. The third outcome is about evaluative activity becoming more visible internally, including prior to formal publication, enabling engagement with findings and learning as they emerge. Visibility is treated as both an outcome in its own right and an enabling condition for use. Achievement of the first two outcomes also contributes to the third outcome, as more production of formal evaluations and other evaluative activity contributes to greater visibility.
Below this, three specific change pathways are integrated into the theory of change, aligning to the ETA change pathway, QA change pathway, and EI change pathway. All of these change pathways incorporate actor-based, and behaviour change inspired thinking to articulate the causal chain from activities and inputs through to behaviour change of relevant actor groups to each change pathway.
ETA change pathway
Expert Panel Members provide the following inputs and support:
1. direct inputs into evaluative activity e.g. Theories of Change;
2. deliver evaluability assessments;
3. conduct participatory workshops which provoke insightful discussions; and
4. provide insight and constructive written and oral guidance.
This ultimately leads to several capability, opportunity, and/or motivation (COM) changes for the primary actor group relevant to this pathway, the EQUALS Users. Figure 3 details these changes through the ETA COM-B model, which unpacks the COM preconditions required to achieve the behaviour change included in the Theory of Change. Please note that the COM-B includes all necessary preconditions, which means it also captures assumptions.

Figure 3: ETA pathway COM-B model
These COM changes in turn enable two key behaviour changes, which are preconditions to the outcome-level objective for the ETA pathway. First, that EQUALS Users make more informed decisions to improve the design and/or adaptation of evaluative activity; and second, that they apply the results of ETA in design and/or adaptation of evaluative activity.
The ETA pathway rests on several key assumptions. It assumes that EQUALS Users have sufficient time and bandwidth to engage meaningfully with technical advice, that the advice provided is tailored to programme-specific contexts rather than generic, and that teams are both able and willing to act on the guidance received and use the products developed.
QA change pathway
Through the same panel of experts as the ETA pathway, these experts:
1. provide clear and actionable recommendations, and consistent ratings across products;
2. share high-quality written feedback tailored to evaluation context; and
3. provide insightful and constructive QA judgment.
The provision of this support enables a number of capability, opportunity, and/or motivation (COM) changes for the primary actor groups relevant to this pathway: EQUALS Users and Evaluation Suppliers. Figure 4 details these changes through the QA COM-B model, which unpacks the COM preconditions required to achieve the behaviour change included in the Theory of Change. The COM-B includes all necessary preconditions, which means assumptions are captured in it too.

Figure 4: QA pathway COM-B model
These COM changes in turn enable two key behaviour changes which are preconditions to the outcome-level objective for the QA pathway. First, that Evaluation Suppliers respond to QA feedback to revise evaluations and improve checklist compliance; and second, that EQUALS Users adapt evaluative designs and delivery in response to QA feedback.
There are several assumptions which underpin the QA pathway, including the following:
1. QA is timely delivered and is contextually relevant;
2. teams trust QA reviewers and feedback;
3. there is consistency in application of QA;
4. feedback is actionable and seen as supportive, not just a compliance requirement; and
5. expectations of higher quality shape supplier behaviour from the outset.
EI change pathway
The Evaluation Insights component complements the ETA and QA pathways by supporting reflective learning at an organisational level. By generating perspectives on priority thematic and methodological areas, tailored to the FCDO’s needs, through the synthesis of EQUALS2-supported evaluations and wider evaluative research, Evaluation Insights contribute to the broader knowledge environment in which evaluation decisions are made. This means that FCDO teams have access to the EIs which are relevant to their work, have increased awareness of the topics covered in the EIs, and appreciate the added value that EIs bring. This in turn allows these FCDO teams to use the EIs to improve their own evaluative activity and reinforce a culture of learning across FCDO.
A key assumption of the EI pathway is that FCDO teams have relevant opportunities to apply EIs.

Figure 5: Revised EQUALS ToC
Evaluation design and methods
The evaluation adopted a theory-based, mixed methods design aligned with the OECD-DAC evaluation criteria of Relevance, Effectiveness, Efficiency, Coherence and Sustainability. The approach was tailored to the nature of EQUALS2 as an enabling and quality assurance mechanism rather than a direct delivery programme, with analytical emphasis placed on contribution, behavioural change and service performance rather than attribution of downstream outcomes.
The refined ToC and an Evaluation Questions Matrix (EQM) guided the evaluation design, data collection and analysis. The EQM mapped each evaluation question to judgement criteria and indicators and specified appropriate data sources and methods. This ensured coherence between the evaluation purpose, the evidence base and analytical judgments. The full EQM is presented in Annex 2. The core evaluation questions and sub-questions were as follows:
Table 2: Evaluation questions
EQ1: Has the EQUALS2 expert technical assistance (ETA) service contributed to high quality evaluative activity? If so, how has it contributed, and if not, why has it failed to do so?
1.1.	To what extent has ETA contributed to improved quality of evaluative activity?
1.2	Where did the ETA fail to improve evaluative activity?
1.3	What factors contributed to whether ETA improved quality or not?
1.4	What areas of ETA offer the biggest value for FCDO?
1.5	How well does the ETA align with current an anticipated FCDO evaluation priorities? What adaptations are needed to ensure future relevance?
EQ2: Has the EQUALS2 quality assurance (QA) service contributed to high-quality evaluations? If so, how has it contributed, and if not, why has it failed to do so?
2.1	To what extent has QA improved evaluation quality?
2.2	Where did QA fail to improve evaluation quality?
2.3	What factors contributed to whether QA improved quality or not?
2.4	What improvements could be made to the QA process to increase the impact on evaluation quality?
EQ3: Have Evaluation Insights (EI) successfully supported evaluative learning across FCDO?
3.1	To what extent to EIs provide rigorous, relevant insights that inform decision-making and organisational learning within the FCDO?
3.2	What factors facilitate or hinder uptake and use of Eis and their findings?
3.3	Could improvements be made to how EIs are commissioned to ensure they meet FCDO learning needs? If so, what are these?
EQ4: Is the existing EQUALS2 delivery model the most effective model to support the evaluative activity across FCDO?
4.1	Has the EQUALS2 service been implemented as intended?
4.2	How well integrated and are the different services?
4.3	Are the opportunities for cross-learning between the services being fully maximised? If not, how could this be improved?
4.4	How could the use of MI data from the service be improved and developed?
4.5	Are there other ways in which the expertise of the panel could be drawn on to support FCDO evaluative activity?
4.6	How should the model evolve to meet the future needs of FCDO in both the short-term (FY 26/27) and the longer-term in any future quality assurance service?
4.7	Have there been unintended impacts or consequences of EQUALS2? If so, what are these?
EQ5: Does EQUALS2 offer value for money for FCDO?
5.1	Is the service run efficiently? Does it contribute to improving quality (as above)? Is the service/panel priced properly compared to the wider market?
5.2	Are there aspects of the service which offer greater VfM than others?
5.3	How could the model be developed to increase the VfM of the service?

EVALUATION DESIGN OVERVIEW
The evaluation design combined portfolio-level analysis with qualitative enquiry to examine how EQUALS2’s service components (ETA, QA and EI) operated in practice and contributed to improved evaluation quality and evaluative practice across the FCDO.
Reflecting refinements agreed during inception, ETA and QA were treated as two distinct analytical pathways, acknowledging that they operate through different mechanisms and influence evaluation quality at different stages of the evaluation lifecycle. ETA was assessed primarily through qualitative evidence on changes in evaluation planning, capability and decision-making (Effectiveness and Relevance), while QA was assessed through structured review of evaluation products complemented by stakeholder perspectives (Effectiveness, Efficiency and Coherence). Evaluation Insights were examined in a lighter‑touch, exploratory manner focused on perceived usefulness and accessibility (Relevance and Coherence). Sustainability was considered primarily in terms of institutionalisation of practices, durability of behavioural change and prospects for continued relevance of the service model, rather than long-term development outcomes.
METHODS AND DATA SOURCES
Our structured approach was designed to progressively narrow a broad evidence base into focused causal analysis and synthesis (see Figure 6):

Figure 6: Evaluation approach
The evaluation drew on multiple data sources to enable triangulation across methods and perspectives. These included:
Document review (secondary data): structured document review constituted a core method for assessing the QA pathway. A sample of evaluation products supported by EQUALS2, including ToRs, baseline report, inception reports and evaluation reports were reviewed using standardised quality rubrics developed at inception (see Annex 5). The rubrics drew on internationally-recognised quality standards, evaluation norms and the EQUALS2 checklists to assess domains such as design and methodology, data quality, reporting and communication, utility and learning, and cross-cutting issues.
The original design envisaged reviewing a stratified purposive sample of 24 evaluations. In practice, access constraints necessitated a pragmatic adaptation of the sampling approach. The constraints mainly affected evaluation products for which publication is not mandatory under the FCDO Evaluation Policy, and reliance on individual commissioners to provide documentation. As a result, the final document review sample comprised nine evaluations for which sufficient material was available within the evaluation timeframe (see Table 3). This adjustment was discussed and agreed with the FCDO during coordination meetings. Time constraints for completion of the evaluation meant there was insufficient time available to collate and review additional evaluations.
Sampling was conducted at the level of evaluation assignment, allowing the evaluation to capture multiple QA and ETA touchpoints associated with the same evaluation. The original stratified purposive sampling strategy accounted for type of support received (ETA, QA, or both), evaluation product type, and quality scoring band, with diversity across sector, geography and commissioning year. Due to document availability constraints, the final document review sample was smaller and availability based.
Table 3: List of final sampled evaluations
#	EvalID	EQUALS2 unique ID	Entry stratum	Support type
1	GLO-275	GLO-275-SOR-ISF	QA TOR/ / Unsatisfactory	QA TOR
2	NIG-018	NIG-018-TOR-Thematic Evaluation	QA TOR/Good​	QA TOR
				QA Inception
				QA Evaluation Report
3	OMA-002​	OMA-002-IR-Country Strategy Evaluation​	QA Inception/Fair (Non-ODA)	QA Inception
4	INPAC-002​	INPAC-002-IR-LCDI​	QA Inception/Good​	QA Inception
				QA TOR
				QA evaluation report
5	MAL-001	MAL-001-ER-National Numeracy Programme​	QA ER/Fair​	QA Evaluation Report
				QA Baseline
6	SOM-017	SOM-017-ER-Gaashaan​	QA ER/Fair​	QA Evaluation Report
				QA TOR
7	NEP-001​	NEP-001-ER-BEK GESI​	QA ER/Excellent​	QA Evaluation Report
				QA Inception
8	GLO-264​	GLO-264-TOR-Safeguarding Resource and Support Hub Programme Evaluation​	QA_ETA/ToR/ / Fair​	QA TOR
				QA Inception
				QA Evaluation Report
9	GLO-209​	GLO-209-ER-CCG-R​	QA ER/Good​	QA Evaluation Report
				QA Inception

Semi-structured interviews (primary data): Semi-structured interviews were the primary source of qualitative evidence. A purposive sampling strategy was employed to ensure coverage of key stakeholder groups and experiences. The FCDO Evaluation Unit contacted commissioners involved in the sampled evaluations, while IOD PARC contacted EQUALS2 expert panel members with experience of ETA and/or QA delivery. Sampling of panel members sought to ensure gender balance and diversity of experience.
A total of 32 interviews were conducted across different stakeholder groups, as summarised in the table below:
Table 4: List of stakeholders interviewed
Stakeholder	Rationale for engagement	Interviews planned	Interviews conducted
IOD PARC	Delivery partner responsible for sourcing and appointing experts; engaged primarily to understand EQUALS2 process	3	2*
EvU	Manages and oversees the delivery of EQUALS2 services	3	3
EQUALS Users	Commission and manage evaluations, and request ETA and QA from EQUALS2	15	18
Expert Panel Members	Carry out QA assessments and provide TA services	10	10
Total		31	32
*Only two members of IOD-PARC were suitable for interview

Interview guides (see Annex 3) were aligned with the EQM and explored both technical and behavioural dimensions of EQUALS2’s influence, including capability, opportunity and motivation factors shaping uptake and use of services. Interviews contributed evidence across multiple DAC criteria, particularly Relevance, Effectiveness and Coherence.
Survey of evaluation providers (primary data): an online survey was designed to capture external evaluation providers’ experience of engaging with the EQUALS2 QA service and to explore their perspectives on the service’s contribution to evaluation quality and methodological rigour. It also sought to gather feedback on the usability, clarity and perceived value of QA inputs.
The survey launched on 11 March 2026 and remained open until 20 March 2026. The FCDO shared an initial list of 57 organisations that had previously delivered evaluations assessed through EQUALS2. This list was supplemented through desk‑based research, resulting in 60 potential provider contacts. Of these, 34 contacts responded and agreed to participate, and the survey was distributed to this group. Given gaps in available contact details, additional outreach was required, and recipients were asked to cascade the survey within their organisations to colleagues with direct experience of EQUALS2 engagement. A total of 17 responses were received.
Survey findings were analysed descriptively and used to triangulate interview and document review evidence, particularly in relation to providers’ perceptions of how QA feedback influenced reporting standards and alignment with FCDO expectations. Survey results were not treated as statistically representative but as complementary evidence to triangulate with other sources of evidence.
Management information, financial and contextual data: management information and other documents (such as quarterly reports, Evaluation Insights, meta-analysis etc) provided by IOD PARC and the FCDO were used descriptively to contextualise findings and inform interpretation under the efficiency and coherence criteria. Annex 7 contains a complete list of documents consulted during the evaluation. Financial data relating to total programme spend and spend and time inputs on each QA, ETA and EI assignment was also provided by IOD PARC to inform the assessment of value for money.
Given the limited timeline and constraints in accessing some documentation, data collection and analysis tools were not pre-tested. However, they were designed to be flexible, allowing for iterative adjustments and adaptation in response to emerging data availability.
ANALYTICAL APPROACH
Analysis was structured around the evaluation questions. Interview data were first analysed in a thematic matrix aligned to evaluation questions, enabling systematic comparison against respondent groups. Emerging findings were discussed during weekly internal coordination meetings to test interpretations, identify patterns and test assumptions.
To ensure a structured and consistent basis for assessing contribution, the document review for case study analysis followed a staged analytical approach. First, the evaluation team conducted an independent review of both versions of the products, before and after EQUALS2 support, against its own internal evaluation quality rubrics. This provided a systematic assessment of the technical quality of the documents, independent of the formal EQUALS2 process, and allowed the team to identify strengths, weaknesses, and areas of continuity or change in a structured way.
Second, the evaluation reviewed the EQUALS2 QA feedback provided on the products and compared it with the evaluation team’s own quality assessment. Where alignment was confirmed, it increased confidence that the issues identified by the evaluation team were not only individual but reflected widely recognised quality dimensions.
Third, the analysis examined the extent to which issues flagged through EQUALS2 feedback at earlier draft stages were subsequently taken on board in the final versions, and whether issues at commissioning stage reemerged in inception or final reports. This allowed the case studies to trace a potential pathway from early feedback, through commissioning decisions, to downstream quality outcomes in subsequent evaluation products.
Triangulation across data sources and methods was a core analytical principle, used throughout the evaluation to strengthen the credibility of findings and mitigate the limitations of any single source of evidence.
To ensure the accuracy and usefulness of the evaluation findings and recommendations, a sensemaking workshop was conducted with IOD PARC on 30 March 2026 to engage IOD PARC directly with emerging findings to refine recommendations and provide context to qualitative data. A second sensemaking workshop with a group of FCDO staff was took place on 16 April 2026, prior to submission of the Final Report.
QUALITY ASSURANCE
Quality assurance was embedded throughout the evaluation process. An external, independent quality assurer identified by Chemonics with no prior engagement in EQUALS provided independent oversight of methodological rigour, transparency and alignment with agreed standards. To avoid conflict of interest, it was not possible for EQUALS’s experts to quality-assure the evaluation, however EQUALS’ quality checklists have been applied at key stages of the evaluation, such as inception, preliminary findings, and final report.
LIMITATIONS and MITIGATION
Key limitations relate to document availability, sample size for document review and reliance on self-reported stakeholder perceptions. The reduced document sample limits the generalisability of portfolio-level quality patterns and constraints the strength of conclusions related to system-wide effects. These limitations were mitigated through triangulation with interviews, conducting additional interviews with EQUALS service users, and internal analytical challenge.
There are also specific limitations connected to the case studies. Limited access to documentation and time constraints meant that the original design, which combined document review with targeted interviews with relevant stakeholders for each case study, could not be implemented. As a result, the case studies draw on quality assessment using the evaluation’s quality rubric and analysis of EQUALS2 QA feedback, without stakeholder perspectives. The initial intention was to select five case studies from the pool of 24 evaluations for this purpose. Following agreement with the FCDO, only four case studies were examined in this way, due to time constraints and the change in the available evidence base. With only nine evaluations available for review, the evaluation team judged that producing an additional case study would have been repetitive, as no further distinct features were identified and the contextual nuances from the interviews were missing. Clear considerations on limitations and how to interpret the findings are reported in each case study. Time constraints also led to a lighter-touch assessment of Evaluation Insights, limiting causal analysis.
Ethics, safeguarding and data responsibility
The evaluation was conducted in line with established principles of ethical research and evaluation, with a clear operationalisation of the “do no harm” principle. All interactions with participants were designed to minimise risk and ensure that no individual was exposed to professional, social or reputational harm. Participation in interviews and surveys was voluntary, with informed consent obtained prior to data collection. Participants were informed of the purpose of the evaluation, how their data would be used, the limits of confidentiality, and their right to decline to answer specific questions or to withdraw from the evaluation at any stage without consequence. Confidentiality was actively safeguarded, and care was taken to ensure that findings were reported in a way that prevented the identification of individual participants or organisations.
Safeguarding considerations were integrated throughout the evaluation process. Particular attention was paid to power dynamics, organisational hierarchies and gender considerations within the evaluation context. Interviewers were trained to create a safe and respectful space for participation and to recognise how positionality or institutional relationships might influence responses. Although the evaluation did not involve vulnerable populations, safeguarding principles were applied proportionately, including procedures for responding to any distress or safeguarding concerns should these arise.
The evaluation team operated independently from EQUALS2 delivery, and potential conflicts of interest were actively managed. Evaluations in which team members had prior involvement were excluded from the sample frame, and known conflicts of interest were identified and removed at the outset. Oversight of potential conflicts was maintained throughout the evaluation through regular team check‑ins and internal review processes to ensure analytical impartiality.
Data protection and responsible data management practices were applied in accordance with applicable data governance standards. All data were stored on a secure SharePoint site with access restricted to authorised team members. Personal identifiers were removed from interview transcripts and internal analytical products, and digital tools were deployed in ways that protected confidentiality. Data storage and handling arrangements were proportionate to the sensitivity of the information collected and the participant profile. Hard copy and electronic files will be retained securely for five years post‑contract, after which retention or secure destruction will be determined in line with data governance requirements. Only data necessary to address the evaluation questions were collected, and access financial data was limited to reduce disclosure risk.
No AI was used for the analysis.
Management and independence
As noted above, stakeholders from IOD PARC and the FCDO were engaged in active conversations around emerging findings and recommendations in the preparation of this evaluation report. In addition, the FCDO management team provided written and verbal feedback throughout all stages of the evaluation. The evaluation team was able to work freely and without interference in conducting the evaluation and findings that are presented.
While Chemonics is an established actor within the UK evaluation landscape, potential conflicts of interest related to organisational positionality were assessed as part of the procurement process. Specific measures were implemented to avoid conflicts of interest, including the explicit exclusion from the sample frame of two Chemonics-delivered evaluations that were subject to EQUALS2 QA. Additional evaluations were excluded from the sample to avoid conflicts of interest with work conducted by members of the evaluation team prior to joining Chemonics.
The evaluations excluded from the sample to avoid any conflict of interest were:
- KEN-006- Portfolio of Election Support- KEVAL: Chemonics carried out the evaluation and was assessed under EQUALS2 QA service
- PAK-004- REMIT: Chemonics carried out the evaluation and was assessed under EQUALS2 QA service
- COL-003-TEFOS: The Team Leader was involved in the evaluation and was assessed under EQUALS2 QA service
- ZIM-003-ER-SAFE: The Team Leader was involved in the evaluation and was assessed under EQUALS2 QA service
- AFR-002-ATIP: The Chemonics’ programme Research and Innovation Systems for Africa (RISA) Fund is involved in ATIP learning and MEL sessions.
These measures have ensured an independent and unbiased evaluation of the EQUALS2 service. None of the evaluation team have served as expert panel members on any iteration of the EQUALS service.
Evaluation Team
The roles and responsibilities of evaluation team members are outlined below:
Jamie Fotheringham, Team Leader: Responsible for overall leadership and accountability for the evaluation; led stakeholder engagement; and provided final sign-off on all evaluation tools and deliverables.
Teresa Di Giacomo, Principal Evaluator: Served as senior technical lead; designed the methodology and approach; and led analysis.
Oliver Ellis, Evaluation Specialist: Supported data collection and analysis; conducted interviews; and supported synthesis and reporting.
Poppy Russell, Evaluation Analyst: Supported report drafting and coordinated interviews scheduling.
Dr Björn Müller-Wille: External quality assurance of the whole evaluation process and deliverables.

Findings
This section presents the findings of the evaluation. Findings are organised by evaluation question and reported under each corresponding sub-evaluation question. Cross-cutting findings and overall trends across evaluation questions are discussed in the Analysis section. For each evaluation question, the evidence base underpinning the findings is described at the outset.
EQ1: Has the EQUALS2 expert technical assistance (ETA) service contributed to high quality evaluative activity? If so, how has it contributed, and if not, why has it failed to do so?
EQUALS2’s ETA service provides an array of technical support to the design and delivery of evaluative activity that apply evaluative thinking to support decision‑making, learning, and accountability, without necessarily meeting the formal standards of a full evaluation. This includes, for example, facilitating theory of change development, conducting evaluability assessments, or technical support on indicator development or evaluation methodologies[7].
[7] EQUALS Programme Summary Notes shared by FCDO as part of the evaluation’s desk review.
This section explores the extent to which ETA has contributed to high quality evaluative activity, drawing on evidence collected through interviews with the EvU, IOD PARC, EQUALS Users and Expert Panel Members (EPMs). Together, this evidence is used to assess (i) the extent to which ETA contributed to quality of evaluative activity (EQ 1.1), (ii) where and why ETA has been less effective (EQ 2.1), (iii) the factors shaping ETA’s contribution to quality of evaluative activity, (iv) what changes could strengthen its impact going forward (EQ 1.4).
EQ 1.1: To what extent has ETA contributed to improved quality of evaluative activity?
Overall, there is ample evidence of ETA contributing to the broader causal pathway towards improving quality of evaluative activity, specifically through ETA being perceived as useful and relevant, as well as it filling specific capability (i.e. skills and knowledge) and opportunity[8] (i.e. time and resources) gaps for EQUALS Users.
[8] “Capability” and “opportunity” are the “C” and “O” of “COM-B” – see Theory of Change section for more detail.
While findings point to ETA clearly enabling better evaluative thinking at specific points in time, the evaluation finds limited observable evidence of sustained behaviour change, such as the routine application of ETA guidance or integrating ETA into wider decision-making to inform evaluative practice.[9] The synthesis across findings demonstrates that ETA’s influence is highly conditional: where ETA is implemented by expert panellists who have built sectoral and technical familiarity, as well as being integrated in ongoing decision-making processes, its contribution is evident. In cases where ETA is implemented as one-off advisory support, or where teams lack ownership or follow-through, it weakens the causal chain. This indicates that although the capability and opportunity changes are key mechanisms, motivation and accountability are essential for translating these into sustainable change. However, it is important to note that this reflects both the episodic nature of ETA delivery and the methodological limits of assessing longer-term behavioural change in a decentralised system, rather than evidencing ineffectiveness of ETA per se.
[9] Sentiments raised during the sensemaking workshop with IOD PARC and EvU, however, acknowledged that EQUALS has no control over whether or how ETA outputs are taken forward, and any continuity depends on FCDO teams and in particular MEL Advisors who should play a bridging role.
For example, opportunity gaps were found to be most prevalent with EQUALS Users who were also MEL Advisors: several MEL Advisor interviewees mentioned that they possessed the requisite skills and knowledge to support an evaluative activity, such as the development of a Theory of Change, yet they did not have the time to do so. As such, EQUALS2 ETA filled this gap by providing time and relevant expertise where resources were constrained for FCDO staff, despite the FCDO staff also having the capability to do so. Nevertheless, some anecdotal evidence suggests that in some specific cases, ETA also plays a quality-enhancing role where EQUALS Users are not MEL specialists, or where requests require niche methodological or thematic expertise that is not readily available in-house.
A combination of opportunity and capability gaps were revealed to be common among EQUALS Users who were not also MEL Advisors. The opportunity gaps were similar to those of the MEL Advisors, primarily around time and resources, though the capability gaps were characterised based on methodological skills and knowledge, such as survey design and qualitative analysis; and more strategic thinking, including how to frame evaluation questions and link findings with recommendations. The ETA in these cases not only filled resourcing gaps, but also provided a level of expertise to the evaluative activity that was not possessed by EQUALS Users at the time.
One clear example of contribution of ETA to the quality of evaluative activity is through ETA provided to the Africa Technology and Innovation Partnerships (ATIP) programme. Sentiments from interviews demonstrate that the quality of the ATIP Theory of Change was improved due to the provision of the ETA expertise, largely in the form of participatory facilitation and innovative MEL approaches.
The initial ToC focused more on quantitative approaches which were seen to be less meaningful, but the ETA made the team more aware of measuring quality and less tangible concepts. This in turn led to FCDO developing a new approach to systems strengthening, as well as delivering several workshops to upskill delivery partners on the updated, more qualitative approach.
However, it should be noted that the evidence for this example stems from just two interviews: one with an EQUALS User, and another with an EPM. Moreover, another factor which impacted the overall strength of evidence in verifying contribution between ETA and evaluative activity quality was the lack of visibility that EPMs have after they provide their ETA, meaning that interviews with EQUALS Users, and limited ETA documents, were the primary sources of evidence.
The presence of a MEL Adviser within programme teams may moderate whether ETA contributes to longer-lasting change, by supporting follow-through and application of advice into routine practice. However, the evaluation did not systematically compare programme with and without MEL advisers, therefore cannot fully assess the magnitude of this effect.
EQ 1.2: Where did the ETA fail to improve evaluative activity?
Overall, findings paint a positive picture on the added value of ETA to evaluative activity, with limited examples of ETA failing to improve evaluative activity. There were, however, two primary challenges that were raised which related to security clearance and the relevance of the selected EPMs to ETA requests.
Regarding security clearance, a recurring theme from interviews with EQUALS Users argued that on the one hand, they do not feel as though the EQUALS2 panel has enough experts with SC and DV clearance, which has created difficulties for them in terms of sharing sensitive information required to deliver the ETA. On the other hand, there was also an appreciation that often evaluation commissioners and EQUALS Users have limited clarity internally from FCDO on the level of security clearance that is required for a particular programme or area of work, which impacts their ability to submit an accurate request to EQUALS2. The sensemaking workshop with FCDO underlined that improving how and when in-house expertise with appropriate security clearance is identified and deployed may be as important as expanding the pool of externally cleared experts.
Almost all interviews with EQUALS Users highlighted that the qualifications and experience of the EPM allocated to them was relevant to their request. However, a small number of examples were provided during interviews with EQUALS Users of EPMs being allocated in response to a request, who did not have relevant expertise. This was particularly in reference to ETA for non-ODA evaluative activities where, in some cases, EPMs lacked the requested thematic background across diplomacy, geopolitics, and influencing. During the sensemaking workshop with IOD PARC and EvU, however, it was noted that many non-ODA teams struggle to articulate what support they need because they are unfamiliar with evaluation concepts. This creates issues regarding how precise the ETA requests are and increases the risk of mismatch.
Similarly, three EPMs remarked that the scope of work and deliverable(s) for ETA can sometimes be vague, compared to the QA which has a clear deliverable in the form of the QA checklist. They recommended that having more clarity on the deliverable(s) they should submit to satisfy the ETA request would be helpful.
Two EQUALS Users also expressed concerns around not having enough guidance on expected Level of Effort (LOE) allocations for different types of ETA, which made submitting an accurate request challenging. For example, interviewees were not confident on how many days of LOE should be expected for a Theory of Change workshop.
EQ 1.3: What factors contributed to whether ETA improved quality or not?
One key contributing factor to ETA quality identified across interviews with EQUALS Users and EPMs was consistently using the same EPM(s) across a particular programme or area of work so they are able to build trust with the EQUALS Users, develop an understanding of the context, and become more familiar with any thematic or methodological nuances. It was also argued that allocating new EPMs to a particular programme or area of work can require EQUALS Users to spend more time explaining the nature of the context and work, which in turn would be less efficient and value for money. This does not suggest that the same EPMs should routinely be assigned to repeat engagements. Rather, it indicates that when programmatic familiarity already exists and aligns with EQUALS’s demand-driven and best-fit resourcing approach, this can contribute positively to the quality of ETA. This is an aspect of EQUALS2 delivery which IOD PARC recognised and aim to prioritise where possible, while continuing to safeguard independence and manage any potential CoI, and ensure fairness across the EPM in terms of the opportunities available to them
Another key contributing factor raised during interviews with EPMs was that ETA requests in which FCDO were clear in terms of what they wanted, generally led to a higher quality ETA output. In cases where users were less clear, it required the EPMs to spend more time to help them figure this out, rather than allocating the LOE to completing the assignment. This demonstrates that the more clarity and detail provided in an ETA request, particularly in terms of the ETA output, generally leads to a more relevant ETA response. It was noted, however, that in some cases ETA is about providing advisory support to inform FCDO’s decision-making which may not require a tangible output as such. That being said, this was not always clear from the ETA request.
EQ 1.3: What areas of ETA offer the biggest value for FCDO?
The strongest trend that emerged in terms of ETA’s biggest value add was the expertise in participatory facilitation that EPMs bring, which are relevant to both ODA and non-ODA work. Several examples were identified in which EPMs navigated complex discussions, steering conversation, and asked thought-provoking questions led to tangible outputs. For example, one interview with an EQUALS User and one with an EPM highlighted how ETA - in the form of high quality facilitation and technical support to a Theory of Change process for FCDO’s counterterrorism team, involving soft power and influence in the non-ODA space - contributed to the development of the FCDO’s strategy for one British High Commission in Sub Saharan Africa. This demonstrates a high value add of effective facilitation to informing decision-making.
“The value add is more in the facilitation and helping people to understand and interact in this process. The thought-provoking questioning was great.”
EQUALS User
Related, another value add of ETA and EQUALS2 more broadly is that given its high reputation for technical proficiency and methodological rigour across the FCDO, it provided internal motivation for FCDO staff to join ToC workshops compared to situations where independent experts were not involved.
Finally, sentiments from interviews with EQUALS Users and EPMs both highlighted that ETA presents a high opportunity to add value to the FCDO in terms of building capability and upskilling FCDO staff across evaluative activity and thinking. The highest value areas to build capability and skillsets referenced during interviews aligned with the FCDO’s future priority areas in the current climate related to international development and MEL, including PMEL; MEL for diplomacy, cybersecurity, and influencing interventions; developing learning systems; “small e” methodologies such as outcome harvesting and process tracing; and leveraging AI across MEL.
The need for TA across the FCDO was well documented across interviews, particularly with EQUALS Users (see quote), so there are opportunities for the FCDO and EQUALS2 to further capitalise on the added value of ETA, and explore how it can continue to adapt to the evolving evaluative needs of priorities of FCDO (see next sub-question).
“Our organisation is crying out for TA, as MEL capacity is stretched. We want people to help us to develop things like PMEL, and to help prepare us for the new MEL world we are going into.”
EQUALS User
EQ 1.4: How well does the ETA align with current and anticipated FCDO evaluation priorities? What adaptations are needed to ensure future relevance?
Overall, sentiments from interviews across all stakeholder groups emphasise the strategic value that EQUALS2 ETA provides to the FCDO, and that it proficiently serves the current needs of the FCDO related to evaluative activity.
There were, however, reflections around how ETA can better adapt to the future needs and priorities of the FCDO. Two key priorities that emerged from the evaluation where adaptations may be needed to the ETA service were:
1. exploring if and how EQUALS may be needed to support more non-ODA work; and
2. PMEL.
For non-ODA work, this is due to how non-ODA interventions are structured: typically non-ODA work has been more discrete and linked to thematic areas such as cybersecurity and the use of diplomatic influencing as a policy tool, rather than embedded within large, multi-year programmes. These distinctions are increasingly blurred in practice, with growing areas of work combining ODA and non-ODA approaches, or applying diplomatic and influencing tools to achieve development outcomes regardless of the funding source. To respond to this, interviewees emphasised the need to have more SC and DV cleared consultants on the panel, as well as additional expertise for these non-ODA thematic areas, including how to measure more intangible concepts such as diplomatic influencing. The latter point also reflects a gap identified in the FCDO’s 2026-2030 Evaluation Strategy: “The distribution of evaluations largely reflects ODA spend, which means there are gaps in other areas, such as diplomatic influencing, non-ODA spend and corporate activity.”[10]
[10] Please see the FCDO Evaluation Strategy 2026-2030, available at: https://www.gov.uk/government/publications/fcdo-evaluation-strategy-2026-to-2030/fcdo-evaluation-strategy-2026-to-2030
The idea of adapting the framing of ETA to a non-ODA audience also emerged from the findings. For example, there was appreciation that “theory of change” as a term may be unattractive for those in the non-ODA space, and instead terminology such as “theory of stability” or framing around “what are we influencing and how can we achieve it?” were proposed as potentially being more suitable. If EQUALS2 is to continue to support non-ODA interventions then further consideration may be needed to ensure users in non-ODA contexts are familiar with the service offering and understand how it can be user to meet their evaluative needs.
Similarly in the ODA space, as a result of budget cuts, there may be fewer programmes with formal evaluations and more evaluative products developed internally by those who may or may not have a MEL background. Several interviewees suggested that EQUALS2 ETA could be the vehicle through which FCDO’s internal capability and confidence could be developed to ensure these evaluative products are developed to a high standard.
Across EQUALS2 documentation, interviews, and FCDO’s 2026-2030 evaluation strategy, PMEL emerged as a MEL delivery structure that the FCDO are prioritising. This includes both cases where PMEL is implemented through third party contracts, and cases where PMEL is conducted in-house. Interviews explored the idea of how ETA could support the design and delivery of PMEL in both scenarios.
While third party PMEL arrangements may absorb some ETA-type functions in specific contexts (for example through built-in support for development of evaluation approaches and capacity building), PMEL delivery models vary considerably, and both third party and internal FCDO PMEL approaches are likely to need continued support from EQUALS for specialist advice, and targeted technical support in the future.

EQ2: Has the EQUALS2 quality assurance (QA) service contributed to high-quality evaluations? If so, how has it contributed, and if not, why has it failed to do so?
EQUALS2’s QA service provides expert review and independent quality assurance of evaluation products (ToRs, inception reports, baseline reports, and evaluation reports) primarily commissioned by the FCDO.
This section examines whether and how the EQUALS2 QA service has contributed to the production of high-quality evaluations commissioned by the FCDO. It focuses on both the nature and the limits of QA’s contribution, recognising quality not only as technical compliance with standards, but also as the extent to which evaluations are improved, strengthened, and made more usable through the review process. The analysis draws on multiple complementary sources of evidence, including interviews with FCDO’s EvU, IOD PARC, EQUALS Users and Expert Panel Members; a survey of evaluation suppliers; and a structured document review of ToRs, inception reports, baselines and final evaluation reports, assessed before and after QA using tailored rubrics. Together, this evidence is used to assess (i) the extent to which QA has improved evaluation quality (EQ2.1), (ii) where and why QA has been less effective (EQ2.2), (iii) the factors shaping variation in QA’s influence on quality (EQ2.3), and (iv) what changes could strengthen its impact going forward (EQ2.4).
EQ 2.1: To what extent has QA improved evaluation quality?
The evidence suggests that QA has improved evaluation quality to a moderate and often meaningful extent particularly in relation to evaluability, clarity, coherence, and usability of evaluation products. Across interviews, survey responses, documentary analysis and four in-depth case studies, QA most consistently contributes to quality by strengthening the foundations of evaluation design, clarifying expectations for suppliers, and enabling commissioners to secure revisions that would otherwise be difficult to justify or enforce.
Survey evidence indicates that evaluation providers themselves generally perceive QA as adding value rather than functioning solely as a procedural requirement. Ten (of seventeen) respondents indicated QA had moderately or significantly improved their evaluation work, with the most common benefits being better structure and clarity of reporting and stronger evaluation standards. Ten respondents also reported that the changes that resulted from QA feedback were meaningful rather than merely cosmetic at least occasionally or half of the time, and thirteen respondents indicated that EQUALS2 had clearly or to some extent improved the overall quality of FCDO-commissioned evaluations.
A clear and consistent pattern is that QA often improves evaluation quality through a combination of technical refinement and institutional reinforcement. On the technical side, the evidence points to improvements in evaluation outputs, risk sections, methodological framing, sampling choices, and overall structure of reports. On the institutional side, QA gives commissioners an independent basis for requiring changes. This latter mechanism is particularly important in a decentralised system: many EQUALS Users described the QA as most useful not because it always identified entirely new issues, but because it validated internal concerns and created a stronger basis for challenging suppliers and pushing products to an acceptable standard. In practical terms, it means that QA improved quality not only through the content of feedback, but through the authority that comes with it.
The document review reinforces these findings, even though the review focused only on products from nine evaluations, therefore representing a limited sample. Across the cohort, QA feedback was consistently shown to engage with evaluability, analytical coherence and usability rather than focusing only on surface-level compliance. In particular, the four case studies (see end of EQ2 section) provide concrete illustrations of how QA feedback, when taken up, can lead to clearer articulation of evaluation purpose and use, more explicit evaluation questions and criteria, stronger specification of methods and data, and better integration of cross-cutting issues such as ethics, safeguarding and GEDSI.
However, there is more limited evidence that QA consistently improves higher-order aspects of evaluation quality, such as methodological innovation, analytical depth, or usability. Many respondents noted that QA often identified issues already known to experienced MEL advisors and added limited new insight unless the reviewer had highly specific technical expertise. Some experts also reported that reviews often focussed on completeness and presentation rather than fundamental methodological issues, partly because most evaluation providers are already technically competent.
Template design is another important factor. The evidence consistently highlights a tension between standardisation and relevance: standardised criteria support consistency, accountability and comparability, but they can also feel too rigid when applied to small evaluations, reviews, PMEL-like outputs or non-traditional products. Moreover, QA is inherently subjective even with checklists, and “light touch” approaches already require judgment rather than mechanical scoring. The implication is not that standardisation is unhelpful, but that the balance between consistency and proportionality is central to whether QA is experienced as useful or distortive.
There is also evidence that QA is particularly valuable earlier in the evaluation cycle. Across the interviews, ToRs and inception reports are repeatedly identified as the stages where QA has the greatest leverage, because this is when design weaknesses, vague requirements or unrealistic expectations can still be addressed before they shape the whole evaluation. Several respondents emphasised that influencing design is more effective than reviewing draft evaluation reports , where it may be “too late” to address fundamental issues, suggesting that the timing of QA is a critical factor in determining its impact[11]. The QA feedback review across different products at different stages of the evaluation also supports this. In most cases, QA feedback at ToR or inception stages focused on foundational design issues, and in all four case studies it was plausibly associated with quality improvement in subsequent products. In Case Studies 1 (GLO 264), 3 (INPAC 002) and 4 (NIG 0018), documentary comparison suggests that revisions linked to QA feedback made inception reports more evaluable and analytically coherent, rather than simply more complete.
[11] As per FCDO Evaluation Policy, QA is required at ToR and Inception report as well.
“(EQUALS) Taught me some things about asking technical questions and methodology. The template is a useful tool.”
EQUALS User
A further, albeit secondary, effect is that QA sometimes contributes to capability-building. Some EQUALS Users reported that the process helped them think more critically about methods, qualitative design, or the kinds of technical questions that should be asked of evaluators (see callout box). The evidence for this is limited, and it would be overstated to present capability-building as a core or universal effect of QA.
“I’m not a qual researcher at all, and skills and knowledge were built [through EQUALS] in terms of qual methods.”
EQUALS User

EQ 2.2: Where did QA fail to improve evaluation quality?
The evidence indicates that QA has been less effective in three circumstances:
1. Where the criteria or template were poorly aligned to the product or context;
2. Where QA came too late in the evaluation cycle to influence core design choices;
3. Where written feedback limited the extent to which comments could be interpreted and acted upon.
The clearest recurring issue is misalignment between the QA framework and the products being reviewed. This draws on convergent evidence from interviews across all categories of stakeholders, supplemented by perceptions captured in the survey of evaluation providers. Across these sources, there is a consistent pattern indicating that the current QA model is strongest for conventional evaluation products and weaker when applied to non-ODA, policy-facing, PMEL-like or otherwise non-traditional outputs. In these cases, even though the template allows flexibility to indicate where specific criteria are not applicable, respondents across all types reported that the criteria could feel rigid, over-specified or based on assumptions more relevant to development programming than to the product at hand. This does not seem to be a matter of user preference, in some cases the mismatch appears to have reduced confidence in the relevance and credibility of the feedback. This does not prove that the template is systematically unfit for purpose, but it does raise concerns around its applicability to different evaluation products.
Evidence strongly suggests that when QA is introduced late, particularly at draft evaluation report stage, its ability to improve quality is constrained. In those cases, QA may still improve presentation, clarity or completeness, but it is less able to correct weak framing, poor evaluation questions, or inappropriate methods already built into the exercise. The survey reinforces this point. Seven of 15 respondents identified late timing of QA as a factor limiting its ability to improve quality, and qualitative responses also indicated that reviews were sometimes commissioned too late to make a substantive difference. Given the small sample, these figures should be treated with caution, but they align closely with the qualitative evidence and help show that this is not an isolated concern.
The final limiting factor is, in some cases, lack of verbal feedback. The evidence suggests that written feedback alone does not always maximise quality improvement, especially where products are non-standard, comments are nuanced, or users need help translating reviewer concerns into concrete changes. Several respondents described follow-up discussion as the point at which the value of QA became clearer, while also noting that such interaction is not always built into the process or clearly signposted. The survey supports this pattern, with 7 of 15 respondents favouring more dialogue-based QA in future. However, the evidence is not one-sided: some experts stressed the importance of preserving blindness and independence and were cautious about more open discussion, in particular with suppliers. The stronger conclusion, therefore, is not that written feedback is inherently inadequate, but that the absence of structured opportunities for clarification can limit quality improvement in some cases. Even though structured opportunities for discussion between QA reviewers and evaluation providers can be built into the process, they are not always taken on and could benefit from more signposting.
EQ 2.3 What factors contributed to whether QA improved quality or not?
The evidence suggests that QA’s contribution to evaluation quality is shaped by a combination of timing, institutional authority, reviewer credibility, commissioning choices and provider capability, rather than procedural features of the QA model.
The most consistent and strongly evidenced factor is the perceived quality, professionalism and independence of the expert reviewers themselves. Across interviews, both users and Evaluation Unit staff repeatedly describe reviewers as highly knowledgeable, technically competent and able to provide credible challenge. This credibility appears to be central to whether QA feedback is taken seriously and acted upon. The document review showed that EQUALS2 QA feedback was mostly acted upon, even in cases where re-submissions or reviews of core requirements were not mandated. Moreover, several EQUALS users emphasised in interviews that the value of QA lies in having access to “external expert” judgement that can validate, reinforce or sharpen internal critique, especially in contexts where commissioners lack time or specialist expertise. The role of QA as an independent validator, rather than simply a checklist function, emerges as a key mechanism through which quality improvements are realised.
Closely related to this is the authority conferred by the QA process itself. The evidence indicates that QA is effective in part because it is not optional. The fact that QA is required for publication creates a system in which evaluation products must meet a minimum standard. This ‘threshold effect’ is repeatedly referenced in interviews, where respondents describe QA as providing leverage in discussions with suppliers and ensuring that certain issues ‘have to be addressed’ in order for work to progress. In this sense, QA improves quality not only through the substance of feedback, but through its institutional position within the evaluation system. There is strong evidence across interviews, documents reviews and the survey that this mandatory nature, combined with scoring thresholds, creates incentives for suppliers to revise and improve products.
The document review showed that the substance of the feedback itself matters. Feedback that was analytically grounded, focused and clearly linked to evaluability and use appears more likely to be taken up than feedback framed primarily in terms of formal compliance. The four case studies provide consistent examples where such quality-oriented and narrative feedback led to substantive revisions. This reinforces interview findings that QA’s value lies less in mechanical scoring per se, and more in the expert judgement and explanatory insight that accompany it, through which suppliers are able to interpret requirements and adjust their approach.
A further contributing factor is the clarity of expectations embedded in the QA framework. Several respondents noted that the templates and criteria provide a clear articulation of what constitutes a publishable evaluation within the FCDO, reducing ambiguity for both commissioners and suppliers. This appears to support quality by standardising expectations and ensuring that key elements, such as safeguarding, ethics and clarity of evaluation questions, are consistently addressed. At the same time, the evidence suggests that familiarity with these expectations matters. Evaluations produced by providers who are accustomed to EQUALS2 requirements tend to align more closely with the criteria, whereas less experienced or less informed providers may struggle to meet expectations or require more substantial revision.
As reported in EQ 2.2, there is some evidence that verbal interaction, where it occurred, has enhanced the effectiveness of QA. Several EQUALS users highlighted that the greatest value was realised when feedback could be discussed, clarified or contextualised, allowing reviewers and commissioners to align their understanding and translate comments into actionable changes. However, this is not a consistent feature of the model, and the evidence is mixed. While some Experts see dialogue as critical to maximising impact, others emphasise the importance of maintaining independence and avoiding undue influence on reviewers.
EQ 2.4: What improvements could be made to the QA process to increase the impact on evaluation quality?
The evidence suggests that improvements to the QA process should focus less on fundamentally redesigning the model and more on refining how it operates in practice, particularly in terms of flexibility, engagement, and alignment with the evolving nature of evaluative activity within the FCDO. The strongest and most consistent finding is that the current model would benefit from becoming more adaptable to different types of evaluation and evaluative work, while preserving its core strengths in independent review and standard-setting.
A central area for improvement concerns proportionality and adaptability of the EQUALS2 QA framework. Across interviews, there is a recurring view that the current templates and criteria are effective in setting standards but can be overly rigid when applied to smaller, lower-budget or non-traditional evaluations. Several experts and users noted that a “one-size-fits-all” approach can create unnecessary burden or misalignment, particularly in contexts such as PMEL, non-ODA work, or rapid and resource-constrained evaluations. This is not primarily framed as a failure of the QA model, but as a limitation in how it is currently configured. The implication is that introducing more differentiated or scalable approaches, whether through different templates or clearer guidance on proportionality, could increase the relevance and impact of QA. The evidence for this is strong in terms of consistency across sources, although less specific on the optimal design solution. Criteria for a ‘light-touch’ QA route could be based on evaluative complexity and product type, rather than contract value alone. Evidence suggests that non-ODA evaluative products may be particularly suitable for a differentiated approach, provided minimum quality standards are retained.
A second area of improvement relates to the degree and structure of engagement between reviewers and users. For evaluation commissioners, the current model does provide an option for follow-up discussion with the reviewers; however, these are not consistently utilised or embedded in the process. On the other hand, for evaluation suppliers, direct interaction with reviewers is not routinely available and tends to occur only in exceptional circumstances. As reported in EQ 2.2. and EQ 2.3, several respondents indicated that direct interaction with reviewers, even in a limited or structured form, significantly enhances the usefulness of QA by allowing clarification of feedback and contextualisation of recommendations. However, considering the concerns around maintaining independence of the reviewers, the evidence supports a more deliberate and proportionate approach to engagement, rather than a shift to a fully verbal model.
The timing of QA engagement also emerges as an important area for improvement. While timing has been identified as a constraint (see EQ 2.2), the more forward-looking implication is that earlier and more iterative engagement could increase impact, particularly at the design, ToR stage and at earlier stages during the evaluation drafting process. Several respondents highlighted that early input is where QA can most effectively shape evaluation quality, rather than simply refining outputs at a later stage. There is also some indication that support at pre-ToR or design stage, potentially overlapping with more ETA, could help teams clarify their evaluative approach before formal review.
Another important area concerns the evolution of QA standards to reflect changing evaluative needs. Both Evaluation Unit respondents and users pointed to gaps in how current templates address emerging areas such as portfolio MEL, non-ODA work, and more sensitive or high-security contexts. The evidence suggests that while the existing framework is robust for traditional evaluation products and traditional development programming, it is still adapting to newer forms of evaluative activity. This is reinforced by examples where QA criteria were perceived as misaligned with the nature of the work, particularly outside ODA contexts. The need to update or expand standards is therefore well supported, although the evidence is less clear on how quickly or extensively such changes should be implemented. The evaluation does not recommend case-by-case tailoring of standards by individual reviewers. Responsibility for defining, revising and maintaining QA standards appropriately sits with EvU as the central standard-setting authority.
Finally, there is some evidence that improvements could be made in how the QA process is communicated and understood by users. Better signalling to suppliers, such as early awareness that a product will undergo QA, could improve preparedness and alignment with requirements. This adjustment may also have a meaningful impact on how effectively QA feedback is interpreted by the EQUALS Users, and acted upon, and may help ensure engagement happens at early stages where it is most valuable.
Case studies on EQUALS2 QA contribution to evaluation quality

This section presents a set of case studies examining the extent to which EQUALS2 QA feedback contributed to the production of high-quality evaluation outputs. The case studies explore where QA feedback was taken up at different stages in the evaluation cycle (including the commissioning process), and explores any longitudinal effects of QA feedback influencing the quality of subsequent evaluation products. The case studies were selected from the nine evaluations reviewed against the internal quality rubrics developed by the Evaluation Team at inception. A detailed description of the methodology is provided in the Analytical Approach section of this report, and limitations on findings and considerations on the approach for each case study analysis are reported case-by-case.
CASE STUDY 1: Provision for safeguarding resource and support hub (RSH) Evaluation (GLO-264)
This case study examines how quality assurance feedback interacted with the development of the RSH evaluation across the ToR, inception, and evaluation report stages, with particular attention to whether feedback appears to have improved the quality of individual products and whether quality gains can plausibly be traced across the evaluation cycle.
At ToR stage, the QA feedback was clearly not limited to surface compliance. Although some comments were institutionally compliance-oriented, especially around explicit references to FCDO expectations such as “do no harm,” ethical protocols, or digital principles, the main focus of the review was diagnostic and quality-focused. The main shortcomings identified in the draft ToR were an unclear evaluation purpose and use, the absence of explicit evaluation criteria, weak articulation of evidence gaps, under-specified methodological expectations, limited detail on data sources and stakeholder roles, and insufficient treatment of ethics, safeguarding, risk, and management arrangements. These are not minor formalities, they speak directly to evaluability, analytical usefulness, and whether suppliers would have enough clarity to design a strong evaluation.
There is strong evidence that some of this feedback was incorporated into the final ToR. The clearest examples are the sharper articulation of purpose and use, the explicit incorporation of OECD DAC criteria, the stronger framing of the evaluation’s contribution to wider evidence gaps, the requirement for an evaluation matrix at inception, and the strengthening of ethical and safeguarding language, including the “do no harm” principle and the requirement for ethical protocols. These changes plausibly improved the quality of the commissioning document, particularly by making the evaluation more clearly decision-oriented and methodologically framed. However, uptake was incomplete. The final ToR still did not fully specify data quality, disaggregation and limitations; stakeholder roles as sources of evidence were not consistently defined; and some governance and uptake issues remained weakly articulated. Risk was strengthened but still appears to have been treated more as an implementation concern than as a design feature shaping methods and sampling. This matters because it means the final ToR was improved, but was not fully strengthened in all the areas the QA review had identified as important for evaluability.
Shortcomings in the ToR were partly seen in the first draft of the inception report. Some of the weaknesses identified at ToR stage do appear again in the first inception report, especially around analytical organisation, evaluability and traceability. The draft inception report was criticised for containing many of the necessary pieces, but in a scattered form that did not yet function as a coherent design-locking document. In particular, the QA feedback noted the absence of a usable theory of change narrative despite the existence of a diagram, a lack of a fully articulated evaluation matrix linking questions, indicators, methods and data, and insufficient explanation of how a large and complex body of evidence would be synthesised within the available timeframe. These concerns echo the ToR-stage weaknesses around under-specified methods, limited clarity on how evidence would be generated and used, and insufficient articulation of analytical logic. In this sense, there is plausible evidence that some ToR weaknesses carried forward into the inception report rather than being fully resolved upstream.
At the same time, the first draft of the inception was clearly much stronger than the ToR in methodological ambition and sophistication. It already contained substantial work on contribution analysis, comparative analysis, triangulation, ethics, risk and quality assurance processes. This indicates that the evaluation team did not simply reproduce the limitations of the ToR. Many of the strongest features of inception report appear to reflect supplier capability rather than instructions embedded in the ToR. The evidence therefore supports a qualified conclusion: some incompleteness in the ToR appears to have left room for similar weaknesses to persist into inception, especially around organisation and operational clarity, but the quality of the draft inception report was also shaped strongly by the provider’s own methodological standards. It would overstate the case to claim that ToR shortcomings drove the main weaknesses in the first inception draft. The relationship is plausible, but partial rather than determinative.
The QA feedback on the inception report was again predominantly quality-oriented rather than merely checklist-driven. Some comments concerned presentation, such as section numbering, diagram labelling, and hyperlinking, but the more important critique focused on whether the report was doing the work of an inception report. The reviewer identified structural and analytical weaknesses: the theory of change existed but did not yet organise the design; the evaluation matrix did not yet provide clear traceability; the methodological architecture was ambitious but not sufficiently operationalised; and cross-cutting issues, especially GEDSI and vulnerability to SEAH, were present but not yet elevated into a clearly structured analytical concern. These are substantive comments about whether the evaluation was focused on evaluable aspects of the project and analytically coherent, not simply whether the right sections were present.
There is strong documentary evidence that the final version of the inception report took on a substantial share of this feedback, and that the changes were quality-enhancing rather than merely compliance-enhancing. The final inception report no longer treated the theory of change as a background annex, but as the organising spine of the evaluation, with explicit discussion of outcomes, assumptions and causal pathways. The analytical approach became much more operationalised, particularly in relation to contribution analysis, comparative analysis, triangulation, and how differences across hubs would be handled. Cross-cutting issues were materially strengthened through the introduction of a stand-alone question and explicit disaggregation dimensions. Sampling also became more transparent, with structured respondent categories, indicative numbers and rationale. These changes do not read as cosmetic responses to a checklist. They made the evaluation design more coherent, more and more credible.
The uptake of inception-stage feedback was not complete, however. The reviewer’s concern that the report was overly long and context-heavy was only partially addressed. The final inception report appears clearer in structure but still extensive, and in places, still more descriptive than necessary. This is important because it suggests that the feedback had the greatest impact where it required clearer analytical architecture, but less impact where it required stronger editing discipline or more radical streamlining. Even so, the balance of evidence supports a reasonably confident claim that the feedback on the first draft of the inception report improved the quality of the final version in a substantive way, especially in design coherence, analytical framing and evaluability.
The final evaluation report appears strongly aligned with the methodological architecture set out in the revised inception report. The evaluation questions remain consistent, the theory-based design is clearly implemented, contribution and comparative analysis are visible in the way findings are structured, and there is continuity in the treatment of ethics, triangulation, GEDSI, and evidence strength. This suggests that most of the major analytical weaknesses identified in the inception report were resolved by the time the evaluation reached delivery. In particular, the concerns around weak analytical architecture and insufficient operationalisation do not appear to persist in the same form into evaluation report. The evaluation report scored highly against the EQUALS2 rubrics, which changes the interpretive question. The issue here is not whether the report was weak and needed rescue, but whether the QA feedback still added value or mainly enforced compliance and polish. The evidence suggests that the feedback remained constructive and quality-oriented, even at this high starting point. The most important comments did not focus only on formatting or institutional references. Instead, they challenged the report’s internal logic, particularly the relationship between findings, conclusions and recommendations; the extent to which conclusions were genuinely higher-order judgements rather than restatements of findings; the need to improve prioritisation and structure of recommendations; and the importance of being explicit about evidentiary limits, especially in relation to efficiency, GEDSI and causal claims. These are core evaluative issues that matter even in a strong report.
There is evidence that at least some of this feedback was taken up in the final version. The clearest example is the restructuring of recommendations into a smaller number of overarching recommendations with priority levels, intended audiences and implementation guidance. This closely reflects the QA feedback and appears to improve usability and decision support. There is also stronger articulation of conclusions as higher-order analysis and more explicit signalling of limitations and evidence strength. These changes suggest that the feedback added value by sharpening synthesis, judgement and use, rather than merely checking compliance boxes.
At the same time, the evidence also indicates that some feedback at evaluation report stage was more selective in uptake, and that not all remaining weaknesses were resolved.
Taken across the whole cycle, the case shows a differentiated pattern of contribution. At ToR stage, QA feedback clearly improved the commissioning document, but uptake was partial and some gaps remained. There is plausible but limited evidence that those remaining gaps contributed to shortcomings in the first iteration of the inception report, particularly around coherence and operational clarity, although the provider’s own capability appears to have been the stronger determinant of quality at that stage. At inception stage, QA feedback was substantively taken up in the final version and appears to have improved quality in a real sense, especially by making the design more evaluable and analytically coherent rather than simply more compliant. By the time of the evaluation report, most of the earlier design weaknesses had been resolved, suggesting that the quality chain from revised inception to delivery was relatively strong.
The main limitation of this case study is that the revised inception report and revised evaluation report were not re-scored, so claims about improvement have to rest on documentary comparison rather than before-and-after rubric results. It is also not possible to isolate the effect of QA from other influences such as internal commissioner input, evaluator learning, or normal iterative drafting. The strongest claim the evidence supports is therefore one of contribution and not causation. Even with that caveat, this case provides credible evidence that QA can improve quality at each stage of the cycle, but that its influence is strongest where feedback is substantively analytical and where teams are willing and able to absorb it. It also shows that weak upstream uptake can limit how much quality assurance at later stages can achieve, while strong provider capability can compensate for some weaknesses in earlier products.
CASE STUDY 2: Integrated Security Fund (ISF) Fund-wide Monitoring, Evaluation and Learning (FMEL) contract (GLO 275)
The Evaluation assessed the Statement of requirements (SoR) for the Integrated Security Fund (ISF) Fund-wide Monitoring, Evaluation and Learning (FMEL) contract, which is a complex, multi-year call-off designed to provide centralised MEL advisory support, independent evaluation and synthesis, and capability building across a £1bn cross government fund operating in politically sensitive and fragile contexts. The quality review examined the draft SoR as a commissioning instrument for evaluation and MEL services, focusing on whether it was sufficiently clear, coherent and evaluable to support strong commissioning decisions, and then compared the revised version produced after structured EQUALS2 feedback to assess how far that feedback substantively improved quality, usability and evaluability, rather than simply addressing surface level or compliance requirements.
In the initial assessment, the SoR was judged to be operationally incomplete, reflecting its draft status rather than a lack of strategic intent. The document demonstrated mature and credible thinking about fund wide MEL in complex and politically sensitive environments, with strong alignment to ISF history, policy priorities and cross cutting standards such as gender, safeguarding, conflict sensitivity and duty of care. However, its quality as a commissioning instrument was constrained by clarity issues, unfinished annexes and a heavy reliance on the inception phase to define core elements. In particular, the intervention logic remained implicit, evaluation scope and questions were under specified, methodological expectations were generic, and workplans and deliverables could not yet be fully assessed for feasibility or value for money. The findings of the EQUALS2 quality assurance review closely aligned with this assessment. Both the evaluation and the EQUALS2 reviews recognised the document’s strong strategic ambition and contextual grounding, while identifying the same underlying weaknesses: pervasive draft markers and placeholders, deferred decisions throughout the SoR, and insufficient specification of causal logic, evaluation purpose, questions, data and methods. The QA’s low scores on purpose, evaluative content and methodological clarity reflected a shared concern that too much substantive design was postponed to inception, limiting evaluability and increasing commissioning risk at SoR stage
The feedback from the EQUALS2 QA review was taken on board in ways that materially improved the document’s quality as a commissioning instrument, even though not all issues were fully resolved. In the first draft, one of the most significant quality gaps was the pervasive draft status: extensive drafting notes, placeholders, duplicated definitions and unfinished annexes made it difficult to distinguish binding requirements from guidance, a problem explicitly highlighted in the QA under Structure and Clarity, and echoed in the Evaluation’s judgement about usability and operational incompleteness. In the revised version, drafting notes at the front of the document were removed, the structure was formalised into numbered sections with a clear table of contents, and paragraph numbering was largely consistent, directly addressing the QA recommendation to reformat the document to improve navigation and referencing. This change improved the document’s usability for bidders and contract managers, which can be considered a quality gain rather than a cosmetic one.
A second major gap in the original draft was the weak articulation of intervention logic at SoR stage: outcomes and outputs were listed, but the causal pathway linking MEL activities to improved decision-making and impact remained implicit, with Theory of Change entirely deferred to inception. The QA explicitly recommended either including a pre-existing Theory of Change or, at a minimum, being clearer about how it would be developed and used. In response, the revised SoR made the development of a Theory of Change explicit both in the scope section and as a named inception deliverable, alongside the results framework and MREL framework, rather than an optional addition. This does not fully resolve the issue that causal assumptions were still not articulated upfront, but it strengthened coherence by making the SoC a contractual output tied to early delivery, which made the final ToR better able to support evaluability than the first draft.
Similarly, the original draft scored very weakly on evaluation scope, questions, and use, with evaluation questions absent, intended users only broadly implied, and use of findings discussed at a high level. The QA feedback repeatedly called for clearer articulation of purpose, accountability versus learning, evaluation questions, and a more explicit account of how findings would be used. While the revised version still did not specify high-level evaluation questions or OECD-DAC criteria, it clarified the primary objective, explicitly referencing accountability in the rationale for MEL, and introduced clearer expectations around reporting, decision-making forums, and governance structures through which evidence will feed into use, such as an FMEL Steering Board and structured reporting cycles. This represents partial uptake of the feedback as the document was clearer about where evidence will go, even if it remained less clear exactly what core evaluative questions would be asked.
One area where the feedback led to a substantive improvement is data. In the initial draft, datasets and data access were almost entirely absent, leading to very low QA scores under Methods and Data Collection. In the revised SoR, a dedicated “Datasets” subsection was added, specifying sources such as quarterly programme reports, annual reviews and management information, clarifying that both qualitative and quantitative data would be used, and acknowledging that dataset requirements would vary by output and be refined through Statements of Work. While still relatively high level, this directly addressed a gap in the first version and improved bidders’ ability to assess feasibility and resource implications.
The revised version also responded directly to feedback that elements of quality assurance and ethics were under-specified. The QA review flagged the absence of any explicit reference to EQUALS2 or quality assurance processes, and the first draft treated these issues implicitly. The final SoR included a discrete Quality Assurance subsection stating that outputs may be reviewed by independent experts and that EQUALS2 may be used for high-risk or innovative evaluative pieces, which is a clear, traceable response to that feedback. This strengthened quality assurance expectations without overly constraining methodological choice.
Taken together, these changes mean that the revised SoR was demonstrably stronger to commission a robust evaluation or MEL service than the first draft. What the EQUALS2 feedback process achieved in this case was not so much to transform a weak SoR into a strong one, but to convert a strategically sound but under-specified draft into a document that was more coherent, more usable, and more defensible as a commissioning document. The first draft may have been “strong enough” conceptually, but the applied feedback reduced commissioning risk by clarifying structure, tightening early deliverables, and addressing critical omissions around logic, data and quality assurance.

CASE STUDY 3: Low Carbon Development Initiative Phase 2 Evaluation (INPAC 002)
This case study examines whether and through which pathway feedback provided at the ToR stage of the INPAC 002 evaluation contributed to improvements in evaluation quality, focusing first on changes between the earlier and later versions of the ToR and then on how those plausibly influenced the quality of the evaluation’s inception report.
At the ToR stage, the initial EQUALS2 review assigned the document a score of 68% (‘Good’). Although this meant that the ToR did not require a second formal EQUALS2 review, the written feedback indicated the presence of several core issues that required attention before the ToR could be published. The checklist review identified a set of substantive weaknesses that spoke to the integrity and usability of future evaluation products. The feedback highlighted, among other issues, the absence of annexed core MEL concepts such as a Theory of Change, ambiguity around roles and responsibilities between the Evaluation Management Unit and the main contractor, lack of clarity around what was meant by “impact evaluation”, insufficient specification of methodological expectations, the absence of a MEL specific risk assessment, and weak or missing requirements on quality assurance and on use and influence planning. These were framed in the checklist as essential gaps to address if the ToR was to provide a sufficient analytical and managerial basis for commissioning a complex evaluation.
Comparison of the later version of the ToR with the earlier draft provides credible evidence that the feedback contributed to quality improvements, albeit in a selective and uneven way. The later ToR is stronger and clearer on governance arrangements, work planning, deliverables, learning, and use of findings, and it articulates independence and quality assurance requirements more explicitly than the earlier version. These areas of improvement map closely onto the QA recommendations that called for consolidation of requirements, clearer articulation of outputs, stronger learning orientation, and more explicit management and quality assurance expectations. In these areas, the feedback appears to have been taken on board to a meaningful degree, and the final ToR was more suited to commissioning a robust and well managed evaluation.
At the same time, the feedback relating to more analytical issues was only partially addressed or left unresolved. Despite the recommendation to annex or formally embed the Theory of Change and other MEL constructs from the Business Case, the ToR continued to rely on references and links rather than incorporating these elements directly. Similarly, QA concerns about the absence of clearly defined evaluation questions, the lack of a shared intervention logic, and the ambiguity surrounding the term “impact evaluation” were not directly resolved in the revised ToR. Instead, responsibility for defining evaluation questions, refining the Theory of Change, and improving analytical focus were deferred to the inception phase. From a commissioning perspective, this represents a conscious choice to preserve flexibility, but it is also one that the QA warned could generate analytical ambiguity and variability later in the evaluation cycle.
These commissioning choices help to explain the quality profile of the inception report. The inception report received an EQUALS2 score of 72% (‘Good’), indicating a generally sound and credible product with some areas requiring further strengthening. There is a strong correspondence between the areas where feedback influenced the ToR and the areas where the inception report is strongest. The inception report demonstrated clarity of purpose, a well articulated learning and dissemination strategy, detailed stakeholder and influence pathways, robust ethical and safeguarding protocols, and a clearly described quality assurance approach – responding directly to earlier QA feedback. In this sense, it can be concluded that feedback provided at ToR stage contributed indirectly but materially to the strength of the inception report in these areas.
Conversely, the areas where the QA feedback was not fully taken up in the ToR are also the areas where the inception report showed limitations. While the inception report introduced a Theory of Change and adopted a contribution tracing approach, these elements were presented in a largely descriptive and provisional manner, with explicit acknowledgement that further refinement would occur later. Evaluation questions were framed as Evaluation and Learning Questions to be finalised in subsequent phases, rather than as a final agreed analytical framework.
Taken together, the evidence supports a contribution claim. QA feedback at ToR stage improved quality, particularly by strengthening governance, quality assurance, learning, and use and influence planning. Where that feedback was reflected in revisions to the ToR, it contributed to strong corresponding sections in the inception report. Where feedback on analytical foundations was only partially adopted, the inception report did not fully resolve these issues gaps. This case illustrates both the value and the limits of early quality assurance. It shows that QA can shape downstream products, but the nature of the feedback and the extent to which it is translated into explicit commissioning requirements determine what kinds of quality improvements are realistically achievable later. In that sense, quality emerges as co produced across the commissioning–delivery chain, and this case provides evidence of how selective uptake of feedback at ToR stage leads to a correspondingly selective quality improvement in inception outputs.
CASE STUDY 4: Twenty years of UK health system strengthening programming in Nigeria Thematic Evaluation (NIG-0018)
This case study explores how EQUALS2 QA influenced the quality of evaluation products across the evaluation cycle, focusing on the Terms of Reference, the inception report, and the final evaluation report for the Twenty years of UK health system strengthening programming in Nigeria Thematic Evaluation.
At Terms of Reference stage, the analysis compared the first and final versions of the ToR against the evaluation’s internal quality rubrics, before examining the associated EQUALS2 QA feedback. The initial ToR scored 60% (‘Good’) in the EQUALS2 review. While this score did not trigger a mandatory second QA round, it indicated substantive weaknesses on core criteria that needed to be resolved prior to publication. The EQUALS2 feedback was largely quality enhancing rather than compliance driven, and it focused on key elements of evaluability, coherence, and likely use.
The principal shortcoming of the first draft ToR was the absence of clearly articulated and prioritised evaluation objectives. While objectives could be inferred, they were not explicit, which the EQUALS2 QA review identified as a risk to downstream design quality. Similarly, evaluation questions were assessed as overly broad, dispersed across different sections, and unrealistic given time and evidence constraints, and resulted in an unsatisfactory rating on this criterion. The feedback also identified weak treatment of context, particularly insufficient attention to Nigeria’s federal structure, state level variation, and the role of non FCDO actors, warning that findings would have limited utility without robust contextual analysis. Additional gaps were identified around the articulation of evaluation use, with no requirement for an evaluation use and influence plan, weak linkage between outputs and timing, and insufficient clarity around governance, independence, and quality assurance arrangements.
The revised ToR showed strong evidence of substantive uptake of this feedback. Objectives were explicitly articulated, prioritised, and linked to learning, programme design, policy engagement, and contribution to the evidence base and reducing ambiguity for suppliers. Evaluation questions were made explicit, and aligned to OECD DAC criteria and better framed to account for contextual variations across Nigeria. More broadly, context was repositioned from background description to an explicit basis for analysis, including attention to government and other partner interventions. Requirements for an evaluation use and influence plan and stakeholder mapping were introduced. Governance and independence provisions were clarified, including conflict of interest management and the role of EQUALS2 in QA. Some QA feedback was only partially taken up, notably concerns about the available evidence base for assessing impact, sustainability, and value for money.
There is plausible evidence that these ToR level changes contributed to a stronger inception report, based on a comparison of first and final inception drafts against the EQUALS2 rubrics and the extent to which earlier ToR-level feedback was taken onboard. The clearer articulation of purpose and objectives in the revised ToR enabled the evaluation team to distinguish learning from accountability more explicitly in the final inception report. Similarly, the ToR’s stronger emphasis on context appears to have enabled deeper contextual analysis at inception stage. However, several concerns remained at inception: in particular, concerns around the availability of evidence to enable robust evaluation of programme effectiveness, sustainability, and impact.
The inception report stage provided clearer evidence of QA feedback improving quality. The first draft inception report scored 56% (‘Fair’) in the initial EQUALS2 review. A second review, following substantive revisions, resulted in a score of 68% (‘Good’), indicating material quality improvement. The main weaknesses related to an overly ambitious scope, unresolved design choices, and claims about methodological strength that were not sufficiently supported. The draft referenced advanced approaches such as realist evaluation, contribution analysis and process tracing but did not demonstrate the level of methodological expertise required to apply them rigorously. As a result, there was a high risk that the evaluation would rely on general qualitative triangulation, while presenting its findings as providing stronger causal insights. Moreover, although context was repeatedly highlighted as important, it was not clearly defined and incorporated into the analytical framework. Finally, the framing of the evaluation questions leaned more towards accountability, rather than supporting the stated intention to focus on learning.
The EQUALS2 QA feedback at inception directly addressed these quality risks, and the final inception report showed substantive uptake. The evaluation purpose was reframed as formative and learning oriented, with explicit statements about what the evaluation would not attempt to do, resolving concerns regarding the earlier draft. Concerns about sufficient contextual factors underpinning the evaluation were addressed through political economy analysis and defined contextual factors that were integrated into case selection and outcome logic models, responding directly to the QA feedback. Evaluation questions were narrowed and categorised according to what could be fully answered, partially answered, or excluded, making trade-offs explicit and improving transparency. The methodological ambition of the evaluation was also revisited, with methods reframed as case-based qualitative analysis rather than formal qualitative comparative analysis or realist evaluation. These changes are attributable to EQUALS2 QA feedback, as they directly respond to the QA feedback and go beyond basic compliance.
In the EQUALS2 feedback, the first draft of the evaluation report showed shortcomings in evidence traceability, analytic transparency, and the distinction between findings, lessons, and recommendations. Claims were frequently synthesised without clear linkage to specific programmes, states, or data sources, that undermined the credibility of the portfolio evaluation. The evaluation matrix did not clearly map questions to judgement criteria, data sources, and programmes, a significant weakness given the mismatch between portfolio scope and primary data coverage. Lessons learned were often not well specified, with a lack of clear linkage between evaluation evidence and the conclusions and recommendations presented. The first draft evaluation report scored 41% (‘Fair’) in the initial EQUALS2 review, indicating serious weaknesses that required a second QA round. Following revisions, the second review score increased to 57% (‘Fair’), indicating improvement but also the persistence of important quality risks. However, the final evaluation report demonstrated some uptake of the feedback. Findings were included only where corroborated by multiple sources, and context was more integrated into the analysis. Findings were structured more coherently around evaluation questions and intermediate outcomes.
Overall, this case demonstrates that EQUALS2 QA feedback can contribute to measurable improvements in quality across the evaluation cycle when it focuses on central issues of purpose, coherence, evidence, and intended use. A structured comparison of draft and final versions of the Terms of Reference, inception report, and evaluation report showed that EQUALS2 QA at earlier stages strengthened subsequent products, particularly by clarifying purpose, narrowing ambition, and improving the transparency of the methodology. At the same time, the ‘Fair’ rating for the final evaluation report indicates the limits of QA in fully offsetting evaluability constraints and design risks embedded earlier in the process. Taken together, the evidence supports a limited contribution claim: QA feedback influenced the development and coherence of evaluation products, while final quality outcomes reflected the interaction between feedback processes and provider capability rather than the effect of QA alone.
EQ3: Have Evaluation Insights (EI) successfully supported evaluative learning across FCDO?
Evaluation Insights are a core component of the support provided through EQUALS2, designed to synthesise evaluation evidence and generate cross-cutting learning on evaluative practice to inform practice, strategy and decision-making across the FCDO. EIs aim to extract lessons from the evaluation portfolio, provide thematic and methodological insights and support organisational learning on key issues such as evaluation quality, utility, innovation and cross-cutting priorities[12]. The EIs delivered to date have focused on a combination of thematic synthesis, reflections on methodologies and emerging strategic issues within the evaluation function. Several products have drawn directly on the FCDO’s existing evaluation portfolio to identify common lessons and challenges, such as the review of barriers and challenges in sustainable development programming. Others have explored specific areas of evaluative practice, including innovation in evaluation methods and the development of portfolio monitoring, evaluation and learning (PMEL), with the aim of informing how evaluation is designed and used across the FCDO. A second group of EIs has addressed forward-looking or strategic topics, often extending beyond the FCDO’s internal portfolio. The study on Artificial Intelligence in evaluation, for example, mapped emerging practices across international organisations, examining use cases, risks and governance considerations to inform the FCDO’s engagement with new technologies. Similarly, EIs, such as one on conflict prevention MEL, reflect an intention to provide evidence-informed guidance on complex and evolving policy and operational challenges.
[12] EQUALS2 inception report.
EIs were intended to be commissioned primarily by EvU, with wider access to wider audiences, including MEL Advisers, programme and policy teams, and senior-decision-makers possible[13]. This section explores the extent to which Evaluation Insights have successfully supported evaluative learning. The analysis draws on evidence collected through interviews with the EvU, IOD PARC, EQUALS users and Expert Panel Members, and it is used to assess (i) the extent to which EIs informed decision making and learning within the FCDO; (ii) the factors that hindered or facilitated uptake and use of EIs; and (iii) what changes could strengthen their uptake and use for learning.
[13] Ibid.
EQ3.1: To what extent do EIs provide rigorous, relevant insights that inform decision-making and organisational learning within FCDO?
EIs provide rigorous and, in some cases, relevant insights but their ability to consistently inform decision-making and organisational learning is often constrained by issues of specificity and usability.
There is some evidence from interviews across the different stakeholder categories that some EIs have directly informed decisions and organisational initiatives. The AI EI is a clear example, having informed the creation of a new workstream on AI knowledge management and supported internal discussions. In addition, the PMEL EI also played a significant role in consolidating thinking, supporting a community of practice, and influencing the direction of the evaluation strategy. These examples demonstrate that EIs can produce credible insights when aligned with organisational priorities and taken forward by engaged stakeholders.
However, many EQUALS Users reported that EIs did not meaningfully inform their work. It is important to note, however, that many EIs were not explicitly designed to inform routine decision-making across a broad user base, and some EIs, such as the Conflict Prevention one, have not been circulated widely due to sensitivities around the content. Some respondents described the EI as too high-level or generic to be actionable, while others felt they were not relevant to their specific operational context. Several users explicitly stated that they had not used EIs for decision-making, and some questioned their practical utility altogether. Even where outputs were considered high quality, they did not always meet the needs of wider audiences, particularly where practical tools were expected but more conceptual or guidance-oriented products were delivered.
There is also evidence that portfolio-level analysis may be too broad to generate actionable insights, reducing their perceived usefulness. This suggests a tension between producing cross-cutting synthesis and delivering context-specific insights that can inform decision-making at an operational level.
EQ 3.2: What factors facilitate or hinder uptake and use of EIs and their findings?
The uptake and use of EIs are shaped by a combination of demand alignment, ownership, accessibility, organisational context and product design, with several significant barriers limiting their broader use.
A key factor shaping use was demand from specific teams: EIs commissioned or actively supported by engaged stakeholders were more likely to be used and inform practice. Similarly, where EIs addressed clearly identified needs or strategic priorities, such as the AI EI, were more likely to generate uptake and follow-on activity. The involvement of multiple stakeholders and the ability to connect ‘top-down and bottom-up’ perspectives enhanced relevance and engagement.
At the same time, several barriers significantly hindered uptake. Limited awareness is a major issue, with many users either unaware of EIs or only vaguely familiar with them. While this partly reflects the fact that commissioning of new EIs has been paused for over a year due to budget constraints, some respondents who were aware of EIs, perceived that they were primarily for evaluation specialists or central teams, reducing their relevance to wider audiences. Another critical barrier is the misalignment between EI outputs and EQUALS Users needs. Several interviewees highlighted that EIs tend to be too high-level, guidance oriented or ‘evaluator-y’, whereas there is greater demand for targeted insights and context-specific applications. There are also structural challenges related to topic selection and scope. Interviews with EQUALS Users revealed that some EI topics are not always well-defined or sufficiently focused, resulting in outputs that are too broad to be useful to this particular audience. The lack of iterative processes and limited engagement with users during commissioning further exacerbates this issue.
EQ 3.3: Could improvements be made to how EIs are commissioned to ensure they meet FCDO learning needs? If so, what are these?
There is strong evidence that improvements are needed in how EIs are commissioned, particularly in relation to topic selection, user engagement, specificity and adaptability, in order to meet the FCDO’s learning needs.
A central issue is the need for a more robust process for identifying and prioritising topics. Several respondents noted that current processes do not sufficiently capture wider user needs (beyond EvU) or strategic priorities, leading to misaligned outputs. While some prioritisation exercises have been undertaken (e.g. producing a longlist of potential topics followed by a purposive selection based on the strategic steer from the Governance Panel and evolving interests across FCDO), these do not appear to consistently result in high-value topics to MEL advisors and other end users. There is a clear demand for greater co-creation with EQUALS Users to ensure that EIs address timely and relevant questions.
There is also a need to shift from broad, portfolio-level analysis to more focused and question-driven approaches. Narrower, more targeted topics are more likely to produce actionable insights.
Another key area for consideration is the type of outputs produced. There is strong demand for moving beyond guidance and synthesis reports towards more practical, usable products such as tools, case studies or interactive learning formats. There is also interest in more iterative and adaptive approaches, allowing EIs to evolve in response to changing contexts.
Overall, there is a need to broaden the intended audience beyond EvU and ensure that EIs are designed with different user groups in mind. This includes considering how to make insights more accessible and relevant to non-specialist audiences.
EQ4: Is the existing EQUALS2 delivery model the most effective model to support the evaluative activity across FCDO?
The EQUALS2 programme inception report prepared by IOD PARC explains the delivery model of EQUALS2 is designed to provide responsive, demand‑led support while also strengthening evaluative culture across the FCDO. The three core services (TA, QA, EI) operate through a helpdesk model that responds directly to the needs of the FCDO and other ODA-delivering government departments, while also generating portfolio-level data and learning.
Governance is provided through FCDO core leadership, a Governance Panel, and the programme’s core management team. The Governance Panel plays a strategic role in ensuring relevance and alignment with the FCDO’s evolving priorities by providing advice, identifying learning themes, promoting uptake of the service, and feeding lessons from delivery back into the FCDO at a senior level. Delivery is further supported by a management information system focused on evaluations submitted through the service, providing robust and timely data to inform management decisions and improve visibility of evaluation activity.
This section explores if the existing EQUALS2 delivery model is the most effective approach for supporting evaluative activity across the FCDO. It considers both how the model has functioned in practice and how well it is positioned to meet current and future needs, recognising effectiveness not only in terms of whether it was implemented as intended, but also the degree of integration, learning, adaptability, and strategic value generated across the service. The analysis draws on qualitative evidence from interviews with FCDO’s EvU, IOD PARC, expert panel members, and EQUALS2 users, alongside a desk review of key programme documentation, including the inception report, the FCDO Evaluation Strategy, and relevant management and reporting materials. Together, this evidence is used to assess (i) whether the EQUALS2 service has been implemented as intended (EQ4.1); (ii) how well the different service components are integrated (EQ4.2); (iii) the extent to which opportunities for cross‑learning between services are being maximised (EQ4.3); (iv) how the use of management information data could be improved and further developed (EQ4.4); (v) whether there are additional ways in which panel expertise could be drawn on to support FCDO evaluative activity (EQ4.5); (vi) how the delivery model may need to evolve to meet FCDO’s short‑ and longer‑term needs (EQ4.6); and (vii) whether the model has generated unintended impacts or consequences (EQ4.7).
EQ 4.1: Has the EQUALS2 service been implemented as intended?
The evidence indicates that EQUALS2 has been implemented broadly as intended in relation to its core delivery processes.
Across EQUALS2 users, the process for requesting and receiving support is typically described as clear, timely and professional, and most users appear to have engaged with the helpdesk and email systems as intended. There is also evidence of active implementation of flexibility within the model. The service has adapted in practice to user needs where possible, for example by tailoring some QA processes, or accommodating iterative approaches for ETA even where these were not fully anticipated in the original design. This indicates that the delivery model has retained the responsiveness envisaged in its design. This is also supported by evidence from QPRs. In 2025, the average acknowledgement times for new requests consistently remained under seven hours, and completion of QA requests within the 10-day standard set in KPI 2 ranged from 82% to 100%, demonstrating timely and adaptive responses to user demand.
However, implementation is less consistent where user needs are not well framed at the outset. In particular, ETA appears more vulnerable than QA to ambiguity in scope, poorly articulated needs or changing expectations on the FCDO side. The most important trend here is not isolated process failure, but the way a demand-led model becomes harder to operationalise when users do not know exactly what they need, or when requests sit in grey areas between evaluation, monitoring and broader advisory support.
The evidence also suggests that implementation has not fully caught up with the increasing diversity of products and contexts passing through the service. A recurring issue is that QA tools have not always been sufficiently adapted to non-standard products such as concept notes or PMEL-related outputs. This has meant that the service has implemented a more standardised model than would be beneficial for some product types. While the service can be tailored in practice, this flexibility is not always well understood among users, especially those less familiar with MEL.
A final implementation trend concerns the wider ambitions of the service beyond direct delivery of QA, ETA and EI. The evidence suggests that broader ambitions set out in the inception report were only partially realised. The inception report gave significant weight to learning, communication, MI and strategic support functions; however, the available evidence indicates that these elements were more unevenly implemented and, in some cases, deprioritised in practice.
EQ 4.2: How well integrated are the different services?
The evaluation finds that EQUALS2 services are weakly integrated. Services are typically experienced and delivered as discrete offers rather than as a connected package. At the same time, this limited integration is consistent with the model’s demand-led design and user expectation, rather than representing a shortcoming in implementation. There is no strong direct evidence that a more integrated model would improve effectiveness overall.
Across interviews, QA and ETA are described as stand-alone, and there is little indication of consistent coordination across these services. As such, services are used on a case by case basis rather than as part of a deliberately linked progression through the evaluation cycle. The service lines are not strongly integrated by design or in practice.
Potentially there may be added value in ensuring greater integration between EI and ETA - by identifying and monitoring recurring ETA requests and areas where teams need more information or technical knowledge, these issues could identify topics for needs-focused EIs. This would also support capability building among non-MEL specialists, by using ETA engagement to address underlying evaluative understanding rather than only responding to immediate technical gaps.
EQ 4.3: Are opportunities for cross-learning between the services being fully maximised? If not, how could this be improved?
The evidence strongly suggests that opportunities for cross-learning between EQUALS2 services are not being fully maximised, possibly because the services operate as stand alone components. While learning has occurred, it has tended to be ad hoc and partial, rather than driven by a systematic model of reflection and feedback across services. This shortfall appears to reflect a combination of limited explicit demand for cross-service learning, contextual changes, and capacity constraints, rather than a single underlying cause.
Where learning did happen, it appears to have been more effective when focused on specific thematic or methodological issues than when framed as broader cross-service synthesis. Some Evaluation Insights and thematic work were useful, while attempts at wider cross-learning or meta-analysis were less used[14]. The recurring issue is not necessarily absence of learning products, but the fact that they were not sufficiently targeted or embedded in management processes to maximise their use. This could be linked also to another trend that showed that MI data are not translated systematically into organisational learning. EQUALS2 holds data that could reveal recurrent weaknesses, emerging patterns or areas where targeted support would be useful, but these insights are not yet routinely captured, fed back or acted on. For more information on MI data, please see sub-question 4.4.
[14] While the meta-analysis stands out as comprehensive and technically robust, there is limited evidence on how it has been used to inform organisational learning or management decision-making.
There is also moderate evidence that the Panel of Experts is underused as a source of cross- learning. A recurring theme among EPMs is the absence of feedback on what happens to their input (especially related to QA), how their feedback is used, and what common patterns are emerging across products or themes. This suggests unrealised potential for peer learning and collective reflection. At the same time, these proposals are mostly prospective. They point to plausible improvements but there is not enough evidence to say with confidence how much demand or organisational appetite exists for such mechanism in practice.
Looking forward, opportunities to better maximise cross-learning could include stronger links with Evaluation Insights, if they were to be repurposed for wider learning purposes and external audiences (see EQ3 for further detail on EIs).
EQ 4.4: How could the use of MI data from the service be improved and developed?
The evidence suggests that MI data, and the dashboard in particular, is not being used as much as it could be. While the dashboard and quarterly reports provide useful descriptive information on service activity and reach, the data is not yet being used strategically or analytically. The main areas for improvement concern the way data is presented, and the way it is used in decision-making and learning.
The programme’s inception report stated that the MI data should provide information on ongoing evaluations, be comprehensive and live ‘as possible’, reduce administrative burden through automatic data feeds, and answer key management questions about the evaluation portfolio. The MI data, as currently presented through the Power BI dashboard, provides a thorough and accessible descriptive overview of key trends, enabling the EvU to explore the origin of requests by department, geographic distribution, types of services requested, and how these have changed over time. The dashboard is valuable in communicating overall programme reach and utilisation in a clear and user-friendly way.
However, the current MI offer is less effective as a strategic management and learning tool. There is the potential for using QA and wider service data to identify recurring weaknesses, common thematic gaps or repeated issues that could justify proactive support. For example, if the MI data is showing that ToRs are repeatedly failing in the context and background sections, or if it shows that suppliers lack knowledge on safeguarding, this should trigger reflection and possibly additional support, or the identification of new targeted Evaluation Insights or guidance.
A limitation of the current model is the absence of a clear ‘journey view’ showing how a product moves from initial submission through review and feedback to final output. This makes it difficult to understand to what degree EQUALS2 contributes to quality improvement in different evaluation products for the same evaluation or programme throughout the evaluation lifecycle. Such linked data would provide a clearer picture of whether support is translating into increased quality evaluation outputs over time. The ‘re-review’ tab is a positive example of more outcome-focused analysis as it shows how poorly scoring products changed after revision and includes criterion-level scoring.
EQ 4.5: Are there other ways in which the expertise of the panel could be drawn on to support FCDO evaluative activity?
The evidence shows that the expertise of the EQUALS2 expert panel is highly valued and already central to the delivery model, and primarily delivers assignment-based QA, TA and EI. There are several ways in which it could be drawn on more effectively to support evaluative activity across the FCDO. These potential uses include strategic thought partnership, targeted learning, early-stage advisory support, and reflective synthesis.
Additional value could be realised by engaging panel members in more structured learning. As mentioned in EQ 4.3, the evidence indicates the absence of structured mechanisms through which panel members can reflect on recurring issues, share insights across assignments, or understand how their input is used. Expert Panel Members consistently described this as a gap both for individual learning and for improving overall service effectiveness.
Given the evolving delivery context and an increasing emphasis on non-ODA and policy-focused work, there may be scope to further draw on the panel’s expertise by including individuals able to operate in high-security environments. Greater access to experts holding appropriate security clearance could enhance the quality, and feasibility, of evaluative activity in increasingly sensitive policy areas. While IOD PARC has already taken steps to mitigate this constraint by identifying potential experts who could be supported through the clearance process, evidence from interviews suggests challenges in securing a sufficient pool of cleared experts. This also reflects the invasive nature of the clearance process and the residency requirements for clearance, which can deter participation. However, this is an important consideration to support future FCDO evaluative activity. While the availability of externally cleared experts remains relevant, improving internal deployment of cleared FCDO staff and clearer decision-making around when external clearance is required, emerged as an equally important consideration during sensemaking discussions with the FCDO.
EQ 4.6: How should the model evolve to meet the future needs of FCDO in both the short term (FY 26/27) and the longer-term in any future quality assurance service?
The evidence from the evaluation and key points in the FCDO Evaluation Strategy point to a clear direction: ideally, the current model should retain its operational strengths while evolving to play a more strategic, integrated and forward-looking role within the FCDO’s evaluation function. The strongest and most consistent finding is that flexibility of the model and responsiveness remain valued and should be preserved, but that the model should consider moving beyond a purely demand-led approach to remain aligned with changing organisational needs. The Evaluation Strategy provides a strong foundation for this, as it explicitly calls for a shift toward a mixed model combining demand-led services with greater central direction, alongside increased emphasis on portfolio-level MEL, broader application of evaluative approaches, and improved use of data and technology. This aligns closely with the evaluation evidence, which shows that while the current model responds well to individual requests, it is less effective at identifying and addressing systemic evidence gaps or supporting portfolio-level learning.
A key implication is that the model will need to broaden its scope to continue strengthening the quality of evaluative activity. Both the Evaluation Strategy and evidence gathered in this evaluation point to increasing demand for support that goes beyond conventional development evaluation products, to include PMEL, policy-focused evaluative activity and more iterative forms of learning.
Another consistent theme is the need to strengthen the analytical and learning functions of the model. The strategy emphasises improved management information, knowledge systems and evidence use, while the evaluation highlights current underuse of MI and limited cross-learning.
EQ 4.7: Have there been unintended impacts or consequences of EQUALS2? If so, what are these?
The evidence on unintended impacts is relatively limited. Nonetheless, some patterns emerged, suggesting that the service has generated both positive and negative effects beyond its intended scope.
One of the clearest positive impacts is behavioural change among evaluation suppliers. There are examples of evaluators adjusting their practices in anticipation of QA requirements, including conducting internal reviews aligned with EQUALS2 QA checklists. This suggests that the service may influence quality not only at the point of review but throughout the production process, and this mechanism is an unintended extension of the QA function.
Negative effects are sometimes created by tight timelines and unclear requests. Some examples indicate that the demand-led nature of the service can result in ‘emergency’ use, where limited time and weak scoping reduce the effectiveness of the support provided and increase frustration in the Experts. These issues appear to arise in specific contexts and seem mainly dependent on individual commissioning practices rather than occurring systematically. However, they are sufficiently recurring to be considered as credible and unintended consequences.
A further unintended effect raised by a small number of interviewees relates to potential disadvantages faced by evaluators or evaluation providers based in the Global South. Interviewees noted that organisations with less prior exposure to EQUALS2 may be at a relative disadvantage compared to larger, Global North–based firms that are more familiar with the service, its processes, and its expectations. This was framed as a potential tension with the localisation agenda: firms with strong contextual and local knowledge may be well placed to deliver high‑quality evaluations, but may be less adept at navigating EQUALS2‑related processes and timelines. At the same time, firms with extensive familiarity with EQUALS2 can more readily align their reports, timelines, and processes with its requirements, which can reduce transaction costs and administrative burden for commissioners. While this does not represent a consistent pattern across the evidence base, the fact that it was raised independently by more than one interviewee suggests it merits reflection.

EQ5: Does EQUALS2 offer value for money for FCDO?
Limited financial data has been provided to the evaluators to assess the value for money of the EQUALS2 service. The data provided to the evaluators comprised only the unit cost of each ETA, QA and ETA product, the total number of consultant days spent collectively across each the three product types, and the total programme spend to date. In the absence of suitable benchmarks for a similar service, the evaluators have been able to conduct an internal comparative VfM analysis.
The available data allows for an examination of how resources have been allocated across the three product types (ETA, QA and EI) and the relative cost of generating different outputs. In and of itself, it does not provide evidence of the quality or usefulness of those outputs or the benefits they may have generated in terms of improved evaluative activity (though some qualitative evidence is included based on interview findings and the document review). As a result, the analysis can only offer a partial view of VFM, focussed on economy and internal programme efficiency.
EQ5.1: Is the service run efficiently? Does it contribute to improving quality? Is the service/panel priced properly compared to the wider market?
This section has been redacted from publication due to commercial sensitivity
EQ5.2: Are there aspects of the service that offer greater VfM than others?
On the available evidence, QA products appear to offer relatively better VfM on the cost and productivity side than other elements of the service. ETA products are clearly the most resource‑intensive and therefore need the strongest justification, but evidence from stakeholder interviews places high value on these activities and a high-degree of additionality, i.e. many of the ETA activities that produced high quality evaluative outputs (ToCs, evaluability assessments, outcome mapping etc.) would not have happened at all in the absence of the EQUALS2 service, which could have led to poorer quality evaluation outcomes without them.
EQ5.3: How could the model be developed to increase VfM of the service?
If the FCDO is seeking to reduce overall cost of the service (Economy) one possible option would be to make greater use of in-house evaluation expertise in delivering at least some of the services provided by EQUALS2. This would also align with the newly published FCDO Evaluation Strategy 2026 which highlights a shift in focus to make “Wider use of internal evaluation expertise across the FCDO’s portfolio”[15].
[15] Please see the FCDO Evaluation Strategy 2026-2030, available at: https://www.gov.uk/government/publications/fcdo-evaluation-strategy-2026-to-2030/fcdo-evaluation-strategy-2026-to-2030
Given the breadth of evaluation expertise across the FCDO’s cadre of evaluation advisors, there is potential to utilise this more to deliver aspects of the EQUALS service, or to consider a hybrid model where FCDO MEL advisors are paired with an EPM for particular assignments to reduce external cost and make better use of inhouse evaluation expertise. However, careful consideration would need to be given as to whether MEL advisors have the capacity to absorb more work among their existing responsibilities. If such capacity exists, there is potential to seek to deploy evaluation advisors to undertake some ETA and EI activity where their skills and expertise matches the required demand. It would be more problematic to deploy in-house expertise for QA activity due to possible conflicts of interest and independence issues that could arise, given evaluation advisors’ day-to-day roles in supporting evaluative activity across the FCDO portfolio.
In terms of adding value to the service, some evaluation providers have indicated that they would welcome more direct engagement with QA reviewers to better explain their work and evaluation choices, and to discuss feedback and possible improvements to their work. At present most evaluation providers see only summaries of the feedback, or in many cases, the full completed QA template. Facilitating more direct engagement between QA reviewers and providers could potentially add greater value (Effectiveness) to the QA process, and overcome concerns that at times the QA does not reflect the complexity of programmes. This would also allow discussion when providers disagree with aspects of the QA feedback provided.
However, the added value of this needs to be considered against the additional cost that would be involved (greater number of expert panel member days to complete the feedback) and the additional time that would be required to complete the QA process by adding this extra step in the process. Some panel members may also be unwilling to do so directly, as many appreciate the anonymity that the current process ensures.
Finally, it is notable that the MI dashboard information does not include any financial information regarding the implementation of the programme. For transparency and tracking of a demand-led programme, it would be beneficial to include some financial metrics within the MI dashboard – including total spend by product type, average unit costs of products, and the rolling share of the programme budget spent across the different product types.

Analysis and interpretation
This section synthesises evidence across the evaluation findings. It focuses on strength and plausibility of causal pathways rather than on attribution, recognising that changes in evaluation quality and use within the FCDO are shaped by multiple interacting factors. The analysis draws together qualitative evidence from interviews, document review and case studies, alongside the strength-of-evidence applied to each element of the ToC (see Table 6)[16].
[16] These criteria was developed by the evaluation team specifically for this evaluation, to ensure it was adapted to the context.
Table 6: Strength of evidence criteria for Theory of Change causal pathways.
Level	Definition
1: Weak	Sporadically mentioned in either interviews, surveys or documents[17]
2: Medium	Consistently mentioned through at least one relevant source
3. Strong	A consistently verified trend through triangulation of all relevant sources
[17] Relevant source interpreted as a source of evidence utilised across this evaluation which could verify a particular change pathway. For example, surveys with evaluation providers are not able to verify change pathways related to TA or EIs, as they could only be verified through interviews and document review. On the other hand, the survey, interviews and desk review could all verify the change pathways related to QA. As such, a consistently verified TA trend verified across interviews and document review, and a consistently verified QA trend verified across interviews, document review and surveys could both score a level 3.

Figure 7 shows the updated Theory of Change with a strength of evidence level mapped onto each causal pathway. The ratings are based on evidence that the evaluation team had access to in the course of conducting the evaluation.
The evidence presented in the Findings section shows a clear consistent pattern: EQUALS2 contributes most strongly where it is embedded in formal decision-making and accountability processes, and contributes least where it relies on voluntary uptake or indirect influence. This distinction helps explain why the QA pathway is supported by Level 3 (strong) evidence across all stages of the ToC, while the ETA and EI pathways show weakening causal links as they move from outputs to behaviour change and outcomes. Implementation quality, however, is not the issue. Across all three services, activities are delivered largely as intended and EQUALS2 outputs are generally perceived as high quality. The point at which pathways diverge is the transition from outputs to behaviour change. Where the transition is structurally supported through authority or mandatory processes, behaviour change has been strongly observed. Where it is not, behaviour change becomes partial, contingent or weakly evidenced.
This system-level lens is essential to interpreting the ToC as differences in impact reflect differences in causal leverage, not in effort or technical quality.
At the impact level (FCDO shares and uses high-quality evaluative products), the evaluation does not find sufficient evidence to support a strong or generalised claim of contribution. There are isolated examples where improved quality or visibility has plausibly fed into learning or decision-making, but these are not systematic. Use appears to be dependent on factors such as leadership engagement, timing relative to decision windows, and the capacity of teams to act on findings, none of which are consistently influenced by EQUALS2. The evidence therefore supports a qualified contribution claim: EQUALS2 strengthens some of the conditions necessary for use, especially through QA (by improving quality and credibility) and ETA (by strengthening evaluative thinking), but it does not reliably bridge the gap between improved products and sustained use. This long causal distance explains why evidence is weakest at impact level and why the ToC statement should be interpreted as aspirational rather than demonstrably realised.
The outcome ‘FCDO publishes credible, rigorous and ethical evaluations’ is the most strongly supported outcome in the ToC, and this alignment is driven mostly by the QA pathway. Across data sources, QA demonstrably improved quality of evaluation products through a clear and repeatable mechanism: independent expert feedback, backed by mandatory requirements for publication created both the authority and incentives for suppliers and commissioners to revise products. These revisions go beyond cosmetic compliance and frequently address core issues of evaluability, analytical coherence and usability, especially when QA is applied early in the evaluation cycle.
The outcome ‘FCDO delivers high quality evaluative activity’, primarily associated with the ETA pathway, is more weakly supported. There is strong evidence that ETA activities and outputs are delivered and valued, and that they fill important capability and opportunity gaps, especially in contexts of constrained MEL resources. ETA clearly enables better evaluative thinking at specific points in time. However, evidence that this consistently translates into sustained behaviour change, such as the routine application of ETA guidance or enduring changes to evaluative practice, is moderate. The synthesis across findings shows that ETA’s influence is highly conditional: where ETA is embedded in ongoing processes, delivered by trusted experts familiar with the context and aligned with concrete decisions, its contribution is evident. Where ETA is delivered as a stand-alone advisory support, or where teams lack ownership or follow-through, the causal chain weakens. This suggests that while the capability and opportunity changes are key mechanisms, motivation and accountability are essential for converting these into lasting change.
The outcome related to greater visibility of evaluative activity, primarily associated with EI pathway, is weakly evidenced. While Evaluation Insights are produced and sometimes perceived as useful, the evaluation consistently finds limited awareness, unclear relevance for many users and weak evidence of use. At the output level, access, awareness and perceived value are fragile, and at the behaviour change level they largely break down. The synthesis across findings indicates that the EI pathway rests on an assumption that producing relevant insights will lead to uptake and use. This assumption is not supported by the evidence, and use, instead, occurs only when EIs are tightly aligned with organisational priorities and clearly linked to application. In the absence of these conditions, EIs tend to inform reflection rather than practice.
Bridging the three pathways together, the evaluation findings point to a clear pattern that EQUALS2 is most effective when it services are structurally embedded in decision-making systems, and least effective when they depend on diffusion of knowledge or voluntary behaviour change. QA is effective because it sits inside formal systems of accountability. ETA is effective when closely coupled to decisions and relationships, but not when delivered in isolation. EI struggle because they lack both authority and systematic pathways to application. These differences explain why similar levels of delivery quality result in very different outcomes across pathways.
Limitations to the analysis: while the ToC clearly describes intended causal logic, it treats all pathways as if they operate through similar mechanisms. In practice, their mechanisms, and therefore their reliability, are different. Then, the evaluation relies primarily on qualitative data, case studies and documentary review, with limited ability to track longer‑term behaviour change or use. As such, claims are strongest at the level of activities, outputs and QA‑related outcomes, and weakest at the level of portfolio‑wide outcomes and impact. The structured evidence ratings make these limits explicit and reinforce the conclusion that EQUALS2 makes a meaningful but uneven contribution, shaped as much by system design as by service quality.

Figure 7: Updated ToC with strength of evaluative evidence integrated
Conclusions
This evaluation explored the performance, value and contribution of EQUALS2 to improving the quality, visibility and use of evaluative activity across FCDO, while also generating learning to inform the future evolution of the service. Taken together, EQUALS2 has made a meaningful but uneven contribution to evaluation quality within FCDO: ETA shows conditional and context-specific contribution; QA shows consistently strong contribution; and EIs show limited contribution beyond specific, well-defined use cases.
The contribution of ETA is nuanced. ETA is highly valued and clearly relevant, and it makes an important enabling contribution to evaluative activity within the FCDO, particularly by addressing gaps in capacity and resourcing at critical times. However, the evidence does not support a strong or generalised claim that ETA consistently leads to sustained changes in how evaluative activity is designed or implemented over time. Instead, ETA’s influence is episodic and context-dependent. Therefore, ETA is best understood as a situational and catalytic intervention: valuable and often necessary, but not sufficient to influence lasting behaviour change at scale. The evaluation found limited evidence that the EI service has achieved its intended contribution to organisational learning and improved evaluative practice across FCDO. While some products are regarded as technically sound, awareness and use remain patchy.
The QA service has been the strongest and most consistently effective element of EQUALS2. The weight and consistency of evidence allow a firm conclusion that QA has contributed to improved quality of evaluation products across the FCDO portfolio. This contribution is evidenced across multiple products, stages of the evaluation cycle and stakeholder groups, and is not dependent on isolated examples. Importantly, the influence of QA extends beyond technical refinement: it provides a legitimising and enabling role for commissioners, allowing them to challenge suppliers and enforce standards in ways that would otherwise be difficult. While QA does not, on its own, ensure that evaluations are used, the evaluation concludes that it reliably strengthens the credibility and publishability of evaluations and therefore represents a core pillar of EQUALS2 overall value.
EIs seem to have been taken up where they were linked to clearly articulated priorities and targeted intended audience, rather than to the EI modality itself. As such, the EI component, as currently constituted, represents the weakest element of the EQUALS2 model, with a gap between ambition and evidence contribution. This does not imply that EIs products lack intrinsic value, but rather that the pathway from insight generation to applied learning is insufficiently supported.
From a delivery and model perspective, EQUALS2 has been implemented largely as intended and responds effectively to demand within its current design. The helpdesk model is generally understood and valued, and delivery has shown flexibility in practice. However, opportunities to use MI and panel expertise more strategically and in a learning-oriented way, are not fully realised. The findings suggest that while the current model is functional and responsive, it is less effective as a learning and strategic support mechanism.
In terms of VfM, the available evidence points to the fact that QA offers relatively strong value due to its consistent delivery, moderate cost per output and quality gains. ETA is more resource-intensive and shows greater variation in cost and scale, but qualitative evidence indicates high perceived value and additionality, particularly where ETA enables work that would not otherwise occur. Evidence on the VfM of EI is more limited. Given data constraints, conclusions on the VfM should be treated with caution, and are strongest on efficiency and economy.
In summary, the evaluation concludes that EQUALS2 is a valuable and credible service that has strengthened evaluation quality within the FCDO, particularly through QA, while making more conditional and uneven contributions through ETA and EI. Its future effectiveness will depend less on expanding technical delivery and more on strengthening the conditions that link support to decision-making, accountability and use. EQUALS2’s contribution to quality evaluative activity is strongest where services are embedded within formal accountability and quality systems, and weaker where they depend on voluntary uptake. This pattern does not imply that services should be more mandatory within a decentralised system, but highlights the structural conditions under which effectiveness has been observed.
Recommendations
General recommendations
EvU should have a strategic discussion on the future priorities of EQUALS2. The evaluation highlighted strengths and bottlenecks of the three core functions of EQUALS2. However, future choices about the service would benefit from clearer prioritisation in terms of what would be feasible from an implementation point of view, but also practical priorities for the FCDO. A practical next step would be for the FCDO and IOD PARC to hold a structured discussion during the remaining contract period to agree the relative priority of these functions and the implications for service design.
This should also inform a clearer statement of purpose, service offer and delivery expectations for any future iteration of EQUALS2. As part of this discussion, FCDO should also consider whether some ETA and Evaluation functions could, where appropriate capacity exist, make greater use of in-house evaluation expertise, while maintaining independent external QA. This also aligns with the FCDO Evaluation Strategy’s emphasis on wider use of internal evaluation expertise and a more strategically directed evaluation function.
- EQUALS2 should place greater emphasis on building FCDO’s capability to undertake evaluative thinking and lighter-touch evaluative work, particularly in areas affected by ODA budget reductions. As formal evaluations become less feasible in some parts of the portfolio, the FCDO is likely to rely more on internally-led evaluative products, portfolio-level work and smaller-scale evaluative exercises. In that context, ETA should not only continue to provide direct technical input, but also more deliberately support capability-building so that FCDO can commission, interpret and, where appropriate, undertake this work to a stronger standard itself. Over time this could support a more sustainable model in which internal evaluation expertise is used more deliberately for lighter-touch evaluative activity and selected technical support functions. This includes supporting staff to act as intelligent customers of evaluation and making more deliberate and strategic use of the Panel of Experts where this adds value. This recommendation is also in line with the FCDO Evaluation’s strategy emphasis on wider use of internal expertise, evaluative thinking and building staff capability to be intelligent customers and users of evaluation.
- EQUALS2 should make more structured use of service-wide learning during the remainder of the contract, and FCDO should decide whether this should become a core feature of any future model. The inception design envisaged more learning, methodological reflection and feedback loops than the evaluation found in practice. During the remaining contract period, the implementer (IOD PARC) should revisit some of these intended functions, including sharing key trends from QA and ETA, producing shorter methodological or thematic learning outputs, and feeding this intelligence back to panel members. Looking ahead, the FCDO should then decide whether such learning and capability-building functions should become an explicit part of any future programme design rather than remaining implicit or optional.
- EvU/FCDO should clarify how ‘quality’ is defined and assessed in the current and future evaluation system, particularly as evaluative activity diversifies. Having a commonly understood definition of ‘quality’ is especially important as the portfolio shifts toward PMEL, non-ODA work, lighter-touch evaluative exercises, and other forms of evaluative thinking. FCDO should therefore revisit the current conceptualisation of quality and fitness for purpose across different kinds of evaluative activity.
ETA-related recommendations
- EvU and IOD PARC should consider reviewing how ETA is expected to operate with regards to PMEL – and how it can and should support PMEL - whether conducted in-house or via contracted suppliers. There is a need to define where PMEL is intended to replace, absorb or continue to require ETA-type support. The evaluation points to a level of uncertainty about the relationship between ETA and PMEL. In some cases, it is possible that externally contracted PMEL may absorb some functions of ETA, particularly around results frameworks, theories of change, and demand-led technical support. FCDO and IOD PARC should consider how best EQUALS can support PMEL and in what circumstances to avoid duplication of effort.
- EvU should consider greater focus on improving how non-ODA and non-traditional users understand and access the existing ETA offer.. The evaluation supports the need for technical assistance that is better aligned to the growing range of evaluative activity outside traditional ODA programme contexts, particularly in areas such as diplomacy, influencing, security-related work and other discrete interventions. This should include reviewing how technical assistance is framed and communicated to non-ODA teams, so that support is not presented only through language associated with traditional development programming where that is likely to be off-putting or misleading. It should also include continuing to broaden panel expertise relevant to these areas. On security-cleared expertise, FCDO should also strengthen mechanisms for identifying and deploying in-house expertise with appropriate security clearance, alongside maintaining access to external cleared experts through EQUALS where required.
- EQUALS 2 should strengthen guidance at the point of requests so that FCDO staff can make better informed ETA requests, particularly on likely LoE and the type of support required. The evidence suggests that some EQUALS Users, especially those without strong MEL backgrounds, lack confidence in specifying the level of effort needed for common ETA requests. The current process does allow requests to be refined through discussion, so the gap is not the absence of support, but the lack of clearer starting guidance. EQUALS2 should therefore strengthen the guidance built into the request process itself. This could include clearer prompts to helps users distinguish between request types, and indicative questions that help the helpdesk identify whether a request is likely to require lighter-touch support, more intensive technical assistance, or another form of engagement. Such approach would support less experienced Users while maintaining the flexibility needed to respond to varied contexts.

QA-related recommendations
EvU and IOD PARC should consider developing a more proportionate framework that maintains consistency while better marching the types, scale and risk profile of the evaluative product. The evidence and feedback collected from different stakeholders supports a more proportionate approach to QA, particularly for smaller evaluations and products that are not conventional formal evaluations. To make this operational. FCDO and IOD PARC could consider a small number of practical changes rather than a complete redesign of many templates.
A workable approach would be to test a two-tier model consisting of a full QA route and a lighter-touch QA route. The full route would continue to apply to larger, higher-risk, or more formal evaluations. The lighter-touch route would apply to smaller or less complex products, while still retaining a documented quality check. To support this, FCDO and IOD PARC could develop clear criteria for deciding which route applies. These criteria could include the nature of the product, the scale or complexity of the evaluation, and indicative budget ranges where appropriate. The evidence is not strong enough to recommend fixed thresholds, so these should be tested rather than assumed.
This triage could be built into the helpdesk or request process through a decision tree or set of structured prompts. These would help users and the helpdesk determine, at the point of request, whether the product is a formal evaluation or another type of evaluative product, whether it is relatively light-touch, and which QA route is most appropriate.
Whichever route is used, the framework should retain a core set of minimum quality standards, so that greater flexibility does not result in loss of consistency. At the same time, the lighter-touch route should reduce unnecessary requirements for products where full QA would be disproportionate.
EvU and IOD PARC should improve guidance on when to initiate QA and how to build enough time into the process for feedback to be used meaningfully. The evaluation found repeated concerns, including from providers, that QA sometimes arrives too late to support meaningful revision. The most practical response is therefore to strengthen communication and guidance across FCDO on when QA should be requested at different stages of the evaluation cycle and how much time should be built in for review, reflection, revision and resubmission. This could be incorporated into user guidance, communications and refresher messaging rather than treated only as a compliance issue for individual teams. In addition, EQUALS should clarify when limited follow-up discussion on QA feedback may be appropriate, particularly for complex cases where written comments alone may not be sufficient, while preserving reviewer independence and anonymity. This recommendation is consistent with the Evaluation Strategy’s emphasis on embedding evaluation support at key moments in the planning and delivery life cycle, in good time to influence outputs.
EI-related recommendations
- EvU should review the commissioning model for Evaluation Insights so that topics, intended users and outputs are defined more clearly at the outset and aligned more explicitly to demand and ultimate utility. The evaluation suggests that Evaluation Insights are most useful where there is clear ownership, a defined use case, and an identifiable audience. EvU should firstly clarify who the EI intended users should be until the end of the programme, and a revised commissioning process could involve more structured engagement with intended users when selecting topics, clearer articulation of the decisions or learning needs the insight is meant to support, and prioritisation of topics based on strategic relevance and evidence gaps rather than ad hoc selection alone. This would also respond to the Evaluation Strategy’s emphasis on identifying evidence blind spots, improving the ability to target evaluations where they are most needed, and supporting more centrally directed evidence generation in priority areas.
- EvU and EQUALS 2 should take into consideration diversifying EI outputs beyond standalone reports and place more emphasis on practical dissemination and use. The evaluation suggests that Evaluation Insights are less effective when they remain as static reports and more useful when they are linked to discussion, tools, communities of practice, or facilitated learning. The recommendation is therefore not simply to produce more outputs, but to plan dissemination and use at commissioning stage and to choose formats accordingly. Depending on the topic and audience, this could include shorter actionable products, workshops, masterclasses, targeted briefings, or topic-led communities of practice. This could also contribute to increased capability to use evaluation evidence in practice.

List of Annexes
Annex 1: EQUALS 2 Evaluation ToR
Annex 2: EQM
Annex 3: Interview guides
Annex 4: Survey of Evaluation Providers
Annex 5: Quality rubrics
Annex 6: List of interviewees (anonymised)
Annex 7: List of documents consulted