## EQUALS 2 Logframe
Please refer to the PrOF Guide for advice on completing the various fields in the logframe.
Smart Guide
PROJECT TITLE: | Evaluation Quality Assurance and Learning Service 2 (EQUALS 2) 301050
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26)
FCDO produces, shares and uses high quality evaluative products across all its work. | If all targets for the outcomes indicators are met, then this indicates that the programme is having the proposed impact. | Planned |  | Meet outcome indicators 1 and 2 | Meet outcome indicators 1 and 2 | Meet outcome indicators 1 and 2 | Meet outcome indicators 1 and 2
|  | Achieved |  | Almost met | Almost met | Almost Met
Source
Outcome indicator results
| Impact Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 |  | Target (25/26)
| Case studies demonstrating EQUALS work contributing to improved evaluation across the department. | Planned |  | Developed process, defining requirements for each of the three context, (embedded, transparent and instrumental) | 5 |  | Post hoc assessment of sample evaluations that have been through the EQUALS process.
|  | Achieved |  |  |  | Met
Source
Case studies provided by EQUALS (short survey and follow up interviews using the ESPF by EQUALS on an annual basis following up all evaluations that have been submitted to EQUALS)
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26) | Assumptions
FCDO publishes credible, rigorous and ethical evaluations | % of FCDO Terms of Reference rated by EQUALS Quality Assurers as unsatisfactory that are re-rated at fair or above | Planned |  | 50% | 60% | 60% | 60% | FCDO and OGDs understand the importance of QA and has the capacity to benefit from external QA. Quality means; relevant, rigorously designed and implemented, ethical, well placed for use and influence and good VfM. EvU has the data and capacity to monitor that all FCDO evaluations are being QA'd at relevant points. Those involved with evaluations in FCDO and OGDs have the information and incentives to use EQUALS to improve their evaluations.
|  | Achieved |  | 40% | 50% | 100%
Source
EQUALS MI data
| Outcome Indicator 2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26)
| % of FCDO Baseline and Inception reports rated by EQUALS Quality Assurers as unsatisfactory that are re-rated at good or excellent | Planned |  | n/a | n/a | 60% | 60%
|  | Achieved |  | n/a | n/a | 100%
Source
|  |  | EQUALS MI data |  | EQUALS MI data
| Outcome Indicator 3 |  |  | Milestone 1 |  | Milestone 3 | Target (25/26)
| % of FCDO midline, endline, final reports rated by EQUALS Quality Assurers as unsatisfactory that are re-rated at good or excellent | Planned |  | n/a | 90% | 90% | 90%
|  | Achieved |  | n/a | 50% | 20%
Source
|  |  | EQUALS MI data |  | EQUALS MI data
| Outcome Indicator 4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26)
| % of EQUALS users perceiving that the expertise received through EQUALS is improving the overall quality of evaluation products or processes | Planned |  | 85% | 90% | 90% | 90%
|  | Achieved |  | 100% | 96% | 85%
Source
User feedback survey and focus groups
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26) | Assumptions
EQUALS provide high quality responses to quality assurance requests within set deadlines | % of QA requests delivered by EQUALS within set deadlines (within ten days) | Planned |  | 94% | 94% | 94% | 94% | FCDO staff don't avoid EQUALS or publications (e.g. downgrade evaluations to review). QA provided by EQUALS reviewers is high quality, timely and practical. FCDO staff have the capacity to use the review to improve the product.
|  | Achieved |  | 93% | 93% | 94%
Source:
EQUALS KPI data
| Output Indicator 1.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26)
| % Staff rate the quality of service as excellent or good (and consideration of other qualitative feedback) | Planned |  | 80% | 90% | 90% | 90%
|  | Achieved |  | 100% | 96% | 96%
Source:
FCDO issued user survey
IMPACT WEIGHTING 40% | Output Indicator 1.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26)
| % of QAs that are quality checked by EQUALS management | Planned | 20% | 20% | 20% | 20% | 20%
|  | Achieved |  | 24% | 24% | 21%
Source:
EQUALS KPI data
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26) | Assumptions
EQUALS provides expert technical advice (ETA) within agreed deadlines | % of technical advice requests completed within set deadlines (set by mutual agreement on case by case basis) | Planned |  | 90% | 94% | 94% | 94%
|  | Achieved |  | 100% | 100% | 100%
Source
EQUALS KPI data
| Output Indicator 2.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26)
| % Staff rate the quality of service as excellent or good (and consideration of other qualitative feedback) | Planned |  | 80% | 90% | 90% | 90%
|  | Achieved |  | 100% | 96% | 97%
Source
Source: FCDO issued user survey
IMPACT WEIGHTING 40%
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26) | Assumptions
Effective information capture and management of EQUALS evaluation data | MIS [function] produces data related to evaluation in a easy to access format on demand | Planned |  | Maintenance of MIS and addressing changing needs as appropriate | Maintenance of MIS and addressing changing needs as appropriate | Maintenance of MIS and addressing changing needs as appropriate | Maintenance of MIS and addressing changing needs as appropriate
|  | Achieved |  | Met | Met | Met
Source
| Output Indicator 3.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26)
| MIS [utility] is used by EvU in [annual, quarterly] reports | Planned |  | MIS is used to present information to seniors | MIS is used to present information to seniors | MIS is used to present information to seniors | MIS is used to present information to seniors
|  | Achieved |  | Almost met | Almost met | Almost Met
Source
PM and PRO to keep records of use
IMPACT WEIGHTING 10%
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26) | Assumptions
EQUALS helps FCDO to learn from its evaluative activity | Methodologies - learning is disseminated based on feedback forms and MIS | Planned |  | Meta-analysis report drawing on the learning from feedback forms and MIS | Meta-analysis report drawing on the learning from feedback forms and MIS | Meta-analysis report drawing on the learning from feedback forms and MIS | Light touch meta-analysis review drawing on learning from freedback forms and MIS.
|  | Achieved |  | Partially met | Partially met | Almost Met
Source
| Output Indicator 4.2 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26)
| Evaluation Insights - Lessons pertaining to pre-identified learning themes (as per concept notes)are harvested and shared (presentation, paper or slide deck) | Planned |  | 2 EIs shared with pre-identified audiences | 2 EIs shared with pre-identified audiences | 2 EIs shared with pre-identified audiences | n/a
|  | Achieved |  | Met | Met | Met
Source
Quarterly reports
| Output Indicator 4.3 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26)
| Learning events delivered based on the learning harvesting activities conducted by EQUALS | Planned |  | 1 event for panel members 1 event for EvU 1 event for wider audience | 1 event for panel members 1 event for EvU 1 event for wider audience | 1 event for panel members 1 event for EvU 1 event for wider audience | 1 event for panel 2 events for wider audiences
|  | Achieved |  | Not met | Almost met | Almost Met
Source
Quarterly reports
| Output Indicator 4.4 |  | Baseline | Milestone 1 | Milestone 2 | Milestone 3 | Target (25/26)
| Technical assistance provided to support the delivery of key components of the FCDO Evaluation Strategy 2025 - 2030 | Planned |  | N/A | N/A | N/A | 2 trainings delivered and/or guidance documents developed and shared with EvU.
|  | Achieved |  | N/A | N/A | N/A
Source
Quarterly reports
IMPACT WEIGHTING 10%
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2018-01-01
1 | Outcome Indicator 1 | Indicator split into two indicators from "% of FCDO evaluation products rated by EQUALS Quality Assurers as unsatisfactory that are re-rated at good or excellent " to "% of FCDO Terms of Reference, Baseline and Inception reports rated by EQUALS Quality Assurers as unsatisfactory that are re-rated at good or excellent" and "% of FCDO midline, endline, final reports rated by EQUALS Quality Assurers as unsatisfactory that are re-rated at fair or above" |  | 2023-05-01
2 | Outcome Indicator 2 | Became outcome indicator 3 |  | 2023-05-01
3 | Outcome Indicator 1 | Indicator split into two indicators from "% of FCDO Terms of Reference, Baseline and Inception reports rated by EQUALS Quality Assurers as unsatisfactory that are re-rated at good or excellent" to "% of FCDO Terms of Reference rated by EQUALS Quality Assurers as unsatisfactory that are re-rated at fair or above" and "FCDO Baseline and Inception reports rated by EQUALS Quality Assurers as unsatisfactory that are re-rated at good or excellent" |  | 2023-08-01
4 | Outcome Indicator 3 | Indicator changed from "% of FCDO midline, endline, final reports rated by EQUALS Quality Assurers as unsatisfactory that are re-rated at fair or above" to "% of FCDO midline, endline, final reports rated by EQUALS Quality Assurers as unsatisfactory that are re-rated at good or above" |  | 2023-08-01
5 | Outcome indicator 4.4 | Added new indicator :Technical assistance provided to support the delivery of key components of the FCDO Evaluation Strategy 2025 - 2030 |  | 2025-06-01
6 | Impact indicator 2 | Changed wording to reflect new direction :Case studies demonstrating EQUALS work contributing to improved evaluation across the department. |  | 2025-06-01
7 |  |  |  | 2025-06-01
8
9
10

## Guidance Notes
Smart Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
A meaningful, easily understood (plain English) Project Title.
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking?
OUTCOME
The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Millenium Development Goals (MDGs) or Climate Change.
An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR). Ongoing monitoring of progress against outcome milestones should still take place as an assessment of whether you expect to achieve the Outcome by the end of the programme will be included in Annual Reviews.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear.
Progress against Output milestones and results achieved will be assessed and scored during Annual Reviews and the Project Completion Review.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
l | Promote a more considered approach to the choice of Outputs at project design stage; and
l | Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of DFID’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual DFID Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
l | Specific – what will be measured? And how?
l | Measurable - data can be collected
l | Relevant - to the results chain
l | Useful – for management decision making
l | Does not include any element of the target
l | Can be disaggregated if relevant
l | Good mix of qualitative and quantitative
l | Already defined - if relevant include indicators which towards the DRF / OP / ICF KPIs / MDGs.
l | Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Results Chain and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / MIS.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.