## Annual Review Template

Title: Education Quality Improvement Programme in Bangladesh (EQUIP-B)
Programme Value £ (full life): £16 million		Review date: 01 November 2025
Programme Code: [AMP ID#] 301052	AMP start date: 01/11/2021	AMP end date: 14/03/2027

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	B	A	A	A
Risk Rating	Major	Moderate	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/90000714.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005320.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]
1. The Education Quality Improvement Programme in Bangladesh (EQUIP-B) is a £16 million bilateral initiative spanning six years. It aims to enhance the quality of primary and secondary education through needs-based, targeted technical assistance (TA). EQUIP-B supports both the Ministry of Primary and Mass Education (MoPME) and the Ministry of Education (MoE) in strengthening the efficiency and effectiveness of the education system, with a focus on improving learning outcomes and increasing girls’ retention through to secondary education. The programme is aligned with planned reforms under the national primary and secondary education programmes.
2. Despite notable progress in access, learning outcomes are alarmingly low and dropout rates remain high and. 16% of enrolled children dropped out of primary school, while 33% leave secondary education prematurely. Approximately fifty per cent of students attain Grade 5-level competencies in Bangla, and only thirty per cent do so in Mathematics. In 2022, proficiency at the secondary level was recorded at twenty-nine per cent in Mathematics and sixty-six per cent in Language, marking a considerable decline since 2019.
3. To improve learning outcome and girls’ retention in education, EQUIP-B’s key focus includes enhancing teachers’ skills, learning assessment, creating girl-friendly school environments, developing and utilising integrated data management systems, climate smart education, evidence-based policy advocacy, and supporting the design of national education programmes. EQUIP-B is a needs-based, responsive technical assistance programme implemented by UNICEF and the World Bank (WB). Both implementing partners (IPs) have a strong track record in the education sector and work closely with the Government of Bangladesh (GoB). The World Bank provides TA for the secondary education sector, while UNICEF supports both primary and secondary education.
4. EQUIP-B is aligned with UK development policy and the priorities outlined in the International Development Strategy (IDS), the FCDO Women and Girls (W&G) Strategy, commitments from the Transforming Education Summit, the Girls’ Education Action Plan, and the Indo-Pacific Tilt papers. The programme aims to improve access to safe, high-quality education, with a particular emphasis on girls. Aligning with FCDO 2030, EQUIP-B embodies the modern development approach shifting to knowledge-based partnership, focusing on TA, policy influence, and system strengthening.
5. Since its inception, EQUIP-B has adapted to a dynamic operating environment. Initial efforts centred on post-COVID recovery, later transitioning towards long-term education reform. However, political disruptions—including the 2023 election cycle, civil unrest, and changes in leadership across ministries and agencies—slowed progress and diverted attention from sector priorities. With the interim government prioritising electoral reform ahead of the 2026 elections, key policy decisions remain on hold. Despite these challenges, EQUIP-B has consistently delivered high-impact technical assistance, strengthened institutional frameworks, and remained a trusted partner in advancing systemic education reform.
6. This AR measures progress and results for EQUIP-B’s fourth year of implementation. It drew on technical expertise of a CBS Education Adviser and Programme Managers within the Human Capital team; desk review of programme reports, field visits to engage with beneficiaries and monitor quality, and cross-cutting advisory support.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]
1. This review scored outputs 1 to 4 based on the progress made against the milestones. Consequently, the overall score of A reflects that the targets have been Met.
2. EQUIP-B has delivered most of the TAs planned for this reporting period. In Primary Education, key achievements include special education needs training to 120,000 teachers, full nationwide roll out of Integrated Primary Education Management Information System (IPEMIS), publish annual census and sector performance reports, and influence the design of 5th primary education sector programme (PEDP5) by using evidence generated through studies and need-based TA support.
3. The key achievements in secondary include mainstreaming of teachers’ guidelines and manuals on formative assessment and remediation, subject pedagogy for blended learning, climate change mitigation and adaptation, school leadership, school-related gender-based violence (SRGBV) prevention, and adolescent mental wellbeing. Other achievements include piloting of micro-skills programming[1] for life and employability skills, gamified learning[2] on Adolescents’ Sexual Reproductive Health (ASRH), cyber safety and well-being, learning enhancement strategy, integrated training and learning management system (ITLMS)[3], and cyber safety and digital literacy[4] package.
  [1] Micro skill aims to promote competency-based, experiential learning focused on life skills and future employability, particularly for adolescent girls.
  [2] Gamified learning is an educational approach that incorporates game elements into learning environments to make the process more engaging, motivating, and effective.
  [3] ITLMS is a self-paced, interactive training for teachers to use through an online platform
  [4] Digital literacy educates how digital tools work, use responsibly, and engage with digital content thoughtfully
4. EQUIP-B is contributing to modernising education system management, improving governance, and fostering evidence-based policymaking to advance national education priorities. Operating within an interim political landscape, FCDO jointly with UNICEF and World Bank, by leveraging its Education Local Consultative Group Co-Chair role, are advocating for long-term systemic reforms that uphold children’s right to inclusive, quality education.
5. EQUIP-B has been instrumental in shaping PEDP5 by helping the government and development partners identify key reforms like foundational learning and pre-service teacher education. This groundwork has led to initial investment commitments from the World Bank and GPE. With continued FCDO support, EQUIP-B is well-positioned to influence future investments by WB, ADB, and GPE ensuring alignment with national priorities and global best practices.
6. The evolving political economy context has delayed the implementation of a few TAs. However, there has been significant progress in those areas in the meantime through effective follow-up and adherence to the flexible approach suggested in the Political Economy Analysis (PEA) jointly commissioned by FCDO with the IPs.

Major lessons learned [1/2 page]
1. Flexibility is essential. Technical assistance (TA) must remain adaptable to evolving government priorities, political shifts, reshuffling of key senior bureaucrats, and emerging requests. For example, the national student assessment has been shifted twice to adjust with government’s priorities. Hence, continuous engagement and consultation with ministries, directorates, and agencies ensures alignment with changing needs and enhances the relevance of TA support.
2. Political fragility and shifts in prioritisation affect implementation. Frequent changes in leadership and policy direction require a responsive and flexible approach to achieve intended outcomes. Also, government prioritisation can accelerate or delay activities, necessitating a dynamic pace of implementation that supports sector integration. For example, the programme needed to deprioritise the development of social behaviour change and communication strategy (SBCC) but prioritise the design and operationalisation of integrated learning and management system for teachers’ professional development.
3. Education reform demands long-term commitment: Technical reforms, require phased implementation and consensus-building, often competing with short-term political agendas. For example, despite the government’s overall recognition of the relevance and merit of TPDF and online training, there are debates within the government about the way it can be integrated. A thorough understanding of the political economy needs to be combined with well-timed engagement in advocating such policy reforms.
4. Advocacy remains vital: Decision-makers may lack strategic vision or technical understanding, putting sustained progress at risk. At the same time, systemic education reform is inherently slow, demanding consensus across diverse actors and phased, adaptive implementation. FCDO and implementing partners play a key role in incorporating key reforms such as pre-service teacher education and foundational learning in the design of 5th primary education development programme (PEDP5) through persistent engagement across government layers.
5. Depoliticization of education: Reducing political interference in educational matters proven to be essential for fair and effective governance. A genuine and robust commitment from the political leadership is crucial to ensure depoliticization of the education reforms and their implementation over political considerations. Without this, efforts to improve learning outcomes and address the root causes of the education crisis will remain constrained, perpetuating inequity and underperformance.
Recommendations for the year ahead:
1. The continuous technical assistance support, expertise, position secured across national platforms, and strong relationships with both the education ministries have established the UK as a key policy influencer. Hence, extending EQUIP-B is crucial to consolidating the progress achieved, ensuring the sustainability of ongoing innovations, and supporting key reforms and policy transitions under the new political government. By December 2025, FCDO in consultation with the IPs shall explore and take decision internally whether to extend EQUIP-B.
2. Both national and global evidence indicates that climate change can influence student retention and enhance education system’s resilience. There is huge potential to leverage improved education systems for both climate change mitigation and adaptation. By January 2026, both the IPs in collaboration with the FCDO, will agree on a coordinated technical assistance package to be provided to both education ministries, aimed at strengthening coordination and the implementation of climate-smart education initiatives.
3. By March 2026, IPs and FCDO will closely watch the evolving country context before and after the upcoming national election, engage with the relevant government agencies to keep track of their priorities, and also to determine if any reprioritisation of activities is needed for the remaining period of the programme.
4. With Bangladesh now financing a major portion of its education and health services, UK support is shifting to support government improve budget effectiveness and system efficiency. Jointly with IPs and development partners, the UK shall continue to strengthen its policy engagement, diplomacy and influence work aligning with limited ODA support within and beyond the programme period.
5. Based on the new government’s reform priorities, FCDO and IPs will jointly review existing and planned TAs and revise the EQUIP-B’s Theory of Change (ToC) and Logical Framework (Log Frame) and budgetary allocation by April 2026.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]
1. The ToC is still valid. There have been no substantive changes to the theory of change in the review year. The theory of change revised in 2023 remains extant. The Business Case assumptions still hold true as there has been no major change of priorities in the education sector.
2. Both UNICEF and WB in consultation with FCDO updated their log frames in February 2025 based on the EQUIP-B Annual Review 2024 recommendations and requests for TA needs from the government. The EQUIP-B Master Log Frame then has been reviewed and revised aligning with the IP’s revised log frames and last year’s AR recommendations. No changes proposed in the impact, outcome, and output statements and indicators. Revision/redistribution of year-wise targets made to align with the evolving context and TA requirements from the government.
3. One new output level indicator (4.4) with milestones added on climate change adaptation in the education system. The results of these indicators will be reflected in the next AR 2026. The implementation of these indicators and milestones needs coordination and collaboration with the DPs, CSOs and GoB.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]
1. EQUIP-B is on track to meet the expected outcomes. Overall, there is good progress at the outcome level. Out of eight milestones, five are met and three are on track against the outcome indicators, though delayed. The key achievements both at outcome and output level are providing a positive trajectory towards achieving the outcomes at the end of the programme.
2. Over 50% of the trained teachers are practicing inclusive education pedagogy based on the training supported by EQUIP-B. A situation analysis study commissioned to understand the training effectiveness and conditionality needed for teachers to practise inclusive pedagogy at classroom.
3. EQUIP-B supported IPEMIS has transformed data management in Bangladesh’s primary education sector covering 120,183 schools, 20.2 million students, and 669,294 teachers. The platform has digitised core administrative functions. By using an operational plan, DPE is using this system generating the annual school census, teacher transfers, textbook distribution, stipend management, and school-level grants improving efficiency, accuracy, and accountability while reducing manual workloads and bureaucratic barriers in making transparent decisions. For the first time, the 2024 Annual Primary School Census was generated entirely through IPEMIS data, marking a milestone in institutionalising evidence-based planning. Note that Before IPEMIS, the DPE has been facing fragmented data systems and lacked an integrated, user-friendly education information management system, resulting in poor interoperability, scalability, security, and decision-making across all levels.
4. EQUIP-B has contributed enhancing teacher capacity by developing comprehensive training manuals and delivering blended learning-focused training to the first cohort of secondary teachers. A 15% rise in teacher competency is anticipated, with online modules expanding reach and impact. Formative assessment and remediation guidelines for grades 6 and 8 developed, piloted, approved, and ready for nationwide rollout. These tools are now accessible via the NCTB website, supporting improved learning outcomes. The school-related gender-based violence (SRGBV) and adolescent mental health developed and approved by the government are expected to empower 30% of secondary school students to access support mechanisms and ensure 50% of reported SRGBV cases are addressed per protocol—advancing equity and inclusion in schools.
5. The evolving political economy context has delayed the implementation of a few TAs. For example, support to national student assessment (NSA) is ongoing, aligning with government decisions to conduct this in 2026. Similarly, the government extended the design period of the 5th primary education sector programme design by one year which has impacted the delivery of planned TA support. However, EQUIP-B has supported the subnational consultations, development of a Strategic Vision Paper endorsed by MoPME, and organising a national prioritisation workshop and inform primary education sub-sector reform to be embedded under PEDP5.
6. Through EQUIP-B TA activities, FCDO and IPs were engaged at the technical level to influence the design and formulation of a national framework and strategies mentioned in the output progress narrative. FCDO continued to strengthen its visibility, networking, and relationship with Education Ministries, development partners, Civil Society Organisations (CSOs) and national education platforms. FCDO leveraged its Education Local Consultative Group (ELCG) Co-Chair role aligning with EQUIP-B TA support influencing both the Education ministries in agreeing priority reform areas and submit application to obtain new GPE’s education transformation grants (US$ 100 million).
7. The planned key activities over the next year in primary education include national student assessment, pre-service teacher education policy framework, and targeted TA to influence and inform the PEDP5 design. The TAs in secondary education include endorsement of the teacher professional development framework (TPDF) and integrated training and learning management system (ITLMS); national rollout of the on-line teacher training programme, learning acceleration through formative assessment and remediation, blended learning and climate education, SRGBV protocol and SOP, mental health support and referral pathways, and climate resilience and activism. Policy advocacy in critical reform areas will also be continued at the same time.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]
1. The EQUIP-B Theory of Change remains valid, as the majority of planned milestones linked to outputs and outcomes have been delivered. It continues to align with the key priorities of the UK Government and national plans to strengthen the education system, improve learning outcomes, and support girls’ access to and retention in secondary education.
2. The implementation momentum established since EQUIP-B’s inception holds promise for achieving programme objectives within the project period. However, reprioritising outputs and corresponding activities to reflect the upcoming new elected government’s reform agenda and new sector programmes will be critical.
3. Both implementing partners are confident in the progress made and their ability to deliver the programme over its duration. The programme is scheduled to close by March 2027 with £5 million unspent under EQUIP-B programme due to ODA reduction.
4. Time extension of EQUIP-B with budget allocation until March 2029 is crucial to consolidating the progress achieved, supporting key new reforms and policy transitions under PEDP5 by its strategic positioning at the policy level, and ensuring the sustainability of ongoing innovations. It will contribute to full mainstreaming of robust data and accountability systems, strengthening government’s capacity for evidence-based decision-making, and our influence on long-standing reforms such as foundational learning, pre-service teacher education, and decentralised education planning. It will also reinforce FCDO’s strategic role as a modern development partner and contribute to building a resilient, inclusive, and evidence-based education system in Bangladesh.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Reforms on teachers' foundational and professional development training initiated
Output number:		1	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes, increased from 10% to 20%

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of reforms initiated on teacher training and management system	Number of online training evaluation recommendations incorporated in the Government's secondary education online teacher training. / Teacher Professional Development (TPD) Framework for secondary education teachers revised and ready for endorsement (UNICEF). / Integrated teacher training and learning management system (ITLMS) developed for NAEM	Score: A (Met expectation) / The Ministry of Education endorsed and incorporated the evaluation recommendations in the online training plan for secondary education teachers. / Teacher Professional Development (TPD) Framework for secondary education teachers has been revised and in the process of endorsement. / The ITLMS has been developed under the leadership of NAEM and ready to complete the piloting by December 2025.
1.2 Policy briefings/guidance notes developed and disseminated on teacher training management	A policy brief on the impact of teacher network/classroom management training platform disseminated to inform the national scale-up	Score: A (Met expectation) / The policy brief has been disseminated with the MoE, and recommendations are incorporated in the secondary education training management platform.

Briefly describe the output’s activities and provide supporting narrative for the score.
1. Overall, this output met expectation as three out of four milestones achieved. A pilot and evaluation of online teacher training supported by EQUIP-B revealed that such programmes can significantly enhance teacher competencies and skills. Their effectiveness can be further strengthened through the provision of incentives linked to skill acquisition. The findings were shared with the Government and have informed the design of activities under the Ministry of Education’s (MoE) secondary education project, financed by the World Bank. Additionally, online sessions are being incorporated into selected training courses within the ongoing secondary training programme.
2. EQUIP-B has contributed to the development of the Teacher Professional Development Framework (TPDF), which includes provisions for gender-transformative education[5] within teacher professional development. Although the final draft of the TPDF was ready for endorsement in July 2024, the process was delayed due to a change in government. Following feedback from the national validation workshop, the National Academy for Education Management (NAEM), with technical assistance from EQUIP-B, has reviewed and revised the framework to align with curriculum changes. NAEM intends to seek endorsement from the MoE by mid-2026 to ensure the support of the newly elected government and facilitate national roll-out.
  [5] Gender transformative education equip teachers to recognize and address gender bias through teaching learning process
3. The Interactive Teacher Learning Management System (ITLMS) has been developed to deliver self-paced, interactive training, including a module on gender-transformative education. This was undertaken under the technical guidance of the Technical Coordination Committee, comprising SHED, DSHE, BANBEIS, and the ICT Division. Concurrently, NAEM has initiated the alignment of selected regular courses to test the platform’s functionality in November 2025. With support from UNICEF, NAEM has also begun developing online courses on Gender in Education—focusing on the effective implementation of gender-transformative pedagogy—and Cyber Safety for secondary school teachers.
4. A study on classroom management and teacher networking platforms, conducted with EQUIP-B support, provided valuable insights into teacher management and the improvement of classroom practices. The findings were shared with the Government and have been integrated into the teacher training package of the MoE’s secondary education project. Furthermore, key insights from the study have been incorporated into leadership training programmes for head teachers.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
No major change or deviation made in this period. Added one milestone against Output indicators 1.1

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Recommendations from 2024	Progress
Given that there is transition in the government, UNICEF will reorient key agencies on the objective, features and scope of the TPD framework as well as the teacher management system and facilitate its approval by February 2025.	Completed. UNICEF has supported NAEM to reorient the technical committee and make required revisions in the TPDF. The approval process deferred by the MoE considering the upcoming national election.

1. Lessons learned: Any system-level reform initiative is time-consuming and requires long time wider and intensive consultation at national and sub-national levels with diverse stakeholders. For example, despite the government’s overall recognition of the relevance and merit of TPDF and online training, there are debates within the government about the way it can be integrated. A thorough understanding of the political economy needs to be combined with well-timed engagement in advocating such policy reforms.
2. Recommendation: WB and FCDO should ensure that these reforms are part of the MoE’s list of key reforms agenda for the new government. Jointly with other DPs, make early engagement with newly elected government to follow up on these key reforms based on understanding the political economy.

Output Title	Government capacity and system improved for national assessment of students’ learning outcome.
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 NSA conducted to assess the learning achievement and gaps in primary education	Assessment items, tools and framework for NSA 2026 developed and piloting initiated	Score: B (Moderately did not meet expectation) / Not completed as the Government decided to conduct the next cycle of NSA in 2026 instead of 2025 with new government in power. However, revision of the assessment framework and development of test items are in progress followed by piloting to be initiated in December 2025.
2.2 DPE has enhanced capacity to manage NSA	1. To strengthen DPE's institutional capacity, relevant staff trained on data analysis, reporting and data use. / 2. NAC staff are effectively engaged in the design and piloting of NSA assessment items, tools and framework to enhance capacity	Score: A (Met expectation) / Relevant DPE and field level staff capacity enhanced through cross country training with India and learning exchange sessions organised at the field level. / DPE’s National Assessment Cell (NAC) are engaged in NSA 2026 framework, test items and tools revision process.

2.3 Formative assessment system improved in secondary education	1. Policy guidance note on formative assessment developed and shared with MoE. / 2. Teacher training on formative assessment initiated.	Score: A (Met expectation) / MoE has endorsed the policy guidance note on formative assessment and remediation to implement at the school level. / The formative assessment guidelines incorporated in the basic training manual, and the teacher training is ongoing now.

Briefly describe the output’s activities and provide supporting narrative for the score:
1. Overall, this output met expectation as four out of five milestones achieved. The MoPME changed its decision to conduct NSA in 2026 instead of 2025 to assess the impact of updated curriculum in learning. This decision has slightly delayed the overall TA support.
2. EQUIP-B adopted a two-pronged approach to strengthen the institutional capacity of the Directorate of Primary Education (DPE) in conducting national student assessments (NSA). This included targeted training for relevant staff and hands-on learning through active participation in the assessment process. The training enhanced officials’ technical understanding of assessment design, administration, data analysis, and evidence-based decision-making. A cross-country exchange with India further enriched institutional learning. As a result, DPE officials are now better prepared to lead future NSA cycles.
3. The National Assessment Cell (NAC) of DPE is currently leading the planning and administration of NSA 2026. This includes revising the assessment framework to align with global proficiency standards, developing and piloting test items by December 2025, designing and administering the NSA 2026, and conducting post-administration analysis and reporting. The NAC has developed a time-bound action plan for the administration of NSA 2026 and is actively seeking support to advance the process.
4. Formative assessment and remediation guidelines for Mathematics and Bangla in Grades 6 and 8 have been developed through extensive stakeholder consultation. These guidelines were piloted by the Directorate of Secondary and Higher Education (DSHE) and subsequently approved by the National Curriculum and Textbook Board (NCTB) and the Ministry of Education (MoE) for implementation in the current fiscal year. The guidelines have been uploaded to the NCTB website, and all secondary school teachers have been advised by the Government to familiarise themselves with them.
5. These coordinated interventions are expected to have a synergistic effect on improving teacher training and student learning assessment systems, thereby contributing to the delivery of quality education for all. To initiate formative assessment, DSHE has selected 1,200 secondary schools and developed reporting tools for Academic Supervisors. Teacher training on formative assessment is currently underway as part of the basic training programme.

Describe any changes to this output during the past year, and any planned changes because of this review:
No major change or deviation made in this period. Changed milestones against Output indicators 2.1 and 2.2 to make stretchable and measurable.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead:
Recommendation AR 2024	Progress
In addition to conducting the next cycle of NSA, FCDO and UNICEF should advocate with government to ensure utilisation of NSA findings to initiate specific interventions under PEDP5 and inform policy around the factors that are strongly associated with learning achievement to improve student learning, by June 2025	NSA 2022 findings were disseminated in all eight divisions and at the national level. Participants reviewed division-specific reports to better understand local learning conditions and identify actions at school, sub-national, and national levels. A national workshop is scheduled for October 2025 to consolidate these insights and support the development of a Foundational Literacy and Numeracy (FLN) Strategy under PEDP5.

1. Lessons learned: Strengthen the national assessment systems to track learning in an informed manner is critical. For this, the systematic capacity development of the government can ensure the periodic administration of NSAs and then analyse the data in a meaningful manner to inform the reforms. The ministries and departments of both primary and secondary education should work together to build a more unified system of national learning assessments.
2. Recommendation: FCDO and UNICEF in collaboration with WB and UNESCO shall strongly advocate with both the education ministries for sustainable institutional capacity for conducting large-scale assessments in Bangladesh, emphasising the need to translate NSA results into policy and programmatic action to improve learning.

Output Title	Girls’ friendly and inclusive education initiatives piloted to improve access, learning efficiency, and retention in selected schools
Output number:		3	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR.	Yes, reduced from 30% to 20%

Indicator(s)	Milestone(s) for this review	Progress
3.1 SEND Framework developed, disseminated and implemented	120,000 of primary education teachers participated in SEND/inclusive education training (govt funded). / A study on inclusive education provisions including children with disability commissioned to inform the design of inclusive education interventions under PEDP5	Score: A (Met expectation) / 120,000 primary school teachers (56% female) trained in inclusive education pedagogy following the SEND framework. / A study on disability-inclusive education commissioned to inform the design of PEDP5.
3.2 Number of targeted schools demonstrating girl-friendly inclusive education model	1. The girls' friendly education model demonstration in 24 secondary schools and evidence generation continued. (UNICEF) / 2. A road map and guideline designed to support implementation modality for a learning accelerator programme in secondary schools. (WB)	Score: A (Met expectation) / Implementation research in 24 experimental secondary schools continued focusing on innovative initiatives. / Roadmap and guideline designed to support the implementation of a learning accelerator programme in secondary schools.
3.3 Communities actively engage in addressing behaviour and socio-cultural barriers to equitable and inclusive education	1. Primary: Policy directions and recommendations generated for enhancing social mobilisation and behaviour change. / 2. Secondary: The development of a SBCC strategy continued.	Score: B (Moderately did not meet expectation) / Policy direction and recommendations generated through extensive consultations with relevant stakeholders at all levels. / No progress made as the MoE decided to pause the development of a SBCC strategy.
3.4 Strengthen capacity and awareness of schools related gender-based violence.	1. Gender based violence prevention committees in targeted schools activated and operationalised. / 2. SOP on SRGBV initiated in the targeted schools	Score: B (Moderately did not meet expectation) / SRGBV and SOP approved my MoE but not yet initiated in schools. However, action plans finalised to activate committees and initiate SOP in schools.
3.5 Number of schools delivered improved mental health and aspiration services.	Mental health and aspiration support provided in 50 selected schools	Score: B (Moderately did not meet expectation) / Mental health guideline approved by MoE but not initiated in 50 selected schools. However, an action plan developed to support mental health in selected schools from January 2026.

Briefly describe the output’s activities and provide supporting narrative for the score:
1. Overall, this Output moderately did not met expectation.
2. EQUIP-B supported the design and approval of the SEND framework followed by developing a pool of expertise to train teachers. DPE using its own budget trained approximately 120,000 primary teachers (56 percent female) in inclusive pedagogy based on the approved SEND framework and action plan supported through EQUIP-B TA. This ongoing training is built on a comprehensive package and cascade model using 224 Master Trainers and 2,052 local trainers supported by EQUIP-B. The training helped to build the capacity of teachers on inclusive education concepts and teaching-learning methods and strategies. This is an excellent example of mainstreaming system strengthening TA support to the government.
3. To strengthen evidence-based policy and planning for inclusive education, EQUIP-B at DPE’s request commissioned a comprehensive situation analysis study on inclusive education. Aligned with the SEND Framework, the study is designed to fill knowledge and data gaps, identify systemic barriers and enablers, and generate actionable recommendations to improve access, continuity, and transition for children with disabilities across primary and secondary education. The findings will directly inform the design of inclusive education interventions under PEDP5 and secondary education projects.
4. EQUIP-B has supported the DSHE to continue the Implementation Research in 24 selected schools through partnership with UNICEF’s Innocenti. The findings on girl’s friendly experiential pedagogy, formative assessment and teachers’ readiness will inform the 2026 curriculum review and will support inclusive, learner-centred, and future-ready education reform in Bangladesh, even during policy transitions. The gamified pedagogy with micro-skills and learning materials for Adolescent Sexual and Reproductive Health (ASRH), Wellbeing, and Cyber safety is one of the innovative initiatives covered under the Implementation Research in 24 schools.
5. EQUIP-B has been instrumental in supporting the PEDP4 on Communication and Social Mobilisation, aimed at empowering parents, teachers, and communities to champion generating demands for inclusive, quality primary education. A comprehensive study conducted following a series of planning meetings and seven divisional-level workshops. This study, endorsed by DPE, generated context-specific policy direction and recommendations that shaped the development of a Communication and Social Mobilisation Action Plan to be implemented under PEDP5.
6. The development of Social Behaviour Change and Communication (SBCC) strategy for secondary education has been delayed due to a priority shift by MoE after July 2024 uprising followed by shifts in senior leaderships. This strategy development is now shifted to 2026.
7. As part of the girl-friendly and inclusive education initiatives, gender-based violence prevention committees have been established in selected schools. The necessary SRGBV guidelines and Standard Operating Procedures (SOPs) have already been developed under EQUIP-B TA and approved by the Ministry of Education (MoE). The SRGBV SOP is designed to support secondary schools in establishing a system for reporting SRGBV-related incidents and providing students with mental health counselling. Preparations are currently underway to activate the school committees.
8. EQUIP-B supported a pilot intervention to address mental health disorders by offering free counselling, with clearly defined referral pathways for further support where needed. Under this TA, a mental health support guideline has been developed and approved by MoE through extensive consultations with stakeholders and partners. Preparations for implementation are in progress to roll out this intervention from January 2026, enabling schools to respond to psychosocial needs and helping students cope with stress, trauma, and gender-related challenges. This initiative aims to foster equitable and inclusive learning environments within schools.

Describe any changes to this output during the past year, and any planned changes because of this review. [1 paragraph]
No major change or deviation made in this period. Changed milestones against Output indicators 3.1 and 3.2 to monitor the progress against TAs on piloting inclusive and gender friendly school models, and social behaviour change for effective community engagement in education.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Recommendation AR 2024	Progress
By June 2025, UNICEF shall complete systematic documentation of implementation bottlenecks and detailed plan of action as per findings from the implementation research in 24 experimental secondary schools.	Completed. Baseline assessment report documented critical learning gaps at Grade VI underscoring the need for foundational learning support in language, math and English subjects. However, positive learning gains were also observed showing learning enhancement strategy’s potential when applied effectively.

1. Lessons learned: Though gender-based violence and trauma are quite pervasive at the school level, there is some sensitivity around this issue. Because of the social stigma associated with these, many victims prefer not to report such incidents. For ensuring successful and effective operation of the gender violence prevention committees, adequate awareness raising and motivation are required among students, teachers, parents and local community.
2. Recommendation: By June 2026, WB to closely follow up on the establishment and functioning of the gender violence committees, and operationalisation of the SOP and mental health support system in the secondary schools.

Output Title	Integrated data management system and evidence enables making policy decisions, programme design and resource allocations.
Output number:		4	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR.	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Integrated Primary EMIS system strengthened and used for better planning, implementing and monitoring	1. Four additional modules/dashboards integrated into the PEMIS as per needs from the DPE. / 2. ASPR 2024 report drafted by using IPEMIS	Score: B (Moderately did not met expectation) / Integration of four modules is yet to be completed by December 2025. / ASPR 2024 drafted by using IPEMIS.
4.2 Number of evidence generated, and TA support provided to influence policy and programme design	1. At least two studies conducted to inform the design of sector programme (PEDP5) and findings disseminated at national level. / 2. Need-based TA provided to design and implement PEDP5	Score: A (Met expectation) / Two studies conducted and disseminated at PEDP5 design workshops and meetings. / TA support provided to develop strategy paper, national and field consultations contributing to the design of PEDP5.

4.3 Number of targeted schools demonstrating blended education delivery model	Piloting of blended learning initiated in selected schools	Score: A (Met expectation) / Blended learning with e-content on language, math and climate education has been successfully piloted in selected schools.
4.4 Policy framework and programme developed to introduce climate change adaptation in education system (New)	1. Climate change in education framework drafted (UNICEF) / 2. Climate resilience programme designed for secondary schools (WB)	Score: A (Met expectation): / A comprehensive climate change in education (CCE) framework developed and in the process of endorsement by MoE. / A climate resilience programme has been designed and initiated in secondary schools.

Briefly describe the output’s activities and provide supporting narrative for the score:
1. Overall, this output met expectation as six out of seven milestones achieved. EQUIP-B has supported the enhancement of IPEMIS to meet DPE’s evolving planning needs, including the deployment of additional six new modules. 100% (65,000) of the government primary schools are using IPEMIS. Design of another four additional modules on SEND, accounting information system, asset management, and non-government school registration has been completed. User acceptance testing, piloting and refinement for final deployment will be completed by December 2025. Meanwhile, 2,500 digital learning resources have been integrated via the Learning Management System to improve access for learners and teachers. To promote system’s use and sustainability, divisional-level training has built sub-national capacity in data entry, analysis, reporting, and peer-led knowledge sharing, helping standardise practices and strengthen sector-wide monitoring and accountability.
2. The Annual Sector Performance Report (ASPR) 2024 report has been prepared using IPEMIS data. The report includes trend analysis on key system and school level indicators, including Key Performance Indicators (KPI), non-KPI, primary school quality level and SDG indicators, and budget execution rates of PEDP4 by component. It offers recommendations to improve access, quality, and governance, while also highlighting challenges in data and reporting. For the first time, field-level officials were involved in data validation and analysis, enhancing the report’s accuracy.
3. At DPE’s request, EQUIP-B supported two studies on effectiveness of continuous professional development (CPD) of teachers and school level improvement plan (SLIP). Findings and recommendations of these studies have been disseminated during the PEDP5 design workshops and consultations. Design notes drafting is in progress to inform the CPD and SLIP interventions under PEDP5.
4. EQUIP-B provided technical assistance to initiate the design of PEDP5. It supported sub-national stakeholder consultations to gather bottom-up insights through visioning exercises, assessing PEDP4 progress and shaping PEDP5 direction. It also supported MoPME and DPE in developing a Strategic Vision Paper, consolidating inputs from the field, key agencies and development partners. The paper was presented and endorsed at a high-level meeting in MoPME. A subsequent prioritisation workshop in September 2025 identified key reform areas, including foundational learning, pre-service teacher education, two years of pre-primary education, catch-up programmes, and decentralised planning and budgeting. This TA support has significantly contributed to policy dialogue and strategic planning, with evidence from data systems, studies, and consultations helping to shape the design of PEDP5.
5. At DSHE’s request, EQUIP-B supported the development of a comprehensive Climate Change in Education (CCE) framework, aligned with national policies and international commitments. A position paper was shared with key stakeholders to establish common understanding and prepare the framework. The framework covers six thematic areas: schools, students, teachers, curriculum, pedagogy and assessment, governance and management, and policy and systems. It is currently undergoing technical review, revision, and consultation ahead of finalisation and DSHE’s endorsement by December 2025.
6. EQUIP-B supported the design of climate resilience interventions for secondary schools, informed by a baseline study on climate mindsets. The programme empowers schools to lead context-specific initiatives and includes training modules on climate change and green skills for teachers, a school-level awareness guideline, and climate-themed competitions for students.

Describe any changes to this output during the past year, and any planned changes because of this review. [1 paragraph]
During log frame review, deleted previous Output indicator 4.2 due to low budget allocation and reprioritisation of TAs. Also, changed the milestone against Output Indicator 4.1 to make it stretchable and measurable.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
Recommendation AR 2024	Progress
By March 2025, UNICEF shall do an assessment of IPEMIS effectiveness to inform the design of interventions under next primary education sector programme.	The assessment deferred to capture the whole system once all modules are deployed.

1. Lessons learned: The IPEMIS is a large system and continuously addressing evolving demands by incorporating new modules and features. The DPE is yet to be fully capable to maintain and run this system independently. Sustained support will be critical to consolidate gains, institutionalise IPEMIS fully, and foster a culture of inclusive, data-driven decision-making under PEDP5.
2. Recommendation: Despite notable progress, challenges remain in broadening public access to sectoral data. The IPEMIS dashboard currently covers only Government Primary School (GPS) data, limiting sector-wide insights. FCDO and UNICEF shall initiate dialogue with DPE and partners to expand access, strengthen data validation processes, and use of data in IPEMIS.

D: VALUE FOR MONEY (1 page)

Key cost drivers and performance
1. Economy: The World Bank and UNICEF’s key cost drivers include individual consultant fees (52%), institutional contracts (28%), and training costs (20%) for secondary education, with operational expenses for surveys and studies managed proportionately and in line with FCDO agreements. The Bank’s cost control is maintained through competitive procurement and strategic task allocation. UNICEF ensures cost-effectiveness by closely reviewing consultant rates, contract durations, and sample sizes, and actively negotiating with government counterparts to align investments with sector priorities.
2. Efficiency across EQUIP-B has been strengthened through strategic planning and adaptive delivery mechanisms. The World Bank improved cost-efficiency by using competitive bidding, applying minimum sampling in studies, and integrating interoperable modules into a single system—reducing duplication and enhancing usability. Training costs were lowered by consolidating sessions at divisional and central levels. Despite sociopolitical instability and funding disruptions, UNICEF maintained delivery momentum by co-identifying TA areas with government counterparts, ensuring demand-driven support. Competitive procurement and proactive planning helped optimise resource use and minimise delays, contributing to overall programme efficiency.
 VfM performance compared to the original VfM proposition in the business case
Effectiveness: EQUIP-B has demonstrated strong effectiveness through targeted, evidence-informed technical assistance aligned with evolving government priorities. The World Bank supported ten TA areas during the reporting year, identified through intensive consultation, and its feasibility study on secondary education directly contributed to the approval of a $300 million government programme (LAISE), showcasing high strategic impact and potential for future cost-benefit analysis. UNICEF delivered high-impact outputs including curriculum reform, teacher development, and capacity building, while leveraging NSA findings and IPEMIS data to inform policy decisions. Additionally, studies on SLIP, CPD, and inclusive education provided actionable insights for future programming, reinforcing the programme’s relevance and contribution to long-term education system strengthening.
 Assessment of whether the programme continues to represent value for money
1. EQUIP-B has demonstrated strong Value for Money (VfM) across its technical assistance components, delivered by the World Bank and UNICEF. Despite operating in a challenging environment marked by political transitions, economic disruptions, and global ODA constraints, the programme has maintained cost discipline, strategic alignment, and inclusive impact. This report consolidates VfM performance across both partners, highlighting key cost drivers, delivery mechanisms, and outcomes.
2. EQUIP-B continues to demonstrate strong Value for Money by maintaining strategic alignment with national education reform priorities, delivering technical assistance through cost-effective and flexible mechanisms, and ensuring evidence-informed programming that influences policy and practice. The programme’s inclusive and equitable outcomes for learners and educators further reinforce its VfM proposition. As Bangladesh advances toward middle-income status, EQUIP-B’s role in driving systemic education reform becomes increasingly vital, with its ability to adapt to political and economic shifts while sustaining quality and impact underscoring its long-term value.

E: RISK [½ to 1 page]
Overview of risk management [1/2 page]
The overall risk rating of EQUIP-B is assessed as ‘Major.’ The EQUIP-B programme operates within a highly dynamic and politically sensitive environment. While the initial programme design incorporated a detailed risk analysis, the evolving context in 2024 introduced several unforeseen challenges. These risks span strategic, operational, commercial, safeguarding, reputational, and environmental dimensions. Both UNICEF and the World Bank have actively managed these risks in alignment with FCDO’s risk management framework, ensuring continued programme delivery and alignment with national priorities.
Strategic and Contextual Risks
1. Strategic and Contextual Risks: Throughout 2024, EQUIP-B faced significant strategic risks due to the transition in government and frequent leadership changes across key ministries and directorates, including MoE, MoPME, DPE, DSHE, NCTB, and NAEM. These shifts led to reprioritisation of the education reform agenda, inconsistencies in decision-making, and delays in approvals and implementation. UNICEF and the World Bank responded by intensifying engagement with interim government officials and maintaining strong relationships with mid-to-high-level stakeholders. UNICEF leveraged Everyday Political Analysis (EPA) to anticipate personnel changes and mitigate disruptions, while both partners continued implementation under previous Rolling Work Plans (RWPs) to avoid service gaps. These efforts reflect a “tolerate” risk response strategy, allowing the programme to adapt while maintaining strategic momentum.
2. Delivery Risks: The programme encountered delivery risks stemming from technical complexity, resource-intensive activities, and leadership gaps. For instance, the National Student Assessment (NSA) required concentrated effort, which slowed progress in other areas. Additionally, frequent transfers of trained officials disrupted continuity and reduced the effectiveness of capacity-building efforts. UNICEF and the World Bank addressed these challenges by reaching consensus with FCDO on flexible pacing and reprioritisation of activities. UNICEF advocated for retaining technical staff in key roles and documented institutional memory to preserve knowledge. These mitigation measures align with a “manage and adapt” strategy, ensuring that implementation timelines remain realistic and responsive to contextual shifts.
3. Operational and Commercial Risks: Both partners faced operational risks related to increased technical assistance (TA) requests beyond the scope of the agreed RWPs. These requests, particularly in areas such as teacher training and PEDP5 design, risked scope creep and resource strain. UNICEF facilitated consultations to assess the urgency and strategic relevance of these requests, opting to decline non-essential ones while escalating priority items to FCDO for approval. Adjustments were made to the RWP to accommodate critical new activities. This reflects a “control” strategy, maintaining scope discipline and ensuring alignment with donor priorities.
4. Safeguarding Risks: No safeguarding or fraud incidents were reported during the reporting period. Both UNICEF and the World Bank have robust safeguarding and Protection from Sexual Exploitation and Abuse (PSEA) policies aligned with international standards. These mechanisms were reviewed through the Enhanced Due Diligence Assessment (EDDA) process. Field visits confirmed strong safeguarding practices and effective reporting mechanisms. The programme continues to monitor safeguarding compliance closely, reflecting a “monitor” strategy to uphold protection standards and accountability.
5. Reputational Risks: A key reputational risk identified was the potential impact of ODA budget pressures on programme delivery. Reductions in funding could affect stakeholder confidence and the ability to sustain planned interventions. FCDO has worked closely with partners to mitigate this risk by reprioritising TA areas and adjusting interventions without compromising core outcomes. Transparent communication with stakeholders has been central to managing expectations and maintaining trust, aligning with a “mitigate” strategy.
6. Climate and Environmental Risks: No climate-related risks were identified during the reporting period. EQUIP-B does not involve infrastructure development, land acquisition, or other activities with potential environmental impact. As such, this risk is considered negligible and accepted without further mitigation.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]
1. Programme Performance and Strategic Alignment: The EQUIP-B programme continues to demonstrate strong performance and remains firmly on track to achieve its intended outcomes within the planned implementation timeline. Delivery partners have exhibited both operational agility and robust execution capacity, fully aligned with FCDO’s compliance and quality assurance standards. Key strategic instruments including the Logical Framework (LFW), Value for Money (VFM) strategy, Theory of Change (ToC), and Risk Register have been finalised and are actively guiding programme delivery. All recommendations from the previous FCDO review have been successfully implemented within the agreed timeframes, reflecting a high level of responsiveness and governance maturity.
2. Financial Management: Financial reporting mechanisms are functioning effectively. Both the World Bank and UNICEF submit periodic financial reports to FCDO on time. Additionally, the World Bank provides detailed financial statements with each disbursement request, including forward-looking fund disbursement projections. All partners have submitted progress reports in accordance with the agreed schedule.
3. Funding disbursements are structured as six-monthly advances, aligned with approved work plans and financial forecasts. As of October 2025, cumulative programme expenditure stands at £8,400,339 million. For FY 2024/25, total spend was £1,925,000 million, with disbursements of £975,000 million to the World Bank and £950,000 million to UNICEF, consistent with country-level budget allocations.
4. Partnership Effectiveness and Governance: The tripartite partnership between FCDO, UNICEF, and the World Bank remains strong, collaborative, and strategically aligned. Quarterly coordination meetings structured under the agreed governance framework have facilitated timely updates on programme progress, strategic pivots, M&E findings, research outputs, safeguarding risks, and cross-cutting opportunities. This mechanism has enabled FCDO to deliver targeted technical and programmatic feedback, enhancing overall delivery effectiveness.
5. Commercial and Procurement: Under the administrative arrangement with the World Bank, all procurement activities were conducted in accordance with the Bank’s procurement guidelines, ensuring transparency, fairness, and accountability. During the reporting period, the World Bank competitively engaged twelve consultants, supported by a robust internal control framework. Similarly, UNICEF operated under an unchanged contribution arrangement with FCDO and signed the Rolling Work Plan (RWP) for 2024–2025 with the Government of Bangladesh. In response to emerging TA needs particularly in teacher training and PEDP5 design UNICEF procured eight agencies and three individual consultants through competitive processes.
6. Both partners demonstrated strong commercial performance through cost-effective delivery of technical assistance. The World Bank achieved notable cost savings by applying minimum sampling in studies and integrating interoperable modules into a single system, reducing duplication and improving usability. Training costs were lowered by consolidating sessions at divisional and central levels. UNICEF maintained cost-efficiency by closely reviewing consultant rates, contract durations, and survey sample sizes, while aligning investments with sector priorities through active negotiation and strategic planning.
7. Despite political transitions and global ODA disruptions, EQUIP-B maintained delivery momentum and produced high-impact outputs. These included curriculum reform, teacher development, and evidence-informed policy support. The programme’s commercial approach remains flexible and responsive, adapting to evolving government needs while prioritizing inclusive, scalable, and sustainable solutions. As Bangladesh moves toward middle-income status, EQUIP-B is well-positioned to continue delivering high value for money through systemic education reform.
8. Asset Management: No assets were procured under the EQUIP-B programme during the current reporting period, ensuring continued compliance with asset management protocols and minimising operational overhead.
G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]
Monitoring and Evaluation
1. EQUIP-B has established a comprehensive and responsive Monitoring, Evaluation, and Learning (MEL) framework to ensure accountability, evidence-based decision-making, and continuous improvement across all programme components throughout the programme lifecycle. This MEL framework integrates monitoring, evaluation, and learning across delivery partners UNICEF and the World Bank in close collaboration with the Government of Bangladesh and FCDO. EQUIP-B has produced a number of studies and assessments to inform programme design and TA reprioritisation. IPs are responsible for quality assurance of evidence prior to publication, ensuring data is disaggregated by sex, disability, and geography for inclusive reporting.
2. The MEL system under EQUIP-B is robust, multi-layered, and action-oriented. It enables:
Strategic alignment with government priorities.
Real-time responsiveness to implementation challenges.
Evidence-driven decision-making and programme adaptation.
Strong FCDO oversight and accountability.
1. UNICEF Monitoring and Evaluation Processes: UNICEF conducts annual, mid-year, and end-year reviews of Rolling Work Plan (RWP) activities with DPE and DSHE, aligned to agreed indicators, while also organizing need-based review meetings with relevant line divisions to enable real-time adjustments. Field-level monitoring is guided by standard tools that support planning, quality assurance, and corrective actions, all of which are aligned with PEDP4 and SEDP Standard Operating Procedures to ensure consistency and rigour. UNICEF staff maintain close collaboration with government counterparts and technical experts to ensure the quality and responsiveness of technical assistance delivery.
2. World Bank Monitoring & Evaluation: The World Bank applied rigorous, data-driven evaluation methods including randomised control trials and results frameworks to monitor the effectiveness of technical assistance (TA) activities. Findings from these assessments directly informed programme design and policy dialogue, ensuring relevance and impact. Stakeholder engagement was strengthened through regular learning events and joint field visits, promoting transparency and shared learning. Built-in monitoring mechanisms enabled early identification of implementation challenges and facilitated timely corrective actions. All reporting was aligned with the global framework agreement, ensuring consistency, comparability, and adherence to international standards.
3. FCDO Oversight: FCDO provided consistent oversight through quarterly and ad-hoc review meetings with implementing partners (IPs), ensuring documented follow-up actions were tracked and addressed. FCDO facilitated 5 quarterly progress review meetings and 3 need-based issue specific meetings with the IPs. Each meeting produced minutes with follow up actions which were shared with partners and followed up. FCDO also reviewed two six monthly and two annual progress reports from the IPs. These ensured additional scrutiny and an opportunity for FCDO to fact checking and reporting.
4. Additionally, FCDO developed a dedicated monitoring plan following the Annual Review to guide programme adjustments and enhance strategic responsiveness. Lastly, FCDO supported Joint Annual Review Mission (JARM) (Oct 2024) and Joint consultative Mission (JCM) (Feb 2025) to assess sector-wide progress and TA impact.

Learning
1. EQUIP-B’s integrated MEL framework jointly implemented by UNICEF and the World Bank has proven effective in ensuring accountability, strategic alignment, and adaptive learning throughout the programme lifecycle. UNICEF’s structured review processes and field-level monitoring tools enabled responsive adjustments and maintained TA quality, while the World Bank’s data-driven methods, including RCTs and results frameworks, ensured rigorous evaluation and informed policy dialogue.
2. FCDO’s oversight through regular reviews and a dedicated monitoring plan strengthened programme responsiveness and transparency. The generation and use of inclusive, disaggregated evidence have supported continuous improvement and informed strategic reprioritisation, reinforcing the value of collaborative, evidence-based MEL systems in complex education reform programmes. FCDO in consultation with the IPs shall start planning for an evaluation of TA effectiveness at the last year of the EQUIP-B programme.

Date of last narrative financial report	World Bank: July 2025 / UNICEF: October 2025	Date of last audited annual statement	World Bank: July 2025 / UNICEF: May 2025

Annex – A: EQUIP-B Annual Review 2025: Progress against outcome level milestones

Outcomes	Indicators	Milestone 2025	Progress against the milestones
Outcome 1: Teacher training and students’ learning assessment system improved contributing to quality education for all	1.1: Teacher training system efficiency improved in secondary education	On-line teacher training and teachers' network introduced based on pilot initiative	Achieved. Comprehensive teacher training manuals have been developed covering subject mastery in mathematics and Bangla, pedagogy for blended learning, climate change adaptation and mitigation, and teacher evaluation methodologies. Training for the first cohort of teachers has been completed in July-August 2025. Training of Trainers (ToT) and content development for the next cohorts are now in progress. A teacher network has been introduced for cross sharing and learning.
	1.2: National students' assessment system improved to assess the quality of primary education	Quality of NSA 2026 design and reporting improved with more granularity, aspiring to contribute to policy decisions on enhancing learning outcome	Delayed and not achieved. Government decided to conduct the next cycle of NSA in 2026 instead of 2025. However, revision of the assessment framework and development of test items are in progress followed by piloting to be initiated in December 2025 to deliver stronger, policy-relevant evidence on primary education quality.
	1.3 School based learning assessment system improved for secondary education	Number of recommendations from the policy brief implemented by the Government to improve formative assessment in schools	Achieved. Based on the policy brief recommendations, formative assessment and remediation guidelines for grades 6 and 8 have been developed, piloted and approved by the National Curriculum and Textbook Board (NCTB) and MoE. All secondary school teachers have been instructed to apply these guidelines. This intervention is expected to garner a synergic effect on improving teacher training and students’ learning assessment system, contributing to quality education for all.
Outcome 2: Equitable and inclusive learning environment promoted to improve girls’ access and retention.	2.1: National education sector plan/policies support gender-responsive teaching and learning	Capacity of the national education authorities strengthened on gender responsive education planning and programming.	Not achieved. This TA has been deprioritised due to repeated reshuffling of key officials in both education ministries and relevant directorates.
	2.2 Improved capacity at national and field level facilitates improved equitable and inclusive education practices	50% of the SEND trained teachers are practicing inclusive education	Achieved. By 2025, EQUIP-B support enabled DPE to train 103,776 primary teachers (56% female) in inclusive pedagogy. Through the interactive sessions, and practical tools, over 50% of the trained teachers are practicing inclusive education.
Outcome 3: Increased use of data and evidence in policy decisions and national programme formulation.	3.1 Key sectoral data used by the stakeholders to influence decision making in primary education	1. 90% of the government primary schools uploaded data in the PEMIS;	Achieved. 100% GPS now upload data in IPEMIS, including completing APSC data filling, managing teacher transfer through TTMS, managing textbook and stipend distribution etc.
		2. 2 national reports and 1 operational plan produced utilising PEMIS data.	Achieved. APSS 2024, ASPR 2022 and 2023 reports have been developed based on data collected through IPEMIS. Operational plan developed and utilised for textbook demand submission, stipend disbursement decisions, teacher transfer application submission, approval processes and transfer decisions.
	3.2: Evidence generated and used for national policy and programme design	The design of 5th primary education sector programme is informed by evidence generated through studies and technical assistance support	Delayed and not achieved. MoPME decided to delay the design of the PEDP5. Hence, the TA support has also been delayed adjusting with the PEDP5 design period. However, EQUIP-B has supported the subnational consultations, development of a Strategic Vision Paper endorsed by MoPME, and organising a national prioritisation workshop and inform primary education sub-sector reform to be embedded under PEDP5.