## EDT2 Year 3 Annual Review

Title: Emergency Deployments Team 2
Programme Value £ (full life): £39.7m		Review date: 12/07/2025
Programme Code: 301054	AMP start date: 12/07/2022	AMP end date: 12/07/2029

Summary of Programme Performance
Year	22/23	23/24	24/25
Overall Output Score	A	A+	A+
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301054
DevTracker Link to results framework:	D0004240.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

In the aftermath of disasters, local emergency responders and systems can become overwhelmed, risking further loss of life, injury and disability, or secondary crises such as disease outbreaks. The Emergency Deployments Team 2 (EDT2) programme provides the UK with bilateral disaster response capabilities to assist countries in need of international emergency medical or search and rescue surge expertise through two official UK teams: the UK’s Emergency Medical Team (UK-EMT) and the UK’s International Search and Rescue (UK-ISAR) team. These teams are designed to provide direct support to the host country’s Ministry of Health or Civil Protection Department respectively.

These capabilities provide the UK with high profile, highly effective and specialised humanitarian response options, strengthening our role in humanitarian leadership and providing key opportunities for UK public engagement in overseas aid efforts. They also provide opportunities for HMG to learn from overseas disaster contexts, and to develop and maintain specialist skills that are useful in domestic responses, for instance during the COVID-19 pandemic. Both the UK-EMT and UK-ISAR are accredited against common United Nations (UN) global standards and managed by the World Health Organisation (WHO), and the Office for the Coordination of Humanitarian Affairs (OCHA) respectively. OCHA and the WHO also play a coordination role in deployments of member states’ capabilities in response to disasters.

Through the EDT2 programme the FCDO is an accredited government Type 1 EMT and Rehab Specialised Care Team (SCT) delivered via the partnership with UK-Med (a registered British charity). The EDT2 Health Lead in FCDO is the UK’s National Focal Point to coordinate all EMT mechanism activities across the UK for WHO on behalf of the Department for Health and Social Care (DHSC). They also provide input from FCDO into high profile WHO initiatives such as the Global Emergency Health Workforce and the FCDO’s pandemic preparedness, as part of HMG’s global position on health security.
[note] A team able to supply their own fixed outpatient facilities such as tents for outpatient initial care of injuries and other healthcare needs up to 100 patients per day, referrals, and community-based primary care from a fixed location.
[note] A team of at least three rehabilitation professionals, with the necessary equipment as per the minimum standards for a rehab Specialised Care Team who can embed into an EMT for at least 3 weeks or into a local facility for a minimum of 4 weeks.

The EDT2 programme provides FCDO with UK-ISAR which is a classified ‘Heavy Team’ for International Search and Rescue. The EDT2 Senior Responsible Owner (SRO) is the UK-ISAR National Policy Focal Point for all UK-related Search and Rescue requests and activities for OCHA, providing key policy inputs to emerging initiatives across approximately 140 international search and rescue member countries, with opportunities for bilateral engagement and partnerships.

The programme also has a focus on investing in local emergency preparedness planning and response capacity through training, mentoring and knowledge exchange with emergency responders and national response teams with host Government counterparts. This can provide a valuable resource both to strengthen national life-saving response capabilities and can support the development of mature and meaningful partnerships with host Governments.

EDT2 is the successor to the EDT programme (EDT1), which concluded in June 2022, and forms an essential part of the UK’s international emergency response toolkit. It is delivered through two external partners who were part of EDT1 and were successful in a competitive process to manage these capabilities for the FCDO under the EDT2 programme until 2029:
UK-Med: a non-governmental organisation (NGO) with close links to the NHS. In partnership with FCDO this forms HMG’s only Emergency Medical Team which is classified by WHO as a ‘Type 1’ Government team. UK-Med is also classified as a Type 1 NGO team and one of only two classified EMTs in the UK.
Merseyside Fire & Rescue Authority (MFRA): a Public Body which holds the only ‘heavy’ team classified by OCHA in the UK, as well as a DEFRA standard flood rescue (boat operations) team. There is also an accredited NGO ‘light’ Search and Rescue team in the UK.

Summary supporting narrative for the overall score in this review

The third year of the EDT2 programme has once again seen an unprecedented level of international engagement from both delivery partners. This reflects their ability to respond to multiple disasters around the world, deliver capacity-building programmes, and maintain readiness in support of the FCDO’s crisis response capabilities. Throughout the year, the programme has provided official UK assistance to host governments across a range of countries. It has also made significant investments in international partnerships and in strengthening its own operational readiness. The deployments carried out this year highlight the continued importance of ensuring that the FCDO can deliver these capabilities during humanitarian emergencies.

During the review period, the UK-EMT carried out five new deployments and conducted four assessment visits, three of which resulted in full deployments. The UK-EMT also contributed to one capacity-building initiative during this period. There were no new UK-ISAR deployments. However, UK-ISAR actively monitored and prepared for six potential responses. The team successfully delivered three new capacity-building initiatives and participated in three additional international engagements.

A full table of Year 3 (Y3) ISAR and EMT engagements is below:

UK-ISAR	UK-EMT
Taiwan Earthquake (monitored no deployment) April 2024	Israel-Lebanon Conflict Assessment, June 2024
Ethiopia Landslides (monitored, no deployment) / July 2024	Israel-Lebanon Conflict deployment, November 2024
Philippines Earthquake (monitored, no deployment) / August 2024	Rwanda Marburg Disease Assessment, October 2024
Bosnia Flood (monitored, no deployment) October 2024	Rwanda Marburg Disease deployment, October 2024
Vanuatu Earthquake (monitored, no deployment) December 2024	Bangladesh Rehab (injured student protests) deployment, October 2023
Myanmar Earthquake (monitored, no deployment) April 2025	Democratic Republic of the Congo (DRC) Goma Conflict Deployment, March 2025
Malawi Capacity Building, February and March 2025	North Macedonia Fire Assessment. March 2025
Tajikistan Capacity Building, November 2024	North Macedonia Fire Deployment, April 2025
Kenya Capacity Building, March 2025	Myanmar Earthquake Assessment, April 2025
Gibraltar- Crisis and Disaster Coordination and preparedness.	Ethiopia Capacity Building – ongoing
Greece (Rhodes)- Crisis management and Spontaneous volunteers
Ukraine Convoy – donating FRS (Fire and Rescue Service) equipment

In this review period the business case budget has been increased by £14.7m and the end date extended by two years (from June 2027 to June 2029). The increased budget will cover the time extension, the procurement of a Type 2 facility (which will enable the reclassification of the UK-EMT as a Type 2 team in 2025) and further investment in capacity-building initiatives. Both UK-EMT and UK-ISAR teams have been working hard across this reporting period to enable the programme to maximise its ambitions. The UK-EMT procured both the necessary equipment for their Type 2 and equipment for the Ethiopian Type 1 within 4 months. UK-ISAR delivered the Known Consignor project, meeting these necessary standards by the end of the financial year while also delivering an additional capacity building scoping mission in Tajikistan and training in Kenya.
[note] Provides Type 1 services plus general and obstetric surgery for trauma and other major conditions as well as inpatient acute care.
[note] A Known Consignor is a company that has been approved by the national aviation authority. They are authorised to send goods by air freight without undergoing additional security checks at the airport.

The emergency response fund within the programme supported 3 UK-EMT assessments (Lebanon, Rwanda and North Macedonia) and 1 deployment (Bangladesh). In all 3 cases, the deployment of the assessment teams resulted in recommendations for full deployments that were funded by Post. This model has been effective in ensuring that the UK-EMT has a strong understanding of needs and partners’ work on the ground, resulting in more impactful subsequent deployments. It is recommended that an indicator is created for the UK-EMT within the partner logframe and programme logframe to capture the delivery of this approach.

There has been significant progress made over the last reporting period to enhance the FCDO deployment processes for both the UK-ISAR and UK-EMT.
1. The EDT2 programme team has developed and agreed with partners the definitions and applications of ‘standby’ and ‘mobilisation’ status ahead of a deployment. The programme team can use programme funds to place teams on standby, ensuring they are ready to deploy as quickly as possible following a final decision from FCDO.
2. The EDT2 team has also agreed the financing mechanisms for a deployment at pace where no Business Case exists, ensuring the programmatic requirements within FCDO do not delay the deployment of a team.
3. Work has been underway to amend the criteria for when we can deploy a team on a ‘no regrets’ basis.

These changes will ensure that, even when information is limited and decisions must be made quickly, we will be able to use ‘no regrets’ options. The changes have significantly improved deployment processes by ensuring improved decision making and clarity on preparing the teams to deploy.

Major lessons and recommendations for the year ahead
FCDO should continue to build on the progress achieved in Year 3 of the programme to maintain its bilateral response capabilities and external capacity-building partnerships, in alignment with the organisation’s humanitarian response priorities. Major recommendations to be taken forward in the following year are:

1. The EDT2 programme ensures it has sufficient resources to continue to fund assessment teams to Post through its emergency response fund. Being able to support this model has enhanced the timely and effective deployments of the EMT and ISAR.
2. FCDO should build on progress to enhance the UK’s capacity-building partnership offer. The programme should continue to deliver the capacity-building objectives approved within the EDT2 business case addendum. This will require using the full programme headroom agreed in the business case in FYs 2026-29.
3. Now that the capacity building strategy has been finalised, EDT2 should agree international partnership projects and work with UK-ISAR and UK-EMT to develop project plans for these.
4. FCDO should conduct an external evaluation of the programme to provide evidence on the impact of the interventions in delivering effective life-saving deployments and in strengthening the capacity of national first responders in priority countries.
5. The UK-EMT is uniquely placed to offer a high-quality rehab capability and the UK-EMT and FCDO should consider ways to highlight this work.
6. The UK-EMT and FCDO should also consider how to support the development of the WHO Highly Infectious Disease standards.
7. Following recently successful deployments focusing on burns rehabilitation, the UK-EMT and FCDO should consider strengthening the burns element of our rehabilitation offer in Year four (Y4) of the programme, through holding stocks of specific burns-related rehabilitation items.
8. FCDO should build on the achievement of UK-ISAR securing Known Consignor status by considering whether UK-ISAR can charter its own flights.
9. FCDO should further strengthen the EDT2 public engagement through external media, internal communications, recognition of partner volunteers, and in-depth stories about individual responders in the UK media.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The underlying assumptions of the Theory of Change remain valid and have been used throughout the reporting year to contribute to the outcome and impact of the programme.  The underlying principles are as follows:
The UK is a leader in global EMT and ISAR networks with experience and influence, adding value through flexible, proportionate response, working within international guidelines and with national systems and responders.
The UK does not unnecessarily duplicate or compete with teams from other countries.  As such the UK is well positioned through this programme to respond when required, mentor others and influence the system.
Strengthening emergency resilience in prioritised vulnerable countries through partnerships and capacity building with local and regional responders is the most sustainable way to prevent suffering and loss of life in the immediate aftermath of disasters.
Continued learning from responses, adapting to changing needs, and working within the international community to improve emergency response standards and coordination will lead to better future responses.

There has been no change to the outcome and impact indicators.  The impact statement for this programme is that: Lives are saved, suffering is alleviated, and dignity is maintained for people affected by disasters and spikes in need during protracted humanitarian crises. The overall outcome is that: Countries are supported through rapid, coordinated, and appropriate medical and search and rescue capabilities in the immediate aftermath of humanitarian disasters and spikes in need during protracted humanitarian crises.

There have been some significant changes to the programme following recommendations from the last annual review. The business case budget has been increased by £14.7m and has been extended by two years from June 2027 to June 2029. The increased headroom will cover the time extension, the procurement of a Type 2 facility and the related reclassification for the UK-EMT; and additional investment in capacity building initiatives.

Amendments have been made to the programme and partner logical frameworks in this review period, effective from Q3 2024/5. This annual review is based on the original logframe which covers year 3 of the programme. The logframe has been amended in collaboration with the partners to reflect programme changes, simplify reporting, incorporate lessons learned from deployments, and better capture how preparedness supports more effective future deployments.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to contribute to the expected outcome and impact. This is on the basis that delivery of the programme outcome, ‘Countries are supported by rapid, coordinated, and appropriate medical and search and rescue capabilities in the immediate aftermath of humanitarian disasters and spikes in need during protracted humanitarian crises’ appears probable.

FCDO has been effective in deploying UK-ISAR and UK-EMT for response and capacity building, while making significant improvements to the programme following recommendations from the previous Annual Review.

While there have been no UK-ISAR deployments this year, significant contributions have been made to building national capacity of first responders, and we have continued to see an increase in international engagements over the reporting period.

There has been a consistent requirement for the UK-EMT to deploy overseas in the year, including in; Lebanon, Rwanda, Bangladesh, DRC (Goma) and North Macedonia. Although not official UK-EMT deployments, the UK-Med team has continued to make a significant contribution in the Gaza and Ukraine responses. They have provided 40% of all EMT capacity inside Gaza and continue to provide frontline mobile medical teams and trauma surgical expertise in Ukraine.

There have been several opportunities to engage the public on development and humanitarian issues through the EDT2 programme. There has been widespread media reporting about the programme deployments and capacity building. There was widespread coverage in Newcastle/North-East media about a team member being deployed to Lebanon as part of the UK-Emergency Medical Team (BBC North East & Cumbria). See Annex A for a list of UK media coverage. There have also been several events where public/official recognition has been given to both EMT and ISAR teams in this reporting period. Four UK-ISAR individuals were awarded the humanitarian medal for the Morocco Earthquake (EQ); five UK-EMT team members were awarded humanitarian medals for the Morocco EQ and one member for the Libya floods (First new medal winner recalls 'extreme devastation' - BBC News). Additionally, 14 UK-Med members were awarded humanitarian medals for the Gaza deployment. One UK-ISAR member was awarded the British Empire Medal, and 3 UK-Med team members were awarded OBEs. The recognition of the teams gained significant media coverage; West Midlands firefighter says King's medal is a huge honour - BBC News. Two UK-ISAR search dogs were recognised at Crufts as Hero dog of the Year for the period of 24/25 (Hero Dog Award 2024 winner | The Kennel Club). The external recognition of the teams demonstrates the value placed on their work.

Over the next reporting period there will continue to be a focus on communicating the impact of the EDT2 programme, with the EDT2 team having developed a strategy for communications and engagement. It is recommended that a logframe indicator on communications for both partners is included in the programme logframe to ensure we are continuing to increase and monitor the internal and external visibility of the capabilities.

The UK-EMT and UK-ISAR are conducting a joint simulation exercise (SIMEX) in September 2025, this exercise will also be used for the reclassification of the UK-EMT as a Type 2. This exercise will present an opportunity to showcase the teams’ capabilities and our international partnerships. It is recommended that the EDT2 team, UK-ISAR and UK-EMT work to establish a joined-up scenario, where the work of both teams can be showcased to seniors in FCDO and as an external communications opportunity.
The MoU (Memorandum of Understanding) between Home Office (HO) and FCDO has expired. The agreement outlined how each organisation would collaborate, communicate, and coordinate to maintain an effective humanitarian emergency response capability. The refresh of the MoU will provide an opportunity to reset collective expectations for the deployment of UK-ISAR and their model of drawing on the wider fire and rescue services. While no major issues occurred during the previous MoU period, we are aiming to streamline UK-ISAR requests from other government departments and to clarify HCRD’s position on Civil Protection. The responsibility for the Fire and Rescue Services has been assigned to the Ministry of Housing, Communities, and Local Government (MHCLG) from the HO. It is therefore recommended that the EDT2 programme team and UK-ISAR refresh the MoU that is held between the HO, FCDO and UK-ISAR and include MHCLG.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

EDT2 remains an essential part of the UK’s emergency response toolkit to deliver lifesaving support, strengthen diplomatic relations, and deepen UK public engagement in overseas aid. The successful and lifesaving deployments this year demonstrate that the programme remains valid and should continue. As stated in the business case, EDT2 is positioned within FCDO’s Humanitarian Framework as contributing to more prioritised and effective humanitarian responses and has delivered against this throughout the reporting year. It has responded to humanitarian emergencies prioritised by FCDO and has begun work to support and complement local emergency responders through capacity building. It is not foreseen that the UK would want to cease or amend the programme objectives at this mid stage, following the agreement to extend and invest in the current programme.

Through EDT2’s international partnerships in capacity building and training, the programme offers a unique way to deliver UK expertise to partner countries. This support combines disaster risk management and resilience and is targeted at priority countries for FCDO engagement, including Commonwealth and NATO members, as well as high-risk, disaster-prone countries where national capacity may be limited. Continuing the investment in this offer via the funding agreed under the business case addendum will ensure these partnerships are strengthened. It will also allow the programme to gather evidence from a broader range of contexts, supporting FCDO in exploring how similar projects could be replicated to strengthen bilateral disaster risk management systems in other countries, independently of the Centrally Managed Programme (CMP). With strong evidence from our partners of the benefits to their own deployment systems, readiness, and skills maintenance, it is strongly recommended that this work continues alongside retaining the international response capabilities.

## C. DETAILED OUTPUT SCORING

Output Title	UK maintains highly effective emergency response capabilities, relevant to humanitarian needs, drawing on skills and expertise, which are readily deployable in response to disasters.
Output number:	1	Output Score:	A+
Impact weighting (%):	50%	Weighting revised since last AR?	N/a

Indicator(s)	Milestone(s) for this review	Progress
1.1 ISAR staff that have undertaken all required training and have attended national training exercises.	Team capability maintained per agreed training and exercising targets (Y/N)	Target Exceeded – 100% of staff have undertaken all required training and have attended national training exercises. / 100% staff completed specialist and technical support acquisition, and maintenance courses and capability maintained. / UK-ISAR completed 3 national training exercises, exceeding their target of 1.
1.2 The UK-ISAR team has a mission ready complement of logistical support, medical care and operational equipment.	Support arrangements and equipment readiness maintained per agreed operational cache and Known Consignor targets (Y/N)	Target Met – All capabilities and equipment maintained. / Known Consignor status achieved and equipment ready to be deployed on a Known Consignor basis. / UK-ISAR have 8/10 canines ready to deploy but does not impact mission readiness.
1.3 UK-EMT roster that have undertaken mandatory training and have participated in simulation exercises	Team capability maintained per agreed training and exercising targets (Y/N)	Target exceeded: / All deployments were staffed appropriately, and UK-Med have met the target on the number of annual simulation exercises completed.
1.4 The UK-EMT team has a mission ready complement of logistical support, medical care and operational equipment	Type 1 facility, additional medical kits and T1+ inpatient capacity and Type 2 procurement complete (Y/N)	Target Met: / All capabilities and equipment maintained. / The procurement of the Type 2 has been completed in the short timeframe agreed.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output is designed to ensure the UK International Search and Rescue (UK-ISAR), and UK Emergency Medical team (UK-EMT) capabilities are maintained and accredited by the International Search and Rescue Advisory Group (INSARAG) and the World Health Organisation (WHO) respectively.  It is focused on ensuring the teams maintain a state of readiness to respond to sudden onset emergencies. The output has been scored an A+ as the targets were either met or exceeded, including additional activities agreed in-year.

UK-ISAR:
100% (240) persons have completed all required training. 100% of persons have completed technician acquisition and maintenance courses. 100% persons have completed specialist and mission readiness training, in areas such as cultural awareness, Assessment, Search and Rescue (ASR), navigation, Safety and Security, Safeguarding, Base of Operations (BoO), Reception and Departure Centre (RDC) / Urban Seach and Rescue Coordination Cell (UCC) awareness. UK-ISAR have completed 3 national training exercises; UK KINVERSTAN 6, Singapore Exercise MERLION 4 and UK Exercise UPKEEP.

This year saw UK-ISAR deliver the first International UCC training course held at the National Resilience Centre of Excellence in Merseyside, with delegates from countries including Algeria, Korea, South Africa, Oman, Malaysia, France, Spain, Italy, Turkey and Germany. The UK-ISAR training course revision is supporting team members to develop the skills, knowledge and understanding to deploy safely overseas. Advances to standardise and accredit (to quality assure) the UK-ISAR annual training and development programme have led to improvements to their training package, setting the standard for others to follow. The standardisation is allowing for courses to be combined to maximise delegate contact times, value for money (VfM) and to support the Fire and Rescue Service (FRS) with releasing their teams at no cost to the EDT2 programme.

The UK-ISAR heavy equipment cache has been maintained at a constant state of mission readiness and complies with general requirements as determined by the INSARAG guidelines. This includes planned and agreed maintenance, Readiness & Deployability and asset refresh programmes. The UK-ISAR team has a mission ready complement of logistical support, coordination, administration, IT, with appropriate maintenance and storage arrangements. All equipment was tested during the monitoring of the Myanmar Earthquake in April 2025 and assured as ready. UK-ISAR is equipped to deliver the required level of effective medical care in support of UK-ISAR deployments and has maintained the appropriate contract for all items and drugs required. UK-ISAR has purchased an updated full secondary cache of equipment in year 3 on schedule.

UK-ISAR has 8 of the agreed 10 Search and Rescue dogs available for immediate deployment and two further in training. Four other UK-ISAR services are actively recruiting handlers and looking to purchase or source canine live scent dogs. UK-ISAR mirrored the national course for grading of search dogs in January and completed a comprehensive 3-day training course facilitated by external instructors.

The operational cache is available and ready for deployment with full Known Consignor status. All the necessary logistical support is in place with approved Known Consignor accreditation, including transportation and warehousing. UK-ISAR has completed the required training to meet Known Consignor status. Ten team members from Merseyside Fire and Rescue Service (MFRS) have been trained, with plans to expand training to additional teams to strengthen overall resilience.

UK-ISAR demonstrated strong VfM through this output with the donation of a vehicle from South Yorkshire Fire and Rescue Service for transporting the deployment cache to and from exercises and airports when deploying. This will support the Known Consignor project and will be used for delivering equipment to regulated agents at any designated deployment airport.

UK-ISAR has exceeded expectations in relation to this output. They have ensured the maintenance of existing team capability and equipment whilst also delivering on agreed programme improvements, including gaining Known Consignor status, addressing a key lesson learnt from the Turkey Earthquake deployment. UK-ISAR have gone above requirements by streamlining their training offer and creating innovative approaches to international training exercises. UK-ISAR have also demonstrated a focus on value for money through this output via changes to the delivery of training and securing the donation of a vehicle for their Known Consignor work.

UK-EMT:
The number of on-call Register Members who are ready to deploy for the UK-EMT in Y3 was 986, significantly exceeding the target of 520. The UK-EMT responses were appropriately staffed for 100% of FCDO requests, according to the ToRs agreed by FCDO and UK-Med. The percentage of deploying register members and core staff fully trained was 80%. The UK-EMT conducted 2/2 of the agreed annual simulation exercises.

During this reporting period UK-Med responded to six FCDO requests for deployment. Deployments have included:

Lebanon – Conflict response with Rehabilitation Specialised Care Team (October 2024 - March 2025)
Rwanda – Disease outbreak response (October – December 2024)
Bangladesh – Surgical/rehab response to trauma patients (November 2024)
Goma, DRC – Conflict response with Surgical Specialised Care Team (March-April 2025)
North Macedonia – Rehabilitation/Burns response to nightclub fire (March – April 2025)
Myanmar – Rapid Assessment Team in response to Mandalay earthquake – deployed from 31st March 2024 to 13th April 2025

UK-Med have also continued to support the wider FCDO response to the conflict in Gaza as a WHO-classified team in their own right, with the deployment of their own EMT and Field Hospital set up. This operation has placed significant demands on the organisation and required focused attention at Board level due to its high-risk nature. However, it has not had an impact on EDT2 deliverables and instead has contributed valuable expertise and development for medical roster staff, as well as made a substantial contribution to healthcare delivery in Gaza.

The UK-EMT defined ‘fully trained’ as: having fully completed the minimum mandatory training requirements. The minimum training requirements consist of six learning activities, all of which can be completed remotely and all of which do not expire.

As part of deployment preparation, the following training was delivered in the reporting period:
Core Training activities:
Blended Hazardous Environment Awareness Training (HEAT) - took place online each month for a total of 28 participants. Safeguarding Pathway – took place online each month for a total of 47 participants. Selection Training – took place for 38 participants. Deployment Course – took place in person for 49 participants.
Specialist training:
Outbreak Training – took place online in June for 26 participants. Training of Trainers – took place in person in May in Nairobi for 11 participants. Advanced Safeguarding Training – took place online for 8 participants. Nutrition in Emergencies Training – took place online in September for 12 participants. Integrating Trauma Based Approaches – takes place online quarterly, this was attended by 23 participants. Assessor Training took place in person for a total of 12 participants from UK-Med Core Staff team.

A Hostile Environment and Awareness (HEAT) Simulation Exercise (SIMEX) took place on 27-28 July 2024. This was a 1.5-day culmination of the online Blended HEAT training and attendees included Register members and new deployable Core UK-Med staff. The UK-EMT Outbreak SIMEX took place on 16-18 September 2024. The two-day exercise was a culmination of the online blended Outbreak Training Pathway, focusing on the establishment and management of a Cholera Treatment Centre. Representatives from the Ethiopian EMT and the Pakistani NGO MERF participated in the event, while members of the UK Public Health Rapid Support Team (UK-PHRST), UK-ISAR, Ethiopian EMT, and FCDO observed the event. UK-Med designed and incorporated leadership specific learning objectives and had dedicated response management and humanitarian coordination injects.

100% of UK-EMT equipment and supplies are appropriately warehoused and the UK-EMT maintains the ability to procure, store, and handle pharmaceuticals. Readiness status per capability as of 31/03/2025:
- Type 1 Fixed: 100% of required supplies and equipment in place. Dangerous Goods paperwork can be done only immediately prior to deployment when consignee address is known.
- Type 1 Plus: 100% of required supplies and equipment are in place.
- Type 1 Mobile: 100% of required supplies and equipment are in place for 3 mobile teams.
- Trauma/Surgical Specialist Care Team (SCT): 100% of required supplies and equipment are in place.
- Infectious Disease Outbreak SCT: 90% of required supplies and equipment are in place. Non-critical pharmacy is pending delivery.
- Rehabilitation SCT: 100% of required supplies and equipment are in place.
A significant milestone for the reporting period was the procurement of the Type 2 equipment. All procurement is now complete with a few items that will be delivered in April 2025 (generators, incinerator, some WASH items, and the Reverse Osmosis System). Work on modularisation and palletisation is in progress, with the aim of having the capability fully ready for deployment by the end of April 2025.

The logistics team has continued to support the dispatch and shipping of kits, supplies and communication equipment for the on-going and new deployments (DRC and North Macedonia) as well as supporting the planning for the upcoming training events (Deployment Course and SIMEX).

In October 2024, the UK Emergency Medical Team (UK-EMT) received its October 2023 classification report, which commended the team for its outstanding rehabilitation capabilities, stating that they “demonstrate an excellent specialist cell capacity for rehabilitation and could set the standard for others to follow.” In addition to several rehabilitation-focused deployments, the UK-EMT has consistently demonstrated its strength as a Rehabilitation Specialised Care Team (Rehab SCT), offering a unique and valuable contribution in this field. Notably, the UK-EMT is one of only two teams globally verified by the World Health Organization (WHO) as a Rehab SCT. With extensive deployment experience, the team effectively delivers a wide range of rehabilitation interventions aimed at optimising functionality and reducing disability. Further information on the benefits and case studies of the UK-EMT Rehab SCT can be found in Annex B.

The UK-EMT has exceeded expectations in relation to this output. They have demonstrated their deployability with a high number of deployments over the year; including two occasions where three teams were deployed simultaneously. This shows that their preparedness activities are enabling them to deliver multiple deployments at the request of FCDO. Whilst responding to these requests to deploy, the UK-EMT has ensured they are maintaining their team capability and equipment requirements. The logistics team have also remained flexible throughout the year, enabling the full procurement of the necessary equipment for the Type 2 facility to be completed in this reporting period.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The EDT2 SRO has been working to agree the FCDO’s approach to civil protection which has implications for the programme’s capabilities. It is recommended that the EDT2 programme capabilities are available on a case-by-case basis for use in civil protection responses overseas, so long as this remains in scope of the teams’ pre-existing capabilities. To prevent affecting the core deliverables of the business case, the teams should not expand their capabilities to cover civil protection responses. This includes areas such as conflict stabilisation, infrastructure repair and wildfire response.

The milestone target for the number of canines ready to deploy for UK-ISAR has been revised down from 12 to 10. This was agreed as the reduction in the target would not impact the team's ability to deploy, whilst ensuring there remained some contingency in the number of available dogs. It is recommended that FCDO closely monitors progress to return to the target number of 10 canines, up from the 8 currently available and work closely with UK-ISAR to mitigate any barriers to doing so.

As UK-ISAR are recognised for conducting international exercises, UK-ISAR should consider how these fit with their current capacity building offer and how this can be effectively captured under output 2.

It is recommended that, to strengthen UK-ISAR’s progress to improve deployment speed and self-sufficiency, UK-ISAR should provide a review and recommendation to FCDO on their ability to take over the chartering of their own flights.

It is recommended that, following the successful procurement of the Type 2 field hospital, the UK-EMT should review the potential benefits of gaining Known Consignor status for their warehouse and make a recommendation to FCDO. This should consider VfM and the potential for this to speed up deployment processes.

Two of the UK-EMT milestones were adapted during the year. The milestone for the number of UK-EMT SIMEXs was revised down from 3 to 2. This was agreed as the reduction in the number of events would not change the number of people trained and would enable better focus on delivering a smaller number of quality exercises.

UK-Med has been following WHO EMT Blue Book guidelines by requiring Register members and Core staff to present a BSAFE (online security awareness training) certificate which has been completed two years (maximum) prior to deployment. However, as of 2024-25, UK-Med is reporting Register members and Core staff who have completed BSAFE at any point as being fully trained. This change in approach has significantly improved completion rates for all six responses in the 2024-25 reporting period. The change in approach does not impact on the suitability of deployees but ensures a pragmatic and sustainable approach to ensuring team members meet UK-Med requirements to deploy.
[note] Classification and minimum standards for emergency medical teams

The UK-EMT demonstrated their strength as a rehabilitation SCT throughout this reporting period, including through their re-classification in October 2023 and through multiple deployments. Rehabilitation work featured as a major component of the UK-EMT deployments in Lebanon, Bangladesh and North Macedonia. The UK-EMT are uniquely placed to offer this capability at a very high quality and the UK-EMT and FCDO should consider ways to highlight the benefits of this work. Following recent successful deployments focused on burns rehab, the UK-EMT and FCDO should consider strengthening the burns element of our rehab offer and ways of leveraging the partnership with Interburns. To enhance rapid and effective burns response, the UK-EMT should maintain a larger stock of burns-specific rehabilitation and patient care items. These can support both Rehab SCT deployments and Type 1/2 facilities when needed, expanding capacity for time-critical care and improving outcomes for patients. As one of the few global EMTs capable of responding to burns rehab, the UK-EMT should leverage this unique strength.
[note] Interburns | Transforming burn care in Asia, Africa and the Middle East.

In Y3 of the programme the UK-EMT has also demonstrated its success as a Highly Infectious Disease (HID) team. The FCDO should consider potential support, through the EMT Secretariat, to WHO on developing the HID Specialized Care Team (SCT) classification. The EMT Standards for Highly Infectious Diseases were released in 2024, but to date the mentoring process, relevant documentation and pathway to classify against these standards as a HID SCT do not exist. Supporting in-kind technical assistance to the EMT Secretariat would help to develop these vital tools for the EMT network and would enable the UK-EMT to be the first global team to achieve this status once the pathway is established.

There are also several outbreak-linked initiatives which the UK-EMT is now part of, including the INITIATE2 project in WHO. This project aims to standardize rapidly deployable Outbreak patient care modules and Personal Protective Equipment. The UK-EMT sent the Outbreak Lead and a Logistics Manager to a training held in April 2025 in Italy. This training showcased the clinical setup and incorporated feedback for eventual bulk procurement for listed partners. The UK-EMT should consider holding these units as they are cost-effective and easily replenishable by the INITIATE network when utilised.
[note] Initiate2

Output Title	First responders in priority countries have greater knowledge and capacity to provide coordinated and timely response following disasters.
Output number:	2		Output Score:	A
Impact weighting (%):	20%		Weighting revised since last AR?	N/a

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of ISAR capacity building programmes delivered	2	Target exceeded – 6 capacity building programmes delivered.
2.2 Percentage of ISAR responses that include capacity building and equipping national stakeholders	100%	N/a - no deployments in this reporting period.
2.3 Number of UK-EMT capacity building programmes delivered	2	Target not Met: / ½ of the capacity building programmes delivered.
2.4 Percentage of EMT deployments that include capacity building for national stakeholders	100%	Target Exceeded: / 100% of deployments included a capacity building component, delivered to a high-quality.

This output is designed to ensure the UK International Search and Rescue (UK-ISAR), and UK Emergency Medical team support first responders in priority countries to gain greater knowledge and capacity in order to provide coordinated and timely responses following disasters. The output has been scored an A as the eligible targets were either met or exceeded, with the exception of one target missed for reasons outside of UK-Med's control.

Briefly describe the output’s activities and provide supporting narrative for the score.

UK-ISAR
UK-ISAR has completed six successful Capacity Building Projects in 2024/25 (Year 3) exceeding their target of 2 projects. The projects are as follows:
- Gibraltar - Crisis and Disaster Coordination and preparedness.
- Singapore (Operation Lionheart) - Timber shoring/ INSARAG External Reclassification (IER) preparation and process/comprehensive portfolio of evidence (CPOE) in person.
- Malawi - Flood response strategic and tactical (boat operations) and boat repairs and readiness/ training.
- Kenya – Urban Search and Rescue (USAR).
- Greece (Rhodes) - Crisis management and Spontaneous volunteers.
- Ukraine Convoy - Donating FRS equipment.

UK-ISAR recently conducted a scoping mission to Tajikistan, offering recommendations for a long-term capacity-building project. Discussions with the British Embassy in Dushanbe are ongoing to define the next phase of work. Early feedback indicates the project is already having a positive impact, with the intervention highlighted at a high-level meeting by the Head of the Committee of Emergency and Civil Defence (COES). INSARAG accreditation is now emerging as a Tajikistan government priority. The visit also enhanced UK visibility and strengthened ties with COES.

The UK-ISAR team conducted a flood response training in Malawi in February. The efforts of the UK-ISAR team were greatly appreciated by both the government of Malawi and World Food Programme (WFP), with a letter of thanks being shared with FCDO. The letter noted ‘This timely intervention has significantly improved our operational readiness and ability to respond effectively to emergencies, particularly in flood-prone areas. We are deeply appreciative of the commitment, expertise, and collaborative spirit shown by the UK-ISAR team and the broader FCDO team.’ A small team returned in March to conduct further boat repairs. This low-cost additional intervention has complimented the training to ensure both the teams and equipment are ready to respond ahead of cyclone season.

The UK-ISAR team conducted an Urban Search and Rescue (USAR) training in Kenya for the Disaster Response Battalion (DRB) and National Disaster Management Unit (NDMU). The training followed an initial scoping visit and aimed to develop both teams in preparation for future USAR responses, whilst conducting a wider gap analysis of their capabilities to inform recommendations for future interventions. The DRB and NDMU provided feedback that the training was highly appreciated, and participants were confident that they could apply the skills they learned. UK-ISAR have made recommendations for the next steps, and discussions are ongoing with Post.

UK-ISAR have not deployed during Y3 of the programme, so indicator 2.2 is not applicable for review.

UK-ISAR exceeded on this output. UK-ISAR have demonstrated an ability to provide a diverse range of capacity building initiatives across the year. Over the coming year, supported by the development of the EDT2 capacity building strategy, it is recommended that UK-ISAR and FCDO develop a plan for their capacity building projects for the remainder of the programme.

UK-EMT

The UK-EMT have delivered one out of the two target capacity building projects. This was due to original plans to deliver capacity building in Zambia not being able to progress. As part of the cholera response in Zambia, the Zambian Ministry of Health and National Public Health Institute had expressed interest in classifying as an EMT, and conversations around establishing a twinning project had taken place. Interest in classifying as an EMT did not come to fruition, limiting the UK-EMT’s ability to deliver the two agreed projects.

The UK-EMT has however, made significant progress with their capacity building project with Ethiopia. Procurement of a Type 1 Field Hospital for the Ethiopian EMT was completed at the end of the reporting period. The joint SIMEX between UK-EMT and Ethiopia EMT took place in June 2025. The SIMEX had two overall aims: 1) UK-EMT to support and capacity strengthen Ethiopia EMT Core Team members’ ability to design, plan and run immersive simulation exercises and 2) to exercise a scenario where an international EMT embeds in a national EMT’s structure and under their management.

The Ethiopian EMT has been supported by the UK-EMT to develop their 5-year National Emergency Medical Team strategy. The UK-EMT has provided ongoing remote follow-up and advice to the Ethiopian EMT on their preparation training activities for their roster members. The UK-EMT has also supported the Ethiopian EMT’s Team Leader Training.

All UK-EMT responses included a capacity building element. Some highlights of these are below.

Lebanon – A total of 251 professionals received training from the UK-EMT, equating to a total of 56 hours of training activities. Stakeholder feedback showed that the UK-EMT had provided high quality on the job training and capacity building activities. The partnership with Lebanese Order of Physiotherapists (LOPT) was recognized by the Ministry of Public Health (MoPH) as key in strengthening national rehab capabilities and supporting LOPT’s efforts to form a national rehabilitation emergency team.

Rwanda – The team provided 92 bedside mentoring sessions over the 6-week deployment. The Infection Prevention and Control (IPC) specialist supported over 12 IPC capacity strengthening activities. They also delivered training to 162 health care professionals on IPC protocols. The EMT trained 338 (including 100% Marburg Emergency Medical Service personnel). The management team at Central Hospital University Kigali (CHUK) expressed gratitude for the support provided and extended an invitation for future collaboration.

Bangladesh – Whilst providing care directly to the patients injured, the UK-EMT were also able to provide rehab capacity building in the hospital. This included: peer-to-peer mentoring and the integration of UK-EMT’s documentation practices into the hospital’s operations which underscored the value of collaborative capacity building.

North Macedonia – Two of the three UK-EMT objectives were focused on capacity building: to develop Burn Rehabilitation competencies of Ministry of Health (MoH) staff and to increase awareness of the importance of Infection Prevention and Control (IPC) measures in departments or inpatient facilities. The impact of the training has been noted as increasing awareness of both rehab and burns treatment across MoH participants. The UK-EMT was thanked for their commitment by the Deputy Health Minister and the British Ambassador.

Overall, the UK-EMT met expectations in relation to this output. This assessment is due to output 2.3 partially not being met. The UK-EMT has, however, provided extensive support to the Ethiopian EMT, delivering both training and logistics requirements for the project to a high-standard. The UK-EMT also demonstrated very highly skilled capacity building interventions throughout their deployments.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Since the last annual review, significant investment has been made in this output. The EDT2 programme team has developed an internal capacity-building strategy now being integrated into FCDO’s bilateral disaster risk management partnerships. The UK-EMT has also compiled a prioritised list of potential partnership opportunities according to WHO priorities. This approach supports FCDO priorities on health, humanitarian response, and climate by strengthening locally led disaster response through international cooperation. Pilot projects have shown strong host country interest, tangible results, and potential for broader partnerships, including with regional blocs, the Commonwealth, and Overseas Territories. It is recommended that the EDT2 gather any lessons learnt from the UK-EMT/ Zambia capacity building project that could not proceed. Country selection for EDT2-funded partnerships is currently being finalised. It is recommended that the programme continues with its current ambitions for EDT2 capacity building to deliver the objectives approved within the EDT2 business case addendum. This will require utilising the full programme headroom agreed in the EDT2 business case in FYs 2026-29.

The UK-EMT have been gathering a strong evidence base for their work in Ethiopia through a range of formative monitoring, learning, and adjustment activities. There are plans in place to conduct a summative evaluation with potentially a light touch contribution analysis. It is recommended that the EDT2 team and delivery partners continue to build a strong evidence base on the impact of this capacity building work, to ensure we can communicate the benefits of this work.

The EDT2 team should use this to work closely with the FCDO Humanitarian Crisis Response Department (HCRD) Preparedness team to highlight this offer to posts, both in preparedness activities and in the aftermath of responses.

Output Title	Evidence is generated to improve the international system, enabling the UK to play a significant role, and maximise leverage, when engaging internationally in working groups to set standard and best practice.
Output number:	3			Output Score:		A+
Impact weighting (%):	20%			Weighting revised since last AR?		N/a

Indicator(s)		Milestone(s) for this review			Progress
3.1 UK-ISAR make effective contributions to international, regional, national, and technical meetings, that lead to improved guidance and processes		7 Working Groups (WGs) and 1 co-chair			Target Met: 7 persons actively involved in INSARAG Working groups
3.2 Number of effective contributions to international, regional, national EMT and Technical Working Group meetings based on lessons learned from response and exercises		3			Target exceeded: / UK-EMT ensured representation on 7 WHO EMT Working Groups

This output is designed to ensure the UK International Search and Rescue (UK-ISAR) and UK Emergency Medical team (UK-EMT) support improvements to the international system, enabling the UK to play a significant role when engaging internationally in working groups to set standards and best practice. The output has been scored an A+ as the targets were either met or exceeded.

Briefly describe the output’s activities and provide supporting narrative for the score.

UK-ISAR

Seven UK-ISAR personnel are actively involved in INSARAG Working Groups (WGs), supporting INSARAG’s core mission to strengthen the coordination and effectiveness of international Urban Search and Rescue (USAR) assistance. The WGs include the Medical WG, IER/ IEC (INSARAG External Reclassification/ INSARAG External Classification) WG, Training WG, Capacity Building WG, Information Management WG, Guidelines review WG, Flexible response WG and Flood response WG.

UK-ISAR has held three working group meetings in the UK for the Africa, Europe and Middle East region (AEME), Global Medical Working Group, Global Training Working Group AEME region Flood Response, AEME region Search and Rescue (SAR) Working group.

In 2024/25, UK-ISAR participated in key INSARAG events, including the Team Leader Meeting in Tunisia, AEME Regional Meeting in Doha, and the Steering Group in Geneva. Two members also served as mentors during the Netherlands NL-01 IER. The UK-ISAR National Coordinator, as co-chair of the Flood Response SAR Working Group, has driven progress to ensure timely delivery of workstreams, Terms of Reference (ToRs) have been established, and objectives are on track for INSARAG Steering Group (ISG) approval.

UK-ISAR attended team leaders training in Doha and UK-ISAR had classifiers at the following IER:
- Logistics Classifier in training for USA-02 IER on 13 - 19 May in Los Angeles, USA.
- Rescue Classifier for NZL-01 IER on 28 - 30 May in Auckland, New Zealand.
- Rescue Classifier for RSA-01 IER on 20 - 27 August – Cancelled.
- Deputy Team Leader (DTL) Classifier in training for AUS-02 IER on 14 - 18 October.
- Rescue Classifier for QAT-01 IER on 25 - 28 November.
- Medical and Rescue Classifier for HUN-01 IER on 02 - 05 October, Bulgaria.
- Medical Classifier for CHL-01 IER on 30 May - 2 June in Santiago.
- Rescue Classifier for FRA-02 IER on 31 March- 4 April in Sancoins.
UK-ISAR has met expectations in relation to this output, it is evident that UK-ISAR are making a significant contribution to the international system through their ongoing engagement at a number of WGs, helping to shape the future direction of INSARAG. The UK is also making a significant contribution to the INSARAG system supporting with the IER classification process. These efforts maintain UK-ISAR standing as a strong supporter of the INSARAG network, working effectively with the international system to ensure continuous improvements.

UK-EMT

The UK-EMT ensured representation on 7 WHO EMT Working Groups, exceeding the agreed target of 3.
- Mental Health and Psychosocial Support (MHPSS) and SCT Minimum Standards
- Social and Behavioural Research
- WHO EURO Region Steering Committee
- Rapid Response Capacity
- Surgical SCT
- Medevac SCT
- Knowledge and Information Management
Key highlights include the formation of the Rapid Response Capacity Working Group, aimed at aligning rapid response modalities (e.g. EMTs, public health teams) and reducing duplication. Three meetings have been held to draft the ToRs for Technical Working Groups and sub-groups. Surgical WG standards are going through final internal review before external consultation and Strategic Advisory Group (SAG) approval. Medevac standards, with UK-EMT input, have completed consultation and await final SAG approval.

The UK-EMT research team published three academic papers in open access journals. The UK-EMT ensured local community members were actively contributing to the research process.
- https://www.cambridge.org/core/journals/disaster-medicine-and-public-health-preparedness/article/what-do-32-covid19-deployments-of-emergency-medical-teams-tell-us-about-challenges-and-lessons-learned/F13403C38A9D93CCDB54480A94071351
- https://www.cambridge.org/core/journals/disaster-medicine-and-public-health-preparedness/article/what-do-patients-seek-care-for-at-a-health-facility-in-the-aftermath-of-an-earthquake-experiences-from-an-emergency-medical-team-in-turkoglu-turkiye-2023/526E8940FAADBA15631183BF7C84DEBA
- https://iris.who.int/bitstream/handle/10665/380077/1020-3397-2024-3012-807-855-eng.pdf?sequence=1#page=8
The EMT is currently collaborating with national and international academic institutions on six research projects to capture best practices and lessons from UK-EMT deployments. Findings will be shared across the EMT network and with stakeholders to support advocacy and strengthen national humanitarian responses.

The UK-EMT has exceeded expectations in relation to this output, it is evident that the UK-EMT is making a significant contribution to the international system. They are supporting a wide range of WHO EMT working groups, driving progress within these groups. In addition, the UK-EMT has continued to produce and publish high-quality academic research papers over this reporting period.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There has been a considerable amount of research that has been delivered and that is underway. The UK-EMT should consider how to capture their research work within the log frame for Y4, taking into account the publication process is beyond the control of UK-EMT.

The UK-EMT should remove indicator 3.2 ‘number of core UK-Med staff trained as WHO mentors and EMTCC coordinators’ from their partner log frame as the output is largely dependent on the capacity of WHO and beyond the control of the UK-EMT.

Output Title	To develop and aim to provide necessary MEL of the programme to ensure we are continually improving the programme.
Output number:	4			Output Score:		A
Impact weighting (%):	10%			Weighting revised since last AR?		N/a

Indicator(s)		Milestone(s) for this review			Progress
4.1 The programme demonstrates good Value for Money		Partners meet VfM indicators as per agreed targets (Y/N)			Target Met: / Both partners demonstrated strong value for money, provided timely reporting, and demonstrated efforts to ensure equity. Variance on their final spend for this FY was well below the agreed maximum.
4.2 The programme follows a Monitoring, Evaluation and Learning strategy		Development of MEL plan and mid-term evaluation procurement started			Target Met. Plans are underway to progress the evaluation in Year 4 of programme. / UK-Med has a Monitoring, Evaluation and Learning (MEL) Plan for the programme. / UK-ISAR have not undertaken MEL but do have a formalised approach to Monitoring and Learning. One recommendation noted during their ongoing due diligence assessment is that this plan should be shared with the FCDO.

This output is designed to ensure the UK-ISAR and UK-EMT provide quality reporting and that the programme team delivers the necessary MEL of the programme to ensure continuous improvements and VfM. This output scored an A as all outputs are on track for delivery.

Briefly describe the output’s activities and provide supporting narrative for the score

UK-ISAR
UK-ISAR has provided all quarterly reporting to agreed deadlines and has produced them to a high-quality standard.
UK-ISAR had forecasted a slight underspend of less than 1% at the final stage, the actual underspend was 0.43% (£10,602).

UK-ISAR continue to drive our programme introduced Equality Diversity and Inclusion (EDI) objectives for 2022-2029 period which are as follows:
- Objective 1. Create and support an inclusive team approach that is positive, rising to the
- future challenges that UK-ISAR will face.
- Objective 2. Ensure that all people from diverse conurbations (inter)nationally receive
- equitable services from UK-ISAR.
- Objective 3. To ensure all UK-ISAR team members can undertake their role whilst
- understanding the need for and benefits of equality, diversity, and inclusion.
- Objective 4. To continue to aspire for equality, diversity, and inclusion excellence; measuring
- UK-ISAR against best practice and benchmarking tools used within the FRS and other
- sectors.

Some examples of how UK-ISAR have worked towards their objectives on Equity Diversity and Inclusion (EDI) include:
- Representation and Advocacy: Participating in and supporting events such as Aspora, the Annual Asian Fire Service Association (AFSA) conference, and Women in the Fire Service, where UK-ISAR has both delivered content and championed inclusion.
- Inclusive Opportunities: Creating and supporting safe, empowering environments for women during international programmes, such as in Malawi, where women have taken on strategic and tactical training roles within their organisations.
- Promoting Visibility and Professionalism: Demonstrating UK-ISAR’s commitment to equality and professionalism at both international and local levels, reinforcing inclusive values within the team.
- Driving Gender Representation: Actively maintaining and increasing the representation of women in UK-ISAR through positive action initiatives up to the point of application.
UK-EMT
UK-EMT has provided all quarterly reporting to agreed deadlines and has produced them to a high-quality standard.
UK-EMT have a 0% variance in their forecast and total spend for FY 24/5.
UK-Med has continued several streams of work to ensure diversity and inclusion in all programmes including EDT2 throughout 2024-25. UK-Med has ensured that fair and inclusive recruitment and management are central to their new Management Development Programme (training provided for all Core staff team managers) with specific sessions on recruitment and selection and EDI for managers.
They have increased the size of the UK-Med Register to 1,355 over the year. The gender split (as reported by members) is currently 48% female. As UK-Med diversify their workforce, UK nationals now make up 48% of Register membership, citizens of African countries 26%, citizens of other European countries 12% and citizens of Asian countries 7%. Other nationalities make up 7%.
All recruitment for the UK-Med Register is advertised openly, in all cases this includes public postings on the UK-Med website and listings on ReliefWeb. They also use other channels to reach a wider audience for specific roles where this is appropriate. All selection follows a robust process to ensure people are selected fairly based on pre-defined, relevant criteria.
Both teams met expectations in relation to this output.
Output 4.2
We have initiated early planning for the external evaluation of the programme, including initial discussions with a Monitoring and Evaluation advisor in FCDO to commence the process. These early conversations have focused on the tendering process and the type of evaluation the programme team aims to conduct. Work on this will continue in Y4.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

It is recommended that the plan to procure an external evaluation in Y4 of the programme continues to progress.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from Y2 AR	Progress
Recommendations 1-5 were aimed at addressing whether FCDO should hold a Type 2 EMT, review our approach to capacity building, review the overall timeframe of the programme, review the overall programme budget to synchronise the end dates, and to develop a business case addendum to cover the costs of the Turkey Earthquake response.	All of these recommendations have been addressed through the development of the programme review, addressing the questions of whether we should hold a Type 2 EMT and the future of the capacity building work. Following this a business case addendum was agreed; extending the programme by 2 years, securing a Type 2 EMT and enhancing the capacity building offer. This also enabled the EDT2 programme team to recover the costs of the Turkey deployment and synchronise the end dates of both partners under the programme.
Work closely with the Risk and Funds team within HCRD (formerly HRG) to establish how the use of the reintroduced Humanitarian Crisis Reserve can be operationalised to mitigate risks around the No Regrets criteria; and potential lack of a suitable business case to charge immediate upfront costs of EDT2 deployments.	This was addressed and an approach to this has been agreed, work has been completed to amend the No Regrets criteria to ensure it is suitable for EDT2 deployments.
Revise the overall programme results and risk frameworks considering the recommendations to partner level output indicators, MEL, and VFM indicators.	This has been partially completed, although more work is required to finalise the plans for an external evaluation. It is recommended this is reviewed again following the Y3 annual review.
It is recommended that both partners include qualitative reporting in their end of capacity building deployment reports to evidence their definitions of success.	Agreed.
The successful completion of the ISAR IER clearly demonstrates the high level of UK-ISAR capacity. The challenge for the remainder of the programme will be to maintain this level. Preparation for the next IER, due in 2028, the final year of this programme should begin immediately.	UK-ISAR is maintaining the IER preparation for the next IER in 2028.
ISAR training efforts should cover the basic requirements of newly joined members, continuous development and upskilling of existing members and an emphasis of identifying and building leadership skills. UK-ISAR identified 47 specialist courses being delivered. A catalogue of the 47 specialised courses being delivered could help to promote learning pathways.	UK-ISAR continues to train new recruits and enhance the skills of existing members through accredited courses. These courses, aligned with international field operations, use live scenario-based simulations to support development across all team levels. / Due to the training budget constraints, the catalogue is undergoing a full review of the necessary courses for the remainder of the current and new financial year. It is recommended this is followed up this FY.
ISAR should be maximising the ability to identify and incorporate lessons and best practices will support efforts to maintain capacity, not only through training evaluations and direct deployment lessons, but also in continuing to take advantage of external opportunities such as the EU Civil Protection exercises and joint exercises with other teams. Where possible, the team could consider deploying research capacity to ongoing responses, even if the full team is not deployed.	EU Exercises are not currently available to the UK. The training and inter-operability gaps with the EU teams have been flagged in UK-EU dialogue on the EU Civil Protection Mechanism. UK-ISAR have not been appointed any exercise to date. Spain has expressed support for UK participation in year four of the program.
The efforts of UK-Med to develop a Monitoring, Evaluation, Assessment and Learning (MEAL) framework could hold some best practices on which UK-ISAR could build	UK-ISAR maintains its own robust framework for monitoring, evaluation, development, and lesson learning. While UK-ISAR has reviewed the UK-Med system, it continues to use the FRS process.
UK-ISAR makes a significant contribution to the governance structure of INSARAG, including the development of policy and guidelines. Such engagement positions the UK as a leader in USAR and strengthens partnerships with a wide range of participating Member States. Reporting for the coming year should capture this important component of their efforts.	Completed as per log frame records. One UK-ISAR team member is in each (INSARAG) WG. Two Co-chair the Medical WG and Flood SAR WG.
Now that the flood rescue capacity is established and has been tested through exercises and a real-time deployment to Malawi during the last reporting period, UK-ISAR is helping INSARAG with developing and piloting a set of standards of excellence and team capabilities, given there are no defined IEC standards yet.	UK ISAR are engaging Africa, Middle East, and Europe (AEME region) and other Country teams via the Flood Rescue WG to support OCHA with mapping of capabilities and development of guidelines.
FCDO and UK-ISAR should consider an adjustment to the indicators of this output to better reflect developments of building the flood rescue capability so far.	Logframe amended.
UK-ISAR and FCDO should jointly examine the capacity building output and discuss opportunities for technical exchange i.e. for countries such as Taiwan and Singapore; feasible opportunities for long-term capacity strengthening endeavours i.e. with Kenya; and the opportunity to work with national fire and rescue services to strengthen the capacity of first responders.	Work in Tajikistan, Kenya and Malawi is underway. Capacity building will remain a focus for the programme in Y4.
As the most globally deployed EMT, UK-Med and FCDO should ensure that lessons are being captured. The newly designed Monitoring, Evaluation, Accountability and Learning (MEAL) framework will support this endeavour and should be closely supported.	Agreed. UK-Med is utilising their MEAL framework across both deployments and preparedness activities.
The roster of personnel is reaching 1200. UK-Med should consider the optimum size of personnel on the roster to ensure feasibility of training and deployability.	Agreed and included within their logframe.
UK-Med has put in place safeguards and has a clear safeguarding policy. Both FCDO and UK-Med should remain vigilant to the potential safeguarding risks and regularly verify the strength of safeguarding measures.	Ongoing. The EDT2 programme team are continuing engagement with UK-Med and following up recommendations from safeguarding cases.
This is the second year that the programme has not met indicator 5.3, albeit with justifiable reasons. It is essential that the UK-EMT continues to invest in the ability to exercise capabilities holistically either through simulation exercises or by capturing lessons – and reflecting on them - via the new MEAL framework. Opportunities to join simulation exercises run by other teams and other UK emergency deployment instruments could be explored.	Complete – Logframe indicator discussed and revised.
UK-EMT to update FCDO on how they are ensuring that training is completed upon departure and are working to establish more robust ways of both communicating with deploying staff and checking completions in real-time.	Definition of fully trained staff shared with FCDO alongside a clear induction pathway.
Capacity building and emergency preparedness have been demonstrated to be core components of UK-Med’s work and should remain a fundamental principle of responses to help ensure or re-establish access to quality essential health services. Indicator 7.1 requires longer-term timeframes to achieve than had been considered at programme design stage, given the delays in setting up the activity due to initial ODA budgetary constraints and the way that posts are funded to undertake bilateral capacity building initiatives. It is recommended to review duration and resourcing for this output.	EDT2 Addendum approved.
UK-Med should continue to strive for the inclusion of capacity building in responses, where feasible, as supporting national structures enhances national autonomy and the capacity to prepare and react in domestic and/or international responses. In some circumstances the immediate phase of the response does not allow for any capacity building due to the sheer volume of clinical work. However, as cases either subside or critical gaps are noted, capacity building should be integrated into workplans.	Discussed with UK-Med who have confirmed that capacity building is embedded as part of all deployments where appropriate.
UK-Med consistently raised concerns that the decision to reclassify as a Type 1 team without a field hospital capacity has limited our ability to engage with and influence the international system and EMT Secretariat and should be revisited considering changing operational contexts and the frequent requests for this capability from the international community.	EDT2 Addendum approved.
UK-Med should continue to identify more opportunities to include the work of the UK-EMT into research and academic papers. As an active member of the EMT community and the most deployed EMT globally this presents an opportunity to ensure these technical expertise and lessons from deployments are shared.	Completed more projects of this nature than planned this FY. Further discussions on an appropriate log frame indicator will be had following the Y3 annual review.
It is recommended that a logframe indicator is included for year 3 that captures partners ability to manage the programme monitoring; including production of timely reports, risk, and financial management.	Agreed and logframe amended.
EDT2 will benefit from conducting an external evaluation to provide an independent assessment of the programme. The decision was taken to conduct this evaluation in year 3/4	This is to be conducted in Y4 of the programme.
During the gap in the health advisor role the EDT2 programme team should draw on health expertise from elsewhere in FCDO, including from our delivery partners in HSOT.	Advice sought as appropriate – new Health policy lead was recruited.

## D: VALUE FOR MONEY

Key cost drivers and performance

In Y3, the main cost drivers for the programme remained the same; funding core staff across both teams, managing and training deployable rosters, and providing and storing essential equipment. Both teams have kept a strong focus on ensuring value for money in all expenditure. The EDT2 programme team has also made sure that value for money is a key consideration when reviewing any additional funding requests.

VfM performance compared to the original VfM proposition in the business case

Under Economy, the business case highlights the removal of the UK-EMT’s Type 2 as a key cost saving measure. In this year, the EDT2 programme team requested the reinstatement of the UK-EMT as a Type 2, as part of an overall business case addendum. The reclassification of the UK-EMT as a Type 2 team will significantly enhance its ability to deliver comprehensive and effective medical services in crisis settings, ultimately saving more lives and improving health outcomes, especially when inpatient care is required. This elevated status will also enable the UK-EMT to engage in higher-level partnerships and capacity-building efforts, participate more prominently in international forums and with the WHO. This will showcase the UK’s strengths in surgical care and patient rehabilitation, as demonstrated in recent deployments to Ukraine, Türkiye, and Gaza.

To ensure strong value for money, the programme has made effective use of existing resources. For example, tents originally intended for deployment to Gaza, which were ultimately unused, were repurposed for the Type 2 facility procurement within EDT2. This year, a standard Type 1 fixed medical facility was donated to the Ethiopian Public Health Institute (EPHI), including 12 tents and supporting equipment, fixtures, and fittings, to strengthen the Ethiopian Emergency Medical Team (EMT). Additionally, UK-ISAR received a donated fire and rescue truck from South Yorkshire Fire and Rescue Service. This vehicle is now used to store and transport UK-ISAR’s Known Consignor equipment cache, supporting their operational readiness.

The business case highlights that a key component of efficiency in humanitarian response is the speed of delivery. It also emphasises that strategic partnerships with key countries can enhance both the speed and quality of response. Over the past year, our EDT2 partners have delivered targeted capacity-building deployments in several crisis-prone countries, including Malawi, Kenya and Ethiopia. These deployments and strong partnerships help improve FCDO’s ability to respond to emergencies, while also strengthening the skills of local emergency teams through shared learning. We have continued to improve deployment speed, with UK-ISAR achieving Known Consignor status during this review period. Additional efforts have also been made to boost deployment efficiency. Notably, the FCDO organised a joint deployment workshop with UK-ISAR and the Humanitarian Stabilisation and Operations Team (HSOT), who charter UK-ISAR flights. This workshop aimed to address and reduce deployment delays identified in the programme’s risk register.

Effectiveness is defined as how well outputs produced by an intervention have the intended effect. The business case notes that this will be achieved using volunteer experts as the main source of deployable personnel. The EDT2 programme continues to rely primarily on volunteer experts, for UK-ISAR and UK-EMT to deliver targeted, high-impact support. By leveraging UK expertise across specialised areas, such as surgery, rehabilitation, and fire and rescue, the programme has expanded its reach.

This year has marked a significant increase in the number of rehabilitation deployments delivered by the UK-EMT, in a range of diverse contexts; responding in Lebanon, DRC (Goma), Bangladesh, and North Macedonia. Additionally, the National Coordinator in UK-ISAR plays a pivotal role in shaping international flood response systems as a co-chair for the Flood Rescue Working Group under INSARAG. Through UK-ISAR's active role in the Working Group the team contribute significantly to international disaster response frameworks, contributing to international guidance that strengthens coordination and operational readiness.

The programme considers equity by providing assistance on the basis of need irrespective of gender or other protected characteristics. Throughout 2024–25, UK-Med has continued to strengthen its commitment to diversity and inclusion. This includes embedding fair and inclusive recruitment practices into the new Management Development Programme, with dedicated sessions on Recruitment and Selection, as well as Equality, Diversity, and Inclusion (EDI) for managers. The deployment register reflects greater gender and national diversity, with 48% female members. To date the register is comprised of UK nationals (48%), African countries (26%), citizens of other European countries (12%), citizens of Asian countries (7%) and other nationalities (7%).

UK-ISAR continues to drive forward equal opportunities with women comprising 13% of the team. This is higher than the national fire service percentage which was 10.7% recorded in 2024. Throughout the year, UK-ISAR has actively continued to champion Equality, Diversity, and Inclusion (EDI) through participation in and delivery of key events, both nationally and internationally. The Diaspora event, supported by UK-ISAR, served as a pivotal occasion, bringing together diverse communities and sectors to celebrate cultural diversity, promote learning, and raise awareness. Additionally, Merseyside Fire & Rescue Service (MFRS) was recognised for its outstanding EDI commitment at the Annual Asian Fire Service Association (AFSA) Awards. UK-ISAR will continue to uphold positive action processes while recruiting team members.

Assessment of whether the programme continues to represent value for money

The programme has continued to demonstrate progress throughout the year in line with its strategic objectives, while ensuring value for money. These efforts reflect a well-managed and impactful programme that continues to deliver results in line with its business case objectives.

E: RISK

Overview of risk management

A due diligence assessment of Merseyside Fire and Rescue Authority (MFRA) as the lead partner for UK-ISAR was previously not required due to their status as an arm’s length body. Following recommendations made in the previous financial year, in line with best practice, work on a DDA has now commenced. The assessment is expected to be completed by August 2025. The refresh of the UK-Med DDA is underway.

The overall risk rating for the programme in the business case was moderate and continues to remain at moderate.

Risk frameworks are in place for both partners, and partner feedback on risk is included in quarterly reporting. The EDT2 programme team continues to monitor all risks and where possible supports with the implementation of the mitigations.

In line with the actions outlined in the previous annual review, the programme has effectively mitigated the three major risks identified in Year 2, namely, the UK-EMT’s classification as a Type 2; the recovery of costs from the Turkey deployment; and the lack of clarity surrounding deployment criteria (including on non-ODA spend, the Overseas Territories, and the FCDO’s appetite for non-humanitarian responses). Mitigating these risks has been crucial in ensuring the programme remains on track to achieve the intended outcomes.

In response to the risks identified under the EDT2 programme we have:
  - Provided an uplift to UK-Med to support the re-instatement of their Type 2 hospital and the reclassification as a Type 2 WHO-verified team.
  - Concerns regarding the lack of clarity around deployment criteria have been addressed through the development of clear internal guidance, including on responding to wildfires and handling non-ODA deployment requests.
  - The approval of the business case addendum has been instrumental in addressing the financial issues within the programme. It has also placed the programme in a stronger position to achieve its full potential and long-term ambitions, particularly in relation to capacity building.
The main risk to the EDT2 programme relates to the security of future funding. If the EDT2 programme does not receive the full budget in the final three years of the programme, this would constrain our ability to engage in further international partnerships agreed in the Business Case addendum. The current EDT2 budget is at a minimum threshold to maintain the two capabilities. Any requirement to reduce these budgets would have consequences on the programme’s ability to deliver against its outputs.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The business case outlines that the full complement of staff managing the programme should be a Senior Responsible Owner, Programme Responsible Officer, Programme Coordinator and Health Adviser. Since the departure of the Health Advisor in Q2 of Y3, the Humanitarian Adviser covered this position, playing a key role in seeking greater coordination and join-up with FCDO’s Global Health Directorate in preparation for and during responses. Despite the departure of the Health Advisor, there has generally been an improvement in overall team capacity and capability, improving the ability to deliver key programme objectives.

Following the framework of previous years in the programme, we have continued to maintain frequent quarterly meetings with partners to discuss performance, finance, and risk. To date the partners have been timely at submitting good quality finance and narrative information ahead of the meetings. Monthly meetings have been introduced to support ongoing discussions around risk, finances, and upcoming communications opportunities. These regular meetings have been key in identifying opportunities and addressing challenges in delivering programme activities.

In Y3, EDT2 undertook a substantial piece of work to progress a business case amendment. As a result, the programme received a significant uplift of £14.7m bringing its total value to £39.7m. In addition, the programme was granted a two-year extension. The amendment acted on recommendations from the Y2 EDT2 annual review to review; the classification of the EMT, the timeframe of the current programme, the approach for capacity building and recover costs from the Turkey response that were covered by EDT2. The amendment has proven highly advantageous in not only securing the programme’s continuity in future years but has also enabled the programme to pursue the full level of ambition it set out to achieve in the business case.

This year, both delivery partners received in-year funding increases to support readiness activities and deployments. For UK-Med, this funding supported deployments to Lebanon, Rwanda, Bangladesh, and North Macedonia, as well as participation in the WHO EMT Civil-Military Technical Working Group, twinning activities in Ethiopia (including procurement of the Ethiopian EMT’s Type 1) and procurement of the UK-EMT Type 2 medical facilities, and the two-year extension of the programme. For UK-ISAR, the uplift funded a capacity-building deployment to Malawi and a scoping mission in Kenya, alongside additional costs related to the programme extension.

Against UK-Med’s revised forecast following their uplift for the year, the final outturn was 0%. Against MFRA’s forecast for the year the final outturn was underspent by 0.43%. Budgets for Y4 will continue to be monitored closely, with in-year adjustments made as necessary, and it is recommended to monitor the budget variance from forecasts on a quarterly basis.

Throughout the year, the EDT2 programme team have developed several strategic plans and key pieces of work to ensure alignment with the objectives outlined in the business case, these include an internal capacity building strategy and communications strategy. As part of the capacity building workstream, we carried out an appraisal of capacity-building options under EDT2. This included reviewing potential countries and partnerships for investment, as well as exploring options for both EDT2-funded and Post-funded deployments. The findings were used to shape a comprehensive strategy for the programme. Looking ahead to Y4 and beyond, the programme aims to secure senior-level support for the strategy to enhance visibility of the programme's capacity building offer. Initial work to promote this began in Y3 and will be fully operational in the coming year. In light of uncertainty surrounding the budget in future years, we will continue to review and refine our capacity building approach throughout Y4, in preparation for the confirmation of the funding allocations for subsequent years.

To support the delivery of the EDT2 communications strategy, an EDT2 Communications working group has been instated to serve as a forum for exploring upcoming communications opportunities. The regular communications meetings have played a crucial role in fostering focused, strategic meaningful communications and engagement on the programme, ensuring appropriate visibility, and proactive communications. In addition, this has also been instrumental in identifying challenges and opportunities for improvement. In Y3 of the programme, work began to develop an updated Communications Standard Operating Procedure (SOPs) for both partners, which will be completed in Y4 and will provide clear guidance and consistency in operations.

G: MONITORING, EVIDENCE AND LEARNING

The EDT2 Programme team has developed a MEL strategy to enable a more systematic approach to MEL across the programme.

Monitoring
The monitoring inputs will be provided by the implementing partners and reviewed by the EDT2 programme team. This will be in the form of:
1. Quarterly reports
2. Quarterly risk updates
3. Quarterly financial reports
4. Quarterly partner log frame submissions
5. External reverification exercises or field monitoring from deployments
6. Partner Annual Reviews (AR)
The above documents (1-5) provided by the implementing partners will be reviewed by the EDT2 programme team and discussed at a quarterly meeting with each partner. This activity, along with the programme AR will enable the programme team to review progress and identify any corrective actions required and lessons to be learnt. We have also completed site visits to both delivery partners and conducted necessary asset checks.
Evaluation
EDT2 will benefit from an external evaluation to provide an independent assessment of the programme. The decision was taken to conduct this evaluation in Y4 of the programme to enable programme delivery to be underway and the initial adjustments and lessons learned from years 1, 2 and 3 to be embedded. The evaluation will provide an opportunity to review the progress of the programme to deliver against the theory of change outlined within the business case. It will also seek to evaluate the impact that the EDT2 programme has achieved through the sustained development of its capabilities. The evaluation will provide recommendations for any improvements that should be enacted within the EDT2 programme or potential future iterations of the programme.

Learning
As part of the MEL strategy, the EDT2 programme team will help to coordinate lessons learned following deployments. The partners will be responsible for providing a lessons learned report following their deployments which will be discussed with the EDT2 programme team to highlight any actions required. The EDT2 programme team will also facilitate the gathering of lessons learned from posts to gain any feedback and actions required. These lessons learned should be captured within a month of the end of a deployment and learning/ actions shared with partners and wider FCDO as appropriate. Over Y4 of the programme, the focus will be continuing to embed the MEL strategy, including the lessons learned element, into the running of the programme.

Plans are in progress to engage an external evaluation consultant to conduct a comprehensive evaluation of the programme in Y4.

Date of last narrative financial report	MFRS/UK-ISAR – 30/04/2025 / UK-MED/UK-EMT - 15/05/2025	Date of last audited annual statement	MFRS/UK-ISAR – February 2025 / UK-MED/UK-EMT- March 2024

Annex A – UK-EMT/ UK-ISAR Media Coverage

Annex B – UK EMT, Rehabilitation SCT