## HEP Annual Review - December 2025

Title: Humanitarian Enablers Programme (HEP)
Programme Value £ (full life): up to £15 million (including £7.5m headroom)		Review date: December 2025
Programme Code: 301072	AMP start date: 5/8/2022	AMP end date: 31/7/2026

Summary of Programme Performance
Year	2023	2024	2025
Overall Output Score	A	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0001144.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005088.xlsx

A. SUMMARY AND OVERVIEW
Description of programme
This is the third Annual Review (AR) of the Humanitarian Enablers Programme (HEP), covering the period from October 2024 to October 2025.

HEP aims to improve the effectiveness of the humanitarian system, including FCDO-funded responses, by investing in critical ‘enabling’ services which underpin the humanitarian system. These services are delivered through multi-year funding to specialist non-governmental organisations (NGOs), providing sector-wide benefits as public goods, and are aligned with three priorities of FCDO’s Humanitarian Framework:
- Prioritise: generating independent, high quality data and analysis to guide evidence-based resource allocation.
- Protect: improving access, safety and security for humanitarian personnel and supporting inclusion of vulnerable groups.
- Prevent: strengthening early warning, risk anticipation and crisis preparedness to enable timely and targeted interventions.
HEP has three partners:

H2H Network: A network of 65 organisations, hosted by the Danish Refugee Council, providing humanitarian actors with open access products and services to strengthen the efficiency, accountability and operational effectiveness of responses. H2H also manages the H2H Fund, which provides rapid funding to member organisations to fill critical enabler gaps during crises.

International NGO Safety Organisation (INSO): Provides security analysis, information and training to NGOs operating in high-risk environments, enabling safer access and informed operational decision making. INSO also plays an important role in shaping global policy and discourse on humanitarian safety. This year, in addition to central funding, INSO received support from FCDO programmes in Afghanistan, Mozambique, Nigeria, the Sahel.

ACAPS/INFORM: Hosted by the Norwegian Refugee Council, ACAPS delivers independent humanitarian data and analysis across more than 150 countries and 100 crises. UK funding to ACAPs also supports important multi-stakeholder humanitarian analysis through the INFORM suite of products (INFORM Severity, Risk, Climate, with the INFORM Warning tool under development).
The scope of HEP was adapted through a Business Case Addendum in March 2023 following ODA reductions in late 2022, and the budget reduced. Direct awards were made to ACAPS and INSO alongside the original partner, H2H, instead of through a planned call for proposals. The programme was also extended by one year to 31 July 2026.
HEP has a total budget of £15m over 4 years, comprising £7.5m core allocation and £7.5m of unfunded ‘headroom’ (meaning additional funding can be allocated should it become available) to allow rapid responses to crises and spikes in need. During this review period, all three partners received uplifts using departmental underspends and unallocated programme budget. Two additional H2H members—IMPACT/REACH (£1m) and the Global Inter-Agency Security Forum (GISF) (£140k)—received exceptional support via a passthrough mechanism (further details in Section F). By the end of this financial year the programme’s headroom will have been fully utilised.
The period under review has seen significant turmoil in the humanitarian system. Global funding cuts of between 35-45% prompted a wholescale ‘reset’ of the humanitarian system, led by the Emergency Relief Coordinator, alongside the broader UN80 reforms. Humanitarian enablers have been particularly hard hit. The additional funding provided through HEP was therefore critical in enabling partners to stabilise operations and safeguard priority services during a period of unprecedented uncertainty and disruption.
## Summary Supporting Narrative for the Overall Score
HEP has scored A (met expectations) for the third consecutive year. This reflects strong programme performance despite a highly challenging operating context, particularly for specialist humanitarian enablers organisations. All partners met agreed targets, maintained service quality, and demonstrated resilience in the face of funding losses and operational pressures - a significant achievement in the current context.

 Notable achievements during this year include:

H2H played a key role in humanitarian reform discussions during 2025, convening and leading discussions on the future of humanitarian enablers and the broader enabling architecture. The H2H Fund was activated four times in response to crises in Lebanon, DRC, Myanmar and most recently Syria. Members provided critical, rapid services in response to address gaps in data/information management and analysis, accountability to communities and delivery standards.

INSO maintained its presence in 21 countries and continued to deliver services to 1,331 NGO members despite significant funding cuts at the start of the year. Their presence has been critical in delivering security analysis and advice which have allowed national and international NGOs to continue to operate in some of the most challenging humanitarian contexts.

ACAPS has successfully maintained a full suite of analytical products, including the INFORM Severity, Risk and Climate Change indexes, and has continued to develop INFORM Warning, despite the impact of funding cuts earlier in 2025. These products remain a bedrock of planning and decision making for key humanitarian agencies and play an important role in informing FCDO humanitarian early warning, risk management and preparatory processes.

HEP has strengthened its approach to Monitoring, Evaluation and Learning (MEAL) with the support of an external consultant, refining its results framework, and supporting partners to improve outcome and impact reporting and evidence. This has improved the programme’s ability to demonstrate the impact of enabling organisations, providing a strong foundation for the development of a successor programme.

All three partners have demonstrated their critical role in supporting humanitarian delivery during a period of significant disruption. In a context of increasingly constrained resources and growing pressure to prioritise ever more rigorously, partners have provided the critical data, information management and analysis to support evidence-based decision making by operational agencies and donors, both globally and at the local level.

Major lessons and recommendations for the year ahead

Finance, Programme Management and MEAL
1. FCDO to take decisions on a cost and time extension to HEP, and on use of the remaining unallocated budget (£564,000) from FY 25/26, by the end of January 2026
2. FCDO to expedite completion of the ACAPS DDA and complete the programme’s overall Risk Appetite Statement
3. All partners have engaged closely with the MEAL consultant during the reporting period. This is evidenced in the improved partner logframes and reporting templates, as well as the overall umbrella HEP logframe. Going forward, it is recommended that this work with all partners should continue. In particular, work should focus on outcome and output evidencing, to better illustrate changes resulting from HEP activities.
4. Building on the MEAL work achieved to date, during the first quarter of 2026 the FCDO/MEAL consultant should initiate work to improve understanding of the impact of humanitarian enablers and how HEP activities and products improve humanitarian action. This can contribute to the eventual Project Completion Report for HEP and development of any successor programme.
Programme implementation:
H2H:
1. H2H to prioritise development of a new strategy and work-plan for the Network and Fund for the coming years. For the Fund, this should build on the lessons and recommendations contained in the H2H Fund review and activation case studies (as outlined in this review).
2. The large-scale donor funding cuts in 2025 have highlighted the risks of over-reliance on a small number of donors. In this context, it is important that H2H develop a clear donor outreach and communications strategy, to support the diversification of its donor base and ensure sustainability.
3. H2H has played a leading role in humanitarian reform initiatives throughout 2025. Building on this, H2H should scale up its role and visibility on reform as a key representative of humanitarian enablers during 2026. This includes strengthening engagement with UN processes, donor forums, and prioritising the planned consultancy-led work on data/IM and broader enablers.
4. During the reporting period H2H has increased its focus on localisation, in line with the recommendations in its report on local service providers (LSPs) and its localisation pilot. Going forward, it should seek to increase the number of local members in the Network, and scale up opportunities for them to secure direct as well as indirect funding.
INSO
1. In response to the increasing operational challenges faced in a number of complex contexts, INSO is undergoing a review of operating models as part of its new strategy. This is crucial, to ensure that implementation approaches are tailored to operational realities. INSO is encouraged to engage donors in the development of this new strategy.
2. The donor conference in October 2025 provided a valuable forum for discussion between the INSO team and key donors. INSO is encouraged to consider holding more regular donor meetings (in-person/virtual) and/ or field visits (where conditions allow).
3. During the reporting period, INSO has increased its policy and advocacy work and engagement on protection of aid workers. This is welcomed and should continue over the coming period. INSO is encouraged to engage with FCDO on the newly established Group of Friends, established to drive implementation of the Political Declaration for the Protection of Humanitarian Personnel.
ACAPS
1. ACAPS to create an organisational strategy to facilitate its transition to independence from Norwegian Refugee Council (NRC). The strategy should include a plan for donor diversification and establish all necessary legal and governance frameworks required for independent operations.
2. Given the critical role of INFORM Severity in humanitarian analysis and funding allocations, ACAPS should prioritise finalising its work on improving the Index. This includes the methodology update, Reliability Index, and the data quality audit.
3. ACAPS’ pilot work with MHPSS data has demonstrated early potential. ACAPS to continue exploring evidence on how integrating MHPSS data enhances anticipatory action and early warning mechanisms.
4. The introduction of the new Risk Radar is a successful addition to ACAPS’ suite of products. It is recommended for ACAPS to continue to develop this product so that it becomes a more dynamic, multi-hazard tool.
HEP is currently due to close on 31 July 2026. At the time of writing this review, budgets for FY26/27 and beyond have not been finalised. At the same time, discussions on reform of the humanitarian sector, including on the data and broader enabling architecture, remain at an early stage. FCDO is actively engaged in these strands of work with partners and donors and will continue this role over the coming months.

Considering this ongoing work, and the potential implications for funding decisions, the programme team would recommend a time and cost extension to HEP. This would allow sufficient time to develop a successor programme which is relevant and appropriate in this evolving context, whilst maintaining support to the current HEP partners.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The HEP Theory of Change (ToC), which was updated under the March 2023 Addendum, sets out how the support to enabling organisations improves the overall effectiveness of humanitarian response, in line with FCDO’s Humanitarian Framework priorities.

The ToC diagram has been slightly adapted during this AR’s reporting period, in order to incorporate recommendations from the previous AR on structuring the ToC and results framework around the three outcomes of the programme and the activities of the three partners. The logic and assumptions on which the ToC was initially based remain the same, as do the overall outcomes and contributions to the humanitarian objectives of Prioritise, Protect and Prevent. These changes are therefore being treated as non-material. The ToC shows how together the three partners create the coherent programme.

The current umbrella logframe, developed by the MEAL consultant, reflects the HEP ToC. It is based on partners’ individual log-frames and arranged around three outcome statements. The outcomes and indicators have been further developed and slightly restructured, but with no change to the overall meaning. Each output is clearly linked to a specific outcome, and in turn to the impact. This allows the logic of the ToC to be tested, making it easier to demonstrate the intended outcomes and the ‘so what’ of the outputs.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Each partner works towards the achievement of a clear outcome, focused on the development and promotion of enabling services, products and activities. These in turn contribute to the overall impact of supporting the humanitarian sector to better prevent crises, reach more people in need, improve access and protection and minimise risk. All three partners have made significant progress towards the achievement of their specific outcome, as outlined below:

Outcome 1 - Contribution to improved decision making, strategy, policy, advocacy and improved response, including with sector-specific data (primary partner ACAPS): On track.

Evidence is collected from web analytics, website use, surveys and interviews with product users, including NGOs and clusters, which demonstrates the utility of ACAPS products. Evidence shows that 80% of the INFORM Severity Index key users continue to use it for prioritisation and to support funding decisions. Donors including FCDO, ECHO and Germany, continue to use the Index for humanitarian analysis and/or as part of humanitarian allocation processes. UN agencies, NGOs and donors have confirmed that they are regular users of ACAPS’ analytical reports and products including the Risk List and the new ‘Risk Radar’, using them to support internal risk and foresight work. Feedback on ACAPS’ pilot project on Mental Health and Psychosocial Support (MHPSS) indicates that it is providing significant analytical and informational value. Users report the ability to support the early identification of risks and more timely and targeted protection interventions.

OUTCOME 2 - Improved security and safety of humanitarian staff, and safe access to vulnerable groups (primary partner INSO): On track.

INSO collects evidence of outcomes from satisfaction surveys undertaken at the country level with partners, post-training surveys, analytics from their internal Conflict and Humanitarian Data Centre (CHDC) and analysis developed by the policy team. INSO activities and products contribute to improved security and safety of humanitarian staff, and improved access to vulnerable groups. Feedback confirms that access to high quality, reliable security data, analysis and information in crises improves safe access for NGOs and humanitarian aid workers.

Additionally, INSO have continued to professionalise humanitarian safety management through training, capacity development, and expanded access to the CHDC. Surveys show 99% of participants agree that the training improved their knowledge and skills during the reporting period. INSO is continuing to develop its approach for assessing how participants have used tools and methods obtained through training session, building on examples from country offices to illustrate its impact on humanitarian safety.

OUTCOME 3 - A humanitarian enabling Network which is an engaged, diverse and collaborative community of enabling service providers (primary partner H2H): On track.

Evidence for this outcome is collected through examples from Network activities, engagement in broader humanitarian reform efforts and through case studies.

Over the course of the reporting period, H2H has actively fostered collaboration amongst its members, broadened the diversity of its membership, and strengthened its representation of independent enabling organisations. Network initiatives, such as the Communities of Practice, have facilitated improved coordination and in-depth peer learning, thereby empowering members to share expertise and best practices. H2H's visible leadership at humanitarian events has highlighted member achievements and demonstrated the Network's unique value, supporting the outcome of greater sector impact and recognition. Furthermore, the focus on localisation through both Network and Fund activities—such as engaging actors from the Global South and involving local and national stakeholders in intervention design and project selection—has advanced equitable participation and ownership, crucial for sustainable humanitarian outcomes.
The H2H Fund, designed to enable operational actors to enhance crisis response and drive systemic change, has proven its effectiveness. Case studies, desk reviews, and interviews with members and end users show that the Fund strengthens the network’s capacity to respond at scale, fosters collaboration, and maintains an agile, needs-responsive funding model. Collectively, these achievements are directly aligned with, and instrumental in, realising the desired outcome of a more inclusive, impactful, and resilient humanitarian system.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

HEP has continued to demonstrate its relevance and importance to FCDO and the broader humanitarian system, during an extremely challenging year. Evidence shows that interventions by all partners are delivering clear added value for humanitarian actors, donors and the humanitarian system as a whole. As resources become increasingly constrained, services provided by ‘enabler’ NGOs have become even more critical: High quality data, information and analysis remain essential for evidence-based prioritisation; strong beneficiary engagement and local accountability ensure resources are prioritised appropriately and reach the most vulnerable; and robust security analysis and support are needed to ensure NGOs can operate safely in conflict-affected contexts. Meanwhile, rapid, agile support from H2H to address gaps in key areas such as MEAL and financing can continue to underpin the enablers sector.

This year the UK has also played an active role in driving forward discussions on reform of the enabling architecture, bilaterally with key stakeholders and through its position on the donor enablers working group. UK engagement and advisory expertise on humanitarian data, protection and diplomacy will become even more important over the coming year, as reform discussions accelerate. The UK’s continued funding to critical enablers further serves to strengthen its role and influence in this space.

Overall, the evidence strongly supports continuing the programme, given its proven contribution to humanitarian effectiveness and the strategic value it provides to both FCDO and the wider system.
## C. DETAILED OUTPUT SCORING

Output Title	OUTPUT 1 (ACAPS): Production of high-quality, independent, accurate data and analysis.
Output number:	1	Output Score:	A (met expectations)
Impact weighting (%):	20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Production of regular high-quality, independent, timely and accurate data and analysis on crisis that responds to information gaps/needs.
1.1.1 # of regular ACAPS products published	Over 276 products published by September 2025 (cumulative target to date)	Exceeded / 341 products published by September 2025 (276 by June; 65 July-September)
1.1.2 # annual website sessions	62,000 sessions (previous milestone of 400,000 was revised due to changes with the new Google Analytics methodology)	Exceeded. Website stats for 1 September 24 - 31 August 25 show annual number of website sessions to be 93,310
1.1.3 Examples of users who state crisis analysis and data products are of relevant quality, detail, and timeliness, are accessible and/or meet their needs	Key stakeholders show examples of users who state crisis analysis and data products are of relevant quality, detail, and timeliness, are accessible and/or meet their needs	Achieved Examples in reports state crisis analysis and data products are of relevant quality, detail, and timeliness, are accessible and/or meet their needs. Consistent positive feedback received through informal channels and social media engagement.
1.2 Provision and maintenance of sector specific data analysis based on need (e.g. protection and gender)
1.2.1 # Regular publication of Protection Risk Monitoring (PRM) tool	PRM tool publications x 5	Achieved – at least 5 publications completed despite temporary pause of data collection following USAID cuts.
NEW 1.2.2 Examples show positive feedback from key strategic actors/users of PRM tool [pilot: requesting feedback on a quarterly basis from 2-3 key users]	Examples show positive feedback from key strategic actors and users of PRM tool	New pilot indicator. Feedback shows it is well regarded by target audience.
1.3 Maintain the INFORM Severity Index (through regular data collection, analysis, and product development, ensuring the index's quality, and that it remains up to date and accessible to users).
1.3.1 # of publications	Severity Index published monthly throughout reporting period	Achieved Severity Index published monthly.
NEW- 1.3.2 # web page visits each year	Baseline of 298 (July–Sept 2025)	On track- 298 visits achieved in July-Sept 2025.
1.4 Regular development and publication of quality crisis overviews and analysis of risk severity, early warning and climate change.
NEW- 1.4.1 # Publications (on risk, early warning early action and preparedness)	ACAPS delivers 10 anticipatory products (alerts, notes, briefings, reports etc.)	Achieved / X 5 publications / X 3 risk lists / X 2 anticipatory analysis
1.4.2 Examples/# of contributions strategic risk platforms (e.g. Interagency Standing Committee Early Warning and Early Anticipation.	ACAPS participates in 3 EWEA meetings, as well as other risk fora and working groups. New schedule	Achieved ACAPS attended all 3 IASC EWEA meetings held in 2025.
1.5 Joint Research Centre (JRC) maintains, and quality assures INFORM Risk and INFORM Climate Change products.
1.5.1 JRC maintains INFORM Risk and INFORM Climate Change and improves methodology of operational INFORM products.	2 INFORM Risk Publications are provided per year. INFORM Risk Publications are quality assured and released six-monthly.	On track / X1 INFORM Risk 2025 midterm released in Aug/Sep, with second product planned for March/April 2026. / INFORM Severity: the report on the upgrade of Severity methodology has been shared with partners for comment (incl FCDO)
1.5.2 JRC develops and publishes the methodological framework for INFORM Warning (in collaboration with INFORM partners)	JRC develops and publishes the methodological framework for INFORM Warning (in collaboration with INFORM partners)	Achieved Outcome of the 7th INFORM warning technical group meeting integrated into the methodology of INFORM Warning – Risk Monitor / -Beta version of INFORM Warning has been shared with the Technical working group.

This output has successfully met expectations, leading to an A rating. The majority of indicators have been achieved or are on track, with one exceeded, despite the challenges incurred by funding cuts to ACAPS and the wider sector.

Maintenance of the INFORM Product Suite
The INFORM suite includes three operational products; INFORM Risk, INFORM Severity and INFORM Climate Change. These analytical products continue to play an important role in donors’ and partners’ decision-making on response mobilisation and funding allocations for humanitarian crises. The INFORM Suite is regarded highly across the humanitarian sector as a source of information and analysis to support decision-making, ensuring funds and resources are directed towards the greatest areas of need with the greatest level of impact. Maintenance and quality assurance is in place for INFORM products methodology and data collection.

The INFORM Severity index measures and compares the severity of humanitarian crisis worldwide, incorporating 31 core indicators. Following the USAID funding cuts, given the importance of the INFORM Severity Index for decision making and prioritisation, ACAPS focused resources on ensuring this was maintained. ACAPS has successfully maintained the data collection and run continued analysis for the INFORM Severity Index, which is part of the INFORM data package. A second edition of INFORM Risk 2025 was published in April 2025, featuring methodological improvements and an updated dataset.

Other data and analysis products
Following the USAID funding cuts, a number of products were temporarily paused or scaled down, including some thematic reports and regular updates to the Protection Risk Monitoring (PRM) tool. Overall, 276 products were published by June 2025 (and a further 115 published in the following 6 months), including; Humanitarian Access Index, Global /Regional/Thematic Humanitarian Access reports, Weekly Highlights, ad hoc briefing notes, thematic reports and Global Risk List updates. These essential products continue to play an important role in the humanitarian needs analysis space enabling responders to shape policy, programmes and deliver aid accordingly.

Significant progress has been made on maintaining and enhancing ACAPS’ early warning, early action, and preparedness activities. This has focused on increasing production and evolving tools to better serve the humanitarian community through the creation of the Risk Radar, an online, live version of ACAPS’ monthly Risk List. This shifts the Risk List and static publications to becoming a dynamic tool, designed to continuously track and update risks in real time. As part of this transition, only one Risk Analysis was produced in the last year. Going forward, the live features of the Risk Radar will provide continuous updates and more timely insights to support anticipatory action. Ad-Hoc risk analysis reports continue to be produced on specific contexts requiring deeper attention, responding to sector needs.

The Protection Risk Monitoring tool (PRM) provides information for decision makers and humanitarian responders on the main protection threats, vulnerabilities, coping mechanisms, and existing capacities in their response contexts. During Q3 of 2025, following the pause due to the USAID/BHA funding freeze, ACAPS restarted data collection for the PRM, ensuring its maintenance and quality. The PRM now systematically captures Mental Health and Psychosocial Services (MHPSS) related cases. The MHPSS pilot recorded a total of 479 Protection Risks, of which 13% were related to MHPSS cases (September 2025). Data collection now includes age breakdowns (Children, Adults), allowing for more nuanced analysis of protection and wellbeing needs. Early insights from the pilot indicate that integrating MHPSS linked data provides significant analytical and informational value, specifically, the potential to identify risks early and support more timely and targeted protection interventions.

Stakeholder engagement and utility of products for partners

Overall, ACAPS data is used across FCDO, including by the Early Warning Analysis and Reporting team (EWAR), to inform decision-making when responding to humanitarian crises. More broadly, informal discussions with key stakeholders, including humanitarian donors and actors such as International Organisation for Migration, Australia’s Department of Foreign affairs and Trade and Global Affairs Canada, as well as Map Action, were positive. ACAPS’ positive contribution to donor and partner decision-making is further reflected by their routine and continued engagement with the Inter-Agency Standing Committee’s Early Warning and Early Action (IASC EWEA) meetings. Social media engagement remains highly positive with key stakeholders engaging with priority products, including the July edition of the Global Humanitarian Access Report.

On the INFORM suite, Partners such as SIDA (Sweden), UK Humanitarian Innovation Hub, ECHO, IOM and others have reported increased confidence and/or usage of INFORM Severity over the past quarter in particular. INFORM Severity is used routinely by donors and UN agencies to determine humanitarian allocations. Data from these products directly feeds into the FCDO’s own analysis conducted by the EWAR team and is critical for producing the FCDO’s Humanitarian Early Warning Note (HEWN) products and Humanitarian Allocation Model (HAM). Due to the positive evidence of ACAPS’ contributions to the programme and wider humanitarian ecosystem, FCDO decided to provide additional funding to advance this work further via a 5-month consultancy focused on developing INFORM Warning.
On the MHPSS pilot and PRM tool, although feedback shows it is well regarded by target audience, low uptake has also been reported. This is likely due the tool occupying a ‘mid-point’ between user needs, with too high level of technicality for some users (e.g. casual users) but lacking sufficient granularity for other users (e.g. protection experts). These reflections have informed some of our recommendations to ACAPS in this Annual Review. This work will continue to explore evidence on how integrating MHPSS data enhances anticipatory action and early warning mechanisms, with an aim to strengthen the link between protection and psychosocial wellbeing.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
With the support of FDCO’s MEAL consultant in refreshing the programme’s outcomes and Theory of Change, some indicators have been refined, with two new indicators introduced, to provide a more comprehensive assessment of the range of activities and scope of work. As part of the TOC refresh, ACAPS’ programme outputs particularly focus on contributing to Outcome 1 (Contribution to improved decision making, strategy, policy, advocacy and improved response, including with sector-specific data).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
1. ACAPS has made significant progress on its MEAL and reporting capacity, with a full refresh of their logframe finalised this year.
2. On the innovative component, following the US funding cuts and re-prioritisation, ACAPS and FCDO agreed to pause. However, following discussions with ACAPS, this work will now resume in January 2026.
Recommendations for ACAPS for the remainder of the programme:
1. ACAPS to create an organisational strategy to facilitate its transition to independence from Norwegian Refugee Council (NRC). The strategy should include a plan for donor diversification and establish all necessary legal and governance frameworks required for independent operations.
2. Given the critical role of INFORM Severity in humanitarian analysis and funding allocations, ACAPS should prioritise finalising its work on improving the Index. This includes the methodology update, Reliability Index, and the data quality audit.
3. ACAPS’ pilot work with MHPSS data has demonstrated early potential. ACAPS to continue exploring evidence on how integrating MHPSS data enhances anticipatory action and early warning mechanisms.
4. The introduction of the new Risk Radar is a successful addition to ACAPS’ suite of products. It is recommended for ACAPS to continue to develop this product so that it becomes a more dynamic, multi-hazard tool.

Output Title	OUTPUT 2 INSO: Development of adaptive safety and access platforms, security training and maintenance of the CHDC.
Output number:	2	Output Score:	A (achieved)
Impact weighting (%):	15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Scalable, relevant, and adaptive safety and access platforms (including the provision of Alerts, Analytical Reports, On-request services, Independent Safety Advisory, Orientation Briefs and engagement in coordination).
2.1.1.# of organisations registered to receive INSO services (National NGO, international NGO, Red Cross/ Red Crescent, donor, local coordination body etc)	1,450 agencies	Almost met / 1,331 organisations – including 1,243 NGOs, 22 Red Cross/Crescent Movement Organisations, 19 donors and 20 partners. / The number is less than anticipated due to INSO’s withdrawal from Burkina Faso and suspension in Nigeria (if these had been included it would have been 1426)
2.1.2 # countries supported with field, remote and mobile services (disaggregated by full-field platforms, distributed responses, etc.)	21 Countries	Achieved 21 Countries – Coastal Countries (to date covering Benin, Togo and Ivory Coast), Cameroon, Central African Republic, Chad, Colombia, DR Congo, Haiti, Kenya, Somalia, Iraq, Lebanon, Mali, Mozambique, Myanmar, Palestine, South Sudan, Sudan, Ukraine, Syria and Yemen. / INSO also has a training project in Ethiopia and had training projects in Burkina Faso until July 2025 and Nigeria until May 2025.
2.1.3. % NGOs stating INSO services are relevant to needs and support them to plan, operate, and deliver aid more safely	70%	The partner satisfaction survey was revised in coordination with the MEAL consultant. At the time of writing the survey was in process; full results will be shared with the PCR. Interim results report 91% of partners affirming that products support safer aid delivery.
2.2.1 Safety and security training
2.2.1 # of individuals trained	2,822 trained by Sept 2025	Achieved INSO delivered training sessions for 2,971 participants (93% participants were national staff; 24% from national NGOs). / In addition, 2,153 participants trained in NGO Security Management through INSO’s Massive Open Online Course (MOOC).
2.2.2 # of training sessions delivered to NGO partners globally (country office + Global Roving Training team)	226 training sessions by end Sept 2025	Achieved 226 training sessions delivered
2.2.2 Maintenance of the CHDC, increasing coverage and use by humanitarian responders
2.2.2.1 # of humanitarian responders trained to access and utilise the Conflict and Humanitarian Data Centre (global and in-country)	800 a year	Exceeded / 1,232 – In the course of 2025, INSO delivered 4 webinars to 1222 attendees and delivered 16 trainings for 110 in-person workshops to the humanitarian personnel. / 100% of global CHDC post-webinar respondents attested the webinar improved their awareness of the CHDC and its features.
2.2.2.2 # of countries CHDC covers	21	Exceeded A total of 28 countries are included in the CHDC. At the time of writing active data collection was ongoing for 23 countries.
2.3 Field driven advocacy, research and engagement.
2.3.1 The number of cases of advocacy engagements and Inter-Agency Coordination INSO initiates or actively participates in at the global level	30	On Track / 16 for period April 2025 – 30 September 2025 (new indicator) / INSO actively participates in the global Inter-Agency Coordination, particularly CMAG, SLT Oversight Committee, and Access Working Group.
2.3.2 # thematic global analysis products and sector research produced.	4	Exceeded / 5 Research by policy and advocacy team (e.g. localisation) + thematic specific reports
2.3.3 Examples of policy briefings, evaluations, reports evidencing use of global INSO data, analysis, or advocacy points.	4	Achieved 4: / 1 report on the emerging threat of drones across complex humanitarian contexts. / 1 survey and security incident data report will be published by the end of year on the direct impact of defunding on NGO risk management; / 1 interactive report on scenarios shaping reformation of the sector. In addition, / 1 localisation research and report (ongoing).

Briefly describe the output’s activities and provide supporting narrative for the score.
This output has met expectations overall, leading to an A rating. The majority of outputs have been achieved, with several exceeded. INSO has continued to deliver localised services in some of the most challenging operational contexts.

The funding cuts in early 2025 had a significant impact on INSO, as with all HEP partners, leading to the closure of 19 field offices, the loss of 450 staff, and suspension of most training activities. However, INSO’s swift response, including adapting models of delivery where offices had been closed, as well as the receipt of additional contributions from other donors, including FCDO, helped to mitigate further impacts. This ensured that INSO was able to continue providing vital services to partners who were themselves affected by a reduction in capacity, as well as strengthening coordination structures at field and HQ levels, and playing a supportive role in the ongoing development of normative humanitarian frameworks.

Service provision to NGOs: During the period 1 January – 30 September 2025, INSO provided services to a total of 1,331 organisations, with 15,694 humanitarian responders registered in its platform, and an estimated 248,823 indirect beneficiaries (the total number of staff members reported by partner organisations to INSO Partners’ Portal). By the end of the reporting period, INSO was operational in 21 countries, which reflects several new or resumed operations, as well as several which had to be suspended. Key services include security analysis and advice, coordination support, operational alerts and crisis management, as well as training. Highlights below:

New/resumed operations during the reporting period:
1. Lebanon – an emergency response team was deployed to Lebanon following the escalation of conflict in October 2024. This was a pilot initiative which has subsequently transitioned into a full country office. The initiative demonstrated INSO’s ability to respond rapidly to new emergencies. The team also supported the expansion of the Syria operation following the fall of the Assad regime in December 2024.
2. A remote platform was established in Thailand to cover Myanmar, at the request of NGOs in Myanmar. The platform is initially focusing on training, information sharing and digital safety with the intention to develop more traditional INSO services in due course.
3. A regional platform, INSO Coastal States, was established to monitor and report on insecurity spreading from the Sahel to Ivory Coast, Benin and Togo (with plans to extend to Ghana). Based in Cotonou, with antennae across the region, INSO Coastal States is designed to support NGOs with early warning and contingency planning across the region.
4. South Sudan – following successful re-registration with authorities, INSO was able to resume its in-country operations in Juba, from the remote operation in Nairobi.
Operations suspended:
INSO has faced a number of challenges of acceptance by government authorities during the reporting period, including Afghanistan and Niger in late 2024, which subsequently forced the closure of both operations. For Afghanistan, INSO has since developed a concept for a remote program to continue core monitoring, reporting and coordination services from outside the country until they are able to return. Niger remains suspended. In Nigeria, INSO was requested by Government authorities to suspend operations on 30 May 2025. Donors, including FCDO, have supported INSO with advocacy, and at the time of writing a positive resolution is anticipated.

The most serious challenge during this period was the detention of nine members of staff in Burkina Faso (4 national, 4 international and a national service provider) including the Country Director and Global Programme Director (September 2025). Public accusations of espionage were made against INSO on 7 October 2025. All staff members were eventually released unharmed at the end of October 2025 after significant diplomatic, donor, humanitarian, and Burkinabè advocacy and influence actions. As a precautionary measure, INSO took the decision to suspend operations from 10 October in neighbouring Mali to review engagement with authorities and prevent similar threats from materialising. These efforts reinforced INSO’s confidence that their operations were sufficiently known and accepted from various state entities; activities progressively resumed from mid-November.

These incidents reflect the growing risks faced by humanitarians operating in complex environments. The role of INSO remains critical, and it is essential that they are able to continue providing services to NGOs. It is therefore important that donors and the humanitarian community continue to support work on the protection, safety and security of aid workers, decriminalisation of aid, and defence of humanitarian space. FCDO is taking a lead role in policy development on this area, in close coordination with INSO. FCDO worked with Australia to develop the Political Declaration for the Protection of Humanitarian Personnel, launched at UNGA HLW in September 2025, and lobbied other states to join. In addition, the FCDO is actively engaged in the establishment of the Group of Friends to drive implementation of the Declaration in partnership with other states. INSO will also be invited to engage at the Group of Friends.

Training: As noted above, training activities were significantly scaled down following the US funding cuts at the start of the year, with contracts terminated for 44 training personnel, and 80% of activities suspended. Additional funding from donors including FCDO has enabled training to be scaled back up, with a projection by the end of December 2025 to have completed 280 sessions/3,200 people (compared with 538 sessions/6,734 participants in 2024). An additional 1,898 participants were also trained virtually in NGO Security Management through INSO’s Massive Open Online Course (MOOC). Furthermore, the Global Training Team successfully conducted Roving Training Missions to Lebanon and Cote d’Ivoire, providing critical support to new training programmes in Ethiopia and Gaza.

INSO’s Conflict and Humanitarian Data Centre (CHDC) has remained a critical security management tool for partners, as well as providing a basis for evidence and advocacy. At the time of writing, the CHDC actively collected data for 23 countries. During 2025 1,222 people received training on the CHDC. Further development of the tool will be considered as part of INSO’s overall strategy over the coming year.

Policy/Advocacy/Research: INSO has continued to strengthen its role in policy discussions and initiatives on NGO safety and security, through its policy and advocacy team. For example, INSO coordinated with Member States and UN agencies to inform debates within the UN Security Council on the safety and security of aid workers. In addition, INSO has initiated a key piece of research which examines the barriers faced by local actors in meaningfully participating in NGO security coordination. The research aims to inform concrete operational, advocacy, and policy changes, and will be completed over the coming months.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
FCDO’s MEAL consultant worked with INSO to slightly restructure this output to reflect more accurately the three main areas of INSOs work: support/service provision to NGOs through in country and remote platforms; training and delivery of the CHDC; and global policy and advocacy. New qualitative indicators have been included based on a new partner survey design and following detailed discussions with INSO. As noted, a small number of targets were narrowly missed or revised down due to programme restructuring (eg suspension of training) or operational withdrawal (Sahel). Targets will be reviewed to ensure they are appropriate for the remainder of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Progress has been made on the majority of last year’s recommendations:
1. INSO’s draft Impact Framework has been shared with FCDO’s MEAL consultant and has fed into the updated HEP logframe.
2. A field visit was not deemed feasible during the reporting period, given operational challenges. With regards to the HQ visit, FCDO attended the INSO donor conference in the Hague in October 2025 and held meetings with the HQ team.
3. Saving Lives Together (SLT) Implementation Report – The SLT initiative aims to improve collaboration between the UN Security Management System, INGOs and International Organisations. Establishing a reporting mechanism to assess the initiative’s implementation is a key priority. INSO has been working with UNDSS/The International Council of Voluntary Agencies (ICVA) to review the template and methodology for this report.
4. In line with the recommendation on scoping additional funds, FCDO provided two funding uplifts to INSO during the reporting period

Recommendations for the coming year
1. In response to the increasing operational challenges faced in a number of complex contexts, INSO is undergoing a review of operational models as part of its new strategy. This is welcomed, and INSO is encouraged to engage donors in the development of this new strategy.
2. The donor conference in October 2025 provided a valuable forum for discussion between the INSO team and key donors, including on progress, challenges and future direction. INSO to consider more regular donor meetings (in-person or virtual) and/or field visits where conditions allow.
3. During the reporting period, INSO has increased its policy and advocacy work and engagement on protection of aid workers. This is welcomed and should continue over the coming period. INSO is encouraged to engage with FCDO on the newly established Group of Friends, established to drive implementation of the Political Declaration for the Protection of Humanitarian Personnel.

Output Title	OUTPUT 3 (H2H): Facilitation of member collaborate, impactful fund activations and strategic engagement with global stakeholders.
Output number:	3	Output Score:	A (Achieved)
Impact weighting (%):	60%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output 3. 1 Facilitation of opportunities for member engagement, member support and creation of opportunities for members to collaborate (facilitation of joint actions, provision of space for members to discuss together and fosters mutual engagement)
3.1 Number of activities conducted including thematic groups and operational sessions	2 thematic working groups with a minimum of 10 members regularly engaging. Conduct at least 3 operational sessions and 6 webinars annually.	Achieved- 2 thematic groups (COPs) are operational on Communications and MEAL with more than 10 members regularly engaging. 5 webinars took place during 2025 (35-40 members joining). In addition, regular dialogues, network meetings and workshops were held.
3.12 Levels of satisfaction and engagement	70% member satisfied or very satisfied with completion, transparency, and fairness of policies, and processes. Team efficiency measured through member surveys	In progress- Due to disruptions experienced this year, the bi-annual member survey has been delayed. It was sent out to members Q3 and is ongoing to date. 2 additional surveys have been undertaken in 2025 with members—one focused on the impact of the USAID freeze and another on the evolving global funding landscape.
3.13 # examples of new regional and country-level collaborations, including involving local service providers.	Examples to show new collaborations in 2 contexts / (new/pilot indicator)	Achieved- Examples of closer collaboration with local NGO forums in the contexts where the H2H Fund has been activated, as illustrated in DRC and Syria and providing H2H services that support and advance locally led humanitarian action. The Network’s activities in DRC have evolved into a more developed partnership with the national NGO network CONFAFOHD.
3.13 # new members joining from global south	3 new members from the global south.	Achieved- 3 in total in 2025, from Cameroon, Sudan and Nepal. Activations have enabled members to downstream funding to national organisations, through sub-grant agreements or service contracts.
3.2 Impactful fund activations for members, provision and management, development of fund strategy, measuring impact of fund and learning, and increasing locally driven services.
3.2.1 Number of Case studies developed for fund activations showing impact, progress and outcomes	Case studies commissioned for all Fund activations including examples of outcomes. Case studies show positive value of service and fund strategy developed.	Achieved - Case studies have been completed for all 3 Fund activations launched in 2024: Sudan, Myanmar and Lebanon. All case studies describe positive achievements and outcomes of the activations, including the longer term impact on the broader humanitarian response (details in narrative below).
3.2.2 # donors contributing to the fund and total contribution.	3 donors contributing, at least 1.5m CHF/ £1.4m.	Partially Achieved - 2 donors (FCDO and DEC) during 2025 [BHA funding until December 2024 (Anticipatory Action activation)] / Fund Value Exceeded: Value of fund for the 4 activations launched during the reporting period is £2.89m (3.08CHF)
3.2.3 # members with access to fund	15 members with access to fund and with Due Diligence Assessment.	Achieved - A total of 35 members completed the H2H due diligence process required to access the fund - 53% of the total membership (up from 24 members in 2024).
3.3 Active and regular engagement with donors, and end users, promotion of network, and role of enablers with key strategic humanitarian actors to ensure influence within the humanitarian system.
3.3.1 # and examples of strategic international events participated in	Participation in at least 5 international events.	Achieved - 9 major international events have been participated in.
3.3.2 # of followers, engagement rates, social media increase on last year	Increase in the number of followers and engagement rates across our website and social channels from previous year figure of 6.3K active users	Exceeded - Website analytics - October 2024–September 2025 shows a notable growth, reaching 8.7K active users, most of whom were new visitors.
3.3.4 # of donors contributing to the network and total value of contributions	Four donors At least 3m CHF secured p/a	Achieved - (FCDO, DEC, BHA, SIDA) / Budget for 2024 – 3,4m CHF / Budget for 2025 (projected) – approx. 5m CHF

Briefly describe the output’s activities and provide supporting narrative for the score. This output has successfully met expectations, leading to an A rating. The majority of activities have been achieved or are on track, with some exceeding the targets set.

H2H Network: The H2H Network has 67 members across the following sectors: i) Data, information management and analysis; ii) community engagement and accountability; iii) quality and sector professionalisation; and iv) security, logistics and programme support. In 2025 H2H welcomed 6 new members, including 3 from the Global South, while three were de-registered due to lack of activity.

Independent enabling organisations have been particularly impacted by the US cuts. A survey of H2H members undertaken in February 2025 reported 67% being affected by the cuts, with 23% facing existential crises. Some organisations, including those providing critical data/analysis and accountability services, reported having lost up to 90% of income without warning.

The H2H Network has been critical in representing its members and ensuring that these NGOs have a clear and coherent voice in reform discussions. H2H has been actively driving forward strategic discussions on the future direction of enablers throughout 2025, engaging in key initiatives on humanitarian reform, coordinating closely with UN leadership and NGO coordination bodies. H2H contributed to public statements and advocacy messages on the importance of preserving critical support services. It has engaged in the Data and IM Technical Working Group under UN80 as well as linked technical discussions with the Inter-Agency Standing Committee (IASC) as part of the humanitarian reset and has worked closely with the SIDA-led donor enablers working group, of which FCDO is an active member. At the time of writing, H2H is leading a collaborative process among humanitarian data and IM actors to co-develop a shared vision and functional framework for the future humanitarian data ecosystem. This will feed into a broad analysis of common services across the sector, their role and value, jointly proposed with The Humanitarian Exchange and Research Centre (HERE-Geneva).

H2H Network initiatives for members during the reporting period have included setting up ‘communities of practice’ on communications and MEAL, which have both supported work on impact and visibility, with webinars and discussions encouraging collaboration and peer-to-peer learning. For example, H2H produced a series of short films, for each of their four focus sectors to strengthen member engagement, by illustrating how the network supports shared visibility, strengthens peer connection and reinforces the collective voice of technical and enabling actors within the humanitarian system.

High level events participation: H2H demonstrated active engagement in multiple humanitarian reform discussions and initiatives during the reporting periods, to enhance profile and visibility. Key events include:
- Humanitarian Networks and Partnerships Week: H2H members led more than 30 dynamic sessions and panels at HNPW including on humanitarian data and analysis, community engagement, and humanitarian reform.
- European Humanitarian Forum – H2H director led discussions on the future of the humanitarian system, reform and operational effectiveness
- Engagement in ICVA Forums: H2H Director has played a leading role in these discussions as representative of the H2H Network. Sessions focused on humanitarian reform and the group produced several papers including an advocacy document - ‘Donor Engagement: Sustaining a needs-based quality response’.
- GISF Global Security Risk and Policy Conference: This provided an opportunity to highlight the strengths of the H2H model for security risk management and engage with a broad spectrum of INGOs.

H2H Fund: Providing H2H members with targeted, efficient, and rapid resources which fill an identified gap or need in a response has remained a central pillar of H2H strategy. The H2H Fund enables H2H members to provide their services to operational actors and the broader humanitarian system during crises, thereby improving responses to specific crisis as well as driving systemic change. During the reporting period, the Fund was activated four times, with two activations continuing since the previous period. Members are now able to channel funding to national organisations, either through sub-grant agreements or service contracts. A total of 35 members (53%) have completed Due Diligence Assessments (an increase of 11 on 2024) and are now eligible to apply under the H2H Fund.

FCDO teams are actively involved throughout the activation process, and a representative from FCDO, either from the respective Post or centre, participates on the grant panel. Engagement from teams at Post has been strong during the reporting period, and feedback received has been positive. FCDO humanitarian advisers have welcomed the flexible and rapid nature of the activations, the ability of H2H members to fill critical gaps in the responses, and the opportunity for FCDO to support the selection process on the grant panel.

Overview of H2H Fund activations continuing or initiated during the reporting period

Activation	FCDO Budget* (£)	H2H Members Funded	Funding Dates	Central Budget/ Post	Other donors
Anticipatory Action	0	Insecurity Insight, Humanitarian Openstreet Map, Clear Global, CartONG, Ground Truth Solutions	Jun – Dec 2024	N/A	BHA (USD $322,392) (approx. £244k)
Sudan Conflict (II)	635,673	Data Friendly Space, Humanitarian Open Street Map, IMPACT Initiatives, CDAC Network, Ground Truth Solutions, Internews, Humanitarian Academy for Development and RedR UK	Jul 2024 – Feb 2025	Central Budget	No
Myanmar (Conflict)	390,159	Clear Global, Insecurity Insight, TNH, BBC MA, Impact Initiatives, Internews	Oct 2024 – Feb 2025	Central budget	No
Lebanon	517,504	The New Humanitarian, CDAC Network, RedR UK, Data Friendly Space, Humanitarian Open Street Map, Impact Initiatives, Diaspora Emergency Action Coordination (DEMAC), Edge Effect.	Dec 2024 – Jun 2025	Central Budget	No
Democratic Republic of Congo	1,164,860	CartONG, Centre for Humanitarian Leadership, DEMAC, Impact Initiatives, Fondation Hirondelle, Global Nutrition Cluster, Groundtruth Solutions, Insecurity Insight, MapAction, The New Humanitarian	Apr – Nov 2025	Central Budget	No
Myanmar (Earthquake)	450,000	ACAPS, Humanitarian Open Street Map, Impact Initiative, Map Action, CDAC Network, Sphere/CHS Alliance, GroundTruth Solutions, Insecurity Insight	May – Oct 2025	Central budget + Post	DEC (£250k)
Syria	549,922	Centre for Humanitarian Leadership, CHS Alliance, DEMAC, Humanitarian Open Street Map, IMMAP/CartONG/ MapAction	Nov 2025-May 2026	Central budget	No

*Figures shown reflect FCDO funding and do not include budget of other donors

Summary of key achievements from activation case studies

Sudan II: (July 2024-February 2025) - The Fund was reactivated due to the continued deterioration of the context in Sudan, with the aim of addressing specific gaps in access to information, accountability and community engagement. Eight H2H members were funded.
Data-Friendly Space (DFS) delivered significant progress by developing the Situation Hub platform and producing comprehensive crisis risk and situational analysis reports, empowering decision makers with timely access to essential information. Internews made notable strides in increasing accountability and fostering community engagement, collecting valuable insights from remote and hard-to-reach communities. This ensured that humanitarian responses were finely tuned to the real needs of beneficiaries across vital sectors such as Cash Consortium, Protection, WASH, Shelter/NFI, Health and Access. Humanitarian Open Street Map played a pivotal role in enhancing operational planning and coordination, successfully bridging spatial data gaps through close collaboration with the Information Management Working Group. Ground Truth Solutions made a substantial impact by elevating the voices of conflict-affected communities, seamlessly integrating their feedback into interagency mechanisms and guiding priorities, with a particular focus on protection and safety concerns. CDAC excelled in strengthening the capacities of both national and international civil society diaspora groups in information management, delivering targeted training and mentorship programmes that inspired innovation and encouraged continuous learning within the sector.
Myanmar (Oct 2024-Feb 2025) The first H2H activation in Myanmar (Oct 2024–Feb 2025) delivered critical support to the humanitarian response amid escalating conflict and severe access constraints. Six H2H members were funded across four coordinated projects that significantly strengthened information access, accountability and operational decision-making. Internews, The New Humanitarian and CLEAR Global improved humanitarian actors’ ability to address misinformation and fostered stronger collaboration with media and data partners through practical tools and guidance. BBC Media Action enhanced accountability and community engagement by providing social media mapping and disability‑inclusive analysis that empowered both humanitarian organisations and local groups. Insecurity Insight filled major information gaps by establishing remote reporting mechanisms on violence against healthcare providers in hard‑to‑reach, opposition‑held areas, offering independent data that countered official narratives and informed safer, more effective responses. IMPACT Initiatives contributed crucial conflict‑damage assessments that improved situational awareness and supported rights‑based decision‑making and advocacy.

Myanmar (May – October 2025). The H2H Fund was activated in Myanmar for a second time following the devastating earthquake which occurred on 28 March 2025. The activation was co-funded from central HEP funds (£300k), FCDO Myanmar (£150k) and the Disasters Emergencies Committee (£250k), supporting eight H2H members. The activation was nearing completion at the time of writing, and a case study will be completed in due course.

Projects aimed to address both the aftermath of the earthquake, for example enhancing geospatial capabilities and producing baseline data on building damage, while also tackling complex issues that characterise the protracted conflict – for instance producing analysis on hard-to-reach areas outside of government control or by analysing the country information ecosystem to overcome risk, fear, and distrust. The H2H Network is collaborating with the DEC to share some of the learning, insights and analysis produced by H2H members with DEC members and partners. In the challenging operational context of Myanmar, H2H-funded projects have demonstrated the value of independent, locally informed data in contested environments. The two activations illustrate the H2H Fund’s ability to fill critical gaps in the humanitarian response by enabling timely, specialized, and contextually relevant services, playing an important role in strengthening evidence-based advocacy and shaping humanitarian policy discussions. Engagement from FCDO Humanitarian Advisers at Post was also extremely valuable, providing contextual expertise and supporting project selection.

Lebanon (December 2025 – June 2025): The fund, activated in response to the escalation of conflict in Lebanon, supported seven H2H organisations whose collective efforts substantially strengthened the humanitarian response. Data Friendly Space, IMPACT Initiatives, and Humanitarian OpenStreetMap (HOTOSM) improved access to timely, tailored information by producing analytical products and developing data platforms that identified community needs and highlighted critical gaps in response and data collection efforts. The New Humanitarian and Edge Effect advanced accountability and community engagement by capturing and amplifying the lived experiences of affected communities—particularly marginalised groups—ensuring their perspectives informed operational planning and service delivery. Additionally, RedR UK, alongside CDAC and HOTOSM, contributed to capacity strengthening by delivering targeted training on security risk management and countering misinformation and disinformation, helping responders operate more safely and effectively in a highly volatile context. CDAC’s recommendations on countering harmful information have been integrated into existing structures including the PSEA network.

Whilst the duration of projects was only six months, the long-term, potentially transformative impact of the activation in Lebanon, in terms of the various platforms, data, outcomes and response actions, has been recognised in the case study. Insights on humanitarian needs and gaps are likely to inform interventions into 2026, and the integration of tools and platforms into existing mechanisms may impact on decision-making and coordination in years to come. The H2H Fund’s support for the inclusion of marginalized voices in operational decision-making has laid the foundations for long-term advocacy and accountability, supporting work on transforming humanitarian systems.

DRC (April – November 2025) - the Fund was activated in response to the crisis in Eastern DRC. Due to the scale of demand for H2H members’ services, FCDO was able to provide a total of £1.165m, supporting 10 organisations (listed in table above). At the time of writing, the activation was nearing completion, and a case study will be prepared in due course.

Interim highlights from the activation indicate that the H2H‑funded organisations significantly strengthened humanitarian response in the DRC by improving coordination, data systems, leadership capacity, community engagement, and evidence‑based decision‑making. For example, CartONG built and delivered a national NGO data platform and trained hundreds in data management; the Centre for Humanitarian Leadership trained emerging and experienced Congolese leaders; and DEMAC improved collaboration between diaspora groups and local actors through research and coordination efforts. Fondation Hirondelle provided trusted information to 1.8 million weekly listeners and trained journalists in crisis reporting, while the Global Nutrition Cluster enhanced nutrition response planning and partner capacity. Ground Truth Solutions gathered community perceptions to inform policy, and IMPACT delivered extensive market, multisector, and public‑health assessments to guide operational decisions. Insecurity Insight strengthened awareness of security incidents and misinformation trends, MapAction built real‑time dashboards that accelerated emergency decision‑making, and The New Humanitarian deepened global understanding of the M23 crisis through impactful investigative reporting.

Building on the partnerships developed through the Fund activation in DRC, H2H, with FCDO funding, has also initiated a localisation pilot project in DRC. This emerged from a recognition that enabling services, despite being open source, are generally designed and delivered by and for international actors and are not adapted to the needs of local organisations. It also builds on the report commissioned by H2H and published in December 2024, ‘Local Service Providers in Humanitarian Response: Pathways for Engagement with the H2H Network’. This sought to explore the challenges, priorities and limitations that local service providers face, and how to overcome these. It recommends concrete operational approaches including advocacy, capacity building and integration of local service providers into H2H activities.

The project in DRC aims to strengthen the capacity of national actors as partners and consumers of humanitarian public goods produced by network members. H2H will be working closely with CONAFOHD, the representative body of local NGOs, representing 500 organisations to develop the project over the coming months.

Syria (November 2025 – May 2026 (Ongoing))
Following an assessment in August 2025 undertaken with key humanitarian actors and civil society leaders, and in consultation with FCDO, H2H decided to activate the Fund in Syria. Stakeholders recommended that an activation could offer timely and valuable support to the humanitarian response in Syria, which, against the backdrop of the political transition, is currently undergoing a reorganisation, creating both opportunities and challenges. The ambition of this activation is to support the humanitarian community to build a more effective, inclusive and accountable response. Selected projects aim to strengthen the foundations for collective accountability, develop coordinated information management services, strengthen inclusive coordination and civil cohesion, and produce geospatial data on infrastructure for effective recovery programmes. The activation is ongoing and will be reported on in the next review.

An independent review of the H2H Fund, published in February 2025, concluded that the Fund has made valuable contributions to humanitarian response. It praised the Fund’s ability to fill critical gaps in humanitarian support services and produce humanitarian public goods that benefit the system. It noted that the Fund fosters innovation, enabling smaller, specialist organisations to scale up and contribute meaningfully to a response. Crucially, the Fund offers donors a high-impact investment opportunity with modest funding. The review identified key areas in which the Fund has made a demonstrable impact to humanitarian response:
- Improving access to information for operational actors and decision makers;
- Enhancing coordination and collective action, particularly through independent data and analysis;
- increasing accountability and community engagement in humanitarian response;
- capacity strengthening and innovation;
- informing effective advocacy and policy discussions.
Several challenges were highlighted, including the relatively short implementation timeframe, limited volume of funding; and in some cases, limited awareness of the H2H service package, particularly amongst local actors. The review sets out several recommendations, including: strengthening partnerships with complementary networks, advancing localisation, and exploring innovative funding partnerships to support its growth and sustainability. H2H is working to take forward the recommendations, and this will remain a priority over the coming months.

Additional contribution to IMPACT Initiatives and GISF: During the reporting period, FCDO provided specific funding for high priority work to two H2H members, IMPACT Initiatives and Global Interagency Security Forum (GISF), which had been severely impacted by global funding cuts. At the time of writing, these programmes were in their initial phases; full results will be shared in the PCR:

The project with IMPACT focuses on both primary data collection as well as secondary analysis, in order to support prioritisation and strategic planning. The objective of this additional funding has been to support IMPACT country operations affected by the US funding cuts. Primary data collection includes core assessments such as Multi-Sector Needs Assessments, Rapid Needs Assessments, market monitoring, and health outcome surveys to ensure timely, reliable information on populations in need. The project then aims to strengthen analytical capacity by producing structured, decision‑focused analysis—most notably the Acute Needs Analysis—to identify populations at highest risk of preventable loss of life, and by generating global cross‑crisis insights to guide resource allocation and strategic planning at the system level. Full results will be shared in the PCR.

The objective of the project with GISF is to strengthen policy engagement on security risk management and aid worker protection. GISF provide a critical forum to convene INGOs to promote collaboration on security risk management, pooled services, share learning and best practice. Activities under this project include drafting policy briefs on security risk management and providing technical guidance to members. GISF also engage in the Saving Lives Together Framework, which the FCDO supports, and a key part of this project will be to strengthen their engagement in the Group of Friends, to drive implementation of the Political Declaration for the Protection of Humanitarian Personnel which the UK has signed. Full results will be shared in the PCR.

Donor engagement and financial support:
During the reporting period, H2H received funding from one new donor, the Disasters Emergency Committee (DEC), which provided funding dedicated to the Myanmar earthquake response. With the exception of the BHA grant (which concluded in December 2024), all remaining funding has been from FCDO this year. H2H has intensified its donor outreach, engaging with the donor working group on enablers, and holding bilateral discussions with potential donors. In line with the recommendations from the Fund review, discussions are continuing with several foundations and private sector actors. These discussions will continue in early 2026.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The H2H output of the umbrella logframe continues to measure three key areas: the Network, the Fund, and donor engagement. With the support of FDCO’s MEAL consultant, indicators have been developed to provide a more comprehensive assessment of the range of activities and scope of work. No major changes are planned as a result of this review, but an additional output may be added to reflect the IMPACT/REACH and GISF contributions.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
H2H has made progress towards last year’s recommendations:
1. Strategy for growth, including increased representation from the global south, and donor diversification: the updated strategic and operational priorities document (outlined in Section B above) set out a work plan which incorporates these key focus areas, and which H2H has been actively progressing. The addition of 3 new members from the global south demonstrates progress on this. Updates on donor diversification are provided in the section above.
2. Instead of a comparative review of case studies, the strategic review of the H2H Fund was commissioned, which provided a detailed evaluation of the Fund to date, and clear, actionable recommendations going forward.
3. Engagement with local actors and platforms – in December 2024 H2H finalised its report ‘Local Service Providers in Humanitarian Response – pathways for engagement with the H2H Network’. The report sets out how H2H is actively taking forward the recommendations through its localisation activation, as well as through increased engagement with local actors and coordination fora in all contexts in which it works.
4. Engagement with MEAL consultant – H2H has worked closely with the consultant during the year to strengthen processes, facilitate the sharing of learning and good practice within activations. This has been focused on capturing outcomes, reflecting on their significance and the sharing of tools with activation members.

Recommendations for the coming year
1. H2H to prioritise development of a new strategy and workplan for the Network and Fund for the coming years. For the Fund, this should build on the solid lessons and recommendations contained in the H2H Fund review and activation case studies.
2. The large scale donor funding cuts in 2025 have highlighted the risks of over-reliance on a small number of donors. In this context, it is important that H2H develop clear donor outreach and communications strategy, to support the diversification of its donor base and ensure sustainability.
3. H2H has played a leading role in humanitarian reform initiatives throughout 2025. Building on this, H2H should scale up its role and visibility on reform as a key representative of humanitarian enablers during 2026. This should include strengthening engagement with UN processes, donor forums, and prioritising their work on a vision for humanitarian data/information management and the humanitarian enabler ecosystem which they have initiated through consultants.
4. H2H should continue to work with the MEAL consultant on strengthening of MEAL for activation members, and the wider H2H network members. A series of participatory webinars will be planned around key themes in line with the opportunities and gaps identified for the H2H Communities of Practice (COP) work. Indicators should also be included to account for the work of IMPACT and GISF.

## D: VALUE FOR MONEY -

Key cost drivers and performance

Economy

INSO is the only dedicated NGO-led security platform for the humanitarian sector. Globally it provides services to over 1,400 organisations, which includes 1,332 NGO partners. This gives it significant economies of scale and enables it to centralise information and training for the entire humanitarian NGO sector. By centralising security analysis, field-based coordination and capacity building into a single shared resource, INSO is able to significantly reduce costs compared to individual NGO’s sourcing these types of services themselves.

ACAPS relies on secondary data analysis, synthesising scattered information into focused reports, and drawing on existing data from other humanitarian actors (e.g. IMPACT/REACH, OCHA, IOM), which reduces costs compared to primary data collection. ACAPS hybrid working mode represents good value for money by saving on physical office space and the use of MS Teams has its reduced communication costs. All products are published online and are therefore paperless and do not incur print production costs. Webinars are used present findings and increase the reach of products without incurring venue costs.

Efficiency

H2H offers FCDO an efficient mechanism to channel funding to multiple NGOs by consolidating multiple grants through a single partner, reducing the administrative burden, and offering benefits that no single organisation could provide on its own. The H2H Fund contributes to more efficient responses by rapidly mobilising a diverse range of specialised service providers that enhance coordination, quality, and overall impact. Since its inception, FCDO has channelled over £10 million to H2H, supporting a total of 128 projects across 35 member organisations, which it would not have been possible to do directly. The H2H team managing the Fund is small and agile and now has well established tools and systems that allow the grant making to be efficient and cost-effective. FCDO’s contribution to H2H has helped establish the Fund’s credibility and visibility, and played a catalytic role in attracting additional support from other donors such as BHA, SIDA, and DEC.

Effectiveness

ACAPS has continued to provide evidence-based, insightful and timely analysis to the humanitarian community, drawing on the expertise of its analysts and partners. ACAPS’ work on the INFORM Severity Index in particular delivers value for money to the broader humanitarian system by supporting prioritisation of donor resources and improving the targeting of people in need, as well as strategic, evidence-based decision-making across the sector.  80% of the INFORM Severity Index key users reporting they use it when making decisions on prioritisation and funding allocations. Additionally, FCDO’s use of ACAPS’ outputs influences value for money decisions of our broader humanitarian interventions and is a critical resource for FCDO. INFORM data directly informs EWAR analysis and products, which in turn feed into the design of the FCDO Humanitarian Allocation Model and support decision-making on allocations for the FCDO’s Humanitarian Crisis Reserve
The services provided by H2H members are designed to improve the overall effectiveness of humanitarian responses and are designed to support the entire humanitarian ecosystem, rather than any single organisation or agency. By providing shared, independent services and products, this helps strengthen overall collective effectiveness and ensures that critical functions remain accessible across the sector and inform operational priorities. Every H2H Fund activation is evaluated through a post-activation case study to confirm that the support provided addressed genuine needs, filled critical gaps, did not duplicate efforts of other organisations, and improves the effectiveness of future activations.
Equity

The H2H Network is committed to promoting equity in its processes, both through the Fund and its membership initiatives. Network membership is mostly small to medium sized NGOs that donors struggle to fund directly due to the administrative burden. Channelling funding through the H2H Network enables these organisations to receive support to carry out their important work complimenting, constructively challenging and supporting the wider humanitarian system. H2H is trialling a localisation pilot in the DRC over the next few months, and this will be an important initiative to explore how the Network can include local actors and fund them in a crisis. In addition, non-funded members can also benefit from H2H support through communities of practice, webinars, panel discussions, dissemination, and visibility opportunities. Given that accountability to affected communities is one of the four categories of H2H membership, H2H Fund activations focus heavily on ensuring and strengthening beneficiary engagement, as detailed in Section C of this review above.
ACAPS ensures that its research is conducted in a manner that respects the dignity, rights and needs of all stakeholders, including affected communities. It applies a conflict-sensitive approach to its research and analysis work and respects the principle of 'Do No Harm'. The rigorous approach to its research ensures its findings are credible and contributes to equitable humanitarian outcomes.
INSO also promotes equity by providing its services free of charge which removes the potential barriers for local and national NGOs accessing training. For example, in 2025, 94% of its training participants were national staff from international or national NGOs
Assessment of whether the programme continues to represent value for money

The products and services provided through HEP are resources offered to the humanitarian community free of charge and are available to small and large organisations, international, national and local alike. HEP offers a cost-effective way for FCDO to contribute to independent, robust, objective analysis on needs, response, access and improved programme quality. FCDO’s investment in these enabling organisations produces global public goods which improve the overall effectiveness of humanitarian responses and promote reform of the system.

The programme continues to offer good value for money for FCDO. The recent large-scale funding reductions across the sector have affected enabling organisations disproportionately and more than ever highlighted the importance of the products and services they provide. The financial headroom in the Business Case has allowed FCDO to swiftly programme departmental underspends to support all three HEP partners affected by the US funding cuts, helping them to manage cash flow and restructure their operating models. Looking ahead, over the Spending Review period, interest in enabling organisations is expected to increase, reflecting the need to preserve and maintain the critical function they perform supporting the wider humanitarian system.

E: RISK – Overview of risk management

The major risk that emerged over the reporting period was abrupt withdrawal of USAID funding in January 2025. This impacted all three HEP partners, as well disproportionately affecting many other enabling organisations within the humanitarian sector.

H2H was less severely affected than some other organisations as it was already planning for the end of its BHA grant. Nonetheless it did disrupt fundraising plans and resulted in the loss of two important positions (Finance & Compliance Officer and Communications Officer) over the summer. The cuts also posed a direct risk for the H2H Network and its members as individual organisations, many of which were reliant on US funding.

ACAPS and INSO both previously received substantial BHA grants and the sudden loss in funding required them both to rapidly review their staffing, structures and priorities to ensure the continuity of their operations. ACAPS carried out a thorough review of its structure which resulted in a restructuring of the organisation and staffing reductions. A particular concern to FCDO was the potential loss of critical datasets and data sources vital to the INFORM Severity Index. Mitigating actions were put in place to protect this as a priority.

INSO received Stop Work Orders for 19 of its BHA grants, representing 38% of its forecasted global budget for 2025. These grants were particularly important for start-up operations in countries such as Colombia, Chad and Sudan, and for existing operations in Africa where BHA funding was the primary source of funding. INSO carried out a rapid review of all of its country strategies, which resulted in the termination of 400 staff members (out of 1,500), and a substantial reduction in its training offer. By downsizing its operations and drawing on strong financial reserves, INSO has been able to maintain operations in all countries, albeit at a reduced level.

INSO has also experienced serious operational challenges in several countries including Afghanistan, Burkina Faso, Niger and Nigeria, leading to the suspension or withdrawal of operations. Whilst the circumstances of each differ, this reflects an increasingly hostile attitude of state authorities towards NGOs in some countries and has resulted in the shrinking of humanitarian space which is a serious concern.

Despite the considerable challenges experienced over the past year, the mitigating actions put in place by the partners mean the overall risk rating for the programme is unchanged and has remained “moderate”. The full impact of the funding cuts on the sector may be still to be fully felt, and 2026 could bring further challenges for HEP partners and humanitarian enabling organisations more broadly. FCDO will continue to monitor the situation and is discussing internally and with other donors what more we can do to support this important part of the humanitarian system.

The programme team has continued to meet quarterly to update the Risk Register on AMP, drawing on the individual partners’ own Risk Registers. The overall Risk Appetite Statement remains outstanding and will be prioritised by the Programme Team for completion during the first quarter of 2026. The Due Diligence Assessment (DDA) for INSO is now complete and the DDA for ACAPS (NRC) remains outstanding but should be finalised by the end of April 2026. In the meantime, FCDO has relied on the assurance provided by the central level NRC DDA as well as country level agreements with ACAPS. Looking ahead, two new emerging risks for FCDO are associated with H2H’s move to a new host (NRC) sometime in 2026, and ACAPS move to independence, also in 2026. ACAPS does however intend to remain a downstream partner of NRC for the time being which should minimise the impact on the FCDO grant. FCDO will continue to actively track these changes and ensure the appropriate risk mitigation process are followed, including conducting new DDAs, if required.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The grants to all 3 HEP partners were increased over the reporting period. For H2H this was in response to new and emerging crises to support Fund activations. All three partners received an uplift at the end of the 2024/25 financial year, utilising the available headroom in HEP, effectively absorbing underspends that had emerged from elsewhere across the department. The timing of this coincided with all partners learning their funding from US had been affected, although it was not intended to be a substitute for the cuts. The extra support helped the partners manage their cashflow at a very difficult time and allowed them time to review and restructure their operations as the full extent of the cuts became apparent. The programme was also able to take advantage of further departmental underspends that emerged midway through the financial year, again utilising the available headroom in the programme, to provide a further uplift to partners.

The Accountable Grants were amended as follows:

The grant with the Danish Refugee Council, who host H2H, was increased to £9.865 million, by:

  - £500,000 in October 2024 for the Lebanon Activation
  - £1.25 million in February / March 2025 for the Democratic Republic of Congo Activation
  - £150,000 in May 2025 for the Myanmar earthquake Activation
  - £2.140 million in October 2025 to support the Syria Activation and the Localisation Pilot (£1 million), plus £1 million to REACH and £140,000 to GISF (as a pass through)

The grant with the Norwegian Refugee Council, who host ACAPS, was increased by £400,000 to £2.4 million in February 2025, and a further £496,000 to £2.896m in November 2025.

The grant with INSO was increased by £600,000 to £2 million in February 2025, and a further £400,000 to £2.4 million in November 2025.
H2H and ACAPS have provided quarterly narrative and financial reports, and INSO have provided six-monthly narrative and financial reports, plus quarterly check-in reports. The quality of narrative reporting received from the partners has noticeably improved following support provided by the MEAL consultant, who has encouraged them to demonstrate evidence of tangible outcomes, and how their work has brought about change and influenced the wider humanitarian system.

The Programme Team have continued to hold quarterly meetings with each of the partners, as well as ad hoc meetings when necessary. These meetings have allowed the programme team to discuss progress with each of the partners and explore some issues in greater detail. Financial management and risk management are standing agenda items at these meetings.

Financial management and forecasting have generally improved and become simpler with H2H being recognised as a multi-donor pooled fund. Reduced capacity within the Programme Team have created temporary challenges around financial management and compliance, however, these have largely been resolved by surging additional staff into the team.

G: MONITORING, EVIDENCE AND LEARNING

FCDO’s MEAL consultant has continued to provide support to HEP partners. Support has been provided to the development of individual results frameworks, quarterly reporting linked to the logframe and the design of an overall HEP umbrella log-frame. This has streamlined reporting and ensured evidence required for the AR and MEAL is captured more systematically.

Following consultation with partners and FCDO a number of support priorities were identified. One of the key gaps agreed was the need to better demonstrate the added value of enabling services and the need to strengthen reporting on programme outcomes. Research was undertaken on best practice on the capturing and reporting of outcomes. Key actors such as Saferworld and those involved in advocacy, conflict resolution, peacebuilding, biodiversity, and climate change programming, were interviewed on their approaches. A series of learning events were then designed and facilitated to share good practice. These were jointly facilitated by Saferworld who shared their outcomes harvesting approach with participants. These were attended by over 20 representatives of HEP partners, the H2H network and those specifically involved in the current H2H DRC and Syria funding activations.

The outcomes approach was trialled by several participants in some small pilots using the tools to collect examples of change into an ‘evidence pot’. A peer reflection process was undertaken on the significance of the changes captured and discussion of how they inform an understanding of added value of the work of HEP held. The consultant developed a series of accompanying guides and simple tools to share with partners. Work on ‘outcome harvesting’ has supported partners to better identify examples of change that HEP activities have contributed to, such as changes decisions, policy, action or strategy.

Several partners are involved in testing new indicators and designing surveys for users of their products. Members of the DRC and Syria activations have been involved in webinars to share their approaches, tools and pilot a simple approach to capturing and reflecting on the significance of example outcomes.

A clear plan for MEAL is in place, and the consultant and partners hold regular discussions on MEAL priorities and activities. Online and in-person support is provided on various aspects of MEAL as requested. Regular visits to all partners to Geneva and the Hague are undertaken by the MEAL consultant to facilitate joint work and learning. Partners engage in regular webinars on MEAL facilitated by Saferworld and the MEAL consultant. These have evolved into the beginnings of a Community of Practice (COP) focused on sharing good practice and approaches between partners, with several sayings its their first external MEAL engagement.
Ultimately, this work will help FCDO to better understand and demonstrate the value of HEP and will support the design of the successor programme.

MEAL Recommendations
- The MEAL consultant should continue to facilitate the sharing of good practice, tools and guidance between partners specifically on; strengthening outcome reporting, indicator development, collecting feedback, developing case studies and examples.
- HEP should work with partners to continue to strengthen partner results frameworks, reporting and the inclusion of qualitative evidence and evidence of outcomes.
- The MEAL consultant should work with partners to pilot and review the evidence collected on new indicators introduced into the logframe in 2025 and capture any learning from this.
- The HEP MEL consultant should continue to facilitate regular MEL webinars and the evolving MEL COP with partners. This should focus on the sharing of good practice, challenges, problem solving and capturing learning.
- The MEAL consultant should continue to support partners in piloting of evidencing of outcomes and the collection of examples of change based on the approach shared in the webinars. This should include testing tools, templates and reviewing significance of examples.
- Partners and the MEAL consultant should continue to identify strategic end users of their products who can influence the sector through using their products and design approaches to collect feedback. This should include feedback on how products have influenced decision making and contributed to change. Approaches to capture and report on informal feedback and ad hoc/informal feedback received such as through emails, discissions and phone calls should be strengthened.
- The MEAL consultant and partners should work together to better articulate their collaboration, what they want to do together as enablers and what the intended outcomes of this collaborate is.
- The MEAL consultant should continue to capture learning and support the development of the overall HEP results framework for the next iteration of HEP. The framework should articulate partners outputs and outcomes at country, crisis, global and sector level and any collaboration between them.

Date of last narrative financial report		Date of last audited annual statement