## Annual Review Template

Title: Governance Foundations to Sustain Forests and people: Forest Governance, markets and Climate programme Phase 2 (FGMC2)
Programme Value: 10yr BC full value: £500m; / £220m approved by Ministers for the first 5 yr period		Review date: 09/10/25
Programme Code: [AMP ID#] 301073	AMP start date: August 2024	AMP end date: August 2034

Summary of Programme Performance
Year	2025	2026	2027	2028	2029
Overall Output Score	A+
Risk Rating	M

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301073 Documents
DevTracker Link to results framework:	Available from 3rd Oct

A. SUMMARY AND OVERVIEW

Description of programme
The aim of the Forest Governance, Markets and Climate (FGMC2) programme is to reduce the illegal and unsustainable use of forest resources, while benefitting poor, forest-dependent people, especially Indigenous People and Local Communities (IPLCs). It promotes sustainable growth in developing countries, supporting them to trade their way out of poverty by changing the way forest products are bought and sold across the globe, establishing forest stewardship to reverse forest and biodiversity decline.
The FGMC2 programme vision is that by 2035 there will be no major international outlets for illegal forest material and that regional and domestic trade in illegal forest products will be significantly reduced. Rights for local communities and Indigenous People will be clarified and respected, and sustainable multiple use forest management practises that incorporate carbon values will be operational in the productive forest areas across as many as 16 partner countries, representing over 360million ha of primary forests (roughly 40% of tropical forests).[1]
[1] Reflects the total area (millions of hectares) of primary forests an estimated 369m ha out 884m ha primary forests in 37 tropical countries, comprising Indonesia, PNG, Solomon Islands, Laos, DRC, Cameroon, Rep of Congo, Ghana, Liberia, Guyana and Gabon, Cote d’Ivoire, Thailand, Cambodia, Surinam, Bolivia (scoping is yet to begin in the latter).
To deliver this ambition, Ministers have approved up to £500m, in a 10-year Business Case, with budget approval of £220m for the first period of the programme as set out in the Business Case (BC). This is the first AR since the programme BC was approved in August 2024.
FGMC2 engages with tropical forest producer countries, consumer countries with significant forest footprints, and international policy processes that influence forest stewardship. Key to FGMC’s approach is the interplay between national and international, between producer and consumer interests that creates the space for and drive reforms.
In up to 16 tropical forest countries, FGMC2:
- Strengthens governance by addressing conflicting policies on forest land uses, including Indigenous rights, carbon, timber, agriculture, and mining.
- Supports national systems to verify compliance with governance frameworks, such as sustainable timber supply chains and national sustainable forest systems (NSFS), including those delivering licences for Voluntary Partnership Agreements[2].
  [2] VPAs are a key element of the EU FLEGT Action Plan, which aims to address illegal logging. Under a VPA, the partner country agrees to export only legal timber products to the EU. The EU agrees to give verified legal ('FLEGT-licensed) timber products from the country free access to the EU market.
- Enhances inclusive forest governance to align with national development and climate goals, and to build investor and business confidence.
FGMC2 partners with commodity-importing countries to promote sustainable forest footprints by:
- Reducing harmful impacts of investments on forests and forest communities.
- Promoting responsible business and investment practices.
- Encouraging deforestation-free supply chains and adherence to environmental, social and governance (ESG) standards that aim to protect forests.
- Blocking illegally sourced timber and products from illegal forest clearance.
At the international level, FGMC2:
- Influences global norms and market standards for responsible trade and investment.
- Shares partner country experiences to support broader forest governance reforms.
- Promotes recognition of forest governance in sustainable investment policies.
- Is establishing a global forest governance hub to support collaboration, south-south exchange, and donor alignment.
- Advocates for inclusive participation and equitable access to information in global forums.
Contextual update:
Since the writing of the FGMC2 business case, the global geopolitical context has changed weakening some of the international norms and institutions related to trade, environmental and social protections and tilting away from action to combat climate change and forest loss. This is exemplified by EU decisions to delay the implementation of the EU Deforestation Regulation designed to stop deforestation through market signals, and to cancel Voluntary Partnership Agreements designed to improve compliance and standards of forestry. Given that the programme is designed to work with trade levers and to strengthen the rule of law, it has reflected on these shifts, revisiting the Theories of Change assumptions and adapting strategies grounded in continual international and national political economy analysis related to forest governance and stewardship.

The political economy context in the UK has also shifted with reductions in ODA over the next Spending Review and associated budget uncertainty. FGMC2 is well positioned to adapt to these shifts, designed to scale up or down in line with budget availability and political priorities. While next FY budget allocation has not yet been determined, the programme will adapt its strategy for engaging with new countries, for example by limiting engagement to 10 forest countries, and delaying planned engagement with 6 further countries until such time as resources are increased, or until we scale back in existing partner countries as needs or priorities change. This flexible approach also allows the programme to invest in or divest from action in countries depending on whether the political context is conducive to supporting forest governance policy reform processes.

Summary supporting narrative for the overall score in this review

This AR covers the period 1st July 2024 to 30th June 2025. It includes the period pre-dating Business Case approval in August 2024 when resources were drawn for design work as well as work through the first year of implementation supported through a bridging arrangement that enabled the programme to sustain critical actions and partnerships whilst procuring the programme’s three main delivery contracts. This year is referred to as a bridging period.

The programme has a score of A+ for the reasons outlined below.

As FGMC1 came to an end, business case preparation and approval was significantly held back due to the calling of a general election and the change of government. This put at serious risk the critical relationships and reform processes built and driven forward over many years. There was concern that key personnel whose skills were honed over many years would be lost whilst procurement and mobilisation of delivery instruments were underway. For this reason, a bridging arrangement was established through an MOU with long-term trusted partner the European Forest Institute (EFI). This enabled continuity for existing contracts (programme management and strategy, facilitation, and technical assistance projects) and a limited number of key grants to avoid a major gap in delivery, and provided the resource for important programme start up activities which included: scoping, relationship building in new countries, developing country strategies, preparing MOUs, developing MEL systems, and launching a new accountable grants programme.
This bridging MOU has delivered excellent value for money. Without it, the programme likely would have faced a one-year delay before becoming fully operational. Thanks to all the groundwork done over the past year, the stage has been set for the programme to run at full speed by the end of 2025, rather than well into 2026.
Thanks to the bridging MOU:
- A seamless transition in programme oversight has enabled a new team to capitalise on the previous programme’s working relationships with partners, draw lessons from the earlier programme to shape MEL, inclusion and country strategies, policy engagement and new grants programme design.
- Analysis, dialogue, and engagement across 10 partner countries have enabled new support projects to hit the ground running.
During this bridging period and through its first year, the programme has not only advanced well with putting in place the building blocks required as planned, priming the programme for an efficient and effective start. It has also driven transformational shifts resulting in real world change by sustaining existing relationships, maintaining momentum in policy reform processes and retaining key personnel. Examples include:

Programme wide analysis carried out, and systems developed ensuring that, once mobilized, new delivery contracts could “hit the ground running”

A significant investment has been made in this reporting period to design and procure the delivery instruments, priming them for action. For example: the programme management strategy support team (PMSST), central to FCDO’s management of the FGMC2 programme, was contracted in April 2025 and successfully ended their inception phase in June, finalising the approach to programme wide monitoring evaluation and learning, initiated under the bridge arrangement, in so doing gaining substantial time. The short inception period was possible because of the bridging phase. A Project Portfolio Manager to oversee technical support to partner countries was contracted in August, and a new Facilitation Service is also under procurement, with both expected to be mobilised by early November.

Also, during this period FGMC2 launched its competitive accountable grants programme, receiving over 191 concept notes, selecting 27 to take forward to full proposal stage. Approximately 20 will be approved in October/November with implementation commencing in November 2025. By hosting an Annual Stakeholder Forum of the FGMC’s community of practice in January 2025, bringing together partners and organisations linked to FGMC2 and its objectives, the programme was able to energise interest in the forthcoming accountable grants call for the new programme, to maintain established relationships, and to bring in new members working in new countries and on new themes (such as forest carbon and mining). There was a palpable sense of excitement at the event, which was well attended, and which set up (anecdotally) new connections between partners.

In addition, the bridging arrangement was used to prime country-specific elements of the programme and delivery instruments ready for a rapid and effective start up. This included country scoping missions, analytical work, relationship building and outreach to stakeholders to develop country and thematic theories of change country strategies and to develop terms of reference for TA projects. This upfront investment means that the newly contracted Project Portfolio Manager (PPM) will be able to immediately start project preparation with the first batch of 5 countries identified for technical support, enabling projects to get underway from as early as November 2025 (Indonesia, Liberia, Ghana, Cameroon and China).

Relationships have been built in new countries linked to new policy themes, identifying new reform processes to support

FGMC2 is designed to broaden out from the first phase both thematically and geographically. During the bridging phase, FGMC deepened partnerships to expand areas of focus, and laid the groundwork for future action across new countries not covered under the first phase. For example: In Vietnam, it is supporting stakeholder Working Groups on consumer market regulations including the EU Deforestation Regulation, strengthening traceability systems and civil society engagement. In PNG, FGMC is backing the development of a Timber Legality Verification System and economic modelling tools, while building a strong relationship with the Forest Authority. In the Solomon Islands, FGMC is becoming an important partner for forest governance, supporting policy development and stakeholder engagement, including in the emerging carbon market. In Cameroon, FGMC advanced a formal partnership with the Ministry of Forests and Wildlife (MINFOF), aligning support with national forest certification goals.

Sustained trusted relationships, driving transformational change with some notable real-world successes:
Ghana, with sustained FGMC support, has advanced to issuing licences for all its timber exports, with FLEGT licenses for timber destined to Europe taking legal effect in October. This marks the culmination of over a decade of investment in improved, national scale, forest governance transformation, positioning Ghana as a global leader in legal and responsible forest production. A FLEGT license certifies that timber has been harvested in full compliance with all the social, environmental and fiscal requirements and meets the EU’s due diligence requirements with full traceability in supply chains. The full-scale operationalisation of Ghana’s Timber Legality Assurance System demonstrates strengthened oversight, streamlined business processes, and enhanced transparency and accountability. This system is reinforced by independent audits and active CSO-led independent forest monitoring lending it the credibility required by international markets. These improvements support more effective forest management by ensuring that logging is aligned with management objectives—allowing harvesting only in forest reserves with updated management plans—and by promoting better application of forest management prescriptions through compliance reporting under the timber legality auditing system. It also has resulted in improved revenue collection with a steady 100% increase from 2020 to 2024 (a composite of fees due), improved disbursement to local government and more effective benefit-sharing with local communities through Social Responsibility Agreements. Forest communities and traditional authorities are now receiving significant revenue—£75,000 to £100,000 annually over the past three years—thanks to private sector compliance with these agreements – demonstrating real world change.

FGMC’s sustained support has enabled Indonesia to maintain reform momentum during a period of significant domestic political change, and to resist rowing back on the universal application of the reformed regulatory system in spite of significant pressure. The programme kept the Ministry of Forestry (MoF) closely engaged, supporting their ambition to lead the Broader Market Recognition Coalition (BMRC) of national forest systems and contributing to the agreement on a new partnership with FGMC. The programme also supported the upgrade of Indonesia’s timber traceability system to provide the evidence required by businesses for compliance with EUDR requirements. FGMC grant partners continued to engage in the Indonesian Sustainable Palm Oil (ISPO) and Indonesia’s Timber management processes, ensuring that civil society perspectives were represented in national standards, compliance monitoring and ensuring inclusive dialogue in forest governance – demonstrating real world change

The bridging MOU has allowed FGMC’s expert facilitators to continue their work uninterrupted, preserving momentum in countries where trust has been built over years. In Liberia, FGMC’s support has sustained inclusive dialogue through platforms like the National Multistakeholder Monitoring Committee, engaging government, civil society, communities, and the private sector. These platforms have enabled discussions on IPLC benefit sharing and forest sector regulations, maintaining governance progress amid institutional fragility, political shifts, and changing donor priorities. FGMC’s ongoing involvement has fostered trust and laid a strong foundation for FGMC2’s future support to further strengthen governance for Liberia’s sustainable economic growth – demonstrating the vital importance of sustaining relationships for influential partnership.

Major lessons and recommendations for the year ahead

Lessons:
The key takeaways from the bridging period and first year of the programme are:

In managing the transition from phase 1 to phase 2 of a programme there is a need to anticipate and plan for a bridging period to sustain key actions and relationships while internal systems play out. A well-constructed bridging phase with a reliable partner avoids any “downtime” between phases and the cost of re-establishment, allows for the retention of key personnel and institutional memory, removes the need to reconstruct working relationships, and therefore represents excellent value for money.

Positive relationships can be developed and maintained even with limited budgets when there is a long-term commitment to accompany reform processes at a more political level. When communicating the potential implications of future budget reductions with partner governments, feedback from at least three Ministers has indicated appreciation for long term commitment, respectful partnership and listening to partner needs as more important than the quantum of finance. FGMC is forging strong partnerships, backed by MOUs, with modest budgets.

Working with partners in shaping FGMC support to their reforms is helping to bring strong ownership and a sense of genuine partnership with FGMC and the UK. This includes flexible mechanisms that allow for different ways to organise and shape future projects - from facilitated co-design at every stage of development to non-objection and a role in assessment panels.

The flexible and adaptive design of FGMC2 set out in the BC bodes well for the ability of the programme to adapt accordingly to ODA reductions and uncertainty.

An increasing focus on deregulation across the globe is proving a threat to forest protection, with trade rules under question and domestic ambition being impacted, both in terms of addressing the footprint of consumption (e.g. through the further delay of regulations in the EU and UK) and in terms of wobbles in national adherence to previous norms (as seen in Indonesia). This reinforces the importance of international alliances and support built through multi-stakeholder dialogue, and the need for private sector leadership including through engagement with trade bodies.

Recommendations:
The year ahead will be the first full year of implementation with all delivery instruments operational, and with a clearer picture of the budget settlement available over the next several years. Given the importance of coherence across the programme components to optimise results and ensure value for money, ensuring that all delivery instruments work in synergy, and the central importance of the PMSST role in supporting this, it is recommended that no later than 6 months prior to the next annual review (October 2026), the PMSST supports a series of reflections to review:

- How effectively the different delivery instruments available to FGMC2 are interacting with each other
- The MEL approach, and to adjust the logframe after at least 2 quarterly reporting cycles have tested:
  - the ease of use of reporting templates,
  - quality of information being reported from delivery partners and whether it is meeting the needs of the indicators in the logframe but also reporting sufficiently qualitatively against the ToC,
  - the usability of the index indicator methodologies.
  - The need for other indicators to capture more qualitative progress for example of the community of practice and its role in the amplification of FGMC2 learning.
- The optimal reporting formats for annual reporting to FCDO.

1. Given the recent decision by the EU to further postpone the roll out of its Deforestation Regulation (EUDR), the programme team will need to reflect on the implications of this decision for the international forest policy landscape. There may be opportunities as well as constraints generated through this decision, and it will be important for the programme to understand how this plays out in each of the countries and in the international forums where we engage.
2. As soon as accountable grants are awarded and all new governance projects identified, the PMSST should plan for the Annual Stakeholder Forum to take place in early 2026.
3. In developing the strategies to inform FGMC work, the team has engaged with wider IFU and cross HMG to inform the programmes actions in new domains such as carbon governance and to foster synergies across programmes. This cross-team engagement has proved useful and FGMC should continue to explore how to build links between HMG programmes and HMG international policy influencing. There is an opportunity to deepen the governance components of other HMG forest programmes, learning from FGMC, and for FGMC to respond to governance needs identified by other interventions for example to address systemic barriers to commercial investment to enable greater flows of private finance.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

FGMC2 works at international and national levels to sustain forests and restore degraded lands to deliver for poor people and build resilience to and mitigate climate change. It addresses governance failures by both government and market to curb deforestation, restore degraded lands and ecosystem services and sustain livelihoods for people in tropical developing countries. It actively promotes a legality-based approach through (a) international rules-based systems for trade and investment in forest, mineral and agricultural products grown on forest lands; (b) national inclusive decision-making that clarify rights and responsibilities, ensure compliance with social and environmental safeguards, strengthen institutions to ensure production and trade balance with local interests, (c) governance foundations to strengthen national climate strategies to sustain and restore forest lands.
FGMC supports the interactions of national stakeholders, not just governments, across these three interrelated components operating at global and national level, and through bilateral alliances. FGMC fosters and supports these critical interactions, by convening meetings between trade associations in producer and consumer countries regarding legality and standards, south-south exchanges to share experiences and learning as well as regional and global events where national stakeholders from both FGMC-supported and non-supported countries participate. These global and international interactions are critical to building coalitions of practitioners, fostering national debate in FGMC-supported countries, and introducing and ‘amplifying’ ideas and momentum to nascent processes in non-FGMC-supported countries.
A simplified programme ToC is depicted below (Figure 1). In a nutshell the intervention logic is that: national, multi-stakeholder deliberative process (Output) will result in a consensus interpretation of the rules (forest laws, norms, institutions etc) that govern the forest sector (Outcome) which will be enforced effectively and fairly (Impact) and, in turn, lead to benefits for People, the Forests and the Planet (Super Impact).’ ‘To secure results at scale, consumer markets (including carbon) have to address demand through the rules governing their forest footprint and global norms established through international processes seeking to safeguard forests.’
There are no changes to the Impact or Outcome indicators from the original BC. Over this first year, the team has developed the MEL approach for the programme that will enable the team to track progress and test assumptions underpinning the programme’s ToCs.

The programme’s Outcome statement is the achievement of a Strengthened national and international policy framework comprising:

- Coherent and effective national policies, laws and standards stimulate governance reforms in tropical forest countries and influence global forest-related trade policies and norms
- Coherent and effective international rules-based system that stimulates and supports governance reforms in producer countries supported by FGMC and beyond and which reflect the realities and needs of forest countries

Figure 1 – simplified ToC
The three indicators at outcome level are:

Outcome Indicator 1: Extent to which national policies supporting effective forest stewardship are in place
Outcome Indicator 2: Degree to which alliance (consumer) countries[3] have put in place policies and regulations to mitigate their forest footprint
[3] Alliance countries are defined as those whose demand is driving illegal logging and forest conversion in many tropical countries, sometimes acting as import processing hubs for onward export, and which could improve their forest footprints were they to tighten up on their sourcing regulations.
Outcome Indicator 3: Extent to which international policy processes have created incentives for national-level forest-land governance reforms and foundations for better forest stewardship
A series of indices are proposed that will enable progress against these indicators to be assessed. These indices are still to be operationalised with the processes and mechanisms needed to collect the evidence that underpins them still being tested. For the purposes of this AR, a selection of examples of progress that broadly align with indicators at outcome level are set out below.
## Outcome Progress area 1 – Extent to which national policies are supporting effective forest stewardship are in place

- The Legal Framework in the Republic of Congo is enabling community forestry and the protection of IPLCs’ rights. Implementing regulations for the new forest law are being promulgated, drafted through a multi-stakeholder group. With FGMC support, civil society organisations are working on the text in advance to provide qualitative inputs to the process. During this reporting period, it included inputs on community forestry regulation and a bylaw on IPLC rights in forest concessions.
- Benefit sharing in Liberia has improved. The National Union of Community Forestry Development Committees (NUCFDC) reported that nearly $4.7 million out of a total $10.2 million owed to communities has been paid, with the government planning to settle the remaining balance.
- In Solomon Islands an inclusive carbon trading policy is under development., The Ministry of Environment, Climate Change, Disaster Management, and Meteorology (MECDM), with support from the Global Green Growth Institute (GGGI), is leading the development of the policy and a Project Steering Committee and Technical Working Group have been established to ensure a multi stakeholder process. FGMC is providing complementary support on outreach and engagement with customary resource owners and local stakeholders to ensure their voices are heard and reflected in the policy.
- In Indonesia FGMC-supported grantees are improving forest policies and regulations to close loopholes and push for compliance. Grant partners EIA and KT organised dialogues with stakeholders and supported independent forest monitoring to counter changes that could undermine the existing Timber legality Assurance System (TLAS) known as SVLK in Indonesia. Although joint statements and a social media campaign resulted in the postponement of proposed relaxation of SVLK requirements, these attempts demonstrated that, in the current political context, deregulation remains a key threat to forest governance reforms
- Advocacy efforts by broad-based coalitions using clear evidence generate political momentum and public pressure that the Government finds increasingly difficult to ignore. Civil society and media in Ghana successfully increased pressure on political parties in the run-up to the December 2024 general elections regarding destruction of forests and pollution of watersheds caused by illegal mining.
- Modest FGMC support and the inspiration of south-south learning is helping PNG’s Forest Authority (PNGFA) realise its ambition of increased market access and strengthened domestic downstream processing of its timber. FGMC supported pilot audits of the Timber Legality Standard (TLS), including the synthesis of findings. PNGFA is now laying the groundwork for a roadmap towards a full Timber Legality Verification System (TLVS), a key first step in securing credibility on the international market.
- Guyana's TLAS implementation continues advancing, with the objective of achieving FLEGT licensing in 2026. The formal rules of procedure and arbitration protocols were adopted at the fourth Joint Monitoring and Review Committee meeting.
- Despite the planned termination of the Cameroon-EU FLEGT VPA, Cameroon demonstrated strong ownership and commitment to upholding its principles. The preparation of the secondary legislation of the new Forest Law from July 2024 is seen by MINFOF as a good opportunity to revive deliberative, facilitated processes that will also have in scope the monitoring of the national forest governance/ public certification system. FGMC2 is set to support.
## Outcome Progress area 2 - Degree to which alliance countries have put in place policies and regulations to mitigate their forest footprint and incentivise forest stewardship in tropical forest countries

- The China Securities Regulatory Commission (CSRC) in 2024 mandated ESG reporting for major listed companies by 2026, aligning with international standards. This has provided an entry point for FGMC to collaborate at industry levels on improved practices and disclosures to create more transparent supply chains.
- Forest Trends analysis found limited impact from direct government engagement in Japan and Korea, prompting reflection on the need to shift toward working with trade associations and industry platforms. This strategic adjustment prioritizes private-sector partners and has broadened Vietnam’s Forest Authority’s (VNForest) exposure to market-driven approaches.
- EIA investigations revealed that illicit timber from Laos is laundered into Vietnam, mainly for domestic furniture production, not destined for export. Weak controls in Vietnam undermine regional legality efforts, highlighting the need for stronger market regulation and traceability, particularly in the domestic market. These findings will also support FGMC grantees in advocating for structural reforms through policy dialogue with VNFOREST and industry groups.
## Progress area 3 - Extent to which international policy processes have created incentives for national-level forest-land governance reforms and foundations for better forest stewardship. Some examples from this past year include:
- FLEGT timber licenses signal comprehensive market assurances: With FGMC support, Ghana has built a robust, rules-based system to verify timber legality. The system is now fully operational, and Ghana began issuing FLEGT licences in August 2025, demonstrating through its evidence strong forest stewardship.
- Vietnam timber product exports and US market influence: Despite the end of US support to Vietnam’s forest sector, the impact of the US Section 301 investigation remains. Vietnam, which supplies up to 40% of US wood imports, continues to face pressure to prove legality and origin of its products.
- Broader Market Recognition Coalition (BMRC) expands its relevance: BMRC remains active, with member and new observer countries committed to improving forest governance and building systems that demonstrate timber legality and sustainability to global markets.
- An influential review of IPLC protections in REDD+ finance: In close collaboration with International Forest Unit colleagues in the REDD+ team in DESNZ, FGMC commissioned Natural Capital Advisors to assess IPLC safeguards in key forest carbon standards and instruments: ART TREES, Verra JNR, and GCF. All showed gaps, with ART TREES offering the weakest protections. Findings have informed UK government input to consultations on GCF and forest carbon standards.
- Impact of EU Deforestation Regulation (EUDR): Although the EUDR is again postponed, it is influencing global agricultural commodity trade, pressuring producers in Vietnam, Indonesia, and West Africa to prove compliance and deforestation free supply chains. Major importers of forest risk commodities like India and China are likely to face scrutiny due to their links to deforestation and in-country processing for onward export to the EU and are therefore looking to prepare for its implementation.
- China’s EUDR readiness: InFIT partners, especially the Chinese Academy of Forests, are monitoring EUDR developments and advising China’s forestry authority. They have conducted field research, training, and provided due diligence guidance to prepare Chinese timber enterprises for compliance.
- Strategic work on forest-mining nexus: FGMC has deepened its understanding of the forest-mining link in China, Indonesia, and Ghana. This work gained visibility at the January 2025 Stakeholder Forum, and key stakeholders have been identified for future engagement.
Gender and Inclusion
FGMC2 has been designed to deliver in compliance with FCDO commitments on gender and against the Public Sector equality duty. The key assumption underlying FGMC is that genuinely inclusive and deliberative decision-making will result in more sustainable, robust, and legitimate outcomes (legal and administrative reforms) and contribute to benefits for both people and forests. Therefore, inclusion is at the centre of FGMC’s approach – cutting across all its activities and processes. The social outcomes of the policy changes being promoted will inevitably have differential effects on groups in society, including Indigenous People, local communities, informal private sector, and women and girls.

Incorporating gender issues into the development of forest governance arrangements and the sustainable management of forests is critical to ensuring inclusive, legitimate, and socially accepted outcomes. Discrimination, lack of rights and security, and limited opportunities lock women, indigenous people, and informal private sector actors into a cycle of vulnerability and poverty. Therefore, gender equality and inclusion are promoted by securing gender justice in law reforms and the use of forest resources.

One of the recommendations from Phase 1, carried into Phase 2 of FGMC was to strengthen gender reporting. For the first time, from next reporting year, FGMC will be able to report against the OECD DAC gender marker, with gender specific indicators built into the programme logframe and reporting framework. FGMC is exploring where it might be appropriate and feasible to consider disability within the programme’s approach and reporting on political inclusion.

Examples of progress:

Activities have begun to yield tangible gender impacts, particularly in forest governance, land rights, and community leadership. In Côte d’Ivoire, ClientEarth’s partner IDEF facilitated the creation of two women’s associations in Diafla and Doufla, following sustained engagement and awareness-raising efforts. These associations, each comprising 15 women, were granted land and formally registered with local authorities. This marks a significant shift in community norms, challenging entrenched taboos around women’s land ownership and inheritance. The initiative aims to strengthen women’s participation in agroforestry and forest restoration, with further capacity-building planned to support legal and managerial competencies.

In Liberia, legislative reforms mandating women’s inclusion in forest management bodies have led to increased female representation in community-level governance. Awareness campaigns have complemented legal provisions, helping to shift cultural attitudes and promote sustainable forest management practices that reflect women’s reliance on non-timber forest resources. Similarly, the Environmental Investigation Agency reported that training and advocacy efforts have empowered Indigenous and local women to participate more confidently in stakeholder dialogues, contributing directly to policy discussions.

Fern noted that advocacy for female smallholders has led to more tailored support mechanisms, particularly in the cocoa supply chain, enhancing women’s economic resilience. In Ghana, despite persistent socio-cultural barriers—such as restrictions on public speaking and land access—community forest monitoring trainings have helped empower women and girls to challenge these norms. In Liberia, policy changes have resulted in a legislative move towards more equitable access of forest resources for women and girls, with increased potential for them to start seeing the benefits of improved legal protection and equal opportunity in decision-making and benefit-sharing.

In the Republic of Congo, capacity-building efforts are enabling more women leaders to participate in local development planning, surfacing gender-specific issues such as water pollution and childcare needs. In Ghana, the formation of the Women in Timber Ghana Association (WiTG) is enhancing women’s understanding of legality and sustainability requirements, positioning them as emerging stakeholders in forest policy processes.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track with its planned year 1 actions and the bridging arrangement has allowed the programme to sustain support to advancing forest governance reforms and thus advancing further than would be expected for the 1st year of the programme. The building blocks established this year will enable to programme to advance at planned pace next FY. The progress made this year in sustaining important processes and relationships bodes well for future progress.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The approach that FGMC takes to establishing relationships with partner governments, supporting their ambitions for their forest sectors through policy and regulatory reform, enabling stakeholders to engage in reform processes, ensuring they are well evidenced and inclusive, and laying forest governance foundations that will enable countries to attract and benefit from climate finance and responsible investment, and trade in new markets, is well aligned with the FCDO’s approach to modern partnerships.

Despite being concerned by news of UK ODA cuts, partner government Ministers have stressed that the long term and respectful nature of the FGMC partnership is far more important than the quantum of funds available; it is this commitment that gives them the confidence to lead challenging governance reforms.

The programme is designed to flex in accordance with changing resource availability and political context. It is therefore well adapted to current uncertainties over budget availability and remains a highly relevant programme within the ICF forests and nature portfolio.

## C. DETAILED OUTPUT SCORING

A draft logframe was developed in 2025 but with work still ongoing to develop the complex index-based indicators and reporting frameworks for new delivery partners to use, it is not possible to report against the logframe indicators for this AR.
During this reporting year, in the absence of a fully functioning logframe with working indicators, progress reporting is set against the narrative of the three programme components and the results framework outlined in the Business Case, that have been refined into outputs for the programme logframe. A fourth temporary output is included in order to capture all the work carried out to design and mobilise the new programme, and to administer the bridge activities. Since this is a temporary output, it has not been ascribed a % impact weighting and as such will not be scored.
Output Title	Legitimate and credible mechanisms of forest land governance and management are in place in producer countries
Output number:		1	Output Score:	A+
Impact weighting (%):		67	Weighting revised since last AR?	First AR

Indicator(s)	Milestone(s) for this review	Progress
Quality, inclusivity and capacity of national (producer country) multi-stakeholder deliberative, decision-making processes - / Deliberative Change Index (DCI)	Index baselines under development / Facilitators in each partner country supporting inclusive policy processes / Design and mobilisation actions for each country carried out (see more under Output 4).	Facilitators have remained active through bridging period in Guyana, Ghana, Liberia, Cameroon, DRC, RoC, and PNG. A new Facilitation Service is being contracted with a target start date in Nov 2025. It will position facilitators in 7 countries with provision to extend to more countries if required and if budget allocations permit.
Degree to which gender opportunities and risks have been promoted and addressed within the context of national policy-making processes - / Gender Participation Index (GPI)	Index baselines under development / Design and mobilisation actions for each country carried out (see more under Output 4).	Through our limited grants and facilitators during the bridging period, focus on Gender and Inclusion has continued, with examples of strengthening capacity to engage, considering implications of reforms for women. / Gender and political inclusion strategy for the programme developed along with specific gender indicators at output level.
Effectiveness and capacity of producer country systems and institutions regulating the trade in products derived from forested areas - / Systems and Institution Building Index (SIBI)	Index baselines under development / Design and mobilisation actions for each country carried out (see more under Output 4).	All countries that FGMC country engages with are either developing or considering developing some form of timber legality assurance system, with FGMC support. These systems are at varying stages of development, e.g. Indonesia and Ghana fully functioning, and PNG starting to prepare. / Systems are also starting to be put in place for forest carbon governance and some FRCs

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focuses on developing partnerships with tropical producer countries in support of national-scale forest governance reforms.
FGMC2 provides support to establish national rules-based systems that ensure good forest land governance with a fair distribution of the costs and benefits (timber, agricultural commodities, mining, carbon, and biodiversity payments) arising from the ownership and management of forest lands and their assets, accruing directly to forest owners and managers or indirectly as public goods.
This first year has been used to ensure that we have a good understanding of the context within each country, the quality of multistakeholder processes, the degree to which gender is considered in policy processes, and the extent to which systems are in place or under development to regulate the trade in forest products or to take advantage of market incentives. Analysis has been carried out (e.g. political economy of the national forest sector, trade), scoping missions undertaken, and stakeholder consultations held to the point where we are confident that we have the right framing and that we understand the policy making opportunities in each country, the entry points for the programme, and the nature of the stakeholder dynamic. Suitable MEL systems have been developed with methodologies to track progress, and these are ready to be tested and rolled out in the coming year (see output 4).

Since the reporting methodologies against each indicator are not yet fully operational, a few examples are provided in this AR to illustrate actions against the three indicator statements, drawing on examples from producer countries.

Indicator 1: Quality of national multi-stakeholder deliberative, decision-making processes

Forest Governance Facilitators are central to supporting multistakeholder deliberative processes in forest producer countries. To illustrate the importance of this role, the facilitator in Liberia created the space for multiple stakeholders, often with competing interests, to engage and advance Liberia’s forest governance reforms. Outcomes from this facilitated multi stakeholder process included the revision of chainsaw milling regulations, the rollout of the Forest Development Administration’s Carbon Department work plan and NDC 3.0 forestry components. Additionally, the facilitator helped prepare stakeholders to benefit from a learning exchange with Guyana to strengthen Liberia’s forest partnership approach.
Examples of Inclusive decision making and deliberation in action include:

Building from experience of developing deliberative process in timber regulation, civil society organisations have transposed this experience to other threats to forests. For example, in Ghana CSO’s such as NDF, Client Earth and Fern have been stimulating stakeholder engagement and generating evidence for ongoing and upcoming advocacy and capacity building work in relation to mining in forest areas, and for commodities such as cocoa.

FGMC is supporting the establishment of mechanisms to ensure that resource owners in the Solomon Islands contribute to the development of a carbon trading policy, and to ensure that feedback mechanisms are in place for community stakeholders to not only be heard in technical working groups but for them to hear back how their concerns and suggestions have been addressed.

In Cameroon the new Forest Law was passed by Parliament then enacted in July 2024. A major overhaul of the legislation introduced in 1994, it seeks to strengthen the framework for protecting the nation’s forests and wildlife while preserving the customary rights of local communities. Innovations include the phasing out of log exports, a strong emphasis on participatory forest management, and reference to the VPA and its principles. As a next step, the secondary law must be developed and MINFOF has committed to this being done through a multistakeholder process, once the revised National Forest Governance System Monitoring Committee (NFGS-MC) has been established. In June 2025, MINFOF submitted the draft decree for the NFGS-MC to the prime minister’s office for signature and has requested support from FGMC to support the multistakeholder deliberative process.

Indicator 2: Gender opportunities and risks have been promoted and addressed in national policy-making processes. Ensuring that women’s voices are heard, their concerns acted upon and reflected in policy making is central to FGMC’s inclusive approach. Examples of where gender opportunities and risks have been considered and reflected in policy making processes include:

Liberia is in the process of developing its policy framework to regulate the voluntary carbon market, but civil society have raised concerns about the inclusivity of the process. Forest Trends is helping to develop a roadmap for non-extractive forestry income in Liberia, raising questions about community rewards for forest protection and the long-term viability of donor or carbon market funding. In Liberia, organisations such as Foundation for Community Initiatives and Sustainable Development Initiative applied gender-sensitive approaches in policy development and project implementation, ensuring equal participation and influence for both men and women. Structured approaches raised awareness of how legal reforms, such as carbon credit regulation, may affect women.
ClientEarth facilitated gender-balanced participation in Legal Working Groups (LWGs) across Ghana, Liberia, Côte d’Ivoire, and the Republic of Congo. In addition to supporting the mainstreaming of women’s voices in decision-making processes, the LWGs supported by ClientEarth in Ghana, Liberia, Côte d’Ivoire and the Republic of Congo also serve as platforms for civil society to advocate the consideration in policy of women’s rights to land and forest resources. The Gender Working Group (GWG) in Côte d’Ivoire, in collaboration with Dr. Raphael Kra, contributed to the national Forest Preservation, Rehabilitation and Expansion Policy, which recognises women as key actors in forest restoration. This led to the launch of the “Women and Forests” project, supporting women’s associations through legal capacity-building and risk analysis.

Guyana has developed tools that will help to institutionalise inclusive, multistakeholder decision-making, such as the Stakeholder Engagement Guide and the recently completed Free, Prior and Informed Consent (FPIC) Protocol. These tools and (equally important) the processes that developed them, will continue to enable the increased engagement of women and IPLCs in forest governance

Indicator 3: Effectiveness and capacity of systems and institutions regulating the production and trade in products from forested areas
Producer countries are at different stages in developing the underlying accountability systems that facilitate trade in forest related products with more demanding markets in the EU, UK, US, Australia, Japan, Korea etc. FGMC is introducing new partner countries to those with more advanced national systems in facilitated peer to peer exchanges. PNG’s visit to Ghana for example has helped PNG’s Forest Authority staff visualise what could be accomplished there, hearing directly from Ghanaian stakeholders in government, civil society and the private sector.

Whilst Timber legality Assurance systems remain central to FGMC2 and are the basis for many countries’ aspirations to be seen to be credible in international markets, other important requirements are emerging, including around forest carbon governance, regulation of mining in forest areas, and of course new requirements from the EUDR which will require producer countries to put systems in place to support compliance. Examples of actions supported through FGMC this year include:

Further support to organisational strengthening of forestry oversight in RoC is being procured to start in October 2025, to enable the Forest Ministry to implement its timber legality assurance system.
The EU Deforestation Regulation (EUDR) has emerged as an important external driver exerting pressure across timber and agricultural commodities in producing countries with significant trading relationships with the EU. Guyana for example has strengthened compliance modules for their digital Wood Tracking System in response to the EUDR
PNG has aspirations to diversify markets for its timber. Furthermore, PNG plans to ban the export of logs and to invest in downstream processing. To achieve both of these aims, PNG needs to demonstrate that it has an internationally credible system to verify the legality of its timber exports. FGMC has been supporting the PNG forest authority in preparing for the development of a roadmap to develop a timber legality verification system of its own.

Describe any changes to this output during the past year, and any planned changes as a result of this review

There are no changes to report during this reporting period.

Anticipating ODA budget reduction will necessitate a change in planned phasing-in of new countries. The team will need to develop a new strategy to amplify programme results. For the coming year the programme will concentrate where partnerships have already been built. The range of intervention areas may also become more focused concentrating on the thematic areas with greatest opportunity and traction to drive and incentivise governance reforms.

Lessons learned this year and recommendations for the year ahead
In the development and design of technical support projects, the Project Portfolio Manager (PPM) is guided by the key principle that national stakeholders are in the driver’s seat when it comes to identifying their needs and the nature of any support provided. Looking to the year ahead, it will be important that delivery instruments are able to adapt to the varying needs and pace of partners (e.g. from no objection to co-design).
During the scoping and design phase, the programme team endeavoured to coordinate and align with other major initiatives and/or other HMG programmes active in the same countries, in an effort to find both synergy and the most compelling entry points for action. This proved a very successful approach in PNG but has been more challenging in DRC for example, where the development partner landscape in the forest sector is complex and progress with other initiatives difficult to assess. We have occasionally been overly cautious about “stepping on the toes” of other initiatives, and in so doing delayed taking advantage of the entry points identified. The lesson from this is that where good entry points have been identified and others notified of our interest, we should not feel constrained to act where we have the right experience and track record.

Output Title	Effective consumer country mechanisms in place to reduce their forest footprint and incentivise producer country reform
Output number:		2	Output Score:	A+
Impact weighting (%):		16	Weighting revised since last AR?	First AR

Indicator(s)	Milestone(s) for this review	Progress
Progress of alliance partner ' efforts to reduce their forest footprint associated with trade and incentivise producer country reform - / Bilateral Alliance Change Index (BACI)	Index baselines under development / Design and mobilisation of actions with alliance countries carried out (see more under Output 4).	Scoping and stakeholder engagement for new Alliance partnerships progressing well as indicated under Output 4. Future Alliance with China and Vietnam advancing with likely partnerships secure next year. Analysis and stakeholder dialogue initiated to develop ideas for an Alliance with India. / Through the Bridge action, key relationships with Chinese institutions have been sustained and new possible partners being tested. / Through bridging action some significant progress made: / China Securities Regulatory Commission in 2024 mandated ESG reporting for major listed companies by 2026, aligning with international standards creating an entry point for FGMC to collaborate at industry levels on improved practices and disclosures to create more transparent supply chains. / China’s relationships with producer country businesses established and sustained with Gabon, RoC, PNG, SI on timber, and with Indonesia and Malaysia on Palm Oil, and with the Mekong region on rubber, timber and FRCs / Through a number of potential accountable grants, engagement with Malaysia as an alliance country is also possible.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output looks at building Alliances with consumer countries working to mitigate their international forest footprint. The trade in forest and other commodities contributes significantly to economic development in many tropical forest countries. The countries that FGMC works with are important sources of forest and forest commodities for consumer markets. In Figure 2, trade data illustrates the significance of these consumer markets, for tropical countries, and notably the growing significance of Asian markets (e.g. China, Vietnam, India) by comparison to EU/ UK’s market “pull”. FGMC has noted the importance of engaging through new alliances with these consumer markets in order to ensure that their trade and investment do not undermine the governance reforms and rule of law in developing (tropical) countries.

Figure 2 - Focus countries' wood product trade with China and the EU

Considerable effort has been made during this bridging year to sustain the relationship with Chinese think tanks and partners and in developing a new relationship with stakeholders in Vietnam. Scoping analyses and stakeholder discussions are on-going to explore the opportunities and potential for an Alliance partnership with India given its increasing forest footprint in its imports from tropical Africa and Asia.

In July 2024, FGMC’s support in China (InFIT) entered a bridging phase, continuing to provide technical and administrative support to implementing partners drawing out experience and learning and fostering stakeholder dialogue to inform the strategy for a new phase.

Since the reporting methodologies against each indicator are not yet fully operational, a few examples are provided in this AR to illustrate actions against the indicator statement, drawing on examples from “alliance” countries and their interactions with producer countries.

Indicator: Progress of alliance partner efforts to reduce their forest footprint associated with trade and to incentivise producer country reform

Examples of efforts being made to address forest footprints include:

- Although Environment Social and Governance (ESG) principles may be coming under pressure elsewhere, the China Securities Regulatory Commission (CSRC) in 2024 mandated ESG reporting for major listed companies by 2026, aligning with international standards. This has provided an entry point for FGMC to collaborate at industry levels on improved practices and disclosures to create more transparent supply chains.
- Policies designed to promote green finance (including green bonds, the carbon market, and ESG disclosures) set out in 2024, continue to provide direction for innovation in green finance instruments in the country. It is opening up opportunities for FGMC to inform how these influence investments in forest-product related trade.
- Chinese Academy of Forests (CAF) continued to represent China's policy positions and proposals in regional and international processes such as Asia Pacific Economic Cooperation (APEC), undertaking targeted research to pave the way for an effective timber legality traceability mechanism. Based on field research, training was organised, and due diligence guidance was provided for Chinese timber enterprises to strengthen their readiness for EUDR compliance.
- In parallel, CAF continued to work with industry associations to provide training to companies and to assist the associations in aligning requirements for timber legality standards with business associations in producer countries. To strengthen compliance with Vietnam’s requirements, the Country Handbook on Sustainable Overseas Forest Investment and Trade by Chinese Enterprises –was updated, and in Gabon technical support and capacity building was targeted at Chinese companies to improve compliance.

Vietnam is an important processing hub for FRCs with a growing overseas tropical forest footprint. The sustained grant with Forest Trends through the bridging period has helped to strengthen regulation and oversight of FRC production and trade in Vietnam. This has included: capacity building for authorities at local levels on legality and sustainability, especially for EUDR evidence requirements; facilitated cross-border exchanges with competent authorities from across the Mekong, and outreach to regional consumer countries, such as China, Japan, South Korea to enhance mutual understanding and to explore opportunities for cooperation. It has also focused on engagement with businesses through trade associations, aimed at helping to adopt sustainability-oriented supply chains, and improving their readiness to meet evolving market demands. Smallholders have been a key focus due to their vulnerability from shifts in international market requirements. Forest Trends has produced reports, briefings, newsletters providing insights into trade trends in forest risk commodities between Mekong countries and markets such as the EU, the US, China, Japan, South Korea, etc. A report on high-risk timber supply chains in Vietnam with connections to China is being finalised for publication in Aug 2025.

Examples of alliance country actions signalling the need for reform in producer countries:
Since China is a major processing hub with onward export to Europe, Chinese implementing partners are tracking closely the implications of the EUDR. Dialogues with important source countries such as RoC and Gabon are ongoing to strengthen understanding and transparency in supply chains, with FGMC implementing partners planning to encourage new dialogues with Malaysia and Indonesia on Palm Oil, and with PNG and SI on timber, which may incentivise reforms in producer countries as the dialogues advance.

Describe any changes to this output during the past year, and any planned changes as a result of this review

No changes have been made to this output. It is likely that the anticipated ODA budget cuts will constrain the development of further Alliances over the next several years. It was expected that the programme would undertake scoping in major regional markets in Africa (notably Nigeria and South Africa) as well as in the Middle East exploring the potential for further alliances. These actions will be paused.

Lessons learned this year and recommendations for the year ahead

Recommend reviewing the indicator – the criteria framed by the index does not adequately address the actions that alliance countries are taking which could incentivise producer country reform

Output Title	International policy processes in place to support an enabling environment for effective and inclusive national forest governance reforms
Output number:		3	Output Score:	A
Impact weighting (%):		17	Weighting revised since last AR?	First AR

Indicator(s)	Milestone(s) for this review	Progress
Progress in supporting and influencing international policy processes that create an enabling environment for national forest governance reforms - / International Policy Influence Index (IPII)	Index baselines under development / Design and mobilisation of actions for thematic domains and international processes carried out/underway (see more under Output 4).	Improved understanding and scoping of the potential of key international policy processes to influence actions that limit deforestation from mining and agriculture commodities (FRC) and incentivise sustainable forestry, and the protection of forest ecosystems for biodiversity, carbon and watersheds. / Extensive mapping and analyses across key thematic policy domains to understand threats and opportunities and to inform the development of new Communities of Practitioners / Theories of Change and engagement strategies across the thematic domains have been prepared. These will facilitate stakeholder engagement and the formation of communities of practitioners as well as the selection of Accountable Grants and future workplans.
Degree to which FGMC-funded entities have taken deliberate measures to promote and mitigate gender opportunities and risks within the context of international policy processes - / International Policy and Gender Index (IPGI)	Index baselines under development / Design and mobilisation actions for thematic domains and international processes carried out/underway (see more under Output 4).	Analysis of forest carbon standards and instruments has identified social inclusion issues, including gender, as a focus area for FGMC engagement in forest carbon governance (e.g. benefit sharing, FPIC

Briefly describe the output’s activities and provide supporting narrative for the score.

This output seeks to shape international market norms and initiatives, supports policy engagement that catalyses change in international markets and global forest governance, engages with political processes such as the climate and biodiversity COPs to galvanise international commitment and action, encourages positive international frameworks to prohibit trade in illegal material and incentivises national forest stewardship through rules that place governance at the heart of schemes/ investment strategies.

Significant effort has been invested this year in the necessary analysis and relationship building with a new range of experts, to support the programme’s expansion of scope into new thematic domains that impact forests or provide opportunity to derive greater value from them. This analysis has informed the development of thematic theories of change, identifying key international issues and policy processes that the programme will focus on. To date, progress has been made on timber and forest governance, FRCs, mining and forest carbon. The analyses and strategies to explore how FGMC could work with the finance sector (green finance and investment and on strengthening governance for other ecosystem services such as biodiversity and watersheds are less well developed.

These thematic ToC informed the shaping of the FGMC accountable grants call in March, and subsequent shortlisting of concept notes to develop into full proposals. The objective was to ensure that between them, grants cover all of these thematic domains and are designed to engage at the international as well as national level. Accountable grants are an important part of the overall suite of delivery instruments that FGMC deploys to strengthen forest governance.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No changes over the last year.

Lessons learned this year and recommendations for the year ahead

More work is needed on how best to report the work under this output.
Recommendation: Reflect on the adequacy of output indicators – they may require modification shaped by delivery partners as they come on board, in particular the grants that are active in the international policy space. Creating space for change at the national level, through the opportunities presented by changes at the international level, is currently not adequately represented in the logframe. Capturing the amplification of lesson learning from the programme and partners beyond the focus countries, and the value that the extended community of practice brings is also currently not captured

Output Title	Bridging actions and Mobilisation processes provide an effective foundation for the implementation of FGMC Phase 2 (until October 2026)
Output number:		4	Output Score:	A+ however not aggregated given short term nature of this output
Impact weighting (%):		N/A	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Key relationships with partners maintained through programme bridging period	October 2025 targets: / EFI Bridging MOU agreed / PMST function extended / Key accountable grants extended until new grants programme initiated / Key TA projects extended (Liberia, RoC) / Facilitators remain active in 7 countries / Draft programme strategy documents prepared for priority countries	EFI bridging MOU extended to end of the year to allow for delays in procurement of the new Facilitation Service contract. Otherwise, all other elements on track
Relationships and partnerships established with new countries and scoping analysis informs strategies for addressing new forest governance challenges	October 2026 targets: / Comprehensive scoping and analysis and baseline across all countries, themes and components prepared for MEL system’s output and outcome indices / Country level theories of change (ToCs) agreed internally, and Country Strategies developed and agreed with stakeholders / Thematic ToCs developed for timber, carbon, finance and investment, forest risk commodities, mining and forests	Comprehensive baselines for all countries take time to develop. The process is ongoing and will be completed by the next AR / All areas on track
Delivery instruments mobilised and operational modalities and structures agreed and established to enable rapid progress in new partnerships	All contracts and delivery instruments mobilised by October 2025, / Grants in place by December 2025 / At least 5 individual country TA projects operational by March 2026 / MEL system developed by July 2025 and operational across all delivery instruments by October 2026 / MOUs with 10 countries in place by March 2026	Currently on track to have all instruments mobilised by December and at least 4 TA projects implementing by end of March 2026 / MEL system is on track, with need for testing of indices and roll out to all partners / 2 MOUs signed (Indonesia, PNG) with a further 2 ready for signature (Guyana, Cameroon) and two in advanced stage of development (RoC, Solomon Islands)

Briefly describe the output’s activities and provide supporting narrative for the score This is a temporary output designed to ensure that the bridging year actions and associated budget is adequately accounted for given that a significant amount of effort was focused on getting the programme to a point where FCDO can have full confidence in the analysis underpinning our framing of the actions, the level of ambition, and that we have the right systems and instruments in place for efficient and effective delivery, . This approach was designed to optimise vfm by ensuring that there was not a complete loss of momentum between FGMC1 and FGMC2.

As described above, all elements are on track. The PMSST in particular has invested significant time in scoping visits, analytical work drawing on the pool of experts, developing the ToC’s for countries (output 1 and 2) and themes (output 3), developing strategies, preparing MOUs, managing an accountable grants process, and building relationships with new sets of stakeholders.

The successful delivery of this output lays a strong foundation for the implementation of the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
So far, the bridging arrangement has progressed according to plan with all deliverables on track for completion prior to the next AR. The bridging MOU with EFI has had to be extended (no cost) in order to retain the existing highly skilled facilitators prior to contracting of the new Facilitation Service. This is the only change that has occurred. This output will close at the time of the next AR

Lessons learned this year and recommendations for the year ahead
Investing in a bridging arrangement between phases of major programmes ensure continuity, represents excellent value for money by sustaining relationships, maintaining momentum and retaining key staff. Longer than expected procurement processes have more than justified the investment in the bridging year since it has provided an opportunity to shorten inception periods, ensuring that systems are in place, analysis has been done, to allow for a swift transition into implementation once contracting is finalised. Getting a head start on the accountable grants call also helped to ensure that implementation could start this financial year.

Recommend a comprehensive review of the MEL system mid-way through next reporting year.
## D: VALUE FOR MONEY

Key cost drivers and performance

As indicated in the Business Case, the key cost drivers in the programme are the specialist expertise required to deliver the different components of the programme; technical assistance, capacity building, accountable grants supporting INGO actions, research and analysis, facilitation of multistakeholder processes, as well as providing or upgrading IT infrastructure for compliance monitoring and product traceability, and training for government services, small businesses, and civil society organisations (CSOs).
As this is the first AR, it is difficult to assess the VFM performance of the programme as a whole when not all delivery instruments are fully operational. As already outlined, the bridging arrangement sustaining relationships and key reform processes, has meant that the programme has not lost momentum as it sustained worked through the transition from Phase 1 to Phase 2, has not had to recruit expert teams from scratch, and has been able to maintain trust with key partners. This constitutes significant value for money. Based on the current time frames for FCDO procurement processes, it is likely that the bridging arrangement has saved at least a year in mobilising the programme and ensured far more likely effectiveness.
The fact that key specialist staff such as facilitators, the Programme Management Support Team, experts from EFI and a pool of governance and legal experts have been retained through the bridging period has been key to sustaining delivery and effectiveness.

VfM performance compared to the original VfM proposition in the business case

After only one year of bridging support and establishing delivery mechanisms for future implementation, VFM performance remains in line with what was envisaged in the BC for the first year. VfM has been an important factor in shaping the TORs for support services, projects and grants as well as a key assessment criteria for all delivery instruments and projects.

Assessment of whether the programme continues to represent value for money
VFM requires informed decision-making based on cost-benefit analysis, risk assessment, and outcome forecasting. The Programme Management Strategy and Support Team (PMSST) throughout the bridging arrangement reviewed quarterly reports from contracts and grants to ensure detailed cost data and robust risk analyses supported VFM-based decisions. Examples include:
Financial Oversight and Risk Management
- Delivery Chain Analysis: Maintained as a live document, tracking all funded entities and spending, helping identify risks like duplicate funding amongst grants and enabling timely mitigation.
- Budget Monitoring for Grants: Quarterly forecasting and reporting ensured tight financial control. Variances between forecasted and actual spending were analysed, with disbursements adjusted accordingly resulting in only a 0.04% discrepancy between FCDO disbursements and grantee expenditure.
- Transaction Checks: Rigorous quarterly reviews of transactions helped prevent ineligible spending.
Strategic Coordination and Global Engagement
- PMSST facilitated strategic alignment between FGMC and global initiatives, sharing governance insights with DESNZ and FCDO to inform forest carbon market discussions.
- In ROC, Liberia, Ghana and other countries, PMSST supported donor coordination to avoid duplication and ensure programme coherence.
China Project Management Office (PMO)
The FGMC PMO in China remained active throughout the transition, ensuring visibility and effective dissemination of FGMC strategy.
Monitoring, Evaluation, and Learning (MEL)
- The bridging period provided opportunity to learn from Phase 1 and prepare a new MEL framework for Phase 2. This was finalised during the PMSST inception period (April-June 2025 and is now ready for testing.
- under this approach, a new approach to better track VFM performance will be developed, in particular to assess cost effectiveness.
Ensuring delivery partners consider equity as part of their VFM
FGMC partners promoted equity by ensuring interventions were inclusive (of men, women, IPLCs and small-scale entrepreneurs), rights-based, and accessible.

E: RISK

Overview of risk management
Risk appetite for the programme across its portfolio and across different country contexts is classed as Moderate, aligned with FCDO’s overall risk appetite. FGMC2 is designed to be receptive to the risks associated with challenging forest governance contexts, working to build strong governance foundations and coalitions of stakeholders engaged to challenge the status quo in the forest sector. These are mitigated through work with international policy levers that seek to create positive incentives for forest stewardship that reinforce national reforms. The programme is also willing to take on and manage reputational risk so long as that does not harm the overall programme’s licence to operate. In line with the FCDO’s new risk management approach, FGMC2’s overall risk appetite across the seven risk appetite categories is as follows:
    1. Strategy and Context: Receptive (eager in some contexts and with major residual risk balanced across different country contexts)
    2. Policy and Programme Delivery: Receptive (Global policy engagement to motivate reforms across 16 countries with moderate residual risk)
    3. Public Service Delivery and Operations: not applicable
    4. People: Cautious
    5. Financial & Fiduciary: Cautious
    6. Safeguarding: Cautious
    7. Reputational: Cautious across the programme, but receptive in specific contexts

The FCDO team has been tracking risks carefully across the year which is routinely reflected in the updated risk register and discussed in monthly meetings with delivery partners.

The most significant risks faced by the programme in this first year of implementation have included:

Political space to address forest governance: Partner country and UK Government ambition on climate and forests is diluted by geopolitical challenges, global shifts in international institutions, (de)regulations and trade rules; economic pressures and market volatility. A crowded donor landscape limits political space for inclusive national scale governance reforms.

Mitigation measures being taken include:
- Ministerial and official level engagement to maintain forest and climate ambition at country and international levels,
- building a community of practitioners to animate and inform policy dialogues,
- support national processes that spur donor coordination and pooling resources where feasible.
- Continuing FGMC’s partnership approach supporting country led priorities and processes

Viability of external market levers: Consumer market legislation (EU, UK, USA) designed to reduce deforestation is seen as a trade barrier by producer countries; combined with perceptions that the EU is no longer committed to voluntary partnership agreements diminishes the value for FLEGT licences and the reforms that underpin them. With the uncertainty around US tariffs on timber and other forest products traded particularly with Viet man, Indonesia, China and Canada, there is considerable uncertainty in global timber trade and investment flows that may shift incentives in partner countries

Mitigation measures being taken include:
- mobilising the FGMC community of practice to support increased understanding of consumer market measures in tropical forest countries and efforts of producer country coalitions to see greater understanding and appreciation of their national systems in large markets beyond the EU FLEGT, notably in Asia.
- Establishing a Communications Framework to support influencing efforts,
- Monitoring global trade dynamics trends and target actions to inform increasingly influential markets.
Shifting political priorities in partner countries: Political priorities shift in partner countries, including due to regime changes or personnel changes within partner government, requiring adjustments to FGMC's country strategies

Mitigation measures being taken include:
- Maintaining frequent engagement with country stakeholders (through PMSST Leads, Posts and facilitators,
- Conducting rapid 'everyday political economy analysis' triangulating evidence from multiple sources to stay abreast of contextual shifts.
Budgetary uncertainty during mobilisation undermines relationship building and identification of priorities with partner countries risking delivery of FGMC objectives.

Mitigation measures being taken include:
- Designing flexible Terms of Reference with break clauses
- Prioritising focal countries where relationships already built and delaying start in new countries
- Emphasising the long-term partnership approach with partner countries
- Prioritising catalytic interventions that complement the actions of other development partners

Review and ensure the main risks identified through partner due diligences,

Due diligence, including scrutiny over SEAH and fiduciary risks, has been an important area of action in this first year as new delivery instruments are being mobilised. The principal due diligence risk identified that required monitoring over this period was the need for the EFI to strengthen its SEAH policies. The DD carried out in April 2025 prior to signing the new MOU with EFI identified the need for a more robust and comprehensive standalone SEAH policy. While SEAH policy provisions were in place, they were found across different standard operating procedures. EFI had initiated a process to strengthen these into a single comprehensive policy. The SEAH policy was approved by the EFI Board in September 2025.

Accountable grant proposals selected to go to final stage of scrutiny (27 in number) are undergoing a full due diligence assessment by the PMSST and any issues identified will be addressed prior to FCDO decisions on the grant and where necessary will form part of due diligence monitoring by the PMSST.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The bridging MOU that the FGMC programme has had with the European Forest Institute since June 2024 to deliver the actions covered under this AR has proved invaluable in sustaining activities throughout the long process of obtaining business case approval and subsequent procurement of delivery instruments (still ongoing as of September 2025). EFI has been exceptionally responsive enabling existing projects and contracts to be continued under their budgetary management. In turn, these contracts have shown flexibility under challenging conditions of uncertainty, have optimised efficiencies to eke out budgets as long as possible, and have been well managed and performed well against their KPIs.

Budget allocations during the design, bridging and mobilisation period, and attribution to outputs up to June 2025 is set out in the tables below.

Table 1: Design and Bridging action through EFI MOUs to June 2025:

Budget line	Value £	Output
EFI admin of the bridge MOU action	866,232	4
EFI TA provision across all countries	2,459,799	1
TA project in Liberia sustained (Palladium sub-contract)	1,740,172	1
Facilitation service sustained (Palladium subcontract)	1,279,167	1
Sustained 5 Grants	5,130,010	1,2 and 3
Programme management support team sustained (Pegasys subcontract)	2,493,387 of which 975,082 is for InFit China	4 and 2
Programme funded roles (Indonesia, DRC/RoC, China)	£207,500	1 and 2
Design work in new countries (EFI Design MOU)	£500,000	4
TOTAL	14,676, 267

Table 2: Budget spend per output during bridging and start-up year (including temporary Output 4)

Output	Spend £	%
1	8,195,143	56
2	2,057,584	14
3	1,539,003	10
4	2,884,537	20
TOTAL	14,676,267	100

Even though this first year of reporting has not included all elements of the programme being fully active, the budget split is broadly commensurate with the proportion of spend across outputs 1-3 as set out in the Business Case. This is with the exception of the grants which are envisaged in the BC to be distributed across outputs as follows: 50% to output 1, 20% to output 2 and 30% to output 3. During this bridging period, the limited number of grants have been largely apportioned to output 1 63%, with 18% to output 2, and just 11% to output 3. This should change once the new grants programme is fully up and running and should be tracked to ensure that, as budgets become tighter, the proportion of budget allocated to Output 3 remains in line with the output’s weighting.

By end of June 2025, one new Contract was fully up and running (PMSST) with inception successfully concluded. The contract was signed in April 2025 and the inception phase concluded after three months. The short inception period was made possible because the bridging arrangement enabled the previous PMST to function through the design and bridging period of FGMC2.

The previous supplier (Pegasys) was able to perform a thorough and efficient hand over to the new supplier (NIRAS) with a number of key staff members continuing into the new contract. This enabled a quick and efficient start up.

Another contract to provide portfolio management services for a series of technical support projects to partner countries was under contract negotiation in July and expected to be contracted in August and the Facilitation Service is under procurement, expected to be contracted by November 2025.

FCDO’s FGMC core team has undergone contract management training and is well placed to ensure the adequate management of these silver contracts.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring, Evaluation and Learning (MEL)

The FGMC2 MEL Strategy is based on two complementary approaches. First, it uses a theory-based approach to support learning, around thematic and country programme theories of change designed to guide implementation. Secondly, it uses an indicator-based approach designed to support the monitoring of progress against programme-level logframe outputs, outcomes and impact. At the time of this review, both of these complementary approaches are in the process of being established and introduced across the programme.

Thematic ToCs and country-level ToCs are close to finalisation covering 11 country strategies and 5 thematic domains. These will be subject to regular review to ensure overall coherence, relevance and strategic focus. The ToC reviews will be informed by analyses of changes in the political economy and reviews of the assumptions underpinning the ToCs as well as through deliberations with sector experts and stakeholders. A system for tracking progress against programme-level indicators is also being established.

A programme-level logframe (see below) that uses qualitative indices at output, outcome and impact levels has been developed. Results reported by delivery partners against their own results frameworks will be linked to the programme-level logframe indices.   An FGMC Knowledge Management System (KMS) will then be used to harvest and aggregate the delivery partner results linked to each programme-level index on a regular basis to inform programme-level reporting.  As different delivery partners become operational, PMSST will work with them to ensure that reporting formats serve both the needs of their local partners (such as national government agencies and other steering committee members) and programme-level reporting. These include reporting of progress against the FGMC logframe (for example for Annual Review purposes), reporting back against country-level theories of change as part of the PMSST quarterly and annual progress reporting to inform future strategy and prioritisation and annual reporting against relevant ICF KPIs. This process is summarised in Figure 3:

Figure 3: Simplified diagram of MEL reporting system

The programme monitoring system is expected to be fully operational and utilised by all programme delivery partners by end of June 2026.

Programme logframe

A programme-level results frame was set out in the business case but a full logframe was developed during the FGMC2 PMSST inception phase (June 2025). Progress is measured using scored indices at output, outcome and impact level that capture the essence of FGMC programme results, with a strong focus on forest governance. Each index is based on a set of generic criteria and rubrics have been developed to facilitate scoring of indices on the basis of evidence and qualitative assessments of the current conditions against each of the criteria. The baseline, milestone and target scores for each of the programme-level indices are being established on a rolling basis alongside the development of country and global policy development strategies.  It is expected that further revisions to the logframe will be required, particularly once real data supplied through partner reporting comes on stream in the next reporting period.

 Programme baseline

The PMSST is currently engaged in the development of baselines for the output and outcome indicators, and country-level baselines (for Component 1) are a central aspect of this work. Working together with Facilitators, EFI and PMSST country leads, evidence is compiled around all relevant criteria for each of the output and outcome indicators. It is expected that a programme-level baseline will be completed for output and outcome levels by end of June, 2026 (covering all supported countries and all three Programme Components).  At impact level, a series of commissioned, evaluative studies are proposed that will benchmark key governance foundations across different country and thematic contexts. Once undertaken, these studies will be repeated mid-term and end-term to provide an overall assessment of impact-level changes across the programme.

Output and outcome indices will continue to be scored annually on a rolling basis. While the scoring process will not be undertaken at the same time for all FGMC2 countries and global processes, the scores included in Annual Reviews will all be based on assessments undertaken at some point over the preceding 12-month period. Figure 4 presents an overview of how evidence for monitoring and reporting is captured on an annual basis

Figure 4: Annual cycle of actions for programme-level monitoring and reporting

Learning

Learning takes place internally within the programme through the continual process of country engagement, political economy analysis, and the PMSST leads engaging regularly with all delivery partners operating in countries or on specific thematic areas. This enables FCDO’s small team to remain sufficiently up to date with developments and able to see opportunities for day-to-day learning across the programme as well as drawing on ideas and evidence to inform FCDO/ IFU policy reflections.

Occasional thematic, cross cutting or geographically focused seminars, bringing together all partners with an interest, also support the opportunity for learning. The Annual stakeholder forums are an opportunity to bring together the FGMC community of practice comprising, government, private sector, HMG and other donor representatives to learn from programme partners and to analyse new trends. The first event under FGMC2 was held in January 2025 to officially launch the start of FGMC2, lay the ground for the launch of the accountable grants call in march 2025, and to welcome new members of the extended community of practice bringing in expertise on new thematic areas such as forest carbon and mining in forest areas, and partners from new countries such as PNG, Solomon Islands, Laos and Vietnam.

A key recommendation from the PCR of FGMC1 was to invest more in communication and learning to wider audiences. To this end, in the design of FGMC2, greater focus has been placed on ensuring the means to communicate and share lessons learnt more broadly, without compromising on the fact that the programme facilitates others, and the experiences and lessons are theirs to convey. The establishment of the International Forest Governance Hub by the EFI, expected to be up and running by early 2026, will enable lessons learnt from the FGMC programme and others working in the forest governance space to be amplified across all interested forest countries. An FGMC website will be established in 2026 enabling engagement with a wider audience, providing access to analysis and signposting to all relevant partner social media.

Date of last narrative financial report	Aug 2025 – EFI Bridging MOU / July 2025 MFGAP Liberia / Aug 2025 Facilitation Service / Sept 2025 PMSST	Date of last audited annual statement / EFI – June 2024

Key documents consulted during this AR:

- The Annual progress Report prepared by the PMSST
- Quarterly Technical Reports (QTRs) and Annual Technical Reports (ATRs) prepared by the following organisations, all holding direct FGMC grants for the period from July 2024 – June 2025: ClientEarth, the Environmental Investigation Agency (EIA), Fern, Forest Trends, Nature and Development Foundation (NDF), and Timber Development UK (TDUK).
- The Country and Summary reports prepared under the Facilitation contract.
- The progress report prepared under the MFGAP contract (Liberia).
- The progress report prepared by EFIRRP
- The progress report prepared by the InFIT Programme Management Office (China).