Business Case

Summary Sheet

Portfolio/ Business/Country Plan Summary: / Energy Climate and Environment Directorate’s (ECED) vision is to accelerate UK action on energy security, and support just energy transitions, and action on climate change, adaptation, and protecting forests and nature. We want to position the UK as a leader on energy, climate, and environment by using our International Climate Finance (ICF), development, and diplomatic expertise to keep the 1.5-degree target alive, support the most vulnerable to adapt and build resilience to climate change, and protect nature and biodiversity. / ECED Business Plan Goal 5 aims to: Support the transition to sustainable forest and land use, food systems, water security and ocean resilience, delivered through a portfolio of ICF interventions, which deliver benefits for people, climate, and nature. / The Forest Governance, Markets and Climate Programme (FGMC) Phase II will be an important element of ECED’s forests portfolio and key to achieving Goal 5 in the ECED business plan, through a focus on addressing local and global drivers of deforestation, and sustainable practices in line with the Sustainable Development Goals and the Paris Agreement 1.5-degree target.

Title: Governance foundations to sustain forests and people: Forest Governance, Markets and Climate Phase 2 (FGMC2)
Programme summary (100 words maximum): / The aim of the Forest Governance, Markets and Climate (FGMC2) programme is to reduce the illegal and unsustainable use of forest resources, while benefitting poor, forest-dependent people, especially Indigenous People and Local Communities (IPLC). It promotes sustainable growth in developing countries, supporting them to trade their way out of poverty by changing the way forest products are bought and sold across the globe, establishing forest stewardship to reverse forest and biodiversity decline
What is the rationale for UK Aid spending? (200 words maximum): / The International Panel on Climate Change’s 2019 Special Report on Climate and Land, and the Dasgupta Review (2021) on the economics of nature loss, highlight that the degradation of nature and biodiversity is taking place on a vast scale and at rapid pace, reducing the resilience of people and economies, as well as our ability to tackle and adapt to climate change. These reinforcing crises pose a significant risk to the achievement of the Sustainable Development Goals (SDGs), with disproportionately large impacts on poor people, in particular women and girls. The UK International Development Strategy highlights that climate change and biodiversity loss will push millions into extreme poverty by 2030 and makes addressing these crises an international priority and essential if we are to create a world free from poverty on a liveable planet. / Forest loss and degradation contributes around 20% of global greenhouse gas emissions. Forests are critical for climate mitigation, adaptation and building resilience. / Forest loss has consequences for people: e.g. Over 70% of households in Sub-Saharan Africa depend on fuelwood and charcoal for their energy needs; and much of the rainfall in the Sahel – and the agriculture which that sustains – is generated in the Congo Basin. Yet global demand for a few internationally traded commodities, such as palm oil, is driving rapid and often illegal forest loss. Additionally, mining is responsible for 7% of tropical forest loss. / Poor forest governance and land-use decision making risks the livelihoods of millions of IPLC and smallholder farmers connected to global supply chains through their production of forest products and forest risk crops such as cocoa, coffee, palm oil and minerals. As consumer markets introduce regulations to shut out illegal and/or commodities produced through forest clearance, strengthening forest governance and land-use decision making will be key to supporting these forest communities and smallholder farmers to keep trading their way out of poverty
		Country/ Region or Sector: Global / Forests and Climate Change.
Department/Country Office confirmation of review processes		Director/HoM confirmation that Departmental processes for BC review have been followed prior to submission
Contact names:		Julia Falconer, Senior Forestry Adviser, SRO. / Gaia Allison, Forest Livelihoods Adviser, PRO / Estefania Liehr, Forest Policy Adviser / Daniel Reid, Programme Manager / Sarah Pettem, Economic Adviser / Joe Goodall, Assistant Economist
Threshold for final approval of Business Case: Minister for International Development; HMT.
Date of Approval of Concept Note:	1/11/2019	Minister for Overseas Territories, Commonwealth, Energy, Climate and Environment, DFID / Secretary of State, DFID
Date of Approval of Business Case:	16/08/2024	Name and role of Approver / Foreign Secretary David Lammy
Programme Code: 301073.	AMP Start Date: 2024	AMP End Date: 2034
Overall programme risk rating:	Moderate
Vault Number:

## ​​ ​​Contents

Annexes below not attached but can be furnished upon request

Annex A - Reviews of FGMC1 and the approach to policy influencing.
Annex B - Climate and Environmental Risk Screening Tool
Annex C - FGMC2 Approach to Gender and Inclusion
Annex D - Details of Appraisal of Strategic Options
Annex E - Delivery options appraisal for preferred programme design
Annex F - Detailed Theory of Change
Annex G - Economic Analysis
Annex H - Partner country analysis and engagement plans
Annex I - Component II: Consumer Market Alliances
Annex J - Forests and mining: opportunities to tackle governance failures
Annex K - Accountable Grants Scheme
Annex L - Approach to Monitoring, Evaluation and Learning (MEL)
Annex M - Programme Insourced Roles for country level engagement: Rationale and Value for Money analysis
Annex N - Review of evidence on Illegal Deforestation
Annex O - Full risk register, risk matrix and risk appetite

## Table of Figures and Tables
Figure 1 - Forest governance foundations	7
Figure 2 - Focus countries' wood product trade with China and the EU	10
Figure 3 - FGMC Community of Practice	14
Figure 4 - Consumer Market Regulations to Stop Import of Illegal Forest Products. Source: BMRC Strategy	16
Figure 5 - Nationwide Approach compared to Certification of Forest Units	19
Figure 6 - FGMC2 Delivery Model	41
Figure 7 - Overarching Theory of Change	42
Figure 8 - Hierarchy of TOCs	44
Figure 9 - Causal Model for Component I. Producer Country Partnerships	46
Figure 10 - Causal Model for Component II. Consumer Country Alliances	48
Figure 11 - Causal Model for Component III. Global Policy Engagement	50
Figure 12 - Stakeholder interaction and engagement shaping the programme logic	52
Figure 13 - Tropical Deforestation Emissions (tCO2) associated with UK commodity consumption in 2018.	55
Figure 14 - FGMC2 delivery model	66
Figure 15 - FGMC2 delivery model	81
Figure 16- - FGMC delivery chain: ECED (IFU)	82
Figure 17-Summary of programme phasing in Tranche 1	84
Figure 18 - FGMC2 Governance Structure	95
Figure 19 - FGMC2 Delivery Chain EDEC (IFU)	96
Figure 20 - Country Level Governance Arrangement	101
Figure 21- Phasing ofFGMC2 mobilisation and implementation for the first 5 year period	104

Table 1 - Expected outcomes and impacts of FGMC2	27
Table 2 - Summary table of delivery options appraisal against FGMC2 critical success factors	41
Table 3 - Breakeven PIF rates for the model’s carbon value scenarios	62
Table 4 - BCRs for different PIF rates in the central model scenario	63
Table 5 - Additional indicators for central scenario	63
Table 6 - Central Scenario Economic Model Results	64
Table 7 - Proposed Delivery Approach	70
Table 8 - VFM Commercial Approach	74
Table 9 - VFM Non-commercial Routes	78
Table 10 - FGMC2 Commercial Risks	81
Table 11 - FGMC2 Cost Profile (spend is indicative & subject to change)	88
Table 12 - Implementation role costings: insourced vs. outsourced delivery	90
Table 13 - FCDO FGMC Team	96
Table 14 - Risk Register	115

## Strategic Case
Overview
The aim of the Forest Governance, Markets and Climate (FGMC2) programme is to reduce the illegal and unsustainable use of forest resources, while benefitting poor, forest-dependent people, especially Indigenous People and Local Communities (IPLCs). It promotes sustainable growth in developing countries, supporting them to trade their way out of poverty by changing the way forest products are bought and sold across the globe, establishing forest stewardship to reverse forest and biodiversity decline.
The FGMC2 programme vision is that by 2035 there will be no major international outlets for illegal forest material and that regional and domestic trade in illegal forest products will be significantly reduced. Rights for local communities and Indigenous People will be clarified and respected, and sustainable multiple use forest management practises that incorporate carbon values will be operational in the productive forest areas across as many as 16 partner countries, representing over 360million ha of primary forests (roughly 40% of tropical forests).[1]
[1] Reflects the total area (millions of hectares) of primary forests an estimated 369m ha out 884m ha primary forests in 37 tropical countries, comprising Indonesia, PNG, Solomon Islands, Laos, DRC, Cameroon, Rep of Congo, Ghana, Liberia, Guyana and Gabon, Cote d’Ivoire, Thailand, Cambodia, Surinam, Bolivia (scoping is yet to begin in the latter).
To deliver this ambition, we are seeking Ministerial approval for the up to £500m, 10-year Business Case, with budget approval now for £220m over the next 5 years (2024-2029). We will revert to Ministers for approval of the remaining £280m in 2028/29 following an independent review of progress. The five-year £220m commitment has been designed as a first tranche of the envisaged ten-year programme, but will achieve results within the first five years, even if the subsequent funding is not approved.
This £500m Business Case was announced at the Climate Change Conference of the Parties (COP) in Glasgow (COP26). It will double the scope and funding that was available under a highly successful programme (FGMC1), which ran from 2011-2024 and secured A and A+ scores with significant transformational outcomes (see Box 1 below). This second phase (FGMC2) will support the UK’s efforts to restore leadership and engagement on climate and nature, forests in particular, and help strengthen governance and counter illegal practices that increase risks to forests. Annex A: summarises reviews of FGMC1.[2]
[2] FGMC1 was implemented in phases over 2011-2024 with a global budget of £280m allocated from the International Climate Finance (ICF). It started in late 2011 and ended in early 2024, with effectively 12 years operations.
The challenge for FGMC2 is to take forward this tried and tested approach and the established platforms into new countries and to address other threats to forests, including forest conversion, biodiversity loss, illegal mining, and the new incentives (and challenges) created by carbon markets.
FGMC2 is well placed to achieve this ambitious vision, based on its extensive experience and the positioning of the national and global community of practice (a large coalition of partners) which has been built during that period. FGMC’s unique approach is to:
- drive strong forest governance in producer tropical countries while promoting reforms in consumer markets that favour legally produced and sustainably managed forest commodities; and
- support national inclusive and deliberative processes that lead to resolution of sector conflicts that allow governments to put into law agreements and settlements that have been politically negotiated by representatives of stakeholders and which are therefore widely held to be socially legitimate.
FGMC1 experience demonstrates the importance of robust governance foundations if lasting change is to be secured. These foundations enable a fair and formal set of rules and system reforms that underpin the distribution of forest benefits. In particular, they must recognise the rights of IPLCs as well as the urgency of addressing the threats to climate, eco-system services and biodiversity from mismanagement of forests. They must be credibly enforced and overseen through independent monitoring, effective traceability systems, and transparent government and business processes that reduce the scope for corruption and elite capture.
The programme focus is on forest land stewardship - establishing governance arrangements and rules-based systems (outcomes) and the changed behaviour of key actors as a result of the implementation and enforcement of those rules (impact). The ultimate benefits to forest, environment and people are captured at the super-impact level. The economic appraisal finds that the proposed programme offers very strong value for money (vfm), with a Benefit Cost Ratio (BCR) in the central economic modelling scenario of 34:1 and significant net incremental benefits of £13.3bn compared to a scenario without the FGMC2 programme.
Box 1 FGMC Achievements:
FGMC has demonstrated that transformational shifts are possible across the entire timber sector through changes to laws, policies and social norms combined with systematic monitoring. The first decade of experience has resulted in a simple and replicable delivery approach that uses deliberative approaches to allow national stakeholders to navigate the complex and political nature of forest land use to address their own national challenges together, as a result owning the outcomes making them more robust to challenge.
An Independent Commission for Aid Impact (ICAI) review of ICF forest and biodiversity programmes singled FGMC out for praise as one of the most successful programmes in the [HMG] portfolio, regarding its impact and operating model noting its successful approach to delivering real change through patient and respectful partnership. ICAI said “it has been able to influence and shape demand for timber in major consumer markets in Europe and China, while supporting reforms in producer countries”.
The review found “significant, visible and widespread evidence of FGMC’s contribution to and influence on establishing new forest governance arrangements and market reforms at international, regional and national levels”. Some examples it quoted are described below.
Indonesia, the world’s largest producer of tropical timber has fully operationalised its “SVLK” system, developed with FGMC technical assistance (TA) support. This forest production and compliance monitoring system (known as SVLK) assures that all its forest product exports, including furniture and paper, now meet all legal requirements and illegal operators have been squeezed out. In 2011, by contrast, 80% of Indonesia’s exports were considered illegal, produced in violation of Indonesia’s own laws. In 2016, it became the first country to issue licences, which provide access to a “green lane” for its exports to UK and EU markets. Since then, timber exports to the UK and EU have increased by 19% to over USD 1.4 billion.
Indonesia credits the overall drop in its deforestation since 2016 (from 2.8% to 1.3%, and more particularly the reduction in loss of primary forests from 1.1% to just 0.3%) in part to the improved compliance monitoring of the SVLK supported by FGMC.
In Ghana, ICAI found FGMC demonstrated an excellent understanding of national and local forest governance contexts noting good progress on strengthening forest governance and legal compliance over the past decade. Ghana now has a fully functioning timber legality assurance system (TLAS). Public access to its wood tracking data, developed with FGMC TA support, has improved accountability; reduced operational costs; made it difficult to introduce illegal timber into supply chains; increased revenue capture; and provides greater certainty for business. Social contracts between communities and logging companies are now honoured, resulting in more community benefits and reduced conflict. For example, revenue collection increased by 240% from 2010 to 2019 despite a reduction in the volume of trade.
FGMC’s work has helped to influence major consumer markets in Europe, the USA and China. FGMC support for forest governance and trade reforms, were instrumental in shaping and putting into practice European policies and regulations to curb illegal logging and the timber trade. Information and evidence developed with FGMC support has resulted in prosecution of operators who imported illegal timber products into the EU and USA; and in China new regulation making it illegal to trade illegal timber products, and codes of practice and tracking systems that govern trade association member practices overseas.

The programme will be delivered through three interlinked components:
  1. Component I: Partnerships with tropical producer countries for national scale forest governance reforms (£136m/ 5 years; £305m/ 10 years). FGMC2 will provide support to establish national rules-based systems that ensure good forest land governance with a fair distribution of the costs and benefits (timber, agricultural commodities, mining, carbon, and biodiversity payments) arising from the ownership and management of forest lands and their assets and accruing directly to forest owners and managers or indirectly as public goods. It will build from established partnerships under FGMC1, to sustain on-going reforms or would focus on new governance challenges related to illegal agriculture and mining or forest carbon governance. It will also explore opportunities for new partnerships to take advantage of the replicable approach and significant demand. Budget provision would support engagement with as many as 16 countries. Precise geographical scope will be finalised during inception and mobilisation and will include Indonesia, Ghana, Liberia, Republic of Congo (RoC), Guyana, Cameroon, Papua New Guinea (PNG), Solomon Islands, Laos, and Democratic Republic of Congo (DRC). A further group of countries will be identified in the 2nd year of the programme following further scoping activity. Engagement will be phased, with a gradual increase in the number of new partnerships.
  2. Component II: Forest footprint alliances with consumer markets (£34m/ 5 years; £79m/ 10years). FGMC2 will support building of alliances for sustainable forest footprints to reduce the negative impacts on forests and poor people from risky investments and will promote responsible business practices in consumer countries. The focus of this component is generating the evidence and understanding to inform consumer market policies that support and incentivise the governance reforms of producer countries. The ambition is to close markets to trade in illegal and unsustainable forest products through effective import management regulations, public and private procurement policies, and by rewarding trade from countries with effective forest governance systems in place. This component will identify market “pull” from consumer countries and will likely include engagement with major processing and consumer hubs, notably the European Union (EU), China, India, Vietnam.
  3. Component III: Global forest governance. (£33m/ 5 years, £81m/ 10 years). This component will seek to shape international market norms and initiatives, support policy engagement that catalyses change in international markets and global forest governance, engage with political processes such as the climate and biodiversity COPs to galvanise international commitment and action, encourage positive international frameworks to prohibit trade in illegal material and incentivise national forest stewardship through rules that place governance at the heart of schemes/ investment strategies. Action will be supported through accountable grants which support non-government organisations who are working to sustain global forests through policy action (e.g. think tanks, advocacy groups, trade associations) who are encouraged to form coalitions to inform pertinent international policy and initiatives aligned to FGMC2 objectives. Examples of how accountable grantees have worked together to influence major policy decisions can be found in section 3 (see Box 4). Through the establishment of an International Forest Governance Hub (IFGH), independent advice will be available to developing countries, enabling FGMC partners to draw on their experience and encourage other countries in their efforts to strengthen forest governance, thereby amplifying FGMC2 outcomes and impacts. This will also create a mechanism that allows for pooling of donor resources further amplifying potential impact.
  4. Programme management (outsourced), policy engagement, monitoring, independent evaluation, learning and knowledge curation. (£17m/ 5 years, £37m/ 10 years)
The delivery strategy: the programme will use a similar format to the first phase, which demonstrated the right mix of agility and soft diplomacy to build strong trusting relationships and drive change. It will be delivered through a mix of facilitation and technical assistance (TA) contracts, accountable grants, and expertise. The commercial strategy will emphasise outsourcing of programme management where possible. Building on the proven model of FGMC1, the programme will be delivered through three service provider contracts (using existing frameworks where practical) and a limited number of memoranda of understanding (MOU) grant agreements with strategic international partners, some of which will enable us to work with other donors and engage directly in international policy initiatives. Coherence across the three components of the programme will be achieved through the coordination, monitoring and planning role envisaged for an outsourced programme management support team that is explained in the Management Case. This builds on the successful approach to delivery under FGMC1.
FCDO has sufficient experience and management capacity to deliver this programme. The FCDO’s Energy, Climate and Environment Directorate (ECED) co-hosts the joint FCDO-Department of Energy Security and Net Zero (DESNZ) International Forest Unit (IFU), providing a solid coordination mechanism to draw together cross-Whitehall policy expertise and Ministerial interests. Within the IFU, the FCDO’s five-person strong Forest Governance and Partnerships team will provide overall strategic policy direction, technical expertise and programme management oversight of FGMC2 (as they have done for FGMC1). Delivery will mainly be through outsourced management capacity. Policy engagement with programme partners will be further supported by an additional 7 programme-financed advisory/ expert roles (insourced) located at key posts. The team will coordinate with the FCDO’s embassy network to ensure joined-up delivery and diplomatic engagement to support wider UK objectives.
Strategic Case
2. Context and Rationale for Intervention
The International Panel on Climate Change’s (IPCC) 2019 Special Report on Climate and Land, and the Dasgupta Review (2021) on the economics of nature loss, highlight that the degradation of nature and biodiversity is taking place on a vast scale and at rapid pace, reducing the resilience of people and economies, as well as our ability to tackle and adapt to climate change. This poses a significant risk to the Sustainable Development Goals (SDGs), making them more difficult to achieve, and with disproportionately large impacts on poor people, in particular women and girls.[1]
[1] International development in a contested world: ending extreme poverty and tackling climate change: A White Paper on International Development November 2023
The IPCC Special Report on Climate and Land also highlights the critical role that forests, and sustainable land use must play in both climate mitigation and building resilience.[2] It underlines the interconnections between nature, biodiversity, land, food and people. Addressing these interconnected challenges requires transformations to the way we use and invest in forests and action at greater scale.
[2] IPCC, (2019) Climate Change and Land: an IPCC special report on climate change, desertification, land degradation, sustainable land management, food security, and greenhouse gas fluxes in terrestrial ecosystems [P.R. Shukla, J. Skea, E. Calvo Buendia, V. Masson-Delmotte, H.-O. Pörtner, D. C. Roberts, P. Zhai, R. Slade, S. Connors, R. van Diemen, M. Ferrat, E. Haughey, S. Luz, S. Neogi, M. Pathak, J. Petzold, J. Portugal Pereira, P. Vyas, E. Huntley, K. Kissick, M. Belkacemi, J. Malley, (eds.)]. In press.
Urgent action is needed to halt and reverse deforestation, and the UK could play a leading role in driving the international response. The importance of forests for tackling climate change was at the heart of the UK COP26 Presidency, and notably through the Glasgow Leaders’ Declaration on Forests and Land Use (GLD) endorsed by 146 countries and later reinforced in the UAE Consensus.[3] [4] UK climate finance for nature and forests are providing resources to deliver on these commitments. However, increased investment alone is unlikely to deliver lasting transformations to forest stewardship or the potential for growth without strong and inclusive forest governance established at national scale.
[3] https://www.gov.uk/government/publications/cop26-world-leaders-summit-on-action-on-forests-and-land-use-2-november-2021/world-leaders-summit-on-action-on-forests-and-land-use COP26 World Leader's Summit ,(2022) Action on Forests and Land Use
[4] https://unfccc.int/documents/636584 UNFCCC, (2023) Matters Relating to the Global Stocktake Under the Paris Agreement
Figure 1 - Forest governance foundations

Why tropical forests?
Tropical forests are critical to climate change mitigation and adaptation, delivering ecosystem services including water and heat regulation, providing livelihoods for local people, maintaining biodiversity, generating revenue and helping to secure many of the sustainable development goals. Forests are consistently undervalued for these services.
Forests are a vital carbon sink. Forests naturally remove carbon dioxide (CO2) from the atmosphere - roughly equivalent to a third of total fossil fuel emissions. Globally forests i.e. trees, absorb and remove twice as much CO2 from the atmosphere as they emit. However, as a result of deforestation, the forests in Asia are now net emitters, in Amazonia are neutral but tipping towards net emissions and the Congo basin remains a carbon sink. Reducing deforestation and restoring forests is critical to meeting climate goals.[5] [3] Forests have the potential of providing 23% of the cost-effective climate mitigation needed by 2030 to meet the 1.5oC target. [6][7] In addition, the biophysical attributes of tropical forests provide a local and global cooling effect, with global forest cover providing up to an additional 1 degree of cooling not accounted for by simply considering CO2 emissions.[8],[9]
[5] FAO (2022) State of the World’s Forests 2022
[3] Deforestation by itself is estimated to account for 4 Gt CO2 per year between 2011 and 2020 – 10% total anthropogenic GHGs.
[6] Austin https://www.nature.com/articles/s41467-020-19578-z
[7] Griscom, et al. (2017) “Natural Climate Solutions.” Proceedings of the National Academy of Sciences 114 (44): 11645–50.
[8] Lawrence D, Coe M, Walker W, Verchot L and Vandecar K (2022) The Unseen Effects of Deforestation: Biophysical Effects on Climate. Front. For. Glob. Change 5:756115. doi: 10.3389/ffgc.2022.756115
[9] https://www.wri.org/insights/how-forests-affect-climate Seymour F, (2022) Wolosin M and Gray E, Policies Underestimate Forests' Full Effect on the Climate
Forests provide the ecosystem services that sustain life and underpin economic activity. More than three-quarters of the world’s accessible fresh water originates from forested catchments.[10] Deforestation effects global and local climate patterns. Major tropical forests like those in the Congo and Amazon Basins support regional atmospheric water cycles affecting rainfall regionally as well as in distant regions including in the Sahel, Ethiopian Highlands, US, India and China.[11],[12],[13],[14],[15],[16] In Africa, millions of farmers reliant on rainfed agriculture will be impacted by changes in rainfall patterns that will arise from fragmentation and drying of the Congo basin forests. [17],[18]
[10] Millennium Ecosystem Assessment (2005). Millennium Ecosystem Assessment, 2005. Ecosystems and Human Well-being: Biodiversity Synthesis. World Resources Institute, Washington, DC.
[11] Pearce, Fred (2018) Deforestation Is Affecting Global Water Cycles. YaleEnvironment360 (https://e360.yale.edu/features/how-deforestation-affecting-global-water-cycles-climate-change)
[12] Lawrence, D et al . (2015). Effects of tropical deforestation on climate and agriculture. 2015. Nature Climate Change. 5(2):27-36
[13] Gong,C. Eltahir, E. Sources of Moisture for Rainfall in West Africa, Water Resources Research, Vol 32, No 10, October 1986 pp 3115-3121
[14] ) Ellison, D. (2018) Background Analytical Study on Forests and Water Prepared for the UNFF13.
[15] Vergara, W. and Scholz, S. (2011) Assessment of the Risk of Amazon Dieback. World Bank
[16] Barimalala, R. et al (2023) Effects of the Congo Basin Rainforest on Rainfall Patterns, Norwegian Research Centre NORCE.
[17] https://eur02.safelinks.protection.outlook.com/?url=https%3A%2F%2Fwww.tropenbos.org%2Fresources%2Fpublications%2Fimportance%2Bof%2Bcentral%2Bafrica%25E2%2580%2599s%2Bforests%2Bfor%2Bregional%2Bclimate%2Band%2Brainfall&amp;data=04%7C01%7Cg-allison%40dfid.
[18] https://www.wri.org/insights/congo-basin-deforestation-threatens-food-and-water-supplies-throughout-africa Bergen M, (2019) Congo Basin Deforestation Threatens Food and Water Supplies Throughout Africa
Forests are critically important for global biodiversity. Tropical forests typically have many hundreds of tree species in a single hectare (compared to temperate forests where half a dozen species account for 90% of tree species) and provide habitat for half or more of the world’s known terrestrial plant and animal species. [19],[20] Yet across the highly biodiverse tropics, 32m hectares of primary or recovering forest were lost between 2010 and 2015. [21]
[19] Biodiversity in rainforests (mongabay.com) , Butler R A, (2019) Why Are Rainforests So Diverse?
[20] IPBES (2019): Global assessment report on biodiversity and ecosystem services of the Intergovernmental Science-Policy Platform on Biodiversity and Ecosystem Services. E. S. Brondizio, J. Settele, S. Díaz, and H. T. Ngo (editors). IPBES secretariat, Bonn, Germany. 1148 pages. https://doi.org/10.5281/zenodo.3831673
[21] Ibid
Forests underpin the livelihoods, welfare and culture of over one billion people, many of them poor, who directly rely on forests for their livelihoods.[22] Twenty to thirty percent of family income and subsistence across Asia, Africa and Latin America result from the food, fodder, fuel, fibre, medicines, resins, dyes, green manure collected from forests.[23] Around one third of jobs in developing countries are directly dependent on biodiversity and ecosystem services.[24] 70% of world’s poor depend on nature for livelihoods.[25] Forests and trees outside forests (including trees in agroforestry systems, on farms and in rural landscapes) are important for the four recognised dimensions of food security: availability, access, utilization and stability.[26],[27].[28]
[22] Newton P., Agrawal A., et al. (2020). The number and spatial distribution of forest-proximate people globally. ScienceDirect/One Earth.
[23] World Bank. World Development Report 2000/2001: attacking poverty. 2001.
[24] See: UNDP/UNEP, 2018
[25] FAO, ILO, UNECE(2023) Occupational Safety and Health in the Future of Forestry Work.
[26] Vinceti, B., Eyzaguirre, P. and Johns, T. (2008). The nutritional role of forest plant foods for rural communities. pp 63-96 in: Colfer, C.J.P. (ed.) Human health and forests: a global overview of issues, practice and policy. Earthscan, London.
[27] Fa, J.E., Currie, D., Meeuwig, J. (2003). Bushmeat and food security in the Congo Basin: linkages between wildlife and people’s future. Environmental Conservation 30(1): 71–78.
[28] https://www.mdpi.com/1999-4907/11/10/1098#:~:text=Secondary%20forests%20and%20single%2Dspecies,food%20and%20other%20important%20products.
Forests are integral to the identity, way of life and livelihoods of approximately 70 million people, many indigenous, living in remote and intact tropical forests and for whom there are limited alternative sources of livelihood. They, and hundreds of millions more rural people living around forest and on farm forest frontiers, manage trees and land under customary systems of tenure. Women in these groups are disproportionately affected by the loss of forests. Indigenous communities make up about one third of the world’s 900 million extremely poor rural people. [29],[30] Indigenous Peoples are amongst the most vulnerable to the effects of climate change due to their dependence on forest resources; climate change also exacerbates political and economic marginalization, loss of land and resources, human rights violations, discrimination, and unemployment.[31]
[29] People and the planet together: Why Indigenous Peoples and local communities are at the heart of climate action (worldbank.org)
[30] Economic and Social Development | United Nations For Indigenous Peoples
[31] Blackman et al. (2017); Ceddia, M.et al., (2015) Land tenure and agricultural expansion in Latin America: The role of Indigenous Peoples’ and local communities’ forest rights. Global Environmental Change, 35:316-322.; Etchart, L. (2017) The role of indigenous peoples in combating climate change. Palgrave Communications, 3, 1–3.; Macqueen et al., (2018) Innovations towards prosperity emerging in locally controlled forest business models and prospects for scaling up. World Development; Pokorny et al., (2016) Drivers of Illegal and Destructive Forest Use. IUFRO World Series 35; Vasco, C., B. Torres, P. Pacheco, & V. Griess. The socioeconomic determinants of legal and illegal smallholder logging: Evidence from the Ecuadorian Amazon. Forest Policy and Economics 78: 133-140.
Forests create resilient environments for a much larger number of people, for example, those living downstream from forests rely on the ecosystem goods and services they provide to maintain water supplies, stop flooding and protect soils. [32] Increasing evidence underlines the value of forests and trees for enhancing resilience of communities, animals and infrastructure to natural disasters, and for promoting climate adaptation by reducing temperatures during heat waves, [33] and moderating or preventing flooding and landslides.[34]
[32] Lawrence, D et al . (2015). Effects of tropical deforestation on climate and agriculture. 2015. Nature Climate Change. 5(2):27-36
[33] Gill, SE, et al. (2007).Adapting Cities for Climate Change: the Role of Green Infrastructure. Climate Change and Cities: 33 (1) pp 115-133
[34] Broadmeadow, S. (2023) Revised Valuation of Flood Regulation Services of Existing Forest Cover to Inform Natural Capital Accounting. Forest Research UK.
Forests generate revenue for development and services. Governments collect rent in the form of royalties from logging that contribute to local and national development, more effective controls yield increased revenue. Illegal deforestation and corruption allow consumers, traders and political elites to benefit at the expense of national and local community revenue.[35]
[35] https://thedocs.worldbank.org/en/doc/482771571323560234-0120022019/original/WBGReport1017Digital.pdf World Bank Group, (2019) Illegal Logging, Fishing, and Wildlife Trade: The Costs and How to Combat It
Whilst forests are an important part of the solution to combatting climate change, they are themselves under threat from climate change. The IPCC 6th Assessment Report projects climate change would have impacts on the structure and diversity of tropical forests, on their carbon stocks, and water availability all exacerbated by deforestation, with increased likelihood of fires. There has been an increase in fire incidents in many forested regions in recent years, with serious impacts on health, transport and regional economies, and there is strong evidence that climate change is an important factor in the increase, and severity and extent of recent large-scale fire incidents. The implications of these changes for sustainable forest management are not yet well understood.
What are the threats to tropical forests and the benefits they provide?
Growing and changing global demand
A growing and wealthier global population is placing increasing and competing demands on tropical forest lands for food, fibre, fuel, and minerals as well as for global public goods like climate regulation.
Growing economies in Africa, South America and Asia together with increasing urbanisation, particularly in Asia has resulted in increased demand for forest products and bioenergy.[36] With population growth and urbanisation, the demand for energy has increased and is being met from charcoal or biofuels such as palm oil. With the policy shifts towards greener energy, demand for non-fossil fuels will place new pressures on forests, as will land clearance for mining rare earth minerals which are needed for green technologies such as photovoltaics, battery storage and electric vehicles.
[36] Dasgupta P (2021) The Economics of Biodiversity: The Dasgupta Review
Around 75% of tropical deforestation is driven by demands for a few commodities, including: wood products, palm oil, beef, cocoa, and minerals (e.g. gold, nickel). Forest Trends estimated that 49% of tropical deforestation between 2000 - 2012 was due to illegal deforestation for commercial agriculture (albeit with a wide range of uncertainty 36% to 65%). Half of what is grown after illegal deforestation is consumed domestically, but the rest is exported. This equates to almost 21 million hectares of illegally cleared tropical forest between 2000 - 2012. More recent studies estimate that about a third of all tropical deforestation-related emissions were driven by international agriculture commodity trade; with much higher proportions (70-90%) sourced from illegal forest clearance.[37] See Annex N for a summary of evidence related to illegal deforestation. It suggests that international demand for forest risk commodities, including from the UK, significantly drives the production of commodities that are not compliant with laws and requirements in source countries. For more details on deforestation trends see Annex G: Economic Analysis.
[37] https://www.forest-trends.org/wp-content/uploads/2018/06/Info-Brief-Costs-of-Illegal-Agro-Conversion_Final.pdf
While the UK and other developed consumer markets are beginning to act on the impact of their imports, emerging consumer markets are now some of the biggest drivers of tropical deforestation. In particular, China is the most important global trader and investor in timber and increasingly in forest risk commodities. While imports of tropical timber to China have increased over the past decade, encouragingly, China’s preference for “low risk” sources is increasing, perhaps reflecting concerns over illegal deforestation. Recently other Asian markets, such as Vietnam are emerging as global processing hubs with their demand increasingly driving illegal deforestation in tropical forest countries.
The trade in forest and other commodities contribute significantly to economic development in many tropical forest countries. Annex I presents information and evidence on market trends for forest and forest risk commodities sourced from FGMC country partners. [38] It clearly illustrates the significance of these consumer markets, for tropical countries, and notably the growing significance of Asian markets by comparison to EU/ UK’s market “pull”. As illustrated in Figure 2. This analysis highlights the importance of engaging through new alliances with these consumer markets in order to ensure that their trade and investment does not undermine the governance reforms and rule of law in developing (tropical) countries.
[38] UK Environment Act defines Forest Risk Commodity as a commodity produced from a plant, animal, or other living organism and where its production may result/has resulted from the conversion of forest to agricultural use.

Figure 2 - Focus countries' wood product trade with China and the EU

Mining represents the fourth largest driver of forest-loss: nearly one third of the world’s forests may already be affected by mining. A World Bank report estimates that 10% of all forests are potentially influenced by large scale mining projects – rising to one third, if mines in development and those currently non-operational are considered.[39] Nearly 10% of the deforestation in the Brazilian Amazon between 2005 and 2015 has been found to be due to mining activities.[40] More than half of global mining areas (56%) visible from satellite images are undocumented.[41] As highlighted in Annex J: forest mining poses particular risk for forests in Indonesia, Brazil, Ghana and Suriname.
[39] World Bank, (2019) Forest-Smart Mining: Large-Scale Mining on Forests (LSM) (https://www.profor.info/sites/profor.info/files/Forest%20Smart%20Mining_LSM%20REPORT_0.pdf)
[40] Sonter, Laura J., Diego Herrera, et. al. (2017) Mining drives extensive deforestation in the Brazilian Amazon. Nature Communications, 8 (1) (https://DOI.org/10.1038/s41467-017-00557-w)
[41] Impacts for half of the world’s mining areas are undocumented (nature.com) Maus V and Werner T T, (2024) Impacts for Half of The World's Minig Areas Are Undocumented (2024)
Governance and Market failures that drive forest loss and degradation
Market and governance failures that result in deforestation and unsustainable forest land uses are deeply entrenched. Market failures relate to the incentives for illegal and unsustainable forest material to be produced, and the level of consumer demand.[42], [43]. Governance failures relate to the absence of nationally accepted or enforced rules.
[42] Intergovernmental Science-Policy Platform on Biodiversity and Ecosystem Services (IPBES) (2019): Summary for policymakers of the global assessment report on biodiversity and ecosystem services of the Intergovernmental Science-Policy Platform on Biodiversity and Ecosystem Services. IPBES secretariat, Bonn, Germany. 56 pages. (https://ipbes.net/sites/default/files/2020-02/ipbes_global_assessment_report_summary_for_policymakers_en.pdf)
[43] Pearce, DW, and Brown, K. (1994), “The Causes of Tropical Deforestation”, UCL Press, London, UK.
Governance Failures
In many tropical forest countries, rules-based systems exist on paper but are not operational. Rights are not recognised, are not effective or not enforced.  In particular, the rights of Indigenous People may not be adequately captured in legislation and even where rights are recognised, entitlement to benefit from them may not be realised in practice. The absence of legal clarity together with the absence of traceability and monitoring systems leads to ineffective management and enforcement and sometimes conflict. [44]
[44] Pauli, Natasha (2010) Tropical Forest Governance in the 21st Century (https://www.oxfordmartin.ox.ac.uk/downloads/briefings/200912-ForestGovernance.pdf).
Rights: Uncertainty regarding forest tenure rights, produces a market failure through the misallocation of forest rents (income generated through forest-related activities) which serves both to increase inequality and reduce efficiency. Unfairly allocated, poorly defined and enforced property rights are commonplace in many forest-rich areas. This is particularly true in fragile states where 15% of the world's forests are located. Limited incentives to protect forests and weak governance are compounded by conflicting legal and customary provisions relating to tenure, rights, access and forest land use. [45],[46],[47],[48] There is a large body of evidence indicating a positive relationship between tenure security and increasing revenues to local people (e.g. from timber harvests).[49] However, in many locations, user rights are insecure, and governments lack the capacity to clarify ownership.
[45] de Koning, R., Capistrano D., Yasmi Y., and Cerutti, P. (2008). Forest-Related Conflict: Impacts, Links and Measures to Mitigate. CIFOR, RECOFTC, Rights and Resources Initiative.
[46] Rights and Resources Initiative (2012). Respecting Rights, delivering development: Forest tenure reform since Rio 1992. Rights and Resources Initiative, Washington DC, USA. & Rights and Resources Initiative (2012). WHAT RIGHTS? A Comparative Analysis of Developing Countries’ National Legislation on Community and Indigenous Peoples’ Forest Tenure Rights. Rights and Resources Initiative, Washington DC, USA.
[47] Rights and Resources Initiative (2012). Strengthening Governance for Forests, Development and Climate Change. Seminar presentation given at the UK Department for International Development (UK), London, UK.
[48] Forests cover approximately 30% of the global land surface area. Large tracts of the global forest area are claimed by developing country governments. In 2012 governments claimed ownership of 98% of forest land in Africa, 68% in Asia and 36% in Latin America. An estimated 52% of the global land surface area is also held or used according to customary tenure.
[49] Sunderlin, W., Hatcher, J. and Liddle, M. 2008. From exclusion to ownership? Challenges and opportunities in advancing forest tenure reform. Rights and Resources Initiative, Washington, D.C.
Conflict is often associated with access to forests either as a source of wealth, or as a means to maintain conflict. Contested forest rights between different interests (IPLCs, concessionaires, and governments) leads to the illegal use of forests and land and an unfair distribution, with powerful interests capturing most of the benefits. Competing claims over forests where forest rights and land tenure are unclear, cause conflict and increase deforestation and can lead to involuntary dispossession of forest-dependent communities from their lands. [50],[51] In tropical forest regions conflicts between Environmental Defenders, often IPLC, and various industries like logging, mining and agribusiness have increased at an alarming rate. The majority of defenders targeted were working to defend their forests from deforestation. Forest resource-related conflicts appear to be increasing and are a major economic drain on developing countries. The cumulative costs of social conflict are significant, normally undervalued and can pose a serious risk to investment return as well as global forest goals.
[50] De Man, Reinier (2012) Agricultural Commodities that Respect Land Rights and Food Security: How to Include Land Governance Issues in Sustainable Commodity Standards? Paper prepared for Presentation at the “Annual World Bank Conference on Land and Poverty”. April 23-26, 2012 (https://rdeman.nl/oldsite/download/2012-04_World_Bank_paper_RdM.pdf)
[51] The Munden Project. 2013. Global Capital, Local Concessions: A Data-Driven Examination of Land Tenure Risk and Industrial Concessions in Emerging Market Economies.
Corruption: The acquisition of forest for logging concessions and commercial agriculture, without a well-regulated and coherent institutional framework for land use, opens opportunities for corruption. Nearly half the world's forests are in countries perceived to suffer “rampant” corruption.[52] Corruption may include large payments from timber or agricultural companies to members of the military, politicians, and officials for forest concessions or approvals for timber processing or forest clearance or avoided payments of resource fees and taxes [53]. Similar concerns are likely to arise with respect to carbon payments.
[52] Irland, Lloyd C. (2008). State Failure, Corruption, and Warfare: Challenges for Forest Policy. Journal of Sustainable Forestry, 27 (3) pp 189-223 (https://doi.org/10.1080/10549810802219963)
[53] World Bank (1999) “Corrupt and Illegal Activities in the Forest Sector”, World Bank, Washington DC
Illegal logging and illegal forest clearance: A large organised transnational trade in illegal timber and illegal wildlife is linked to tropical forest destruction, loss of revenue and environmental harms. 2 Forest Trends estimated that illegal deforestation generates economic losses in tropical countries of more than $17 billion per year.[54] Since illegally produced commodities are generally cheaper, their presence on the market can depress prices (it is estimated they depress timber prices by about 7-16% and result in annual losses of £8 billion for legitimate business) The intergovernmental Financial Action Task Force (FATF) classifies these as “environmental crimes” noting that the UK is a source, transit and destination country. Annex N presents a summary of evidence on the nature, scale and impacts of illegal logging and illegal deforestation, reflecting on the challenges of drawing together such evidence and making direct links between the demand for forest risk commodities in specific countries and illegal deforestation.
[54] https://www.forest-trends.org/wp-content/uploads/2018/06/Info-Brief-Costs-of-Illegal-Agro-Conversion_Final.pdf
Decision making and voice: Forests are predominantly managed by indigenous people and local communities – An estimated 1.6 billion people – more than 25% of the world’s population – live in and use forest and land resources for their livelihoods, with an estimated 36% of intact forests within Indigenous Peoples’ lands. [55],[56],[57] IPLCs are stewards of 80% of the world’s remaining biodiversity [58],[59],[60] and yet are frequently excluded from policy decision making.
[55] Forests and poverty reduction (fao.org)
[56] Importance of Indigenous Peoples’ lands for the conservation of Intact Forest Landscapes - Fa - 2020 - Frontiers in Ecology and the Environment - Wiley Online Library;
[57] By the Numbers: Indigenous and Community Land Rights | World Resources Institute (wri.org)
[58] The role of Indigenous Peoples in Biodiversity Conservation: World Bank Document
[59] The Economics of Biodiversity Dasgupta Review 2021
[60] Schuster et al. (2019). Vertebrate biodiversity on indigenous-managed lands in Australia, Brazil, and Canada equals that in protected areas. Environmental Science and Policy 101: 1-6. See also IPBES (2019). Global Assessment Report on Biodiversity and Ecosystem Services
Girls and women in forest-dependent communities are frequently excluded from property rights, rarely own land, or have secure access to forest resources whilst being disproportionately dependent on forests for their livelihoods.[61] They are also often underrepresented in policy.[62] Men and women use forests in different ways, benefit from different parts of the supply chain, have distinct roles in managing forests, and differentiated needs and perspectives. However, women and youth are often unrecognised by formal rules pertaining to forests and in trade discussions. [63] [64] [65]
[61] https://www.ilo.org/ipec/areas/Agriculture/WCMS_172421/lang--en/index.htm
[62] Sellers, S. (2016). Gender and Climate Change: A Closer Look at Existing Evidence. Global Gender and Climate Alliance (GGCA), p6
[63] Rights and Resources Initiative. 2017. Power and Potential. A Comparative Analysis of National Laws and Regulations Concerning Women’s Rights to Community Forests. https://rightsandresources.org/wp-content/uploads/2017/05/Power_and_Potential_Final_EN_May_2017_RRI-1.pdf
[64] Colfer, C. et al. 2016. Gender and Forests.Routledge/Earthscan/CIFOR. https://www.cifor.org/publications/pdf_files/Books/BColfer1701.pdf
[65] https://www.u4.no/publications/gender-forestry-and-corruption-promoting-a-gender-sensitive-approach-to-addressing-corruption-in-the-forestry-sector
Forest Management & enforcement capacity: Many countries have adequate policies and regulations on paper to inform forest management and balance multiple uses including environmental and social safeguards. However, these are commonly not enforced and may be inconsistent with policies and regulations of other sectors. Weak governance also prevails where there is limited accountability, transparency or monitoring and may reflect limited capacity for enforcement. For FGMC, improving access to evidence, information and independent monitoring have proved critical in strategies to address governance challenges and in enabling markets to understand their supply chains in tune with FCDO best buys.[66]
[66] 2020-05 Best buys in governance.pdf
Market failures
Market failure occurs when the allocation of goods and services is not efficient from a social point of view and not reflected in the market price. Forest clearance by individuals incur costs to society through negative externalities, such as through degrading ecosystems, contaminating water or emitting air pollution. [67],[68] The costs of eroding natural capital are borne by wider society rather than by those deforesting land, whilst the economic benefits flow directly to producers. This leads to over-supply of goods with negative externalities, and prices consumers pay for commodities do not reflect the environmental degradation attached to them. This exacerbates the market failures as incentives to degrade land through illegal timber harvesting, especially in countries with weak governance, outweigh incentives to preserve or restore forests.[69]
[67] intergovernmental science policy platform on biodiversity and ecosystem services (2019): summary for policy makers of the global assessment report on biodiversity and ecosystem services of the intergovernmental science policy platform I'm biodiversity and ecosystem services IPBES
[68] Pierce, DW, and Brown, K (1994) the causes of tropical deforestation, UCL press London UK
[69] Roots of Prosperity: the economics and finance of restoring land, WRI. (roots-of-prosperity_0.pdf (wri.org))
Information asymmetries mean consumers may not be able to distinguish between commodities that have been legally or more sustainably produced, giving a competitive advantage to goods that are illegally and/or unsustainably produced as their costs of production are lower, resulting in higher demand than the social optimum. [70]
[70] https://www.gov.uk/government/publications/final-report-the-economics-of-biodiversity-the-dasgupta-review
In response, most major consumer markets have introduced legislation to exclude illegal and unsustainable forest-based commodities, as regulation can be necessary to address these sources of market failure. However, despite significant shifts in their trade the large Asian processor / consumer countries (China, India and Vietnam), still do not have operational import controls in place.
The ecosystem services (ESS) and carbon sequestration provided by forests have public good characteristics, as they are non-excludable and non-rivalrous. This leads them to be undervalued and under protected by the market. As set out in the Dasgupta Review, there is a gap between the prices we pay for nature’s goods and services and their social values (accounting prices).
The failure to value and include carbon and ESS in forest management incentivises alternative uses for forest land. Recent Climate and Biodiversity COPs have increased interest in carbon and ESS as revenue streams. Carbon markets, biodiversity credits and payments for ecosystem services establish more holistic monetised values for forests and could ‘internalise’ these externalities. Arrangements are now being established by governments and international bodies for payments for these services, but these are complex and often poorly understood by local stakeholders[71],[72],[73].  Decisions on rules covering these benefits are now being contested and lack the multi-stakeholder deliberative processes needed to reach understanding and consensus.
[71] RRI Technical paper (2021) - Status of Legal Recognition of Indigenous Peoples’, Local Communities’ and Afro-descendant Peoples’ Rights to Carbon Stored in Tropical Lands and Forests https://rightsandresources.org/wp-content/uploads/CarbonRightsReport_v10.pdf
[72] Blum,Marieke (2020)Whose climate? Whose forest? Power struggles in a contested carbon forestry project in Uganda Forest Policy and Economics Volume 115, June 2020, 102137 https://www.sciencedirect.com/science/article/pii/S138993411930382X
[73] Pan, C., Shrestha, A., Innes, J.L. et al. Key challenges and approaches to addressing barriers in forest carbon offset projects. J. For. Res. 33, 1109–1122 (2022). https://doi.org/10.1007/s11676-022-01488-z )
Green finance, namely public and private finance aligned with the objectives of climate change mitigation and reversing biodiversity loss, has increased over the past decade from a low base of $5.2bn in 2012 to $540.6bn in 2021. [74] However, little has been directed at forest conservation, sustainable land use or community forest enterprises due to concerns around governance of the sector and consequent risk of misuse of funds. [75] [76]
[74] Climate Focus. 2019. Updated assessment of New York Forest declaration Goal 8. Public support for the development and implementation of strategies to reduce forest emissions and private investment targeted at reducing forest emissions from domestic and international finance International finance. https://forestdeclaration.org/images/uploads/resource/2019NYDFGoal8.pdf
[75] Climate Focus. 2019. Updated assessment of New York Forest declaration Goal 8. Public support for the development and implementation of strategies to reduce forest emissions and private investment targeted at reducing forest emissions from domestic and international finance. https://forestdeclaration.org/images/uploads/resource/2019NYDFGoal8.pdf
[76] Thales A. P. et. al (2023) Action needed to make carbon offsets from forest conservation work for climate change mitigation
Forests are often regarded as an open access resource which incentivises over-consumption and marginalises users with customary claims. Importantly, uncertain property rights means people do not invest in the land due to fear that any capital invested risks being lost.  Overlapping and multiple claims over forests lead to coordination failures which increase deforestation and can cause delays and additional costs for investment projects, thereby discouraging investment.[77],[78]
[77] Notess, L. et al. (2018.) The Scramble for Land Rights. Reducing Inequity between Communities and Company. WRI/CIFOR/AsM
[78] Bebbington, A. et al. 2018. Resource extraction and infrastructure threaten forest cover and community rights. PNAS December 26, 2018 115 (52)
Weak Global Forest Governance. Global policy frameworks, norms and processes relating to forests and their ecosystem services are distributed across different international processes related to the environment, climate, sustainable development and trade. This creates an ambivalent global policy environment. Further, the lack of a consistent and coherent global framework does not contribute to the sense of urgency required to encourage countries to reform forest governance and promote legal and sustainable trade.
What are the consequences of ineffective forest governance?
The consequences of forests being badly governed, with markets taking minimal account of the environmental services of forests or the legitimate origin of forest products; of rights not respected and of rules not enforced, are serious and experienced locally, nationally, and globally.
  1. Locally: poor forest sector governance leads to increased forest degradation and loss, increased corruption and conflict and diminished resources for livelihoods.
  2. Nationally: environment and climate harms, revenue for development is lost, forest investments are not forthcoming and projected returns not realised and the rule of law undermined. Ecosystem services are lost to local communities, including cooling effects and water regulation.
  3. Globally: habitats are lost forever, forests move from carbon sinks to sources, regional rain and weather patterns shift, international markets for legitimately produced goods are undermined.[79]
    [79] https://www.wri.org/insights/how-forests-affect-climate Seymour F, Wolosin M and Gray E (2022) Policies Underestimate Forests' Full Effect on the Climate
Over the past decade while efforts to reduce illegal logging are working, the causes of deforestation have grown with forests threatened by rising demand not just for timber but for agriculture commodities and minerals. The next decade will be key for implementing new international rules and norms to comprehensively help reverse forest and biodiversity loss.
3. What action has been taken to address these challenges?
For more than ten years FGMC has been a high performing programme (scoring A and A+ in annual reviews). See Annexes A and D for an overview of evidence. The Independent Commission for Aid Impact (ICAI) review of the International Climate Finance (ICF) Forests and Nature portfolio (2021) singled FGMC out for praise regarding its impact and operating model, noting “FGMC offers a strong example of how to approach commodity-related deforestation and is one of the most successful programmes in the [HMG] portfolio, with lessons to offer other programmes in the sector, not least the value of sustained long-term relationship building and investment..[80]
[80] ICAI 2021International Climate Finance: UK aid for halting deforestation and preventing irreversible biodiversity loss, pp21,25
In the early 2000s, under pressure to ban tropical forest products over concerns about the Amazon rainforests, the UK forged agreement at the G8, UN, and at political summits in Asia and Africa to tackle illegality in the forest sector. This agenda became known as Forest Law Enforcement Governance and Trade (FLEGT). It called for coordinated measures from the demand and supply perspective to transform business practices and tackle entrenched forest governance challenges. The UK led the development of a comprehensive EU plan that combined development cooperation and consumer market regulations, known as the FLEGT Action plan to assist developing countries to improve forest governance.[81]
[81] https://eur-lex.europa.eu/legal-content/EN/TXT/?uri=CELEX:52003DC0251 Communication from the Commission to the Council and the European Parliament - Forest Law Enforcement, Governance and Trade (FLEGT) - Proposal for an EU Action Plan
The UK, informed by FGMC1 and an earlier DFID programme, shaped the key pillars of that policy, namely the FLEGT Voluntary Partnership Agreements (VPA), between timber producer countries and the EU (and now the UK) that frame both governance and market reforms and link these to UK market access. The VPAs aim to eliminate illegal forest products from trade with the EU and UK. VPAs comprise two essential elements: (i) a national system in producer countries that assures compliance with their legal requirements (known as Timber Legality Assurance System (TLAS)) and (ii) an EU (now UK) regulation that checks imports from VPA countries to ensure they accord with their TLAS. This reinforces national systems of control and provides a “green lane” for businesses importing to the UK in meeting their due diligence obligations. FGMC1 support has established, as international best practice, facilitated multi-stakeholder policy deliberation[4]. FGMC1 enabled national stakeholders to shape the VPA and supported the implementation of forest governance reforms that are enshrined within them.[5] The VPA have provided the framework through which FGMC supports facilitated deliberations on policy and law and coordinated donor action to support the necessary institutional capacity building to apply and enforce the reformed governance arrangements.
[4] Deliberation is defined as a formal, informed, and inclusive process of reaching collective decisions, made in the common interest, resulting in agreements or settlements that are subsequently defined in law, other rules or norms and framed in systems that check to see that they are implemented or enforced.
[5] The UK is committed to future VPA where countries have established credible national verification systems. The first such agreement is with Indonesia https://www.gov.uk/government/publications/cs-indonesia-no12019-ukindonesia-voluntary-partnership-agreement-on-forest-law-enforcement-governance-and-trade-in-timber-products FGMC2 will support VPA countries in strengthening their national systems that serve the VPA intent.
FGMC1 was crafted back in 2011 to support UK action under its FLEGT policies. At that time ideas on using trade as leverage to stop illegal logging had been agreed at political level, but there was limited understanding of how to do it in practice. Most development partners continued their existing bilateral projects but included into them support for forest governance reform. DFID (as was) took a bold decision to fund FGMC - a different kind of programme, signalling a 10-year commitment that recognised the challenges of tackling governance failures and coupling this to reforms in global markets. It was designed to work at both international and national levels, and with a diversity of actors – often at loggerheads – to change the attitudes and practices of governments and business as well as non-government organisations (NGOs) in both producer countries and consumer markets and putting concerned local people at the heart of policy decision-making.
As a policy and governance programme, FGMC1 was designed to achieve results through ‘influencing’ policies and supporting institutional development to put policy into practice, rather than investing directly in forests. Approaches to influencing pervade all aspects of the programme. Therefore, programme results reflect transformational shifts in markets and sector governance, in improved understanding of businesses and regulators and through FGMC-backed initiatives that work with and inform international policy processes and thus the key metric for ICF reporting has been KPI15 on transformational change. Compared to 2011 there have been significant shifts, today:
- market regulation to shut out illegal material has become the norm in the majority of OECD[6] countries (as indicated in Figure 4);
  [6] Organisation for Economic Cooperation and Development
- traceability and certification of timber supply chains to demonstrate compliance with requirements in source countries is the accepted business practice across most major markets, as reflected in the purchasing policies and guidance of the UK, EU, USA, China trade associations. National scale traceability and certification (like Indonesia’s SVLK) is being developed by many countries (much of tropical SE Asia and Central and West Africa)[82];
  [82] In Liberia, C Ivoire, Ghana, Cameroon, Gabon, Rep of Congo, C.Africa Republic, Malaysia, Vietnam, Thailand, Laos, Colombia, Guyana, Honduras, PNG
Civil society organisation (CSO)-led independent forest monitoring (IFM) is now well established as a means to assure markets and demonstrate accountability, for example, across the Congo Basin, IFM reports are linked to WRI’s Open Timber Portal that provides international buyers with information on sourcing legal timber.
These changes have been made possible through FGMC’s combination of approaches. First, evidence generated by research and advocacy groups has publicised problems and stimulated action in both importing and producing countries in tightening implementation of their regulations. New regulations in consumer countries (such as the UK Timber Regulations) have been important incentives for reform in producer countries. Second, research on trade and drivers of deforestation, and provision of legal advice has helped underpin regulatory reform that is aligned with national and international rules. Third, facilitation helped build trust between national stakeholders who were traditionally antagonistic and helped them to cooperate in finding their own solutions (rather than external projects developing them). Fourth, CSO capacity to monitor the sector has been strengthened and acceptance of their findings by government has made it more likely that authorities would take action to address non-compliance. Fifth, FGMC has built a global community of practice, that includes governments, trade bodies, research organisations and CSO networks committed to sustaining forests and the people who depend on them.
FGMC1’s vibrant community of practice works to sustain forest governance and international market reforms. TA support to producer governments was complemented by accountable grants with a variety of organisations: (i) international NGOs who supported national CSO networks; (ii) advocacy groups that exposed bad practice; (iii) trade associations that supported members in adapting to change; and (iv) think tanks who convened, developed new tools to inform government and business decision making; (v) research bodies that analysed forest and market trends and impacts. Chatham House has helped build coalitions through policy research, convening of experts, advocates and officials over 12 years to exchange information and build relationships, which have underpinned the FGMC community of practice[83]. Annex K describes the accountable grants programme and some of the results achieved under FGMC1.
Figure 3 - FGMC Community of Practice
[83] https://forestgovernance.chathamhouse.org/publications Chatham House retains an archive of research and meetings convened over the past 12 years as well as an archive ed newsfeed.
Cooperation amongst FGMC’s community of practice, and pressure through advocacy and evidence has helped shift global understanding and driven transformational shifts. Box 4 below provides a powerful example of how FGMC accountable grants, members of the FGMC community of practice, were over many years able to bring evidence, voices from tropical forest countries, advocacy and exposés together in a coalition that lobbied consumer market countries to address their forest footprints.
FGMC’s support for national processes has resulted in legislative reform, negotiated through multistakeholder deliberations involving national CSOs, business organisations and government, and informed by evidence generated by FGMC partners, to address incoherence and loopholes (see Box 2). These reforms now frame the backbone of national systems that demonstrate that their wood products have been legally produced. The systems include checks to verify compliance, supply chain traceability and, importantly, independent audits to provide assurance that the systems are being implemented and delivering what they intend.
As indicated in Box 1 above, Indonesia and Ghana have established fully functioning and self-sustaining systems of compliance checks through national Timber Legality Assurance Systems (TLAS). Establishing similar national-scale compliance monitoring is now being adopted across numerous tropical forest countries, pushed both by international market signals and national stakeholder interest.[7] These are generally built in stages and FGMC experience has shown that they deliver results even before they are working as fully intended across all parts of the sector. FGMC2, alongside other donors, will continue to support their development in partner countries as an important element of governance foundations.
[7] FGMC has supported TLAS development in Ghana, Indonesia, Liberia, Rep. of Congo, Guyana, and through joint arrangements in Cameroon, Vietnam, Laos, Honduras, Thailand, C.dIvoire. Gabon, Malaysia, Colombia are also establishing national approaches.
The TLAS facilitate independent CSO-led forest monitors by establishing a conduit for independent information to inform decisions. FGMC1 has fostered Independent Forest Monitoring (IFM) in many countries particularly focused on strengthening capacities of local CSO or IPLC groups. This has resulted in greater confidence and understanding between authorities and CSO and in some instances cooperation in strengthening enforcement as better quality evidence from field investigations inform compliance checks. Box 3 describes the important role of IFM.
Box 2: Illustration of legal reforms supported through FGMC partners
FGMC helps countries establish new governance arrangements at national scale that suit their needs. The Voluntary Partnership Agreement processes create the opportunity for review of legal frameworks and reforms that clarify and strengthen rights and responsibilities and address shortcomings in law or policy. For example:
In Liberia, the 2009 Community Rights Law, gave communities the right to use and benefit from local forest areas in which they live. FGMC support has helped put structures and secondary regulation in place to make this law operational and ensure that the communities are able to negotiate fair agreements with logging companies.
In Indonesia, support via an accountable FGMC grant was instrumental in a 2013 Indonesian Constitutional Court decision that gave Indigenous People the right to manage their forests, and invalidated the government’s claim to millions of hectares of customary forest land. This was then integrated to the legality verification of the SVLK.
In Ghana the process facilitated by FGMC created the opportunity for national multi-stakeholder deliberations on several highly contentious aspects of forest law. Ministerial allocation of “special” forest rights was widely seen as a source of political patronage and lacking in transparency and operated counter to the principles enshrined in the VPA to increase transparency, and accountability. Civil society advocated strongly for this to be addressed and after extensive negotiations the Ministry agreed to a new law (approved by parliament in November 2017) that was jointly developed by Forestry Commission, NGOs and the Attorney General. This is now routinely monitored through the TLAS and NGOs have successfully challenged subsequent special allocations in Court demonstrating that the governance reforms being established with FGMC support are creating new mechanisms that stakeholders can use for greater accountability.
ICAI found in its evaluation of ICF that FGMC supported: partnerships between international, national and local NGOs in timber-producing countries have helped to amplify the voice of marginalised forest communities (including indigenous peoples) and have led to improvements in national policies and improved accountability in national governments and the private sector.
Box 3: Independent Forest Monitoring (IFM) is enhancing transparency and legal compliance / Civil society organisations and communities document and report suspected illegalities taking place in forests. This is known as IFM. The development of TLAS under the VPA has created opportunity for IFM. A 2022 review by the World Resources Institute (WRI) on IFM across the Congo Basin[84] concluded that despite the challenges in navigating relationships with governments, IFM organizations have delivered significant outcomes including the withdrawal of illegal forest titles and the adoption of new ministerial orders improving forest legality and forest governance. Examples of FGMC supported action include: / In Cameroon, IFM reports have led to timber seizures, temporary suspensions of logging permits, the opening of legal proceedings against companies for unauthorized logging, formal notices for illegal logging of communal forests—even sanctions against Ministry of Forests and Wildlife officials that were complicit in illegal logging activities. / In Indonesia, IFM has become institutionalised and is part of the process underpinning the Timber Legality Assurance System (SVLK). Evidence from IFM has been successfully used in prosecutions of forest crimes in Indonesia. / In RoC, the revised forest law creates the legal basis for community observation, and a mandate for state law enforcement agents to follow-up on community-generated alerts. / ForestLink, a near real time alert system helps community monitors in Africa point to illegal activity in their forests. The alerts are leading to the confiscation of illegal timber, evidence for prosecutions, and helping secure compliance by logging companies for social and environmental obligations. The systems are increasingly also being used to monitor wildlife crime and human rights violations. In Ghana the system is endorsed by Forestry Commission. / Independent forest monitoring strengthens enforcement and helps governments identify field level problems. But it faces ongoing challenges, especially for funding beyond donors and government sources. FGMC2 will continue support to IFM and help find solutions for long term support that safeguards their independence.
[84] https://files.wri.org/d8/s3fs-public/2022-04/independent-monitoring-congo-basin.pdf?VersionId=XBj8nw5qoKFFRxrLFF.qWe0O5PfXeiUo

FGMC-supported implementation of nation-wide compliance monitoring systems in Indonesia and Ghana has led to a transformational shift across all productive forests (20+million ha in Indonesia and 1.5million ha in Ghana), even without programme investments in specific landscapes. Indonesia credits its improving record of controlling deforestation in part to the improved compliance monitoring of its national (SVLK) TLAS (the steep drop in deforestation between 2016 and 2020 coincides with the full roll out of the SVLK across the entire country[85] Drawing confidence from this experience, and supported by FGMC, Indonesia has now further strengthened its standards to verify compliance for a higher level of sustainability, with 80% of the production from natural forests now certified for sustainability.[8]
[85] https://www.wri.org/blog/2019/07/indonesia-reducing-deforestation-problem-areas-remain#:~:text=The%20Indonesian%20government%20released%20its,2017%20number%20of%20480%2C000%20hectares. Wijaya A, Samadhi T N and Juliane R (2019) Indonesia is Reducing Deforestation, but Problem Areas Remain
[8] Reflecting significant VfM, FGMC has contributed approximately £25m to these efforts over the past 10 years
Transformational changes in markets informed by FGMC community of practice
There has been a significant transformation in international consumer markets for forest products over the past decade. This has evolved from what was largely a laissez faire approach in the 2000s (“forest governance failure in developing countries is not our problem”), to adoption of trade-based regulations aimed at curbing illegal logging through imports in major consuming countries (including the EU, UK, USA, Japan, S Korea, Australia see figure 4). The idea of regulations obliging business to exercise due diligence was initially viewed with scepticism by businesses in Europe as well as in producer countries. For government administrations it was equally novel. These are now the international norm as confirmed in independent market monitor reports[86]. FGMC1 was at the heart of this shift. It supported: research and evidence for policy makers, practitioners to implement new regulations, supporting exchanges, information sharing and capacity building. Support to NGOs has delivered evidence for action by national authorities in prosecuting offenders with successful high-profile cases in the EU and USA that served to send important signals in the market.
Figure 4 - Consumer Market Regulations to Stop Import of Illegal Forest Products.
Source: BMRC Strategy
[86] ITTO monthly Tropical Timber Market Report https://www.itto.int/direct/topics/topics_pdf_download/topics_id=7792&no=1
While market reforms were signalling the need for due diligence in timber supply chains to stop the trade in illegal forest products, there were widespread concerns that Chinese markets provided a major outlet for illegal material given that China accounts for nearly 30% global tropical wood trade. FGMC established an influential partnership with Chinese trade associations and think tanks to encourage sustainable sourcing of forest products, natural rubber and palm oil from tropical forest countries. FGMC focused on building understanding of governance challenges and requirements in FGMC partner countries, of approaches to controlling imports and/or promoting sustainability standards. This engagement yields promising results:
- 10 years ago, there was little consideration of illegal material in supply chains and a strong sense that it was not their problem, rather that of producer countries to regulate. Now there is clear recognition in China of the negative impact of its overseas forest footprint.
- The national forest law has been modified, incorporating the principle of due diligence to exclude illegal timber from its market, but it is unclear if and how this will apply to imports.
- significant shift in trade with an increasing % of timber from lower risk origins.[9] This is sending a signal to tropical producer countries of the need to establish effective legality systems and China’s intention to exclude Illegally sourced material.
  [9] There has been a significant shift to sourcing from lower risk supply chains (with increased use of timber from domestic sources, US, New Zealand, France and Germany), demand for tropical hardwoods still exerts pressure on forests in countries with weak governance. PNG, a high-risk country for illegal timber, is now the largest source of hardwoods into China since the collapse of imports from Russia.
- There is willingness to engage with tropical forest country national legality systems.
- Guidance for international operations framed by international ESG principles for timber, rubber, palm oil that has been tested and are being deployed.
- Ways of working. FGMC has introduced multi-stakeholder engagement with external stakeholders (not common earlier); interesting collaboration for example Global Witness (a high profile advocacy International non-government organisation - INGO) and Chinese think tanks developing a sustainable natural rubber standard.
The ICAI review of ICF forest programmes observed "One notable success has been the FGMC programme’s engagement with China, which is a major importer of tropical timber and other forest-risk commodities. This support contributed to China’s adoption of a new forest law in 2019, which introduces some limited due diligence obligations for Chinese companies importing timber products”."… reflecting that FGMC “has been able to influence and shape demand for timber in major consumer markets (such as Europe and China), while supporting in-country reforms in producer countries. (ICAI 2021)[87]
[87] ICAI report on HMG ICF (Forests and Biodiversity) 2021
As illustrated in Figure 4 above, the dominant position of China, and increasingly India and Vietnam, as the global market destination for forest and other commodities from FGMC partner countries makes clear the strategic importance for FGMC2 of finding ways to encourage China and other global markets to recognise and incentivise product sourcing that fully respects national environmental and social requirements in producer countries. (Annex I on Alliance Countries includes information on market trends.) The approach will be consistent with the UK government’s overall policy on engagement with China, India and other emerging global players.
BOX 4: Coalitions of FGMC partners influence consumer market regulations. / Since 2012, FGMC1’s accountable grants have supported organisations like FERN, Environmental Investigations Agency, ClientEarth to form coalitions with civil society organisations from tropical forest countries and other European NGOs advocating for action on the trade of commodities that put tropical forests at risk of deforestation. The FGMC coalition drew from their experience with FLEGT which combined market measures with supply support to advocate for import measures that would curb illegal tropical forest clearance and incentivise sustainable production. A decade ago, consumer governments relied on voluntary industry initiatives and non-binding policy measures. However, new evidence about the rising problems of illegal deforestation, practical experience with implementing import measures for the timber trade and combined with increased pressure from both business and NGOs has pushed governments to adopt binding supply chain rules. / In 2021, the EU Deforestation Regulation (EUDR) was proposed. The FGMC1 community of practice shared evidence, convened voices from tropical forest countries and shared ideas to improve the proposal, including strengthening enforcement provisions, transparency and reporting, protection of rights of IPLCs and advocated for greater voice from tropical forest producer countries. The finalised text of the Regulation, which enters into force in 2024, includes many of the suggestions proposed by the FGMC coalition. FGMC’s community of practice continues to provide inputs to EU authorities, businesses, producer governments and their stakeholders as the practical mechanisms for implementation are being established. They continue to press for greater attention to partnerships and cooperation with producer countries. The FGMC community of practice also worked closely with Defra in the development of UK equivalent legislation. The EUDR presents a significant success for the FGMC community of practice and demonstrates the significant return on investment of concerted and informed advocacy supported through FGMC accountable grants programme.

FGMC1 enabled the UK to lead international efforts to strengthen forest governance and combat illegal logging, forging bilateral partnerships with tropical forest countries and building common understanding in international markets, including with China. It helped to build coalitions of practitioners through accountable grants with policy and advocacy organisations, engaged globally in improving understanding and transparency: For example, providing seed finance for initiatives such as Global Forest Watch (WRI), the Taskforce on Nature-related Financial Disclosures (TNFD) and TRASE[10] that are now important tools informing international efforts to reduce forest and biodiversity loss. [88],[89],[90] The evidence derived from these tools, when combined with the advocacy of other FGMC accountable grant partners such as FERN and ClientEarth, formed an important coalition that over many years advocated for and influenced consumer market policy. Box 4 is a powerful example of influencing by the FGMC coalition. Annex K provides an overview of the planned FGMC accountable grants programme drawing from this experience.
[10] TRASE – is a not for profit institute founded in 2015 by the Stockholm Environment Institute and Global canopy to bring transparency to deforestation and the agricultural commodity trade.
[88] https://www.globalforestwatch.org/
[89] https://www.globalforestwatch.org/
[90] https://trase.earth/
FGMC’s unique approach is to drive stronger forest governance in developing tropical countries while promoting reforms in consumer markets. Based on the experience of FGMC1, it is evident that transformational governance reforms are possible, even in contexts with very poor governance track records or wider context of instability.
4. Opportunities and Scope for transformations in forest stewardship
In assessing the future scope and opportunities for FGMC2 to support transformational change in forest stewardship, we build on experience learnt over decades of UK engagement in forest governance and from FGMC1, in particular. These include:
  1. Building respectful partnerships that focus on supporting countries’ own plans, prioritising their capability to implement them.
  2. Ensuring the right people are in the room by facilitating the inclusion of indigenous communities, women and girls in the decisions that affect them and for the effective delivery of the UK’s mission to create a world free from poverty on a liveable planet.
  3. Strengthening the legitimacy of governments with their populations through supporting the building of accountable, effective, and inclusive institutions, and championing the rule of law.
  4. Addressing illegality in trade, including illegal wildlife trade and illegally produced products which increase risks to forests and impoverish many forest-dependent people.
  5. Attracting investment and increasing revenues from tax collection and trade to drive economic growth as a result of investing in improved governance
  6. The promotion of sustainable trade, through trade agreements, through initiatives to unlock trade flows and reduce barriers, and by improving the UK’s global environmental footprint
  7. Reforming global markets and supply chains for forest and agricultural commodities, reducing deforestation
  8. Supporting the growth of high-integrity carbon and nature markets
The ideas set out in this section reflect on the current challenges and opportunities faced by tropical forest countries. They highlight policy domains and governance reforms that FGMC2 will consider supporting and they are further assessed in the Appraisal case and Annexes D and H. It should be stressed that FGMC2 will work with partners to determine their priorities for action, but it is not the intention that the programme will work on all of the issues highlighted here in all contexts.
Opportunity to drive further reform and improvement in countries supported under FGMC1:
Progress has been made in Indonesia and Ghana, already described as having successfully transformed the governance of their productive forest sectors. Not all VPA countries (partners supported by FGMC1) have fully designed and mobilised new (or retooled) national forest systems. This reflects differences in the challenges, forest sector capacities, as well as national policy dynamics. The pathway to sector wide governance reforms is long requiring inclusive processes to first secure national agreement and then carry out reforms of laws and regulations; ensuring rights are protected and benefit sharing mechanisms are in place; setting up systems to ensure transparency and accountability; setting up independent monitoring systems and ensuring that effective enforcement is in place.
Systemic transformation and difficult legal reforms take time, as does building a constituency for the reforms sufficient to sustain them. The development of national traceability and verification systems has been challenging. Ghana for example, had several attempts before locking in a system that meets their needs. Countries will therefore transform their forest sectors at their own pace. Guyana, Liberia, Republic of Congo, Vietnam, and Cameroon are at various stages of the design and roll out of their national systems. In all these cases deliberative multi-stakeholder structures are in place, with varying degrees of inclusion, legal reforms are in place, institutional capacities are being strengthened through the provision of technical assistance and they are at various stages of testing or roll out of their national sustainable forestry systems. The strength of national stakeholder engagement, coupled with growing pressure from international markets for certified timber give confidence that these processes will advance. FGMC2 will build from the monitoring approach adopted in FGMC1 that tracked policy results (linked to TA projects) to monitor institutional development as key to building governance foundations.
In almost all countries, there are established coalitions of national reformers. They drive the deliberative processes to reform legal and management practices. FGMC’s role is not to press for delivery through a project, rather to support the reform process with the means to build evidence, capacity development to engage, and facilitation to help bring stakeholders with differing positions to reach consensus. Where these processes are well established (through FGMC1 support), stakeholders are keen to apply lessons to address new opportunities and threats to forests.
In responding to interest from new countries, FGMC2 will support the development of similar coalitions. FGMC2 will also promote learning and exchange between producer countries. Depending on the context, this may enable much more rapid deployment of new approaches.
FGMC2 will sustain established partnerships where appropriate and where stakeholders are pressing to extend the practice to tackle other forest threats. In Ghana and Indonesia, where national systems are fully operational, little external assistance is required other than to ensure that independent monitoring and external audits continue. Political challenges (e.g. instability, general elections, politically connected stakeholder lobbying) as well as external threats such as the Covid pandemic, have tested the sustainability and robustness of the governance reforms that are secured in the national Timber Legality Assurance Systems (TLAS) and the resilience of inclusive and legitimate multi-stakeholder deliberative platforms that continue to drive positive change. This provides confidence in the resilience and sustainability of the governance shifts.
For the other partner countries under FGMC1, (Guyana, RoC, and Liberia) and for new countries, where interest exists, (Cameroon, DRC, Laos, PNG, SI) FGMC 2 will continue to build up their national timber governance systems. FGMC 2 will establish delivery instruments able to respond rapidly to need, be deployed where opportunity arises, and be redirected where priorities or context changes.
Once the systems are operational, there may be opportunity for the UK to formalise the partnership signing Voluntary Partnership Agreement with regards to forest product trade with the UK. The Management Case sets out the phasing planned, first to establish delivery mechanisms, second to carry forward identified actions in countries where FGMC1 has established working relations, and then in year 2 or 3 to identify further partners based on need and extensive scoping work.
FGMC2 will seek ways to align and join forces with other donors supporting national systems where appropriate. Detailed scoping and development of country specific plans outlined in Annex H (partner country analysis and engagement plans) will ensure FGMC complements and adds value to other on-going initiatives. Coordinated action means that in some contexts the UK (through FGMC2) will lead support to governance reforms, whereas in other contexts where other donors have established forest programmes FGMC2 support will be light touch and focus on encouraging learning between countries. FGMC1 worked jointly with France, Germany, Netherlands, Norway and the EU at different periods of time.
In many producer countries, including where national systems are being developed, voluntary certification schemes are also in place and utilised by business wishing to export into controlled markets Over the past thirty years a plethora of international voluntary private certification and standard setting bodies to encourage sustainability have been established, but alone, have proven insufficient to reduce tropical deforestation at the scale required (see footnote ).[11] [91]
[11] Forest Stewardship Council (FSC), Round Table on Sustainable Palm Oil (RSPO), Round Table on Responsible Soy (RTRS), Global Roundtable for Sustainable Beef (GRSB),, Cocoa & Forests Initiative, Rainforest Alliance certificates for cocoa, tea and coffee to name a few. Mining schemes are less well developed when it comes to standards relating to forests. These include the Aluminium Stewardship Initiative, Better Coal Code, International Council on Mining and Metals Sustainable Development Framework, Institute for Responsible Mining Assurance, Towards Sustainable Mining, Responsible Jewellery Council, Fair Stone, the Fair mined Standard for Gold, and others.
[91] See, e.g., Conniff Richard (2018) Greenwashed Timber: How Sustainable Forest Certification has Failed (https://e360.yale.edu/features/greenwashed-timber-how-sustainable-forest-certification-has-failed)
Certification of forest products has had its main impacts in temperate and boreal regions but has made minimal headway in the tropics, where weak governance, poor enforcement and sub-standard forest management remain significant challenges. Of the more that 400m hectares of certified forests, only 6% were in the tropics.[12]
[12] Under the leading FSC and PEFC schemes, FSC certificates covered 200.7 million ha and PEFC certificates 325.4 million ha; allowing for double certification the total global certified forest area was 433.6 million ha; of these only 27.6 million ha (6.4%) were in tropical countries in 2019. IPE Tripleline Report: FLEGT Voluntary Partnership Agreements: An Approach for Other Forest-Risk Commodities? October 2020
Because of the national scope of the approach supported by FGMC, and the challenge of shifting entrenched positions and securing legitimate buy in from stakeholders, legal compliance may not deliver in all instances, particularly during the early stages of forest sector reform. In the longer term, however, mandatory legal compliance across all forest operations, especially with strengthened legal frameworks, is more likely to be sustainable than small ‘islands’ of responsible production achieved through individual businesses with voluntary certification operating in a ‘sea’ of illegal and destructive practice (see Figure 5).The reality is that in many countries, whilst national systems are being strengthened, individual businesses with export markets will also engage in certification, at least until such time as national systems are viewed as credible.
Figure 5 - Nationwide Approach compared to Certification of Forest Units
Companies want a more level playing field, fairer competition, and a new generation of consumers want much more robust assurances about their purchasing decisions. A credible national approach to driving up forest governance will respond to these needs.
Coalition of tropical forest countries calling for stronger consumer-producer country action.
FGMC has supported a group of tropical forest countries who have been actively engaged in international FLEGT action, to reflect on how to derive greater benefit from the national systems they have put in place sustain their forests. They have formed a coalition, known as the Broader Market Recognition Coalition (BMRC) and they want to gain international recognition for their national sustainable forest regulatory systems.
They are frustrated by the proliferation of different consumer market regulations and the challenges they face in securing market acceptance for their national sustainable forest systems. As a starting point, the coalition seek greater understanding and recognition of each other’s systems so as to facilitate trade. The BMRC countries are seeking ways to ensure businesses work to the strengthened national scale regulatory and monitoring systems that they credit with turning the tide on combatting illegal logging and curbing deforestation.
By the end of 2021, 75% of the value of all wood and wood furniture exports from lower and medium income countries worldwide (which include nearly all tropical countries and their major direct competitors) was destined for markets with import controls designed to exclude illegal timber in place. This is shown in Figure 4 above. However, forest countries find that there is limited understanding in these international markets of the national systems they have established to promote sustainability and curb illegal logging. Most buyers in consumer countries (and markets) are opting for private certification schemes over national systems despite their potential to deliver more significant sustainable forest outcomes. Reasons for this preference include:
- a lack of knowledge;
- that certification schemes tend to be based in consumer markets and so seem more accessible to buyers;
- that the national systems provide assurance and traceability to the point of import but have not invested in labelling to the end consumer, whereas certification systems reach the end consumer through chain of custody;
- that fully functioning national systems are still limited to Indonesia and soon Ghana; and,
- that FLEGT is still seen as an EU instrument.
The BMRC will play an important role in raising awareness of national systems and providing the assurances that coalition member countries are meeting internationally credible forest standards through independent assessment panels.
FGMC2 will support BMRC in their efforts to build the coalition encouraging other producer countries to join. This will entail outreach to other producing countries with an interest in building national approaches. The BMRC will encourage engagement with consumer markets to expose them to their standards (performance and systems) and address consumer country concerns. The BMRC will explore the development of positive market incentives that reward strengthened forest governance. Countries that are making efforts to practice sustainable forest management and agriculture and to strengthen forest and land governance are not yet seeing the “rewards” they hoped for. Existing market instruments (such as Due Diligence legislation) serve as “sticks” and exclude goods that do not comply. However, producer countries are seeking positive incentives to encourage more ambitious action and are concerned that these are not prevalent. The BMRC is exploring opportunities to advance dialogue with more producer and consumer countries through international policy processes, including the Forest Agriculture and Commodity Trade (FACT) dialogue[13], ASEAN[14], International Tropical Timber Organisation (ITTO) and United Nations Forum on Forests (UNFF). In the long term, should they succeed in shifting the international dialogue, this process could result in new international norms for sustainable timber production and its associated trade.
[13] https://www.factdialogue.org/resources/forest-agriculture-and-commodity-trade-fact-dialogue/
[14] ASEAN – Association of Southeast Asian Nations
Addressing illegal deforestation
In some countries national stakeholders are keen to apply the experience of dealing with illegal logging to other illegal activity that threatens forests. The tools and processes developed under FGMC1 could help governments and other stakeholders address challenges in the governance of forest land use decision making to stop illegal forest clearance. At the intersect of other forest land uses such as mining where rules and policies may be incoherent, the FGMC approach might help prioritise and clarify forest use decision making and improve compliance monitoring.
Mining
Sometimes forest and mineral resources are in the same place, governance challenges are compounded by sector management structures that are poorly coordinated or incoherent, and mining interests strongly threaten forests. This is true of potential FGMC2 partners Ghana, Indonesia and Guyana in particular. There are opportunities for FGMC2 to support national stakeholders interested in addressing illegality at the forest-mining interface. These include strengthening legal safeguards regarding mining in sensitive ecological or traditionally protected areas (such as biodiversity “hot spots” of intact high forests or IPLC sacred sites) and bringing greater transparency into how decisions are made regarding the awarding and licensing of mining concessions in forests and how they are monitored, and forests restored.
FGMC’s experience of deliberative processes could be extended to bring different interests engaged in mining in forest areas (a contested space) together. Section 2 outlined that mining activities in forests are growing, driven by high global gold prices and the search for rare minerals. Some of this mining is illegal and/or “informal” and can result in conflicts with other forest users. The intention of FGMC2 is not to prevent mining in forest lands (unless these are legally protected from such activity) but rather to help stake holders develop and agree rules and safeguards and to ensure these are applied and monitored. Space also needs to be created for concerns to be addressed, particularly from local people, regarding the environmental and health impacts of unregulated mining in forest communities and for agreement to be reached on more responsible mining practice.
In some countries (RoC, DRC, Liberia) the forest and mining sectors are both signed up to the Extractive Industries Transparency Initiative (EITI). This presents an opportunity for cooperation and lesson learning. For example, in DRC, civil society organisations active in the mining sector have been reviewing the benefit sharing provisions in the forest code in an effort to learn from experience.
Forest Risk Commodities
As indicated in section 2 above, agricultural commodities such as palm oil, cocoa, soya, beef are responsible for substantial areas of illegal tropical forest clearance. There is growing awareness of this in global markets and policy and market measures are being put in place in the UK, USA, EU and elsewhere to reduce the risks of imported deforestation in supply chains, or worse the risks associated with importing commodities produced illegally against the laws of the countries of origin. While it is challenging to analyse the extent of illegal deforestation, Annex N provides an overview of current understanding and evidence. FGMC1’s focus on supply and demand-side policies, generating evidence and empowering coalitions of interest, particularly from developing countries served to inform the development of EU, US, Chinese and UK policies aimed at encouraging business to take responsibility for sourcing, and cut illegal material out of their supply chains.
FGMC1 has encouraged lesson learning and practice between those working to strengthen governance of timber and agriculture commodity sectors where forest land serves as common ground for a coordinated approach. The programme has supported the development of transparency tools which are now available globally (eg Global Forest Watch, TRASE). In a few countries, stakeholders have brought the experience with timber to similar discussions on the cocoa and palm oil sectors. For example, CSOs are engaged in deliberations shaping national policies on sustainable cocoa in Ghana and Cote d’Ivoire supported through legality ‘clinics’ and research undertaken by FGMC partner ClientEarth.
The emergence of consumer market import regulations and due diligence requirements to cut out imported deforestation from supply chains has spurred a huge interest in international businesses and producer associations to improve traceability and other systems that inform corporate due diligence. Trade-led initiatives are growing and are well supported by international platforms such as the Tropical Forest Alliance (TFA), Soy and Sustainable Palm Oil round tables. Other IFU programmes such as Investing in Forests and Sustainable Land-use (IFSLU2) are well positioned to support and champion this emergent interest. This is a domain where FGMC2 would not engage.
However, where forest risk commodities are driving illegal deforestation and national stakeholders are keen to use the pressure of from international markets to strengthen forest land governance, FGMC2 would be well positioned to support national stakeholders with that ambition. The experiences of addressing illegal logging for timber and other forest product commodities through the development of national forest governance reforms and monitoring systems would be useful in informing future national government led strategies. Stakeholders in potential FGMC2 partner countries, such as in Indonesia and PNG have signalled a strong interest to develop a national approach to compliance monitoring and strengthening the policy and legal context of forest land allocation processes for the commodities that put forests at risk. Where forest clearance is taking place illegally, FGMC experience and approach could potentially support processes to clarify and strengthen forest land-use decision making, and to encourage national stakeholders to apply the lessons learnt from FGMC1’s focus on timber to securing a policy framework that safeguards forests. Where there is strong demand from stakeholders, the focus of FGMC2 will be on strengthening national governance (rights, regulations, transparency) and improving national transparency mechanisms that enable international markets to understand national requirements. FGMC2 support could therefore strengthen countries capacity to respond to the requirements of UK’s due diligence Forest Risk Commodity (FRC) legislation (under the Environment Act).
FGMC2 will draw inspiration and lessons from the UK Government’s Global Resource Initiative that established a multi-stakeholder task force to consider evidence, options and strategies to enable the Government to take forward the ambition of the 25 year environmental plan that called for UK leadership in tackling global deforestation driven in part by UK consumption, [92][93] our overseas forest footprint. Through FGMC’s alliances with consumer markets FGMC2 could support efforts that help inform similar policy processes in other countries, where FGMC2 would enable direct links to tropical forest country partners so that consumer market policies are better informed by the ambition, realities and challenges faced by tropical countries in securing effective forest stewardship while supporting sustainable production. Globally, FGMC2 will grow relationships established under FGMC1 to foster communities of practice working to reduce imported illegal deforestation.
[92] https://assets.publishing.service.gov.uk/media/5ab3a67840f0b65bb584297e/25-year-environment-plan.pdf HM Government (2018) A Green Future: Our 25 Year Plan to Improve the Environment
[93] https://assets.publishing.service.gov.uk/media/62bf0abfd3bf7f16434f7149/global-resource-initiative-finance-report-may-2022.pdf Economic Climate Environment (2022) Global Resource Initiative Finance Report
Scope and opportunity for FGMC2 to engage in forest carbon governance
The UNFCCC COP 26 marked a step-change in how forests were addressed in the climate agenda as set out in the Glasgow Leaders Declaration on forests.[15] One clear area with potential to attract finance to tropical forest countries is through forest carbon markets. A key blockage to attracting reliable finance at scale are the weak forest governance foundations common in many tropical forest countries. Drawing from the experience and networks established by FGMC1, the programme is well positioned to assist partners to strengthen forest governance to then leverage investment/finance. Clear and legitimate national regulatory frameworks, greater transparency, accountability and stakeholder buy in will be essential to provide the private sector confidence required for forest carbon initiatives to succeed.
[15] Glasgow Leaders Declaration on Forests Pledge, specific pledges on the Congo basin and IPLC, FACT dialogue, FCLP, LEAF initiative, TNFD,
Carbon markets are still nascent, and subject to a number of risks that have caused demand and prices to wobble significantly. Risks to the value of forest carbon credits relate to the forest conditions (that lend carbon its market value) and forest governance. These include that forests may be lost (permanence); that deforestation may be displaced to other locations (leakage); that claims may be inflated (additionality); and issues related to authority (consent) and contested benefit sharing particularly in areas where IPLC claim customary ownership rights.
Early experience and exposés provide evidence of failures in forest carbon projects, including no evidence of additionality, giving rise to accusations of worthless “phantom credits”. [94] There have also been accusations on social issues, such as failure to secure the Free, Prior Informed Consent of local communities, and moving communities from their lands because their traditional agricultural practices were inconsistent with project goals. [95] [96] These reports have resulted in reputational damage to the integrity of carbon markets generally, price volatility, significant declines in the value of forest-based credits in the voluntary market, and developers pulling out of projects due to lack of confidence in standards. [97] In turn, these reports have led to calls for increased scrutiny of how the Voluntary Carbon Market (VCM) operates.
[94] For example, see (i) Haya, B. K., et.al. (2023) Quality Assessment of REDD+ Carbon Credit Projects; and (ii) Thales A. P. et. al (2023) Action needed to make carbon offsets from forest conservation work for climate change mitigation.
[95] https://www.abc.net.au/news/2023-02-14/carbon-credits-projects-papua-new-guinea-logging-four-corners/101936714 Long S, Bali M and Murch M (2023) Carbon Colonialism
[96] https://www.abc.net.au/news/2023-02-14/carbon-credits-projects-papua-new-guinea-logging-four-corners/101936714 Long S, Bali M and Murch M (2023) Carbon Colonialism
[97] https://www.reuters.com/sustainability/cop/carbon-offset-firm-south-pole-cuts-ties-with-zimbabwe-forest-project-2023-10-27/ Twidale S (2023) Carbon Offset Firm South Pole Cuts Ties With Zimbabwe Forest Project
International rules are being developed to address these problems, with the UK as an important champion. These include refining the concept of high integrity carbon credits.[16] Several tropical countries have started to put regulations in place to give them greater control over how their voluntary and compliance markets operate. The Integrity Council for the Voluntary Carbon Market (ICVCM) has been established (with UK support) to set and enforce global standards that identify high-quality carbon credits.[98]
[16] The ICVCM broadly defines high integrity carbon credits as needed to adhere to the following three broad principle: 1) Credits derived from programmes or schemes with effective governance measures in place to ensure transparency and accountability, that credits are uniquely identifiable and registered, and that they are third party verified; 2) They must have a clear emissions reduction impact demonstrating additionality against business as usual, they must be permanent, have a robust system in place to quantify them and there must be no double counting; 3)They must contribute to sustainable development including strong provisions for environmental and social safeguarding
[98] https://icvcm.org/ The Integrity Council for the Voluntary Carbon Market
Several countries have started to develop national forest carbon rules. In many cases, these are motivated by potential international trading of their national mitigation results under Article 6[17] of the Paris Agreement. Some countries that are prospective buyers of credits under Article 6 are also establishing bilateral schemes with tropical forest countries. Rules are sometimes developed without involvement with (or even knowledge of) stakeholders, particularly those who should benefit from the proceeds.
[17] Article 6 pertains to the establishment of international compliance carbon markets governed by the rules of the Paris Agreement of the UNFCCC where countries can trade carbon credits.
These new carbon schemes raise questions of how the processes of the type established through FGMC can continue to play a role in inclusive forest governance reform, consolidating gains made in developing national systems related to timber production and trade. Legal and sustainable forest management, of the type that FGMC-supported processes have developed, results in better carbon outcomes than the previous status quo and have had strong stakeholder involvement and ownership. Yet that ownership may be undermined if rules and systems of carbon schemes are imposed by external actors, such as project developers or international initiatives.
FGMC experience can help inform the development of strengthened forest carbon governance including: the facilitation of inclusive processes for the development of new rules reflecting on rights, responsibilities and benefit sharing, independent forest monitoring; transparent compliance verification and reporting, negotiating an understanding and common ground in developing standards at national or international levels. Box 5 provides an example from Guyana where FGMC support to the VPA process has been credited with providing the governance foundations sought by buyers of high integrity forest carbon credits, illustrating the opportunity for FGMC2 to link forest carbon to governance reforms.
Box 5: Investing in forest governance foundations secures carbon finance. / In 2022 Guyana was the first country to secure a sale of forest carbon credits worth £750m approved by the high integrity standard known as ART TREES ( Architecture for REDD+ Transactions (ART)[18] programme) which sets the highest level of environmental and social standards for forest carbon deals. The FGMC-supported VPA process was key evidence that helped Guyana establish the credibility of its forest governance (controls), its commitment to stakeholder engagement, benefit sharing arrangements, and focus on safeguarding. This evidence helped Guyana secure the ART TREES standard which was crucial to the deal. In February 2024 Guyana announced it will make the first carbon credits (ART TREES approved) available to airlines to counter pollution under a landmark U.N. emissions deal in Carbon Offsetting and Reduction Scheme for International Aviation (CORSIA).
[18] REDD+ - reducing emissions from deforestation and forest degradation - a framework to encourage developing countries to reduce emissions and enhance removals of greenhouse gases through a variety of forest management options, and to provide technical and financial support for these efforts.

FGMC could also support national processes to frame and integrate forest carbon rules within national forest policy and requirements that govern multiple use forest stewardship. It is not sufficient that transparency and accountability is strengthened for forest carbon in isolation of other forest uses. FGMC’s approach could bring forest carbon stakeholders into the deliberative platforms developed for timber, to encourage a more holistic approach to regulatory frameworks and systems that optimise the generation of sustainable value from forest lands. This would strengthen ownership, reduce transaction costs and increase enforcement for governments currently dealing with bespoke governance requirements for multiple initiatives.
Work with IPLC and considering impacts on women and the poor.
The IPLC Pledge at COP 26[19], has increased political attention on IPLCs and has prompted greater emphasis on initiatives addressing tenure rights, benefit sharing, access to direct finance and advocacy. As outlined in Section 2 above IPLCs are stewards of 80% of the world’s remaining biodiversity and yet are frequently excluded from policy decision making processes that often disproportionately affect them. They frequently lack security of tenure and rarely derive a fair share of the benefits that should accrue to them from forest revenues. FGMC1 has years of experience of understanding the importance of inclusion in policy reform processes, including:
[19] The COP26 Joint Donor Statement on the Congo Basin, pledging at least $1.5 billion between 2021-2025 to support the region to protect and maintain the Congo Basin forests, peatlands and other critical global carbon stores, with EU, Germany, France, Japan, Belgium, the Netherlands, Norway, Sweden, South Korea, the UK, the US, and the Bezos Earth Fund.
    1. supporting the development of legal frameworks that enshrine the rights of IPLCs through technical expertise, convening, analysis, advocacy. Under FGMC1 all processes resulted in clarification or strengthening of legal provisions, for example support for greater participation of communities resulted in fairer reforms, as seen in Liberia’s landmark Land Rights Act (2018), or Free Prior Informed Consent being enshrined in RoC’s 2020 Forest Law.
    2. Ensuring their voices are heard in major decisions that affect them (e.g. The Nationally Determined Contributions (NDC) submitted by Central African countries at COP26 included measures to strengthen IPLCs' livelihoods and forest tenure rights and those of women, and Ghana’s NDC incorporated recommendations about gender-responsive sustainable forest management. These were a direct result of FGMC-supported CSOs promoting the voices of communities in the process.
    3. Securing rights to community forests, enhancing forest values and potential income streams through multi-purpose forest management, e.g. FGMC grantees and projects supported community and multi-purpose forest management in legal and policy reform in Indonesia, DRC, Liberia, RoC.
    4. Securing a share of benefits accruing from forest operations, e.g. In Liberia, a National Benefit Sharing Trust has been established to manage forest-related fees (30% Land Rental Fees) intended for the benefit of communities. By 2018 a total of USD 2.6 million in owed land rental fees had been paid to communities, supporting 40 development projects.
    5. Strengthening institutions and structures to enable effective benefit sharing e.g. In Ghana, where a Social Responsibility Agreement (SRA) with IPLC is a legal requirement for any company operating in forest areas, communities have been trained to alert Government to cases of poor SRA performance, and officials are now better able to act on alerts. With FGMC backing, a CSO database interfaces with Ghana’s Wood Tracking System, allowing SRA non-compliance to be identified. All SRA are now paid before export permits are secured, previously these were rarely honoured.
    6. Establishing systems to ensure compliance with social and labour requirements – Ghana’s TLAS enforce worker’s health and safety requirements. FGMC supported action has enabled small businesses to comply and audits now check that companies have the necessary health and safety certification. Those that lack the relevant evidence are unable to sell their goods. This has created a strong incentive for companies to strengthen health and safety standards, thereby reducing injuries and death among workers.
    7. Monitoring and reporting forest crime. A key development under FGMC 1 has been the institutionalisation of the civil society-led Independent Forest Monitoring (IFM) function, including community-based monitoring, as a governance tool that increases transparency in relation to forest and timber trade and improves enforcement with the legal frameworks. In Ghana, Cameroon, DRC and RoC, community monitors are empowered and capacitated to report infractions in real time sending alerts that can be picked up by officials themselves, or by NGOs for advocacy purpose.
FGMC2 will continue to support reform of legal frameworks for IPLC rights and navigate inconsistencies and incoherence therein. This will include coherence with national climate strategies. FGMC2 will also build on the positive legal shifts that are occurring in countries like Liberia, RoC and DRC to support the development of systems and tools, needed to see rights respected, and compliance monitored. FGMC’s will support deliberative processes, including strengthening capacity through legal working groups for example and continuing to support independent forest monitoring at the grass roots as a way of tracking compliance and feeding back into national systems.
FGMC2 also offers opportunity to strengthen gender and political inclusion in the sector governance reforms, with policymaking in the forest sector having historically been dominated by men and officials from governments and major companies. FGMC2’s gender and political inclusion approach is set out in Annex C and described in the Appraisal Case.
In response to FGMC reviews and ICAI observations, greater emphasis will be given to the carrying out of ex-ante analysis in reform processes to deepen understanding of the potential impact that reforms might have on IPLCs, women, and small and medium enterprises dependent on forests for example. FGMC2 will encourage and support stakeholders to assess and consider benefit flows and impacts of policy reforms as integral to the deliberative process.
As we have seen in countries where the TLAS is now operational, the value of including the social and IPLC linked requirements into compliance monitoring, is that often for the first time it shifts attention from securing rights to a focus on ensuring that they are complied with. These systems have created a powerful tool for IPLC to engage with both government service and businesses to see obligations met as their performance is now directly linked to markets and trade.
Box 6: How does the first phase of FGMC inform the design of the new programme?
First, FGMC1 addressed market failure that encouraged illegal logging, and the associated illegal timber trade. It included a component testing approaches to address deforestation driven by agricultural commodity production. It did not focus on either mining or infrastructure influencing forests. It strongly emphasised illicit behaviour, while recognizing that market failure also encourages legal logging and legal deforestation.
Second, FGMC1 addressed government failure, specifically the weak regulation of logging and the trade in illegally sourced timber, touching less on other forest commodities. FGMC1 was a global programme. This enabled it to develop a coherent strategy directed at improving public and private standards at multiple levels, internationally and nationally. Mutual enforcement of these in producer and consumer countries led to reduced illegal logging globally.
Third, FGMC1 addressed the inequitable distribution of resources that results from illegal logging and untransparent forest clearance, from associated corruption, and from the collection and distribution of forest revenues. Improvements in the distribution of revenues benefited large numbers of poor people living around forests. It supported some work on the forest rights and land tenure of local communities.
Fourth, FGMC1, developed and supported inclusive stakeholder-driven processes that have helped to create legitimacy for resulting policy and regulatory reform. This has built a strong base of support focused on monitoring and implementation of reforms that has managed to sustain these through significant political shifts suggesting long term sustainability.
Lastly, the formation of and support to coalitions working at national and international levels has helped create and sustain momentum for change and commitment to reform and implementation. These coalitions have brought together experts from different domains, north and south, to shape international policies and initiatives – e.g. Rights and Resources Initiative’s leadership in campaigning for a shift in priorities beyond the recognition of IPLCs as forest stewards to ensure their genuine agency, greater say in decisions that affect them, and a bigger share of the resources that are deployed in their name, influenced the COP 26 IPLC Pledge. Evidence and thought leadership from the FGMC community of practice has also been drawn upon by the UK to enable HMG to shape and lead international policy agendas e.g. the GRI, FACT Dialogue, UK FLEGT reviews, and BMRC.
In ICAIs 2021 review of ICF forest spending, it found that: “the experience of the FGMC … provides a model for work on other commodity supply chains: it was built on deep sectoral expertise and experience, was genuinely multi-stakeholder, and adequately resourced relative to the scale of the commodity market. It involved a package of demand- and supply-side measures, implemented in formal partnership with both producer and consumer countries, and worked to create clear economic incentives for producers to change their practices. Currently, UK efforts on other forest-risk commodities lack such a systematic approach”.
5. FGMC2 IMPACT AND OUTCOMES
FGMC2 will use UK International Climate Finance to achieve results for poverty reduction and development, safeguarding forests and biodiversity, benefitting forest-dependent people and consequent climate resilience and reduced greenhouse gas emissions. Programme funding will contribute towards the transformation of the sector in tropical forest countries, as well as global markets for forest products. [99] Table 1 sets out the expected super goal, impact, systemic outcomes, behavioural intermediate outcomes and direct outcomes for beneficiaries (super impact).
[99] IPCC, (2019) Climate Change and Land: an IPCC special report on climate change, desertification, land degradation, sustainable land management, food security, and greenhouse gas fluxes in terrestrial ecosystems [P.R. Shukla, J. Skea, E. Calvo Buendia, V. Masson-Delmotte, H.-O. Pörtner, D. C. Roberts, P. Zhai, R. Slade, S. Connors, R. van Diemen, M. Ferrat, E. Haughey, S. Luz, S. Neogi, M. Pathak, J. Petzold, J. Portugal Pereira, P. Vyas, E. Huntley, K. Kissick, M. Belkacemi, J. Malley, (eds.)]. In press.
FGMC2, like FGMC1 will be a centrally managed global programme. This has been core to FGMC1 success. The programme is designed to achieve impact on a global scale, working with the most significant international market drivers and supply chains of tropical timber and “forest-risk” commodities. It will engage with international policy-making processes that aim at influencing business and investment norms and standards to encourage production and consumption behaviour change at national levels.
The programme will focus on achieving coherence amongst producer countries efforts in ways that accelerate global progress and ratchet up overall ambition. Commensurate with UK leadership ambition on forests and climate change, we will double the value of a new 10-year phase of FGMC, work with more than twice as many producer countries, encouraging them to learn from and be influenced by each other across social, economic, and political boundaries, and to cooperate with each other. The capacity to invest in a cross-country dynamic, as distinct from a multiplicity of separate country programmes, reflects the realities of global trade dynamics and supply chain structures impacting forests.
Table 1 - Expected outcomes and impacts of FGMC2
Outcomes / (Systemic changes)	National rules-based systems are established in tropical forest countries for effective management of forests underpinning climate, development and forest sector strategies / National rules-based systems for trade and investment linked to forests footprints of consumer markets are established to incentivise forest governance reform in tropical forest countries. / International systems, norms and initiatives value and incentivise forest governance reforms / Increased investment requiring forest governance in sustainable forest uses / Increased global market for products from countries with national sustainability systems / Complementary policy actions implemented by consumer and producer countries
Outcomes (Behavioural changes)	changed behaviour of stake holders, respecting rights & responsibilities in forest management / Inclusive deliberative sector policy making / Reduced corruption / Consumer markets and investment measures close outlets for illegal products / Carbon markets close out low integrity forest carbon credits / Regulations that recognise and reward commodities or forest carbon credits from countries with national forest sustainability systems / Effective international policy processes commit governments to sustaining forests and measures that incentivise compliance with national requirements
Impact	Transformed forest land governance for forest stewardship: / Forest stewardship is the care and wise use of forest lands that ensures their health and productivity for current and future generations. / It includes fair and sustainable governance arrangements (rights, regulations, accountabilities, incentives) and reduced risk for public and private forest investments and supply chains.
Super impact direct outcomes for beneficiaries	Productive tropical forests are sustained realizing their potential to provide climate change mitigation and resilience, livelihoods for poor people, biodiversity, economic growth, with reduced deforestation, enhanced forest conservation and reduced illegal logging. / Livelihood, gender and poverty impacts / More forest land under multiple use sustainable management / Increased and predictable share of forest benefits and revenue / Improved local environment for forest communities, accessible water, rainfall and cooling. / Increased private investment into IPLC-led sustainable forestry including for carbon

Results indicators will gauge change in markets, business standards and systemic transformational change across the forest sector at national levels. Monitoring will be designed in line with HMG priorities, including ICF KPIs, poverty, gender, trade, climate mitigation, adaptation and resilience, and biodiversity. Monitoring, results chain, indicators are discussed in the Management Case and in more detail in Annexes F and L on the programme Theory of Change and results framework, and approach to programme monitoring, evaluation and learning (MEL). These will be further developed on approval.
As we have seen in Indonesia and Ghana, the implementation of nation-wide compliance monitoring systems does lead to transformational shifts at scale. For example, effective compliance monitoring covers all of Indonesia’s (20+million ha) and of Ghana’s (1.5m ha) primary productive forests.
The ambition of FGMC2 is that over a 10-year period we will see forest stewardship secured across all productive primary forests in as many as 16 partner countries equating to about 40% of tropical primary forests[20].
[20] Annex F on the detailed Theory of Change and results described key indicators and the mechanisms proposed for monitoring progress.
What will FGMC2 do?
It will build from established partnerships under FGMC1, and expand in response to identified need to strengthen forest governance with up to 16 forest countries working with FCDO country offices, to:
- Build governance foundations to address the incoherence in policies and laws that reflect competing pressures on forest land including for Indigenous People’s rights, carbon, timber, agriculture and mining. It will also ensure coherence with national climate strategies that include forests as a significant element of NDCs and National Adaptation Plans.
- Support the development of national systems to verify compliance with agreed governance frameworks, for example with timber supply chains encouraging the development of national sustainable forest systems (NSFS) that verify compliance at scale and underpin UK VPA partnerships, where relevant;[21]
  [21] The UK has secured bilateral timber trade agreements (VPA) with Indonesia and Ghana and would be receptive to agreements with other countries once their NFSF are fully operational (VPA could be secured readily with Rep of Congo, Cameroon, Cote d’Ivoire, Liberia, Guyana, Honduras, Vietnam, Laos and Thailand.
- Help strengthen forest governance arrangements, supporting inclusive deliberative policy processes so that forests contribute to national development and climate change strategies and foster greater confidence with international investors and local business.
The programme will work with countries that, like the UK, consume and import commodities sourced from tropical deforestation and illegal land conversion. It will forge alliances for sustainable forest footprints in consumer markets that will:
- reduce the negative impacts on forests and poor people from risky investments; and
- promote responsible business practices in partner countries;
- encourage business and investors to remove illegal deforestation from their global supply chains and investments, and meet environmental social and governance standards of source countries;
- shut out illegally logged timber, together with other products sourced from illegal forest clearance.
International policy engagement will help to: (a) shape international norms and initiatives; (b) develop international market standards to promote responsible trade and investment; (c) enable partner countries to draw on their experience to support others in their forest governance reforms thereby amplifying outcomes and impacts; (d) encourage international policy processes to recognise the importance of forest governance for the sustainability of forest-linked investments; (e) establish an international forest governance hub of expertise that supports plurilateral action, fosters south-south exchange and galvanises a focus on improving forest land governance in donor actions; and (f) promote a level playing field in terms of who is at the international table and has access to information and evidence.
6. Dependencies and strategic decisions that have already been taken
Programme size
The intention to launch and fund FGMC2 with up to £500m of funding drawn from the UK’s International Climate Finance was announced as part of a package of support at COP26. The £500m UK funding package drawn from the £3bn International Climate Finance committed for nature and biodiversity will fund a second phase of the Forest Governance Markets and Climate (FGMC) programme over a 10 year period. This was announced at events on Nature Day at COP26 and at partner country hosted events launching pledges of support to Indonesia’s forests and the Congo Basin and IPLC forests pledges.
This Business Case, like the previous FGMC programme, has been designed and costed for a £500m 10-year investment, in line with the approved Concept Note which was announced at COP26. It frames a 10 year vision to support the transformation of national and international forest governance and market regulations. We are seeking Ministerial approval for the up to £500m, 10-year Business Case, with budget approval now for £220m over the next 5 years (2024-2029). We will revert to Ministers for approval of the remaining £280m tranche in 2028/29 following a review of progress. The five-year £220m commitment has been designed as a first tranche of the envisaged ten-year programme, but will achieve results within the first five years, even if the subsequent funding is not approved.
Programme duration
The programme’s vision extends to 2035. This reflects the 10-year programme time frame, justified by the time it takes to develop trusted relationships capable of dealing with the many interests and complex behavioural changes needed to bring about transformational change at global scale. It is also important for countries to know that they can count on long term support when they embark on challenging forest governance reform processes. Although reform processes take time, once institutional structures are in place with in-built incentives that are sustained, exiting is important.
Geographical focus
FGMC2 will work globally to shift international norms and rules linked to forests and forest product trade as well as focusing on forested developing countries, including in the large tropical forest basins in Southeast Asia and the Pacific, Central Africa and South America, as well as where there is strong potential for FGMC to support system-wide national scale governance reforms leveraged through trade or other market levers. The programme will contribute to the delivery of UK ICF pledges to fund forest protection and restoration in Indonesian (£350m), the Congo Basin (£200m) and Amazon region (£300m) as well as with IPLC forest stewardship (£163m).
- Component 1 will build from established partnerships under FGMC1, where there is significant interest to build from earlier support to address new governance challenges, in response to identified need and opportunity. Precise geographical scope will be finalised during inception and early years of mobilisation, but will include Indonesia, Ghana, Liberia, Republic of Congo, Guyana, Cameroon, Papua New Guinea, Solomon Isles, Laos and DRC (the country-specific focus is further described in Annex H partner country analysis and engagement plans). A further group of countries will be identified in the 2nd year of the programme following further scoping activity (these are described as “Tier 3” in Annex H).
- Components 2 will forge alliances with important consumer markets for forest risk products originating from tropical forest countries including China, India, Vietnam (as described in Annex I: Alliance country engagement). The focus of this component is generating the evidence and understanding to inform policies that support and incentivise the governance reforms in tropical forest countries.
- Component 3 will focus on international engagement that seeks to shape international norms and initiatives, including at Climate and Biodiversity Conferences of the Parties, to enable FGMC partner countries to draw on their experience to encourage and support other countries in their efforts to strengthen forest governance thereby amplifying outcomes and impacts.
7. Comparative advantage of UK support and engagement
The UK is well positioned to influence and drive forward international work on forests. It has a track-record of international action on tropical forests, working through diplomacy, trusted partnerships, and programmes to achieve its aims.
- FCDO has been instrumental in mobilising international efforts to tackle illegal logging and deforestation associated with agricultural commodities; and promoting trade and investment in legal and sustainable forest and other commodity production and strengthening sector governance foundations to create the enabling environment for investments.
- DESNZ (Department for Energy Security and Net Zero) has worked to ensure forests are included within international climate agreements and engaged in the development of the REDD+ emissions reduction framework and forest carbon markets.
- Defra has developed demand-side policy measures to ensure the UK market is aligned with the commitment to reduce deforestation associated with agricultural commodities and ensuring forests are included within international agreements on biodiversity conservation.
FGMC1 enabled the UK to lead international efforts to strengthen forest governance and combat illegal logging, forging bilateral partnerships and building common understanding in international markets. FGMC1 filled a niche in the donor-funding landscape with support mechanisms adaptable to work across geographies – linking demand with supply, and flexibility to expand or shift resources to complement efforts of other donors. FGMC1’s approach supporting different stakeholders through a variety of channels has helped foster political momentum for transformational change building understanding and the evidence base for such collaborations. FGMC1’s focus on supply and demand-side policies, generating evidence and empowering coalitions of interest, particularly from developing countries served to inform UK, EU, US, Chinese policies that encourage businesses to take responsibility for sourcing, and ridding illegal material from supply chains. Initiatives such as the FACT Dialogue has drawn heavily on FGMC’s evidence base and collaborative partnerships. This network of partnerships provides a strong foundation from which to expand efforts to transform forest sector governance in response to increased interest and demand from tropical forest countries.
FGMC2 will leverage the UK’s influence in this area and help deliver UK commitments made to the Sustainable Development Goals, on the provision of International Climate Finance, and on forests at United Nations International Conferences of the Parties (climate and biodiversity).
- Support towards the Sustainable Development Goals (SDGs), e.g. Goals 12 (responsible consumption & production), 13 (climate action), 15 (life on land), 16 (peace, justice & strong institutions).
- Delivering the UK’s international climate commitments, contributing to the target to double International Climate Finance (ICF) to £11.6 billion (FY 2021/22-25/26) including £3 billion on nature, of which £1.5 billion is on forests. FGMC2 funding is fully allocated to ICF contributing to its target for mitigation and adaptation and associated pledges.
- The delivery of Forest commitments and dialogue processes launched at COP 26 including the Glasgow Leaders Declaration on Forests and Land Use (GLD), the Forest and Climate Leaders Partnership (FCLP), the Forest, Agriculture and Commodity Trade (FACT) Dialogue, and the UK’s contributions to the Global Forest Finance Pledge, IPLC forest tenure pledge, Indonesia pledge, and Congo Basin Joint Donor Statement.[100]
  [100] https://www.gov.uk/government/publications/cop26-world-leaders-summit-on-action-on-forests-and-land-use-2-november-2021/world-leaders-summit-on-action-on-forests-and-land-use COP26 World Leader's Summit ,(2022) Action on Forests and Land Use
These international commitments align with the government’s aim to “create a world free from poverty on a liveable planet” and include:
- addressing illegality; helping communities to secure rights to the land and resources they depend on for their livelihoods; and helping to reform global markets to reduce deforestation and improve transparency. (2023 White Paper on International Development);
- addressing climate change and biodiversity loss reflecting that “climate change and biodiversity loss are important multipliers of other global threats and are guaranteed to continue to worsen over the next decade: six of the top ten risks for the decade ahead identified by the World Economic Forum relate to climate, the environment and nature. [101] The consequences are both acute and chronic, resulting in … significant setbacks to progress towards the SDGs.” (Integrated Review);
  [101] Global Britain in a competitive age (publishing.service.gov.uk) Cabinet Office, Global Britain in a Competitive Age, The Integrated Review of Security, Defence Development and Foreign Policy (2021)
- supporting actors in developing countries to develop systems to meet emerging global requirements (reflected in Strategic Sustainable Commodity Action Plan as recommended in the Global Resource Initiative (GRI);
- Responding to HMG’s ambition for a liveable planet, minimising the UK’s forest footprint, and promoting sustainable trade and investment as framed in the 25-year Environment plan. FGMC2 will contribute to this by supporting the implementation of UK international environmental and trade regulations, notably the FLEGT policies and regulations, UK VPAs, and the implementation of the UK’s due diligence regulations for timber and Forest Risk Commodities.
8. Complementarity with other UK and international support
FCDO’s IFU forest portfolio consists of two large centrally managed programmes working across multiple countries and regions. FGMC2 will work primarily in partnership with developing country stakeholders (governments, CSO and private sector) to support regulatory reform and strengthen forest sector governance and stewardship, and to tackle illegal practices that drive deforestation. Investing in Forests and Sustainable Land-use IFSLU2 works primarily with the private sector and small-scale farmers, establishing public-private partnerships to shift commodity production practices and catalyse investment.
The FCDO’s Africa Regional Climate and Nature programme provides support to the Congo Basin via the Central African Forest Initiative (CAFI). CAFI works with Congo Basin countries in support of their climate and national development objectives and national investment frameworks that decouple development from deforestation, providing resources to implement priority actions. The Africa Region’s Congo Basin Forest Action Programme (CBFA) will support sustainable development of local communities at grassroots level across the Congo Basin, with a focus on community forestry. It will empower forest communities and seek economic incentives to encourage behavioural change in landscapes experiencing high rates of deforestation. FGMC2 will be highly complementary to these initiatives. Discussions with CAFI and CBFA leads in FCDO have already identified areas of complementarity. In Indonesia, FGMC2 will rekindle UK engagement with the Forests Ministry, complementing Post-led programmes working on land use planning and investing in nature.
We also expect to build on the wider benefits of FGMC’s experience, relationships and networks helping to provide an operating environment for other ICF forest programmes by building trusted relationships with partner governments and civil society, where partners feel genuine ownership and agency. The transformational governance outputs (rights, laws, standards, policies, transparency and third-party civic society engagement, compliance assurance systems (TLAS)) established and enforced under the programme are difficult to measure directly. In addition, as well as the direct benefits derived from reforms, the introduction of global standards, greater transparency and national regulations for responsible supply chains will help create the foundations for effective and lasting results in forest investment programmes, so results of FGMC-supported governance reforms should improve the effectiveness of ICF-financed forest investment programmes (such as IFSLU2, Mobilising Finance for Forests programme).
FGMC2 will strengthen the coherence between forest carbon governance and other forest uses, complementing DESNZ support for REDD+, which seeks to incentivise government action to stop deforestation through results-based payments as well as its pioneering work developing forest carbon markets. Over the past year the FGMC team has worked with DESNZ colleagues responsible for carbon initiatives (LEAF, AIM4Forests, UNREDD, REDD+ Early Movers) to share FGMC experiences and identify areas for complementary intervention, particularly in relation to the role of multi-stakeholder deliberation to establish nationally owned policy processes. FGMC2 will catalyse processes that will help build the legitimacy of, and IPLC support for, forest carbon initiatives and REDD+ results-based finance in a similar way to how this has been done for the management of productive forests.
FGMC2 will continue to provide support to developing countries keen to strengthen their national systems of forest governance, in the context of FLEGT policies. This support will complement Defra’s policy leadership and Posts engagement in FLEGT Voluntary Partnership Agreements for the timber trade as well as UK FLEGT policies (such as UKTR and public procurement) which serve to create positive incentives for the national systems of certification. FCDO country offices will help leverage the impact of programme to reduce global deforestation, by facilitating the institutional relationships for engaging in national forest and climate strategies. The programme proposes to finance several experts at Post to strengthen HMG capacity to engage and support national forest sector policy reform processes.
FGMC2 will align with and complement other donor-funded initiatives. Germany, Norway, France, the Netherlands, Japan, Australia, New Zealand, S. Korea, the EU, USA, Sweden all support relevant work focused on sustaining forests, forest governance, support for IPLC forest tenure security, sustainable trade and supply chains and forest carbon governance. FGMC1 established effective mechanisms for cooperation and coordination at country-specific and international levels, including through joint financing. FGMC2 will build on these relationships to foster common approaches and cooperation for greater impact at scale. FGMC2 will establish an International Forest Governance Hub, as a centre of expertise that serves tropical forest country-led initiatives. Initial scoping has identified a strong ask from developing countries for such a facility. The FGMC team will work with the interest expressed by long-standing partner European Forest Institute to establish such a facility and explore options with other donors after the Business Case has been approved. Such a Facility could serve as a vehicle for future collaboration with other donor partners, including other HMG Departments.
9. Risks and Assurances
Climate and Environment:
The programme aligns with the Paris Agreement and will deliver high positive impacts for climate, nature, and biodiversity, in line with the Programme Operating Framework (PrOF) All programme spend will be ICF contributing to the nature and forest spending commitments announced at COP26.
The programme will contribute to both climate adaptation and mitigation. FGMC2 will, where indicated as a priority, assist partner countries establishing strong forest governance foundations that help them deliver their Nationally Determined Contributions (NDCs) where nature-related actions help deliver their adaption and mitigation strategies. Relevant ICF KPIs are included in the results framework. As indicated in the Management Case management arrangements will ensure sufficient climate and environment expertise and input are accessible to deliver the programme and identify and mitigate any potential risks.
A high-level Climate and Environmental Risk screening is provided in Annex B, which assesses that FGMC2 carries a moderate climate risk and a low environmental risk. As a programme focused on policy developments at national and international levels, its specific environmental risks cannot readily be linked to any specific landscape or people. However, given that the programme purpose and actions focus on generating evidence to inform and strengthen environmental planning and regulation and helping stakeholders orient and align their efforts to address environmental and social harms it is highly likely environmental impacts will be positive.
Since the programme’s focus is on supporting development of national policy and regulation for strengthened forest land governance, mitigating measures will predominantly include the assessment of climate and environment risk within the policy formulation process. This could include ex ante analysis of policy implications for climate and environment risk. A similar process is envisaged to assess potential impacts of policy reform on women and poorest forest dependent people. These mitigatory measures will be integrated into the Terms of Reference for delivery partners, will be factored into screening criteria for future accountable grants. and will be routinely part of risk assessments and mitigation measures. Measures to monitor and manage these risks/safeguards are documented in the Management Case.
Gender, Inclusion and ‘Leave no one behind.’
Climate change disproportionately impacts the poorest and most excluded. Women and girls, and Indigenous Peoples and Local Communities (IPLCs) are disproportionately impacted by environmental degradation and typically have less ability to cope with shocks and stresses. The disproportionate impacts of biodiversity loss on women and girls include higher domestic work burdens and exposure to gender-based violence, loss of income and declining health.[102] IPLCs, women & girls are also disproportionately less able to engage in and influence policy decisions which affect their lives, reinforcing this cycle. [103]
[102] Booker et al. 2022. Women, girls and biodiversity loss: an evidence and policy review Department for Environment Food & Rural Affairs, The Gendered Impact of Biodiversity Loss and Environmental Degradation - BE01106 (2022)
[103] Convention on Biological Diversity - Addressing Gender Issues and Actions in Biodiversity Objectives
FGMC2 will continue and deepen the well-documented approach of FGMC in improving and institutionalising stakeholder participation in government and private sector decision-making processes. It will deepen and broaden inclusion in forest and land governance partnerships that had previously excluded young people, women, IPLCs, and other forest user groups, while being sensitive to political economy and cultural perspectives. [104] This will involve discussion of social safeguards based on early analysis of gender and inclusion issues. The Appraisal case sets out the steps to be taken to build and refine strategies to actively address gender inequality and social exclusion and will ensure that the programme is fully compliant and acts in the spirit of both the International Development (Gender Equality) Act and Equality Act (Public Sector Equality Duty).
[104] Speechly 2020: Inclusion in FGMC FGMC internal report. p5/6
Recent ICF guidance on gender and social inclusion states that “all new ICF programmes should be designed to score at least a “1” against the OECD Gender and Equality Marker”. [105] While gender has been and continues to be a priority for FGMC, it is not considered a stand-alone goal. However, there is clearly a need to capture the important gender-based results across the four priority areas above if the proposed score is to be reached. This will be undertaken through the application of gender indices that assesses the degree to which gender opportunities and risks have been supported or promoted within the context of national and international policy-making processes. This is discussed in more detail in Annex C: FGMC 2 approach to gender and inclusion.
[105] International Climate Finance. (2022). Gender Equality and Social Inclusion Guidance. HM Government.
Safeguarding
FGMC2 will focus on policy and technical interventions; first tier partners will not be working directly with communities, making this programme relatively low risk in terms of sexual abuse, exploitation, and harassment (SEAH). As with FGMC1, it will be a priority to ensure that each of the directly funded partners are compliant with HMG safeguarding requirements, having whistle-blowing and anti-harassment policies and understand their responsibility to take all reasonable steps to prevent sexual exploitation, abuse and harassment by either their employees or downstream partners, and to report any incidents immediately.
Through its work to support the development, implementation, and monitoring of social safeguards in a wide range of geographies and sectors, there will be opportunities for FGMC2 to advance and elevate global awareness and action on safeguarding, including the prevention of exploitation and abuse within forestry and other FRC sectors with particular regards for safeguarding IPLCs. This may be taken forward by including safeguarding as a priority theme for the International Forest Governance Hub. FGMC2’s approach to safeguarding will be informed by analysis based on experiences in FGMC1, to be completed during the first phase of the programme.
Conflict sensitivity, fragility and peacebuilding
There is good evidence that the deliberative multi-stakeholder processes that are central to the VPA process, and to FGMC’s approach, have had positive impacts on governance in some fragile and conflict affected countries. [106]Based on VPA experience so far, the process is more likely to be effective in countries at the more stable end of the spectrum, rather than those facing a risk of armed violence, or undergoing armed violence, or where post-conflict peace agreements have not taken hold - although there is evidence of some successful progression of VPAs despite ongoing conflict. [107]
[106] Based on analysis in Vernon/Triple Line (2020)
[107] If one applies the broader concept of fragility and includes countries like Ghana and Indonesia in the Warning category of the Fragile States Index (The Fund for Peace, 2020). Note that this analysis is based on the Transformational Change Index.
FGMC has a high level of awareness of the political economy, and it pays great attention to incentives. The next stage of FGMC2 will involve integrating a peace and conflict lens into its planning, by considering the links to peace and conflict dynamics, the opportunities for building peace and the risks of doing harm.
There are opportunities to enhance conflict sensitivity and capitalise on peacebuilding opportunities in the next phase of the programme. Approaches could include systematic inclusion of conflict in training, terms of reference, programme monitoring, and further engagement of conflict and peacebuilding expertise at the appropriate levels. [108] We will also work with Posts to ensure the programme does not contribute to worsening conflict and, with wider Government stakeholders, undertake and share conflict analysis and information.
[108] DFID Stabilisation Unit, (2019) The UK Government’s Approach to Stabilisation: A guide for policy makers and practitioners; DFID, 2016, Building Stability Framework
Counter terrorist financing and anti-money laundering:
FCDO does not fund proscribed organisations, nor designated individuals or entities subject to financial sanctions in the UK. FCDO is committed to the prevention, deterrence and detection of terrorist financing and money laundering. The programme will apply a zero-tolerance approach towards terrorist financing and money laundering. Due diligence and monitoring will be applied to ensure compliance with this policy. All implementing partners will have passed due diligence or fiduciary risk assessments and have a strong track record of delivery.
Public Sector Equality Duty
FGMC2’s approach to public sector capability and delivery specifically focuses on inclusion as a key aspect of the quality of public sector institutions. The programme will operate in line with Public Sector Equality Duty (PSED) and the requirements of The Equality Act 2010. This includes due regard to the need to eliminate prohibited conduct, such as unlawful discrimination, harassment and victimisation; advance equality of opportunity between people who share a protected characteristic and people who do not share it; and foster good relations between people who share a protected characteristic and those who do not share it. . Implementing partners will be expected to uphold standards and principles relating to non-discrimination and no harassment or victimisation, as well as international human rights provisions. This will be addressed through due diligence on partners, operating policies, and monitoring.
Partnership Principles:
The programme is designed to be consistent with the four partnership principles of a commitment to reduce poverty, respect human rights, strengthen financial management and public accountability. Programme funds will be delivered through established international organisations or contracted service providers and not directly through governments and to that extent the Partnership Principles do not apply. Nonetheless the programme is committed to establish close engagement with partner Government and ensure that any capacity building instruments are designed and overseen by them. Should any direct bilateral aid be provided, the programme team will ensure the Partnership Principles are applied in any agreements and followed closely.
Risk
Risk appetite for the programme overall is Moderate. There is appetite to take risk with policy and programme delivery, using the programme to establish new ways of addressing underlying governance and market failures. There is no tolerance for safeguarding and fiduciary risk. There is willingness to take on and manage reputational risk, so long as that does not harm the overall programme licence to operate. Further information on risk and escalation is set out in the Management Case below.
## Appraisal Case
The Strategic Case outlined the rationale for FGMC2, and this Appraisal Case considers how best to design and deliver the programme to meet this need and deliver the anticipated outcomes and transformational impacts (as indicated in Section 5 of the Strategic Case). Two options appraisals have been performed to answer connected but distinct questions:
- Strategic options appraisal: Which set of interventions best serves the need and delivers the outcomes and impacts specified in the Strategic Case?
- Delivery options appraisal: What delivery approach - working with which types of delivery partners and instruments - are best suited to delivering the interventions envisaged?
This section provides a summary of these appraisals, the design rationale and evidence that inform the proposed programme actions, articulates the programme’s Theory of Change, identifies the best suited delivery approach and delivery instruments, and assesses the value for money of the preferred option.
The detailed analyses underlying these summaries are presented in Annex D (Strategic Appraisal) and Annex E (Delivery Appraisal). They adhere to guidance set out in the Treasury Green Book and PrOF Guides. The rationale for the preferred option and Theory of Change is further elaborated in Annex F (ToC and results framework) drawing from the analyses of our experience with FGMC1 that has helped to inform the way forward. The structure of the programme and underlying assumptions are also set out in Annex F, together with the instruments to measure and track progress. A detailed logical framework will be prepared during the inception following approval of the Business Case.
### Strategic options appraisal summary
We examined feasible intervention options for delivering the forest stewardship outcomes set out in the Strategic Case at two levels: firstly, reflecting on the intervention approach for the programme, and then secondly, drawing from experience of the first phase of FGMC, we assessed its thematic focus reflecting choices about programme design, needs, demands on FCDO’s financial and human resources.
The appraisal case considers whether the approach FGMC1 took to addressing the drivers of illegal logging and broader tropical deforestation remains valid or should be modified in the light of experience, new evidence, the changing context, the expanded level of urgency and need, and whether it is commensurate with UK leadership in international cooperation. The first level of this appraisal assesses FGMC1’s established approach against alternative ways to shift demand and supply. This detailed analysis is presented in Annex D.
The options are appraised using evidence-based SWOT analysis undertaken in reference to the expected outcomes and impacts specified in the Strategic Case drawing heavily from evidence from over 10 years of global action in this domain. Three centres of expertise have helped to curate information serving to build global understanding of the challenges of tackling illegal logging and establishing effective forest governance. Through FGMC grants Chatham House built a forest governance policy domain and has convened annual policy dialogue for more than a decade; The European Forest Institute’s (EFI) International Partnership Facility (IPF) curates information from FLEGT VPA countries; the Food and Agriculture Organization (FAO) and FGMC-backed FLEGT programme supports CSOs and small businesses through grants. The FGMC1 programme team has established a comprehensive Knowledge Management System to curate information generated through FGMC.[22]
[22] The FGMC Knowledge Management System is not yet in the public domain but will be available under the new FGMC2 programme. Access can be provided on request.
The options were assessed against Critical Success Factors (CSF) established for HMG investments (Treasury Green Book) namely: Strategic fit with UK priorities; Potential Value for Money; Potential affordability; Potential achievability; Potential Adaptability; Likelihood of contributing to transformation change and Inclusion principles. The key success factors considered for achieving FGMC2’s strategic objectives included: the fit to FGMC approach; address features necessary for national-scale governance change; adaptability to new threats and opportunities and the potential for driving fair international norms. The detailed criteria considered for each factor is set out in Table 1 of Annex D.
Consideration of the intervention options reflected on the factors highlighted in the Strategic case, drawing on the successful approaches deployed in FGMC1, including:
- Protecting intact forests, managing already disturbed forests, and restoring forests and tree cover, including around mines will contribute to climate mitigation and adaptation.
- Despite progress in reducing the volume of illegal tropical timber traded internationally, where governance remains weak or corrupted, illegal logging and illegal forest land clearance carries on.
- Asian markets with the growth in demand, increasingly provide a market outlet for illicit material.
- The rise in consumer market measures to combat tropical deforestation is creating the need and demand for greater transparency and national approaches.
- Increased interest in forest carbon initiatives, including significant UK engagement in REDD+ instruments and carbon market processes[23], place consideration of forest carbon governance and its associated risks, especially for IPLC as a IFU priority.
  [23] For example - Forest carbon partnership facility, REDD+ Early Movers, Lowering Emissions by Accelerating Forest finance (LEAF) Coalition, Aim4Forests to strengthen forest carbon monitoring results and verification systems in forest countries, support to the Voluntary Carbon Market Integrity initiative and the Integrity Council for the Voluntary Carbon Market.
- Increased interest in biodiversity and strategies to better pay for nature’s ecosystem services.
- Palm oil, beef, soy, cocoa, and rubber production together with increased interest in minerals have joined illegal timber as important global drivers of tropical deforestation.
- Some commodities affect forest livelihoods in complex ways. Different governance approaches and market mechanisms may better align benefits to poor people (especially IPLC).
- Development of national climate strategies have advanced in many countries with greater opportunity to adopt a more comprehensive approach to multiple and sometimes conflicting forest uses with a focus on forest stewardship.
- In some country contexts, established networks, coalitions of practitioners provide a strong basis from which to further support forest sector governance reforms building from best practice to address sensitive new challenges such as illegal mining in forests linked to organised crime.
- FGMC1 has firmly established that inclusive processes deliberating to reframe forest policy, law and enforcement have demonstrated the potential to support transformation in forest sector governance.
Sector-wide forest-land governance reforms are highly political with important links to local conflict, therefore sensitive engagement, and flexibility to work with political momentum requires dynamic delivery options. Drawing from FGMC1 experience, we reflect on ways to address the challenges to sustainable forest stewardship, notably addressing additional threats to forests and opportunities to better incentivise stewardship at increased scale.
The first level of the strategic options appraisal considered feasible intervention approaches for FGMC2’s intended scope and action areas:
- Option 0: Do no more. No funding is allocated for the delivery of FGMC2.
- Option 1: Business as Usual addressing illegal logging and timber trade, and so working with demand and supply measures. FGMC2 would remain focused on existing partnerships as FGMC1 (fostering south-south learning in more countries & international policy engagement)
- Option 2: Producer country focus - only supply side action. This would support governance reforms in more tropical forest countries to address threats to forests arising from illegal logging and commodity production. It would support no action at international level if other programmes and processes deliver the necessary international political signalling.
- Option 3: International policy and leverage – only demand side action: As a global programme focus on the international dimensions of FGMC1 focusing on shifting international markets and influencing international drivers including international standards for traded commodities and significant market players (e.g. India, China, Vietnam). This assumes that external levers and evidence will deliver change on the ground in tropical forest producer countries.
- Option 4: Securing forest stewardship by combining scaled-up action in more forest countries with international markets linking demand and supply: partner with more tropical forest countries for greater impact addressing critical threats and opportunities to secure forest stewardship, with international action that incentivises and drives transformational governance and market shifts. This is the preferred approach.
The strategic options appraisal considers further choices at a second level examining the thematic focus for FGMC2 to address additional forest threats and opportunities that were described in the Strategic Case going beyond timber and illegal logging. In all four of these scenarios FGMC2 would scale up efforts to partner with more countries (up to 16 are budgeted for) building from the achievements of the first phase, enabling us to respond to increased interest and ambition. In FGMC1, we focused our TA and capacity building with 5 partner countries, while working with more[24] through grants and with other donors (this was a result of donor coordination efforts). This second level in the strategic appraisal considered whether FGMC2 should remain focused on timber trade and forest production or shift the focus to take into consideration governance reforms needed to better regulate forest clearances and shifts to other land uses, or to address the governance of the forests’ rising ecosystem values that may be created through new carbon and biodiversity finance instruments. The analysis informs programme design and delivery options.
[24] Cameroon, DRC, Gabon, Central African Republic, Cote d’Ivoire, Myanmar, Vietnam, Laos, Honduras, Brazil, Thailand
Options considered in the strategic options appraisal for FGMC2’s potential thematic focus included:
- Option 4.1: Forest degradation. continue to build from FGMC1 to focus on illegal logging driven by the national and international timber trade.
- Option 4.2: Forest loss: illegal deforestation. broaden from FGMC1’s focus on timber to additionally address governance challenges associated with illegal deforestation that is driven by the international commodity trade, including illegal clearance for mining and agricultural commodities.
- Option 4.3: Forest and biodiversity loss broaden the focus to support efforts to build strong governance foundations necessary to secure forest carbon and ecosystem service values that help deliver forest conservation building from FGMC1’s focus on national timber governance.
- Option 4.4: Forest stewardship. focus on tackling significant threats and opportunities for improved forest sector governance, working with international levers to incentivise long-term forest stewardship. This is the preferred option.
Drawing from Green Book and PrOF guidance, these strategic options were appraised using evidence-based qualitative analysis against the desired programme outcomes set out in the strategic case and a set of Critical Success Factors (CSFs) that are specified in Annex D (Strategic Appraisal). It is based on available evidence, including detailed global and country-by-country review of international commodity trade data, spatial land use data, as well as governance indicators. It weighs recent evidence on the gender and social inclusion aspects of improving governance of forests. It considers the most recent peer-reviewed science on the global forest carbon by the IPCC, as well as the independent Dasgupta review on the economics of biodiversity. It draws from lessons learned from the first phase of the programme.
The appraisal progressed in two stages, first reflecting on options with different scale and approach to addressing the challenges framed in the Strategic Case, and in a second stage assessing options that build from FGMC1’s experience with timber supply chains, to consideration for broadening the focus to a wider set of governance challenges including illegal mining, illegal forest clearance and establishing the governance foundations for investments in forest ecosystem values.
The appraisal concluded that Option 4.4 offers the optimal scope and mix of programme opportunity supporting a multi-faceted strategy. Option 4.4 continues with FGMC’s support to international efforts to stop illegal logging, alongside new dimensions focused on measures to i) reduce illegal forest land clearance for agriculture and mining and ii) strengthen multi-purpose forest governance that integrates forest carbon and biodiversity values together with wider forest uses helping to secure long term forest stewardship, especially for IPLCs. Currently, programmes and policies tend to manage forest land in compartments (with Units working on biodiversity, distinct from those working with carbon markets, those working with communities, with farmers, with loggers, etc.). In addition, international initiatives tend to work along supply chains (cocoa vs timber vs palm oil) linking to trade norms and expectations, or finance objectives streams. While the external market and finance levers may help create the drive for governance reform, they may further lock in compartmentalised and incoherent policies. The broadening of FGMC2 scope, to be anchored with a forest stewardship ambition, positions the programme to foster greater coherence across forest land use policies and thus be more likely to achieve impactful outcomes.
The multi-faceted strategy will address the dynamic spectrum of opportunities and threats to tropical forests and is most likely to achieve the necessary transformational change for lasting forest stewardship. While the breadth to tackle different challenges in different places will enable the programme to build from experience, networks and coalitions to help stakeholders address new governance challenges, it will take care to adopt a laser-focused strategy to identify where we might add value and foster change where other actors (donors, government services or traders) are not already engaged. This broad focus is not expecting to engage on all focal areas in all countries (e.g. in Ghana the focus might be illegal forest mining, in Liberia the governance and rights of IPLCs, in Indonesia integrating forest carbon with timber, etc). It concludes that FGMC2 should continue to work with both national and international levers.
Overall, option 4.4 is the preferred strategic option, offering the optimal scope and mix of programme components to build from the experience and coalition of interests developed through the first phase of the programme to deliver the objectives specified for FGMC Phase II. This will deepen the relationship in some countries and add new country partnerships and, in some instances, broaden the commodity focus beyond timber strengthening connections to consumer market reforms that seek to exclude commodities produced from illegally cleared forest lands. It is the intention that the programme will focus on the most pressing challenges in a particular country context. Illegal logging will remain the main focus of FGMC2. In some countries the action will remain focused on regulating the timber sector because there remains much to do, but in others, national stakeholders may draw from their FGMC-backed experience to address other threats to forests. More detail of how activities will be phased and the process by which they will be assessed across countries are set out in Annex H (Partner country analysis and engagement plans). Detailed discussions with potential partner countries will be initiated upon approval of the Business Case. The analysis concludes this option is optimal:
- It will retain FGMC1’s successful combination of demand and supply measures, and action at national and international levels that offer high potential for transformational change as indicated in Annex A on the FGMC Approach.
- It will build on the successes of FGMC1 working in the timber sector to broaden the scope of the programme to equip it to better address the varied spectrum of forest governance challenges faced in specific country contexts. While FGMC1 was focused on timber and the international timber market levers, because forest governance reforms must address a range of forest uses, the programme partners already were transferring practice to other domains. The broadening of the FGMC programme will mean that we develop the instruments and tools to foster and support that wider read across.
- A new focus on forest stewardship will necessarily encourage stakeholders to address policies and strategies in a more coherent way, to draw from the political energy in one domain to drive forward reforms that are anchored in the real choices that forest communities, forest managers make in terms of the diverse and sometimes competing pressures on forest lands.
- This approach does not necessarily make action more complicated, in some contexts it may simplify action and have significantly greater impact. Since forest governance reform isn’t necessarily linked to specific supply chains, it will be more efficient to support forest governance reforms, especially in domains related to IPLC rights and responsibilities across supply chains/initiatives that are rather linked to forest lands and their governance. For example, forest-linked rights and benefit sharing arrangements for IPLCs for forest carbon deals should relate to policies and agreements on rights and shares associated with timber or other commodities produced from the same forests.
- It will enable the programme to sustain strong partnerships to address new challenges, while deploying resources to meet growing demand for long term partnership and support from countries where FGMC1 “footprint” was limited. Under FGMC1, we focused TA support and political engagement to a few (5-6 countries depending on the time in the programme), while we engaged “remotely” with others through other instruments that enabled the programme to have quite broad influence and scope (i.e. joint support through other donors and multi-donor facilities as well as accountable grants). Initially this strategy was a feature of the FLEGT Action Plan where European countries agreed to share the effort in partnering with tropical producer countries. The scaled-up resource for FGMC2 will enable further partnerships with specific tropical countries where bilateral engagement would be opportune and the same time as allowing the programme to have global coverage and impact through opportunities to co-finance initiatives that further the global forest governance agenda.
- It will enable the programme to target the specific drivers of deforestation and threats to forests in particular countries, focusing on creating the enabling policy conditions, often in challenging contexts where corruption and local conflict in forest land uses threaten on-going forestry reforms, and to respond to international market shifts.
- It will enable a substantial scale up of action to meet the growing demand for support, motivated by shifts in international markets requirements that extend beyond timber, and to build on the success of countries like Indonesia and Ghana in transforming forest management for their timber trade.
- It will increase opportunities for empowerment and inclusion bringing deliberative processes into addressing a range of FRCs, linked to some of the biggest issues affecting the poorest and/or most marginalised people within forest communities.
- It will complement and support the objectives of other HMG forest programmes by working with partner governments on reforms that create enabling conditions for investment.
Based on this assessment, Option 4.4 is advanced to the delivery option appraisal.
 Delivery options appraisal summary
This assessment considers the delivery approach best suited to delivering FGMC2 interventions (Option 4.4 above), i.e. supporting a scaled-up programme that works across more countries, expands beyond timber to other commodities, and broadens its international policy engagement to drive global shifts that help establish lasting forest stewardship.
FGMC2 will support actions at national and global levels which will require bilateral and international structures that deliver political engagement, flexible and adaptive programme management and extend programme influence beyond FCDO spend. Delivery mechanisms will support varying degrees of action across as many as 16 tropical forest countries, engage with important consumer market countries, and enable both bilateral engagement (partnership) and the availability of independent advice to tropical country stakeholders. The programme will expand the number of countries it engages with gradually. This will entail building from the 5 focal countries (Guyana, Ghana, Indonesia, Liberia, RoC) partnered with under FGMC1 and deepening our engagement with others where FGMC1’s support was less concentrated and action was mainly supported through accountable grants (e.g. Cameroon, Gabon, DRC, Vietnam, Cote d’Ivoire, etc) or where we were engaged indirectly with other donors (e.g. with Germany in Cameroon, Laos and Vietnam). Potential threats to forests and opportunities to do more, will be assessed on a country-by-country basis. FGMC2 will not work in all countries on all potential forest threats and opportunities simultaneously. The process for identifying where to work and what to work on is set out below with greater detail and in Annex H (Partner country analysis and engagement plans).
FGMC1 worked through FCDO country offices, other donors, civil society, not-for profit organisations and service providers using suitably tailored instruments. It found that delivery through a variety of partners improved efficiency and flexibility and spread risk. This also proved an effective means to amplify the reach and influence of the programme without additional spend.
Successful programme implementation will require delivery arrangements that facilitate political engagement and effective cooperation with Government, civil society and private sector stakeholders. Delivery arrangements need to be flexible and responsive, to be able to create, identify and seize opportunities and work effectively in partnership in a mix of country contexts, support flexible and adaptive management and establish a mechanism that helps build international support for a forest governance approach.
We consider 4 options for delivering the preferred programme scope (i.e. option 4.4 above), the required delivery structures and the components of FGMC2. The four delivery options considered are:
- Option A: The Business Case objectives are delivered through a single multilateral partner or an organisation within the United Nations. In this scenario, FCDO would deal with one institution responsible for management and delivery, freeing up time for the FCDO team to engage in policy work, but may struggle to engage politically with trade and market instruments.
- Option B: objectives are delivered by FCDO in-house using core staff. In this scenario, FCDO would deliver all aspects of the programme relying on the existing ECED Programme Team under a mixture of commercial contracts and accountable grants best suited to delivering different elements of the programme with insourced/programme financed staff at Posts supporting action in some countries. This option would place considerable strain on FCDO resources.
- Option C: objectives are delivered through one umbrella outsourced commercial delivery partner, which would act as programme manager mobilising a combination of accountable grants and contracts to organisations best suited to delivering each action. This would minimise FCDO programme management to overseeing one agreement and free up time for the FCDO team to engage in policy dimension, but this option would disconnect policy engagement from programme ground realities.
- Option D: objectives are delivered through a mixed delivery model tailored to both the political and technical nature of the programme and realities on the ground in each country, building on the approach refined through FGMC1. This combines the expertise of different suppliers, gives FCDO control over costs and performance, makes use of FCDO staff, centrally and at Post, where there is existing capacity and considers FCDO programme funded posts where needed and resources are available, to support UK influencing and partner engagement.
Option D, as proposed, would entail 3 commercial contracts, 1 MOU with an international organisation (EFI) that would serve to establish the outsourced monitoring and oversight and multi-country delivery instruments. The three contracts are:
- An outsourced programme management strategic support team (PMSST), which effectively “runs the programme” working closely with FCDO providing strategic oversight, ensuring coherence, administering the accountable grants programme and undertaking programme wide MEL functions.
- A Facilitator service, managing impartial facilitators in multiple countries to support multi stakeholder deliberations, at the invitation of government. Management of this contract by FCDO is important in reassuring partner country governments given the political nature of the work.
- A technical assistance portfolio manager (TAPM) to procure and manage all long term TA project contracts with focus countries under one contract, where these were previously managed directly by FCDO. This will allow more time for the FCDO core team to engage in national and international policy processes.
An MOU with the European Forest Institute (EFI) will provide resources for the creation of an International Forest Governance Hub, which will attract other donor finance and enable impartial high quality advice to be made available to countries beyond those receiving focused support from FGMC2.
In addition, the proposal makes provision for potential cooperation agreements with other donors (MOUs) where cooperation would be efficient for our partners while also influencing other donor action.
Learning from FGMC 1, the diversity of partners supported through different delivery routes helped to foster coalitions of practitioners, build capacity and stimulate innovations (Box 7 below). It provided flexibility in delivery that helped mitigate risks and adapt to new opportunities. FCDO retained direct management responsibility for the more politically sensitive tasks as well as engagement through MOUs with international or donor organisations. For these reasons - this is the preferred Option for FGMC 2.
Like the strategic intervention options, the delivery options were assessed against CSFs drawn from Green Book and PrOF guidance. The Critical Success Factors (CSF) and detailed delivery appraisal are set out in Annex E (Delivery appraisal). The options were assessed against CSF established for HMG investments, namely: Value for Money / Cost drivers; Supplier & partner capacity and capability; FCDO capacity and capability; Potential adaptability; Control over risk and delivery; Timing and resource requirements; Potential achievability; national ownership. The detailed criteria considered for each factor is set out in Tables 2-5 of Annex E. A summary is presented in Table 2 here:
Table 2 - Summary table of delivery options appraisal against FGMC2 critical success factors
:		A	B		C	D
CSFs	Potential Value for Money / Cost drivers	2		4	3	3
	Supplier & partner capacity and capability	2		3	3	5
	FCDO capacity and capability	4		1	4	4
	Control over risk and delivery	3		4	3	4
	Timing and resources	1		1	3	3
	Adaptability	1		4	3	5
	Achievability	2		2	2	4
	National ownership	1		3	2	4
	Summary	16		22	23	32

Scores: 1 = unsatisfactory; 2 = weak; 3 = satisfactory; 4 = strong; 5 very strong
The assessment draws strongly on the experience of FGMC1 that worked with different types of delivery models over its 12 years (Box 7). This FGMC1 experience, combined with the latest PROF guidance, informs the choice of assessment criteria. Supporting complex, sector governance reforms has benefitted from a delivery strategy that places national stakeholders in the driver’s seat of policy development, that has focused on impartial facilitation of the process with support focused on building capacity to engage and an evidence base to inform decision making. This has avoided the problem of a UK-financed project team in country being seen as the driver of reforms. Therefore, “likelihood of national ownership” is an important success criterion for consideration.
Options A and B are discounted as some CSF variables are deemed unsatisfactory, suggesting they would not be appropriate without significant change in the Business Case strategy and objectives.
As set out in detail in Annex E (the detailed analysis for the Delivery Options Appraisal) the appraisal concluded that Option D is the preferred option for delivering FGMC2 and has been assessed to deliver the best possible outcomes.
Box 7 FGMC1 delivery experience and lessons for FGMC2 / Phase I was managed over 12 years by an SRO and Programme Manager, with advisory support and several programme-financed roles in strategically placed positions in the EU, Indonesia and China. / At the outset of FGMC1, accountable grants, MOUs with international organisations and various Supplier Contracts providing TA to forest countries were all managed directly in-house by DFID. However, as the programme grew in scale, direct management of every accountable grant and TA contract proved untenable with the HR available to the central DFID team resulting in some projects being shifted to management at Posts with capacity (Beijing and Jakarta). The most significant development was the introduction of an outsourced programme management support team (PMSST) working alongside FCDO to improve efficiency, manage the programme’s Accountable grants (20+ grant agreements), ensure coherence across all delivery partners against the programme’s theory of change, and carry out monitoring, evaluation and learning activities across the whole programme. / This PMSST was key to the success of FGMC1 because it freed up the time of FCDO staff from carrying out many administrative functions, to enable more effective performance and strategic oversight, and increased capacity to engage politically and internationally. A close working relationship with FCDO enabled significant delegation to the PMSST, whilst FCDO retained decision making. The PMSST, with a team of 5 technical experts provided specialist advice along with grant management. They were better able to support governance reform processes in various countries and to orient and shape accountable grants to complement the wider programme thereby improving learning, coherence and influence. A pool of on call experts were able to help the programme respond quickly to requests for advice to inform policy development processes. This expertise greatly improved the FCDO’s oversight and decision making. / It was through this outsourced advisory and management service that FCDO was able to oversee the programme with a small team to cover what can appear to be a complex and large programme. FGMC 2 will continue this model, with a larger PMSST to cover the wider geographic spread, with wider technical capabilities within a pool of experts to cover the additional scope of the programme (such as on forest carbon market governance). In addition, the FCDO has increased its staffing level compared to FGMC1, with the addition of a full time adviser and will draw on the services of up to 7 programme funded posts if approved. / Under FGMC2 further streamlining will occur by outsourcing most TA contracts in addition to the Accountable Grants Scheme. FCDO will directly manage 4 instruments. This will include 1 technical assistance portfolio manager contract, 1 outsourced management contract (the PMSST), 1 MOU with the international organisation European Forests Institute and 1 Facilitation service contract, which due to the political nature of the work, is best managed by FCDO. / FGMC2 aims to expand the number of countries it partners with. FGMC1 already has experience of working in close partnership with five focal countries (Guyana, Indonesia, Ghana, Liberia and RoC), and a further 7 through the multi-country approach of the accountable grants programme and other instruments (Cameroon, Gabon, DRC, CAR, Cote d’Ivoire, PNG, Laos). / It is expected that FGMC 2 will be able to mobilise quickly in the 5 legacy FGMC1 focal countries. Scoping has taken place in a further 5 (Cameroon, PNG, Solomon Islands, DRC and Laos) where work will be able to commence more gradually in response to demand. / The remaining (potentially up to 6) producer countries will be confirmed once the programme is up and running, instruments are established and scoping can take place, likely not until year 3. This gradual phasing ensures that workload is not overly concentrated from the outset and provides opportunity to test the ability of the delivery mechanisms to manage broader scope and more geographies.

Figure 6 below sets out the structures for delivering FGMC2. This is described in more detail in the Management Case. Of note is the role of the PMSST as part of the FGMC core management team alongside FCDO. As for FGMC1, the close relationship between the PMSST and the FCDO will mean that many day-to-day functions are carried out on behalf of FCDO, but with close supervision by FCDO due to regular interactions, including detailed monthly meetings where all elements of the PMSST’s workplan are scrutinised. The PMSST will provide strategic guidance to all implementing partners to ensure coherence with the programme Theory of Change, maintain a monitoring, evaluation and learning role across the whole programme, including the contribution of FCDO to policy influencing.
Figure 6 - FGMC2 Delivery Model

### Preferred option: FGMC2 programme design and delivery model
The FGMC2 programme is framed by a Theory of Change that is informed by an assessment of the evidence, lessons and recommendations generated by the experience of FGMC to date. The new programme design draws from the findings of independent evaluations and learning, consultations with stakeholders, experts and partners engaged in Phase I, reflections on changes in the context for the programme, experienced gained in scoping opportunities in new geographies in the Mekong and Pacific regions, reviews of the peer-reviewed and grey literature, and consultation with FCDO Posts in relevant countries. A more detailed Theory of Change, providing more detail of the results chain, definitions, causal assumptions, and reference to the evidence base can be found in Annex F. Details on how monitoring of outputs, outcomes and impact will occur and inform adaptive programming, is explained in the Management Case, in Annex F (ToC and results framework) and Annex L (Approach to MEL).
The programme will work at international and national levels to sustain forests and restore degraded lands that deliver for poor people and build resilience to and mitigate climate change. It will address governance failures by both government and market to curb deforestation, restore degraded lands and ecosystem services and sustain livelihoods for people in tropical developing countries. It will actively promote (a) international rules-based systems for trade and investment in forest, mineral and agricultural products grown on forest lands; (b) national inclusive decision-making that clarify rights and responsibilities, ensure compliance with social and environmental safeguards, strengthen institutions to ensure production and trade balance with local interests, (c) governance foundations to strengthen national climate strategies to sustain and restore forest lands.
The FGMC2 programme identifies international levers that incentivise national level governance reform in producer countries. The TOC for driving systemic transformations is set out in this section and is depicted in Figure 7. The programme is structured into three interacting components that will work to catalyse transformations in the governance of forest lands at national scale as well as changes in the ways international markets and international forest initiatives incentivise forest stewardship.
The intervention logic is depicted through an overarching Theory of Change (Figure 7). In a nutshell the intervention logic is that: national, multi-stakeholder deliberative process (Output) will result in a consensus interpretation of the rules (forest laws, norms, institutions etc) that govern the forest sector (Outcome) which will be enforced effectively and fairly (Impact) and, in turn, lead to benefits for People, the Forests and the Planet (Super Impact).’ ‘To secure results at scale, consumer markets (including carbon) have to address demand through the rules governing their forest footprint and global norms established through international processes seeking to safeguard forests.’
Figure 7 - Overarching Theory of Change

The programme’s intended impact is indicated as “forest stewardship” which is the care and wise use of forest lands that ensures their health and productivity for current and future generations in the context of multiple and, often competing, interests.
The outcomes are framed as the (1) fair and sustainable forest governance’ arrangements through which rights and entitlements, regulations, voice and oversight, accountabilities and the management of forest lands are determined and (2) the reduced risk for public and private forest investments and supply chains. ‘Governance’, refers to the means, and by whom, forest sector decisions are decided i.e. made, overseen and enforced.
‘Forest sector decisions’ relate to institutional arrangements (laws, rules, norms) which determine forest management and trade practices, including (i) legal rights, entitlements, and benefit-sharing arrangements; (ii) government and trade business processes, including traceability systems, transparency, public access to information and independent third-party monitoring: (iii) voice (inclusion) and process over decision-making, oversight, and enforcement.
Forest stewardship will result from the changed behaviour of forest stakeholders, alignment with new rules, regulations and incentives and the extent to which more stable and clear governance arrangements result in greater private and public investment in the forest sector.
The changed behaviour of key actors in the forest land sector is the essence of forest stewardship. This results from compliance and alignment with new, revised or more effectively implemented institutional rules (i.e. the “rules of the game”). These rules and norms are developed though domestic policy processes (Component I), Consumer market policies (Component II) and international rule and norms (Component III).
The results of improved forest stewardship are not easily separable. They include economic benefits (livelihoods, revenues, profits, carbon stored) as well as less tangible externalities (ecosystem services including water resources, biodiversity, cultural identity, etc.).
FGMC’s approach is to support national, multistakeholder, deliberative processes to arrive at a consensus that is enshrined in law and policy. The historic contestation and conflict over forest resources in most countries arise from different stakeholders’ perceptions concerning their rights. Clarification of rights and settlement of differences through deliberation results in rules that are recognised as socially legitimate and, therefore, fairer, and more enforceable.
FGMC2 will expand the programme scope to reflect on all significant threats to forests providing the opportunity to address governance challenges beyond illegal logging. While FGMC2 will remain focused on illegal logging, this broader scope will enable national stakeholders to prioritise their attention to the threats and opportunities most in need of forest governance reform. In some places this may mean a focus on illegal forest conversion for agriculture, or illegal forest mining as well as opportunities arising from initiatives designed to give value to forest carbon and ecosystem services.
The key elements of this consensus are closely linked and relate to:
- Forest stakes. Recognition of the traditional rights and norms of IPLCs, which may or may not be enshrined as rights.
- Forest rights. As well as not recognising forest stakes, legal forest and land rights are often contested or unclear and therefore not enforced.
- Benefit-sharing arrangements. Even when rights are clear, the entitlements they define may not be agreed, nor implemented in practice, or otherwise captured by those in authority.
- Responsibilities and incentives. The benefit-sharing arrangements establish positive incentives for responsible for forest management in the collective interest. These incentives are driven partly by national rules but also by the opportunities created by bilateral and international trade rules, which are addressed in Components II and III.
Approach. The FGMC supports governance processes by building the capacity of national actors to come together to reason and negotiate their own consensus for the establishment of a national legality system for forest land sustainability, with national rules related to the allocation and sustainable management and use of forest lands. Impartial Facilitators assist in what are often contested policy domains. FGMC helps to ensure they do this aware of the emerging, but increasingly onerous, requirements of consumer countries and in the light of global frameworks. As well as capacity building, FGMC supports the generation of evidence to inform the process and provides TA to support stakeholder participation and the development of systems needed to make enforcement of the agreed rules effective.
Success factors to build into future FGMC2 strategy: In the context of FGMC1, support to deliberative policy processes was associated with the VPA. In drawing lessons for future action, it is important to reflect on the partnership dynamic and what helped to create the conditions for governance reform. Under new partnerships, FGMC2 will seek to support governance reforms that go beyond timber and illegal logging to address wider forest threats and opportunities. Key features to carry forward into FGMC2 include:
  1. Scale- working at national scale avoids challenges of leakage and equity and encourages approaches that work for small businesses as well as larger multinationals.
  2. Defining and agreeing norms, rules, rights through multi-stakeholder deliberation helps build legitimacy, fairness, understanding, and common ground.
  3. Establishing transparent systems and independent monitoring to ensure compliance – builds confidence, creates the tools and mechanisms for challenge and redress.
  4. Consequential linking of performance to benefits (markets, access, incentives, promotion) motivates reform implementation and reduces opportunities for corruption.
The three components are:
- Component I: Partnerships with tropical producer countries for national scale forest governance reforms to establish and implement comprehensive national rules-based systems that ensure good forest land governance with a fair distribution of the costs and benefits (timber, agricultural commodities, mining, carbon and biodiversity payments) arising from the ownership and management of forest lands and their assets and accruing directly to forest owners and managers or indirectly as public goods.
- Component II: Forest footprint alliances to close markets to trade in illegal and unsustainable forest products through effective import management regulations, public and private procurement policies and recognition and rewards for trade from tropical forest countries with effective forest governance systems in place.
- Component III: Global policy engagement that catalyses change in international markets and global forest governance, establishes positive international frameworks (understanding and norms) to prohibit trade in illegal material and incentivise national forest stewardship through national and international rules that place governance at the heart of schemes/ investment strategies.
The programme level TOC provides the overall framing for the programme and the logic underlying its causality and impact pathway. Nested within the programme TOC, component TOCs, play a similar role for each of the relevant domains (Partner producer countries, Alliance countries and international processes). Again, nested under the programme TOC, thematic TOCs will track and inform strategic engagement on focused policy themes that cut across geographies and components covering for example, livelihoods of IPLC, forest carbon governance, forests and illegal mining, gender, etc., and cutting across the component TOCs will be prepared to expand on aspects or issues within the programme TOC. These TOC are an active tool, used to help build coalitions of actors working at national and international levels that will in turn help inform and shape strategies that work to connect national-level and international policies. Figure 8 sets this heirarchy out schematically.
Figure 8 - Hierarchy of TOCs
Specific country or domain TOCs will be developed for each country or domain where the programme is working, grounded in country realities, and again nested under the overarching programme and component TOCs and aligned with relevant thematic TOCs. Annex H (partner country analysis and engagement plans) includes initial country TOC and intervention logic based on initial scoping in preparation of this Business Case. These will be further developed once the BC is approved and dialogue commences with national stakeholders.
Ensuring programme coherence. The programme, components and thematic TOCs will be used to inform overall strategic and programming decisions. The country TOCs are more specific and serve as the basis for coordination of implementing partners and as well as enabling the programme to identify and respond to gaps and blockages. The FGMC approach to using TOCs has been to capture the role of different actors / stakeholders engaged in key deliberative sector processes. The idea is not to be prescriptive but to reflect on the overall external social and political environment in a particular domain / country and to understand the incentives and constraints faced by each stakeholder. The TOC captures programme understanding, outcomes and impact pathways at a given moment of time.
Programme learning - monitoring, tracking and evaluation. TOCs provide a framework not just for strategic and operational planning but also as a basis for learning and for reporting. Learning is an ongoing process that takes place throughout the programme, as well as amongst stakeholders engaged in national deliberative processes. The reality for a policy programme, such as FGMC, is that achievements and blockages are strongly conditioned by the socio-political context in which programme partners are engaging. As a result, during FGMC1, the country TOCs have proven more useful than a log frame results framework for guiding, tracking and reporting FGMC activities. They have allowed the programme to adopt a responsive and adaptive management approach under which Delivery Partners can update their workplans (quarterly) within an overall programme and country framework.
Delivery partners. FGMC supports national stakeholders to engage in a national process, through a mix of grants to International NGOs to support national NGOs and projects that provide a mix of facilitation and technical assistance. As is discussed in the Commercial and Management Case all the delivery instruments (e.g. accountable grants, in-country facilitation, technical assistance) to support the national process are designed to support action across multiple countries. Under the first phase of FGMC we found that this provides greater opportunities for sharing lessons between countries and their national networks. It provides greater flexibility to adapt resourcing to the opportunities and blockages in specific national contexts. As well, the programme encourages, through these instruments engagement in international and regional policy arenas; some provide evidence to inform national or international processes; and others expose illegality or governance failure.
Outputs and activities. These consist of a mix of (a) facilitation and convening; (b) technical support and capacity building to stakeholders engaged in national or international processes to establish rules-based systems; (c) provision of evidence and information, including support to independent monitoring and the development of tracking systems; and (d) TA to support development of legal and benefit sharing arrangements. The balance and focus of support in specific countries varies based on needs and interests, these will be developed and agreed with national stakeholders and framed into annual plans of work and which inform country-specific Theory of Change. A preliminary reflection of country-specific action is set out in Annex H to provide an indication of the nature of FGMC country level support. Details of actual support will be developed in consultation with stakeholders in country once the key delivery instruments have been mobilised (as discussed in the Commercial Case).
Programme components
Component I.	Producer Country Partnerships
This component addresses national governance failures. The outcome of this component is to establish national rules (rights and benefit-sharing arrangements, regulations, and business processes) to incentivise changed behaviours by forest managers and investors, through inclusive multi-stakeholder deliberative processes. Few countries have inclusive multi-stakeholder deliberative processes in place.
The programme will support stakeholders in partner producer countries, to engage in inclusive, multi-stakeholder and deliberative processes to reach a consensus on the national rules governing the forest sector.
The outcome space focuses on defining and enshrining in law national governance arrangements for the forest sector. This involves inclusive stakeholder engagement in an informed deliberative process that identifies and, where needed recommends modifications to, regulations and systems that govern forest sector management. The process addresses each group’s stake in forest land, the rights associated with those stakes, and their expected benefits from forest land uses. Deliberations result in a settlement on these aspects, clarifying stakeholders’ responsibilities linked to their rights, and the incentives (which may include more effective enforcement) needed to deliver forest land stewardship (Impact).
Figure 9 - Causal Model for Component I. Producer Country Partnerships

The FGMC approach supports inclusive multi-stakeholder processes that bring together stakeholder representatives to deliberate and reach a national consensus on a rules-based system for long term sustainable forest management (Figure 9). These rules establish or clarify rights and benefit-sharing arrangements and the systems and procedures to implement them nationally. In practice, this has required lengthy and informed negotiations between government, private sector associations and civil society, including IPLC representatives. Once agreed or ‘settled’ between the parties, the rules (rights, laws, policies, procedures, etc) are enshrined in law and arrangements for oversight and accountability, including independent third-party monitoring of compliance and enforcement are put in place.
In many countries, where deals related to forest benefits are traditionally done under the table and where there is resistance to involving civil society in public decision-making, such processes are new and require adjustments from all stakeholders to come together and use evidence to negotiate and agree collective action. In these situations, although rules may be in place they are often not fully implemented, with informal payments and patronage creating a system benefiting some stakeholders at the cost of others. In these circumstances, the incentives for those benefiting from informal systems, is to maintain the status quo.
The aim of a deliberative process is to strengthen governance with legally enshrined rights and rules that are widely regarded as fair and enforceable. The deliberative process is effective where there is contestation between divergent interests and the potential for conflict. The approach is similar to those used in post-conflict contexts to settle longstanding and intractable issues and move on.
Strengthened governance will be demonstrated by improved rule of law, and protection of rights, accountability and transparency, representation of stakeholder voice in reaching settlements on rules and norms and reduction in corruption and rent seeking. A Policy Change Index (PCI) will measure these changes.
FGMC understands ‘deliberation’, in contrast to consultation, to be:
    1. A formal process of reaching collective decisions, made in the common interest, resulting in agreements or settlements that are subsequently defined in law (or other rules) and framed into systems with the genuine intention that these rules will be implemented or enforced. an informed process, which is not just based on negotiation between stakeholders and interest groups, but on collective engagement and reasoning around evidence. For the process to be truly deliberative and not reduced to either negotiation/horse-trading or mere consultation, stakeholders need to have access to credible evidence, to deconstruct this evidence, to reconstruct a common understanding of the collective issues facing them and to agree on practical and fair solutions.
    2. An inclusive process, which takes place takes place within a country and includes participation of all national stakeholders, each with an incentive to engage with others and reach a settlement in their overall common interest. This requires stakeholders not just to have an incentive and interest in reaching agreement but also the capacity to engage knowledgably in the process.
In tropical forest countries, multi-stakeholder deliberation is often a new and challenging mechanism for public decision-making; traditionally this has been the sole domain of government and open to secretive manipulation by business and politicians. As a result, FGMC has supported national processes of inclusive, multi-stakeholder deliberation supported by independent facilitators. The starting point for multi-stakeholder deliberation is an understanding that there are divergent perspectives, strong vested interests, and power imbalances. To shift from this context, these processes will need patience, strong incentives, and facilitation. FGMC1 experience demonstrated it is feasible, and the TCI annual monitoring tracks progress (or the reverse) enabling teams to adjust strategy, or exit. The associated risks and assumptions are discussed further in Annex F.
A key principle underlying the FGMC approach is that an inclusive deliberative process will result in socially legitimate and sustainable governance reforms that, with support, can be enshrined in law and enforced in practice. Experience from FGMC1 practice has demonstrated this and independent reviews have confirmed the dynamics and consequences of these deliberations. The assumptions associated with this principle are discussed in Annex F setting out the detailed Theory of Change and associated evidence.
Deliberative processes require sufficient gravitas to be taken seriously by all stakeholders by creating sufficient incentives for them to engage in addressing forest stewardship. In FGMC1, these processes were established and underpinned through the legally-binding timber trade agreements – Voluntary Partner Agreements (VPAs) – with the EU and more recently with the UK. In FGMC2, the programme will continue to support VPA processes while seeking similar processes for other commodities, ideally anchored by international treaties or similar arrangements.
Also, key to a successful deliberative process is the support of an impartial facilitator. Experience under FGMC1 has shown that facilitation ensures the quality of national deliberations and inclusion, and helps clarify misunderstandings and promote lesson learning, thereby helping to secure effective implementation of the reforms that are required for the VPA. Facilitators have demonstrated their value: providing trusted, neutral advice to government, community, and industry stakeholders, and helping to overcome conflicts and blockages in the VPA process. Governance reform processes take many years, and both trusted relationships and understanding of local political sensitivities are critical to the success of the facilitation work. There is no reason this approach cannot be applied to other deforestation drivers beyond illegal timber. FGMC2 will encourage facilitators to explore opportunities to engage with new stakeholders to optimise the value of forests (e.g. through integrating forest carbon values into sustainable forest management) or to address other drivers of forest loss resulting from illegal activity and/or weak governance and non-transparent decision making. This could include mining activities in forest areas or the illegal conversion of forests to commodity agriculture, in addition to illegal timber.
The programme will promote national rules-based systems that are applicable across the whole country, to all actors and across all commodity chains, thereby avoiding differentiation between legal and illegal, sustainable, and unstainable material emanating from the same source country.
The programme will expand its geographic coverage from the first phase, supporting reform processes with as many as 16 countries. Country specific engagement and planning will be phased in over the first 4 years of the programme. The design of country-specific engagement requires in depth political economy analysis, and consultations with national stakeholders. In developing the Business Case the FCDO has worked with UK Posts and FGMC’s network of practitioners to develop ideas to shape country work plans for possibly 10 countries. These are summarised in Annex H (partner country analysis and engagement plans). Upon approval of the Business Case, the team would further consult with stakeholders to develop work plans for the inception period. Then once the instruments of the programme are fully mobilised in year 1, further scoping would explore opportunities in other countries where FGMC has limited experience or networks. The allocation for this component is £136m for the first 5 years and £305m over the full ten years. This component accounts for 60% of total programme spend as indicated in the Finance Case.
Process and likely FGMC2 actions under component I. As indicated in the component description above, deliberative multi stakeholder platforms are at the centre of the partnerships developed with producer countries. The actions that FGMC2 will support are designed to support the development of these deliberative platforms, the capacity of the stakeholders that are part of them, and to enable different actors to generate evidence and analysis to inform their processes. FGMC2 will also provide advice and technical assistance to partner governments and will support national civil society to monitor and hold to account the stakeholders responsible for forest management decisions and implementation. Next steps on approval of the business case will include detailed discussions with stakeholders in partner countries to identify priorities, develop country specific theories of change, and workplans that engage all delivery partners and stakeholders. Annex H (partner country analysis and engagement plans) provides more detail on the process to be followed and actions specific to each producer country partner so far scoped.
Component II. Consumer Market Alliances
This component addresses perverse trade incentives. The outcome of this component is to establish import management and overseas investment that eliminate outlets for illegal and unsustainable products from tropical forest lands and to reward and incentivise governance reforms in tropical forest countries.
The programme will form alliances with consumer markets, to share with and support stakeholders to establish rules (regulations and incentives) aimed at minimising the negative impacts of their forest footprints (Figure 10). This will encourage those markets to recognise effective legal and sustainable systems in tropical forest countries, thus incentivising other producers to similarly gain such recognition. It will also encourage consumer and processor countries to regulate their commodity investments that affect forests and forest communities. To motivate these changes, FGMC2 will support evidence gathering in developing countries on the damage to forests, livelihoods, and the environment resulting from consumer and processor countries’ forest footprints as well as improved market understanding of the requirements at source in tropical forest countries.
Figure 10 - Causal Model for Component II. Consumer Country Alliances

The programme builds on FGMC1 experience where sufficient interest was created in consumer and processor countries to establish regulations, guidance and incentives aimed at minimising the negative impacts of their commodity trade and investment, including restricting, or prohibiting the import of commodities linked with illegal deforestation and regulating overseas investment practices.
The outcome space FGMC will work in will be primarily emerging economies which import significant volumes of commodities that affect tropical forests (e.g. timber, palm oil, rubber, cocoa, cassava, gold) or invest in commodity production in developing forest countries. These are described in Annex I (Alliance country engagement). Stakeholders will include government agencies with roles in environment, trade, and investment; chambers of commerce; trade associations; national research bodies; and CSOs. FGMC partners will develop understanding and evidence of countries’ overseas trade and investment impacts and generate interest in developing regulations and/or codes of practice. These would incentivise the development of national forest stewardship systems that meet acceptable standards, for example through formal agreements.
FGMC 2 will continue to support reform of market and trade rules through alliances with importing countries and companies to improve their forest footprint. To date, this has been focused on China but, through FGMC2 support, will be expanded to include Vietnam, India, and other regional trade hubs. The objective of this component is to establish import management controls that excludes trade in illegal and unsustainable forest products and thereby helps to create positive incentives that encourage tropical forest countries to establish national standards and assurance systems. These, in turn, could be recognised by consumer markets and rewarded with fiscal or procedural benefits. The UK has followed a similar process through the work of the Global Resource Initiative Task Force, which established a multi stakeholder process to develop recommendations for the UK to address the sustainability of its forest footprint[25].
[25] Reports linked to the work of the GRI Task Force can be found on the UK Government site https://www.gov.uk/government/publications/global-resource-initiative-taskforce
FGMC1 supported action to encourage consumer countries to establish import management and overseas investment systems that reduce markets for illegal forest-based commodities, while supporting links to producers to understand their requirements. The introduction of consumer market rules was due, in part, to the sharing of ideas and the provision of evidence, understanding and analysis, generated by FGMC1 through global communities of practice that informed implementation in practice.
The process and likely FGMC2 actions to be taken under component II. It is estimated that £34m in the first 5 years and £79m over 10 years will be spent on this component. Programme resources will not be spent on supporting actions in consumer market countries themselves. Rather, the focus of FGMC2’s support is on raising awareness of the footprint that consumer market countries have in the countries from which they source their forest products and commodities derived from forest conversion, facilitating connections between consumer markets and stakeholders in tropical forest countries, and encouraging consumer market countries to tighten up on their import controls, have greater oversight of overseas investment vehicles in forest countries with weak governance and create positive incentives for forest stewardship. More detail on the process that will be followed to mobilise component 2 actions can be found in Annex I (Country Alliances).
Examples of actions that FGMC will support include:
- Research, analysis and evidence gathering raised awareness in China of the environmental, social and economic impacts of their unregulated sourcing strategies. This evidence was used to inform the reform of their market and trade rules, e.g. article 65 of the Forest Code states that no organization or individual may purchase, process, and transport wood in full awareness of their illegal origins such as illegal felling or wanton deforestation.
- FGMC support to advocacy and investigative organisations has held consumer markets to account against their own legislation, and businesses against their declared standards – for example the Environmental Investigation Agency provided compelling evidence of breaches in the EU and UK Timber Regulations regarding the import of sanctioned Myanmar teak.
- FGMC has supported consumer markets to deepen their understanding of the legal frameworks in producer countries from which sourcing takes place, e.g. through the production of legality checklists for use by trade associations and their members, or the development of guidelines for government to government engagement between China and producer countries such as Liberia, Gabon, PNG; and has ensured producer country stakeholders are aware of the import requirements of consumer market countries they export to by fostering business to business and government to government links (e.g. the Vietnam-Cameroon relationship brokered by GIZ), and advice to trade associations and investment regulators.
- FGMC encourages consumer market countries to engage in international dialogues and platforms that bring producer countries and markets together, such as through the FACT dialogue, and encourages consumer markets to recognise the efforts of producer countries to develop national forest systems.
- Support to the development of tools that track compliance by investors and companies include SPOTT which supports the financial sector and supply chain stakeholders to manage environmental, social and governance (ESG) risk through transparency assessments of soft commodity producers and traders.
As with FGMC1, FGMC2 will work with a wide range of organisations, including think tanks and researchers, trade associations and advocacy organisations within consumer market countries, where they have trusted relationships, an understanding of the political economy, what works and what doesn’t, as well as supporting them to connect with more established international organisations. Further information on next steps is set out in Annex I on Country Alliances.
Component III. International Policy Engagement
This component aims to shift international systems and ensure a global environment that is both informed by and incentivises national reforms and norms in producer and consumer countries as illustrated in Figure 11. The outcome of this component will be a positive global understanding and norms that shape and oversee forest governance and trade and ensures a voice for tropical forest country stakeholders in framing this context. In shifting international norms and systems the programme will amplify results from specific country partnerships to encourage global transformation in markets and forest stewardship in countries not directly supported by FGMC.
The programme will support FGMC partners to engage in international processes to create a positive global environment that frames rules-based systems in both producer and consumer countries and amplifies these results in non-FGMC focus countries.
This engagement will focus on four key domains:
    1. Catalysts for national action: reputations; international engagement
    2. Processes to shift international trade and investment rules.
    3. Processes to mobilise or create new finance instruments and incentives.
    4. International cooperation that reinforces and enforces national rules.
The Outcome spaces in which FGMC will work include global processes that focus on forest stewardship, identifying opportunities for collective action, especially linked to commodity trade and investment (including carbon and ESS). These may include global political negotiations such as the Climate and Biodiversity Conferences of the Parties, established bodies such as the International Tropical Timber Organisation (ITTO), World Trade Organisation (WTO), Multilateral Development Banks and bilateral donors; as well as dialogues such Forest Agricultural Commodity Trade (FACT), the Forest and Climate Leaders Partnership (FCLP), the Tropical Forest Alliance, and bodies connected with the evolving carbon markets such as the ICVCM, the VCMI, and other others.
Figure 11 - Causal Model for Component III. Global Policy Engagement

As part of this component, FGMC will continue to support a global community of practice in which stakeholders can engage across components and encourage non-FGMC partners countries to also develop their own systems (See Section on relationship between components, below).
FGMC2 will mobilise an international forest governance hub with EFI’s International Partnership Facility and initiate discussions with other development partners to gauge interest in co-funding. The IFGH will be a centre of expertise able to provide independent advice and to convene south-south learning so as to empower tropical forest countries to engage effectively in international policy domains, irrespective of whether they are partners of the FGMC2 programme. The provision for a multi-donor trust fund will support the amplification of the programme impact.
FGMC2 will support the development of the Broader Market Recognition Coalition (BMRC). This evolved out of a trade association initiative, “Global Forests need Global Governance”, led by the Timber Development UK, at the Glasgow COP. This initiative aims to establish a mechanism to recognise ‘National Sustainable Forestry Systems” (NSFS) in producer countries to encourage the uptake of such systems and to gain recognition for legal and sustainable forest material. This drives sustainable production for domestic markets and all export markets without requiring consumer country legislation.
The programme will engage with and support other forest-related policy initiatives and processes of priority to HMG such as the COP26-legacy initiatives FACT, FCLPs, that work with the political momentum they created to support ambitious governance reforms. The FGMC community of practice has consistently contributed to both the biodiversity and climate COPs including driving the IPLC forest tenure agenda which led to the IPLC pledge at Climate COP 26 and tracking its subsequent progress, promoting the importance of forest governance foundations for sustainable trade, etc.
The process and likely actions to be undertaken in Component III will include taking stock of those international processes that have the potential to create a catalyst for change or that can reinforce existing rules as per the 4 domains identified in the theory of change. These are: International processes that can serve as catalysts for national action (e.g. VPAs, the future of FLEGT licenses, engagement on due diligence, or the BMRC); processes that shift international trade and investment rules (e.g. the Taskforce on Nature-related Financial Disclosures); processes that mobilise or create new finance instruments and incentives (e.g. integrating governance into the forest carbon/REDD+ instruments); and International cooperation that reinforces and enforces national rules (e.g. cooperation between competent authorities on due diligence, international action on crime, international cooperation on the BMRC and/or other means of generating positive incentives to reward forest stewardship.
FGMC2 will seek to influence relevant international policy processes by building the community of practice to engage with them. The FGMC2 accountable grants programme will be launched. It will encourage the operational independence of accountable grantees in alignment with the broad domains outlined above. A call will be lodged framed around these domains with a view to attracting proposals that will provide additional evidence and impetus to influence them.
International processes will be prioritised according to where there is a strong opportunity for FGMC’s community of practice to influence consideration of forest governance. This will likely include processes related to timber supply chains (the BMRC) processes that relate to import requirements for agricultural commodities and mining and processes to help shape the development of forest carbon markets, in particular the need for clarity on rights and benefit sharing. Given the broader scope of processes beyond timber, it is likely that the community of practice will extend to new partners.
Examples of how FGMC might engage with forest related policy initiatives and processes include the provision of facilitation support to Indonesia as co-chair of the FACT dialogue, to prepare for meetings and to develop proposals seeking recognition of national legality assurance systems. FGMC community of practice experience is already harnessed by the UK to engage proactively in the Trade and Markets group of the FACT dialogue and in working groups under the FCLP. FGMC has provided advisory and convening support to producer countries to rally around their search for market recognition and reward of their national sustainable forestry systems, leading to the creation of the BMRC. Under FGMC2, the programme will help with the setting up of an independent structure to serve as secretariat for the BMRC.
Under the proposed international forest governance hub actions will include making important data more accessible to countries, for example trade data which can be difficult for individual producer countries to access. It will also provide for more south-south exchanges to learn from experience, a model already tested under FGMC1. This will be particularly important for new countries coming into FGMC2 that will be facilitated to learn from other producer countries that have experienced the challenge of establishing genuinely deliberative multi stakeholder processes for example.
The overall expected spend for this component is £33m in the first five years, and £81m over 10 years.

Relationship between components
The three components are interrelated through the engagement of national stakeholders, not just governments, in both global and bilateral interactions as well as in their own national processes (Figure 12).
FGMC fosters and supports these critical interactions, by convening meetings between trade associations in producer and consumer countries regarding legality and standards, south-south exchanges to share experiences and learning as well as regional and global events where national stakeholders from both FGMC-supported and non-supported countries participate. These global and international interactions are critical to building coalitions of practitioners, fostering national debate in FGMC-supported countries, and introducing and ‘amplifying’ ideas and momentum to nascent processes in non-FGMC-supported countries.
Figure 12 - Stakeholder interaction and engagement shaping the programme logic

Cross-cutting Gender issues
FGMC2 approaches the issue of gender and inclusion from the perspective of both participation in national or international policy processes and assessment of the gender effects of policies being promoted. This contrasts from many other, more field-based projects which aim to deliver concrete (and measurable) benefits at the household or community level.
FGMC has worked to support multi-stakeholder participation in decision making processes around substantive and procedural rights. [26]Advocacy relating to clarification and reform of forest tenure rights and community-based forest management, have been an especially important aspect of FGMC’s work, for example ensuring that resource ownership rights are legitimate and granted only with rights holders’ proper consent. [27] Such reforms are also an opportunity to promote equal tenure rights between men and women, as well as marginalised groups. [28]
[26] Substantive rights being the rules that define rights and obligations around resource ownership and use, and procedural rights being the processes for the exercise and protection of substantive rights, such as access to information, participation and fair adjudication.
[27] ibid
[28] ibid
FGMC’s gender framework focuses on four key areas:
    1. Interventions - Organisations and project activities: This relates to the way in which FGMC-funded entities (projects, organisations, governments) consider and actively promote gender within the design, implementation, and monitoring of their activities.
    2. Voice - Policy processes: This relates to the degree to which the voices of women and girls are represented and included within national, international, and private sector policy-level decision making and deliberation. Most typically this takes place through representative organisations who have a mandate to speak on behalf of and represent the interests of women and girls within such processes.
    1. Policies - Policy outcomes: This relates to the degree to which public policy, legal frameworks and rules as well as private sector policies influenced by FGMC, support gender equality and address areas of concern for women and girls.
    2. Impacts - End results for women and girls: This relates to the impacts of policies, laws and rules on gender equality – including rights (the rights of women and girls are strengthened); choice (women and girls have equal choices and opportunities from forests as men); control (women and girls have equal control and decision-making over access to and benefits from forest resources and benefits (women and girls receive an equal share of benefits accruing from forest resources).
FGMC grant management guidelines state that grantees will promote gender equality of stakeholders in project implementation and in the advocacy of roles, rights, and access to forest resources within local communities in accordance with the International Development (Gender Equality) Act (2014) and the FGMC gender guidelines. FGMC will require all funded entities, in accordance with law, to consider how gender is incorporated into (a) what they are advocating for, researching, developing products and (b) how they engage in policy processes. Grantees will certify each year that they comply with this requirement.
FGMC2 also could exercise international thought leadership via the International Forest Governance Hub. This may be through identifying and prioritising gender and inclusion themes to pursue through research and analysis, building on the rich body of analysis already produced by FGMC1 grantees on gender and social inclusion issues. The International Hub will also have the capacity to convene different interest groups to participate in knowledge exchange and learning activities, and to empower these groups to feed this learning into policy and advocacy activities, including those supported by the rest of the FGMC2 programme. Annex C sets out FGMC2’s gender and inclusion strategy.
The steps outlined above, to thoroughly analyse, build and refine strategies to actively address gender inequality and social exclusion, will ensure that the programme is fully compliant and acts in the spirit of both the International Development (Gender Equality) Act and Equality Act (Public Sector Equality Duty).
Value for Money (VfM)
A VfM assessment using the FCDO’s 5Es framework will assess whether FGMC2 represents an optimal use of resources to achieve intended outcomes based on its Economy, Efficiency, Effectiveness, Cost-effectiveness, and Equity. The findings of this assessment are that FGMC2 can be expected to deliver very strong VfM across each of the 5Es and be highly additional, supported by evidence from FGMC1 and economic modelling carried out for this business case.
Economy
Economy refers to the degree to which FCDO or our agents can be expected to buy the inputs required to produce FGMC2 outputs at an appropriate quality and cost. Inputs would include staff, third-party consultants, raw materials and/or capital. Based on FGMC1, direct costs are likely to be driven by the sourcing of specialist expertise and the associated fees. FGMC1 spent approximately two thirds of the total global budget on Output 1 over 12 years of the programme which focussed support on forest sector governance processes and management in producer countries. This output requires the most intensive technical inputs and higher expenses, with costs driven by delivery of technical assistance, overseas office costs, travel, and security.
The main cost drivers are likely to be similar to FGMC1 although overall costs will be greater to reflect the expanded scale of the preferred option, there may be some potential for economies of scale at the country level by growing existing scope. The key cost drivers are the specialist expertise required to deliver the different components of the programme; technical assistance, capacity building, accountable grants supporting INGO actions, research and analysis, facilitation of multistakeholder processes, as well as providing or upgrading IT infrastructure for compliance monitoring and product traceability, and training for government services, small businesses, and civil society organisations (CSOs). Cost drivers across commercial contracts and their respective VfM considerations are set out in more detail in the Commercial Case.
Specialist expertise can be provided directly through the programme’s delivery partners, or through third parties. Control over costs throughout FGMC2 will be ensured through monitoring management fees and through competitive procurement. Commercial criteria will be used in the assessment of delivery partner bids to assess economy before contracts are awarded, and throughout programme delivery. Refer to the commercial case for more detail on cost drivers and procurement approach.
The proposed spend profile of up to £500m over 10 years is double that of Phase1, with an initial budget allocation of £220m for the first 5 years. The VfM assessment and economic modelling is carried out for the full £500m over a 10-year period; see the Financial Case for more detail on spend profile. Increasing the scale of FGMC2 under the preferred option will enable:
    1. significantly increased geographic coverage and coordination, deepening partnerships to support reforms in up to 16 tropical forested countries, building from country engagement in earlier FGMC1 mainly in West and Central Africa and Asia.
    2. addressing the most serious threats to forests as indicated in specific country contexts including illegal forest clearance for mining and agriculture commodities.
    3. engaging with national climate strategies and particularly forest carbon governance on forest lands.
    4. addressing both demand and supply side mechanisms.
    5. levelling the playing field for all businesses by adopting a national forest governance approach designed to address international markets.
    6. expanding to work with major global markets, such as India, Vietnam, or China, to promote sustainable forest footprints by reducing imported deforestation[29], and encouraging greater responsibility and transparency in overseas investments in developing forest countries.
      [29] Imported deforestation refers to the loss or degradation of forest in producer countries caused by supplying a consumer market country’s agricultural imports (agricultural food and commodities, biofuels, aquaculture and forest products)
Management fees for the programme will be a key driver of cost. Open competition and a competitive procurement process will be followed to ensure that management costs remain at a level that offers value for money, and this will be monitored throughout the programme lifetime as part of the Annual Review process.
Fees including administration charges, overheads and project support for IFU programmes typically range from 3 – 13% depending on the scope of the programme and the experience of the delivery partner organisation. Multilateral programmes and technical assistance programmes have typically higher fees of up to 15%.
Efficiency
Efficiency refers to the degree to which FGMC2 activities convert the aggregate inputs into desired outputs. The preferred option builds from the FGMC1 experience as a flexible and adaptive management approach able to support actions both for global and country governance reforms, increasing efficiency. FGMC1 has been delivered by a Programme Management Support Team (PMSST).
The PMSST is responsible for providing strategic advice to FCDO over the management of the programme, technical support and the oversight of FGMC-funded accountable grants. The PMSST will be procured through fair and open competition for FGMC2, ensuring good VfM. More details on the management arrangements for FGMC2 can be found in the Management Case, in particular the figures on delivery structure and governance structure, and in the Commercial Case on the outsourcing of PMSST for FGMC2.
FGMC1 established effective ways of working, delivering at country and global levels and working jointly with other donors, which improves efficiency and effectiveness. To date, 15 countries have been engaged in Voluntary Partnership Agreements (VPAs), making up 80% of the EU/UK’s tropical timber imports covered by legally binding treaties. The UK, through FGMC1, led the support to Indonesia, Ghana, Guyana, Liberia, and the Republic of Congo (RoC), while other European donors support action in other VPA countries. FGMC secured co-finance from the EU and Norway in Liberia and Guyana, France in the Republic of Congo and Germany in Vietnam, Cameroon, and Laos. Multi-country support was delivered through facilities that pool donors to extend support to, and influence, more countries and regions, improving efficiency. For example, the UK, EU, US, and other OECD markets have all now introduced legislation requiring due diligence in timber supply chains. More details are explored in the FGMC lessons learned box 9 in the Commercial Case, for example the benefits of pooled resources across donors.
There are four main ‘instruments’ that FGMC1 uses to support and deliver activities in its focus countries and international arenas, which are expected to continue in FGMC2 as they have proven highly effective. These are Facilitation service, TA capacity building projects, Accountable grants and technical expertise and these are described further in the Management Case. FGMC has strong complementarity with other IFU programmes, as set out under the section covering Complementarity with other UK and international support in the Strategic Case. The programme works through a range of mechanisms working in partnership with FCDO country offices, other donors, civil society, not-for profit organisations and service providers. See the delivery and instrument overview in the Management Case for more details.
FGMC1 awarded over 60 accountable grants to approximately 25 strategic partners whose activities include developing innovative tools, generating information and analysis, policy advocacy, capacity building of private sector federations and civil society, independent monitoring and raising market awareness. This is a key strength of the FGMC model as buy in and delivery through a broad range of partners improves efficiency of the programme, as well as meaning that key stakeholders are already bought into FGMC2 through Phase 1.
FGMC’s deliberative processes include groups often excluded from policymaking such as women, indigenous people, informal organisations, and small- and medium-sized enterprises (SMEs). Giving all stakeholders a voice in decisions about the rules and systems that govern forest sector management is key to the FGMC approach as it improves legitimacy and the likelihood of lasting transformative change. The 2017 mid-term review found that FGMC’s approach has proven a highly effective model for addressing the complexities of trade and governance through mutually reinforcing actions relating to supply-side, demand-side and business measures. Being politically inclusive therefore improves both efficiency and equity.
Effectiveness
Effectiveness refers to the rate at which FGMC2 outputs are predicted to transform into desired outcomes and impacts. As an ICF programme, FGMC is ultimately oriented towards contributing to transformational change towards lower carbon development. However, FGMC does not directly invest in forests; it invests in forest governance and systems. This will deliver significantly stronger value for money than if the funding volume were spent directly on forests, as it will catalyse system changes in governance over much larger areas of forest land. The benefits and costs of governance changes enabled by the FGMC process do not generally lead to quantified results which are directly attributable to FGMC. Instead, FGMC works at global scale brings together trade policy with development assistance to improve global business practices. Nonetheless, realised forest stewardship through governance reforms will benefit communities and governments, and lead to lower carbon development.
Globally, FGMC2 will grow relationships established under FGMC1 with key countries (e.g. EU, USA, China, Vietnam, Japan, potentially India, Malaysia) and other markets to reduce “imported deforestation”. Data on estimated sources of imported deforestation to the UK is presented below (Figure 13), totalling 18MtCO2 of “imported deforestation” i.e. tropical deforestation emissions associated with UK commodity consumption.
Figure 13 - Tropical Deforestation Emissions (tCO2) associated with UK commodity consumption in 2018.
FGMC2 will build on the experience and success of FGMC1, working through national and international policy processes to bring about institutional and governance reforms. In turn these should deliver economic impacts through norms and rules around forest related trade, inducing investment through trade in timber and other commodities, and securing sustainable livelihoods for local communities and Indigenous Peoples. Legal requirements alone do not ensure sustainable forest management; the inclusive multi-stakeholder national process, incentivised by external trade requirements or carbon finance incentives, is what will effectively deliver sustainability. Inclusive processes are critical as effectiveness depends on establishing governance systems that are nationally supported, regarded as legitimate and fair and, therefore, are enforceable. A key assumption is that the deliberative process can reach agreed national rules, standards or rights that become enshrined in law and are more legitimate than outcomes achieved in a counterfactual without the FGMC programme. Examples of the FGMC approach in practice are provided in the Strategic Case.
For the FGMC approach to continue to be effective, a critical number of significant stakeholders must see a benefit from engaging and reaching a consensus. The more inclusive the engagement, the more legitimate the outcome. FGMC’s national facilitators support the process and FGMC grantees support national partners to engage effectively and with evidence in these processes. Often, at the start of a national process, FGMC commissions economic analysis which provides stakeholders with a sector overview of the ‘forest rent’ and who receives it.
A variety of instruments will be employed to drive systemic change, tailored to specific contexts. These include policy engagement, technical and governance support, facilitation of national processes, generating evidence, knowledge and capacity. FGMC works with the most significant market drivers and major sources of tropical timber and agricultural commodities to deliver impact at scale. Measures encompass policy, standards, regulation, reporting and enforcement. FGMC’s interventions are wide ranging and include demand and supply side measures at both global and national scales with examples set out below. A breakdown of funding allocations across the programme components is provided in the Financial Case.
Demand side action
Closing markets to illegal timber products requires:
    1. Enhanced enforcement, where regulations exist.
    2. Improved measures in other markets, including processor countries.
    3. Improved business practices, compliance and investor behaviour.
As well as helping to close markets to illegal timber, these activities help to reinforce supply-side action and secure legal timber supplies, contributing to economic growth, poverty reduction and sustainable forest management.
Supply side action
Stopping the flow of illegal timber products involves:
    1. New systems and reforms are often needed to encourage compliance and support enforcement.
    2. FGMC supports action to strengthen forest governance for timber production as has been the case through VPAs. This includes the development of a comprehensive, independently audited national system for verifying the legality of its timber exports including agreement in defining legality, traceability and supply chain controls, verification of compliance, independent audits, and licensing of verified legal timber exports.
    3. To be credible for national stakeholders and international markets the systems are designed through a inclusive process; stakeholders deliberate on definitions of legality including resolving questions of rights, what sustainability norms to pursue, what information to make public, how to monitor compliance, and what checks and balances to establish in its operability.
    4. Stakeholder engagement is sustained in implementation of reforms and continuous improvement is fostered and strengthened through national engagement and ownership.
The 2021 FGMC Annual Review found that at a programme level, a preliminary study on revenue impacts of FGMC carried out by PELT, estimated a potential increase in revenue to governments in the 16 countries implementing VPAs of £1.6 billion per year (assuming a 10% increase in efficiency of revenue collection due to the VPA).
By improving legal clarity, participation and transparency, countries whether bound by VPA or developing a national assurance system can increase accountability, reduce corruption, protect rights and ensure obligations are met. By making and enforcing collective choices, they can achieve an equitable and legitimate distribution of resources. This can improve livelihoods, increase revenue, promote sustainable management — with benefits for trade, biodiversity, and the climate — and strengthen societies by upholding the rule of law, creating effective institutions and empowering citizens. Ultimately, these gains can help reduce poverty and boost economic growth, delivering strong effectiveness.
The independent mid-term review by ITAD (June 2017) of FGMC1 found “significant, visible and widespread evidence of FGMC’s contribution to and influence on establishing new forest governance arrangements and market reforms at international, regional and national levels” and found “strong evidence that FGMC has contributed and will continue to contribute to the outcome areas of improved governance and market reforms that reduce illegal use of forest products”.
The trust developed over many years of UK engagement in the VPA process delivers strong effectiveness due to the UK’s reputation as a valued long-term partner and bodes well for continuing to develop partnerships. This is supported by the 2021 ICAI Review’s findings mentioned in the Strategic Case, and a 2014 ICAI Review which commended ICF forestry initiatives for strengthening law enforcement and forest governance and found good evidence of positive national impact in land-use planning and forestry governance. ICAI further commended the direct assistance to poor communities through recognition of their rights to land and forest resources.[109]
[109] The UK’s International Climate Fund - ICAI (independent.gov.uk). December 2014
Additionality
FGMC’s lasting impact will result from the changes developing countries make to the stewardship of their forests, resulting in stronger business standards, rights, accountability and transparency, benefits accruing to local communities, revenue collection and exports. Sustainability is secured by changes in law and demand through evolving business standards in producer and consumer countries, and by establishing partnerships with countries that are based on economic interests, rather than an aid-focused relationship. Working with China and other unregulated markets, who dominate the global timber trade, to close their borders to illegal material, to promote legal timber will also help to secure lasting benefits of the reforms we have supported in developing countries. See the Management Case section on sustainability and exit strategy for more details.
FGMC results are achieved by continuing support until new systems are well established and are self-sustaining. During the current phase, Indonesia and Ghana have reached the milestone of nation-wide controls and all their timber exports to all markets are now from independently audited factories and forests. This reflects a comprehensive reform of their timber sectors and compliance with national tax, labour, social, environmental and forest laws and regulations. Indonesia credits the decline in deforestation over the past few years in part to the strengthened controls of their new system.
FGMC2 must build on the success of FGMC1 and deliver additional activities and outcomes which would not otherwise have been realised by other programmes or by the legacy of FGMC1. Additionality is characterised by comparing the preferred option to a counterfactual of “without programme” i.e. Option 0 set out in the options appraisal above (see Annex D: Appraisal of strategic option, Option 0 and Annex G: Economic Appraisal, Supporting Evidence section.
The forest policy shifts in some countries supported through FGMC1 are likely to be sustained without programme spend, as FGMC1 has been designed to deliver sustainability and shift norms. However, the scaled-up funding and scope of the preferred option will deliver significant impacts beyond business as usual practices delivered under FGMC1, in particular through the broadened scope governance challenges addressed. Furthermore, FGMC2 will support multi-stakeholder policy platforms that are otherwise unlikely to be sustained in Option 0.
During the programme lifetime qualitative assessments of additionality will help to design and target assistance more effectively, as needs become better understood for different components of the programme. An independent mid-term review of FGMC1 found positive results and gives strong endorsement for the multi-faceted approach of the programme, and independent reviews must continue in FGMC2 to ensure the sustainability of FGMC’s impacts and of additionality compared to the counterfactual.
### Cost-Effectiveness
Cost effectiveness refers to the overall rate at which FCDO funding to FGMC2 is expected to transform into desired outcomes and impacts, relative to the aggregate costs of inputs. In this assessment cost-effectiveness is considered in terms of a benefit-cost assessment and net present values (NPVs) derived from an economic model initially developed by external consultants and adapted for this business case by Economic Advisers in FCDO.
#### Economic Domain Model Approach
The economic model for FGMC is constructed to capture the size of the domain in which FGMC operates and determines the break-even level of policy change required for benefits to cover programme costs. The model assesses the full programme, with £500m spend over 10 years with a 30-year horizon for programme benefits. Recent average rates of deforestation and forest conversion are used to forecast future rates (the ‘without programme’ scenario). The ‘with programme’ scenario estimates the area of avoided deforestation/conversion due to programme activities. These estimates are based on plausible reductions to the forest area that would have been lost without programme interventions, quantified through the concept of a Policy Impact Factor (PIF). The PIF determines the area of deforestation and conversion saved and estimates the quantities and values of timber and stored carbon from these areas.
The PIF value is an assumption, set at a plausible level of the likelihood that the programme interventions will drive change that leads to the identified benefits. The greater the positive impact of FGMC2, the higher the value of the PIF, the more deforestation and illegal logging are reduced, with more Reduced Impact Logging (RIL) being practiced and more standing carbon retained. The model captures the incremental impact of Reduced Impact Logging (RIL) over Conventional Logging (CL) and estimates the impact of the clarification of rights and benefit-sharing arrangements in terms of reduced conflict.
The model estimates the potential incremental value of the domain in which FGMC operates and explores the likelihood of the benefits of FGMC’s policy impact exceeding programme costs. Rates for the PIF are set conservatively. It is not possible to directly or precisely attribute change in forest governance, including deforestation, to the FGMC2 programme given that many confounding factors exist. Separate runs of the model use different assumptions about values of carbon the PIF rate to determine the robustness and sensitivity around the base reference rate (See Annex G: Economic appraisal). A breakeven value of the PIF was calculated for each carbon value scenario (using HMG discount rates), to test how low policy impact could fall before benefits would no longer cover programme costs. The base case sets the PIF at 0.1% per annum, the low policy impact scenario set PIF at 75% of the base case; and the very low impact scenario sets PIF at 25% of the base case.
As above the model estimates changes in the quantities of timber production and stored carbon from areas no longer deforested or converted and captures the incremental impact of RIL over CL in terms of monetary value (£m), carbon (MtCO2) and ecosystem services (ESS) (£m). The model also estimates the benefit of the clarification of rights and benefit-sharing arrangements in terms of reduced conflict.
These potential results within the domain in which FGMC functions will not all be due to FGMC2 and are not targets for the programme per se. Estimating the potential incremental value of the universe in which FGMC operates allows us to test the robustness of assumptions about the likely benefits of FGMC’s policy impact exceeding programme costs, under different price assumptions. Limitations of the model are set out in the Technical Annex of the Economic Appraisal (Annex G). The economic domain model and the analysis reflect the nature of the FGMC programme and its policy change objectives and unlike other international climate finance programmes which invest in forests, cost effectiveness or abatement costs are not appropriate to such a model.
Benefits are summed across three types of forest:
    1. Protection forest delivers a small volume of ecosystem services.
    2. Production forest delivers net benefits from conventional and reduced impact logging (RIL), carbon sequestration, ecosystem services and reduced conflict.
    3. Converted forest uses the value of natural rubber (latex) smallholder production as a proxy for forest conversion crops and includes the value of carbon in rubber trees. [30]
      [30] When the programme shifts land from conversion to more sustainable uses this forgoes the value of production under BAU land use. This is not treated as a cost because when forests are converted their value is not reduced to zero; they gain value to both agricultural production and CO2. If treated as a cost, BCRs are significantly underestimated.
The model uses the deforestation rate from Global Forest Watch (2021) for each country and applies it equally to protection and production forests. The “without programme” scenario assumes historic trends in deforestation and land conversion continue. The model derives benefits from shifting land away from converted forest into production and protection forest, thereby reducing the amount of land converted to unsustainable agriculture as in the ‘without programme’ scenario. This approach solves for the PIF rate, rather than an investment model which would solve for rate of return. Therefore, unlike many other international climate finance programmes, a rate of return or abatement costs would not be appropriate to assess using this model. This approach and the underlying data supporting the model are set out in the Technical Annex of the Economic Appraisal (Annex G), as well as further analysis of the impacts of varying the PIF rate.
The central model scenario applies a value to carbon emissions avoided at a rate of £134/Mg CO2e in 2021, which reflects the low values of the HMG Accounting Carbon Value series. Sensitivity scenarios varying the value placed on carbon are used to stress test the model results. The carbon values are calculated as a base rate in 2024 and adjusted using a Hotelling rule.[31] HMG’s carbon values for appraisal are much higher than the price currently paid through carbon markets or donor programmes, therefore the lower values reflecting regulatory and voluntary market prices were also modelled. A carbon value of £48/Mg CO2e is used to reflect regulatory carbon market prices, £8/Mg CO2e approximates voluntary carbon market prices, and two extreme scenarios apply a zero-carbon value and the central HMG appraisal series of £269/tCO2e.
[31] While this approach is not aligned with the latest Green Book guidance, it complied with the Green Book approach at the time of initial model development in Spring 2021.
There is a significant lag between the realisation of benefits and implementation of the programme activities of several years, reflecting the time to develop policy, implement a timber legality assurance scheme (TLAS), and reach some level of enforcement. This reduces the BCR but is essential to reducing optimism bias and ensuring realistic expectations of programme impact.
#### Economic Model Results
The break-even rate of the PIF represents the level of effectiveness of the programme at which the BCR equals 1; where costs and benefits of the programme offset each other. Carbon values are a significant driver of benefits in the model and we estimate the breakeven PIF rate for different carbon values.
The table below shows the break-even PIF rates for each series of carbon values. With positive carbon values, the breakeven rate of policy impact needed is significantly lower than our base case PIF, and therefore the programme can be considered highly likely to deliver significant positive returns. For example, in the core model scenario (highlighted in the table below), the level of policy impact required to break even is only 3% of the level set in the base case.
Even with lower carbon values, shown in the rows above the highlighted figures in the table, the required level of impact to breakeven remains small, at 7.8% compared to the base case when using a proxy for regulatory carbon prices, and 34.5% when using a proxy for voluntary carbon market prices. Where no value is placed on the carbon benefits of the programme, the policy impact must be higher to break even, at a rate of 146.3% of the base case PIF.
Table 3 - Breakeven PIF rates for the model’s carbon value scenarios
Carbon Value	£/Mg CO2e	Breakeven / Policy Impact / (% of base rate PIF)

Zero	-	146.3%
Market	8.00	34.5%
Regulatory	48.00	7.8%
Accounting (HMG low)	134.00	3%
Accounting (HMG Central)	269.00	1.5%

Central model scenario
The table 4 below shows results for the central model scenario using the HMG appraisal carbon value low series, with strongly positive BCRs across all modelled policy impact scenarios. The column on the right shows the rate of the PIF required to break even for this scenario. The central BCR used in this appraisal is highlighted in orange, which uses the HMG low carbon value series (£134/tCO2e in 2024) and the base impact PIF, a rate of 0.1%, achieving a BCR of 33.7. Comparing BCRs across the policy impact scenarios provides an indication of the likelihood of positive impact.
Table 4 - BCRs for different PIF rates in the central model scenario
	Base policy impact	Low policy impact	Very low policy impact
PIF rate	0.100%	0.075%	0.025%
Benefit Cost Ratios	33.69	25.26	8.41

We find a very strong likelihood of positive impact of the programme in the central model scenario, with net incremental benefits of over £3bn and a BCR of 8.41 even with the least ambitious expectations of policy impact.
In this central model scenario 564,000ha of natural forest are retained, i.e. avoided deforestation compared to a scenario without the programme. Sensitivity analysis is carried out with lower PIFs; a lower policy impact scenario leads to 423,000ha of natural forest retained, and in the very low policy impact scenario 141,000ha are retained. Hectares of avoided deforestation and emissions sequestered by reduced impact logging concessions lead to net reductions in greenhouse gas emissions equivalent to 151Mt of CO2e, 113MtCO2e, and 38MtCO2e for each of the respective impacts.[32] For context, the annual greenhouse gas emissions of the UK in 2022 were 417MtCO2e and the UK landmass is 24.8 million hectares.[110]
[32] Estimated reductions in GHG emissions are net of increased emissions which result from hectares brought under agricultural production.
[110] 2022 UK greenhouse gas emissions: provisional figures - statistical release (publishing.service.gov.uk) Department for Energy Security and Net Zero (2023) 2022 UK Greenhouse Gas Emissions, Provisional Figures
The volume of annual timber harvest increases by 0.6 million m3 with the programme compared to without it. This increase is driven by increasing hectares of productive forests, particularly through the adoption of reduced impact logging. Despite increasing the overall timber harvest, more sustainable practices are expected to lead to both carbon and ecosystem service benefits.
The number of forest-dependent people benefitting is a function of population density at the forest frontier. The model estimates approximately 309,000 for the base policy impact, 231,000 for the low policy impact and 77,000 for the very low policy impact. These figures are a significant underestimate as this calculation is a static assumption based on the number of people living on forest borders, with input data averaging less than 0.4 people per hectare at the forest frontiers in the 18 countries included in the model.[33]
[33] Note that the economic domain model 18 country database was set up prior to the decision to work with up to 16 countries under the programme.
Table 5 - Additional indicators for central scenario
	Without Program	With Program, base rate PIF
Natural Forest Retained (ha)	0	563,914
Avoided Emissions (Mg CO2e)	0	150,723,780
Forest People Affected (#)	0	308,687
Mean Annual Timber Harvest (m3)	321,881,203	322,492,914

The net present value (NPV) is a partial estimate of net incremental benefits of the programme driven by the selected level of policy impact, compared to the scenario without the programme. In a scenario assessing the full 10-year programme using the base PIF, the low HMG carbon appraisal values, a discount rate of 3.5% and a time period of 30 years, the NPV is significantly positive at £13.3bn, predominantly driven by carbon benefits compared to the “without programme” scenario.
The figures presented below are a partial estimate of programme impacts and the NPV is relatively conservative. This is because the model includes impact level benefits such as the value of carbon and ecosystem services but doesn’t explicitly include outcome or output level programme benefits such as the value of improved forest stewardship or secured tenure rights as these are assumptions required to deliver the quantified programme benefits. The model includes production forest and conversion of forest to agricultural production adjusted for the associated costs of production, harvesting and inputs.[34]
[34] Rubber is used as a proxy for agricultural production in the model.
Table 6 - Central Scenario Economic Model Results (discounted figures presented in £m); HMG Accounting Carbon Value (low series) and base PIF (0.1%)
Benefit Category				Without programme / (BAU)		With programme	Increment
Protection Forest
	Ecosystem Services			13,767		13,773	5
Production Forest
	Timber (conventional logging (CL)			5,098,254		5,098,561	307
	Timber (reduced impact logging (RIL)			0		713	713
	Carbon			0		24,663	24,663
	Ecosystem Services			30,966		30,978	13
	Conflict			0		5	5
Converted Forest
	Agriculture Latex			602,776		600,671	-2,105
	Agriculture Carbon			2,373,002		2,363,185	-9,817
	Programme Costs			0		-409	-409
Net Present Value / (Net Incremental Benefits)				8,118,765		8,132,139	13,374
BENEFIT COST RATIO							33.69

Under the business-as-usual (BAU) scenario, assuming current trends in deforestation and conversion rates and with conventional non-sustainable logging, the majority of all revenue (95%) would be received by loggers. Conventional logging is projected to generate approximately £5 trillion over the 30 years. Conversion to latex production linked to deforestation generates more than £602 billion over the 30-year period. The model assesses the impact of trends in conversion rates using smallholder natural rubber (latex) production as a proxy for forest conversion crops. These negative outcomes are offset in the “with programme” scenario.
The “with programme scenario” reduces the area of forest conversion, increases the value derived from forests through more sustainable production forests, and increases areas of protected forest. Production forest includes both CL and RIL; adoption of RIL leads to significant carbon monetised benefits and also ESS and benefits of reduced conflict. The model estimates an additional £18m in ecosystem service values and £713m from RIL, £5m in increased productivity due to a reduction in conflict and £24,663m in carbon benefits when using the HMG low series accounting price for carbon. In addition, the monetised value of CL is £307m greater with the programme than without; an increase in CL still leads to net benefits of the programme, as less area is converted with the programme. Net losses in economic activity from reducing forest conversion under the programme are comparatively small at £2.1bn over the 30 years, compared to £602bn overall.
Reduction in conflict is not only included due to improvements in resolving conflict around resource ownership and access, it also of relevance due to broader issues of the paradox of plenty, or the resource curse. This is explored in more detail in the IPE Triple Line report on The Interaction of Multi-Stakeholder Forest Governance with Peace and Conflict from June 2020. The value of this benefit is a proxy for conflict relating to land rights issues valued at £70/ha. More details of the modelling approach are provided in the Economic Analysis Annex of the Economic Appraisal (Annex G).
The value of carbon is included in the economic model, but it has no influence on incentives for forest managers or agricultural crop producers, as this is for appraisal purposes and does not represent a price in a system of carbon payments. If a system of carbon or ecosystem service payments was introduced in countries where FGMC activities occur, for example the sale of voluntary carbon credits or other payments to forest managers for sequestered carbon or ecosystem services provided, this could provide further incentives to protect standing forest. However, the model does not explore distribution of payments and there is no implication of where the finance for such payments would be sourced.
The values of carbon abatement and ecosystem services are generally recognized but rarely paid for, and so these benefits often remain externalities. The model includes a very conservative value of £9.4 per hectare per year to the area of ecosystem services delivered by the programme, net of the area of forest that would be protected without the programme. The carbon value scenarios reflect HMG guidance on appraising carbon, as well as market prices for carbon. Compliance markets generally place higher values on carbon, but these markets typically do not allow nature-based credits, so this scenario is simply provided as a reference. Despite growth in AFOLU credits in the voluntary market, the voluntary market price scenario is relatively low. This value is ambitious compared to the prevailing market price for AFOLU credits such as from REDD+.
Capacity to engage with carbon market is currently limited in most FGMC countries and there is a strong case for multistakeholder platforms to improve governance, rulemaking and participation in carbon markets compared to a typical consultation approach. This would better inform potential market participants of how carbon market mechanisms work and how rules would affect them, improving outcomes in terms of rights, obligations, and benefit sharing. In addition, reducing the perceived risk of reversals and poor-quality monitoring in forest countries would improve viability of selling and could increase prices obtained from carbon credits.
The domain model doesn’t address issues of distribution i.e. who has the right and therefore the entitlement to revenues such as those from carbon or from logging. Regardless, it is worth noting that even if there is only a 1% change to the distribution of revenue from CL and RIL (say from private to government), this would represent over £750bn/yr. Alone, this one year’s worth of revenue growth for government, provided it was collected effectively, would pay for almost twice the cost of the entire programme, even if there was no decrease in the deforestation rate.
Geographic distribution of results should be considered for additional reasons beyond effectiveness in agricultural production and land use change. There is large variation in the underlying parameters across the 18 countries in the economic model e.g. stocking density, timber and income from rubber, production costs etc. The model shows that when smallholder agriculture is unprofitable and logging is highly profitable (as in DRC), halting deforestation and increasing RIL creates high economic returns. In contrast, when agriculture following forest conversion is profitable, but timber has low returns, opportunity costs would outweigh benefits from the value of ecosystem services and carbon. Where economic incentives do not support more sustainable outcomes, policy changes are required using the FGMC approach. Therefore, localised approaches and expectations will be crucial to understanding overall effectiveness in FGMC2.
In line with expectations, as the policy impact and the value placed on carbon declines, net benefits fall. In the most extreme model scenarios, for example where there is zero value placed on carbon and/or the policy impact is very low, some scenarios have BCRs of less than 1, indicating that the quantified benefits of the programme would not outweigh the programme cost. In these instances, greater programme effectiveness than the base PIF rate would be required to break even. This is due to the approach of the model which assesses broad policy impact through the PIF, rather than approximating actual model activities. More detail of the model results and limitations of the model are provided in the Economic Analysis Annex of the Economic Appraisal (Annex G).
Equity
Equity relates to how benefits are distributed amongst the population and between generations as is reflected in the programmes aim to establish forest stewardship. Equity is particularly important for delivering FCDO’s commitment to “leave no one behind”, ensuring UK aid benefits the poorest and most marginalised people. Climate change currently poses a significant risk to the Sustainable Development Goals, making them more difficult to achieve, and it will have disproportionately large impacts on poor people, in particular women and girls.
Many components of FGMC2 can be expected to deliver benefits for the poorest and to marginalised groups. FGMC2 will lead to positive change for both current and future generations, ensuring intergenerational equity. For example, Voluntary Partnership Agreements (VPAs) have the potential to increase transparency and accountability, and to achieve a better balance between public and private goods, more equitable distribution of private benefits, and more civic ways of managing conflicting interests into the long term.
The FGMC programme extension (2021 – 2023) estimated that the 16 countries engaged in negotiating or implementing VPAs – 7 of them supported by FGMC interventions - have approximately 100 million forest-dependent people, all of whom are potential beneficiaries of forest governance reforms being implemented within these countries and could be supported by Phase 2 of the FGMC programme.
The 2017 mid-term review found that one of the most significant achievements of FGMC has been facilitating the inclusion of stakeholder groups who often were previously unable to exercise any significant level of influence in policy making, particularly representation of Indigenous Peoples and SME forest managers and processors. Support provided by NGO grantees has shaped and strengthened the voice of civil society in national-level policy processes across many countries supported. This approach will continue to be central to FGMC2.
A key benefit of the approach is the ability to link different actors working at multiple levels, as set out in the strategic options appraisal. The 2017 review found significant, visible, and widespread evidence of FGMC’s contribution to and influence on establishing new forest governance arrangements and market reforms at international, regional and national levels. The review found strong evidence that FGMC has contributed and will continue to contribute to the outcome areas of improved governance and market reforms that reduce illegal use of forest products. This was further corroborated by evidence in the 2020 FGMC Briefing Note on Policy Influence, and the 2021 ICAI Review which emphasised that the FGMC programme takes a sophisticated approach, engaging with multiple stakeholders across producer and consumer countries and building in clear economic incentives for producers. The ICAI Review noted that work in other forest-risk commodities was not as well developed; the preferred option will incorporate lessons learned into the next phase of programming to ensure effectiveness and scope increase proportionately.
The 2021 ICAI Review also highlighted that the evaluation of the FGMC programme and subsequent research commissioned by FCDO found that partnerships between international, national and local NGOs in timber-producing countries helped to amplify the voice of marginalised forest communities, including indigenous peoples. These partnerships have led to improvements in national policies and improved accountability in national governments and the private sector.
The 2023 Annual Review also found that FGMC grantees have played an important role in informing international policy and galvanising coalitions of organisations around shared objectives, again highlighting the need to include a range of voices. NGO voices were instrumental in drawing EU and member state policymakers to the need for binding rules that ensure deforestation-free supply chains and working in coalitions helped make advocacy efforts more coordinated and consistent, even despite differing perspectives within the NGO community.
According to the 2019 Climate Best Buys, there are strong adaptation and long run livelihood benefits of forest governance reform that disproportionately benefit marginalised communities. However, community-based adaptation is unlikely to happen autonomously due to barriers which arise from market, information, policy and governance failures. The impacts of FGMC involvement in governance reform will help to address these barriers.
FGMC’s monitoring indices to capture transformational change and policy change include equity components, for example assessing rights to forest land, protection of customary rights and community rights in producer countries, as well as worker’s rights in the context of sustainable forest management.
FGMC developed a Gender Equity and Social Inclusion framework to guide the programme. The mid-term review in 2017 found that integrating and mainstreaming gender had limited success, so the framework was updated and outreach by FCDO with delivery partners, accountable grants in particular, emphasised the importance of the framework, with encouraging results. It was most recently updated in 2022 with greater emphasis on political inclusion rather than all aspects of inclusion, given the scope of the programme. The revised framework tracks gender within interventions, voice and representation, policies, and impact. At the national level, FGMC encourages inclusive policy making processes, generates evidence to strengthen a focus on women and other marginalised groups such as IPLC. The updated Gender and Political Inclusion frameworks are at Annex C.
Girls and women in forest-dependent communities are frequently excluded from community and private property rights, rarely own land, or have secure access to forest resources. Management rules may be dependent on gender due to national or community rules. In addition, benefit-sharing is often collectively defined at district, community, or household level, so depending on their voice in these forums, women may not see benefits from collectively agreed arrangements.
Discrimination, lack of rights and security, and limited opportunities keep women in a cycle of vulnerability and poverty. FGMC grants help tackle this through reform of tenure and laws. Actions through FGMC2 will continue support to build the capacity of civil society, research to better understand the human rights implications of customary law for women, legal action to address violations of the rights of women and girls, and support to encourage inclusive national processes that involve women in policy and legal advocacy work. FGMC1 has resulted in significant shifts in legal frameworks, including benefit sharing rules, which will continue in FGMC2.
Box 8: working with women and girls / In Ghana, ClientEarth supports a CSO-led Legal Working Group that is contributing to the revision of the Forest and Wildlife Policy. This has included a legislative audit on gender and community consultations with female-only, youth, and mixed focus groups, to help inform drafting the Forest Code. It recommended that the new policy ensure that all decision-making bodies in the forest and wildlife sector should include women. It identified aspects of the law that unevenly affect women such as ownership of shea trees. This has been included in the Forest Policy with an ambition that women are more likely to benefit from shea exploitation. / In Cameroon, the Rights and Resources Initiative successfully built the capacity of local partners to engage traditional and customary leaders in order to promote greater recognition of women’s rights within local systems of resource management. As a result of this engagement, traditional chiefs are now engaged in partnerships with women’s networks to address land tenure issues.

A challenge for FGMC is its focus on supporting policy issues and processes which emerge from national deliberative processes that are embedded in the social and cultural context of each country and are therefore not necessarily universal or gender neutral. A strong focus of the programme’s gender framework has been on the outcome level and ensuring that gender is actively addressed in terms of both (i) voices engaging in processes and (ii) the substance of the policies under discussion. As such, incorporating gender is an ongoing and continuous process of contextual reflection, analysis, planning and re-planning.
FGMC is not typically involved in supporting the implementation of policies on the ground, and therefore is not directly engaged with end-user beneficiaries and often lacks access to ex-post end user data. Assessing the direct impacts of FGMC on beneficiaries and livelihoods is unlikely to be feasible at the programme level. However, in specific countries and through specific TA projects, FGMC may support and test the roll out of new systems as was the case of MFP3 in Indonesia (2014-2018) who worked directly with around 68,000 individuals, testing approaches to work with small and medium enterprises and community forestry groups. .
FGMC grant holders have a role in ensuring that partners engage with the community in an inclusive, equitable and gender conscious way and, where necessary, support partners to understand their own power in community dialogue. There are annual dedicated gender training workshops for all FGMC grantees, FLEGT facilitators and FGMC staff. These workshops focus on building skills as to how to embed gender into programme delivery, and on sharing knowledge and learning on how gender is included in the participants’ work and how to address gender in reporting.
Finally, as set out in the cost-effectiveness section, the domain model approach does not model the distribution of programme benefits. However, the fundamental principle of FGMC is the multi-stakeholder deliberative process, which ensures that the views of the poorest and most marginalised groups are recognised in policy decisions. FGMC recognises that forest dwelling people are unlikely to change behaviour to reduce deforestation if it harms their economic interests; modelled policy changes do lead to land shifting away from conversion and/or conventional logging, but there is a significant proportion of land which continues to be used for cash crops or as productive forests. The programme does not assume that all forested land must remain untouched to deliver its objectives, as forest dwellers must continue to be at least as well off as they would be without the programme.
Overall Value for Money Assessment
Based on this analysis, FGMC can be confident in delivering a strong positive impact across the 5Es and has a high likelihood of transformational change and low risk of costs exceeding benefits. In the core model scenario, assuming HMG’s low carbon accounting price, £500m of FGMC2 programme spending over a 10-year period is projected to deliver net incremental benefits of almost £13.3bn, with a BCR of 24.55. Using lower carbon values more aligned with those observed in the market still leads to strong positive BCRs and high NPVs, with a proxy for the voluntary market at £8/tCO2 leading to net incremental benefits of over £600m and BCR of 33.7.
The reduction in deforestation of 564,000 hectares as modelled using the base PIF would avoid emissions of 150 Mt of CO2e over 30 years and ensures that over 309,000 people would not suffer the degradation and loss of forests on which they depend. There are likely to be additional, non-monetised benefits from better managing forested land as compared to the degradation caused by conventional logging, and from the activities which would be carried out under FGMC2 but are not encapsulated by the economic model. However, these are not possible to quantify due to the attribution issues and indirect causal chains associated with FGMC’s activities, as discussed in the appraisal case.

## Commercial Case
The Commercial Case sets out the approach to delivering the outcomes outlined in the Appraisal Case. The Commercial Case explains how value for money (VfM) will be achieved when sourcing suppliers, selecting partners, drafting contracts, non-contract MOUs and accountable grant agreements. The Commercial Case also highlights the safeguarding responsibilities suppliers will need to uphold and the key commercial risks that can be expected from the proposed delivery arrangements.
Figure 14 - FGMC2 delivery model
Figure 14- FGMC2 delivery model
As indicated in the Delivery Options appraisal, the FGMC2 components will not be delivered by distinct delivery partners. Rather, successful programme implementation will require delivery arrangements that can work flexibly and respond to needs and demands from partner countries, facilitate political engagement and effective cooperation with Government, civil society, and private sector stakeholders, as well as support international policy processes. FGMC2 will make full use of the multiple instruments available to the programme to deliver on each of the three components’ outcomes, with some instruments contributing to more than one component (see Table 7 and Figure 14). For this reason, the commercial case is set out by delivery instrument rather than by component.
This Commercial Case has been developed in close collaboration with colleagues across the IFU and in Posts and the Commercial Department. It builds from the experience of FGMC1, and the inputs from consultants, organizations, and partners from across the FGMC community of practice, from stakeholder discussions in several partner countries and with other donors working in this domain. Lessons from FGMC1 to inform FGMC2’s commercial approach are summarised in Box 9. To support cross country learning, build coalitions to drive reforms at both national and international levels, FGMC delivery instruments are deliberately designed to work across several countries as this has proved an important means of delivering VfM and improved learning.
FGMC2 will be delivered through 3 commercial contracts, 1 MOU with an international organisation (EFI) and is making provision for potential cooperation agreements with other donors for where the opportunity arises. Accountable grants will be administered through one of the contracts. The three contracts are:
- An outsourced programme management strategic support team (PMSST), which effectively “runs the programme” working closely with FCDO, providing strategic oversight and advice to other delivery partners and FCDO, ensuring coherence, administering the accountable grants programme, and undertaking programme wide MEL functions.
- A Facilitator service, managing impartial facilitators in up to 10 countries (1 per country) to support multi stakeholder deliberations, at the invitation of government. Management of this contract by FCDO is important in reassuring partner country governments given the political nature of the work.
- A technical assistance portfolio manager to procure and manage all long-term TA project contracts with focus partner countries under one contract, where these were previously managed directly by FCDO. This will allow more time for the FCDO core team to engage in national and international policy processes.
An MOU with the European Forest Institute’s International Partnerships Facility (EFI IPF) will provide resources for specialist technical expertise and the creation of an International Forest Governance Hub, which will attract other donor finance and enable impartial high-quality advice to be made available to countries beyond those receiving focused support from FGMC2.

Box 9: FGMC1 Lessons
Outsourced management of accountable grants, programme oversight and monitoring to Pegasys who formed the Programme Management Support Team (PMST) enabled more effective engagement with partner countries and greater capacity to support reform processes and technical projects. It enabled stronger focus on learning and encouraged collaboration between the various projects supported by the programme.
Support to national reforms processes was delivered through various instruments depending on country context, ranging from direct Financial Aid to TA contracts procured directly by FCDO, through International Organizations, to projects managed by DFID country offices. This enabled the programme to tailor support to local donor and country context and advance quickly when needed. The timescales to mobilise TA contracts were often a constraint when the political timing was opportune. Key lessons below, noting FGMC2 proposed to continue these approaches:
- The mix of delivery mechanisms was important for the resilience of the forest governance reform processes. In 2020 in Indonesia when a business faction attempted to undermine the timber legality and sustainability verification system this was successfully countered through a coalition of global FGMC-partners making use of their knowledge, expertise and extensive network.
- European Forest Institute developed a rapid response TA mechanism to mobilise support that helped sustain reform processes working with positive political momentum. Reviews found that the rapid turnaround and ways of working (putting beneficiaries in the driver seat) greatly contributed to FGMC’s impact.
- Pooling resources between donors has fostered coordination, for example in Liberia, DFID was able to pool EU and Norway resources through FGMC action; while in ROC and Vietnam FGMC contributed to actions managed by AFD and GIZ that fostered a stronger focus on governance and practical market linkages. While joint donor action is cumbersome for donors, it works well for partners.
- In Indonesia, long term support for stakeholder driven and owned processes helped drive transformative shift in forest production.
The Accountable grants programme helped create a community of practice connecting stakeholders in various countries and to global initiatives and generating a wealth of intelligence and innovation. The multi-country approach fostered collaboration and extended FGMC’s reach beyond the programme. Investigations by CSO grantees exposed serious criminal activity in the timber sector, leading to strengthened regulation, and in some cases convictions. Grantees' views, especially those of CSOs, sometimes challenged FGMC teams’ which provided counterbalance, ensuring the programme remained responsive to issues on the ground. The shift to outsourced administration of AG greatly improved efficiency and eased pressures on FCDO team.
Dedicated facilitators provided impartial support to stakeholders engaged in governance reforms have been impactful and cost-effective. Through inclusive processes, this has created the space for greater involvement of IPLCs and other marginalised groups. A source of intelligence on governance reform processes, they help the FCDO team better understand national dynamics and coordinate other FGMC interventions. The shift to a multi-country Facilitation Service improved quality of facilitation across all countries, provided greater facility to pivot in and out of processes and fostered great cross-country learning.
Building on the appraisal case and preferred option, the programme team intends to build from FGMC1 established ways of working but with a greater degree of outsourcing of TA project contracting and management as summarised in Table 7 here (noting that the budget figures are indicative and will change with scoping work and more detailed planning upon approval of the Business Case:
Table 7 - Proposed Delivery Approach
Function	Component	Instrument	Process
Outsourced programme management & strategy team (PMSST) responsible for supporting FCDO with programme strategy, programme-wide MEL, managing grants scheme (£12m)	All	Service contract	Competitive tender
Facilitation Services: placement of up to 10 facilitators (FTE) to support country processes (£16m)	1	Service contract	Competitive tender
TA project portfolio manager: outsourcing contracting and management of TA projects & platforms: route determined by need and context likely 15-20 TA projects (£75m)	1,2	Service contract	TA Portfolio manager (outsourced through competitive tender) / They will then mobilise multiple (likely 15-20) TA capacity building projects across multiple countries.
TA delivered through other donors where identified as more efficient to deliver country strategy (£7m)	1,2	MOU with other donor	MOU with donors, where more appropriate to jointly support TA in a specific country. This will be identified during mobilisation.
Accountable grants with about 25 INGOs & business associations multi-country (£58m) PMSST to contract	All	Accountable grants to non-profits.	Competitive accountable grants scheme. Administration, oversight and contracting by the PMSST.
International Partnerships Facility (EFI): multi-donor forest governance knowledge hub & rapid response expertise (£48m)	All	Contribution Agreement with international Organisation	MoU with international organisations, European Forest Institute
Programme-financed roles (Insource) in key Posts supporting policy engagement (£3.2m) [35]	1,2	Fixed-term contract	FCDO HR, up to 7 posts, priority CBS
Evaluation Year 4 £0.5m	All	Service contract	Competition, GEMFA
[35] rationale for insourced roles is set out in the management case and a vfm assessment is available in annex M

### Commercial strategy for FGMC2 programme delivery instruments
The two proposed routes to delivery under the programme are:
    1. Commercial procurement and contract award - where assessments during the Appraisal Case identified that a competitive commercial process is more likely to secure the skills and resources required, where more direct control over delivery by ECED is required and where close positioning with FCDO is appropriate to further bilateral partnership arrangements. FCDO will follow the Public Contracting Regulations (2015) for any procurement and contract award.
    2. Non-contract agreements that establish partnership through Accountable Grants, MoUs and delegated cooperation – where assessment in the Delivery Options Appraisal (Annex E) identified existing institutions with expertise in FGMC2’s thematic areas and a credible track record of programme delivery, that propose programmes that align to the objectives of FGMC2, or where the positioning of the organisation better serves the aim to establish delivery routes that strengthen national stakeholder ownership.
In order to inform the commercial strategy and to help develop specific Terms of Reference for delivery options, a market analysis has been undertaken via in-depth scoping trips to Congo Basin countries, the Mekong, the Pacific and Liberia, a review of lessons from FGMC1 (including FGMC completion reports), review of on-going and previous HMG-funded forestry programmes in Indonesia, Laos, Vietnam, the Congo Basin, West Africa, the Pacific region and Guyana and discussions with other donors working in the same domain (including Germany, the EU, France, Sweden, Norway and NL). Feedback from initial assessments/scoping reviews indicate there is sufficient local expertise and suppliers required to deliver a programme of this nature. This analysis has fed into the choice of route to market mentioned in the sections below. Building on this analysis, a number of Early Market Engagement (EME) events will be conducted with interested suppliers in early 2024, to generate market interest, for the Outsourced programme management support (PMSST), Facilitation Service and Technical Assistance projects portfolio management contracts.
Drawing on the experience of FGMC1, the team will be ready to advance rapidly to market for these three contracts. We will further streamline management functions by outsourcing the administration of TA projects to a TA projects portfolio manager, thus reducing considerably the number of direct contracts managed by FCDO.
DIRECT PROCUREMENT THROUGH CONTRACTED SUPPLIERS
 A. Outsourced Programme Management Support and Strategy Team (PMSST) supporting all programme components)
Overview:
An outsourced programme management support and strategic advice (PMSST) function will be commercially procured to support the ECED team in the overall management of the programme. This role will work closely with FCDO ECED in support of all aspects of the programme: providing analysis and technical guidance, mobilising support for partner countries, and leading programme wide monitoring, evaluation and learning. The PMSST will oversee and mobilise the FGMC’s competitive accountable grants programme. A variety of organisations may be eligible under the grants scheme such as INGOs, policy think tanks or business associations.
Rationale for identified delivery route:
A Programme Management, Support and Strategy Team (PMSST) will be sourced competitively by contracting a supplier through the Public Procurement Regulations and likely via the open procedure. In light of the nature of the role, i.e. working closely alongside an FCDO team in both policy and political engagement, there is no option to deliver this role through a multilateral organisation or a civil society organisation. The need to source a wide range of specialist skills and experience suggests that it would not be feasible to use an existing framework contract to procure these services.
Role & evidence of what has worked:
Detailed Terms of Reference for this role will be finalised upon approval of the Business Case. It will be informed by the existing outsourced programme management support function, market engagement and lessons learnt under FGMC1. See Box 9.
The PMSST will assist in the management and oversight of all components of FGMC2. This will include monitoring, evaluation, and learning, and providing strategic and technical advice to FCDO and programme partners, while ensuring overall coherence with the programme’s Theory of Change. It will also manage a portfolio of accountable grants (approximately 25) on behalf of FCDO across partner countries in Asia, Pacific, Africa and South America. The Accountable Grant Scheme will work to a budget ceiling and fund administration will be managed and reported separately from the fees and costs associated with delivering the programme management. The delivery appraisal sets out the rationale for why accountable grants are one of the preferred delivery instruments (see also Annex E: Delivery Options Appraisal). The Supplier will play a crucial role in ensuring that the results already achieved in phase 1 of the programme at national and global levels will be shared, sustained, and extended to new geographies with increased scope to address evolving threats to and opportunities for forests.
Partner delivery requirements:
The commercial supplier will establish a management and support team with appropriate technical and non-technical expertise, experience, and capacity to administer Grant Funds, knowledge and experience of the priority countries indicated in Annex K (accountable grants scheme) across Asia, Pacific, West and Central Africa and the Amazon, as well as providing technical and strategic guidance, monitoring, evaluation and learning across the entire programme. The PMSST will establish finance administration capacity for grant funds, due diligence and risk management processes, and grant management capacity to deliver against the terms of reference. This management approach was used successfully in Phase 1 and therefore the same approach will be followed for Phase 2. These will be key areas of expertise and capability evaluated within the tender process to ensure the Phase 2 supplier meets these requirements. In order to ensure that programme wide MEL remains as objective as possible, the PMSST supplier is NOT eligible to bid for other contracts (such as for the TA portfolio manager or Facilitation service). Further details are provided in the Management Case.

B Facilitation Service: of multi-stakeholder processes (Component 1)
Overview:
A Facilitation Service will be commercially procured to support national multi-stakeholder reform processes under Component 1, building on experience from phase 1. Facilitators will have a particularly important role in countries where the UK has established voluntary partnership agreements (VPA) linked to the timber trade. The facilitation service will mobilise up to 10 FTE country-based facilitators in the first 5-year period (approximately £16m) with a view to further expansion as the programme grows (Annex H: partner country analysis and engagement plans, indicates where Facilitation Services would be valued).
Rationale for identified delivery route:
The Facilitator role as envisaged under FGMC2 is critical to supporting an inclusive multi-stakeholder process. The Facilitators will be supporting often politically sensitive processes and as such, a Commercial Supplier contracted directly by the FCDO is more likely to be seen as accountable to the process than other more arms-length arrangements with International Organizations. Attracting a range of bidders for this Tier 1 delivery role with the specialist expertise required for this service will be a priority.
Role & evidence of what has worked:
Upon approval of the Business Case, the FGMC team will develop and finalise TORs for the Facilitation Service, drawing on experience from FGMC1, market findings, discussions with Government counterparts in Tier 1 and Tier 2 countries (Annex H: partner country analysis and engagement plans) and Posts.
The Supplier will report directly to the FCDO FGMC Team providing real time political economy analysis whilst maintaining as far as possible the impartiality of the facilitators in-country. The Facilitation Service will deploy Facilitators across 10 countries initially, with the potential for more once Tier 3 countries are identified.
The Supplier will work closely with the PMSST in developing the programme-wide MEL, and to provide assessments of progress that will inform FGMC2’s ICF KPI reporting, monitoring progress at national level through country specific TOC (see Annex F: ToC and results framework & Annex L: approach to MEL)
Partner delivery requirements
The supplier will establish country-based facilitators and offices in indicated priority countries as well as backstopping services that enable cross country learning and engagement with FGMC2’s community of practice. The quality of the Service is wholly dependent on the individual facilitators and their “fit” with local circumstances in each country. Partner governments will be asked to validate the placement of selected individuals.
A facilitator requires strong interpersonal, analytical, strategic, communication and coordination skills, to enable them to build an understanding of the forest sector as well as the wider political economy. A facilitator can be a national or non-national, but their perceived impartiality is essential for their ability to work effectively. Any Supplier will need to have the ability to recruit and retain such individuals.
### C.TECHNICAL ASSISTANCE PROJECTS PORTFOLIO MANAGEMENT CONTRACT (components 1 &2)
Overview:
Appraisal of delivery options identified the importance of providing technical assistance to partner countries in as flexible and timely a way as possible, providing countries with choice depending on the needs they prioritise. FCDO will contract a TA portfolio manager who will commercially source TA projects in support of agreed national strategies. In some circumstances TA projects may be supported through alternative arrangement where joint donor support would be more appropriate. These would be through third party non-commercial contract routes such as MOU arrangements.
A commercial supplier will be procured to deliver long term TA projects in support of partner government reform processes. A wide range of TA will be provided according to need and demand including supporting government capacity to regulate, building traceability systems, organisational development, building capacities of trade associations and of CSO’s to engage in policy. The supplier will ensure the provision of technical assistance, capacity building and analysis on a demand-led basis, ensuring it is tailored to country context, aligned with partner priorities and informed by TORs prepared by the PMSST (FGMC country team) to support the country TOC and strategy. Decision-making on contract award will be the responsibility of the FCDO programme team and in some instances will include partner Government representatives.
Delivering via a commercial supplier will allow specialist staff to be contracted, providing services in multiple countries. This will provide ECED with flexibility to handle delivery and other issues as they arise and will reduce the programme management burden for ECED allowing a greater strategic oversight role.
#### Rationale for identified delivery route:
Under FGMC1 long term TA contracts were directly managed by FCDO providing bespoke TA services in a number of countries with as many as 7 TA contracts operating at any one point in time. Delays in our procurement process were in some cases a problem for programme delivery. With the increase in the number of countries, ECED does not have the capacity to procure and manage individual long term TA contracts directly across as many as 16 countries. For this reason, FGMC2, will outsource management of TA to one commercial Supplier responsible for procuring tailored TA projects.
Role & evidence of what has worked:
Experience under FGMC1, demonstrated the importance and value of the partner country being in the driving seat when it comes to the identification of needs and the development of ToRs. TA projects co-designed by FCDO with partner governments, delivered by a Supplier but co-steered by partner governments, led to a high degree of government ownership. FGMC2 seeks to build on this approach. However, the long time periods to procure and mobilise through FCDO process posed a challenge for programme delivery, outsourcing this function could improve efficiency.
The role performed by the commercial supplier will be finalised after business case approval with inputs from Commercial Directorate as we work through commercial governance processes. This will be set out in a clear term of reference that will form part of the contract with the supplier. The likely responsibilities for the commercial supplier will include:
    1. Overall management of TA contract funds reporting regularly to FCDO. The supplier will be responsible for all disbursement, due diligence, and fiduciary oversight of all downstream spend.
    2. Procuring, managing, and overseeing TA project requests as indicated in TOR that have been agreed between FCDO and partner Governments. In most cases TA projects will be overseen by a Government- FCDO (or PMSST) steering committees.
    3. Providing FGMC country oversight team with reports of ongoing activities on a quarterly basis and ensuring they remain engaged in the programme.
#### VFM and cost drivers across all 3 commercial contracts
The commercial approach will achieve value for money predominantly in the areas of economy and efficiency.
Table 8 - VFM Commercial Approach
Economy	Will be achieved through a competitive approach to market, commercial assessment of bids and commercial criteria in the assessment of bids, and benchmarking of fees and costs. These elements will drive down supplier costs
Efficiency	Will be achieved through management of the supplier, best practice in the contract model to incentivise a flexible and efficient programme management service. It will build from FGMC1 best practice lessons to mobilise and advance processes as efficiently as possible.
Effectiveness	Will be achieved through the programme theory of change, which is well evidenced and demonstrates that public funds can be used to influence policy and institutional shifts at national and international scales. It will improve the quality of policy processes strengthening ownership and legitimacy of reforms, thereby increasing the likelihood that they are sustained and implemented. The multi-country framing for these contracts have demonstrated effectiveness delivering greater cross-country learning. Lessons learned will be taken from Phase 1 and applied.
Equity	Will be achieved through the programme strategy which is focused on engaging and building capacities of IPLC, small businesses and other marginalised groups. Facilitation and TA contracts will be framed by the Gender and Inclusion Strategy which emphasise voice, rights and benefits and support to inclusive processes

#### Cost drivers and cost control across all 3 commercial contracts
The primary cost driver is likely to be the sourcing of expertise and associated fees, costs of deployment including potentially the setting up of country offices, travel costs, provision of training and learning events, and IT equipment. The costs of operating in priority countries will vary, with operations in fragile countries being more substantial.
The cost of sourcing expertise is particularly relevant with the PMSST contract which requires a balance of programme administration and technical sector expertise on forests, forest carbon, development, governance, trade and market analysis, private sector engagement, social and environmental expertise. To increase effectiveness, and encourage a wide pool of expertise, the Supplier should reflect on the breadth of countries where the programme may operate and consider national experts as a means to reduce the costs associated with sourcing international expertise. Phase I experience will support benchmarking of fees alongside the experience of other forest-related programmes supported by HMG.
Additional cost drivers associated with individual contracts include:
    1. For the PMSST: the costs of expanding to new regions such as the Pacific, with associated travel costs for programme management and monitoring.
    2. For the Facilitation Service: Depending on the local political context, the Facilitation Service will be encouraged to recruit national experts where feasible which would reduce costs. Based on experience from FGMC1, facilitators can successfully be a national or non-national, but their perceived impartiality is essential for their ability to work effectively.
    3. TA contract: Depending on the local availability of expertise, the TA supplier will be encouraged to recruit national experts which would reduce costs. Based on experience from FGMC1, capable local TA service providers are available and can be included as part of consortia.
#### Programme sourcing strategy, & route to market for all three commercial contracts
Procuring via a tender process is the preferred approach for all three commercial contracts. It will ensure the eligibility of the best equipped organisations and increase the ability of the FCDO to access the best expertise in the supplier market. Interest is likely from a number of international development service providers, including FCDO top suppliers, as well as a more specialised set of service providers focused on the forest sector. The assumption that there is sufficient/strong market interest is made based on experience with FGMC1 and of other HMG supported forest programmes, from discussions with other donors currently supporting similar programmes, as well as informal expressions of interest to the SRO enquiring about the prospects for a future programme.
Early market engagement has also commenced to gauge the level of interest in the three commercial contracts, inform the market about the scope of the contracts and requirements, and to inform the development of the terms of reference for each contract. In the case of the Facilitation service contract, discussions will be held in priority countries with stakeholders to assess the potential and role for Facilitation. Early market engagement will test market appetite and capability to provide TA across a large number of countries, a wide range of technical areas, and in close cooperation with partner countries, often with partner governments co-steering the TA projects.
For the Technical Assistance contract, following approval of the business case, ECED will work with our Commercial Adviser to finalise a decision on the commercial delivery model and create a sourcing strategy. The strategy will propose a procurement route along with the selection and award criteria to be approved according to the appropriate FCDO commercial governance process. We anticipate a procurement process being followed that will take approximately 12 months. A key consideration during procurement will be the flexible nature of TA delivery and the need to work across up to 16 countries with fairly specialised skills.
Draft Terms of Reference for all contracts will be shared with the market for feedback. Tender evaluation criteria and weighting will be developed in conjunction with the terms of reference for the contracts, balancing the quality of the team, relevant experience, ability to deliver the required range of services and any commercial aspects of the bid. Evaluation criteria and TOR will be agreed in consultation with FCDO Commercial advisers.
As adopted in Phase I, it is expected that a combination of KPIs and milestones will be used to manage supplier performance, to be confirmed in consultation with FCDO’s Commercial Delivery team. Tender evaluation criteria and weighting will be developed in conjunction with the TOR for the work stipulated under each contract, balancing the quality of the team, relevant experience, ability to deliver the required range of services and commercial aspects of the bids.
Options to scale-up or scale-down the contract will be set out in the terms of reference with guidance from Legal services on wording. The contract will also have provisions to allow for extension options (both in time and value).
#### ECED oversight and supplier management across all 3 commercial contracts
Supplier performance will be managed in line with prevailing FCDO guidance and practice. Contract models to incentivise continuous improvement and drive learning and performance will be considered. Poor performance will be managed through improvement plans, escalation as required, and potential termination of the contract. Contract managers will complete the appropriate CMCP training.
All contracts with commercial suppliers will incorporate a performance-based element where feasible, incorporating KPIs and/or milestones that reflect feedback from the FGMC community of practice in the priority countries. KPIs will be specified in the contract, ensuring the supplier demonstrates high standards in programme management, including mobilisation of experienced facilitators, timeliness and quality of reporting and finance administration, safeguarding, and cross-country learning. In the case of the PMSST contract, specific attention will focus on effectiveness in mobilisation of the Grants scheme and programme-wide learning. Additionally, due to the close working relationship with the PMSST function, and regular in depth meetings covering all areas of their workplan, experience has indicated that this approach provides a high level of oversight on supplier performance.
As the Facilitators working under the Facilitator Service do not contribute to specific outputs, rather they assist national stakeholders to engage and drive reform processes, an output-oriented contract model would not be appropriate rather would be paid on fees and expenses. Reporting arrangements will be agreed with FCDO and will include confidential “intelligence briefs” providing FCDO intelligence on national processes as well as quarterly and annual updates of the national processes that will contribute to programme-wide annual reporting.
Depending on the approach taken, the contract with the commercial TA Projects Portfolio Manager supplier will incorporate performance based KPIs responding either to procurement, management, and oversight of TA contracts, and/or the delivery of the contracts, incorporating KPIs and/ or linked to milestones that reflect feedback from the partner countries in receipt of the TA services.

DELIVERY THROUGH THIRD PARTY ORGANISATIONS: non-contract arrangements
### D. Joint Action with other donors (components 1&2)
#### Rationale for identified delivery route
TA support to forest governance reforms may be delivered through a joint funding arrangement with other donors where opportune, and efficiency gains are evident in specific country contexts. Where other donors are supporting forest sector reforms, where there is sufficient alignment to FGMC2’s objectives, and where partner countries want development partners to be more joined up, the FGMC team will explore options for delegated cooperation through MOUs. Under FGMC1, we worked jointly with Germany, France, Norway and the EU in Guyana, Liberia, Republic of Congo, Cameroon, and Vietnam.
Pooling resources between donors supporting national governance reforms helps foster a coordinated approach and may also influence other donors to place a stronger focus on governance, on multi-stakeholder deliberations to drive reforms and to invest in connecting sectoral reforms to international market requirements. While joint donor action is bureaucratic, it tends to work well for partners. FGMC2 will explore opportunities for joint support that stimulates new ways of working during the inception period.
Scoping for the development of the FGMC2 Business Case has identified an interest in a joint approach in Vietnam where Germany has an established forest governance programme assisting the Ministry of Forestry A joint approach would enable FGMC2 to more rapidly to establish a working relationship with the Ministry. During the inception period we will explore options for joint action with other donors in other geographies (Annex H partner country analysis and engagement plans, identifies opportunities for cooperative action).
Partnering with a selection of like-minded donors will enable the UK to align and pool its funding and minimise fragmentation.
Role & evidence of what has worked:
Delivery through other donors is an option that the FGMC2 team will explore during the inception period. The ECED team, together with colleagues at Post have extensive experience and networks to explore options upon approval of the Business Case and the development of detailed country strategies, building from initial scoping set out in Annex H (partner country analysis and engagement plans). The partnerships established through MOU arrangements will also allow the UK to align funding with other donors. Specific Terms of Reference, roles and responsibilities and arrangements will be developed in the first few years of the programme.
#### Partner delivery requirements
### FCDO will be supporting the work of existing organisations and existing programmes which are aligned with the aims of the FGMC2, so responsibility for delivery will be delegated to partner donor’s delivery organisation. FCDO will participate in relevant governance arrangements, including project steering committees.
### E. Joint action with the European Forest Institute’s International Partnerships Facility (components 1&3)
#### Overview:
A new MOU agreement with the European Forest Institute’s (EFI) International Partnerships Facility (IPF) will be agreed to secure forest governance expertise and a new knowledge hub that supports all components of the programme. EFI is an International Organisation specialised in forest policy and research (to which the UK is party through international treaty). It is a global centre of knowledge that supports policy and governance reforms. It draws on its in-house expertise to facilitate partnerships between producing and consuming countries to foster legal and sustainable production and provides guidance to over 20 tropical forested countries. The IPF has developed specialist expertise in traceability systems, interactive forest and land-use planning tools and forest governance monitoring as well as more general knowledge on forest governance and deforestation. The IPF is uniquely positioned to provide science-based technical support to countries re-tooling their forest regulation and monitoring systems.
Since 2012, FGMC1 has worked with EFI. Building from successful partnership under FGMC1, ECED will work with EFI IPF upon approval of the business case to finalise its proposal for continued support to producer countries. The EFI IPF will maintain its core team of experts to supply expertise at pace (mobilising within weeks) in response to partner country requests for advice and information to inform policy development, whilst also supporting FCDO/IFU needs for analysis to inform our engagement in global processes. This rapid response mechanism has been widely praised by FGMC1 partners for: the quality of expertise, the short mobilisation time and its stakeholder-led approach to delivery. This has helped FGMC to secure strong partnerships with countries who particularly appreciate its responsiveness.
EFI IPF will also further develop, together with ECED, the proposal for an international forest governance policy hub (IFGH). This would have a core team of experts and would establish a wide network of associates building from EFI’s model for engagement with policy makers and research bodies. It will draw from the extensive stakeholder consultations in developing countries conducted over the past year. The Hub would provide a platform that other development partners could buy in to (through a multi-donor pooled fund). It would play a critical role in enabling the scale up of FGMC as set out in Component 3 of the programme. As indicated in the Appraisal Case and the Theory of Change, Component 3 focuses on shifting international norms and policies for global impact. A multi-donor mechanism will support international engagement (Component 3), providing both impartial evidence and guidance that is decoupled from bilateral engagement as well as a mechanism to expand the reach of FGMC2 through additional resources from other donors and international partners.
#### Rationale for identified delivery route:
Based on experience from FGMC1, as well as early scoping discussions in preparation of this Business Case, we know partner countries are likely to identify specific highly technical or analytic requirements. EFI IPF are well placed to respond rapidly while longer term TA is designed and mobilised (which would then be delivered through contracted TA projects) as well as to provide impartial advice for highly technical service delivery oversight (for example when countries mobilise IT-based tracking systems EFI has provided timely guidance to help partner Government monitor and oversee contract performance). In some instances, and for sensitive domains, partner countries sometimes prefer a non-commercial route to advice, and the EFI IPF have established their reputation as impartial from specific schemes or technologies. As a well-established International Organisation, with highly specialised expertise, and a good track record with FCDO and with partner countries, securing a new MOU Agreement with EFI IPF will provide an important delivery instrument to support action under Component 1 and 3 that can be mobilised very rapidly and complements other delivery instruments of FGMC2.
An MoU, agreement with EFI IPF would be established soon after business case approval and due diligence checks are completed. This would allow the programme team to rapidly mobilise technical expertise in partner countries alongside the development of Country-specific roadmaps to carry forward governance reforms (see Annex H: partner country analysis and engagement plans, where need for rapid deployment of technical expertise has been indicated).
#### Partner delivery requirements:
FCDO will be supporting the work of an existing organisation and an existing programme aligned with the aims of the FGMC2, so responsibility for delivery will be delegated to EFI IPF. FCDO will work jointly with EFI IPF to ensure that its proposed work is aligned with the aims of the FGMC2. FCDO will participate in relevant governance arrangements for the multi-donor fund. EFI IPF will coordinate its action across the FGMC2 programme liaising closely with the PMSST through quarterly updates and annual meetings. The PMSST will provide any necessary monitoring of delivery in partner countries. Management arrangements are indicated in the Management Case. The details of the arrangement will be finalised upon approval of the Business Case and following FCDO guidance on engaging with International Organisations
#### VFM of third-party non-commercial delivery routes
The approach will seek to achieve value for money in the following ways:
Table 9 - VFM Non-commercial Routes
Economy	The proposed routes are through non-profits. Scrutiny of fees, salaries and costs prior to signing agreements will help to ensure economy. FCDO will ensure that partner procurement process and contracts are fully aligned with FCDO requirements and guidance. / For working with other donors, where feasible, we would work with FCDO established cooperation frameworks. There will also be economy for partner countries experiencing reduced transaction costs if actions are more coordinated amongst donors, in alignment with DAC Paris rules. / Establishing a Facility alongside an existing initiative should allow for reduced costs particularly linked to overheads
Efficiency	Assurance over efficiency will be provided through the track record of other donors’ delivery partners as well as the efficiency gains of joint rather than overlapping donor efforts. / Due diligence of international organisations will help to ensure efficiency. / Pooling resources with other donors, improving coordination and designing an instrument that directly speaks to the needs of participating partner tropical forest governments will bring efficiencies.
Effectiveness	Will be achieved through ensuring that Terms of reference for any analysis or TA are co-developed by partner country stakeholders, and steering committee structures are overseen by partner governments and the PMSST or FCDO. / Pooled resources will increase the scale and impact of interventions and place governance reform at the centre of other donor initiatives, thereby amplifying programme impacts. / Valuable lessons learned from FGMC1 implementation will support the development of ToR and ways of overseeing the contracts that will optimise effectiveness.
Equity	Will be achieved through placing country stakeholders at the heart of delivery enabling them to drive the technical assistance provided. Procurement of locally available experts will also be a feature of the TA, ensuring the programme strengthens capacity and profile of local expertise. / Efforts to develop and implement governance impact monitoring at global scale will place increasing focus on questions of equity.

#### Cost drivers and cost control of MOU arrangements
Across the MOUs, cost drivers include the costs of providing Technical Assistance, sourcing of expertise (locally and internationally), logistical costs of supporting field activities in forest areas, travel for cross country learning, security, meeting and conference costs, information sharing, monitoring, and audits. Cost control measures will include competitive procurement of any specialist expertise not available in house and working with national staff, reducing reliance on international staff where possible. Other donors may have higher overheads and costs than FCDO is accustomed to. However, sharing costs with other donors may also introduce efficiencies and effectiveness by reinforcing existing efforts and promoting greater coordination and coherence between initiatives. In the case of the International Forest Governance Hub with EFI IPF, costs will be shared with other donors, and efficiencies will be made by promoting greater coordination and coherence between initiatives.
#### Programme sourcing strategy and Partner arrangements
Following approval of the business case, FCDO will:
    1. work to finalise and confirm the arrangement (MOU contribution agreement) with EFI, for final sign-off at the relevant level of delegated financial authority. This will include a clear plan for the development of the proposal for an International Forest Governance Hub including convening other donors. The FCDO programme team will work with FCDO Commercial to ensure that all necessary processes are followed to finalise the MOU agreement.
    2. Identify potential opportunities for cooperation with other donors, in the development of country specific strategies (as indicated in Annex H: partner country analysis and engagement plans). This process will continue throughout the programme as our engagement deepens.
#### Partner and supplier management
In the case of the two non-commercial delivery instruments, ECED will ensure oversight through regular progress meetings against agreed workplans, and that all instruments are working closely with the PMSST to align with programme ToC and MEL requirements. Any support through these delivery routes will respect the principles of national ownership framed and led by national stakeholders as indicated in the Management Case.
Due diligence will be carried out or refreshed prior to entering into any MOUs to ensure that the Organisations policies still meet FCDO safeguarding, fiduciary and commercial requirements. This will include an assessment of procurement capability.
### Mobilisation and phasing of contract and non-contract agreements
Mobilisation and procurement will commence following business case approval. The use of different funding instruments means that some activities have potential to start quickly, enabling the FGMC team to engage with partner countries to scope and prepare future partnerships that will frame support to policy reforms, while long-term arrangements to support implementation are put in place. Mobilisation and inception timelines will vary across partner countries advancing more rapidly where action builds from the work of FGMC1 and networks, analysis and plans are well advanced.
As indicated above, instruments requiring a tender process will take approximately one year to mobilise and establish. Drawing on the experience of FGMC1, networks, systems, lessons will be used to make the procurement, contracting and mobilisation as efficient as possible. The mobilisation of the outsourced programme management function will be most critical in terms of timing, as the mobilisations of other delivery instruments will be supported by this function. The ECED team will advance the preparations for that procurement process prior to the approval of the Business Case so that the process may launch as soon as possible thereafter. Phasing of the various instruments is set out in a Delivery Table in the Finance Case (para 399).
#### Due diligence of suppliers
Due diligence will be undertaken prior to entering into agreements, to ensure that partner organisation policies meet FCDO safeguarding, fiduciary and commercial requirements. This will include an assessment of procurement capability, where the organisation may be required to procure goods and services, to ensure alignment with FCDO’s commercial requirements, guidelines and best practices. Due diligence will also cover the supplier’s governance structures and controls, capability to deliver and financial stability.
Tier 1 suppliers will also be required to undertake their own due diligence on any sub-contractors/grantees that it intends to appoint to support programme delivery, and cascade safeguarding requirements down where necessary. To ensure that this due diligence is sufficiently robust, due diligence requirements of downstream suppliers will be specified in contract and non-contract agreements.
#### Key terms in contracts and non-contract agreements
Following due diligence checks and appointment, Tier 1 suppliers will be awarded contracts or non-contract agreements that accord with prevailing FCDO guidance and practice. Suppliers awarded contracts will use the standard FCDO terms and conditions. This ensures key provisions and requirements which are oriented towards incentivising performance, continuous improvement, value for money and acceptable levels of risk for FCDO. Delivery partners working through non-contract arrangements (grants or MOUs) will use the FCDO’s standard accountable grant template, the relevant MoU templates or delegated contribution agreements that meet FCDO requirements. All these agreements will include the standard key provisions and requirements to advance value for money and acceptable risk.
##### Flexibility, amendments and extensions
As a programme seeking to influence forest and land governance, policies, rules at national and international scale that drive transformation in the use of forests, FGMC2 is envisioned to be a genuinely adaptive programme. Indeed, FGMC2 seeks to enable possibilities for combining central programme funding with funding from posts, and other donors.
Contracts and non-contract agreements will need to be agreed with sufficient built-in flexibility to enable learning, pooled funding, and to be scale-up and down as appropriate. Dimensions of flexibility will be set out clearly in terms of reference and the contracts will contain clear, precise and unequivocal provisions to amend and extend (both in time and value). FCDO Legal and Commercial Advisers will be consulted for guidance on wording in both the terms of reference and contracts. In practice, contract amendments and extensions will only be considered if they clearly represent VfM, the reference and scope of the programme components remain consistent with the original procurement, and amendments can satisfy FCDO commercial rules and procedures.
Phasing: We propose to deliver FGMC2 in two tranches. The first period will run for five years. Depending on results of FGMC2’s year 4 review and Minister’s decision on subsequent budget scenarios. We will work with commercial colleagues to ensure that MOUs and contracts align to this phased approach.
#### Safeguarding responsibilities
FGMC2 tier 1 suppliers must have adequate safeguarding policies, procedures, and measures in place to protect beneficiaries and staff. Organisations contending to be suppliers of programme components will be required to provide their safeguarding policies and a clause will be included in contracts and non-contract agreements to ensure that safeguarding requirements, along with whistleblowing and complaint procedures, are adequate. Additionally, the capacity of tier 1 suppliers to install, monitor and respond to safeguarding measures will be assessed as part of the due diligence checks that will take place prior to the signing of contract and non-contract agreements. Contracted suppliers will also be expected to adhere to the FCDO Supplier Code of Conduct and other standard FCDO safeguarding policies.
The FCDO Programme team will draw on FCDO guidance and the expertise of safeguarding champions to ensure that best practice is followed. Indeed, the FCDO programme team will ensure that they complete all mandatory safeguarding and SEAH training and fully understand their roles and responsibilities in respect to safeguarding.
Key commercial risk
Commercial risks relating to FGMC2 are presented in 10 along with proposed mitigations. These feed into the full risk register set out in Annex O (Full risk register). All commercial risks at the programme and project level will be captured on a risk register on AMP and regularly reviewed and updated.

Table 10 - FGMC2 Commercial Risks
Risk	Mitigation
Changes in political-economy contexts in partner countries hinder FGMC2’s ability to effectively support sector governance reforms requiring the programme to amend strategy and delivery plans including exit from countries if significant changes occur.	In preparing for FGMC2, the Business Case builds from political economy analyses for each of the priority countries (see Annex H: partner country analysis and engagement plans) and has built PEA into programme monitoring. The delivery instruments have been selected and will be procured and mobilised specifically with the need for flexibility to adapt to changing political and economic circumstances and opportunities in mind. All sub-contracts will include clear provisions to stop or adjust planned action according to circumstances and need. All programme instruments work across multiple geographies which should provide the necessary flexibility and resilience. / ECED will ensure that all contracts, MoUs and grants include clauses that allow for an exit if needed. At programme level risk will be mitigated by the portfolio of actions across multiple geographies
FGMC2 may work in a few post conflict country contexts where forest land use may remain contentious: while they offer important opportunities for forest governance reform they also entail heightened delivery risk	The instruments and governance structures established to support reform processes in these contexts will require skills in conflict sensitivity analysis and specific strategies to address heightened risks, and requiring close monitoring, reporting and management. Nonetheless the FGMC approach fostering inclusive processes and supporting a wide spectrum of stakeholder perspectives has particularly where focused on forest rights and benefits has helped to resolve disputes and create opportunity for greater accountability
Limited market interest in the opportunities to support the management and administration, of the programme with a risk that limited competition reduces our ability to appoint a strong organisation.	FGMC1 has an established pool of interested Suppliers for various aspects of the programme. Early market engagement will increase awareness specifically regarding the procurement opportunities under FGMC and prepare the market to respond. ECED will work closely with PCD during this process, including to understand market capacity and latest procurement trends.
The expansion of FGMC2 to cover more geographies, overstretches the ECED team’s capacity for programme oversight.	ECED will monitor and review capacity for oversight and will explore alternative arrangements with Posts to strengthen FCDO capacity, if needed. Programme reviews will afford opportunity to scale back the breadth of the programme should the delivery approach prove too challenging.
Delays in FCDO procurement processes delay FGMC2 delivery.	ECED will work with PCD to set out timescales and deliver procurements. Where possible, ECED will mobilise a variety of delivery routes to allow for early action while longer term procurement is underway. ECED will reprofile programme budgets should timescales slip.
Awarding accountable grants is delayed due to a lack of interest or quality projects, or lengthy assessment and mobilisation processes leading to budget management issues and impacting FGMC2’s delivery.	ECED will work closely with the PMSST supplier to ensure that a balanced process is established that allows decisions to be taken effectively and efficiently, avoid weak proposals receiving support, and help put in place the right support to the grantees to strengthen delivery and management of HMG funds. ECED will have the final decision-making responsibility for approving grants and will work with the PMSST supplier to ensure sufficient information is provided in an accessible format that allow ECED to make well-informed, robust, and swift decisions. ECED will monitor programme budget spend and reprofile as needed (see Management Case).
International Organisation (EFI) capability and interest to deliver international forest governance hub .	Due diligence will be undertaken prior to any agreement, to ensure the partner organisation’s systems meet FCDO standards, such as safeguarding, modern slavery, anti-corruption, fraud, bribery and risk management. Delivery chain mapping, due diligence and monitoring will be used to manage delivery risk
There is a risk that UK/FCDO is unable to attract other donor investment into the EFI IPF International Forest Governance Hub and is therefore left exposed - providing most of the funding.	Initial discussions with other donors have indicated an interest in pooling resources. The International Forest Governance Hub has a purpose to distance itself from the direct steer of individual bilateral donor agendas, and to provide independent advice to partner countries. This approach diminishes risk to UK in the unlikely event the EFI are unable to attract other bilateral finance. The Hub purpose will deliver, with or without other donors.
Partners are unable to deliver activities on time, resulting in programme underspend. This will be highest during years 1-3 of the programme but is anticipated to smooth over time (see Financial Case).	The principal risks relate to the time taken to mobilise and establish the team and systems required to deliver the programme, and the performance of the contractor during implementation. Delivery chain mapping and due diligence and monitoring will be used to manage delivery risk. / The primary commercial risks relate to partner commercial capabilities. Due diligence will be undertaken prior to the award of grants and contracts, to ensure commercial policies in partner organisations meet FCDO standards. Delivery chain mapping and monitoring will be used to manage delivery risk during implementation. / ECED will agree a workplan with each Tier1 delivery partner that will be regularly updated at least annually. Each workplan will set out budget requirements for each partner against a set of planned activities.
Other donor’s partner capabilities and the complexity of bureaucratic arrangements may make delivery cumbersome and inefficient.	Due diligence will be undertaken prior to the MOU arrangement with any other bilateral donor, to ensure commercial safeguarding, fiduciary and commercial policies of other donors meet FCDO standards. DD is already in place for bilateral organisations such as GIZ, likely to be one of the first donor partners. Delivery chain mapping and due diligence and monitoring will be used to manage delivery risk during implementation.
FGMC2 will deliver beyond the current spending review period and under future spending reviews, may not secure the funding required for the proposed scale of delivery.	ECED will include clauses within agreements with each partner to allow ECED to reprioritise delivery in light of reduced budgets or exit projects and/or the programme early if needed. / ECED will use evidence generated under the programme and the findings of annual reviews to inform any future decision making during this process.
Misuse of advance payments.	We do not plan to pay in advance of need under FGMC2– this will be the default position. If a strong justification for this is presented, ECED will ensure that clawback clauses are included in any agreement, a detailed workplan is agreed, regular progress meetings are held, payments are limited, and a final payment is made against a final report’s delivery.
Transition from the first phase of FGMC1 to new phase poses a risk of disruption to on-going reform processes and rupture of effective working relationships with key stakeholders	A Bridging arrangement (through a MOU) working through the international organisation EFI has been developed to extend contracts and grants in critical geographies for 2024 drawing from funds of FGMC1 and an agreed workplan that may be mobilised as soon as the FGMC2 Business Case is approved to sustain technical as sistance and avoid risk of rupture of ongoing processes while the more detailed design of new actions is designed throughout year 1

## Financial Case
#### Affordability, Budget timeframes and phased approach
This is a £500m, 10-year Business Case, of which we are currently seeking approval for £220m over the first 5 years. FCDO will provide up to £220m of RDEL funding over a period of five years from 2024. The long-term commitment of £500m funding in support of forest governance reforms was announced at COP26 and will contribute to the ICF nature and forest funding commitments and to commitments announced at COP26. The Concept Note for this £500m Business Case was included in the consolidated set of pre-COP approvals agreed by FCDO Ministers (and HMT) in November 2021. The programme is affordable within the ECED budget, subject to decisions of future Spending Reviews.
The concept note for FGMC2 was approved as a ten-year programme of up to £500m in spend. The longer programme cycle reflects evidence of the time required to achieve impact in the forest and land use sector, particularly in supporting transformational shifts in sector-wide national scale forest governance which implicate legal and regulatory reforms, retooling forest management and business practices. Such reforms require signals of long-term engagement for them to be implemented through several political cycles to achieve lasting impact.
To ensure that Ministers have oversight of spend and strategy over this length of programme cycle, financial approvals will be set out in two five-year tranches. The division into tranches provides scope to adjust programme strategy, secure approval for new partnerships, instruments and approaches to delivery developed during Years 1-5, and support responsive and adaptive management. Further information on the programme’s management approach can be found in the Management Case.
On this basis, this Business Case seeks approval for a five-year tranche of up to £220m. Based on programme performance and continued need and relevance, officials will submit a Business Case addendum to Ministers in Year 4 to seek approval for a second tranche of funding covering the second five-year period.

#### Budget classification
Funding for FGMC2 will come from the budget of ECED and will be entirely classified as Official Development Assistance (ODA) and International Climate Finance (ICF). The programme is classified as 100% ICF spend as all components have strong climate objectives and expected climate results contributing equally to adaptation and mitigation objectives. All programme funding will contribute to the £3bn ICF Nature Commitment and the £1.5bn ICF Forest Commitment.
The programme budget will use RDEL as FGMC2 is a technical assistance intervention that will not create any tangible capital assets that would be owned by the programme and used over the long-term. FCDO funding will be used by suppliers and grant holders to provide services for technical assistance, evidence gathering, research, monitoring and evaluation, south-south learning, knowledge dissemination and stakeholder engagement, communications, and management. As the programme develops, the programme team will review its planned research and development to consider whether it might be classed as intangible asset CDel, however based on current programme scoping the planned action primarily capacity building should be fully classed as RDel.

#### Contribution to HMG funding pledges made for COP26
As highlighted in the Strategic Case, FGMC2 expects to contribute to HMG ICF forests and nature funding pledges made for Indonesia (£350m), the Congo Basin (£200m) and Amazon region (£300m), as well as IPLC Forest Stewardship (£163m ($224) all of which pledge funding over a five-year period from 2021-26.
BUDGET PROFILE < PLANNING AND FORECASTING
### Overview of funding currents
Tranche 1 will have a 5-year budget of £220m. Figure 15 illustrates the delivery structure through key instruments to programme Components. Table 11 below sets out the cost profile for the 10-year Business Case. This funding will be allocated to programme components and programme management as follows:

I. National-scale forest governance reforms: Partnerships in up to 16 countries:	£136m
II. Consumer market reforms and standards: Alliances on overseas forest footprint:	£34m
III. International policies and processes to catalyse transformational change:	£33m
(iv) Programme administration, strategy, country engagement, MEL (outsourced):	£12m
(v) Partner country engagement: programme financed posts:	£5m

Figure 15 - - FGMC2 delivery model
Funds will flow from FCDO to the PMSST a Tier 1 supplier who will oversee programme strategy, monitoring and learning, orienting action across all three components. The PMSST will award accountable grants for delivery under all three programme components, and then to downstream Tier 2 and Tier 3 partners engaged in project delivery (Figure 16). FCDO will directly contract a Facilitation service to mobilise Facilitators to be placed in most Tier 1 and Tier 2 priority countries. Facilitators play a key neutral role is supporting the multi-stakeholder policy processes and importantly will be positioned as separate from any TA or other project support. FGMC2 will work with the European Forest Institute International Partnership’s Facility to support partner country requests for advice and expertise (mobilised through an MOU grant agreement) and as set out in agreed annual workplans. EFI IPF will be responsible for Tier 2 suppliers and grants. FCDO will outsource project procurement, contracting a service provider to administer a portfolio of TA projects supporting country level action under Component 1.
Figure 16 - FGMC delivery chain: ECED (IFU)

##### Programme management, support & strategy, monitoring & Learning (PMSST).
Much of the programme administration and technical oversight will be outsourced to a Tier 1 service provider. As discussed in the Commercial and Management Case, the PMSST will support the management and oversight of all three components supporting the award of Accountable Grants and manage programme-wide MEL. The budget for an outsourced programme management and MEL supplier is estimated to be about 5% of the overall budget. This represents a significant commitment to support responsive and adaptive management, continuous learning that informs country strategies and international policy, design and scoping work in new geographies (Tier 3 countries in particular), outcome monitoring as well as evaluation at relevant points in the programme cycle, including ahead of decisions on tranche 2 funding, and the end of the programme.
Based on our experience with outsourced programme support that worked across fewer countries and with less contracting responsibility (FGMC1 outsourcing support, monitoring and grant management was about £1.2m/yr), for the purposes of budget modelling, we propose a level of £12m for 5 years. This rate – 5% of overall programme resources – has been benchmarked against other comparable programmes.
As indicated in the Commercial Case. a Tier 1 supplier providing outsourced programme management support (PMSST) will be appointed through an open procurement. The appointed PMSST will issue grants. A second supplier will be procured to administer a portfolio of modest TA projects (£0.5m-£10m) to be delivered in partner countries as identified by FCDO and partner Governments in up to 16 countries (likely no more than 10). FCDO will conduct due diligence on the Tier 1 suppliers prior to signing the contract, and the supplier will be responsible for establishing due diligence procedures, financial management and risk management systems to ensure good management of public funds and value for money through the delivery chain of Tier 2 and 3 implementing partners.
##### Component I: Partnerships & policy reforms to catalyse transformational change at national scale
Funds will flow through various instruments to support policy processes and reforms in producer countries. This builds from the experience of FGMC1 that worked through TA projects (capacity building), facilitation of multistakeholder processes and grants to non-state actors to build capacity and understanding to drive sector reforms. FGMC2 is doubling the scale, to support policy reforms in more partner countries and to engage with a wider set of forest governance challenges.
Facilitation Services will be procured through competitive process directly by FCDO as a Tier 1 supplier to provide in-country facilitators in partner countries. The EFI IPF will continue to support governance reforms in countries where they have established relationships with partner governments (mobilised through MOU agreement) and a track record of work on traceability systems. Long term capacity building TA projects will be mobilised through a “TA projects portfolio manager” providing a diversity of delivery options for partners. The “TA projects portfolio manager” will be contracted by FCDO, with oversight and monitoring of the TA projects provided by the PMSST.
Grants will be provided through the appointed PMSST (the FGMC2’s main Tier 1 supplier) which will issue grants and provide supporting advisory services. Tier 2 suppliers and grantees will include companies and non-governmental organisations engaged as partners in the programme.
FCDO will conduct due diligence on the Tier 1 suppliers prior to signing contracts, and the suppliers will be responsible for establishing due diligence procedures, financial management and risk management systems to ensure good management of public funds and value for money in the delivery chain.
The country-level policy support will continue in FGMC2 as the programme’s largest component. The financial proposal represents doubling the spend from FGMC1, reflecting the increased demand from interested forest countries and the success achieved in influencing policy-driven transformations through multi-stakeholder driven reforms. The cost profile draws upon FGMC1’s experience of supporting inclusive policy deliberations and delivering technical assistance to support legal and regulatory reform. Annex H sets out the initial scoping for the country partnerships.
As indicated in Figure 17 below, for phasing and budgetary purposes, potential partner countries are grouped into 3 categories: Tier 1 are long standing partners keen to build on FGMC1 to address new governance challenges and will likely mobilise quickly; Tier 2 are new contexts where countries have indicated strong interest to initiate governance reforms or deepen engagement with FGMC2; Tier 3 are new geographies where further scoping, dialogue and Political Economy Analysis are required to inform whether or not to engage. Action in Tier 3 countries would unlikely start until year 3 at the earliest. Indicative finance allocations to each Country where scoping work has been undertaken has been modelled to guide initial dialogue with partner governments and help frame the scale and intent of the programme. For Component 1, the Business Case models an indicative £10 million per Country (with a range of £4m-£16m over the 5 years depending on needs). These are indicative envelopes that can be adjusted upwards or downwards in response to need and opportunities for transformational reform.
##### Component II: Support to alliances with consumer markets to improve forest footprints
Funds will flow to through the appointed PMSST (the FGMC2’s main Tier 1 supplier) who will issue grants, support policy research, convening and cross country learning to inform policies and import and sourcing practices. The TA contracts supplier will contract technical services in support of agreed workplans as indicated by FCDO. Annex I (Alliance country engagement) sets out information and scoping for countries with significant forest footprints whose demand is driving illegal logging and unsustainable practices in tropical forest countries. FGMC1 forged an effective alliance with China encouraging stakeholders to understand their forest footprint, to shape new regulations and business standards for trade in timber from tropical forest countries.
Indicative finance allocations to support policy processes in alliance with significant markets has been modelled based on FGMC1 experience to guide initial dialogue with potential Alliance partners and help frame the scale and intent of the programme. For Component 2, the Business Case models an indicative £4 million per Country (with a range of £2m-£6m over the 5 years depending on scale of trade dynamic, levels of understanding and opportunity. These Tier 2 suppliers may issue sub-grants to delivery partners, such as consultants undertaking analysis and developing knowledge products, and service providers supporting implementation of collaborative actions. FCDO will expect the PMSST (Tier 1 supplier) to conduct due diligence on any Tier 2 suppliers prior to signing grant agreements and ensure that these grantees have adequate policies and systems in place to manage sub-granting and ensure value for money. The phasing is indicated in Figure 18 below.
##### Component III: International processes and market rules that incentivise forest stewardship
Support to international policy processes that galvanise momentum for governance and market reforms will work through Accountable Grants awarded to a selection of non-profit organisations and/or international organisations through a series of competitively awarded grants. The PMSST (the tier 1 supplier) will award and manage grants that deepen understanding of market trends, illegal forest uses and associated trade, develop knowledge products, expose illegality and environmental crime, support international policy processes that incentivise strong forest stewardship. The PMSST (Tier 1 supplier) will manage the accountable grants programme ensuring due diligence on all partners prior to signing grant agreements and ensure that the grantees have adequate safeguards, policies and systems in place to manage sub-granting and ensure value for money.
In year 1, FCDO will work together with EFI IPF to co-design a multi-donor supported International Forest Governance Hub that will provide independent guidance and advice to tropical forest countries on re-tooling their policies and institutions to secure forest stewardship and access new forest ecosystem finance initiatives. This will build from extensive stakeholder dialogues in developing countries over the past year. This Hub will enable FGMC2 to further scale up actions and promote south-south cooperation and learning. The design for this action will phase in later, starting in Year 3 as indicated in Figure 17
Figure 17-Summary of programme phasing in Tranche 1

### COST PROFILE PLANNING
The cost profile is set out in Table 11 below. Funding will come from the FCDO ECED. 100% will be classified as ODA and ICF RDel contributing towards the £3 billion nature funding target, and the global £1.5bn forest-related funding target. As actions address sector-wide reforms they apply equally to mitigation and adaptation strategies.
The annual indicative spending profiles across each component and particularly between countries will be confirmed through detailed work planning together with interested partner country stakeholders once the business case is approved. As Indicated in Figure 17, country engagement will be phased as interest, analysis and opportunity are identified. We will maintain flexibility to adapt funds between components and countries depending on needs and performance as well as to stop action when necessary.
Assumptions around the programme’s mobilisation for this funding profile are set out below:
    1. The Business Case is approved by Ministers and HMT in [August 2024] and runs for a period of five years, with the first tranche of funding.
    2. Programme timeframe is divided into two five-year tranches (as discussed above), with approval for a second tranche secured in year 4 via a Business Case addendum.
    3. Procurement of the contracts for the outsourced Programme Management Support team, country-based Facilitation Services and TA project service start as soon as the Business Case is approved and take no more than 12 months to mobilise.
    4. Design work and country focused engagement in Year 1 will secure agreement on country specific strategies and roadmaps for Tier 1 and Tier 2 countries. In Year 2 the PMSST will launch the FGMC2 grant scheme. A TA projects portfolio manager will be procured and mobilised with the capacity to initiate TA projects by month 15 as identified through the country strategy process.
    5. Budget estimates for each potential partner country are indicated in Annex H: Partner Country Analysis and Engagement Plan, based on initial scoping and lessons drawn from FGMC1. These indicate annual spend per country of £0.5-£3m/ year for building capacity and supporting policy reform processes.
    6. Scoping, political economy analysis and country engagement for Tier 3 countries will begin in Year 2 with a view to mobilise action in Year 3.
    7. Programme-financed staff will be mobilised as soon as the BC is approved, working together with concerned Posts to agree TOR with country-based positions mobilised by the end of year 1.
    8. The negotiated non-contract agreement (i.e. MOU with international organisation) will start as soon as the Business Case is approved providing a “bridge” of identified short-term TA to sustain reform processes and maintaining in-country engagement in year 1 providing a bridge until longer term support is procured and mobilised.
    9. Negotiation of non-contract agreements (i.e. MOU or contribution agreement) to establish a new partnership with the EFI International Partnership Facility that will secure a new partnership supporting the governance policy work. This will include securing in-house expertise to provide on-demand guidance to partner countries and co-creating a new International Forest Governance Hub (Component 3). This engagement will start when the Business Case is approved, with due diligence processes and mobilisation of agreements expected to take six months.
	Tranche 1					Tranche 2
£ million	24 - / 25	25 - / 26	26 – / 27	27 - / 28	28 - / 29	Total	29 - / 30	30 – / 31	31 – / 32	32- / 33	33- / 34	Total	Total	%
National processes component #1	13	22	29	36	36	136	36	36	36	36	23	167	303	60%
Alliances markets Component 2	1	4	9	10	10	34	10	10	10	10	5	45	79	16%
International processes Component 3	1.5	4.3	8	10	10	33.3	10	10	10	10	8	48	81.3	17%
Outsourced management & MEL		3	3	3	3	12	3	3	3	3	3	15	27.5	5%
Country engagement: insourcing staff	0.3	0.5	0.8	0.8	0.8	3.2	0.8	0.8	0.8	0.8	0.8	4	7.2	1.6%
FCDO Oversight & learning	0.2	0.2	0.2	0.2	0.2	1	0.2	0.2	0.2	0.2	0.2	1	2	0.4%
Total	16	34	50	60	60	220	60	60	60	60	40	280	500	100

Table 11 - FGMC2 Cost Profile (spend is indicative & subject to change)
The Component 1 cost profile is based on several international procurements in year 1 and inception phases involving extensive co-design with local stakeholders. Through FGMC1 we have extensive experience at procuring Facilitation Services as well as outsourced programme management and we expect those processes to advance smoothly.
Political Economy Analyses and scoping for action in Tier 1 and Tier 2 countries informs the Business Case and dialogue with interested Governments and may proceed quickly once the Business Case is approved. Engagement with Tier 3 countries will only start in year 2 or 3.
A Bridge funding arrangement working through an MOU with the European Forest Institute has been agreed to sustain reform processes in a few countries while longer term instruments are procured. Bridge actions may commence as soon as the Business Case is approved. This component will be supported by programme-funded (in-source) positions based in priority regions. Rapid mobilisation on staffing will facilitate the inception and stakeholder dialogue in Year 1.
The cost profile assumes that component I will taper towards the end of the programme, as countries fully implement new regulations and policies. It also presumes that actions in some countries will taper sooner while action in other countries grows depending on the pace of reforms and investments by business in compliance with mandated sustainability requirements.
The Component 2 cost profile is based on establishing a set of strategic alliances and grant agreements to stimulate understanding of downstream forest impacts and encourage strengthened regulation and standards in significant consumer markets. This component will be mobilised once the PMSST (outsourced programme manager) is mobilised. FCDO engagement will secure workplans and MOUs over the course of year 1 to enable rapid mobilisation in the 2nd year. Alongside this, the FCDO programme team will work with international partners and initiatives to encourage greater interest and understanding of market-associated forest footprints.
The Component 3 cost profile will depend on the mobilisations of the PMSST who will manage the FGMC Grants Scheme and will commence in earnest in Year 2. Extensive EME with potential grant partners have taken place during this design period and many organisations are keen to submit proposals as soon as the FCDO is in a position to consider them.
The ECED FGMC team will work together with the EFI IPF to further develop the proposals for an international forest governance policy hub (IFGH). It will draw from the extensive stakeholder consultations in developing countries conducted over the past year. The Hub would provide a platform that other development partners could buy in to (through a multi-donor pooled fund). EFI IPF will convene discussions with interested donors and partners. The design and testing ideas for the Hub will take place over the first year. Programme mobilisation will commence in year 2 depending on the interests of other donors. UK funds are likely to be pooled with other donor and philanthropic funding to deliver this work, and costs within the activities are relatively static, leading to a flat cost profile for the duration of programme.
All implementing partners will be required to submit annual budgeted work plans for FCDO approval containing detailed estimates for fees and reimbursable expenses, including disbursements to third party organisations. These will be followed by regular financial reporting containing details of historical spend, forecast spend and estimated total spend for the current financial year including an explanation for any marked deviations from expected spend. These will help FCDO to assess partners’ budget utilisation rates and to further inform our forecasting.
A forecast, updated on a monthly basis, will be used to update projections and monitor their accuracy. We will not earmark funding allocations to the component lines but will maintain flexibility for the SRO to approve the movement of funds between components depending on how well areas are performing and needs changing. The flexible design of the programme will allow FCDO posts (and possibly OGDs) to expand the programme where opportunities and demand for this arise.
### FINANCIAL PRINCIPLES AND PARAMETERS
Costs Directly Incurred by FCDO
Programme management, monitoring and delivery will be largely outsourced, and delivery costs will be incurred via the tier 2 contractors and grantees (Figure 17), with all Tier 1 and Tier 2 agreements made in GB pound sterling. The costs incurred directly by FCDO are staff costs incurred within ECED IFU for the programme’s management, oversight, monitoring and country engagement. The Management Case provides detail on the expected FCDO staff resources required to manage FGMC2.
Programme-financed (Insourced) Roles Costings: Subject to HMT approval, we intend to support country-level engagement with national policy processes and partnership with programme-financed inhouse staff in up to 7countries. This means up to 7 insourced roles over the programme period. Depending on the local context we expect the majority of these to be Country Based Staff (CBS) reflecting their deep understanding and established networks from which policy influencing and engagement may be more effective. For budget planning purposes we are making provision for 2 of these to be UK Based (UKB) staff where the local political context suggests an international expert could provide more neutral engagement with sensitive processes. Most of these implementation roles are expected to start in the second year for a duration of 36 months, with the potential to extend a further 24 months subject to programme need and resource availability. Two CBS have already been identified by Post and are engaged short-term in FGMC2 design work (in Jakarta and Beijing). Start dates for Tier 3 countries such as India may be in years 2 or 3.
If delivered by FCDO inhouse, the UKB implementation roles are expected to cost £200,000 per annum each. This is based on established Grade 7 salary bands plus relevant allowances for FCDO country posts and accounts for variations in costs from post to post. The CBS roles are expected to cost approximately £60,000. This reflects an accurate midpoint of salary bands across the FCDO posts where FGMC2 is likely to engage. The figure was calculated using data from FCDO Regional HR Hubs and HR managers in relevant FCDO posts. For the purposes of benchmarking fee rates against the local market so as not to exceed what is required to attract, retain and motivate suitable staff, FCDO costs are adjusted to remove allowances not ordinarily included in outsourced rates. Annex M (Insourced roles justification and VfM) sets out in detail the VfM analysis comparing insourcing with outsourcing costs at equivalent grades for a selection of countries.
Table 12 sets out a summary of average fee rates at G7 grade, for FCDO UK based staff deployed to countries (UKB overseas) and country-based staff (CBS) is compared with average rates for national and international fee rates at an equivalent grade. This demonstrates a 40% saving rate is achievable on the basis that 5 CBS and 2 UKB overseas staff are deployed. [redact before publication due to commercial sensitivities].
Table 12 – Indicative costings: insourced vs. outsourced delivery
	Delivery	Geography	Job Family	Level	Annual rate*	Roles	12 mths	24 mths	36 mths
	Outsourced	International	Programme Leadership	Standard	£115,400	2	£0.23m	£0.46m	£0.69m
		National	Programme Leadership	Standard	£92,400	5	£0.46	£0.92m	£1.38m
	Insourced	International	Programme Leadership	G7	£78,320	2	£0.16m	£0.31m	£0.47m
		National	Programme Leadership	G7	£52,757	5	£0.26m	£0.53m	£0.79m
*To enable a like for like cost comparison between FCDO staff rates and those of outsourced suppliers, allowances that are not ordinarily included in commercial outsourced rates are removed from FCDO rates. Average figures are used based on data from 7 countries, received from HR hubs and the contracts database.							Outsourced Total		£2.1m
							Insourced Total		£1.26m
							% Difference		40%
							£ Difference		£0.84m

Financial Aid to Governments
Financial aid to governments is not planned under this programme. There may be some cases where targeted funding for discrete activities, may be needed to support progress. In any such cases, support will be agreed and provided in line with FCDO policies.
Pooling of Resources
This programme covers all three tropical forest basins where other HMG-financed forest and land programmes are on-going or planned. Working closely with Posts will help FGMC2 and its partners better realise the ambition and opportunities framed in sector-wide and national scale forest governance reform processes. The programme’s focus on building strong governance foundations aims at improving the enabling conditions for investors and donor-supported investment projects. One option for engagement by Post is the provision of additional finance to FGMC2 for the delivery of activities that align with both the objectives of FGMC2 and the Post’s country objectives. In principle, this approach could be pursued through any of components 1,2 or 3, providing additional support for policy reform and engagement of non-State actors.
The preferred method for Post buy-in is through separate budget codes that would be agreed with Post, this represents the best value for money option based on programme management burden for additional components and staff time. This approach will follow agreed provisions for accounting for ICF spend and results at posts. Alternatively, Posts would be able to finance directly through the multi-donor International Forest Governance Hub once established.
FGMC2 could work with other HMG Departments (e.g. DESNZ or Defra) where joint action would represent greater efficiency and VfM and where the forest governance reforms supported through FGMC2 help create positive enabling conditions for further investments (such as for forest carbon or biodiversity initiatives). In such instances the FGMC2 programme team would explore the most efficient route to joint action while remaining consistent with the PrOF rules.
Other donor funding: Components 1 and 2 will be funded bilaterally by FCDO, but the grants made under Components 3 will involve pooling FCDO funds with those from other donors and philanthropies. The ambition for the establishment of the International Forest Government Hub is that it encourages other donors to support these foundational reform processes and thus further scale up the ambition of this programme. Where pooling of FCDO funds occurs, suppliers will be expected to provide financial reporting that separately identifies FCDO funds and associated disbursements.
### Financial management, monitoring and reporting arrangements
### Payment arrangements and triggers
As laid out in the Commercial Case, funding will be provided via a mixture of contracts (for Programme Management & Support, TA project portfolio management and Facilitation Services) and grants through MOUs to international organisations. The outsourced Programme Management Strategy and Support Team (PMSST) will administer accountable grants with International NGOs on FCDO’s behalf. Oversight and governance arrangements are set out in the Commercial and Management Case. FCDO will review contracts and grant agreements prepared by the PMSST in advance of their issuance to ensure they comply with FCDO’s programme and financial requirements.
For commercial contracts, funds will be disbursed to lead suppliers in arrears against inputs with performance criteria or against milestones, defined at contracting stage. Contracted suppliers will likely invoice FCDO monthly or quarterly. There may be exceptions to this where a clear demonstration of need is provided. The payment schedule covered through the MOU grant agreement with the European Forest Institute International Partnership’s Facility will be based on annually agreed workplans reflecting priorities agreed with partner governments and a quarterly disbursement schedule.
For accountable grant agreements, under the FGMC accountable grant scheme managed by the PMSST some smaller NGOs organisations may require payments in advance of activity taking place due their relatively smaller size, however this will only be agreed where a need is demonstrated; a preference is retained for payments in arrears where possible.
For multi-donor trust funds (Component 3) payment will not be in advance of need and will be in line with FCDO payment rules for multi-donor trust funds.
Payment claims from Tier1 suppliers will be checked by the FCDO programme team, and funds will only be released if sufficient evidence is provided. Disbursement requests will detail the funding needs, cash balance and liquidity position to avoid payment being made in advance of need. In accordance with any applicable terms in the contract or non-contract agreements, payment may be withheld in instances of poor performance.
### Financial reporting and asset management
As is standard practice for FCDO ODA programming, spend for FGMC2 will be monitored in line with the payment schedules agreed with suppliers using the established and robust programme management processes used within FCDO. A quarterly and annual financial reporting regime will be established by FCDO, in consultation with the supplier, and funds managed by suppliers will be held in bank accounts that are tracked. Partners will report regularly to FCDO to account for how funds are being used. Tier 1 suppliers will need to provide audited financial reports, that separately identify FCDO funding, disbursements, and unspent financial resources.
Payments will be made through the FCDO payment system to registered suppliers. All forecast and actual payments will be recorded in AMP/HERA so that progress can be monitored and payments to the programme can be easily separated out. FCDO accounts will be monitored to check transactions are made to suppliers.
As this is a technical assistance programme supporting policy and regulatory reform, it is not anticipated that suppliers or partners will procure significant numbers of assets. All assets procured through programme funds will be tracked and monitored through asset registers held by each tier 1 supplier. Asset management will be in line with FCDO procedures and outlined in the relevant agreements with partners. Registers will be updated regularly and audited by the external audits and FCDO owned assets transferred or disposed of at the end of the programme according to usual FCDO rules and processes. Due diligence procedures will help enable FCDO to ensure partners have robust mechanisms in place for any asset management and disposal.
### Transparency
FCDO expect all its partners to meet IATI standards. FCDO will publish the programme’s business case, logframe and Annual Reviews on DevTracker in line with FCDO’s programme rules.
ECED will require all partners to have in place processes to ensure their accountability to beneficiaries. This will include ensuring that results are effectively shared, as well as opportunities created for stakeholders to provide input and feedback during project design and delivery.
ECED will require that all partners inform ECED in advance of any unexpected potential significant changes in financial forecasts.  The Programme Manager will reconcile these forecasts against (i) relevant data on FCDO systems; (ii) work plans and budget; (iii) previous reports; and (iv) previous disbursements and past spending trend.  Any discrepancies will be raised immediately with partners and necessary changes to forecasts will be agreed.
### Currency Risks
ECED will specify in all agreements with suppliers and partners that payments will be made in pound sterling. Partners may convert this to the appropriate local currency using a method agreed with the programme team and set out in agreements. The payments are therefore susceptible to currency fluctuations in exchange rates between local currencies and pound sterling. In the event of adverse currency movement, there may be reduced potential for specific project fulfilment. We will work closely with partners to monitor these risks and take appropriate action in accordance with HMG policies.
### Assessment of financial risk and fraud
FCDO has a zero-tolerance policy towards fraud and corruption, money laundering and the financing of terrorism. Delivery partners must take appropriate measures to prevent fraud and corruption in connection with the use of FCDO funding. This means adopting appropriate fiduciary and administrative practices and institutional arrangements to ensure that the funding from FCDO is used only for the purpose for which it was given.
FCDO is committed to the international fight against terrorism, and against the financing of terrorism. Delivery partners must comply with appropriate policies, procedures, and controls such as: compliance with applicable national laws and regulations for anti-money laundering and combating the financing of terrorism; a written policy on anti-money laundering and combating financing of terrorism policy; due diligence requirements; record keeping reporting of suspicious transactions; anti-money laundering and combating financing of terrorism training for all their staff.
Programme funding for contracts and grants will be paid in arrears, or under exceptional circumstances in advance, to ensure that disbursements are based on demonstrated need and avoid the build-up of unspent cash balances. Financial reporting and transparency requirements, as well as rigorous due diligence and auditing will help to mitigate the risk of corruption and fraud in the partnership and grants managed by suppliers. Regular monitoring will also help to identify risks and facilitate early corrective action. All beneficiaries of the programme will apply the standards and best practices required by FCDO. The FCDO’s requirements will be codified in all agreements and contracts as well as in MOUs with partner countries.
The overall financial and fraud risk is assessed to be Moderate, with the following identified risks:
    1. Risk of supplier fraud in procurement, leading to misuse of funds is assessed to be Minor. Due diligence and monitoring reduce the risk of fraud in procurement of goods and services as well as administration of accountable grants in the programme. Suppliers will be encouraged to report to FCDO any instances of fraud or potential fraud, in part to demonstrate that their monitoring systems are working.
    2. Fraud and misuse of funds by Government is assessed to be Minor, as no funding is expected to flow directly to government.
    3. The risk of underspending and overspending, and volatility in financial forecasting is assessed to be Major. This reflects the reality of bilateral delivery working across multiple countries, with FCDO paying suppliers on the basis of need, without the buffer offered by trust funds, or payments based on promissory notes. This means that any delays in activities due to unforeseen events cascade directly into FCDO’s payment schedule. As the programme intends to build partnerships with up to 16 tropical forest countries, the risks associated with anticipating the pace of reform across them is likely to remain significant. Forecasting is likely to be challenging especially in initial programme years, as different spending modalities are put in place but should become more predictable as the programme matures.
If fraud is detected, FCDO will require full remedial action including repayment in full if the fraud involves diversion of UK funds. Continued disbursement of funds will be contingent on adequate financial oversight mechanisms.
Financial performance will be monitored through annual reviews and by financial audits to determine the accounting standards and practices put in place. Spot checks for FCDO owned assets and financial spot checks will be undertaken as appropriate. FCDO will also consider undertaking full follow-the-money exercises.
## Management Case
The Management Case provides an overview of how ECED will deliver and oversee FGMC2 to ensure it performs to a high quality, achieves VfM and manages risks within ECED appetites. Internal and outsourced programme management arrangements will be established to support FGMC2 implementation and oversee the use of public funds for programme delivery.
### Overview
The Management approach builds on 12 years of experience with what has worked well. The FCDO FGMC team will make use of established programme management tools and controls, provide oversight and strategic guidance through programme-wide and country-specific governance arrangements as set out below. In supporting country-level engagement under FGMC partnerships, the programme will draw on country expertise and engagement of key Posts supported through in-sourced country-based staff where feasible. Monitoring, evaluation and learning strategies will be developed to inform country-level engagement, including regular political economy and gender analyses. At programme-wide level, MEL will be integral to the outsourced adaptive programme support as well as complemented by independent research and contracted periodic evaluations. Collectively, these measures will ensure appropriate oversight, management and influence over FGMC2, enable effective engagement with partner Governments, national and international stakeholders, support flexible programme management, ensure coherence and learning across the programme actions, and enable the management of risks as they arise. Lessons from Phase I that inform the Phase II management approach are summarised in Box 10.

Box 10- FGMC1 lessons to inform management approach
Phase I was managed over 12 years by an SRO and Programme Manager, with advisory support and several programme-financed roles in strategically placed positions in the EU, Indonesia, and China. It was highlighted in the ICAI review of HMG projects supporting action on forests as delivering strong policy influencing results at national and international levels supported by an adaptive approach that has helped build a strong coalition of practitioners.
At the outset of FGMC1, accountable grants, MOUs with international organisations and various Supplier Contracts were managed directly in-house by DFID. As the programme grew in scale, direct management proved untenable with the HR available to the central DFID team resulting in some projects being shifted to management at Posts with capacity (Beijing and Jakarta). An outsourced programme management team (PMST) was procured to improve efficiency and to manage the programme’s Accountable grants (20+ grant agreements). FGMC2 will further streamline FCDO direct programme management by additionally outsourcing the administration of most TA contracts.
The PMST’s team of 5 technical experts provided specialist advice along with grant oversight. They were able to support governance reform processes in various countries and to orient and shape accountable grants to complement the wider programme thereby improving learning, coherence, and influence. A pool of on call experts were able to help the programme respond quickly to requests for advice to inform policy development processes. FGMC 2 will continue this model, with enhanced skill sets and capabilities within the pool of experts.
FGMC1 worked both through multi-donor trust funds as well as jointly with donors where we were able to capitalise on their wider sector knowledge or existing programmes (in Liberia with the EU, in Guyana with Norway, in the Republic of Congo with AFD, in Vietnam/ Cameroon with GIZ and with Ghana through sector budget support with other donors). This helped build coherence in support of national sector reforms, influenced other donor approaches as well as leveraging resources to achieve scale. FGMC 2 will continue to align and work closely with other donors, it will also establish a new independent international forest governance hub as a source of impartial advice and analysis accessible to forest countries and create a mechanism to fosters donor collaboration.
As the scale of the programme grows in FGMC2, it will be important to maintain the elements of the Phase I management arrangements which supported efficient delivery, including clearly defined roles and responsibilities, complementarity between FCDO policy engagement and programme delivery through service providers and partners, and recognition of where accountability and risk is held within the delivery arrangements.
The FCDO team that will be responsible for strategic oversight and the management of delivery partners is set out, including detailed descriptions of the working relationship proposed between the FCDO team and the outsourced programme management strategy and support team (PMSST). This is a key relationship and the roles and responsibilities, and key decision making and oversight structures for the model are described.
In supporting country-level engagement under FGMC partnerships, the programme will draw on country expertise and engagement of key Posts supported through in-sourced country-based staff where feasible. Posts and key stakeholders have been engaged in the design of the programme and will have an important role in country level governance. Monitoring, evaluation and learning strategies will be developed to inform country-level engagement, including regular political economy and gender analyses.
At programme-wide level, MEL will be integral to the outsourced adaptive programme support through the PMSST as well as complemented by independent research and contracted periodic evaluations. Collectively, these measures will:
- ensure appropriate oversight, management, and influence over FGMC2,
- enable effective engagement with partner Governments, national and international stakeholders,
- support flexible programme management, ensuring coherence and learning across the programme actions, and
- enable the handling of risks as they arise.
The programme will phase delivery gradually, with a midterm review after 4 years for Ministerial approval on continuation. The arrangements and timing for this are also set out, along with a discussion of the sustainability strategy for the programme. Lessons from Phase I that inform the Phase II management approach are summarised in 13.
### Delivery structures and the implications for programme management
As set out in the Appraisal and Commercial Case, the proposed delivery structure builds from FGMC1 experience and will establish structures that are adaptive and flexible with the capacity to work at country and global levels and with instruments designed to mobilise rapidly to work with political opportunity and momentum. FGMC1 relied on four main ‘instruments’ to support and deliver activities at country and international levels to be continued in FGMC2 as they have proven highly effective. These instruments have delivered policy engagement, technical and governance support, facilitation of national policy making processes, capacity and evidence to inform national and international processes. These 4 instruments are:
- The provision of Technical Assistance for capacity building (people and systems) through TA contracts tailored to the specific needs of partner countries and driven by country governments.
- Facilitation services, delivered through a contract to provide the services of impartial facilitators to support multi stakeholder deliberations, at the invitation of government.
- The provision of short term specialist technical expertise to tropical forest countries delivered through a long standing relationship with EFI, an international organisation that has built up a strong reputation and expertise in forest governance.
- Accountable grants with not for profit organisations such as think tanks, researchers, advocacy organisations, business associations, investigative journalists, covering a broad set of issues aligned to the programme theory of change.
Critical for ensuring there is coherence across the programme, will be the mobilisation of an outsourced programme management team with specialised expertise and sufficient resources for continuous learning. A new outsourced programme support team (PMSST) will be established with the capacity to support action at greater scale, oversee and administer accountable grants and provide technical backstopping and strategic guidance to TA contracts operating across as many as 16 countries. The administrative burden for FCDO’s core FGMC team will be further streamlined by establishing a TA Project Service to deliver projects as indicated by FCDO and partner Governments as set out in the Commercial Case.
Supporting complex, highly political sector governance reforms has benefitted from a delivery strategy that places national stakeholders in the driver’s seat of policy development, that focused on impartial facilitation of the process, with TA support focused on building capacity to engage and an evidence base to inform decision making. This has avoided the problem of a UK-financed in-country project team being seen to drive and “own” reforms. It has, however, necessitated strong oversight of many projects working with different stakeholder interests; a function that the outsourced programme management support team will be responsible for.
As FGMC2 doubles the scale of the programme, it will be important to maintain the elements of the Phase I management arrangements which supported efficient delivery, including clearly defined roles and responsibilities, complementarity between FCDO policy engagement and programme delivery through service providers and partners, and recognition of where accountability and risk is held within the delivery arrangements.
### Overarching programme-wide governance principles and arrangements
Requirements of governance arrangements
Overall, FGMC2 governance and management arrangements will need to perform a variety of functions that engage, support, influence and deliver interventions including, but not limited to:
    1. The support to multi-stakeholder driven policy processes at national and international levels, including investment in facilitation services, that establish legitimate and credible forest land stewardship.
    2. The provision of technical assistance to help countries develop forest policies and institutional arrangements that deliver accountable forest stewardship in tropical countries.
    3. The improvement of enabling policy and transparency conditions for initiatives and new instruments that support forest stewardship that deliver development and climate benefits.
    4. Evidence and understanding that inform demand-side consumer policies to take responsibility for their forest footprint and to incentivise markets for sustainably produced commodities.
Flexible and responsive management approach
FGMC2 will deliver results through national processes and platforms. Consequently, the programme will need flexibility to adjust resources and activities in response to changing contextual factors across a range of countries and international markets. Country-level actions (Component 1) will require an approach to design, delivery, management, and monitoring which is explicitly adaptive and responds to the priorities identified through national stakeholder deliberations (see Figure 21 below –with reference to partner country governance). As the programme is explicitly focused on strengthening forest and market governance in countries with complex forest land and political contexts, it will need to scale up or scale down action as risks and opportunities arise. In addition, by working across all three of the major tropical forest basins, the programme aims to influence directly (in focal countries) and indirectly (through support to south-south learning, influencing international policy and markets). Annex H (partner country analysis and engagement) sets out the preliminary country-specific priorities as well as the process through which these will be developed with stakeholders.
#### ECED FGMC2 programme team
The programme will be managed by the Forest Governance and Partnerships Team in the International Forest Unit (IFU) in the ECED. It will draw upon resources within the IFU to implement the programme, along with other resources available in the ECED Directorate and in key HMG Posts across Asia, Africa and South America.
As indicated in Table 13, the ECED core team will work closely with, and be supported by an outsourced programme support team (PMSST) providing adaptive management and strategic advice, to FCDO and key implementing partners. This team structure will ensure that sufficient capacity is in place to support international policy engagement, bilateral partnerships and manage key contracts and MOUs. The ECED FGMC team includes an SRO with overall responsibility for the entirety of FGMC2, a PRO with day-to-day responsibility, supported by a Programme Manager, and a share of FCDO technical advisers. It is expected that FCDO resource requirements will vary over programme implementation and will be greater in the build and mobilisation period. ECED currently retains the FTE required (as per Table 13) to deliver the programme. To help support active engagement with forest policy reform processes in some partner countries, we propose in-sourcing country-based advisory capacity as indicated in Table 12.

Table 13 - FCDO FGMC Team
Role	Grade	FTE	Overview
Senior Responsible Owner (SRO)	Grade 6	0.7	Responsible for overall programme delivery, compliance and governance processes / Responsible for all grant and TA project award decisions administered through outsourced service providers. / Lead relationships with partners and ensure delivery of HMG priorities. / Lead FGMC2 engagement with Posts in Asia / Lead FGMC’s coherence with other IFU and HMG forest-linked activities. / Ensure FGMC has sufficient human resource, working with others in ECED, and risks are appropriately managed.
Programme Responsible Owner (PRO) and lead advisor	Grade 7	0.9	Lead FGMC2’s engagement and strategy. / Lead day to day programme oversight fulfilling PRO role as per ProF guidance. / Lead FGMC2 engagement with Posts in the Pacific and Africa / Coordinate FGMC’s reporting, including from partners and annual review.
Programme manager	HEO	1	Day to day programme administration / Support FGMC’s supplier engagement, risk management, governance, commercial and financial activities. / Provide support to the PRO where needed.
ECED Climate & Environment or Food Agric Adviser	SEO	0.5	Lead FGMC2 engagement with Posts in the Americas & Mekong / Support FGMC engagement, providing advisory capacity to FGMC2. / Support FGMC’s delivery and alignment with wider HMG policy objectives and commitments, particularly linked to IPLCs.
ECED Economists (& fast stream)	G7/ / HEO	0.1 / 0.2	Provide policy support to FGMC and its delivery partners. / Support FGMC economic modelling &country-specific policy engagement. / Support FGMC2 annual reporting.
TBC - Programme funded advisers (in-sourced)	SEO / G7/ G6	up to 7	TBC – in-sourced to provide additional HMG capacity in country/regions to support delivery. Possible roles are proposed in: Indonesia, China, Congo Basin, PNG (or Pacific), Vietnam (or Mekong), West Africa and India. It is unlikely that all roles will be active simultaneously or for the full duration of the programme. Should these arrangements prove unworkable following the HMT guidance alternative outsourced arrangements will be considered
Cross-cutting advisory support	SEO, G7 or G6	TBD	Additional technical expertise as required as a % support. This will be required during the first year, particularly in supporting the commercial procurement process and establishing MEL approach. Support will be sought from the IFU as well as food & agriculture, climate & environment, economists, social development, governance, and evaluation adviser cadres as need arises and in support of specific policy engagement (such as on forest carbon markets).

The members of the core programme team will have different roles and capabilities. The SRO, PRO and Programme Manager will fulfil their accountabilities and responsibilities in line with those set out in the PrOF guides. In practice, some of the PRO, Advisory and Lead functions will be combined. At country level, the programme will work closely with Post, where staff are engaged with the sector or may be strengthened through “insourced” programme financed expertise.
The ECED core programme team will bring together a mix of expertise and will be committed to their continuing professional development. Members of the core team currently hold accreditation to a variety of FCDO Professional Cadres (Climate and Environment, Food and Agriculture), and will use their expertise and those of their cadre networks to ensure that sufficient capability is applied to FGMC2. The team will also draw on the policy influencing and diplomatic acumen of colleagues within ECED, at Post, from across the International Forest Unit and FCDO’s Geographical Departments. All FCDO officials involved in managing contracts will receive recommended training in line with PrOF Guides, as well as holding relevant technical accreditation.
The core team will be supported by ECED economists and MEL experts, FCDO finance, commercial and legal advisers more broadly, especially during the programmes “build period” when we seek to forge new partnerships and delivery arrangements.

Overview of the programme governance structure
The management structure for FGMC2 is outlined in Figure 18. This will support routine decision making, channel strategic and or other high priority decisions upwards, set out posts’ involvement and support partner coordination. The ECED FGMC team will establish a cross Whitehall Advisory Group involving DEFRA, FCDO and IFU colleagues with an interest in the governance reforms helping strengthen coherence across UK forest-relevant programmes, creating the enabling conditions for other investments in forest land uses and the partnerships underpinning UK’s regulation of its forest footprint, such as FLEGT VPAs. The programme will specifically support VPA partnership arrangements (led by Post and Defra timber policy team).
Figure 18 - FGMC2 Governance Structure

The FGMC core management is made up of ECED’s FGMC Team and the outsourced programme management strategy and support team (PMSST). This combined core team will oversee FGMC’s day-to-day delivery, including finances, risk, reporting, monitoring, and stakeholder engagement and meet regularly as set out in paragraph 476 below to monitor progress. This close working relationship with regular review of progress and performance against work plans and KPIs, ensures FCDO oversight of PMSST’s key functions.
The IFU Deputy Director will have oversight of the programme meeting once a quarter with the FGMC programme team to discuss performance, key and emerging risks. The DD will provide advice to the programme team and will determine whether any items need to be raised at Director level. Other ECED or FCDO officials will be invited to join these meetings as required e.g., PCD, Finance, etc.
A FGMC2 Cross Whitehall Advisory group of interested colleagues from Defra, FCDO (geographic desks), and wider IFU will meet periodically with the FGMC team to discuss progress, learning and coordination with other forest and biodiversity related programmes. This will include informing relevant UK policy developments and/or UK positioning in international policy processes, for example related to forest and forest risk commodities and the UK’s forest footprint as well as UK positions of forest carbon market and biodiversity credit instruments and policies. This advisory group might also identify opportunities for other departments to contribute to FGMC2, for example through the International Forests Governance Hub or the European Forest Institute’s International Partnership Facility.
#### ECED FGMC team responsibilities and oversight
The ECED team will provide strategic oversight working closely with the PMSST, including monthly finance, risk (including safeguarding) and performance monitoring, financial management and forecasting, engaging with partners, engaging with Posts, leading communications, and ensuring compliance with the PROF rules. They will report through management channels to the DD for the International Forest Unit. To maximise efficiency and flexibility, decisions will be cascaded to the appropriate level of leadership. Decisions within programme scope will be within the remit of the SRO and PRO as appropriate. Decisions to close poorly performing projects and establish new partnerships will be within the SRO remit but will be considered both with the IFU DD and concerned HMG Post to understand risks and sensitivities. The DD for IFU will, in consultation with the programme team, decide on issues to raise at Director level including reputational risk or significant delivery considerations.
##### Roles and responsibilities of FCDO in managing delivery partners
The ECED Team will have programme-wide management and oversight functions. The team will further develop the programme, procure lead suppliers, mobilise contracts and non-contract agreements, manage Tier 1 contractors and delivery partners working closely with the PMSST and colleagues at Post (see delivery chain below in figure 20). The team will be responsible for routine management tasks such as monthly review of financial forecasts, monitoring of results, writing annual reviews, ensuring compliance with the PrOF rules, liaising with country offices, and working with key suppliers. The team will also work, together with the PMSST, to ensure complementarity across the programme and link FGMC2 with other relevant HMG programming and policy work. Figure 19 sets out a preliminary delivery chain for FGMC2.

Figure 19 - FGMC2 Delivery Chain EDEC (IFU)

Standard FCDO programme management approaches will ensure supplier performance is managed effectively and ensuring ongoing value for money. Performance will be managed through KPIs set out in contract and non-contract agreements, results frameworks agreed between FCDO and the tier 1 suppliers (and other donors if applicable). The PMSST will assist the ECED Core team in monitoring performance and providing technical guidance. FCDO oversight through steering committees and other governance arrangements, direct engagement with suppliers, and monitoring of field activities. Quarterly and annual reporting regimes will also be established by the FGMC Core Team and the suppliers, supplemented by informal monitoring. Poor performance will be managed through improvement plans, escalation as required, and potential termination of the contract.
The ECED team will work closely with the PMSST in oversight of the programme. While ultimate decision-making authority rests with the FCDO core team, these responsibilities are strengthened by evidence and strategic advice from the PMSST. Drawing on PrOF guidance, the FCDO team will structure and document their oversight around the AMP platform and ensure that information on risks, financial management, and monitoring are kept up to date. Management arrangements to ensure sufficient oversight and close cooperation between FCDO teams and suppliers, will be refined once the outsourced PMSST supplier has been selected, but are likely to include the following:
- Weekly programme management meetings.
- Weekly strategy meetings (e.g. to update on country contexts, policy and delivery challenges).
- Weekly country-specific meetings to update and problem solve (especially in year 1 mobilisation) together with Post advisors where relevant.
- Management meetings to advance approvals on grants and projects as required.
- Monthly strategy and planning meetings (involving all country leads and senior leadership from the Supplier) reviewing performance against workplans and budgets.
- Regular joint country monitoring visits.
- Annual stocktake workshops to assess progress with policy influencing and transformational change, validation of reporting indices/tools, and to inform KPI reporting.
- Annual meetings with lead delivery partners to agree annual workplans.
- Annual programme-wide learning event with all partners.
##### Roles and responsibilities of outsourced programme management support team
The PMSST will have the main responsibility for driving towards FGMC2’s outcomes through support to FCDO’s strategic engagement with national and international policy processes, monitoring of TA projects and delivery of the FGMC Accountable Grant Scheme. The delivery mechanisms established will need to meet evolving needs, conform with the terms of the contract and non-contract agreements, and align with the programme’s overarching Theory of Change and logframe. The PMSST will be responsible for establishing the internal capacities and processes through which to establish an adaptive approach to management that is informed by learning. They will make use of established programme management and monitoring tools and controls tested under FGMC1. Annex L (Approach to MEL) sets out the role of the PMSST in managing the MEL functions of the programme. Effective handover process will be assured in the contracting process.
The PMSST will be responsible for ensuring that they and their downstream partners comply with FCDO financial and management requirements. The FGMC grants scheme will be designed to conform to FCDO guidance on the award of accountable grants. The PMSST will build from the experience of FGMC1 as indicated in Annex K (Accountable Grant Scheme). FCDO, together with the PMSST will decide on grant awards and the PMSST will hold grant agreements on behalf of the FCDO. The PMSST will need to manage risks and finances, provide adequate reporting to the FCDO programme team, and conform to FCDO requirements on safeguarding.
##### Roles and responsibilities of other tier 1 delivery partners: Facilitation Service, TA Projects Portfolio Manager, EFI IPF’s international Forest Governance Hub
FCDO (ECED core team) will retain direct management responsibilities for several Tier 1 delivery arrangements, additional to those administered by the PMSST. This will include commercial contracts for a multi-country Facilitation Service and for FGMC TA Services (TA project portfolio manager) and non-contract arrangements with international organisations or other donor agencies. All these Tier 1 delivery partners will work across several partner countries and their roles and responsibilities will be determined at a country level tailored to meet identified needs (see country governance arrangement below) and designed to strengthen national ownership of reform processes.
Globally, the Tier 1 delivery partners will be key for driving forward and enabling the reforms and transformational shifts framed as FGMC2 outcomes. They will be responsible for putting in place responsive instruments that support action [needs] identified at country level, conform with the terms of the contract and non-contract agreements, and align with the programme’s overarching Theory of Change and country strategies. Within the terms laid out by the contracts, MOUs and grants regarding objectives and eligible expenditure, the Tier1 partners will have the remit to deliver outputs in the manner local partners regard as optimal. Tier 1 suppliers will be responsible for establishing the internal capacities and processes through which to undertake an adaptive approach to delivery, informed by learning. They will liaise closely with the PMSST to ensure that monitoring, learning and reporting feeds into the global programme processes (Annex L provides further details of the MEL approach in FGMC2).
They will be responsible for ensuring that they and their downstream partners comply with FCDO financial and management requirements. They will need to manage risks and finances, provide adequate reporting to the PMSST and FCDO programme management team, and conform to FCDO requirements on safeguarding.
#### Decision-making and partnership arrangements
Decision-making structures and processes with respect to strategies and approval of projects or activities will vary between components and country partnership contexts. Details of these arrangements will be developed during the Inception period and in country-specific contexts, together with the PMSST country lead and colleagues at Post. Delivery instruments will be designed to support annual work planning, including budget allocation. It is envisaged that delivery instruments will be anchored by Country strategies and governance arrangements that put partners in the driver seat in making decisions.
The decision-making process for the award of Accountable Grants is set out in Annex K and will be further developed during the inception period informed by early stakeholder engagement. The FGMC SRO will approve all grant proposals based on advice from the programme team. The PMSST will be responsible for grant agreements and monitoring.
Despite their different specifics, across all programme components and country partnership contexts the FCDO programme team will seek to delegate day to day decision-making to the PMSST and other Tier 1 suppliers as much as possible. To successfully implement adaptive programme approaches, suppliers need to feel empowered to make appropriate decisions quickly rather than having to obtain FCDO permissions for all decisions. This decision-making approach will be underpinned by maintaining clear visions, objectives, and strategies, agreed and documented delivery plans, as well as open communications between FCDO and suppliers, and clear documentation of decisions (and rationales) when they are taken.
#### Programme Coherence
Maintaining and coordinating the programme’s partnerships with different countries as well as international policy engagement and funding arrangements to ensure coherent and effective delivery will incur relatively high transaction costs. The complexity of the programmes mirrors the complexity of the global transition to sustainable forest stewardship supported by international market reforms, and the necessity of adopting inclusive multi-stakeholder approaches involving a range of partners and stakeholder groups. The programme is designed to foster cross-country, cross-stakeholder learning that enables actors to advance challenging and often contentious reforms. It also seeks to ensure that national experience and practice informs international policy processes. A variety of measures will maintain the programme’s internal coherence.
    1. The FGMC core team will routinely use informal communications and meetings to link, inform and harmonise actions across programme geographies and stakeholders.
    1. Secondly, a range of thematic workstreams will be identified, e.g. Cross-cutting workstreams such as gender, independent forest monitoring, the development of traceability systems which would aim to involve partners from different parts of the wider community of practice to strengthen learning. This would help ensure that concerns and innovations developed at national level inform international policy and dialogue.
    1. Thirdly, the internal coherence and strategy of the programme will be reviewed as part of annual team meetings and the annual review process.
    1. Fourthly, an Annual Forum will be held bringing together the global community of practice from all partner countries to exchange ideas and experience.
### Country level programme governance and cooperation with Posts
#### Collaboration between HQ and Posts in programme development and delivery
The FGMC core team and delivery partners will work closely with posts to ensure FGMC2 is aligned to country strategies, bilateral and centrally managed programmes. Bespoke arrangements between the programme team and each priority country post will be agreed during the mobilisation period. As a minimum, posts will review country Theory of Change and workplans that outline FGMC’s partners’ work and activities and the core team will provide regular reports to Posts.
FGMC1 experience indicates that where feasible the support of advisers at Post helps in facilitating government and stakeholder relations and delivering programme results. The local knowledge and networks of Embassy leads will help to inform the development of FGMC2 country strategies and their implementation, and Posts will bring their in-depth understanding of political context to the regularly conducted political economy analyses that are a feature of the programme. Posts will play an important role in ensuring FGMC2 coherence with other HMG programmes and donor activity. In addition, feedback from Posts provides an important additional channel of feedback for FCDO oversight and management of suppliers. Where posts have limited capacity to engage and there is a clear rationale for FCDO forest policy engagement in-country, in-sourced roles may be considered where there is keen interest from Posts.
FGMC1 established a variety of different collaboration arrangements between Post and HQ, including in countries where there is no UK resident diplomatic presence. FGMC2 will build on these to strengthen engagement with partner governments and seize opportunities and help deliver on HMG-wide pledges to key geographies. Examples are provided in Box 11 below.
The FGMC core team has consulted officials from many Posts in the preparation of this Business Case and made design-related visits to all Tier 1 and Tier 2 priority countries including Indonesia, Vietnam, Laos, PNG, Solomon Islands, China, Liberia, Ghana, Cameroon, Congo, DRC, and Guyana. All these Posts are supportive of FGMC2 and have indicated that they will engage with the programme during design, mobilisation, and delivery. FGMC2 Business Case design has been actively supported by programme advisors in Beijing and Jakarta. Routine engagement between FGMC and Posts will be supported no matter the resources available at Post. Where Posts are able to dedicate staff resource to support forest sector policy engagement, particularly in UK VPA countries (currently Ghana and Indonesia, with more planned), the ECED core team can tailor FGMC2 resources to strengthen this engagement. To encourage this, the FGMC team has liaised with Embassy leads to ensure that FGMC2 features in and aligns with the country business plan of each Post. Annex H (partner country analysis and engagement) and Annex I (alliance country engagement) set out the opportunities and how these align with stated Post priorities.
In priority countries, FGMC2 support will likely be framed through a partnership arrangement with key Government services, whether in support of formal VPA-type partnerships, Roadmaps or MOU that indicate priorities for support to national forest governance reforms. Where appropriate, Post will advise and support the development of workplans, terms of reference for TA suppliers and agreement on delivery instruments. Once delivery is fully up and running, Posts may be involved with local governance arrangements and will always be invited to join monthly update meetings, and to participate in the Annual Programme Forum where cross programme learning will feature, particularly on strategies for inclusive deliberative policymaking as well as opportunity to meet colleagues working in other geographies. Additional formats for routine and ad hoc engagement will be established in line with need and interest as the programme advances.
##### Dedicated resource at Post to support FGMC2 delivery
Once the Business Case has been approved the ECED Team will further discuss with Posts strategies to best support UK policy engagement in FGMC focus countries (partner and alliance countries)[36]. This will largely be focussed on supporting stakeholder engagement in country and providing strategic advice to help orient and align with national and UK priorities. We have designed FGMC with a variety of mechanisms to work in country and with Posts whose interest and capacity to engage with forest sector reforms will vary.
[36] Guyana, Ghana, Liberia, Cameroon, RoC, DRC, Indonesia, China, Vietnam, PNG, Solomon Islands
In instances where Posts do not have the capacity to engage with the forest sector policy dynamic, but Embassy support is critical, close alignment will be sought by establishing dedicated FTE in-sourced advisers in country (programme financed roles). Requirements are likely to vary between countries depending on the policy engagement opportunities for FGMC and needs of the Embassy as to what % time would be dedicated to FGMC2 for such roles. In China Post for example, FGMC1 has shared the cost of an in-sourced/programme financed role, with 50% of their time required to have sufficient input into strategy and policy engagement activities, and the other 50% to support Post. In Indonesia, by contrast, two programme financed positions were dedicated to the programme full time. Any in-sourcing will be carried out in accordance with all HMG guidance and rules and will be agreed with posts. ECED will set a clear term of reference for programme funded advisers, agreed with posts, and ensure they enhance FGMC’s delivery and impacts.
The behavioural and technical requirements for in-source roles will be agreed in consultation with FCDO country posts and relevant Heads of Profession. The roles will have clear aims and success criteria and directly support the delivery of programme outcomes. Line management and oversight responsibilities will be agreed on a case-by-case basis with concerned Posts.
FGMC2 plans to deploy up to seven programme insourced roles on fixed-term contracts to work in priority countries and/or regions over the lifetime of the programme. These are unlikely to be over the full timeframe of the programme and will likely not be introduced simultaneously. Fixed-term contracts ensure that FCDO’s workforce is not potentially impacted in an unhelpful way in the medium or longer term. Decisions on whether to deploy UK home civil service (HCS) or staff appointed in country for these in-sourced roles will be made on a country-by-country basis in full consultation with posts and heads of profession given the potential implications for contingent liability in the future.
In agreement with Posts, the in-sourced roles will be managed at Post with quality assurance functions covered by the FCDO FGMC team centrally. The FCDO FGMC team will assume line management responsibilities where Post does not have the capacity to do so.
#### Requirements of country specific governance arrangements
FGMC supports national processes to address governance reforms, particularly the shaping of national forest regulation and policy as well as consumer import signals, that are inherently political and complex processes. Programme results are achieved through these national processes rather than the direct action of projects or partners. The FGMC will support these processes through the provision of impartial facilitation services, promoting inclusion and the development of evidence and understanding to inform decisions. Programme engagement will be undertaken by a mix of delivery partners and fostered, where appropriate, through country partnerships including VPA’s. The governance arrangements depicted in Figure 20 reflect this. This will require that lead Suppliers work very closely with the FGMC team and Posts.
At country level, FGMC2’s governance arrangements need to account for the programme’s focus on fostering inclusive policy deliberations and strong national ownership. The governance arrangements need to facilitate effective engagement with governments, civil society and the private sector. Consequently, governance arrangements need to balance FCDO oversight with the space for decentralised decision-making by delivery partners to respond to policy reform opportunities where they arise. Nevertheless, arrangements will still need to foster coherence and coordination between the programme’s components.
We envisage working this way in partnership with up to 10 countries. In the remainder of the countries (up to a possible 16) we will aim to work through cooperation agreements with other donors. Additional support will come from accountable grants and EFI’s International Forest Governance Hub.
Country Specific Governance arrangements
Arrangements for FGMC2 governance in partner countries will be developed specifically since priorities and needs of the partner country, stakeholders, capacities, and their corresponding delivery modalities will differ from country to country as illustrated in Annex H on partner country plans. As discussed above, UK engagement with reform processes will also vary.
Country specific TOCs/strategies are shaped to support on-going forest governance processes. In some contexts, these are driven by formalised processes, like the VPA that has already established a negotiated roadmap of needed regulatory and governance reform. In other cases, the processes are less well defined. Initial country strategies drawing from FGMC1 experience, programme reviews and stakeholder discussions during scoping missions are presented in Annex H (partner country analysis and engagement plans). Upon approval of the BC these will be refined and agreed together with the FGMC Core team (FCDO and PMSST). The FGMC2 delivery instruments (ref above) are designed to offer a variety of support, depending on need. The FGMC Core team will help facilitate the development of a roadmap which will help to determine the optimal mix of support. The details of the strategies/ roadmaps will affect the in-country governance arrangements.
All country-level governance arrangements will have in common the importance of ensuring local ownership, that they are inclusive of diverse views, that coherence with other sector programmes is considered, and that structures allow maximum flexibility. They are likely to include the services of an in-country impartial facilitator, technical assistance is some form (either short term and/or longer-term support), the actions of a range of accountable grants, and in some instances, the deployment of an FGMC funded role. Figure 20 below sets out this generic structure for where we will be forging country partnerships.
Figure 20 - Country Level Governance Arrangement

The starting point for all governance arrangements in partner countries is a strategy developed and agreed with government and national stakeholders by FCDO (ECED and Post) with support from the PMSST. This provides the basis for an agreement between FCDO and the partner government, framing potential FGMC supported actions. This could be framed through an MOU or alternative partnership mechanism.
At this level, the FGMC core management may include the ECED and PMSST country leads together with a FGMC in-country engagement lead (either from Post or a programme financed advisor). This combined core team will provide strategic orientation, guidance and oversight of FGMC’s support as indicated in the country roadmap, including its mobilisation through a preferred delivery route. The core FGMC team will work with Government to agree priorities for FGMC2 support to the reform process. The core team will be responsible for monitoring progress, finances, risk, reporting, and stakeholder engagement and meet regularly as set out in the Monitoring, Evaluation and Learning section below.
The FGMC SRO and/or UK Country Ambassador (or delegate) will have oversight of the programme meeting once a quarter with the FGMC programme team to discuss performance, key and emerging risks. They will provide advice to the programme team and will determine whether any items need to be escalated.
A combination of different delivery partners could provide support in the partner country, and depending on need, a combination of these will be mobilised to support delivery of the country strategy. These include:
  1. the services of an impartial facilitator to support multi-stakeholder deliberation;
  2. A mix of technical support for the IT required to establish traceability systems and other specific inputs, and longer term technical assistance supporting developmental challenges such as capacity building of national stakeholders, building forest administration governance systems and the capacity to implement them, transparency measures;
  3. accountable grants to build capacity of civil society, community organisations, trade associations and small business representatives, to develop evidence and understanding and improve transparency connecting stakeholders to international peers;
  1. The provision of impartial analytical services from the International Forest Governance Hub.
The PMSST will play a key role in ensuring that delivery of each instrument is aligned to the strategy, and that the actions are coordinated. The Monitoring Evaluation and Learning section below and Annex L set out the role of the PMSST in ensuring oversight of all delivery instruments. FCDO will ensure oversight through the ECED FGMC team working closely with Post.
All of FGMC2’s different delivery instruments are established at programme level to work across a number of countries and as such will have monitoring and reporting structures to the FGMC Core Team. The facilitation service overall is accountable to FCDO through a direct contract, but at country level, the facilitator is accountable to the national process that he or she is facilitating, with its own governance process, liaising closely with all stakeholders, and coordinating with the PMSST country lead.
Technical assistance to build capacity of key institutions will be delivered through project contracts tailored to each country context and managed by a TA projects portfolio manager. In some countries FCDO may co-finance with other donors providing similar support and with existing structures in place. The PMSST would provide technical monitoring of performance. Governance arrangements would be agreed with the partner government, with co-steerage with the partner government the norm, through the ECED FGMC team and/or Post.
The MOU with EFI’s International Partnerships Facility will respond to requests for short term specialist technical expertise from partner governments. These actions are steered by FCDO in agreement with partner countries. FCDO agrees an annual workplan with EFI for the services of this Rapid Response Facility based on requests from Government counterparts framed in country-level steerage. The Annual workplan has considerable flexibility built in to accommodate requests during the year. FCDO meets with EFI on a quarterly basis to assess progress and adjust workplans with PMSST responsible for monitoring and technical guidance and to ensure coherence with other activities. Governance arrangements would be agreed with partner Government. In the case of the IFG Hub, also hosted under the MOU with EFI, performance will be managed through results frameworks agreed between other contributing donors, FCDO and partners, with PMSST oversight of activities through steering committees and other governance arrangements that directly engage partner countries.
Accountable grants are directly managed by the PMSST having been agreed with FCDO. The PMSST ensures that accountable grant holders submit quarterly progress reports, and these are checked and compiled for FCDO. The PMSST would encourage coherence with country strategies and between grants working across several countries.
The governance arrangements set out in Figure 20 will vary from country to country for the reasons described above. Lighter touch arrangements will be developed for countries beyond the 10 forest countries that FGMC will partner with. Box 11 provides examples of country level governance arrangements deployed for FGMC1. They illustrate the variations in structures that are likely depending on what is the best fit for each country given the focus of reforms and the nature of support to be provided.

Box11: FGMC1 examples of ways of working at country level
### Indonesia: strong engagement from Post and a long association of UK engagement in the forest sector. FGMC support is framed by a partnership agreement with the Ministry of Forest and Environment (MOU) framing FGMC activities in country. The MOU sets out the governance arrangements for co-steerage of a multistakeholder forests programme (providing grants to local organisations and technical TA). The Ambassador and Forests Minister co-chair this arrangement with a focal point and FGMC adviser and programme manager in country to administer and support this programme (an HEO and G6 post). Accountable Grants also support work with civil society and the private sector providing independent (of Government) TA to build capacity. The country specific Theory of Change is regularly updated through political economy analysis with the PMSST and CBS working closely together to coordinate amongst delivery partners to ensure that all elements of the programme are aligned. The FGMC funded advisory post helps to ensure that trusting relationships are built, particularly with government, and that Post is kept well informed.
### This situation contrasts with RoC where there is no resident diplomatic presence (handled from DRC) and no programme-financed position. Post (DRC) engages wherever feasible and lead in coordinating a forest sector roadmap that sets out UK and RoC ambition in the forest sector. At the outset, FGMC joined forces with French cooperation financing several TA projects together. Development assistance was coordinated in support of the FLEGT VPA with France, UK, the EU and World Bank supporting sector reforms. That arrangement proved cumbersome. More flexible technical support was established through the EFI Facility. FGMC’s work in ROC is framed by an MOU with the Ministry of Forest Economy. A high-level steering committee led by the FGMC SRO and the Minister provides oversight and a frame for policy engagement. A country specific Theory of Change monitored by the PMSST guides work plans of EFI and Accountable Grants. A country-based facilitator supports multi stakeholder deliberations and encourages coordination amongst FGMC delivery partners.
### In Liberia, the UK has supported efforts to reconstruct the forest sector following the protracted civil war alongside other donors (USA, EU, Norway, World Bank). Through FGMC, the UK has co-financed several projects with the EU and Norway. There is very limited UK diplomatic presence in country, with no capacity on climate & environment (and development cooperation is coordinated from Ghana). Despite this, the UK Embassy is diplomatically engaged in the forest sector and has played an important role coordinating with development partners and engaging across multiple Ministries. An MOU with the Ministry of Justice provides the framework for FGMC support in-country. Biannual meetings are held bringing together all the Government Agencies supported through a Technical Assistance Programme, FCDO (including Post), the PMSST, and representatives of other development partners active in the forest sector are invited as observers. The PMSST lead for Liberia ensures that the country theory of change is regularly updated and that all FGMC delivery partners, including Accountable Grants, are aligned with it.
### Stakeholder engagement in programme design and delivery
This business case has been developed collaboratively, drawing on a variety of expertise within the IFU and the local knowledge and expertise of FCDO officials at Posts. This internal expertise has been complemented by the extensive knowledge and network of the FGMC1 Programme Support team as well as country-based Facilitators in Guyana, Ghana, Liberia, Cameroon, the Congo Basin and engagement with civil society experts from across the three tropical forest basins. Programme strategy and design has been informed by evidence and input from communities of practice supported during FGMC1, including through programme reviews at global and national levels, thematically focused cross-country multi-stakeholder learning workshops as well as country focused programme evaluations. In a few priority contexts i.e. shifting into new domains (such as illegal mining in forests) or new geographies (such as in the Pacific) the BC has been informed through several design projects that focus on analysis, stakeholder engagement and economic modelling to inform policy dialogue.
Once the outsourced PMSST is appointed they will be expected to undertake further scoping analysis on forest contexts, political economies, stakeholder analyses to identify pressing needs and suitable opportunities to support stakeholder-driven policy reforms building from the country-focused plans set out in Annex H (Partner country analysis and engagement). They will be expected to engage stakeholders and incorporate relevant feedback into the refinement of country specific programme proposals and TOC. These design activities will enable the PMSST and FCDO to make an informed decision on where and how to intervene.
As FGMC2 is building from a long-standing programme – with new domains that draw on earlier experiences and networks– the programme design also reflects many of the lessons and key challenges experienced by forestry stakeholders, government services, civil society and businesses in tropical forest countries and proposes new engagement processes to address new challenges. Core to the programme’s strategy is supporting inclusive, nationally owned policy and governance reform processes, proactive stakeholder engagement will feature at every stage of the programme’s mobilisation, inception and delivery. The programme’s approach stresses the importance of supporting a diversity of stakeholder perspectives to shape the support provided by the programme and future policy and regulation. It will place emphasis on establishing support mechanisms that strengthen ownership and responsibility for outputs and outcomes.
### Key delivery phases and timeframes
Building from FGMC’s established networks and working relationships, we envisage (1) a bridge and building period (0-18mo); (2) a rapid mobilisation and engagement period (12-24mo); (3) implementation period (4) phasing down period as indicated in Figure 21 The tempo of engagement will vary in specific countries with the programme exiting as re-tooled forest governance systems are established on a sustainable footing. The Business case frames a 10 year period of engagement reflecting the importance of signalling long-term engagement with challenging sector governance reforms and re-tooling of institutional arrangements for forest protection, production and trade at national scale. This draws inspiration from the example of FGMC1 (a 12 year Business Case) that secured Ministerial approval for budget commitment and allocation in 3 phases over that period building from programme reviews. The long timeframe enabled the programme to adapt to both changing political and policy contexts as well as drawing lessons from implementation arrangements to improve efficiency and effectiveness. A long timeframe also signals long term commitment to partners, giving confidence to embark upon sometimes difficult reforms that require support over a longer period to build trust.
Figure 21- Phasing ofFGMC2 mobilisation and implementation for the first 5 year period

#### Programme design: bridge and building period
Mobilisation will commence following business case approval, along the timelines set out in the Commercial Case. The use of different funding instruments means that some activities may start quickly, helping to sustain existing working relationships, while longer-term partnership arrangements to support implementation are put in place.
Support to on-going governance reform processes which build from FGMC1 may be supported in the “bridge and building” period through an MOU with the International Partnership Facility of the European Forest Institute. Subject to BC approval a programme of design work has already been agreed and teams identified to mobilise rapidly on BC approval. This will allow for more in-depth country level design work to progress in parallel to commercial procurement processes that will secure the longer term working modalities, including the PMSST, Facilitation and TA Portfolio Service. The identified EFI IPF workplan secures design work in the Pacific region, Indonesia, Vietnam, Ghana, Liberia, Guyana and the Congo region.
#### Programme mobilisation and inception
The procurement of an outsourced programme manager (PMSST) will require a tender process. Based on experience of establishing similar implementing arrangements in Phase I, the mobilisation and start-up time will require approximately nine months, followed by an inception phase to become operational. Where possible, efforts will be made to shorten procurement, contracting and mobilisation times, drawing on the experience of Phase I and the strategies, networks and systems developed to support delivery. As the PMSST will establish the accountable grants programme, develop the detailed logframe and support the development of country strategies that identify TA needs framed into new FGMC country partnerships, this PMSST procurement process will be the top priority for the FGMC team in the first months following BC approval.
Once the Business Case has been approved, ECED will work with EFI IPF to finalise a new MOU arrangement. During the first year of mobilisation EFI IPF will work with partner country governments to develop workplans for future support to governance reforms and with the PMSST to set out protocols for delivery of rapid response to requests for expert advice. The EFI IPF would agree annual workplans with concerned national counterparts guided by the FGMC Core management team [PMSST and FCDO team]. The workplan will be developed in the last Quarter of the calendar year for mobilisation from January. The rapid mobilisation of the EFI IPF will allow the programme to respond to requests for support from partner Governments as the scoping work progresses.
The ECED team will initiate a co-design process with donors and partner governments interested in establishing an International Forest Governance Hub hosted by the EFI IPF to provide a source of independent guidance and capacity for interested tropical forest countries. This will build from the research and international engagement of FGMC1 [as highlighted Annex A). This would commit grant funding or TA to strategic international policy initiatives (such as the Broader Market Recognition Coalition).
Mobilising the necessary TA and stakeholder support for country governance reform processes may require a commercial tender for longer term capacity building in partner countries. The orientation of these TA projects will be country specific drawing where feasible from local expertise and tailored to support capacity gaps and stakeholder processes. Based on experience from FGMC1, it is likely that these will be modest in scale (ranging from £1m-£10m over 3-4 year time period) providing flexible support to dynamic policy processes (that may stall or accelerate). These TA projects will be procured by the TA Projects Portfolio Manager through a commercial tender process managed by that outsourced function. The TA Portfolio Manager will coordinate with the PMSST in finalising TOR and establishing the appropriate governance arrangements. Therefore, mobilisation of TA projects is likely from Year 2 of the programme.
FGMC2 will build on the experience gained through the deployment of in-sourced roles in Jakarta and Beijing. As suggested in new ProF guidance for in-sourcing roles, a vfm case with estimated costings is included as Annex M (Insourced Roles). We have discussed this proposal with some posts where they have indicated potential value in these roles. On approval of the BC, we will fully assess the implications with Posts and Heads of Profession and determine on a case-by-case basis whether a UK HCS or CBS appointment is most suitable, and the development of terms of reference in conjunction with Posts. As a contingency, should in-sourcing prove unfeasible, alternative outsourcing approaches may be required.
#### Future tranches and scaling up of engagement
As explained in the Financial Case, delivery over the ten-year period will consist of two five-year tranches of funding, with Ministers taking a decision on if and how to proceed with the second five-year tranche in Year 4. The strategy and approach for the second tranche will be informed by the learning and evaluations of the first tranche. The first tranche is expected to focus ‘testing’ approaches to new challenges (such as illegal mining in forests and credible governance of forest ecosystem (carbon) values and consolidating reforms in countries who are currently retooling their forest sector governance to meet international market expectations. The second tranche is expected to have a greater focus on ‘scaling-up’ successful approaches to addressing the new challenges driving forest clearance and new opportunities afforded through the development of forest ecosystem values that secure long term forest stewardship, particularly in new geographies.
#### Sustainability [ Exit strategy]
FGMC2 aims to support reform processes that bring about changes in how forests are managed, how decisions about forest land are made, and how the rights, responsibilities and benefits are shared. FGMC will provide TA to support these policy reform processes up to the point where policy and regulations are agreed, management and compliance systems are established and fully functioning and capable of operating without project support. For example, national compliance monitoring for timber production has become the BAU in Indonesia and Ghana. At this point FGMC’s technical assistance in this domain would naturally end. [37]
[37] Experience from FGMC 1 indicates that the cost to provide TA and engage in supporting policy reform processes is relatively low. In countries with stronger capacity this averages £1 million per year – ranging up to £3 million/year in countries with much weaker capacity to engage.
However, this does not necessarily imply that FGMC2 would “exit” from that country. The partnership with the country will evolve and continue through dialogue and could be further mobilised to help address new threats or opportunities that would further strengthen sector governance and forest stewardship. A good example of this can be seen in Ghana. FGMC1 supported Ghana’s efforts to reform the regulation of forest production (timber) and it has now largely stamped out illegal logging from its gazetted forests and has the systems and procedures in place to identify problem areas and deal with them. However, other forest lands are increasingly threatened by unregulated cocoa and mining activities. National stakeholders are keen to draw lessons from the governance reform processes to engage with the forest mining threat that is emerging, involving a new set of stakeholders and political incentives, requiring a different set of systems and regulations.
With this perspective of sustainability in mind the “exit strategy” at the programme level, would be that institutional and governance reforms necessary to secure long term forest stewardship:
  - are well understood with clearly evidenced results and impacts enabling more countries and initiatives to build from it.
  - have shifted forest management practices and established sustainable institutions ensuring compliance with rules and regulations that help secure long term forest stewardship.
  - have established National structures for oversight and governance.
  - and that international market requirements value strong national forest governance and forest carbon initiatives place governance at the core of future investments.
The country-specific reform processes will focus on long-term sustainability and self-financing of any institutional arrangements from the outset to facilitate eventual exit.
FGMC2 will work with countries on differing forest governance pathways, with different governance arrangements and capacities in place. Annex H sets out initial positioning, opportunities, and challenges that FGMC2 support could address. At any given time therefore, FGMC2 will be working with countries at different stages along their forest governance pathways and with different priorities, meaning the programme will not be working with all of them in the same way simultaneously over the full ten years.
Support to inclusive policy reform processes that are based on multi-stakeholder collaboration and partnership-based activities tends to be reliant on public funding. Predetermined exits from public financial support for such stakeholder-led inclusive processes is challenging. An innovation being introduced into FGMC2, in part to respond to this requirement for longer term support, is the establishment of an International Forest Governance Hub that aims to pool resources from more and diverse donors to provide countries with readily accessible resource, particularly focused on evidence and tools innovations that support policy processes into the future, beyond the scope of FGMC2.
Monitoring Evaluation and Learning
FGMC’s approach to monitoring, evaluation, and learning (MEL). FGMC2 will invest significantly in monitoring, evaluation, and learning (up to 10% of the programme’s total budget) not only in terms of programme accountability against results frameworks, but also within the components of the projects and their operating context, to gather evidence to inform programme strategy and the very reforms and policies that the programme is seeking to support. The PMSST will lead MEL for the programme, ensuring that the reporting of all delivery partners speaks to the programme results framework and theory of change, and will coordinate and commission the monitoring of trends, and gathering of evidence to demonstrate shifts in policy and policy outcomes. Annex L sets out FGMC2’s approach to MEL and learning from FGMC1.
Programme accountability will be assessed against the results frameworks set out in Annex F: Details of the Theory of Change and results framework.
Building understanding and evidence is core to FGMC2’s approach reflecting the adaptable and responsive management approach of a policy-oriented programme. The programme as whole and each component requires a deep understanding of their operating context to gather evidence to inform both programme strategy and the reforms and policies that the programme is supporting. MEL will be essential for orienting programme priorities and strategy, understanding influence and transformational change, strengthening the evidence base for interventions; supporting efforts to achieve informed policy deliberations and transformational change; tracking value for money in delivery; providing the information required to support innovative, flexible, and adaptive programme management.
Based on experience from FGMC1, FGMC2 will adopt a flexible and responsive approach to both programme management and monitoring with a focus on both understanding the context in which policy change is being considered and on lesson-learning from experience. This will involve the active management of a rich network of actors who form a community of practice developed under FGMC1 that mutually supports different initiatives across the world, through:
    1. joining forces on shared agendas, forming coalitions of interest where ordinarily they might be competitors or ideologically opposed, either for advocacy (for example, CSOs and the private sector coming together as unlikely allies in Ghana refusing to allow the inclusion of ‘special’ or discretionary permits as a legal source of timber.) or for efficiency (for example grant holders collecting corporate performance data being open to aligning indicators and methodologies rather than creating a proliferation of tools with no comparability)
    2. strategic events where vision and understanding are developed and shared. This includes an annual stakeholder meeting hosted by Chatham House and attended by over 250 participants from around the world, including high-level government officials and occasionally Ministers; an Annual Forum for FGMC partners to foster learning and coordination across the programme; and country level learning events to share lessons and coordinate action with national private sector, civil society and government services.
    3. programme MEL. Feedback and evidence based on field visits, regular reviews and partner reports, will be assembled by the PMSST into quarterly and annual progress reports which form the basis for internal FCDO reporting. Regular face to face meetings will be held with Grant holders and commercial suppliers to ensure lessons are transferred across the programme and activities are coordinated.
PMSST’s role. The programme’s monitoring, evaluation and learning activities will be led by the PMSST, with dedicated resource for commissioning and carrying out evaluative studies, previously outsourced under FGMC1. Monitoring and learning are at the heart of the programme that aims to influence national and international policies in part through evidence and support for stakeholder deliberations. Therefore, MEL functions will be integral to the PMSST function. They will build on the MEL lessons from FGMC1 (see Annex L: Approach to MEL) where MEL helped inform strategy and orient specific project investments. The PMSST will have oversight of all monitoring and reporting across all suppliers, irrespective of whether these fall under the management responsibility of the PMSST or not. The structures proposed for MEL, and the rationale are based on how MEL evolved under FGMC1 are set out in Annex L. Although monitoring progress towards specific grant or contract results will be the responsibility of the relevant supplier, they will frame their reporting under the overarching programme, component and country theories of change and utilise the FGMC reporting framework to be developed by PMSST. All suppliers will share their reports with PMSST. This approach will facilitate review and monitoring at the programme level and theory of change. All implementing partners will be encouraged to establish feedback mechanisms from beneficiaries and stakeholders to inform future engagement.
MEL strategic plan. The PMSST will also ensure that monitoring arrangements are in place to track progress and enhance understanding of the causal assumptions in the theory of change. The programme’s MEL plan will be finalised when the PMSST has been appointed. This plan will include detail on appropriate baselining approaches, indicator methodologies and ongoing metrics for assessing progress and VfM. FGMC 1 tested a range of index indicators, for example in the assessment of transformational and policy change. These will be further refined under FGMC2 having reflected on lessons learnt from the use of these methodologies in FGMC1.
MEL methodologies. Once lead tier 1 suppliers are appointed, longer-term metrics for monitoring effectiveness will be developed. As part of this process, FCDO and delivery partners will agree a programme logframe that will include indicators for measuring expected outcomes and impacts alongside nested results frames to track country-specific progress. Methodologies for tracking these impacts will be developed during the programme inception period. This will include any targeted policy results that help secure livelihood benefits such as women’s access to forest land and resources data on gender, and IPLCs. A number of the methodologies will be compatible with reporting against some of the ICF Key Performance Indicators (discussed further in paras 547 and 548).
FGMC approach to gender. Internationally, FGMC encourages all partners to generate understanding and ideas for ways to ensure that women participate in and benefit from governance reforms and private sector investment in the forest and land use sectors. As a policy programme, FGMC supports processes where the terms of engagement are set by national stakeholders and not by the programme. FGMC therefore does not set requirements for women’s participation or clauses within policy but rather supports local actors to build capacity of women’s representatives to engage in policy making processes, and to generate evidence to encourage all stakeholders to focus on women and other marginalised groups such as IPLC. This has resulted in significant shifts in legal frameworks, including benefit sharing rules.
Ex ante analysis of reforms and their potential impact on women, IPLCs, SMEs etc will be an important element of future evidence gathering and MEL. A common concern is that a push for legal compliance resulting from forest and land governance reforms may unintentionally criminalise the customary practices of communities upon which their livelihoods depend. FGMC2 will place additional focus on this activity in response to the observations of the 2021 ICAI review which highlighted concerns regarding insufficient attention paid to unintended harm across the ICF nature portfolio.
Gender reporting. Interventions funded by the FGMC programme have focused on anticipating and mitigating these possible side effects ensuring that the voices and concerns of communities are heard in deliberative processes and their rights recognised and respected. Although FGMC1 worked successfully on gender and inclusion as described above, this was not always adequately captured in results reporting. FGMC2 will build on the experience gained under FGMC1 and the revisions made to the programme’s gender and political inclusion strategies to enable improved capturing of gender and political inclusion results through the use of gender indices.
Evaluation studies. The PMSST will commission regular evaluative studies for specific themes such as gender impacts, for geographies, and will capture learning making full use of the community of practice of programme partners and regular stakeholder fora.
Forest sector trend tracking.	The services of an independent think tank or research organisation will be procured to monitor trends in the forest sector over regions and the timeframe of the programme. This will provide important independent and credible contextual data to both inform the programme and situate programme results.
FCDO oversight. The FCDO programme team will oversee progress under the MEL plan and against the results framework through receipt of:
    1. Quarterly and Annual Progress Reports,
    2. Periodic evaluation reports, and
    3. Regular monthly meetings/calls with PMSST.
    4. Feedback from Posts
FCDO oversight will ensure that credible data are collected to meet FCDO reporting requirements (Annual Reviews, ICF KPI reporting) and monitoring needs. These arrangements will be finalised once suppliers are appointed.
PMSST reporting to FCDO and information sharing. The following documents, systems, and processes will form the backbone of the programme MEL system:
    1. Strategies, Theories of change, Logframes, and assumptions will be regularly tested and updated annually.
    2. Annual work plans of implementing partners, including grantees, will be monitored and reported quarterly, and outputs and outcomes tracked.
    3. Results monitoring and reporting, capturing information from the programme to contribute to ICF KPI reporting and supporting ongoing monitoring of results (building from tools developed to monitor policy and transformational change under FGMC1 – see Annex F: ToC and results framework).
    4. Financial reporting and forecasting.
    5. Regular sessions with the FCDO team to ensure MEL systems capture political engagement and influencing activities carried out by FCDO and other government departments.
    6. Periodic assessments that support lesson-learning and adaptive management.
Annual review.	In addition, FCDO will undertake an Annual Review of the programme to assess progress as required by PRoF. This will draw heavily on the reports and analysis of the PMSST complemented with feedback from country offices where appropriate. Where possible, the FCDO programme team and PMSST will seek feedback from in-country stakeholders.
ICF KPI reporting. Transformation al Change (ICF KPI 15) was the main indicator under FGMC1 to report to ICF and will remain so for FGMC2. Monitoring transformational change requires a specific framework (Transformational Change Index – TCI) developed using the published ICF methodology. It monitors the quality of the deliberative process including inclusiveness, leverage, capacity, evidence and reasoning. In addition, the TCI scores innovation and sustainability to better align with the ICF KPI 15 components in the KPI methodology. Monitoring KPI 15 will also be an important way to monitor progress of less tangible FGMC2 activities, assess effectiveness, and identify if and how to change course. Details on the methodology for the TCI are provided under Annex F (ToC and results framework)
Other ICF KPIs.	Despite FGMC’s ambition to contribute towards reversing forest loss, the long causal links between policy change and reduced forest loss suggest that FGMC would not be able to report on KPIs such as hectares of ecosystem loss avoided (ICF KPI 8), value of ecosystem services protected (ICF KPI 10) and hectares of land under sustainable management (ICF KPI 17)..
However, there are relevant ICF KPIs included in the indicator methodologies which have been specifically developed for technical assistance programmes and which FGMC2 will report against:
- Technical Assistance KPI 1- Countries Supported
- Technical Assistance KPI 2- Individuals and Organisations Supported
- Technical Assistance KPI 3- Climate Policies Informed
- Technical Assistance KPI 5- Emissions Reductions Supported
Independent programme review. FCDO will also commission an evaluation/Mid Term Review in year 4 and 10 of the programme to inform FCDO decision making. The year 4 review will provide evidence to inform the development of the second tranche of the programme from year 6-10.
### Risk management
The risks associated with the programme relate principally to the fragile, sometimes post-conflict, contexts where tropical forests and forest people live, often with deep-rooted and entrenched challenges affecting transparency, accountability, and capacity. These include: (a) poverty and natural resource degradation; (b) conflict; (c) forest access controlled by regimes without regard to the rights of indigenous people or forest-based communities; (d) institutionalised corruption; (e) conflicts of interests; (d) and political instability, economic and health crises.
FGMC2 is designed to be receptive to the risks associated with challenging forest governance contexts, working to build strong governance foundations and coalitions of stakeholders engaged to challenge the status quo in the forest sector. These are mitigated through work with international policy levers that seek to create positive incentives for forest stewardship that reinforces national reforms. The programme is also willing to take on and manage reputational risk so long as that does not harm the overall programme’s licence to operate. In line with the FCDO’s new risk management approach, FGMC2.s overall risk appetite across the seven risk appetite categories is as follows:
    1. Strategy and Context: Receptive (eager in some contexts and with major residual risk balanced across different country contexts)
    2. Policy and Programme Delivery: Receptive (Global policy engagement to motivate reforms across 16 countries with moderate residual risk)
    3. Public Service Delivery and Operations: not applicable
    4. People: Cautious
    5. Financial & Fiduciary: Cautious
    6. Safeguarding: Cautious
    7. Reputational: Cautious across the programme, but receptive in specific contexts
FGMC2 will continue to adopt a portfolio approach to managing and balancing risks across a range of different country contexts and projects with a variety of types of partners. This portfolio approach will apply particularly to Strategy and Context, Policy and Programme Delivery, and Reputational risks, and enable certain aspects of the programme and/or certain projects to adopt a higher risk appetite for these risk categories and they will be counterbalanced elsewhere in the programme. For example, the forest governance context in Congo Basin countries is likely challenged by greater residual risks than in other geographies who may regulate the sector more effectively and ensure a balance of benefits to local communities and Indigenous peoples. The programme will manage and monitor significant reputational risk, noting the high visibility of the programme, work with emerging markets (eg India and China) and work with critical NGOs to improve accountability, combat crime and corruption.
We judge an overall moderate risk across the planned portfolio of FGMC2 similar to the risks encountered in the first phase of the programme and within our ECED and FCDO overall risk appetite.
The programme’s risk appetite is aligned with FCDO’s overall Risk Appetite Statement.
#### Initial delivery chain risks
Key risks relate to the identification and mobilisation of suppliers. Successful appointment of suppliers and mobilisation of TA contracts to support reform processes in priority focal countries (Components 1 and 2), and to launch the FGMC Accountable Grants programme. The design of the International Forest Governance Hub, hosted by EFI IPF, to provide independent responsive advice and analysis for partner countries requires the financial contribution of other donors to deliver to its full potential. Although other donors have expressed interest, this will require further work from the ECED FGMC team to secure their commitment. All Tier 1 suppliers will be subject to rigorous due diligence to ensure their capacity to deliver in line with current FCDO policies. The FGMC Accountable grants scheme will build from earlier phases of the programme, with key lessons for delivery integrated into the new management arrangements. This will ensure that grants are well targeted and fully meet all aspects of FCDO due diligence and safeguarding requirements. Further detail on the accountable grants scheme is set out in Annex K.
#### Risk management measures and escalation
FGMC2’s risk management strategies draw from the approach applied to risk management in phase 1 and the PrOF guidance on risk management. Risks will be mitigated by adopting a delivery model that has largely been tried-and-tested in FGMC1 and through careful design and management of the contracts and non-contract agreements. The responsibility for monitoring, managing and reporting programme delivery, people, fiduciary and safeguarding risks in the delivery chain will largely be transferred to the PMSST and other tier 1 delivery partners, and thorough due diligence prior to appointment will test prospective suppliers’ risk management capacity and processes.
Nevertheless, the FCDO programme team will be responsible for managing and mitigating risks. The SRO and programme team will be responsible for identifying, assessing, treating, monitoring, reporting and escalating risks on a day-to-day basis. The programme will maintain a risk register on AMP to identify and categorise risks, assess them in line with risk appetite and document risk treatment. The SRO and programme team will engage in regular conversations about risks with programme partners and suppliers, FCDO posts and programme stakeholders, and will be responsible for updating and reviewing the risk register on a monthly basis. Formal control points, such as Annual Reviews and periodic management meetings, will provide additional forums to consider wider risks beyond the immediate scope of programme delivery, such as political and economic issues and policy priorities. As required and appropriate, risks will be escalated to senior managers and ministers along the escalation routes described earlier in the Management Case.
The staggered approach to delivery will provide clear decision-points to consider risk and course-correct. This approach to delivery over the programme’s ten-year lifespan will provide an opportunity for ministers and senior management to consider overall risk and risk appetite, consider emerging lessons, and adjust the approach to risk management as appropriate.
#### Risk register
Key programme risks, mapped against the FCDO’s seven categories of risk, are the risk of loss of momentum and commitment to climate and nature action as short-term crises absorb focus and attention, and the challenges of implementing transformational change in the forest sector, where many vested interests, perverse incentives and strong market pressures drive change (Table 14). A more detailed risk register, risk matrix and risk appetite can be found in Annex O.

Table 14 - Risk Register
Risk Category	Key Risks	Mitigation
Strategy and Context	Fragile and or conflicted affected states, , civil unrest and security risks, particularly associated with IPLCs, forest crime could affect programme delivery.	Conflict-sensitive and politically smart approaches to delivery, including political economy and conflict analysis in policy dialogue, safeguarding approaches in supporting IPLC. Facilitation of deliberative processes that foster social inclusion. / The programme will seek to address forest-resource related tensions fostering inclusive processes and contributing to wider peacebuilding where possible. Skills in PMSST in conflict sensitivity and PEA to guide country strategy processes
	Partner (and UK Government) ambition on climate and forests diluted by geopolitical challenges, economic pressures and market volatility. A crowded donor landscape limits political space for inclusive national scale governance reforms	Ministerial and official-level engagement to maintain forest and climate ambition and engagement at country and international levels. Build a community of practitioners through grants and policy engagement to animate and inform policy dialogues; support national processes that spur donor coordination and pooling of resources where feasible; develop the International Forest Governance Hub with strong outreach to producer countries and other donors
	Shifts in international trade patterns, the increasing influence of Asian and regional markets diminish the influence of regulated consumer market measures	Programme will monitor global trade dynamics trends and target Component 2 and Component 3 actions to inform increasingly influential markets. FGMC2 will invest in building and capitalising on strong relationships with partner countries and international bodies to respond to emerging contextual risks. With respect to Asian markets, Component 2 is designed to foster dialogue and understanding with tropical forest countries
	Consumer market legislation (EU, UK, USA) seen as trade barriers by producer countries; combined with perceptions that the EU no longer backs VPA which diminishes the value for FLEGT licences	The programme will support increased understanding of consumer market measures in tropical forest countries. It will support efforts of producer country coalitions to see greater understanding and appreciation of their national systems in large markets beyond the EU FLEGT, notably in Asia
	The Theory of Change causal assumptions do not hold, particularly in the context of improved benefit flows to poor forest users and insufficient incentive and motivations of forestry stakeholders to engage in genuine deliberative processes	Political economy analysis and conflict-sensitive approaches to country specific strategies and interventions inform policy and legal reforms to strengthen IPLC and other forest stakeholders’ rights. Global market and political actions create sufficient external leverage to incentivise national stakeholders to engage. Monitoring and learning will focus on potential benefits and negative impacts in reforms that will inform country strategies; monitoring will inform strategy to focus action where multi-stakeholder political engagement is feasible and to exit where it is not. Facilitators will help to ensure that the deliberative process engages all stakeholders
Policy and Programme Delivery	Rights of Indigenous people, poor forest dependent people and other marginalised groups not prioritised in reforms, perpetuating, and entrenching social inequality and injustice	Support to stakeholders to actively engage in deliberative inclusive processes, building capacity to give voice to women, and IPLCs on issues that concern them. Ex ante analysis will be carried out to inform such processes. Impact monitoring, safeguards on rights, social and environmental protection are all built into the timber licenses that many of the countries are seeking. Evidence from FGMC1 suggests that improved regulations are helping communities secure more benefits from forest operations. Facilitators will help to ensure that the deliberative process engages all stakeholders
	Low partner government and CSO & private sector stakeholder technical capability, notably with regards to compliance with and enforcement of governance reform and risk of abuse of enforcement authority	Technical Assistance will strengthen Government abilities to lead reforms and put actions and systems in place that encourage implementation and compliance with agreed reforms by business, government agencies and CSO alike. Civil society and the private sector capacity development will be supported through accountable grants.
	Grants and technical assistance are poorly coordinated across many countries	PMSST will work closely with FCDO (FGMC team and Post) in oversight and strategic guidance across all elements of the programme and the country-level strategic planning will help manage this risk. . PMSST will manage the accountable grant scheme and provide technical backstopping to country focused TA projects. Grant holder onboarding will ensure coherence with country level theories of change.
Public Service Delivery N/A		N/A
People	Insufficient FCDO capacity and expertise to oversee the programme owing to staff turnover or internal human resource challenges.	Centrally managed programmes provide streamlined oversight; and outsourced delivery harnesses the market for specialised expertise. The FCDO team should remain alert to risks of over-extension and to principle agent problems, these will be managed and mitigated through clear governance arrangements and periodic reviews The International Forest Governance Hub will make expertise available for FCDO and Posts in support of policy dialogues. Insufficient capacity in key Posts may be supplemented through in-sourcing (programme financed posts) or outsourced management if required
Safeguarding	Policy reforms result in harm to poor and vulnerable communities in forest regions.	Careful and continuous risk assessment of any policy and legislative reform processes to identify risks of unintended consequences or of process being subverted to promote other interests.
Financial and Fiduciary	Contract and Grant funding for activities is misused, embezzled, or not used for intended purposes.	Due diligence, payment in arrears, regular monitoring and audit.
Reputational	FGMC partners act in a manner that damages UK reputation by association with organisations critical of partner government (in)action on corruption, human rights problems, environmental crimes	Forests are contested resources with different stakeholders having views on how they should be managed. FGMC sets out to support all sides of the debate through facilitated inclusive and deliberative processes, with a view to arriving at agreed positions through reform processes As such, FGMC delivery instruments provide support to all stakeholders to participate in these processes.
	Public criticism for engagement and geopolitical tensions with China, India and other MICs that are major importers of tropical forest products	Clear communication of the rationale for FGMC working with middle-income countries such as China and India (major importers of timber and forest risk commodities) necessary to create the positive incentives for reforms in tropical forest countries. Alliances with consumer markets are critical to encourage them to close their markets to illegal products, that support forest stewardship in tropical forest countries. The government’s aim to ensure a long term consistent approach to engaging with China on global issues such as the climate and nature agenda reinforces the position set out in the refresh of the Integrated Review. But there remains a risk that wider geopolitical tensions make meaningful engagement challenging

[111]
## References