## Annual Review Template

Title: Start Fund III - a global response mechanism for providing lifesaving humanitarian assistance through NGOs
Programme Value £ (full life): £49 million		Review date January 2026
Programme Code: 301074	AMP start date: 4/10/2022	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2022/23	2023/2024	2024/2025
Overall Output Score	A+	A	A
Risk Rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://view.officeapps.live.com/op/view.aspx?src=https://iati.fcdo.gov.uk/iati_documents/D0003482.odt&wdOrigin=BROWSELINK https://iati.fcdo.gov.uk/iati_documents/D0003482.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0003851.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Start Fund is a global pooled financing mechanism designed to enable rapid, flexible, and locally led humanitarian responses to underfunded small to medium scale and ‘under the radar’ crises (those that receive little attention from media or donors but still require urgent action), as well as sudden escalations in ongoing humanitarian emergencies. In its third year, marked by deepening global funding gaps and rising humanitarian needs, Start disbursed £18.9 million to support 87 activated alerts across 44 countries, reaching over 1.19 million people. It continues to demonstrate strong performance in speed and responsiveness, with 83% of projects delivering assistance within seven days of activation. Based on their performance during this reporting period, Start has earned an overall score of A (met expectations).
The Start Fund’s model is grounded in the principles of localisation, agility, and accountability. It has made significant strides on anticipatory action this year, with 42% of relevant projects with established protocols successfully reaching communities before the onset of crises, while consistently maintaining high levels of community engagement and satisfaction. It also played a critical role in leveraging additional funding (£7.98 million) demonstrating its catalytic value within the wider humanitarian financing ecosystem.
While the programme remains highly relevant and effective, challenges persist in meeting some localisation targets, particularly in direct funding to local and national non-governmental organisations (LNNGOs) (6% overall, though 30% in countries with LNNGO presence). Access to training for all NGO members, and learning, integration into projects also require further attention. Start has clear strategies in place to address these gaps, including strengthened onboarding, mandatory Indirect Cost Recovery (ICR)-sharing, and expanded learning and accountability frameworks. Despite these challenges, the Start Fund continues to fill a vital niche within FCDO’s centrally driven offer to the country network, responding quickly to small-to-medium scale crises and enabling locally led action.
Major lessons and recommendations for the year ahead

Lesson 1 – The Start Fund Model: Start’s rapid disbursement and locally led implementation remain central to the Fund’s effectiveness. Projects initiated within seven days of activation consistently deliver high-quality, relevant assistance, reinforcing the value of decentralised decision-making and rapid funding.
Lesson 2 – Resources and Prioritisation: 2025 has seen an unprecedented number of alerts raised, with the total now reaching over 1,000. As ODA budgets decline and underfunding of crises becomes more severe - Start will need demonstrate more clearly that resources are being rigorously prioritised and are reaching the most vulnerable and marginalised populations in the countries most in need.
Recommendation 1: Start should further strengthen and clearly communicate its prioritisation criteria and processes, ensuring that resource allocation is transparent, evidence-based, and focused on the most vulnerable and under-served communities.
Lesson 3 – Localisation: Localisation is at the heart of Start’s delivery model, but there is further to go to genuinely localise responses and to bring more power and decision making to local communities. Growing competition among NGOs for limited funding could also undermine progress in directing an increasing share of funding to LNNGOs.
Recommendation 2: Start should continue to monitor and track progress against targets for localisation and focus on addressing challenges to achieving localisation objectives - particularly by increasing direct funding to local and national non-governmental organisations (LNNGOs) where appropriate.
Lesson 4 - Alert Patterns: Start’s performance in responding to ‘under-the-radar’ alerts (36% vs. 55–60% target) reflects increasing demand from larger and higher profile emergencies. Members are creating more ‘gap filling’ alerts to address rising humanitarian needs and diminishing funding from other sources.
Recommendation 3: START should continue leveraging its comparative advantage in locally-led delivery and a focus on under-the-radar, small to medium-scale crises and surges in chronic humanitarian emergencies, rather than expanding to ‘gap fill’ larger and higher profile responses. This will help maintain its niche within the evolving global humanitarian landscape and make the best use of increasingly scarce resources.
### Lesson 8 - Accountability The Finance Management and Assurance Check-in Tool (FACT) continued to monitor risks, but no projects triggered spot checks or audits this year. Reliance solely on project assessments limits assurance breadth and embedding assurance checks systematically will ensure risks are identified early and addressed consistently.
Recommendation 6
Start should consider making audits and spot checks mandatory on a minimum percentage of projects, even where thresholds are not met, and embedding assurance checks systematically in projects to enhance transparency and accountability.
Lesson 9 - LNNGO Onboarding
START’s rapid and high intake of LNNGO membership at a single time adversely affected the participation metrics of LNNGOs during the alert cycle. Start successfully onboarded 53 new LNNGO members during the year, but participation in proposal submission, alert surveys and training was below target, especially among new members. Newly onboarded LNNGOs require time and support before they can fully engage with Start Fund processes and governance.
Recommendation 7
Start should focus on embedding onboarding mechanisms for new member LNNGOs, providing structured induction and ongoing support to enable meaningful engagement with Start Fund processes. A phased onboarding approach, coupled with capacity-building initiatives and targeted support and mentorship will help new members integrate effectively and improve overall participation in Start governance and decision-making processes. Start should also consider building in feedback loops and use insights to refine training content, delivery formats, and engagement strategies.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Start Fund’s Theory of Change (ToC) continues to guide its strategic direction. By pooling resources from multiple donors, decentralising decision‑making to its diverse membership, and embedding localisation principles, START seeks to address critical gaps in the humanitarian system. START’s response has reached over 1.19 million people across 44 countries during the review period August 2024-July 2025, with 83% of response projects delivering assistance within seven days; demonstrating fast, flexible, and more locally led humanitarian responses. In June 2025, minor changes were made to Output 1.5 following the recommendations from the August 2024 Annual Review. In light of the extension of the existing Business Case (to 31 March 2026), an additional reporting period was added (August 2025 to March 2026). The logframe has also been updated to reflect the extension.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Progress towards impact and outcomes in 2024/25 was mixed but broadly positive.

Impact: The programme continued to improve its timeliness, with 83% of projects beginning within seven days of activation, exceeding the target range of 55–60% and improving from last year’s 81%. The average number of days between a project’s start date and the date of reaching affected populations was 7 days, highlighting an improvement on last year’s average of 8 days. Impact monitoring also revealed high satisfaction rates among affected communities. For example, 94.5% of respondents reported satisfaction with timeliness, 95.5% with quality, and 92.5% with relevance. There was also evidence of medium- and long-term benefits linked to activities such as capacity building that strengthened knowledge and skills, WASH infrastructure improving hygiene and disease prevention, and cash transfers that enabled savings, investment in agriculture, and home reconstruction. However, the total number of people reached 1.19 million (53% were female and 47% were male) was slightly below the target of 1.37 million. This figure is expected to improve based on predicted results of 20 projects that are currently being reviewed. A key area of concern is the decline in direct funding to local and national NGOs (LNNGOs), which dropped to 6% from 11% last year, falling short of the 12% target. This decline is attributed to increased global demand on the Fund and delays in onboarding new LNNGO members and also potentially INGOs not passing resources on to LNNGOs.

Outcome: The Start Fund’s outcome performance reflects a mix of progress and challenges. Improvements were seen in several areas: the average alert time for response to reach beneficiaries from project start date rapid onset crises improved to 15 days, better than last year’s 16 days; 42% of anticipatory projects reached communities ahead of crisis onset, exceeding the 20–25% target; and 90% of training participants reported increased confidence, surpassing expectations. Core outcomes remained stable, with 100% of projects seeking community feedback and 73% implemented in consortium, both consistent with/or above targets. However, some outcomes fell short. Only five of eight Learning Grants embedded learning into practice, and just 18% of LNNGOs submitted proposals, well below the 50–55% target, largely due to onboarding delays. Training access also lagged, with only 67% of eligible agencies participating, particularly among newly onboarded LNNGOs. These results highlight the need for continued investment in capacity building and support for local actors and also for Start to effectively manage its growth in way that ensures there is sufficient support available for new Members.

ToC Assumptions: Core assumptions of the Theory of Change largely held true. Local actors demonstrated meaningful engagement when supported, as seen in increased alert submissions and participation in decision-making. The assumption that rapid funding leads to timely impact was validated by the high percentage of projects reaching communities within seven days.  However, the assumption that learning would be consistently embedded into practice was only partially met. While several Learning Grants led to policy influence and operational improvements, such as gender-inclusive disaster governance in India and inclusive DRM legislation in Zimbabwe, others faced delays in reporting or required more time for learning to be applied. This highlights the need for continued support in translating learning into action, especially for smaller or newly onboarded local organisations, and the need for a continued focus by Start on monitoring and evaluating its programmes.

Looking ahead, Start will continue to refine its theory of change through the ongoing log frame revision and external evaluations. The Evaluation of Locally Lead Humanitarian Action from 2025 provides new evidence on Start’s normative contribution to system change and FCDO will work with Start to track progress against evaluation recommendations as part of the follow up to this Annual Review. Alongside this, the embedding of a new AAP framework and the scaling of post‑distribution monitoring will further test the assumption that faster and more locally driven delivery produces more accountable and effective responses. Together, these processes will help ensure that START’s theory of change remains fit for purpose in a rapidly evolving humanitarian landscape.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Overall, the evidence in this annual review confirms the continuing relevance of Start Fund but also highlights areas requiring attention. The model continues to deliver high-impact, rapid, and locally led humanitarian responses in an increasingly resource-constrained global environment. It remains clearly effective in achieving speed, accountability, and anticipatory action. For example, during the reporting period, it reached over 1.19 million people across 44 countries, with 83% of projects delivering assistance within seven days.

However, this reporting period was marked by significant external pressures, including global funding cuts, particularly from USAID, which increased demand on the Start Fund and intensified competition amongst INGOs and LNNGOs. Start will need to reflect on its operating model in an increasingly ODA constrained world to ensure it continues to focus its efforts on reaching the most vulnerable populations in the most at-risk countries.

The onboarding of 53 new LNNGO members introduced capacity and engagement challenges, requiring time and support to fully integrate into Start Fund processes. Operationally, Start adapted by introducing Indirect Cost Recovery (ICR)-sharing with LNNGO members, refining allocation criteria, and leveraging automation to improve efficiency and equity. These shifts underscore the need for continued prioritisation, capacity building, and strategic adaptation in the year ahead.

## C. DETAILED OUTPUT SCORING

Output Title	Quality and timely crisis alerts are raised, which align with the Start Fund niche. Fund decision-making is collaborative and informed by humanitarian expertise and local knowledge.
Output number:		1	Output Score:		B
Impact weighting (%):		50%	Weighting revised since last AR?		N/A

Indicator(s)				Milestone(s) for this review		Progress
1.1: % of Start Fund alerts that are considered 'under the radar' crises according to the Start Fund 's internal definition				55-60%		36%
1.2: % of alerts activated				85-90%		69%
1.3: % of activated alerts that are anticipatory or based on a forecast				20-25%		22%
1.4: # and % of members participating in at least one alert survey per year (disaggregated by national and international organisations in the narrative)				75-80%		70% (74 out of 106)
1.5: % of Start Fund activations in which funding is initiated within 72 hours				a) within 72 hours: 65-70% (excluding activations in Latin America); / b) within 74 hours: 65-70% (including activations in Latin America)		78% / 84%

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicator 1.1: The indicator was not met. A score of 36% of Start Fund alerts that were considered 'under the radar' crises (according to Start Fund’s internal definition: “crises which are not the subject of, or linked geographically or thematically to, an active emergency response, whether or not emergency response capacity is coordinated by the respective, responsible government or the international system”) is a 9% decline compared to the previous year, and highlights the strain on the global humanitarian financing system. The percentage of alerts categorised as ‘gap-filling’ (i.e. responding to underfunding in higher profile, active responses) rose from 38% in 2023/24 to 48% in 2024/25, reflecting the overall rise in humanitarian needs and the lack of funding available.

Indicator 1.2: The indicator was not met. Out of 127 alerts raised, 87 were activated. Non-activation occurred primarily when alerts fell outside Start’s niche, followed by concerns around timeliness and limited potential impact within a 45-day response window. This lower activation rate reflects both the increased volume of alerts and stricter prioritisation by allocation committees comprised of INGO and LNNGO members. These reasons, often overlapping, reflect a more rigorous decision-making process introduced in response to USAID funding cuts and increased global demand.

Indicator 1.3: The indicator was met. 19 anticipatory alerts were activated across 15 countries, addressing floods, disease outbreaks, conflict-related displacement, and cross-border migration. The consistently high activation rate reflects members’ growing commitment to forward-looking action. This proactive approach enables timely relief before disasters occur, safeguarding lives and preserving the dignity of affected communities.

Indicator 1.4: The indicator was not met. Participation from INGOs was very strong (92 percent), but engagement by LNNGOs was lower at 58 percent, largely due to the induction of 53 new members, including 29 new LNNGO members and two INGO members in Pakistan, who are still consolidating their role in Fund processes.

Indicator 1.5: The indicator exceeded target. Activation response time saw a marked improvement compared to the previous year (36%). This was enabled by refined alert scheduling rules and automation of monitoring tools.

Overall, Output 1 showed mix performance and scored a B. Start exceeded targets on timeliness, with 78% of activations funded within 72 hours, and met expectations on anticipatory alerts (22%). However, under-the-radar alerts fell to 36% and activation rates dropped to 69%, highlighting pressures on its niche role. Overall, Start continues to deliver speed and anticipation but fell short on coverage of neglected crises and inclusivity.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

During 2024/25, Start revised its allocation decision-making guidance to sharpen prioritisation, introducing anonymous polling, structured historical notes, and additional questions on niche and impact. Scheduling rules were also adapted to improve timeliness across time zones. There has been a shift in response allocation from ‘under the radar’ alerts to ‘gap-filling’ alerts. This shift is linked to the overall increase in humanitarian need and the noticeable funding gaps being reported due to USAID funding cuts. Looking ahead, Start plans further refinements to allocation processes to ensure speed is balanced with effectiveness and impact, as well as the expansion of anticipatory action through FOREWARN hazard groups and the integration of gender-sensitive approaches into allocation discussions.

Progress on previous recommendations from the 2024 Annual review:

Previous Recommendations (PR)	Progress
PR 1: Continue to prioritise increasing the pace of response implementation.	Start Fund made adjustments to its internal processes to schedule alerts and ensure, where feasible, that project selection takes place within 72 hours, while continuing to prioritise quality and risk mitigation. For example, in complex contexts, such as sanctioned countries, conditional awards may apply pending form approval. Moreover, in line with FCDO’s recommendation from the previous Annual Review, Start Fund now reports alerts raised in Latin America separately due to time zone differences.
PR 2: Continue to develop support to enable more anticipatory responses.	Start Fund has strengthened its anticipatory action through the FOREWARN platform and is establishing hazard-specific expert groups and improving collaboration between technical experts and NGO members. It is also supporting LNNGO members in implementing findings from the locally led anticipatory action evaluation and exploring multi-risk analysis approaches.
PR 4: Continue to prioritise empowerment of affected communities and increased Accountability to Affected Populations (AAP) as a vital and integral part of truly locally led responses.	Start continues to embed Accountability to Affected Populations (AAP) as a core principle. High community engagement in programme design and delivery reflects this. In 2025, Start developed an AAP framework, with consultations underway to ensure it is practical and responsive to operational constraints. Follow up action: Building on the progress, Start should continue to strengthen its commitment to Accountability to Affected Populations (AAP) by operationalising the newly developed AAP framework across all stages of the alert cycle.
PR 5: Review the degree to which gender-sensitive and gender-transformative principles are considered throughout the alert cycle; and review opportunities for tracking and promoting involvement of women-led organisations in the delivery of Start Fund responses.	Start initiated internal reviews to integrate gender-sensitive and gender-transformative principles across the alert cycle. Early efforts include co-designing gender-focused SOPs with members in Bangladesh, with further integration planned for 2026.
PR 7: Start Fund should work with FCDO to identify quantitative and qualitative indicators which better evidence the quality of interventions and their impact.	Start rolled out a set of mandatory post-distribution monitoring (PDM) indicators to better evidence the impact of its response. While uptake is still growing, initial qualitative insights are included in this review, with more comprehensive findings expected in the upcoming reviews. Follow up action: FCDO and Start should jointly review the initial uptake and effectiveness of the mandatory post-distribution monitoring (PDM) indicators. This review should inform the development of a refined set of quantitative and qualitative indicators that better capture the quality and impact of interventions. Additionally, both parties should agree on a timeline and methodology for integrating these indicators into future programme evaluations and reporting frameworks.

Lessons learned this year and Recommendations for the year ahead:

New Lessons	Recommendations
L4: Alert Patterns - Start’s performance in responding to ‘under-the-radar’ alerts (36% vs. 55–60% target) reflects increasing demand from larger and higher profile emergencies. Members are creating more ‘gap filling’ alerts to address rising humanitarian needs and diminishing funding from other sources.	R3: START should continue leveraging its comparative advantage in locally-led delivery and a focus on under-the-radar, small to medium-scale crises and surges in chronic humanitarian emergencies, rather than expanding to ‘gap fill’ larger and higher profile responses. This will help maintain its niche within the evolving global humanitarian landscape and make the best use of increasingly scarce resources.
L5: Anticipatory Alerts - Consistent performance on anticipatory alerts demonstrates growing member confidence in forward-looking and proactive approaches. The increased proportion of anticipatory projects reaching communities ahead of crisis onset (42%) shows growing capacity and confidence in forecasting and early action. However, the effectiveness of these interventions depends heavily on crisis type and timing, highlighting the need for tailored approaches.

Output Title	The network access learning, resources and training. Best-practice and innovation are made available and disseminated across network and sector. Assurance and accountability measures are appropriate and implemented.
Output number:		2	Output Score:		A+
Impact weighting (%):		30%	Weighting revised since last AR?

Indicator(s)			Milestone(s) for this review	Progress
2.1: # of learning tools and resources designed to enhance learning developed through the Start Fund (incl. Learning Grant Outputs, Research, Evaluations)			9	18
2.2: # of advocacy events/conferences with SF representation where SF plays an influencing role			4	19
2.3: # and % of Start Fund projects that undergo additional learning and assurance assessment (disaggregated by: project assessments, spot checks, and audits)			10%	9 out of 93 10% (9 project assessments – 6 in person, 3 remote, 0 spot checks, 0 audits)
2.4: % of anticipatory alerts informed by forecasting and risk analysis groups, i.e., FOREWARNs (disaggregated by a) % global FOREWARN, and % national FOREWARNs) or by b) technical support from Start/inclusion in the Risk Brief			a) 25-30% / b) 25-30%	a) 9% / b) 70%
2.5: # and % of member agencies which can access funding and attend training designed to enable Start Fund access and improve the quality of Start Fund alerts and responses (disaggregated by INGO/LNNGO in narrative)			75-80%	67% of member agencies that can access funding (60 out of 89); / 32 INGOs (out of 37 (86%)) / 28 LNNGOs (out of 52 (54%))

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicator 2.1: The indicator exceeded expectations. A total of 18 tools and resources were developed, including a major external evaluation on locally led humanitarian action, research on anticipatory action and loss and damage, and multiple learning grants that generated context-specific insights. Examples include Christian Aid’s cholera response analysis in Zimbabwe, ActionAid’s study on women- and youth-led responses, and Bright Star’s work challenging assumptions on long-term impact of short-term aid. Seven case studies on anticipatory alerts were also produced, covering floods, disease outbreaks, displacement, and climate-related hazards. While some learning grants are still pending final reports due to extensions, the volume and diversity of outputs demonstrate a strong commitment to learning and innovation. The priority for the year ahead is ensuring these findings are systematically disseminated and integrated across the network, particularly to support new LNNGO members and strengthen anticipatory approaches in disaster management and continued investment by the Start Network in monitoring and evaluation.

Indicator 2.2: The indicator exceeded expectations. Start Network contributed to key events and forums including COP29, the Humanitarian Finance Summit, and the Climate and Disaster Risk Financing Forum through thought leadership, panel discussions, and strategic advocacy highlighting the importance of localisation, anticipatory action, and innovative pooled financing, while also informing new initiatives such as the Conflict Anticipatory Action Project. Participation at this scale shows Start Fund’s growing influence, however, it is yet to be explored how these engagements and advocacy efforts can translate into tangible results. Going forwards Start could initiate impact assessments of its recent global engagements, including establishing action steps and results tracking that align with Start’s strategic objectives.

Indicator 2.3: The indicator was met. Nine projects underwent assessments, split between in-person and remote modalities. These included both anticipatory and response activations. While most findings were positive, two projects showed weaknesses in community feedback mechanisms, which were addressed through management responses. The Finance Management and Assurance Check-in Tool (FACT) continued to monitor risks, but no projects triggered spot checks or audits. Meeting the target reflects progress, yet reliance solely on project assessments limits assurance breadth. Given donor concerns about fiduciary risk, Start should consider introducing random spot checks and/or audits, even when thresholds have not been met, to strengthen transparency and accountability. Embedding assurance checks systematically will ensure risks are identified early and addressed consistently.

Indicator 2.4: The indicator was partially met. Technical input targets were far exceeded, with 70% of anticipatory alerts informed by the Crisis Anticipation and Risk Financing (CARF) team or Risk Bulletins. However, FOREWARN engagement fell short at just 9%. This imbalance reflects declining participation of FOREWARN experts as Start transitions to automated systems like Salesforce, though CARF stepped in to provide consistent support. The revamped Risk Bulletin has proven particularly influential, informing 48% of alerts compared with 22% last year. Plans are underway to revitalise FOREWARN through recruitment drives, training, and new engagement formats. The dual challenge for the coming year is to sustain the technical team’s strong contribution while rebuilding FOREWARN’s role as a community-driven knowledge platform.

Indicator 2.5 The indicator was partially met. Overall, 67% of member agencies accessed training, with strong uptake from INGOs (86%) but lower participation among LNNGOs (54%). Gaps were most evident in Pakistan, where many LNNGOs engaged more with Start Ready and missed Start Fund training. Training included online compliance sessions, in-person workshops in six countries, and self-paced modules, yet participation disparities suggest accessibility and relevance issues remain. Since training is central to enabling equitable access to funding, underperformance here risks slowing localisation progress. To address this, Start Fund should expand targeted outreach to LNNGOs, provide country-specific training, and actively track barriers to participation. Improving LNNGO uptake will be critical to achieving both equity and localisation commitments.

The score for output 2 is A+, reflecting delivery that moderately exceeded expectations overall. Overall, Start has demonstrated strong performance across multiple key areas, with significant achievements in learning, advocacy, and technical support. Nonetheless, there remain strategic opportunities to strengthen equity, accountability, and engagement. In particular, improving the accessibility of trainings will be critical to ensuring greater participation among LNNGOs.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

While there have been no changes in the output, training access for Local and National NGOs (LNNGOs) was below target, 55% for LNNGOs vs. 86% for INGOs, which poses a challenge for Start in building local capacity and ultimately achieving its localisation goals. Start should explore expanding its targeted outreach to LNNGOs, offer country-specific training, and track barriers to improve LNNGO engagement and support localisation goals.

Progress on previous recommendations from the 2024 Annual review:

Previous Recommendations	Progress
PR8: Identify opportunities to better track and articulate the relationships between Start Network activity and the benefits for the wider humanitarian system.	To better communicate the wider system-level impacts, Start are exploring ways to track and articulate how their innovations, approaches, and member-led actions contribute to broader humanitarian system change thinking. This includes incorporating system-change indicators into their organisational learning framework and sharing learning that highlights how START’s work influences policy, practice, and collaboration across the sector. / In practice, Start Network will look at sharing learning through: / Regular reporting cycles i.e. their annual reports, where they will highlight evidence of policy, practice and collaboration shifts influenced by Start Network’s work. / Start Network events i.e. Annual Assembly, Bi-annual learning exchanges, where they meet with their members and key stakeholders to reflect and synthesise on key thematic areas. / Collaboration and policy-oriented platforms e.g. Pooled Fund Community of Practice, Anticipation Hub, Global Dialogue Platform, etc, where they will continue active engagement through framing key discussions and sharing learnings.

Lessons learned this year and Recommendations for the year ahead:

Lessons	Recommendations
L6: Training - High satisfaction with training content (90% confidence increase) confirms the value of Start’s training offer. However, access remains uneven, especially among new members. Training uptake was strong among INGOs but low among LNNGOs, pointing to accessibility and relevance issues that must be addressed to ensure equitable participation and progress on localisation.	R4: Start should improve equity in access to training by identifying and addressing barriers faced by new members and LNNGOs. Prioritising accessibility and tailoring content to maximise relevance will be essential to drive localisation and ensure inclusive participation.
L7: Global Advocacy - Start’s active presence at global forums (e.g. COP29, Humanitarian Finance Summit) has elevated its visibility and influence. Yet, without structured impact assessments, it’s difficult to measure how advocacy efforts translate into tangible outcomes.	R5: Start should develop a system to track, evaluate, and report the outcomes of its global engagements to ensure it is achieving maximum impact and value for money.
L8: Accountability - The Finance Management and Assurance Check-in Tool (FACT) continued to monitor risks, but no projects triggered spot checks or audits this year. Reliance solely on project assessments limits assurance breadth and embedding assurance checks systematically will ensure risks are identified early and addressed consistently.	R6: Start should consider making audits and spot checks mandatory on a minimum percentage of projects, even where thresholds are not met, and embedding assurance checks systematically in projects to enhance transparency and accountability.

Output Title	The network access funds for humanitarian action, with local actors increasingly engaging with and gaining an increased proportion.
Output number:		3		Output Score:		A
Impact weighting (%):		20%		Weighting revised since last AR?

Indicator(s)			Milestone(s) for this review		Progress
3.1: # and % of member LNNGOs who submit alerts or proposals in countries where an alert has been raised.			Submitting alerts: 60-65% / Submitting proposals: 50-55%		Submitting alerts: 57% (38 out of 67) / Submitting proposals: 18% (12 out of 67)
3.2: % of activated alerts (in relevant countries i.e. where French or Spanish is the official working language) where alert documentation (proposal/ reports) is submitted in a language other than English			45-50%		78%

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicator 3.1 –The indicator was partially not met. For Local and National NGOs (LNNGOs) alert submission was 57%, just below the target of 60%-65%, and proposal submission was 18%, significantly lower than the target of 50%-55%. These figures were significantly lower than last year’s achievement that stood at 100% and 75% respectively and may therefore not be a true reflection of long-term performance against this indicator.
Start explained that the shortfall was due to the onboarding of 53 new LNNGOs in six countries, many of whom joined late in the reporting year and had little time to engage and familiarise themselves with the alert processes. While India and DRC showed relatively strong engagement, countries like Somalia, South Sudan, and Pakistan lagged, largely due to recent inductions. To address these gaps, Start launched a structured support plan in July 2025, providing targeted orientation, training, and tailored accompaniment for LNNGOs. This new approach includes quarterly collection of feedback from LNNGO members, to better understand experiences and eventual barriers to participation in the alert cycle. With continued investment in capacity-building and closer follow-up, Start aims to accelerate LNNGO participation and close the gap on ambitious localisation targets.
Indicator 3.2 –The indicator was substantially exceeded. Of 41 activated alerts in French- or Spanish-speaking contexts, 78% included proposals or reports in the relevant language, significantly surpassing the target of 45%-50%. This maintains last year’s strong performance (77%). Accessibility has also been extended to tools such as Learning Grant and Impact Monitoring reports. This steady compliance shows that multilingual engagement is now embedded in Start Fund processes, lowering barriers for non-English-speaking members and enabling more equitable participation. The challenge going forward is to sustain translation coverage and ensure quality while exploring ways to extend language accessibility further.
Overall Output 3 showed mixed progress, but with mitigating factors in areas of underperformance. Start just fell short on LNNGO submissions of alerts and proposals (3.1), primarily due to the large intake of new local and national members (which in itself is positive) who are not yet familiarised with the alert mechanism. By contrast, performance on language accessibility was very strong, with 78% of documentation in French or Spanish (3.2), significantly above target. This indicates that inclusivity in processes is becoming embedded across Start .

The overall score for this output is A (met expectations), reflecting that results on indicator 3.1 were affected by the large number of newly onboarded LNNGOs who have not yet had an opportunity to submit proposals.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There is no change to this output. However, there are notable contextual changes and programmatic adaptations that affected the performance of activities. In 2024/25, Start significantly expanded its membership by inducting 53 new LNNGOs. This expansion experienced a lag in engagement, which is expected to improve as new members become more familiar with processes. Looking forward, hubs are expected to play a greater role in providing ongoing accompaniment to new members, ensuring their faster transition from induction to full engagement in governance and funding.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Previous Recommendations	Progress
PR 3: Focus performance improvement on enabling locally led action.	Start has acted by substantially expanding LNNGO membership and implementing mandatory ICR sharing with the NGO members, improving equity in partnerships. Induction of newly onboarded NGO members was redesigned with in-person workshops, enabling faster engagement in governance and funding. While direct funding remains below target, these measures demonstrate clear structural progress. / Hubs are emerging in Afghanistan, Bangladesh, DRC, Guatemala, India, Philippines, Somalia, South Sudan, and Pakistan, with Pakistan hub closest to independence. Further member intake across 2026-2027 is expected in Afghanistan, DRC, Guatemala, Somalia, and South Sudan. These hubs are being positioned to deliver the sustained accompaniment to members recommended in previous reviews.

 Lessons learned this year and Recommendations for the year ahead:

Lessons	Recommendations
L9: Partner Onboarding - Start’s rapid and high intake of LNNGO membership at a single time adversely affected the participation metrics of LNNGOs during the alert cycle. Start successfully onboarded 53 new LNNGO members during the year, but participation in proposal submission, alert surveys and training was below target, especially among new members. Newly onboarded LNNGOs require time and support before they can fully engage with Start Fund processes and governance.	R7 – Start should focus on embedding onboarding mechanisms for new member LNNGOs, providing structured induction and ongoing support to enable meaningful engagement with Start Fund processes. A phased onboarding approach, coupled with capacity-building initiatives and targeted support and mentorship will help new members integrate effectively and improve overall participation in Start governance and decision-making processes. Start should also consider building in feedback loops and use insights to refine training content, delivery formats, and engagement strategies.

## D: VALUE FOR MONEY

The Start Fund continues to represent strong value for money across all four dimensions of the FCDO Value For Money (VfM) framework: economy, efficiency, effectiveness, and equity. In a year of heightened demand and financial volatility due to US funding cuts, Start demonstrated that it can continue to deliver lifesaving assistance quickly and at scale, providing a cost-effective way to respond to small to medium-scale crises, while advancing localisation and accountability objectives. It has also provided a visible way for the UK to reach the most vulnerable, particularly in hard-to-reach areas, and where FCDO does not have humanitarian programmes. It delivers on FCDO's policy priorities of fast, flexible, locally led disaster responses.

On economy, the Start Network has worked to minimise costs by using internal capacity and new technology:

- AI tools were used to translate research and evaluation into Spanish and French, with external interpreters engaged only for proofreading, cutting translation costs significantly.
- Travel costs were reduced by using regionally based staff for in-person project assessments, such as those conducted in India, Senegal, and Colombia. Additionally, Start adopted a simplified travel planning process that allowed for trip consolidation and increased use of online participation, further reducing emissions and costs.
- Capacity strengthening for new LNNGO members has been achieved at relatively low cost through peer support by regional hubs, maximising reach while keeping training and induction expenditures proportionate.
The top three key costs are staffing, third-party briefing notes and Learning Grants. These costs are covered by contributions from multiple donors, ensuring efficiency and shared value.
Despite significant growth in disbursement over the years, now close to £20 million per year, core costs have been kept proportionally low, by operating with a lean team.
- Third-party briefing notes provide decision-makers with crisis analysis to triangulate information quickly – a service that is both unique and valuable for quality decision-making.
- Learning Grants are small awards to implementing members that capture and share lessons from early responses, ensuring knowledge is disseminated and applied across the network and the wider humanitarian sector.
On efficiency, during the reporting period, 78% of activated alerts were funded within 72 hours and 84% within 74 hours (including Latin America). This rapid disbursement mechanism allowed Members to initiate life‑saving activities within a week of crisis onset in most cases, with 83% of projects reaching affected populations within seven days. These figures confirm Start’s comparative advantage is the speed at which it is able to provide assistance to affected communities, unmatched by other pooled mechanisms, and ensuring that limited resources achieve maximum immediate impact.
Other examples of efficiency gains included using local storage facilities, pre-identified vendors, and community-based monitoring to reduce operational costs. The Start Network also has a good record of catalysing funding from others with initial “seed” funding attracting support from other donors, amplifying its impact.
On effectiveness, this was evident through Start’s rapid response and high-quality delivery. During the reporting period 1,195,363 people were reached with life-saving assistance across 44 countries. This is slightly less than the previous reporting period and is largely explained by the fact that, at the time of reporting, 20 projects had not yet submitted final reports, and some were still under review. Updated reach figures will be shared with FCDO later this year.

Timeliness also improved with 83% of projects reaching affected communities within seven days, up from 81% last year. Impact monitoring found that 94.5% of beneficiaries were satisfied with the timeliness of the response, 95.5% with the quality, and 92.5% with the relevance of assistance provided.

External evaluations and learning grants have confirmed that LNNGO-delivered projects delivered faster and more contextually appropriate responses, whereas INGOs were better equipped to meet donor requirements and brought technical capabilities. For example, ActionAid Zimbabwe’s Learning Grant (Alert 688), implemented through a LNNGO partner, influenced national disaster legislation to include women, youth, and people with disabilities in decision-making structures. Similarly, the evaluation of Alert 850 in the Philippines (convened by the INGO Humanity & Inclusion, and implemented in a mixed consortium made up of both INGOs and LNNGOs) demonstrated the effectiveness of anticipatory action in preventing disease outbreaks following Typhoon Carina.

Accountability has been strengthened by the development of an AAP framework and the piloting of post-distribution monitoring, which has provided evidence on the impact and appropriateness of projects. Of the projects that have submitted reports, 89% conducted Post-Distribution Monitoring (PDMs) and/or Impact Monitoring. Together, these demonstrate that Start is not only fast, but also effective in delivering relevant and responsive humanitarian assistance.

On equity, Start continued to deliver on its localisation objectives despite a constrained funding environment. During the reporting period, 1,195,363 people were reached with life-saving assistance in 44 countries. Of these, 53% (631,173) were female and 47% (564,190) were male; 44% (525,503) were children under 18, 44% (531,096) were aged 18 to 50, and 12% (138,764) were older than 50. In addition, 21,221 people with disabilities were reached, just over half of whom were female. Inclusive programming remained a priority, with 87% of projects targeting marginalised populations and 81% of communities reporting fair and impartial aid distribution.

Geographically, the largest proportion of responses were delivered in Eastern Africa (42%), Western Africa (20%) and Central Africa (7%), alongside significant responses in South America, the Caribbean, Southern Asia and the Middle East. These included fragile and conflict-affected states such as Somalia, South Sudan, Sudan, Afghanistan, and Haiti.

Direct funding to LNNGOs fell to 6% of total allocations (and 30% in countries where Start Network has LNNGO members), down from 11% last year. Start attributes this decline to growing global demand on the Fund, which has led to more alerts being raised and activated in countries without LNNGO presence, as well as heightened competition following sector-wide funding cuts. However, progress was made on localisation through the induction of 53 new local members and the introduction of mandatory Indirect Cost Recovery (ICR) sharing, which supported the financial sustainability of local partners. In countries with LNNGO presence, 37% of projects were led by local organisations, exceeding the set target for this period.

Although localisation and gender integration targets remain ambitious, they represent a significant shift towards a more equitable distribution of resources and responsibilities within the network, with potential to enhance value for money and contribute to system change in the longer term.

Assessment of whether the programme continues to represent value for money

The Start Fund continues to represent good value for FCDO’s investment. It provides cost‑effective humanitarian assistance, ensures resources are deployed efficiently and rapidly, achieves effective outcomes for affected populations, and makes equity central to its operating model. In the year ahead, continued focus will be required to meet localisation targets, deepen gender integration, and capture evidence of long‑term system change to further strengthen Start ’s VfM case.

E: RISK

Overview of risk management

The programme’s overall risk rating remains Moderate and is in line with FCDO’s risk appetite for the programme. The rating reflects the inherent high level of risk present in humanitarian contexts, alongside Start’s robust internal systems for mitigation and accountability.

During the reporting period, Start and FCDO actively managed risks through quarterly reviews of its risk register and by following established serious incident reporting protocols. Quarterly risk reviews included in-depth meetings to update risks and mitigation plans to ensure ongoing programme compliance. As part of the transition from Start Network being a hosted entity under Save the Children UK (SCUK) to becoming and independent entity, a dedicated incident reporting protocol was developed to ensure continuity and accountability. The revised Start Fund Handbook, formally rolled out to members in June 2025, includes a dedicated reporting channel within the Start Network.

FCDO and Start actively manage the fraud and safeguarding cases reported by Start members. New cases are reported to FCDO in line with agreed procedures and reporting mechanisms appear to be working properly. Monthly meetings are held to review and assess the status of new and open cases, and regular management is needed to track their status, with a particular focus on following up legacy cases to expedite closure.

Financial assurance and risk monitoring were strengthened this year through Start’s Financial Management and Assurance check-in tool (FACT), which acts as a feedback loop that helps improve key compliance processes like SOPs, templates and guidance documents. It provides a source for trend analysis which then informs where additional oversight, capacity strengthening support, or audits may be required. Further investigations or audits may be triggered following the completion of a financial management and assurance check-in, depending on the severity of findings (especially where these relate to the management of safeguarding incidents, critical incidents or frauds), or due to the quality of the management response to check-in findings.  Although no cases triggered formal audits during the reporting period, the tool has proven effective for early risk detection. Findings from financial assurance and compliance spot checks and audits are also fed back into learning cycles, which helps strengthen controls, and improve accountability across the portfolio. This further supports evidence-based decision-making at governance fora (e.g. Start Fund Committee), ensuring risk management approaches are applied consistently.

Start Network’s membership selection process involves a thorough Due Diligence Assessment that considers key compliance, regulatory, and operational capacities of prospective member organisations. Data gathered from this assessment is used to determine each organisation’s level of risk and how much funding they can access within Start Network. Based on this, organisations are classified into tiers, which inform not only whether they can access funding, but also when and how much they can access, and what risk management measures are required. Lower-tier organisations can typically access organisational strengthening support to build their capacities, while higher-tier members are eligible to access Start Fund grants directly.

Key risks identified and mitigation

Risk Type	Description	Mitigation
Financial	Failure to meaningfully diversify and sustain the donor base within a constrained humanitarian funding landscape.	Actively seek opportunities to promote the Start Fund, and intentional engagement of existing donors as fundraising partners.
Programme Delivery	Due to ODA cuts, some members have downsized staff at HQ and country offices, reducing capacity to engage in Start Fund decisions at both allocation and Project Selection Committee stages	Start Network has inducted more members in hub countries, which allows for responsibilities such as participating in decision-making meetings to be spread across a wider range of members.
Programme Delivery	Reduced amounts of funding reaching local and national NGOs due to increasingly constrained ODA context	Closely track and monitor levels of funding channelled to LNNGOs and provide capacity building to ensure targets are met

Overall, the risk position of the programme remains stable. The programme team will continue working closely with Start to implement risk management in line with PrOF guidance throughout the next reporting period.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

The Start Fund continues to deliver effectively against the targets set out in the Business Case and logframe. FCDO’s relationship with Start is characterised by proactive engagement and a productive and collaborative partnership which supports delivery of the programme’s objectives. Financial reporting updates are timely and consistently of a high quality. Formal reports are submitted annually, supplemented by regular informal updates during monthly meetings. Start demonstrates strong financial management, including accurate forecasting and effective asset monitoring. Audited financial statements are delivered in line with expectations.

Strategic Relationship and Commercial Considerations

SCUK served as the Grant Custodian for the Start Fund on behalf of the Start Network since its inception in 2014. In May 2019, the Start Fund became a legal entity, independent of Save the Children UK (SCUK). However, due to the phased transition of operations and programmes from SCUK to the Start Network across all grants, the process was fully completed on 13 October 2025. The final steps this year focused on ensuring a smooth handover of responsibilities and systems, which was concluded successfully without major challenges, marking a major milestone for the Start Network.

The Start Network adheres to the Supply Partner Code and meets cost and transparency requirements, including Open Book Accounting where relevant. Strategic Relationship Management assessments reflect positively on Start’s performance and contribution to programme outcomes.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring

For this year’s Annual Review two FCDO colleagues from outside the department were engaged to assess programme performance, provide an external and objective assessment of the evidence gathered, and make independent recommendations for strengthening the programme.

The Start Fund continues to strengthen its systems for management, accountability, and impact assessment. Recent developments have enhanced the consistency and quality of data collection across projects, enabling more robust insights into programme outcomes. In October 2024, Start introduced a revised Project Assessment Tool to assess management, accountability, and financial and logistical systems across projects and make recommendations on areas that require strengthening. In January 2025, a mandatory impact monitoring questionnaire was launched which was designed to harmonise quantitative and qualitative indicators when assessing impact across projects. The Start Fund is considering how to integrate impact monitoring data and analysis in future logframe indicators.

So far, 30 projects have adopted the impact monitoring tool following the successful pilot in January 2025 (out of the 58 projects implemented after the launch of impact monitoring and of the 33 reporting as of 15 August). For projects implemented before impact monitoring became mandatory, 86% (30 of 35) shared PDM results with the Start Fund. Therefore, of the projects that submitted reports so far, 88% (60 out of 68) have conducted Post-Distribution Monitoring (PDM) and/or Impact Monitoring. Early results show high levels of community satisfaction with the timeliness, quality, and relevance of interventions.

Lesson 10: Logframe Indicators - It was observed during this review that Start has not revised its indicator targets for future years based on performance in the current and previous reporting periods.

Recommendation 8: To ensure targets remain realistic and aligned with actual progress, Start should review and adjust upcoming targets to better reflect past achievements.
Recommendation 9: Start should continue to embed changes resulting from previous recommendations PR3, PR4, PR6 and PR7 from last year’s annual review, relating respectively to improving performance on locally led action, empowerment of affected communities and Accountability to Affected Population (AAP), tracking Start’s impact on the wider humanitarian system, and identifying indicators which better evidence the quality of interventions and their impact.

Evaluation & Research

Two external evaluations and one research study were completed this year. The ‘Measuring the Impact of Locally led Action’ evaluation found LNNGO-led projects to be highly effective, particularly on speed, quality, and community trust, though gaps remain in visibility and equitable power-sharing with INGOs. It found evidence of Start’s normative influence on the wider humanitarian system, providing a proof of concept for locally led, rapid financing and shaping discussions on localisation and anticipatory action. However, the evaluation noted that systemic change remains limited and impact to date is catalytic rather than transformative. Evaluation recommendations include empowering local actors, ensuring fair partnerships, speeding up funding, strengthening accountability, promoting learning, and advocating for systemic localisation. FCDO will work with Start to track progress against these recommendations as part of the follow up to this Annual Review, with some of the recommendations already incorporated into the Review's findings.

The ‘Towards Locally-Led Anticipatory Action’ evaluation assessed the inclusivity of anticipatory systems for LNNGOs, and recommended providing more tailored support, stronger integration of local knowledge, and improved technical resources to LNNGOs. The evaluation findings have been used to strengthen and expand Start’s approach to locally-led anticipatory action (LLAA), including embedding localisation criteria into Start Ready’s expansion, and integrating a community-led pillar within the Conflict Anticipatory Action Programme, with the prioritisation of LNNGOs.

The ‘Anticipatory Action and Loss and Damage’ research paper explored the role of anticipatory finance in reducing risks and highlighted the relevance of Start’s models for other policy makers. The key findings and recommendations from the paper have informed Start’s approach to the loss and damage agenda and have also been used to inform key strategic engagements in the margins of the World Bank and IMF Spring Meetings.

Learning

Learning was advanced through two Start learning events and new joint-learning exchanges, providing opportunities to share good practice on accessing hard-to-reach communities and age-inclusive programming. The first learning event focused on ‘gender mainstreaming and beyond’ and the second explored findings and recommendations of the external evaluation. Start is also piloting an AI-powered tool to connect agencies developing proposals with evidence and peers from past projects to help drive continuous improvement.

Key learnings from the programme this year include:

Lesson 1 – The Start Fund Model: Start’s rapid disbursement and locally led implementation remain central to the Fund’s effectiveness. Projects initiated within seven days of activation consistently deliver high-quality, relevant assistance, reinforcing the value of decentralised decision-making and rapid funding.
Lesson 2 – Resources and Prioritisation: 2025 has seen an unprecedented number of alerts raised, with the total now reaching over 1,000. As ODA budgets decline and underfunding of crises becomes more severe - Start will need demonstrate more clearly that resources are being rigorously prioritised and are reaching the most vulnerable and marginalised populations in the countries most in need.
Recommendation 1: Start should further strengthen and clearly communicate its prioritisation criteria and processes, ensuring that resource allocation is transparent, evidence-based, and focused on the most vulnerable and under-served communities.
Lesson 3 – Localisation: Localisation is at the heart of Start’s delivery model, but there is further to go to genuinely localise responses and to bring more power and decision making to local communities. Growing competition among NGOs for limited funding could also undermine progress in directing an increasing share of funding to LNNGOs.
Overall, START has strengthened its evidence base and learning this year, embedding impact monitoring and including recommendations from evaluations into its programming. The year ahead will require Start to consolidate its post-distribution and impact monitoring, embed evaluation recommendations, and scale up its innovative tools to build on and improve its operational practice. The current phase of FCDO’s support to the Start Fund through this programme will conclude in March 2026, and learning from the full life of the programme will be captured in the Programme Completion Report in June 2026

Date of last narrative financial report	10/06/2025	Date of last audited annual statement	24/05/2025