## Annual Review Template

Title: Nutrition Action for Systemic Change (NASC)
Programme Value £ (full life): 9,700,000		Review date: 27/06/2025
Programme Code: 301076	AMP start date: 25/10/2023	AMP end date: 28/06/2030

Summary of Programme Performance
Year	23/24	24/25
Overall Output Score	A	A+
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Logframe

A. SUMMARY AND OVERVIEW

Description of programme

The Nutrition Action for Systemic Change (NASC) Programme is a 7-year (2023-2030), £9.7 million programme which contributes to preventing and reducing malnutrition in all its forms with a particular focus on tackling undernutrition and improving diets of women, girls and children. The primary objective of NASC is to increase access for poor households, particularly women, girls, and young children, to sustainable and climate-resilient nutrition services and healthy diets, ultimately contributing to reductions in all forms of malnutrition. NASC focuses on three core strategies: (1) holding the food industry accountable for its nutrition-related practices and promoting reform through engagement with policymakers, investors, and civil society; (2) supporting global accountability through the Global Nutrition Report to ensure the international nutrition community delivers on its commitments and is guided by evidence; and (3) providing technical assistance to FCDO programme teams to integrate nutrition across sectors and implement policies that strengthen health, food, and related systems, with a focus on women, girls, and children. The programme intends to focus on supporting governments and multilateral organisations following the initial years of the programme.

NASC helps deliver the Foreign Secretary’s priorities on development, health, and climate and contributes to human development necessary for growth. For every $1 invested in nutrition, the expected return is $23 (World Bank 2024). Tackling malnutrition is a complex challenge that requires integrated action across sectors such as health, agriculture, education, WASH, and social protection. NASC’s approach reflects this complexity, ensuring that nutrition is embedded within broader systems and aligned with cross-cutting priorities including gender equity, climate resilience, and sustainability.

NASC Partners
The programme is made up of three components and combines technical assistance (TA) with diplomatic and policy campaigns to strengthen the efforts of governments, private sector, civil society, and international partners, to address systemic barriers on nutrition, in particular barriers faced by women, girls and children in low-income households. The programme supports ATNi (Access to Nutrition initiative) and the Global Nutrition Report (GNR). Both mechanisms are central to shared accountability and a means to share evidence from the implementation of commitments. ATNi also drives forward private sector actions in nutrition and improves private sector nutrition financing. The third component is a TA Facility, managed by DAI Global UK and provides support to FCDO teams, governments, and multilateral organisations, with a particular focus on supporting teams to integrate nutrition objectives or interventions throughout their work in different sectors such as health, agriculture, climate, social protection, economic development, and so on.

Summary supporting narrative for the overall score in this review
This review covers the second year of implementation of the NASC programme from 28 June 2024 to 27 June 2025. The programme is achieving expectations overall, with an output score of A+. Despite a challenging external environment, including a significant reduction in global Official Development Assistance (ODA), the programme has maintained strong delivery across all three components. The TA Facility exceeded expectations, delivering high-quality support to 24 programmes and initiatives across eight FCDO country offices and nine commercial agriculture programmes, with strong results on nutrition integration, gender equity, and climate relevance. GNR performed well on stakeholder engagement and visibility at the 2025 N4G Summit, and ATNi demonstrated strong influence on private sector accountability and investor engagement. Although one deliverable was delayed (Output 3.1), timely mitigation measures effectively minimised the overall impact. Both ATNi and GNR have made progress in diversifying their funding bases, though financial uncertainty remains due to the temporary pause in FCDO funding.

In addition, the Nutrition Programme Team, working closely with NASC partners, delivered a major policy initiative by launching the Global Compact for Nutrition Integration at N4G Paris. The Compact has so far been endorsed by more than 80 governments and organisations.

The programme has responded well to recommendations from the previous review, including finalising the TA logical framework (logframe), refining indicators, and strengthening monitoring and learning systems. Overall, NASC continues to represent good value for money (VfM) and remains well-positioned to deliver on the UK’s international nutrition commitments, assuming that anticipated funding is available following the 2025 Spending Review.

Major lessons and recommendations for the year ahead

Across the NASC programme, several key lessons have emerged over this review period. The past year has underscored the importance of maintaining flexibility and financial resilience across all components of the NASC programme. The UK general election and subsequent change in government brought shifts in development priorities, while reductions to the Official Development Assistance (ODA) budget created uncertainty and funding gaps. These external factors directly impacted the delivery of technical assistance under DAI and created financial pressures for GNR and ATNi. The ability to adapt to evolving political and funding landscapes, by maintaining flexibility, diversifying funding sources, and planning for transitions, has proven essential to sustaining momentum and minimising disruption in a changing global environment.

Another lesson has been the importance of tailoring technical assistance to local contexts and aligning support with critical points in programme cycles, particularly the design stage. For the TA Facility, while stakeholder engagement and capacity building have been strong, challenges remain in tracking the long-term impact of technical assistance, particularly in light of shifting priorities and limited feedback mechanisms. There is also a growing need to improve the dissemination and uptake of knowledge products across FCDO and partner networks. It is recommended that the NASC programme team, along with the wider Nutrition Policy Team, strengthen efforts to share and promote the application of these products across both internal and external networks.

ATNi’s work highlighted the need for early identification of systemic barriers in the food industry, such as the slow pace of product reformulation and the profitability of less healthy product portfolios. These insights have helped ATNi sharpen its focus on long-term, systemic change and the importance of robust, standardised data to support accountability. Another lesson this year has been the importance of adaptive, trust-based engagement, particularly in complex markets such as East Africa, where flexibility and sustained dialogue are essential to building partnerships and overcoming resistance.

GNR’s visibility at global events like the 2025 N4G Summit enhanced its influence, reinforcing its role as a key accountability mechanism in the nutrition space. However, delays in publishing its progress report on 2021 commitments, though mitigated, limited its advocacy impact in the lead up to the Summit. This highlighted the need to strengthen strategic partnerships to amplify GNR’s voice, extend its reach, and facilitate more timely engagement with key stakeholders in order to align its outputs with global policy moments, sustaining its effectiveness.

In the year ahead, NASC is well-placed to support the delivery of the Global Compact on Nutrition Integration, launched by Baroness Chapman at the 2025 N4G Summit through its experience delivering high-quality technical assistance, fostering multisectoral collaboration, and generating actionable knowledge products. NASC can support Compact members through targeted TA and funding to the Scaling Up Nutrition (SUN) Movement Secretariat to support their outreach to governments in the global south and the implementation of the Compact, coordinating efforts among signatories to translate commitments into strategies and investments. This aligns closely with NASC’s Theory of Change, which emphasises embedding nutrition across systems, and leveraging accountability mechanisms to hold commitment makers to account.

Recommendations for the year ahead include:
1. FCDO should prioritise strategic engagement and resource mobilisation and strengthen VfM metrics across all components in response to tightening ODA budgets
2. FCDO should focus technical assistance on high-impact, policy-influencing and resource mobilisation opportunities, and support countries in operationalising global nutrition commitments. FCDO should review the geographic focus of NASC’s technical assistance following the 2025 Spending Review.
3. ATNi and GNR should diversify their funding sources by engaging non-traditional donors, including philanthropic and private sector partners.
4. GNR should strengthen partnerships and alignment of key outputs to maximise advocacy and influence.
5. NASC should fund the SUN Movement Secretariat (SMS) to coordinate and support SUN countries (which make up the largest share of Compact members to date) on the implementation of the Global Compact on Nutrition Integration.

Follow Up to Recommendations from 2024 Annual Review

Owner	Programme Management Recommendations 2024	Progress
DAI and FCDO	Finalise the TA Facility logframe and agree milestones for all indicators by 31 Dec 2024.	Completed. Milestones for all output indicators have been agreed until 2030. Continued attention is needed to ensure outcome-level progress is measurable.
ATNi	Extend NASC support post-FY24/25; continue efforts to secure long-term funding; agree on additional outcome/impact indicators.	Ongoing. NASC secured FCDO funding for ATNi for FY25/26, however this has been temporarily paused due reductions in ODA. Budget for FY25/26 will be confirmed in June 2025. Other sources of funding remain uncertain beyond FY25/26, and diversification efforts are ongoing. ATNi has made progress in refining indicators and tracking influence (e.g. citations, stakeholder engagement).
GNR	Continue fundraising and build strategic partnerships to secure long-term financial sustainability through to 2030 Sustainable Development Goals (SDGs).	Ongoing GNR secured multi-donor funding in 2024. However, a gap in funding remains, impacting the GNR’s ability to deliver its full ambition. Fundraising and partnership-building remain critical priorities.
FCDO	Continue promoting nutrition integration internally and externally, highlighting its value for money and contribution to broader development goals.	Ongoing. NASC has supported integration across multiple sectors and countries. However, further internal advocacy and clearer value for money messaging are needed, especially in light of ODA cuts.
DAI and FCDO	Focus TA on highest-priority countries (e.g. those facing food insecurity), and review country focus post-election to align with new government priorities.	Ongoing. TA has been targeted to countries like Afghanistan, Nigeria, and Ethiopia. A further review of country priorities is expected following the 2025 Spending Review.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Assumptions
- Demand for UK support on nutrition from governments and other organisations – with relevant structures / operations in place that can take forward TA advice
- Relevant FCDO policy engagement and programmes in place, with adequate staff resources to receive, make use of and oversee TA support
- Other donors also support global governance and accountability mechanisms
- Political, economic, climate, environmental or public health emergencies do not divert attention and/or resources
- UK domestic agenda remains supportive of FCDO’s work on nutrition
- TA Facility able to access right expertise to address key knowledge and evidence gaps
- Investors, civil society and consumers want to take action on nutrition

The Theory of Change (ToC) underpinning the NASC programme remains valid and continues to guide its implementation. It stipulates that by supporting governments, businesses, civil society, and other partners to prioritise nutrition, enhance their capacity, and strengthen accountability mechanisms, there will be increased public and private investment in nutrition, improved policies, and better integration of nutrition across sectors. These changes are expected to lead to improved access to nutrition services and to nutritious, sustainable diets, ultimately contributing to reductions in malnutrition, particularly among mothers and children. Since the programme’s inception in June 2023, there have been no changes to the nature of NASC’s intended outcomes or impact. However, unprecedented ODA reductions and increased number of humanitarian crises pose a risk to meeting the levels of impact anticipated.

The ToC is built on a robust evidence base demonstrating that technical assistance (TA) can effectively strengthen the capacity of governments, businesses, civil society, and other stakeholders to develop and implement nutrition-sensitive policies, mobilise financing, and direct investments toward systemic change. By enhancing the ability of these actors to integrate nutrition into their work and by reinforcing accountability mechanisms, the programme aims to increase public and private investment in nutrition, improve policy environments, and embed nutrition more deeply across sectors.

The ToC assumes that FCDO teams, both centrally and in-country, as well as other TA recipients, will continue to have sufficient demand and resources to act on the support provided. It also relies on a favourable enabling environment that allows stakeholders to translate enhanced capacity and evidence into meaningful policy and investment decisions. Knowledge generated through the programme is expected to influence a broader set of actors, including donors and private sector partners, by shaping how they engage with governments and businesses on nutrition.

FCDO’s support to global accountability mechanisms such as the GNR and ATNi serves as an additional lever to incentivise action. These platforms publicly assess and report on the performance of governments and businesses, enabling civil society, consumers, and investors to advocate for change. Their effectiveness depends on the credibility of their findings and the willingness of stakeholders to engage in accountability processes. While their influence is constrained by broader political and market dynamics, past experience shows that sustained engagement can yield meaningful shifts in behaviour and policy.

NASC actively engages a diverse range of stakeholders, including FCDO country teams, national governments, civil society, private sector actors, and global institutions, to ensure that its technical assistance and accountability mechanisms are relevant, responsive, and impactful. This engagement is central to the programme’s ToC and is used strategically to co-create solutions, build ownership, and drive systemic change. For example, we worked closely with the SUN Movement which played a critical role in supporting the FCDO and mobilising support for the Global Compact on Nutrition Integration ahead of the 2025 N4G Summit. By coordinating across SUN countries and engaging national governments, SUN helped secure widespread endorsement of the Compact, reinforcing the programme’s aim to embed nutrition across systems and drive collective action.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The NASC programme is on track to contribute to its expected outcomes and long-term impact. The programme has delivered strong performance across all three components, TA Facility, GNR, and ATNi, with outputs aligning well to the intended pathways of change. The TA Facility has exceeded expectations, supporting 24 programmes and initiatives across eight FCDO country offices and contributing to improved nutrition integration, particularly for women, girls, and children. GNR has maintained its role as a trusted accountability mechanism, supporting commitment tracking and visibility at the N4G Summit, while ATNi has strengthened private sector accountability and actions, and investor engagement. Although the programme is still in its early stages, with just under two years of implementation, the evidence to date suggests that NASC is laying a strong foundation for systemic change. Continued progress will depend on sustained demand, uptake of recommendations, and the ability to adapt to evolving priorities and funding constraints.

Over the next year and subject to funding allocations following the 2025 Spending Review, the programme will continue to deliver impact through its three core components: technical assistance (TA), support to the GNR, and funding to ATNi. In addition to these components, this annual review recommends that NASC provides funding to SMS to support their outreach to governments in the Global South, where FCDO has more limited direct engagement, and in operationalising the Global Compact on Nutrition Integration.

The TA Facility will prioritise support to Compact members, including deep dives in selected countries and tailored support to help governments translate their new N4G 2025 commitments into actionable, cross-sectoral strategies and investments. In response to high demand from countries, the programme will also co-develop a series of webinars to share practical experiences on nutrition integration, with a focus on resource mobilisation and accessing global financing mechanisms such as climate funds. Internally, TA will continue to strengthen FCDO’s own nutrition integration efforts. GNR will focus on finalising and publishing the N4G 2025 commitment tracking report and will draft the thematic Global Nutrition Report, which this year will centre on food systems to promote healthier diets.

In 2025, ATNi will introduce several strategic initiatives aimed at transforming global and local food systems. These include the launch of the VitaMin Index, an assessment of global premix suppliers that evaluates the quality, availability, and accountability of vitamin and mineral premixes used in staple food fortification. This Index will be accompanied by in-depth case studies from India and Kenya to highlight regional practices and challenges. ATNi will also roll out a Global Retail Assessment to evaluate how major retailers contribute to healthier food environments through product offerings, pricing strategies, and in-store marketing. In Kenya, ATNi will initiate complementary foods assessments to support the local production of nutritious foods for infants and young children, aiming to strengthen domestic food systems and reduce reliance on imports. Concurrently, ATNi will enhance its Investor Platform by integrating standardised nutrition metrics, enabling institutional and impact investors to better assess and influence corporate performance on nutrition. Looking ahead, ATNi is also adding in AI applications, and plans to launch an AI-enabled Nutrition Portal to provide deeper insights into healthier and more sustainable food markets.

The NASC programme is an important part of FCDO’s Global Health Centre of Expertise. The CoE supports a multi-sectoral approach to ending preventable maternal, child, and newborn deaths, and NASC plays a key role in delivering the Centre’s role as a hub for health, nutrition, WASH, and climate expertise across the FCDO network.

During this review period, NASC intended to transfer from the Expert Advisory Call Down Service 2 (EACDS2) to the Global Development Delivery (GDD) framework, however, this was postponed to avoid a gap in service provision whilst we waited for the outcome of the 2025 Spending Review. The TA Facility contract under EACDS2 will expire in February 2026. NASC will likely change TA providers, moving to the GDD framework, which will allow greater flexibility to provide support to civil society, multilateral organisations and governments and to support longer term TA assignments. Ideally, NASC would aim to have a short overlap period of the two frameworks to factor in time to hand over ongoing work under the TA Facility and to minimise disruption. However, this may prove difficult as the procurement process will start until after the 2025 summer Spending Review complete.

The external context for the NASC programme remains complex and continues to pose risks to the achievement of its objectives. Global drivers of malnutrition, including the ongoing conflicts in Ukraine and Gaza, the worsening global food security crisis, the unprecedented reductions of ODA spend from donors across the globe, and the remaining effects of COVID-19, have intensified the need for coordinated, multisectoral nutrition action. Domestically, the UK Government’s recent decision to reduce Official Development Assistance (ODA) from 0.5% to 0.3% of GNI has meant a pause in funding to ATNi and GNR as their Accountable Grant Agreement (AGA) extensions had not been signed at the time of the announcement. This may affect delivery timelines and outputs in the short term. The outcome of the 2025 spending review will likely require further adjustments to programme budgets and timeframes.

The planned mid-term review, originally scheduled for early 2025, did not take place. Approval was granted to postpone the review due to the timing of government spending reviews and associated budget uncertainties. A revised timeline for the review will be considered once there is greater clarity on future budgets and programme direction. The review will assess progress to date, identify successes and challenges, and inform decisions on the programme’s future direction, including the potential for a cost-extension beyond FY25/26.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the evidence provided in this review, including the achieved outputs and the programme’s demonstrated VfM, there is sufficient evidence to justify the continuation of the NASC programme. The programme has achieved its targets across all key indicators, delivering high-quality technical assistance, influencing both national and global stakeholders. It has maintained a strong focus on equity, climate resilience, and sustainability, aligning well with new UK government priorities and international commitments. The programme remains central to delivering the UK’s commitment to integrate nutrition objectives across its development portfolio, and supports the integration of the OECD-DAC Nutrition Policy Marker into FCDO systems. The Ministerial Launch of the Global Compact for Nutrition Integration at N4G in March 2025 further signalled the UK government’s commitment to these goals and reinforced the relevance of NASC’s work in advancing nutrition integration. It also contributes to broader UK priorities on women and girls, climate, humanitarian and global health, and aligns with ICAI’s recommendation to monitor nutrition outcomes in commercial agriculture programmes. Despite a constrained funding environment, NASC continues to represent good value for money by leveraging partnerships, embedding nutrition across sectors, and supporting systemic change. Continued implementation will ensure that the programme sustains its momentum and delivers long-term impact.

## C. DETAILED OUTPUT SCORING

Output Title	FCDO, governments and other organisations have increased capacity and evidence to take action on nutrition across different sectors, including in policy and investments
Output number:		1	Output Score:	A+
Impact weighting (%):		35	Weighting revised since last AR?	Yes. This output was not weighted in last year’s AR as most of the review period was spent completing a procurement exercise.

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of FCDO posts, governments and global stakeholders with increased capacity to invest in nutrition, integrate nutrition across other sectors, and put in place and implement policies to strengthen health, food and other systems for nutrition, including for women, girls and children.	30	Exceeded: / 40 FCDO advisers, Senior Responsible Owners (SROs), Programme Responsible Officers (PROs), and representatives from governments and other organisations who have received TA improve competence to integrate nutrition.
1.2 Number of FCDO posts / policies and programmes that integrate nutrition and promote and support government, business and civil society action on nutrition outcomes for low-income groups, in particular women, girls and children.	15 programmes/ initiatives/ organisations that have received TA and improved their nutrition integration as a result / 65% programmes/initiatives where TA was provided that resulted in an improved focus on the nutrition needs of women, girls, and children	Substantially Exceeded: / 24 programmes received TA and improved their nutrition integration. / 100% programmes/initiatives where TA was provided resulted in an improved focus on the nutrition needs of women, girls, and children
1.3 Number of new global knowledge and evidence products about investing in and integrating nutrition across multiple sectors produced, disseminated, and integrated into FCDO's policy and programmatic work	6	Substantially Exceeded: / 12 new nutrition knowledge and evidence products used by FCDO. See Annex I for the list of products.

Briefly describe the output’s activities and provide supporting narrative for the score.

The NASC Technical Assistance (TA) Facility, launched in December 2023, provides TA and capacity development on nutrition and food systems to the FCDO and its partners. This output has exceeded expectations in the programme’s second year. The Facility is implemented by a consortium led by DAI Global UK, in collaboration with NutritionWorks, Options, and the Natural Resources Institute. Development Initiatives was a consortium partner until October 2024, after which they ceased operations. NASC’s initial contract ran from December 2023 to December 2024, with a second contract currently in place from February 2025 to February 2026. A longer-term follow-on contract is anticipated through the GDD framework, pending the outcome of the 2025 Spending Review.
The Facility supports the design and delivery of FCDO programming and policy, contributing to the UK’s international nutrition commitments and broader objectives around food and health system integration, as well as responses to food and nutrition crises. While support to date has focused on FCDO’s central and country teams, the longer-term aim is to extend assistance to low-middle income country (LMIC) governments and other stakeholders, including multilaterals, development finance institutions, and global platforms.
Between June 2024 and May 2025, the NASC TA Facility provided high-quality support to 24 programmes and initiatives across eight FCDO country offices in Afghanistan, DRC, Ethiopia, Nigeria, Sierra Leone, Somalia, South Sudan, and Zambia as well as to nine commercial agriculture programmes. A total of 40 deliverables were submitted during this review period, with demonstrable improvements in nutrition integration, particularly for women, girls, and children. The TA was highly relevant to FCDO’s strategic priorities, supporting delivery of the UK’s 2021 N4G commitments and responding to recommendations from the Independent Commission for Aid Impact (ICAI) review on UK aid to agriculture. NASC’s work also aligned with FCDO’s broader objectives on ending preventable deaths and promoting climate-resilient nutrition systems.
Assignments include:
Running the 2024 and 2025 feedback survey for FCDO’s partnership with UNICEF on child wasting in 10 countries, capturing perceptions of stakeholders addressing child wasting to improve nutrition programming.
- Supporting the FCDO Afghanistan Office to better understand and navigate the nutrition data landscape, to promote data availability and accuracy to improve decision making and programming. NASC TA also supported FCDO Afghanistan develop a nutrition framework to strengthen impact across their portfolio and a third assignment is currently underway to help assess the impact of restrictions on women and girls, reviewing post-2021 funding, and advising on the strategic use of FCDO funds from 2025 onwards.
- Supporting FCDO ODA transparency and accountability through analysis of nutrition spend and programme alignment with the OECD-DAC nutrition policy marker (NPM)
- Supporting FCDO Ethiopia to deepen their understanding of how the evolving aid landscape for nutrition, food security, health, WASH, and social protection addresses the nutrition related needs and helping identify and prioritise FCDO nutrition investments in Ethiopia
- Developing a Strategy on Resource Mobilisation for the Nutrition Technical Team (NTT) in Nigeria
Carrying out analysis to support FCDO in integrating nutrition across its ODA portfolio, in line with the UK’s 2021 Nutrition for Growth commitments and the ICAI review on ‘UK aid to agriculture in a time of climate change’.
Development of a Framing Paper on nutrition integration into primary health care, to summarise the evidence and support internal and external advocacy on health integration.
- Support to FCDO Zambia to carry out an independent review of the office’s approach to nutrition and to inform future strategy and programming.
- Support to the Food and Agriculture Organisation (FAO) in developing an action plan to improve nutrition integration and strengthen the nutrition-sensitivity of FAO’s work.
- Produced operational guidance for FCDO Advisers to support the implementation of WHO’s guidelines on the prevention and treatment of Child Wasting.
DAI have made strong progress in strengthening nutrition integration across FCDO’s ODA portfolio. Despite ongoing challenges such as limited FCDO capacity and budget uncertainties, DAI demonstrated adaptability, responsiveness, and a strong commitment to learning and impact. The programme exceeded expectations across all three output indicators, delivering tailored technical assistance (TA), generating high-quality evidence, and embedding gender equity and climate considerations throughout its work.

All supported programmes demonstrated improved focus on women and girls, and 50% addressed the links between nutrition and climate. The 12 knowledge products (see list in table 1 below) developed surpassed the milestone target of six, with all incorporating gender, equity, and social inclusion (GESI) considerations and 83% addressing climate relevance. Sustainability was embedded in 75% of assignments, and follow-up mechanisms were established to track the uptake and impact of TA recommendations. NASC also implemented a revised client feedback process and produced learning briefs on monitoring, evaluation, and learning (MEL) and capacity building. The results of these knowledge products are shaping future TA, guiding decision-making and response planning, and informing dissemination strategies, such as upcoming webinars targeting members of the Global Compact on Nutrition Integration.

Work is currently underway to provide support to FCDO nutrition team and the SUN Secretariat to take forward the Compact and Coalition on Nutrition Integration, a key post-N4G priority for the FCDO. The Compact currently has 86 signatories comprising governments and organisations who commit to better integrate nutrition interventions and investments across their policies and programmes.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The output has not changed over the past year. The indicators were defined as part of the original logframe. Milestones and targets were established for this output through a TA logframe workshop which was attended by FCDO’s NASC programme team and DAI.

This output was not assigned an impact weighting last year, as only five months had passed between the contract signing and the drafting of the annual review, and therefore, an insufficient period to assess DAI’s performance against the agreed indicators. This year, Output 1 has been assigned a weighting of 35%, based on its proportional share of the programme’s overall financial allocation during the review period.

There was a break between contract between December 2024 and February 2025 and there were no live assignments during this time. The gap had minimal impact on the delivery of the programme and the TA outputs. The rollout of the CWIP feedback mechanism survey and the support to the Nigerian NTT were slightly delayed due to this gap but deliverables have not been affected.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

In response to last year’s Annual Review recommendations, DAI continued to strengthen NASC’s TA work on the nutrition integration agenda and focus on the highest priority countries, by engaging with eight FCDO country offices, in Afghanistan, DRC, Ethiopia, Nigeria, Sierra Leone, Somalia, South Sudan, and Zambia, to support multisectoral nutrition integration and with nine programmes in the commercial agriculture portfolio, supporting FCDO’s response to the International Commission on Aid Impact (ICAI) review of UK aid to agriculture in a time of climate change. NASC TA produced guidance on enhancing nutrition integration to programme teams, strengthening impact, and identifying relevant nutrition indicators to track progress. Next steps will depend on available resources and staff engagement. The TA team is continuing to follow up with programme teams to assess how these recommendations have influenced nutrition integration. Key lessons from working with FCDO Posts were captured in the Nutrition Integration MEL and Capacity-Building briefs.

Over the past year, the NASC TA Facility has highlighted that integrating nutrition into development efforts is most effective when tailored to local contexts and aligned with key stages of programme design and review. While technical assistance has been well-received, tracking its long-term impact remains a challenge due to limited feedback and shifting priorities. Capacity gaps persist among FCDO staff and partners, particularly in areas like nutrition indicators and policy integration, highlighting the need for ongoing training and support. Cultivating strong relationships through regular and timely engagement with stakeholders has proven essential for ensuring relevance and uptake of recommendations. Although climate-nutrition linkages are increasingly recognised, more structured efforts are needed to mainstream them and access climate finance. Knowledge products developed by NASC have been valuable, but their dissemination by the FCDO Nutrition Policy Team could be improved to reach wider audiences.

Recommendations for the year ahead:
1. DAI should continue to assist FCDO in operationalising the Global Compact for Nutrition Integration, launched at the 2025 Paris N4G Summit. This includes supporting countries in translating global commitments into national strategies and action plans.
2. DAI should reinforce its focus on climate-nutrition integration by supporting selected governments to access climate finance for nutrition. This includes supporting countries like Madagascar and Bangladesh to integrate nutrition into climate policy and access climate funds, providing models for other countries to adapt.
3. In light of current funding constraints, FCDO and DAI should prioritise TA where it can most influence programme investments or policy, especially during key planning or review phases. Focus should be on high-impact sectors and countries with strong demand and alignment to FCDO goals. As part of this, DAI should set out a forward-looking plan that identifies upcoming opportunities to influence investment plans across countries, enabling a more strategic deployment of TA where it can have the greatest impact.
4. Future assignments should continue to incorporate sustainability mechanisms, ensuring that technical assistance leads to long-term change. This could include securing written commitments or action plans from government or organisation counterparts to take forward TA recommendations and identifying local champions to lead follow-up, for example, SUN focal points.

Output Title	Accountability of the food industry has increased at global levels and in LMICs, in particular regarding their impact on the diets of poor women and children
Output number:		2	Output Score:	A+
Impact weighting (%):		35	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of businesses being held to account for their practices on nutrition.	46 unique companies (Cumulative between 2024 and 2025: 85)	Substantially Exceeded: / 81 (121 cumulative) multinational and national unique companies assessed across all products (Global Index, Breastmilk Substitutes (BMS), Spotlight Indexes).
2.2 Number of policymakers, civil society organisations (CSOs) and consumer associations drawing on ATNI findings to promote change in food industry practices.	224 policymakers, CSOs and consumer associations drawing on ATNI findings to promote change in food industry practices.	Substantially Exceeded: 450 / 420 investors, CSOs, governments and business platforms engaged with ATNI to inform their decisions and actions / 8 ODA country governments engaged in ATNI’s outreach events / 22 Number of collaborative engagement and investor actions targeting index companies
2.3 Number of accountability products, tools and assessments available at global and country level.	13	Exceeded: 17 / 14 publications (including Global Index, BMS, Spotlight Indexes etc) / 3 pieces of action research / policy briefs

Briefly describe the output’s activities and provide supporting narrative for the score.

ATNi has made significant progress in advancing private sector accountability and actions for nutrition, particularly in LMICs. Through a range of initiatives, the organisation has strengthened its influence on food industry practices and policy environments. One of the key achievements in this reporting period was the continued rollout and engagement around the Global Access to Nutrition Index. Following its launch in late 2024, ATNi held one-on-one meetings with 15 of the 30 assessed companies to discuss their results, clarify methodologies, and encourage improvements. These engagements have already led to internal reviews and early signs of change within several companies. Complementing this, ATNi launched a comprehensive Retail Assessment across six countries, examining how modern food retailers influence diet quality through pricing, private label strategies, and policy environments.

On the policy front, ATNi played a central role in launching the Paris Declaration on Business & Nutrition 2030 during the N4G Summit. This declaration, developed through extensive stakeholder consultation, sets a roadmap for private sector engagement in nutrition through to 2030. At the GNR’s request, they supported France to screen N4G commitments for eligibility. ATNi also co-hosted a regional policy dialogue in East Africa with the African Population and Health Research Centre (APHRC) and the Kenyan Ministry of Health. The event brought together 68 stakeholders from across the region and resulted in a roadmap for healthier food environments. These efforts demonstrate ATNi’s growing influence among policymakers, civil society organisations, and consumer associations. ATNI has also exceeded its target for 224 actors and organisations to draw on ATNi’s, promoting change in food industry practices.

ATNi’s commitment to transparency and data accessibility was further demonstrated through the finalisation of its Data as a Public Good Strategy. This included the launch of a beta version of the Product Profile Dashboard, which visualises trends in the healthiness of food portfolios over time. ATNi also began piloting the PRIME (Preventable Risk Integrated ModEl) model to estimate the health impacts of dietary changes, using its own data on carbonated drinks and savoury snacks in the U.S. These tools are designed to support investors, governments, and civil society in holding companies accountable and driving systemic change.

Investor engagement remains a cornerstone of ATNi’s strategy. In Q1 2025, the organisation mobilised seven institutional investors, representing $1.2 trillion in assets under management, to make new N4G commitments. These investors pledged to use recognised nutrient profiling models in their engagement with food companies and to advocate for greater transparency in reporting healthy versus unhealthy sales. Additionally, three investors signed the Global Compact on Nutrition Integration, reinforcing ATNi’s role in influencing institutional investors to consider nutrition and health outcomes when making investment decisions in the food and beverage sector. Lastly, ensuring that nutrition is systematically part of investing practice moving forward is critical. Due to ATNi’s work, FTSE Russell, ISS, and S&P Global CSA use ATNi indicators and data in their guidance and frameworks to companies.

Based on data collected from July 2024 to April 2025, ATNI has performed well against its targets and output indicators agreed with FCDO, exceeding output targets for all indicators. The organisation’s activities have been both wide-ranging and impactful, spanning corporate engagement, policy influence, data transparency, and investor mobilisation and demonstrate their potential to make an important contribution to achieving NASC’s outcome that the private sector (agri-food businesses and their investors) increases investments in sustainable, nutritious foods that are affordable and accessible to low-income groups, in particular women, girls and children, and shifts away from harmful practices. While challenges such as company resistance in East Africa were encountered, these were effectively mitigated through extended engagement and support from advisory partners, leading to ATNi substantially exceeding its target for indicator 2.1.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The output has not changed over the past year. The milestones were defined as part of the original logframe, agreed with ATNI in October 2023.

ATNI’s logical framework was finalised before the signing of the accountable grant agreement in October 2023. An additional three indicators have been added to ATNi’s project level logframe but this has not impacted NASC’s overarching logframe. The additional indicators are:
Count of requests from policymakers inviting ATNI to share its findings, expertise, or recommendations.
Number of investors using ATNI’s data or analyses, evidenced by public reference to ATNI.
Number of investor resolutions making direct reference to ATNI data.

This year, Output 2 has been assigned a weighting of 35%, reflecting its proportional share of the programme’s overall financial allocation, which is similar to that of Output 1. Last year, Output 2 was assigned a higher weighting of 50%, as Output 1 was not weighted due to insufficient time for performance assessment. As a result, the impact weightings for Outputs 2 and 3 were correspondingly higher.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

ATNi has addressed recommendations from last year’s annual review. Details of progress can be found in the table below.

Progress Against Recommendations from Previous Annual Review

2024 Recommendations	Progress against 2024 recommendations
ATNi and FCDO to agree targets for additional indicators to assess ATNi’s contribution to the programme’s overall outcomes and impact and ensure they complement the overarching logical framework’s goals.	Completed. ATNi agreed target for additional indicators and has strengthened its monitoring, evaluation, and learning (MEL) systems. ATNi tracks the progress of its projects against centralized indicators. The M&E tracking tool covers all projects included in ATNi's portfolio, monitoring performance and progress towards objectives, supporting efficient reporting to donors, and easing the monitoring process by attributing clear roles and responsibilities.
ATNi to continue to invest in securing long-term funding to ensure security and sustainability of activities such as the expansion of assessments into Tanzania and Kenya.	Ongoing. At the December 2024 Board meetings, a fully funded budget for 2025 of €3.7 million was approved. This included £1 million from FCDO, covering FY25/26. However, following the UK Government’s decision to reduce its ODA spend, FCDO and ATNi have had to suspend signing an AGA addendum, which would have released these funds. The NASC programme team has applied for a funding exemption, and the outcome is expected to be announced in June 2025. ATNi continues to prioritise long-term funding through its risk management and board oversight processes, although changes in 2025 funding will impact ATNi’s ability to deliver maximum impact.
ATNi to reflect on their approach to win early signatories of the CEO Compact on Healthy and Sustainable Diets. ATNi should continue to engage and target CEOs to join the Compact in order to achieve the greatest impact and further strengthen collaboration.	Completed. ATNi had planned to launch the CEO Compact at the 79th UN General Assembly in September 2024,aiming to secure five company commitments ahead of the event. However, reviewed their approach to focus on the N4G Summit and build a stronger base of signatories, the launch was rescheduled for March 2025. To maximise impact, ATNi focused on issuing an Open Letter to Industry Leaders in September 2024, which was endorsed by 19 prominent individuals and institutions. In addition, the remaining elements of the CEO Compact became the Paris Declaration on Business & Nutrition 2030 which was successfully launched at N4G in Paris in March 2025.

Key lessons have been identified during the review period. Early identification of challenges in the food industry is key. Insight into the slow pace of product reformulation and limited adoption of healthier product standards enabled ATNi to refocus on systemic change and long-term impact. Another key takeaway was the importance of standardised, transparent product data, provided by the companies themselves, to support meaningful comparisons between products and producers and enhance accountability. The Materiality of Nutrition assessment also revealed that while healthier product portfolios can be profitable, companies with less healthy offerings often have higher profit margins, highlighting the need for stronger regulatory incentives and regulatory frameworks.

This review period also highlighted the importance of trust and flexibility in stakeholder engagement, particularly in contexts such as East Africa, where company resistance resulted in the need for extended timelines and deeper dialogue and consultation with those companies. Additionally, the pilot use of artificial intelligence in research showed promise for improving efficiency, but underscored the need for ethical oversight and human validation. These lessons should inform ATNi’s 2025 strategy, emphasising the value of adaptive engagement, robust data systems, and responsible innovation to drive meaningful progress in global nutrition.

Recommendations for the year ahead:
- In light of reduced ODA budgets globally, ATNi should prioritise diversifying its funding base. This includes expanding engagement with philanthropic foundations, private sector partners, and multilateral institutions to secure both core and project-based funding beyond 2026.
- Continue to build on momentum from the N4G Summit by deepening collaboration with institutional investors. Focus on embedding nutrition metrics into Environment, Social, and Governance (ESG) frameworks and leveraging investor influence to drive corporate accountability.
- To sustain and scale impact in LMICs, ATNi should strengthen partnerships and knowledge transfer with government, regional institutions and local civil society organisations. This will support more context-specific assessments and advocacy, particularly in East Africa and South Asia.

Output Title	The global nutrition community is being held to account effectively for their commitments on nutrition.
Output number:		3	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of stakeholders registering, reporting and making progress on commitments in the NAF	N4G Statement Annex produced / Commitment registration guidance, including how to develop commitments with dimensions of equity, published / Report on progress against N4G 2021 commitments published	Achieved: / N4G Statement Annex produced / Commitment registration guidance published. / The report on progress against N4G 2021 commitments published and presented at a webinar on 20 May 2025 (publication was delayed)
3.2 Number of CSOs and others drawing on GNR data to promote change	Nutrition for Growth (N4G) references GNR's Nutrition Accountability Framework (NAF) and/or resources / [GNR Target by June 2026 is 5,000 unique page views of NAF tracking data and progress reporting]	Achieved: / The NAF and other GNR reference were referenced in both the N4G Commitment Guide and the N4G Statement Annex published by the French Ministry for Europe and Foreign Affairs / President Macron’s N4G speech referenced the GNR as “the platform” and used data provided by GNR. / [16,173 unique page views of NAF tracking data and 1,923 unique page views of resources that support commitment progress reporting, substantially exceeding the 2026 target]
3.3 Number of policy and decision makers drawing from GNR data and knowledge products.	None for this AR. / [GNR Target by June 2026 is 1,000 mentions, formal citations and references to and evidence in GNR publications]	[1,930 mentions, formal citations and references to and evidence in GNR publications in this reporting period, exceeding the 2026 target]

Briefly describe the output’s activities and provide supporting narrative for the score.

Over the year, the GNR has supported commitment registration and progress tracking through the Nutrition Accountability Framework (NAF), produced and disseminated data and tools, and maintained strong engagement with commitment-makers and global stakeholders. It secured new funding (e.g. from the European Commission and BMZ), reduced the 2025 funding gap, and strengthened partnerships with France, SUN, ATNi, and others. GNR was credited by donors and other stakeholders for maintaining high visibility at the N4G Summit and across global fora, reinforcing its role as the leading accountability mechanism for nutrition commitments.

The GNR secured their role as the key accountability mechanism in France’s N4G 2025 Summit process, demonstrating their added value and independent nature. In particular, the GNR has demonstrated strong performance during the first quarter of 2025, effectively delivering on its core objectives in preparation for the Summit and meeting milestones for indicator 3.1. The finalisation of the N4G Statement Annex (compiling and showcasing eligible commitments), updates to the commitment registration process to enhance trackability, supported by a comprehensive Frequently Asked Questions page for clarity and the integration of equity considerations (64% of registered commitments doing so) reflect its dual role of providing trusted policy-relevant evidence on the state of nutrition and supporting accountability to drive greater action to end malnutrition in all forms. GNR’s active engagement with partners and visibility at major events reinforced its role as a trusted accountability mechanism. While one milestone, the GNR report on progress with 2021 N4G commitments was completed late and published after the 2025 N4G Summit (with results being posted online this reporting period, and the report being published soon after), overall GNR is on track and meeting expectations. (with results being posted online this reporting period, and the report being published soon after), overall GNR is on track and meeting expectations.

The GNR’s NAF continued to serve as a central platform for commitment data for use by civil society organisations (CSOs) and decision-makers (indicators 3.2 and 3.3). Various N4G products referenced the GNR and its data, and there was significant use of NAF data as well as mentions of GNR during this period. For commitment-making, weekly data downloads were shared with key Summit partners, including France and ATNi, to facilitate the screening of commitments for the Summit Annex. This collaboration ensured that only eligible commitments were presented in the Annex and on screens around the Summit venue, highlighting the relevance of GNR’s data. As well, the NAF Commitment Tracker was updated with the latest progress assessment data in March, and a report was published and launched on a May webinar to encourage engagement with the data.

The GNR’s efforts to have its data and tools leveraged by CSOs and decision-makers were evident through its active participation in multiple N4G events. These included two webinars co-hosted with the N4G Outreach Group, a technical assistance table at the Civil Society Organisation Pavilion and main Summit (GNR was the only group to “table” at any official N4G events), and several side events, including the GNR-hosted Protecting the Ethos of Accountability in a Changing Environment. These engagements not only supported commitment makers but also strengthened relationships.

In summary, the GNR’s activities during this period reflect progress across its strategic outputs, including the production of the N4G Statement Annex, publication of commitment guidance with equity dimensions, integration of GNR resources into N4G processes, and active dissemination of tools and data through events and online platforms.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to the outputs over the past year. However, the NASC programme team has discussed with the GNR potential adjustments to the GNR-specific outputs to better align with indicators agreed upon by other GNR donors, without compromising the programme’s objectives. These proposed changes will be reviewed after the submission of this annual review to ensure that the most impactful indicators are being measured to demonstrate progress.

This year, Output 3 has been assigned a weighting of 30%, based on its relative share of the programme’s overall financial allocation. In the previous year, Output 3 was assigned a higher weighting of 50%, as Output 1 was not weighted due to insufficient time for assessment. Consequently, Outputs 2 and 3 carried a greater proportion of the overall impact weighting.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress Against Recommendations from Previous Annual Review

2024 Recommendations	Progress against 2024 recommendations
PATH to provide clarifications related to safeguarding in the Due Diligence Assessment (DDA).	Ongoing. The noted action in the DDA was for the GNR Independent Expert Group (IEG) Chair & SG co-Chairs, with PATH support, to provide clarity or clear statement on safeguarding in the Stakeholder Group (SG) terms of reference (TOR). Although work to update the TOR has begun, it is still a work-in-progress given all the changes in membership in the past year. So, this action is still pending, and alternative plans might need to be made to respond to this recommendation if the SG leadership is not in a good place to update the TOR soon.
PATH to continue to invest in fundraising and its strategic partnerships over the next year, to secure additional resources to meet the priorities and ambition of the GNR and nutrition community, and to secure the longer-term financial security for the GNR in the lead up to the 2030 SDGs.	Ongoing. PATH has actively pursued new funding and strengthened strategic partnerships to support the GNR’s sustainability. Over the year, it secured new grants (e.g. from the European Commission and BMZ), engaged with potential donors, and reduced the 2025 funding gap to under $1.1 million. Funding from USAID was not secured following changes in the US administration. It also deepened collaboration with key stakeholders (e.g. SUN, ATNi), co-hosted events, and maintained high visibility at the N4G Summit, demonstrating strong progress in securing resources and influence for the GNR.

Over the course of this review period, key lessons have been identified. Firstly, strong visibility at global events like the N4G Summit boosted GNR’s influence and credibility, demonstrating the crucial role the GNR plays by holding the global community to account for their commitments to nutrition. In addition, having flexibility in timelines and proactive technical support were important for increasing stakeholder participation and improving the quality of commitment reporting. However, while this approach successfully increased participation, it also resulted in the progress report on 2021 N4G commitments being published significantly later than planned, after the N4G Summit. The report would have had greater impact and served as a valuable advocacy tool in the lead up and during the Summit had it been published prior to N4G. To mitigate this, key findings began to be socialised with key stakeholders (such as with the SUN Anglophone Africa Hub and with LMIC and LIC governments) who particularly needed the information as early as November (4 months before the Summit), ensuring the information could be leveraged timely.

Recommendations for the year ahead:

- GNR should proactively engage a broader range of donors, including philanthropic and non-traditional funders, to reduce reliance on government funding (as governments globally are reducing ODA budgets) and fill the funding gap. This includes developing a targeted fundraising strategy aligned with the 2030 SDG timeline.
- To maximise advocacy impact, particularly around key global events such as the N4G Summit, GNR should prioritise strengthening strategic partnerships that can amplify its voice, extend its reach, and facilitate more timely and responsive engagement from stakeholders. Given that the production of key outputs often depends on external data contributions, building trust-based relationships and communication channels with data providers may help reduce delays and improve coordination, even in the absence of formal leverage.
- Building on its strong presence at N4G, GNR should continue to position itself as a leading voice in global nutrition accountability by engaging in high-level policy dialogues such as at the Committee on World Food Security.

## D: VALUE FOR MONEY

Key cost drivers and performance

For Output 1 (the TA Facility), the primary cost drivers are consultant fees and the core team’s costs. These include daily rates for short and long-term experts, as well as management time for coordination, quality assurance, and MEL. The fee rates were centrally negotiated through the Expert Advisory Call Down Services (EACDS) framework, which governs both the 2024/25 and 2025/26 contracts. Rates and staff costs have remained stable throughout the year. To ensure value for money, the NASC programme team reviews proposed project budgets, assessing the number of days, consultant rates, and the scope of work. Additional cost drivers include travel and expenses for in-country missions, stakeholder consultations, workshop delivery, and the development of tools and resources (e.g. guidance notes, training materials, and survey platforms). Where possible, local consultants are engaged, such as in Ethiopia, Nigeria, and Zambia, offering both cost savings and valuable expertise. FCDO also reviews invoices, financial reports, and feedback to inform future TA projects and optimise delivery.

For Outputs 2 and 3 (ATNi and GNR respectively), internal staff costs are the main cost drivers. These include salaries for technical and operational staff, as well as costs associated with research, data analysis, and stakeholder engagement. FCDO has benchmarked these against comparable organisations and found them to be reasonable. Other cost drivers include travel and event participation (e.g. global fora and regional dialogues), communications and advocacy materials, and the production of accountability tools such as the Global Index and Nutrition Accountability Framework. A consistent cost for GNR is website hosting, which is managed through PATH. This arrangement provides access to shared services such as finance, HR, legal, and grant management, contributing to operational efficiency. For ATNi, additional costs include product assessments across multiple markets, investor engagement activities, and the development of data visualisation tools and dashboards.

VfM performance compared to the original VfM proposition in the business case

Economy: Throughout the assessed period, DAI has sought to improve the economy of the TA it delivers by utilising existing expertise and local knowledge. The core team have utilised their own expertise as well as employing locally-based consultants where possible, such as in Afghanistan, Ethiopia, Nigeria, and Zambia. This approach also included re-engaging consultants with prior experience under the TASC project, such as those involved in the Child Wasting Guidance and Accountability Report workstreams. For example, the same consultants contributed to both the 2022 and 2023 Accountability Reports, drawing on their experience with the SDN and NPM methodologies.

The GNR maintains a small core team at PATH. To support resource mobilisation, PATH recruited a part-time intern focused on identifying new funding streams. GNR has also benefited from in-kind support from the IEG and support on screening of private-sector commitments from ATNi. GNR has successfully finalised a contract award with Germany’s BMZ and with the European Union (via Expertise France), with other donors continuing to provide support, Ireland (Irish Aid) and Canada (Global Affairs Canada).

ATNi also operates with a core team, currently comprising of 25 full time staff. Its Audit and Risk Committee meets twice a year to review the independent financial audit as well as the annual budget. This ensures that ATNi remains within budget and delivers good value for money. ATNI has made progress in securing renewed project level funding from Irish Aid, GAIN, and WHO, however, core funding beyond 2026 remains uncertain, with the Gates Foundation currently the only confirmed core donor.

Efficiency: The TA Facility continues to learn from past assignments and apply these lessons learned to new projects. For example, in developing the Training of Trainers (ToT) guide for the Better Lives programme in Somalia, DAI identified existing training materials, such as UNICEF’s Maternal, Infant, and Young Child Nutrition (MIYCN) training package, to fill identified gaps. The TA also developed the UHC framing paper and the updated Child Wasting Guidance which have been utilised for work under the new contract for 25/26. GNR ensures efficiency through maintaining a small team which engages with a broad network of stakeholders to gather inputs and amplify GNR outputs, automating processes when high quality outputs can be assured, and reducing or increasing oversight and management as appropriate for current activities. ATNi demonstrated efficiency through its Global Index which reviewed around 52,000 products from 30 companies in 25 different markets from across the world. Additionally, ATNi have collaborated with GAIN and the Paris Peace Forum (PPF) to deliver the Paris Declaration on Business & Nutrition 2030, a key output of the N4G Private Sector working group.

Effectiveness: The TA Facility has produced several outputs throughout the year that have been actively utilised by both FCDO and external organisations to drive systemic change for nutrition. For example, the Afghanistan NIS findings were shared with US stakeholders who have referred to the recommendations as being useful for nutrition programme planning, whilst through the commercial agriculture EOI, findings, insights, and learnings have been shared with the FCDO’s AgRED team and the Gates Foundation. GNR has proven effective in supporting 179 commitment-makers to prepare and submit commitments for the 2025 N4G, providing tools, guidance, and technical support. ATNi has a strong track record with delivery. Its Global Index launch received widespread media coverage and ATNi continues to work with the private sector to support efforts in improving the healthiness of products. These actions are leading to measurable changes in the healthiness of private sector products. ATNi also took a leading role at N4G, engaging investor groups, coordinating the Paris Declaration, and supporting the GNR in reviewing private sector commitments.

Equity: NASC continues to prioritise equity, particularly for women, girls, and children, across all components. The TA Facility is guided by four cross-cutting principles, including gender, equity, and social inclusion (GESI).  This is monitored in the logframes of each NASC partner. At the start of the project, the core team outline how GESI will be addressed during the assignment, ensuring that those most at risk of malnutrition are deliberately included in the strategy and approach. At a project level, this includes the participation of Afghan women as key informants in all Afghanistan-related assignments and the development of an approach for Northwest Nigeria to identify those most in need based on rates of malnutrition, climate shocks, and locations prone to the impacts of violence.

GNR encourages commitment makers to consider equity when registering a new commitment by asking for the relevant dimensions of equity. GNR also highlighted the importance of considering equity for achieving inclusive and sustainable progress in the commitment progress report on 2021 commitments. The inclusion of a dimension of equity within a commitment (with age or life-course stage/status, socioeconomic status, sex, and income status of the country being most common) provides an additional layer of information when tracking commitment outcomes and understanding underinvestment in certain groups across all commitments.

ATNi has highlighted disparities in product quality and marketing between high and low-income countries, with media coverage reinforcing these findings. Furthermore, ATNi has continued their work on accountability around the marketing of Breast Milk Substitutes (BMS). This contributes to better outcomes for children, as well as building on the success of the BMS index released in March 2024. They have performed on-the-ground assessments in five countries, publishing reports throughout 2024.

Overall Cost-Effectiveness:
All three of NASC’s programmes demonstrate strong cost-effectiveness. At the 2025 N4G Summit, both ATNi and GNR played prominent roles. ATNi led the private sector working group and GNR supported and tracked commitments and participated in multiple working groups. Separate to the Summit, ATNi has also achieved significant success through the launch of its most recent Global Index, the results of which received media attention, including from Reuters and The Guardian. The GNR’s Commitment Progress Report has drawn interest from a range of organisations, particularly civil society, with it being the first report accounting progress on N4G 2021 commitments. NASC’s TA Facility has also demonstrated cost-effectiveness including through advancing the adoption of the Nutrition Policy Marker (NPM) and integrating nutrition objectives across FCDO’s ODA portfolio, two of FCDO’s commitments that were made at the 2021 N4G Summit.

Assessment of whether the programme continues to represent value for money

Based on the assessment above, NASC continues to represent strong value for money, and should be continued. The programme has delivered efficiently across all components by leveraging existing expertise, using local consultants, and applying lessons from previous work. ATNi and GNR have demonstrated strategic value through their roles at the 2025 N4G Summit, while the TA Facility has supported systemic change across FCDO’s portfolio. A strong focus on equity, particularly for women, girls, and children, further reinforces the programme’s relevance and impact.
E: RISK [½ to 1 page]

Overview of risk management

The majority of risks identified in the business case for NASC remain relevant with clear mitigation strategies in place, with risks reviewed on a monthly basis. The overall risk rating for the programme is major. Risks to the programme have changed since the last annual review, with the current fiscal circumstances being a driver for uncertainty relating to both the programme’s strategy and its component delivery. The significant ODA cuts globally will impact overall health and nutrition outcomes and our ability to demonstrate impact. All partners have risk monitoring mechanisms in place and produce updated risk registers in their quarterly reports, as well as providing verbal updates at programme meetings, highlighting updates to current risk ratings, mitigation strategies or emerging risks. The main risks relating to NASC, alongside their mitigation strategies are as follows:

Risk Title	Category	Residual Risk	Mitigation Strategy
Overarching delivery risk to NASC from reduced financial capabilities and shifting development priorities.	Policy and Programme Delivery	Major (Exceeds Appetite)	NASC’s programme was designed with the assumption that it would be possible to secure additional funding following a successful mid-term review to justify a cost extension. The fiscal circumstances have changed since the approval of the business case, with a reduction in ODA spend from 0.5% to 0.3%. With the uncertainty around future priorities and the ongoing Spending Reviews and Finance Strategy Reviews, this means that the outlook for NASC is uncertain, considering the low-level of outer year spend in the business case.
ATNi unable to secure additional funding to deliver core projects.	Policy and Programme Delivery	Major (Exceeds Appetite)	FCDO’s funding through NASC has provided a significant proportion of ATNi’s core funding. ATNi receives project funding from many donors, however, only the Gates Foundation has provided core funding alongside FCDO. Cuts to ODA in North America and Europe have impacted ATNI’s funding prospects. / ATNi currently receives funding from the Gates Foundation, Ireland, GAIN, and CIFF. As part of their own internal mitigation processes, ATNi have scaled back some of their activities until additional funding is secured for 2026 onwards. FCDO is continuing to look at mechanisms to support ATNi, and has submitted a bid to continue funding.
Instances of fraud, corruption, or bribery lead to diversion of funds, undermining of programme impact, and damage to FCDO and partner reputation.	Financial & Fiduciary	Moderate	FCDO due diligence processes ensure partners have the requisite financial systems, processes and capacity in place to mitigate this risk. The project team regularly reviews financial reporting and annual audited statements or equivalent from partners in line with reporting timelines. Incidences of fraud, corruption or bribery will be reported immediately and investigated in line with FCDO procedures.
Host of GNR fails to secure sufficient funding from other donors to remain viable.	Policy and Programme Delivery	Moderate	Discussions took place through the SUN donor network and bilaterally to ensure there was and continues to be sufficient cross-donor support for GNR and to manage gaps in funding cycles. GNR is recognised as a critical part of the global nutrition architecture, including in its role at the 2025 N4G, and informal discussions indicate there is likely to be sufficient donor interest for its ongoing viability. / GNR have secured funding from Global Affairs Canada, BMZ, Irish Aid, and the European Union (via Expertise France). Diversification of its donor base to reduce this risk will also be a key part of the host’s remit e.g. targeting philanthropies. There has been a pause in FCDO’s funding of GNR since April 2025, although an exemption request has been submitted for this financial year. This would be significant for GNR as it is core funding, as opposed to project funding.
Lack of sufficient number of FCDO programmes/capacity at post to make effective use of TA to integrate nutrition.	Strategy & Context	Moderate (Exceeds Appetite)	Demand for expert technical assistance (TA) on nutrition has remained steady from FCDO posts, despite ongoing ODA budget constraints. The Nutrition Policy Team (NPT) continues to receive new TA proposals, although engagement tends to be concentrated among a small group of FCDO staff who have an invested interest in nutrition. Uncertainty around the future of the TA offer has grown in light of ongoing spending reviews and internal strategic finance processes. These challenges are likely to intensify following the reduction of ODA to 0.3% of GNI and increased competition for funding across sectors. To mitigate this risk, the NPT is actively raising awareness of the value of nutrition integration and building capacity across FCDO’s ODA portfolio and policy work. This includes ongoing efforts to support adoption of the Nutrition Policy Marker (NPM). Should internal demand decline, the TA Facility has demonstrated sufficient flexibility to respond to external requests from international and domestic partners, ensuring continued alignment with the programme’s objectives.

Compared to the previous Annual Review, which identified one major risk, NASC now faces two major risks, with several others showing increased residual impact and likelihood. Three risks are currently assessed as outside the programme’s risk appetite: 1) uncertainty around future programme delivery (major), 2) financial instability at ATNi (major), and 3) limited capacity at FCDO posts to effectively utilise TA (moderate). A key driver of these risks is the ongoing fiscal uncertainty, particularly the impact of the ODA reduction to 0.3% of GNI and the pending outcomes of the Spending Review for FY 2025/26 and beyond. This uncertainty not only affects NASC’s own funding but also limits the ability of FCDO teams to plan and commit to TA, as they may need to reprioritise.

Despite these challenges, NASC has made progress in mitigating several risks. The risk related to internal programme management capacity has been addressed through staff recruitment and strengthened capabilities within the Nutrition Team. Improvements have also been made to monitoring and reporting on impact, especially for women, girls, and children have mitigated against strategy risks. The programme has also elevated nutrition on the policy agenda through targeted engagement with parliamentarians and ministers, including at the N4G Summit.

DAI has implemented robust mitigation strategies to manage delivery risks. These include regular monitoring of indicators, quarterly risk reporting, and strong communication protocols, particularly around safeguarding. The use of local consultants and the ability to operate flexibly through hybrid working models have further reduced operational and delivery risks. DAI shares a quarterly risk register with FCDO. DAI’s most recent risk register highlights safeguarding of staff from security threats as the highest residual risk, with mitigation measures in place such as security awareness training and incident response protocols.

PATH, as host of the GNR since May 2023, applies a structured risk management framework to the GNR covering operational, strategic, reputational, and financial risks. The most recently shared risk register included 25 risks, of which 4 risks have become active issues over the past year. Similar to the previous year, one of the main risks to the GNR related to its funding, to be able to fulfil key activities for its overarching strategy. The GNR has managed to secure funding from Ireland, Germany, Canada, and the European Union, however, the current ODA landscape continues to pose risks to long-term financing. To mitigate this, GNR has prioritised core activities and scaled back lower priority outputs where necessary. FCDO will continue to advocate for the GNR, and continues to monitor the GNR’s funding in the NASC risk register.

ATNi identifies and manages risk through monthly internal management meetings, quarterly Board meetings, and biannual meetings of its Audit and Risk Committee. The Committee reviewed the independent financial audit, updated the risk register, and endorsed revised mitigation strategies. ATNi continues to demonstrate transparency and accountability, with any safeguarding or financial concerns reported to donors. In 2024, ATNi formalised a new child safeguarding policy and incorporated relevant provisions into its Code of Conduct, aligning with FCDO priorities. One of ATNi’s most significant risks remains long-term funding stability. While a fully funded 2025 budget of €3.7 million was approved, the organisation continues to face uncertainty due to the broader ODA funding environment, particularly reductions in North America and Europe. To mitigate this, ATNi is actively pursuing new funding sources, refining its reserve policy, and implementing quarterly budget reforecasting. The organisation also maintains a Continuity Reserve, with a target of 30% of annual operating costs, to help manage financial shocks. ATNi will continue to monitor emerging global risks and adjust its timelines, workplans, and forecasts accordingly. FCDO will continue to track ATNi’s financial position through the NASC risk register.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues

NASC programme performance is measured against an overarching logical framework for the programme, and against individual workplans and logical frameworks for each implementing partner. Delivery is reported and monitored through regular monthly or quarterly programmatic meetings, covering work-planning, results, financial and risk management, and quarterly narrative and financial reporting.

The programme’s approved budget is £9.7 million of ODA across seven years, from 2023 to 2030. NASC intends to seek a cost-extension, after the FCDO’s Spending Review and the conclusion of the programme’s mid-term review. Of the initial £9.7 million approved NASC has disbursed over £4.2 million across FY 23/24 and FY 24/25, with a further £1 million committed in a TA contract through to February 2026. NASC is awaiting the result of the ongoing Spending Review to ascertain its budget moving forward.

ATNi received £1.19 million from NASC during FY 24/25. £1 million was disbursed under the existing Accountable Grant Agreement (AGA) signed in October 2023, with an additional £190,000 provided following an addendum to the AGA. ATNi has provided detailed quarterly narrative reports and provided detailed financial reports in line with payment requirements. ATNi met all report submission deadlines. FCDO funding to ATNi’s for FY25/26 remains unconfirmed and is expected to be clarified in June 2025. Without continued FCDO support, ATNi’s financial situation remains uncertain.

The GNR received £525,000 from NASC during FY 24/25, comprising £500,000 under the existing AGA, with a supplementary £25,000 through an AGA amendment. GNR has continued to receive financial support from Irish Aid and Global Affairs Canada and has also secured a new funding agreement with Germany (BMZ). In line with the Spending Review, there has been a pause in FCDO funding since April 2025, and future funding arrangements are under review. Similar to ATNi, this is expected to be clarified in June 2025. FCDO and GNR continue to engage between reporting periods to discuss progress and ensure alignment with other GNR donors, with FCDO also participating in the quarterly GNR donor group meetings.

DAI Global Ltd manages the NASC TA Facility through contracts called down from the central EACDS2 framework. The first contract ran from December 2023 to December 2024, followed by a second contract from February 2025 to February 2026. Both contracts were valued at £1 million. Payments to DAI are made in arrears, with the core team fees split between input based and KPI based. Invoices are received quarterly, with monthly updates to forecasts. While quarterly spend varies due to the phasing of TA projects and the timing of the second contract award, DAI has forecasted these fluctuations accurately. Across Q1-Q3, DAI scored 1702.5 out of 1800 KPIs, a score of almost 95%. The TA provision from DAI ends in February 2026, and the NASC programme team will continue to monitor procurement options, including switching to the Global Development Delivery (GDD) framework, pending the outcome of the Spending Review.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The Annual Review process is led by the SRO and contributed to by the component sub-SROs and programme officer, using inputs from the quarterly and annual reports of ATNi, GNR, and DAI, as well as insights from ongoing engagement throughout the year. As part of this process, the SRO, along with the Head of the FCDO Nutrition Team and the Head of the Human Development Department, attended N4G in Paris. This provided a valuable opportunity to observe ATNi and GNR’s work, offering direct insight into their visibility, influence, and effectiveness in a global forum. The Head of the FCDO Nutrition Team and the Head of the Human Development Department provide internal quality assurance and approval.

FCDO reviews all deliverables produced under the TA Facility managed by DAI to ensure that they meet assignment objectives and contribute to broader programme goals. Regular updates are also provided against portfolio wide outcomes on progress against wider objectives. For ATNI and GNR, monitoring and reporting are carried out in line with the requirements set out in their AGAs. This includes the tracking of project-specific indicators and submitting narrative reports, such as activity updates and stakeholder engagement reports, which are supplemented by annual reports.

DAI reports annually against the indicators agreed with NASC for the TA whilst also meeting with the NASC programme team monthly on progress of the TA offering at a portfolio wide level. DAI have agreed with FCDO touchpoints on each of the TA projects with these having more direct oversight of project delivery, as well as involvement in the approval of pre-agreed milestones and deliverables. This combined approach has supported transparent and collaborative monitoring of TA progress.

The Global Nutrition Report (GNR) reports against a set of indicators agreed with donors, as outlined in its logical framework. These span impact, goal, outcome, and output levels, and include measures of stakeholder engagement with GNR’s evidence and data, serving as an indirect measure of the value and influence of its work, since direct attribution to nutrition outcomes is beyond its scope. At the impact level, GNR also tracks how many commitments achieve positive progress (of those reporting), while recognising these results are not solely attributable to GNR. The donor group, including FCDO, meets quarterly to review financial and activity updates, and GNR provides annual progress reports. While impact-level results cannot be directly linked to GNR alone, they remain valuable for global nutrition accountability.

ATNi tracks its progress against centralised indicators, with the tracking covering all of ATNi’s project portfolio. ATNi has in previous years faced issues with collating data for its logframe at outcome and impact level. ATNi has made progress in addressing this challenge by refining its indicators. The secondary outcome level indicators now focus on publicly stated uptake by a broader range of stakeholders. For the first time, ATNi has tracked separately citations of its work by policy makers or direct requests to share expertise in engaging with the private sector. This aligns with it evolving strategy and TOC where engagement with policy makers is core. At the primary outcome level, 34% of sales from companies assessed in the 2024 Global Index were from healthier products, with 73% of companies showing improvement since 2021, though methodological changes limit direct comparison. Further analysis is planned in 2025.

Evidence

NASC has supported the generation of evidence products that can be used by FCDO and external stakeholders. DAI as providers of TA for NASC as well as ATNi continue to produce research papers and policy briefs, with DAI producing 12 knowledge and evidence products (see Annex I) and ATNi publishing 3 pieces of action research.

NASC continues to support several publicly facing accountability mechanisms with the following all releasing updates in the reviewed period: the FCDO Nutrition Accountability Report (for 2022 spend), the GNR’s Nutrition Accountability Framework (updates include tracking of progress), ATNi’s accountability indexes (including the Global Index), and GNR’s report on commitment progress. These all have helped to foster accountability in the global nutrition community, whether this be through private sector accountability (Global Index), or through government and organisation commitment reporting and monitoring.

With the launch of the Global Compact and Coalition on Nutrition Integration, FCDO recognises the importance of accountability on integration, and the lessons that can be learned through its utilisation of the Scaling-Up Nutrition (SUN) Donor Network (SDN) and Nutrition Policy Marker (NPM) methodologies for nutrition integration. Both methodologies are reported against within the Accounting FCDO’s Progress Against its Nutrition Pledges report, published on the GNR’s website.

Looking forward, NASC remains committed to the completion of its mid-term and endline reviews. The mid-term review timeline has been altered to accommodate changes in future budgets, with this change approved by the Head of the Human Development Department.

Learning

The NASC programme team works in collaboration with DAI to refine their monitoring and learning approach. Following on from each TA assignment, FCDO has agreed with DAI an approach including closing interviews and evaluations of successes and areas for improvement. Learnings from assignments carried out under the 2023 to 2024 contract have been taken forward where applicable to the 2025 to 2026 contract assignments.

GNR and ATNi have demonstrated a strong commitment to continuous learning and adaptation over the past year. GNR refined its data management and stakeholder engagement processes during the Nutrition Accountability Framework (NAF) cycle, incorporating lessons from the 2024 commitment progress tracking to streamline the 2025 registration process. This included simplifying commitment structures, enhancing equity-focused questions, and improving user tools such as instructional videos and FAQs. Similarly, ATNi applied insights from its Delphi study on nutrient profiling models to develop clearer reporting guidelines and improve transparency in product healthiness assessments. Both organisations have used these learnings to strengthen their methodologies, improve stakeholder engagement, and enhance the quality and usability of their outputs.

Lessons learned during this review period can be found in Section B and output specific lessons in Section C.

Annex I: Nutrition knowledge and evidence products produced through NASC TA

	Knowledge or Evidence product (Indicator 1.3)
1	Accounting FCDO’s Progress Against its Nutrition Pledges - 2022
2	Nutrition Accountability Report 2023
3	CWIP Feedback Mechanism Year 3 report
4	CWIP Feedback Mechanism Year 4 report
5	Afghanistan’s summary of findings and recommendations, including a situation analysis and NIS data matrix
6	Framing papers on Nutrition Integration in PHC
7	FAO Action Plan on Nutrition Mainstreaming
8	Updated guidance on Child Wasting
9	NIS Learning Brief
10	MEL brief
11	Food safety and storage publication
12	Animal production publication

Date of last narrative financial report		Date of last audited annual statement