## NASC Logframe Dec25
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
Poor households, in particular women, girls and young children have increased access to sustainable and climate resilient nutrition services as well as sustainable, healthy diets – leading to reductions in all forms of malnutrition. | Number of FCDO NASC supported countries that make progress in increasing access to nutrition services and healthy diets for target groups. | Planned | AFG - very low/very limited; BAN - moderate/ limited; ETH - low/very limited; NIG - low/very limited; SOM - very low/very limited | N/A | N/A | N/A | Improving/positive trends
Achieved
Source - Combined DHS/MICS coverage indicators (nutrition services) with FAO healthy diet affordability data (diets), triangulated through the WHO-UNICEF Tracking Tool. Note: for this indicator, data is for Afghanistan, Bangladesh, Ethiopia, Nigeria, and Somalia.
| Impact Indicator 2 |  | Baseline (2020) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
| Number of FCDO NASC supported countries on track to meet global nutrition targets (6) as per WHA and SDG 2, using GNR reporting. | Planned | 6 - AFG 2/6, BAN 0/6, ETH 1/6, NIG 1/6, SOM 2/6 | N/A | N/A | N/A | 10 targets across 5 countries on course/met and improving trends across focus countries
Achieved
Source - GNR Nutrition Country Profiles. Note: for this indicator, data is for Afghanistan, Bangladesh, Ethiopia, Nigeria, and Somalia.
| Impact Indicator 3 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
| Proportion of children that are stunted in FCDO NASC supported countries. | Planned | 32.04% | Not measured | Not measured | Not measured | <30%
|  | Achieved |  | 32.06%
Source - WHO: Global Health Observatory. Note: for this indicator, data is based on a mean of Afghanistan, Bangladesh, Ethiopia, Nigeria, and Somalia.
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030) | Assumptions
Governments in LICs and LMICs, incl. EPD countries, allocate additional public resources to nutrition interventions and implement policies across multiple sectors to improve nutrition, including through the food system so that nutritious foods are more available, affordable, accessible, and appealing, in particular for low-income groups, women, girls and children, and produced sustainably. | Number of governments making commitments on nutrition as reported in GNR/NAF | Planned | 78 (2021 N4G Tokyo) | N/A | 80 | Not measured | 90 | Commitments made by governments are adhered to, there is government ownership and governments are prepared to be held accountable. Government commitments will lead to financial and policy investments in nutrition. Those who make commitments would be expected to want to make progress towards enabling more nutritious diets through food system strengthening and/or scale up coverage of essential nutrition services through health system integration
|  | Achieved |  | N/A | 80 governments made commitments at N4G 2025
Source - GNR Data: Commitments relating to N4G 2025
| Outcome Indicator 1.2 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
| Number of governments making commitments and making positive progress with implementing them as reported in GNR/NAF | Planned | 63% of commitments show positive progress | N/A | Not measured | 70% of commitments show progress | 75% of commitments show positive progress
|  | Achieved |  | N/A | Commitments finalised in Sep 2025; proportion making positive progress reported from June 2026
Source - GNR Data: Commitments relating to N4G 2025
| Outcome Indicator 1.3 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
| Number of SUN countries to have joined the Global Compact on Nutrition Integration | Planned | 0 | N/A | 30 of 67 countries | 40 of 67 countries | 60 of 67 countries
|  | Achieved |  | N/A | 38 of 67
Source - Indicator SO 1.1.2 SMS
INPUTS (£)
INPUTS (HR)
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030) | Assumptions
The private sector (agri-food businesses, investors) increases investments in sustainable, nutritious foods that are affordable and accessible to low-income groups (women, girls and children) and shifts away from harmful practices. | Proportion of companies assessed by ATNi's Global Index that are improving on either product healthiness or responsible practices | Planned | 0 | N/A | 5% of companies increase their product profile assessment | N/A - pending next Global Index publication | (TBC) 20% of companies increase their product profile assessment | By engaging businesses and holding them to account for their actions, this will result in them adapting their product-base and marketing approaches to facilitate a global food industry that supports and enables access to healthier, affordable, nutritious foods. Through action in HICs, as well as in LICs, this will ensure that businesses change their approach to ensure higher-quality products are sold globally, rather than varying the quality to improve profit. Work by ATNi has shown that businesses are currently selling worse quality products in countries with more relaxed regulation where they are able to. Through change in demand/products that are available, this will shift diets and consumption habits. Greater sustainability may also lead to greater in-built resilience within the food system and more localisation
|  | Achieved |  | N/A | 10% of companies
Source - Indicator PO2 ATNi
| Outcome Indicator 2.2 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
| Number of investors endorsing ATNi projects and targets, in addition to membership of ATNi's Investors in Nutrition and Health (AINH) | Planned | 0 | 4 investors endorsing | 9 investors endorsing (total) | 13 investors endorsing (total) | N/A
|  | Achieved |  | 4 | TBC
Source - Indicator IO1 ATNi
INPUTS (£)
INPUTS (HR)
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030) | Assumptions
The ‘international system’ (global governance mechanisms, donors, multilateral organisations) give adequate attention and funding to nutrition alongside other (in particular climate and food security) priorities in an evidence-based, collaborative and coordinated manner and targeting the particular needs of vulnerable groups, including women, girls and children. | Number of multilaterals and other global institutions that integrate nutrition into their policy and financing across other sectors and collaborate with each other as a result of FCDO support or engagement TA | Planned | 0 | 1 | 2 | 3 | 4 | Through demonstrating the return on investment for nutrition, the multi-sectoral benefits, and the accountability that is built into the system, this can drive the 'international system' to support greater investment in nutrition -unlocking financing from organisations such as the World Bank, the climate funds (GCF, GEF, AF), development banks (AfDB, ADB, IDB - Inter-American DB), etc.
|  | Achieved |  | 1 - FAO | 2 - FAO & WB
Source - NASC's TA provider (cumulative)
| Outcome Indicator 3.2 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
| Number of donor and multilateral organisations making commitments on nutrition and making positive progress with implementing them as recorded in GNR/NAF | Planned | 0 | N/A | 20 donor & organisations make commitments at N4G 2025 | 25 donor & organisations make commitments as part of N4G 2025 | >30 donor and organisations make commitments at N4G
|  | Achieved |  | N/A | 23 donor & organisations made commitments
Source - GNR Data: Commitments relating to N4G 2025. Proportion making positive progress reported from June 2026
INPUTS (£)
INPUTS (HR)
OUTCOME 4 | Outcome Indicator 4.1 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030) | Assumptions
Civil society and consumers increase their demand for good nutrition from governments and business, in particular for low-income groups, women, girls and children, and alongside their demands on food security, climate and nature | Number of CSOs and consumer associations using data or analysis produced by ATNi with public referencing | Planned | 5 | 18 | 31 | 50 | TBD | Private sector nutrition accountability and advocacy will improve the availability and accessibility of affordable nutritious foods for those living in LICs, as well as HICs, and for women, girls, and children. By improving the availability and accessibility of nutritious products, this will also translate into increased sustainable food production. This would increase local/regional food system resilience and mitigate against potential impacts on the local/regional food industry from climate change, and wider natural disasters/shocks.
|  | Achieved |  | N/A | 44
Source - Indicator IO3 and IO4 ATNi (cumulative)
| Outcome Indicator 4.2 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
| Number of CSOs making commitments to nutrition and making positive progress with implementing them as per GNR / NAF | Planned | 0 | N/A | Not measured | 60 | 75
|  | Achieved |  | N/A | 51 organisations made commitments at N4G 2025
Source - GNR Data: Commitments relating to N4G 2025. Proportion making positive progress reported from June 2026
INPUTS (£)
INPUTS (HR)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030) | Assumptions
TA Facility FCDO, governments and other organisations have increased capacity and evidence to take action on nutrition across different sectors, including in policy and investments | Number of FCDO advisers, governments and global stakeholders with increased capacity to invest in nutrition, integrate nutrition across other sectors, and put in place and implement policies to strengthen health, food and other systems for nutrition, including for women, girls and children | Planned | N/A | N/A | 30 FCDO advisers, SROs, PROs, and representatives from governments and other organisations | TBC once nutrition TA transitions to EPD | TBC once nutrition TA transitions to EPD | By supporting programme teams, and through the development of internal policy and accountability tools, that FCDO programming will be more impactful on nutrition and that prioritisation on nutrition will be more effective - that strategies and frameworks for action can and will be adopted and put into action. From an accountability standpoint, this will also help to influence other donors and organisations, to be transparent and open about progress.
|  | Achieved |  | N/A | 40 engaged
Source - NASC's TA provider
| Output Indicator 1.2 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
| Number of FCDO policies and programmes that integrate nutrition and promote and support government, business and civil society action on nutrition outcomes for low-income groups, in particular women, girls and children | Planned | N/A | N/A | 15 programmes, initiatives, and organisations to receive TA and improve integration 65% of programmes or initiatives where TA was provided see improved focus on nutrition needs of women, girls, and children | TBC once nutrition TA transitions to EPD | TBC once nutrition TA transitions to EPD
|  | Achieved |  | N/A | 24 recipients 100% of these with improved focus on nutrition
Source - NASC's TA provider
IMPACT WEIGHTING (%) | Output Indicator 1.3 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
2026: 33% | Number of new global knowledge and evidence products about investing in and integrating nutrition across multiple sectors produced, disseminated, and integrated into FCDO's policy and programmatic work | Planned | N/A | N/A | 6 new nutrition knowledge and evidence products used by FCDO | TBC once nutrition TA transitions to EPD | TBC once nutrition TA transitions to EPD
|  | Achieved |  | N/A | 12 products used
Source - NASC's TA provider
INPUTS (£) | FCDO (£) per year
1000000
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030) | Assumptions
ATNi Accountability of the food industry has increased at global levels and in LMICs, in particular regarding their impact on the diets of poor women and children | Number of multinational and national companies, unique companies, assessed across all of ATNIs products (including Global Index, BMS Marketing Index, Spotlight Indexes, etc.) | Planned | N/A | 39 (Unique) | 46 (Unique) 85 (Cumulative) | 26 (Unique) 101 (Cumulative) | TBD | Holding businesses to account by making underperformance and areas of improvement public will drive wider private sector change, led by the targeting of industry leaders to make change happen. Indications to date on effectiveness have been positive, however, there are no guarantees. ATNi continue to explore new methods to expand reach and impact, whilst also looking at opportunities to utilise local accountability mechanisms to sustain action. ATNi does have a focus on the diets of poor women and girls, however this can be harder to capture. ATNi have highlighted the issue of product disparity in HICs vs LICs and the impact this has on diet. They have also worked on developing benchmarking products on breast milk substitutes and adherence to standards (BMS code) through their BMS Marketing Index.
|  | Achieved |  | 40 | 81 (Unique) 121 (Cumulative)
Source - Indicator R7 ATNi
| Output Indicator 2.2 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
| Number of investors, CSOs and business platforms engaging with ATNI to inform their decision and actions | Planned | N/A | 220 (Unique) | 224 (Unique) | 250 (Unique) | TBD
|  | Achieved |  | 413 (Unique) | 450 (Unique)
Source - Indicator R2.3 ATNi
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
2026: 33% | Number of accountability products, tools and assessments available at global and country level | Planned | N/A | 18 accountability products, tools, and assessments | 13 accountability products, tools, and assessments | 25 accountability products, tools, and assessments | TBD
|  | Achieved |  | 19 (11 action research/policy briefs and 8 publications) | 17 (3 action research/policy briefs and 14 publications)
Source - Indicator R3 (Action Research/Policy Brief) and R8 (Publications) ATNi
INPUTS (£) | FCDO (£) per year
1000000
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030) | Assumptions
GNR The global nutrition community is being held to account effectively for their commitments on nutrition | Number of stakeholders registering, reporting and making progress on commitments in the NAF | Planned | 217 entities registered (N4G 2021) 0% reported against | N/A | N/A | 210 registered 50% reported against | TBD | All countries and organisations with nutrition as a focus of their work, (the global nutrition community), will make commitments on nutrition and engage with GNR as the primary accountability platform. Accountability helps to ensure that governments and organisations follow through on their actions. The GNR has been rather limited so far in its advocacy work with a degree of reliance on other partners to take the lead, such as France on N4G with support from ATNi Note: GNR is limited in its ability to secure commitments or updates on commitments from countries and organisations who have made pledges.
|  | Achieved |  | 217 (N4G 2021) 2% reported against | 160 registered (post N4G 2025) 52% reported against
Source - Indicator G1.1 (entities) and G3.2 (proportion of commitments reported against) GNR
| Output Indicator 3.2 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
| Number of tools developed and shared by GNR and the number of thought leadership pieces published | Planned | 0 | N/A | N/A | 8 (inc. GNR Thematic Report) | TBD
|  | Achieved |  | 8 (8 tools) | 9 (6 tools and 3 thought leadership pieces, inc. N4G 2025 Statement Annex)
Source - Indicator OP2.1 (tools) and OP2.2 (thought leadership pieces) GNR
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
2026: 17% | Policy and decision makers drawing from GNR data and knowledge products, through a) events where GNR resources and/or guidance is presented, b) strategic partnerships are established, and c) engagement activities | Planned | 0 | N/A | At least 8 | At least 8 (a-6, b-2) | TBD
|  | Achieved |  | N/A | 11 (a-5, b-3, c-3, inc. presentation of resources at N4G summit and an AFSF side event)
Source - Indicator OP3.1 (events resources/guidance presented), OP3.2 (strategic partnerships), and OP3.3 (number of engagement activities) GNR
INPUTS (£) | FCDO (£) per year
500000
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030) | Assumptions
SMS Compact members and SUN countries are able to integrate nutrition across portfolios and enable greater action and financing for nutrition. | Facilitate knowledge generation and sharing on nutrition integration | Planned | N/A | N/A | N/A | At least 2 webinars and a survey | TBD | By countries and organisations signing up to the Global Compact or as a SUN member, that those countries will then take active steps to integrate nutrition further utilising resources made available. Through nutrition integration, governments/organisations will enable a cross-sectoral approach and provide more opportunities for nutrition-relevant interventions to reach those who need them. Utilising a cross-sectoral approach mitigates against broader ODA cuts as it diversifies the portfolio of programming that nutrition interventions are delivered through
|  | Achieved |  | N/A | N/A
Source - Indicator SO 3.1.2.1 SMS
| Output Indicator 4.2 |  | Baseline (2023) | Milestone 1 (June 2024) | Milestone 2 (June 2025) | Milestone 3 (June 2026) | Target (2030)
| SUN 4.0 strategy and operational plan developed and approved, and other milestone deliverables | Planned | SUN 3.0 strategy ends in 2025 | N/A | N/A | SUN 4.0 endorsed and operational plan finalised | TBD
|  | Achieved |  | N/A | N/A | Yes
IMPACT WEIGHTING (%) |  | Source - Indicator SO 4.2.1 SMS
2026: 17%
INPUTS (£) | FCDO (£) per year
500000
INPUTS (HR) | FCDO (FTEs)