## Annual Review Template

Title: Young Lives at Work, Improved Understanding of the Effect of Educational Opportunities on Labour Market Outcomes
Programme Value £9.4m		Review date: June 2025
Programme Code: 301108	AMP start date: 20/12/2019	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2020	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A	A+	A
Risk Rating	Major	Major	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/52784570.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004113.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

Young Lives (YL) is a unique and innovative longitudinal cross-country study which has followed the lives of 12,000 individuals since 2001 in Ethiopia, India (in the states of Andhra Pradesh and Telangana), Peru and Vietnam.[1]
[1] To date, there have been four phases to the programme with YLAW representing a new and fifth phase.

‘Young Lives at Work’ (YLAW) is the latest phase of FCDO’s support to YL, with the new phase commencing in January 2020. The purpose of the programme is to improve global understanding of how poverty affects young people’s transition to adulthood, generating data and evidence to inform ways to improve education, labour and well-being outcomes for young people. YLAW longitudinal data and analysis is used to:

Shape global and national policy debates and enable FCDO to further demonstrate thought leadership on youth employment, education, skills and poverty;
Inform and challenge policy and practice on youth employment, skills development and higher education at international and national levels;
Deliver a rich dataset to generate new research on, for instance, youth employment, occupational segregation, gender (or other) disparities;
Expand opportunities for data matching with existing national surveys and strengthen capacity among researchers to maximise the value of this longitudinal research.

Since 2005, YL has been led by Oxford University’s Department of International Development (ODID) with country research teams and additional partners[2] embedded in each of the four countries. YLAW is largely funded by FCDO but also co-funded by the Old Dart Foundation, The Packard Foundation, Echidna Giving, the Wellcome Trust, the Medical Research Council (MRC) and National Institute of Health (NIH)[3].
[2] Policy Studies Institute (Ethiopia), Pankhurst Development Research Consulting (Ethiopia), Center for Economic and Social Studies (India), Grupo de Analisis para el Desarrollo (GRADE) (Peru), Instiuto de Investigacion Nutricional (IIN), Government Statistics Office (Vietnam), Center for Analysis and Forecasting- Vietnam Academy of Social Sciences (CAF- VASS)
[3] The current phase of FCDO support (£9.4m) has made up 65% of YL funding since 2018 (£14.5m)

In May 2024, FCDO granted YLAW a no cost extension to March 2026 due to delays caused by suspension of Round 7 (R7) activities in Vietnam.

Summary supporting narrative for the overall score in this review

The programme is awarded an A score for the review period, reflecting strong performance across outcome and output indicators, and evidence of clear added value in research quality and policy influence. Over the past year, Young Lives has made notable contributions to both international and national policy discussions, underpinned by new analysis and dissemination of the Round 7 (R7) data. The publication of nine thematic factsheets across core domains - Education, Learning and Skills; Health, Nutrition and Wellbeing; and Work and Family Lives - marked a milestone. These were launched via country-level events that attracted local media attention and helped position the research for direct engagement with stakeholders.

The programme exceeded expectations on several key indicators, particularly in terms of policy influence and academic uptake. Highlights include Young Lives’ invitation to contribute to the WHO Expert Technical Committee on mental health, with findings subsequently cited in the new WHO global guidance on mental health and wellbeing. At country level, Young Lives evidence played an important role in proposed education reforms in Peru, while the team’s engagement with the OECD further demonstrates its strategic policy reach, with Young Lives papers expected to inform Peru’s accession processes.

Young Lives’ data and evidence continue to be widely used by a growing and diverse network of researchers, including from low and middle-income countries (LMICs). Although the milestone for dataset downloads was narrowly missed, progress across other output indicators was strong. Notably, the team has sustained low attrition rates and pursued data-matching innovations, enhancing the quality and comparability of the longitudinal analysis.

The year also marked progress on fundraising and thematic expansion. New funding was secured for the sixth qualitative round in Ethiopia from FCDO Ethiopia and Irish Aid and seed funding from the University of Oxford enabled the launch of the Young Lives Research Hub on Climate Change and Environmental Shocks. The team showcased its climate-related findings at COP29 side events and continues to collaborate with UNICEF, Save the Children, and FCDO to inform international climate policy processes, including preparations for UNFCCC’s Bonn Climate Conference and COP30.

Major lessons and recommendations for the year ahead

- As the programme enters its final year, the team should focus on consolidating and disseminating the methodological, operational and policy-related learning from over two decades of longitudinal work. The team are planning to produce four comprehensive legacy reports and briefing notes on the available datasets. FCDO and the Young Lives team should consider options for sharing the lessons from these outputs both externally and with FCDO colleagues, potentially through a series of ‘legacy learning’ events.
- Investment in Young Lives has demonstrated the value and applicability of longitudinal evidence, and the programme has maintained impressively low attrition rates. Young Lives and FCDO should continue to consider how to share the lessons from this, including dissemination of Young Lives’ note on the value of longitudinal research, and FCDO should look for opportunities to champion Young Lives internally and externally as a model for long-term, policy-relevant research.
- With programme end approaching in 2026, risks to sustainability of access and engagement need to be proactively managed to ensure continued impact. The team should continue to focus on implementation of the sustainability strategy, including consideration of continued access to all programme research outputs. This should also include planning for how to track the programme’s outcomes and impacts beyond the lifetime of FCDO funding, to ensure continued learning and evidence of longer-term change.
- In taking forward legacy learning products, the team should ensure that lessons on labour market issues are clearly drawn out and communicated. They should also target relevant stakeholders working on labour market issues and actively promote the use of Young Lives data to inform research and policy on labour markets and youth employment.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change (ToC) for the YL programme, including the YLAW phase (Figure 1), was designed in 2020 based on the recommendations of an external evaluation (by Ecorys[4]). This states that the programme:
[4] Ecorys and the Institute for Development Studies have conducted an evaluation of Young Lives, a DFID funded longitudinal research programme. | Ecorys

Generates longitudinal data using an innovative inter-cohort design.
Publishes the data open access (within constraints of anonymity).
Conducts secondary analysis.
Publishes high-quality research and policy products.
Generates technical expertise on data and survey methodologies.
Shares and disseminates evidence with policy makers.

The intended impact of the programme is to improve understanding of childhood poverty on young people’s transition to adulthood (taking account of on-going gendered inequalities and external shocks) and inform policies and programmes with rigorous evidence to improve outcomes for young people. Outcomes will be discussed in detail in the next section.

Figure 1: YLAW Theory of Change

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme is on track and largely meeting or exceeding expectations at outcome and output level (with two output targets missed by a small margin).

Outcome 1: Improved knowledge of how early experiences of childhood poverty affect later life outcomes shaped by intersecting inequalities and vulnerability to external crises.

Indicator(s)	Milestone(s) for this review	Progress
1.1. Examples of high level local and global buy in and acceptance of YL data, evidence and research methodology (cumulative).	22 examples	Exceeded. 24 examples (6 new)
1.2. Number of articles published by non-YL researchers that use YL data and research or cite YL research (cumulative).	669 examples	Exceeded. 819 examples (312 new)

YL has moderately exceeded expectations with respect to Outcome 1.1 which focuses on high-level local and global buy in and acceptance of YL research (target was increased following the 2024 annual review due to strong performance). Examples from this year:

- Young Lives at COP29 and informing UNFCCC process towards COP30: Young Lives presented research at two side events at COP29 in Baku, highlighting the long-term impacts of climate shocks on children and the need for better social protection to mitigate these. They have continued to build momentum around their policy influencing on the impacts of climate shocks. This includes identifying opportunities to inform processes leading up to the UNFCCC climate meeting in Bonn (June 2025) and COP30 (November 2025). In preparation, the team prepared two submissions to UNFCCC on i) the Global Goal on Adaptation; and ii) gender and climate (accepted in March 2025). This is the first time a formal submission directly from the University of Oxford has been included as part of the UNFCCC process.
- Young Lives’ impact recognised through awards: The Young Lives team was awarded the University of Oxford 2025 Social Science Impact Award for their involvement in influencing a change to legislation banning child marriage in Peru. Young Lives was also shortlisted for the University of Oxford’s 2025 Vice Chancellor’s Award for Excellence in Research Engagement, which recognises high-quality research and innovation. The nomination highlights Young Lives’ impact on shaping policy, highlighting their role in influencing Peru’s Right to Education Bill and legislation to end child marriage. The Young Lives Peru team were also selected as a finalist in the 2024 Peru SDGs Awards in the ‘People’ category, recognising their impactful research and policy engagement to promote sustainable development in Peru.
- Advising on Peru’s OECD Accession: Young Lives Peru have been invited to present evidence and expert advice to the international consideration of Peru joining the OECD. Young Lives Peru team members met with an OECD delegation in December 2024 to present Young Lives’ evidence relevant to assessing the adoption of measures to promote economic growth and equality. Upon request from the OECD, Young Lives Peru submitted several Young Lives papers for use in the delegation’s report setting out recommendations for incorporating Peru into the OECD. The related OECD report is expected late 2025/early 2026.
- Young Lives Ethiopia celebrates 15 years of Research and Practice Forum: Young Lives Ethiopia established the Children, Youth & Women’s Research and Practice Forum (CYW-RPF), in partnership with the Ministry of Women and Social Affairs, UNICEF and UN Women. This monthly forum brings together influential national stakeholders to share evidence and inform policy debates. In February 2025, it celebrated its 15-year anniversary with a high-level event, including a keynote address from the Minister for Women and Social Affairs. The membership base of the forum includes 1,450 individuals from research and policy organisations, UN organisations, international NGOs, and local networks. The long-term relationships established through the network have helped deliver meaningful policy impact at scale, having informed numerous policies in Ethiopia, including National Action Plans on Child Labour, Harmful Traditional Practices, Social Protection and Youth Development over the last 15 years.

Indicator 1.2 is used to understand wider usage of YL open access data to produce research and measures the number of articles published by non-YL researchers using YL data. 819 cumulative citations have been recorded against a milestone of 699 (the target was increased following the 2024 annual review based on strong performance). In the past year, Young Lives data and research findings have been cited by researchers working in a variety of countries and across a broad span of research areas. The work has been cited in journals ranging from the International Journal of Educational Research to Child Protection and Practice to Frontiers in Psychiatry. Of the 312 new article articles in the past 12 months using YL data and citing YL research findings, 87% were journal articles, 57% of the authors were women, and 47% of the articles were authored by academics from the LMICs. Highlights include:

- Productivity of schooling: An article published in The World Bank Economic Review on the productivity of schooling is based on Young Lives data from Rounds 2 to 4 collected in Vietnam, India and Peru. This uses Young Lives cognitive test scores and schooling data to propose that learning is maximised when the level of skill attained by the child matches the complexity of the learning experiences offered at school, and that mismatches in either direction are detrimental for learning. The article argues that this provides direct evidence about the importance of tailoring the learning experiences offered at school to the degree of competence of the child.
- Natural hazard exposure and mental health: An article published in the journal Scientific Reports and featured on the Nature website uses Young Lives data from Ethiopia, India, Peru, and Vietnam to estimate the effects of natural hazard exposure during early developmental stages on later anxiety and depression symptoms among young adults, arguing that high-quality evidence should drive structures for mental health service provision among the most impacted populations.
A number of journal articles and working papers that cite Young Lives data were presented at the annual conference of the Centre for the Studies of African Economies (CSAE) in March 2025.

Outcome 2: National and international policies and practices informed by Young Lives evidence to improve the lives of young people who have grown up under disadvantaged circumstances.

Indicator(s)	Milestone(s) for this review	Progress
2.1. Examples of YL data and evidence informing a future change in policy and/or programmes (at country and global level) that are likely to contribute to improving the lives of children and young people (cumulative).	8 examples	Achieved. / 9 examples (3 new)

Outcome 2.1. YL continue to perform in line with expectations with respect to examples of evidence and data informing changes in policy or programming, with three new examples this year:

- WHO Guidance on Mental Health Policy and Strategic Action Plans: Young Lives’ research and policy recommendations directly informed the WHO 2025 flagship global guidance on mental health policy and strategic action plans, launched in March 2025 by Director-General Tedros Adhanom Ghebreyesus. Young Lives’ Deputy Director, Kath Ford, was invited to join the WHO Expert Technical Committee for developing and reviewing these guidelines throughout 2023-2024. The guidelines include three specific citations to Young Lives evidence.
- Ensuring the right to basic education for all children in Peru: In August 2024, the Young Lives Peru team presented new Young Lives research on school drop-out numbers to high-level stakeholders. They also produced a policy brief (in Spanish) and videos for social media to ensure research findings were accessible to a wider non-academic audience. This engagement prompted Congresswoman Flor Pablo to request further Young Lives evidence and expert advice for a legislative campaign supporting the right to basic education for children who have previously dropped out of school. A new Congressional Bill was introduced in November 2024, directly citing Young Lives evidence. The Bill aims to extend the age limit for accessing basic education and implement flexible school policies to support the reintegration of excluded children, estimating that this has the potential to transform educational access for over one million young people affected by poverty, disability and violence.
- Informing national policy debates to end child marriage in India: Young Lives has continued to inform national policy debates to end child marriage in India. As reported in Year 5, Young Lives India’s evidence directly informed the parliamentary Bill, ‘Prohibition of Child Marriage (Amendment) Bill, 2021’ to increase the marital age of women and reduce early marriage. While this Bill has not yet been passed at the national level, a similar Bill was passed at state level in 2024: The Prohibition of Child Marriage (Himachal Pradesh Amendment) Bill was passed by the Himachal Pradesh Assembly on 27th August 2024. It is waiting for the assent of President Droupadi Murmu to become law. This amendment raises the legal minimum age of marriage for women in Himachal Pradesh from 18 to 21 years, in line with that for young men. In October 2024, in response to a writ petition citing Young Lives evidence on the long-term impacts of child marriage, the Supreme Court of India issued comprehensive guidelines for effective implementation of the Prohibition of Child Marriage Act 2006, aiming to strengthen the enactment of this Act to end child marriage in India.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on its sustained high performance, policy relevance, and unique longitudinal dataset spanning over two decades, the programme should continue to the end of the current phase. Young Lives at Work offers strong Value for Money (VfM) and remains an important component of the FCDO’s research portfolio on youth and poverty. The ability of the programme to generate robust, policy-relevant insights and to respond to global challenges - such as climate change, education access, and gender inequality - makes it strategic in the context of FCDO’s wider goals. The final year of the programme provides a good opportunity to consolidate its legacy and share lessons learned across the span of the programme, increase uptake of the final Round 7 dataset, and enhance visibility of FCDO’s long-term investment in high-quality, longitudinal research.

## C. DETAILED OUTPUT SCORING

Output Title	High quality, publicly available longitudinal data
Output number:		1.	Output Score:	A
Impact weighting (%):		35	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Covid Phone Survey and Household surveys designed and undertaken to collect longitudinal data on two existing cohorts across four study countries.	Attrition reports published	Achieved: The attrition rates have been analysed and discussed in the R1-R7 Attrition Report, published as planned.
1.2 Overall attrition rate of Young Lives cohorts	Cohort maintenance undertaken	Achieved: In Round 7 located and interviewed 81.9% of the original 2001 Round 1 sample, with an overall attrition rate of 18.9% over a 20+ years period.
1.3 Young Lives data is prepared for analysis and publicly archived.	Round 7 survey data cleaned & prepared for analysis	Achieved: Data cleaning has been a focus of Year 6 and is on track. The team created key variables and indicators used for the analysis presented in the R7 factsheets, and it is still working on the constructed datasets (including variables consistently collected across survey rounds) that will be archived alongside the raw clean data in Year 7.
1.4 Young Lives data matched with other datasets and make the (anonymised) matched datasets publicly available.	Further data matching opportunities explored (one additional matching completed, possibly using education data)	Achieved: Data matching initiatives have been scaled up through the creation of the YL Research Hub on Climate Change and Environmental Shocks. / Additional work has been done in matching Young Lives data with administrative education data in Peru.
1.5 New and cumulative number of downloads of Young Lives data from UK Data Service	22,394 cumulative downloads of YL data sets / • 2,723 new downloads of YL data sets / • 581 new users of YL data sets	Missed by small margin: / • 22,011 cumulative downloads of YL data sets / • 2,368 new downloads of YL data sets / • 531 new users of YL data sets

Briefly describe the output’s activities and provide supporting narrative for the score.

This output scores an A having broadly met expectations against milestones this year. The programme missed its target on data downloads by a small margin, but otherwise met expectations on attrition, data cleaning and data matching.

With Round 7 (R7) fieldwork complete, this year the research team has focused predominantly on aspects related to data management and data cleaning of the R7 data, and on the analysis of key patterns emerging from the newly collected data compared to previous survey rounds.

Output 1.1 focuses on “Surveys designed and undertaken to collect longitudinal data across four study countries.” The programme met the target for this year, publishing the Attrition Report in March 2025, a technical note documenting the R7 attrition rates. It provides details on the completion rates observed for specific components of R7 that required additional informed consent (a self-administered questionnaire, anthropometric measures, reading comprehension, computerised cognitive tasks, and hair sample collection).

Output 1.2 considers overall attrition rates. Using Round 1 sample as the baseline year, an overall attrition rate of 18.9% was achieved (with attrition rates of 25.6% in Ethiopia, 11.5% in India, and 19.8% in Peru), significantly below the target of 35%. The programme’s work to reduce attrition has been impressive, with an annual attrition rate of less than 1% since 2001. This means that the fieldwork teams could locate and interview 81.1% of the Round 1 respondents, more than 20 years after they were first interviewed, corresponding to 91.9% of the Round 5 sample. The team has also been successful in the recovery of some respondents who were not located or interviewed during the 2021 phone survey (which explains the negative attrition rates -16.2% when using Round 6 as a baseline year).

Output 1.3 focuses on the preparation and cleaning of data ready for analysis. Following the conclusion of the fieldwork activities, the raw datasets from R7 data have undergone several stages of checks and corrections to produce a clean, accurate and consistent dataset for internal use, which will eventually be archived for public use on the UK Data Service. Currently two datasets are being created that will be archived by the end of Year 7: i) a “raw (anonymised) dataset” including all the information collected in R7; and ii) “constructed panel” databases that harmonise some of the key variables collected across the seven rounds. The datasets will be archived alongside survey documents and technical notes (including the survey questionnaire, data dictionary and data handouts).

Output 1.4 looks at matching YL data with other datasets. During the past year, the Young Lives data matching initiative was scaled up by creating the Young Lives Research Hub on Climate Change and Environmental Shocks, with seed funding from the University of Oxford Social Science Division. The main objective of the Hub is to provide evidence on the effects of climate change and environmental shocks on cognitive skills development and physical and mental health, across the life course and two generations of children growing up in poverty. The foundational phase of the Hub has the primary aim of creating the Young-Lives-Pollution-Heat Panel (YLPHP), a high-resolution, cross-country panel dataset, that tracks Young Lives respondents’ exposure to air pollution, extreme temperature and rainfall shocks (and other environmental extremes) from conception to young adulthood. This requires matching Young Lives data with NASA (the US National Aeronautics and Space Administration) and the European Union’s air pollution and temperature data using the GPS coordinates of the Young Lives respondents’ residences and their migration/movement history. The Oxford team started systematising the available information about individual locations across the seven survey rounds to construct the migration history of our participants and track their locations throughout their lifespan. This is the first step in the construction of the YLPHP panel.

There has also been ongoing data matching work investigating the long-term effects and sustainability of a comprehensive secondary-level public school reform called the Extended School Hours Program (Jornada Escolar complete, JEC) in Peru. The researchers are using administrative data from Peru’s Ministry of Education to track almost 900,000 students enrolled when JEC began in 2015 and are matching the datasets with Young Lives, to measure access to the labour market by the cohort who entered the reform.

Output 1.5 measures new and cumulative number of downloads of YL data from UK Data Service. In this reporting period, there have been 2,368 new dataset downloads from 531 users. These users come from 35 different countries, with 36.5% of the downloads from LMICs. The cumulative number of downloads of Young Lives data sets from the UK Data Service (UKDS) now stands at 22,011 which equates to 98% of the logframe milestone of 22,394. This has narrowly missed the milestone target, however there is an expectation that download numbers will increase following the public archiving of R7 data later in Year 7.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following the previous annual review, a new milestone target for Output 1.3 was set for 2026 and Output 1.5 milestone 5 was re-benchmarked given over-performance in 2024 (re-benchmarked at M4 actuals + average increase) and a milestone 6 target was added. Given the fieldwork has been completed, the ongoing focus for this output for the year ahead will be on preparation and archiving of the R7 data. Milestone targets for Outputs 1.1 – 1.3 have been achieved and there is little scope of the programme to exceed delivery against these targets. The target for Output 1.4 remains appropriate given that it was narrowly missed this year. Achieving the target for downloads should be a priority under Output 1 for the year ahead, given the increased importance of dissemination and policy influencing and engagement as compared to data generation in the current programme phase.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s Annual Review made two recommendations, both of which have been addressed. The first recommended that Young Lives explore new data matching opportunities in the current year. This has been achieved through work to explore matching Young Lives data with satellite data, particularly to support the development of the new Young Lives Research Hub on Climate Change and Environmental Shocks. This innovative approach lays the groundwork for future research into the intersection of poverty, childhood development, and environmental stressors.

The second recommendation encouraged the Young Lives team to reflect on and share lessons from its low attrition rates - a distinctive feature of the dataset. Young Lives and FCDO have discussed ways to share these insights through events, blogs, podcasts, and internal briefings. However, given the importance of this legacy learning, and the potential value for other longitudinal studies and donors, this recommendation should be carried forward into the final year, with more concrete outputs planned.

Recommendations for the year ahead:
The YL team should continue to consider opportunities to share lessons on the low attrition rates in the programme, with other longitudinal surveys and with FCDO colleagues. This could be a dedicated knowledge-sharing event on longitudinal retention via a joint webinar or workshop (potentially with FCDO and other funders of longitudinal studies) focused on how Young Lives achieved low attrition rates. Include methodological insights, ethical considerations, and lessons for future research investments.
Promote global visibility of the dataset in LMIC academic and policy circles. Actively disseminate information about data access and legacy products to academic networks, social science research bodies, and regional development partners.

Output Title	High quality research and relevant policy outputs
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of YLAW peer-reviewed research documents submitted for publication authored by YL researchers or externally commissioned, disaggregated by gender and north/south status of authors.	53 cumulative submissions	Exceeded: 67 cumulative submissions (23 new)
2.2 Number of YLAW non-peer reviewed working papers authored by YL researchers or commissioned by YL, disaggregated by gender and north/south status of authors.	31 cumulative examples	Target missed: 29 cumulative submissions (two new)
2.3 Number of YLAW published policy briefs and reports authored by YL researchers or commissioned by YL, disaggregated by gender and north/south status of authors.	4 Policy Briefs	Achieved: 4 Policy Briefs (including 2 co-funded)

Briefly describe the output’s activities and provide supporting narrative for the score.

This output looks at the research and policy outputs of the programme and finds the programme has exceeded the number of peer-reviewed research documents, achieved the number of published policy briefs and missed the target on non-peer reviewed working papers, but by a narrow margin. Given that the team was prioritising publishing all existing research articles as journal articles, the output has been scored as an A overall.

Indicator 2.1 considers peer-reviewed research documents submitted for publication and YL has exceeded delivery against this target by 14, with 67 cumulative submissions. 49% of contributors were from the Global South and 44% identified as female. Nine new papers were published with four additional papers at Revise and Resubmit stage.

Indicator 2.2 measures the number of non-peer reviewed working papers, and narrowly missed the target, delivering 29 cumulative examples. For non-peer reviewed working papers, 100% of contributors were from the Global South and 50% identified as female.

Key examples of the peer-reviewed papers published this year include:

- Economic inequalities in adolescents' internalizing symptoms: longitudinal evidence from eight countries: This paper investigates whether mental health inequalities differ across a diverse range of countries and multiple measures of economic circumstances. They find evidence for cross-country differences in economic inequalities in adolescents' internalising symptoms, most prominently for inequalities according to household consumption expenditure.
- Gender Differences in Socioemotional Skills among Adolescents and Young Adults in Ethiopia, India, Peru and Vietnam: This paper examines the emergence of gender differences in socioemotional skills during adolescence, and the socioeconomic and cultural factors that may explain these gaps in Ethiopia, India, Peru and Vietnam. Young Lives findings show that the gender gap in self-efficacy emerges around age 19, with males scoring more highly than females in Ethiopia, India and Vietnam. Similar, but less consistent, patterns were observed for self-esteem and peer relations.
- Late-Childhood Foundational Cognitive Skills Predict Educational Outcomes Through Adolescence and Into Young Adulthood: Evidence from Ethiopia and Peru: This paper estimates associations between foundational cognitive skills measured at age 12 and educational outcomes measured at ages 15 and 19 to 20 in Ethiopia and Peru. The results provide additional evidence to justify the importance of promoting investments in cognitive skills throughout childhood and adolescence and elucidate how such investments impact educational achievements.
- Long-term effect of rainfall shocks on foundational cognitive skills: evidence from Peru: This paper analyses the effects of early exposure to rainfall shocks on four foundational cognitive skills, including Executive Functions (EFs) that have been found to be key predictors of educational success. The results show significant negative effects of early life exposure to rainfall shocks on EFs, especially on working memory, measured in later childhood.
- How Early Nutrition and Foundational Cognitive Skills Interconnect? Evidence from Two Developing Countries: This paper finds robust evidence that stunting at about age five is negatively related with executive functions measured years later, predicting reductions in working memory and inhibitory control. These results shed light on mechanisms that explain the relationship between early nutrition and school achievement tests suggesting that good nutrition is an important determinant of children’s learning capacities.
- The long shadow of conflict on human capital: Intergenerational evidence from Peru: This paper estimates the intergenerational impacts of mothers’ exposure to the 1980–2000 Peruvian civil conflict on their children’s socio-emotional skills development, finding that mothers’ exposure to conflict has adverse intergenerational effects on their children’s socio-emotional outcomes of agency and pride.
Output Indicator 2.3 considers the number of published policy briefs and reports delivering four policy briefs, two at the international level and two at the policy level, meeting the target during the review period. These publications were:

- Lightening the Load: New Evidence on the Impacts of Unpaid Care Work on Women and Girls: This policy brief summarises Young Lives findings on the disproportionate share of unpaid care work done by women and girls across the world and suggests ways that policy and practice can support a more equal distribution of unpaid care work with men and boys. The evidence identifies adolescence as the key inflection point when gendered inequalities in unpaid care emerge. It also shows how girls and women take on the majority of unpaid care duties during crises such as COVID, conflict and climate shocks.
- Building Fairer Futures: Women’s Economic Empowerment in the Face of Climate Change: This policy brief summarises Young Lives findings on how climate shocks impact on women and girls’ education, health, and economic opportunities. Evidence spanning three generations reveals the long-term effects of climate change on young women and girls, highlighting the need for targeted policy interventions that address their distinct climate-related vulnerabilities, including social protection, education and training. Climate transition is a huge opportunity to shift the dial on women’s economic empowerment, but this demands a deliberate effort from all stakeholders, including gender-responsive climate finance and action plans at national and international level.
- School drop-out and educational vulnerability; recommendations for basic education in Peru: This policy brief summarises the causes of secondary school drop-out following the COVID-19 pandemic and its disproportionate impact on the affected students. Young Lives evidence shows that children from rural, indigenous and extremely poor households are at much greater risk of school drop-out, with low educational quality further compounding risk. The brief argues that public programmes seeking to mitigate the problem have limited impact due to the lack of comprehensive policies and adequate educational resources. It proposes strengthening prevention, retention and school reinsertion strategies through integrated approaches, expansion of educational programmes and promotion of gender equity.
- The impact of COVID-19 on subjective wellbeing among rural and urban youth in Peru: This policy brief summarises findings from the fifth wave of qualitative research (undertaken with additional funding from the Old Dart Foundation). It explores the relationship between subjective wellbeing and young people's experiences during the pandemic. It focuses on how the pandemic exacerbated inequalities, highlighting the role of gender, place of residence, and stage in the life course in affecting young people’s perception of wellbeing and their expectations for the future, setting out policy recommendations to strengthen related public policies, with a focus on creating a more equitable and sustainable future.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following last year’s review, a new milestone for Output 2.1 was set for this year given previous overperformance, no-cost extension targets were added for 2026 and additional indicators for Output 2.3 were added as per the no-cost extension business case.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Both recommendations from the 2024 Annual Review have been successfully addressed. The first - revising milestone targets upwards in response to strong performance - was completed following the last review. The second focused on strengthening the translation of research outputs into policy impact. Young Lives has demonstrated progress here, with several research products contributing to meaningful policy engagement. Notably, a policy brief and accompanying research paper on school dropouts in Peru were used to support a legislative campaign led by Congresswoman Flor Pablo on securing the right to basic education for children and adolescents who are overage / behind in school grades.

In the final year, the emphasis will shift from research production to strategic dissemination, uptake, and embedding findings into policy and practice.

Recommendations for the year ahead:

Prioritise publication of remaining high-impact peer-reviewed articles and working papers. Focus on completing and submitting those working papers with the strongest policy relevance or legacy value.

Output Title	Expanded dissemination of YL outputs and data by researchers and policy makers, facilitated by communications activities through multiple channels and policy-engagement events and interactions.
Output number:		3	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of blogs, articles, TV/radio interviews, etc. based on Young Lives findings	At least 181 cumulative outputs	Exceeded: / 222 cumulative outputs (71 new)
3.2 Number of followers of Young Lives on social media	Total followers: 42,850	Exceeded: / Total followers: 43,524
3.3 Number of known users of Young Lives research outputs	50,000 cumulative website PDF downloads	Exceeded: / 51,030 cumulative website PDF downloads (11,589 new)
3.4 Number of engagements with stakeholders where YL evidence or analysis is presented and discussed both at Oxford and Country Level	377 cumulative events	Exceeded: / 430 cumulative events (93 new)

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focuses on dissemination and communication activities. Overall, YL performed strongly and exceeded expectations in terms of expanding the dissemination and communication of their research through communication channels and engagement events, scoring an A+ overall.

Output Indicator 3.1 measures the number of blogs, articles, interviews etc to promote YL findings and was exceeded by 41 outputs. Highlights include:

- In June 2024, Young Lives evidence and a quote from Director Marta Favara featured in an article in the UK’s Financial Times, Conflict and climate shocks fuel food poverty crises, exploring the impact of conflict and climate shocks on food poverty.
- In early 2025 Marta Favara was invited to take part in a flagship BBC World Service programme 'The Covid Generation Revisited’ revisiting young adults previously interviewed about the impact of COVID 19 in 2020 as they enter the workplace in 2025. Marta discussed the impact of the pandemic on young people’s lives, using evidence from Young Lives R7 findings.
- In Ethiopia, India and Peru the launch of the R7 results received widespread coverage. There were reports in multiple Ethiopian newspapers, including The Reporter and The Ethiopian Herald, as well as on Tirita Radio and Sheger Radio. In India, the findings were reported in the Deccan Herald. In Peru, the results were discussed on Epicentro TV, whilst articles were published in Ojo Público on 'Millennium Children': A generation marked by inequality’ and ‘Invisible traps: Gender gaps that shape the future of young Peruvian women’.
- In the summer, the team launched a new Young Lives podcast series on the University of Oxford podcast platform, also available on Apple Podcasts and the Young Lives YouTube Channel. The series features conversations about Young Lives’ latest methodological initiatives, data collection, research findings and policy recommendations.
- The Young Lives Communications teams created a series of short films highlighting the work of their fieldworkers who have been collecting data from 12,000 study participants for over 20 years.

Output Indicator 3.2 focuses on YL social media following. The milestone was exceeded with a current total of 43,524 followers across X, Facebook and LinkedIn. During the year, the team launched an Instagram account and a Bluesky account (noting the general move away from X to less politicised platforms).

Output Indicator 3.3 measures the number of known users of YL data and was exceeded with 11,589 PDF downloads, resulting in a cumulative total of 51,030 downloads.

Output Indicator 3.4 considers the number of stakeholder engagements conducted to present and discuss Young Lives evidence and also exceeded the target with 430 cumulative events at both international and country level. Highlights include:

- International: Young Lives evidence on the long-term impacts of early climate shocks on children’s learning was presented at the REAL Centre symposium on education and climate change (May 2024).
- FCDO: Young Lives contributed to an FCDO/STAAR (Social Protection Technical Assistance, Advice, and Resources) workshop on gender-responsive and inclusive social protection research priorities (May 2024).
- India:
- Presented evidence on intersecting inequalities in Early Childhood Development at the ARNEC Regional Conference (May 2024).
- Shared findings on multidimensional child poverty at a UN Knowledge Session on Child Poverty (Oct 2024).
- Presented at a national seminar on early childhood education policy (Nov 2024).
- Engaged with high-level government officials on disability, women’s empowerment, and child marriage.
Ethiopia:
  - Continued engagement through the Children, Youth and Women – Research and Practice Forum and Academic Breakfast Networking Forum.
  - National TV interviews on poverty, early learning, and SRH (June–Aug 2024).
  - Presented at the (Data and Evidence to End Extreme Poverty) DEEP Ethiopia Challenge Fund launch (July 2024).
  - Country Director appointed to key advisory and technical working groups.
- Peru:
- Hosted a three-day methodological workshop for ministry, NGO, and aid agency representatives (Feb 2025).
- Advised at a UNESCO/Institute of Statistics (UIS) roundtable on SDG 4.1.1 data eligibility (May 2024).
- Presented findings on malnutrition and education at the World Public Health Nutrition Congress (June 2024).
- Shared evidence on early stunting and cognitive skills at the Fundacion Exito event (Aug 2024).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following last year’s review, new baselines were set for all of the output milestones for this year given previous strong performance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were two recommendations from 2023 Annual Review that were repeated in last year’s review. The first recommended conducting an international engagement exercise leveraging FCDO events and networks to align with FCDO policy priorities. This has been partially achieved through participation at COP29 and other international forums, and is set to continue, with a planned presence at the Oxford Climate Change Summit, UNFCCC’s mid-year Climate Change Summit (June 2025), and COP30 (November 2025). Young Lives’ final-year influencing strategy outlines targeted international and national-level policy engagement to maximise uptake of evidence.

The second recommendation called for more robust capture of policy influence and reach, particularly in case studies. Young Lives has continued beneficiary reach analyses in line with the agreed methodology and developed a number of case studies.[5] Planned Year 7 impact case studies include refreshed analyses of Young Lives’ influence on Peru’s JUNTOS conditional cash transfer programme and Ethiopia’s Productive Safety Net Programme.
[5] For instance, Young Lives evidence has directly informed the roll-out and strengthening of pre-primary education through the large-scale expansion of the ‘O-class’ early child development (ECD) programme in Ethiopia, which currently reaches over 2.5 million children. In Peru, legislative change protecting thousands of vulnerable girls from child marriage was informed by YL evidence (with over 4,000 child marriages registered in the last decade and over 50,000 in informal unions).

Lessons learned this year include the importance of sustained and strategic engagement with policy stakeholders through established and trusted channels; the need for ongoing validation of impact through case studies; and the value of coordinating closely with FCDO policy teams to increase evidence uptake. In the final year, it will be critical to consolidate dissemination and policy influence activities to leave a sustainable legacy.

Recommendations for the year ahead:

- Consolidate and promote policy impact case studies. Complete and publish the JUNTOS and PSNP case studies with clear narratives of impact, linked to quantifiable reach metrics and policy outcomes.
- Strengthen sustainability and legacy through institutional partnerships. Identify key in-country institutions and regional networks to continue to share Young Lives datasets and insights beyond the programme’s end.

Output Title	Production of learning tools and resources based on innovative and best practice research methods.
Output number:		4	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of methodological tools and technical notes published on YL websites.	13 cumulative examples, including: / • R1-R7 Attrition report / • R7 Fieldwork report	Achieved:13 cumulative examples (2 new)

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focuses on the production and publication of methodological tools and technical notes. Output Indicator 4.1 had a target of 13 cumulative examples, which was met with two new technical notes produced this year. The notes produced were:

- “Young Lives Attrition Report: R7” (February 2025) documents the attrition rates from the seventh round of the Young Lives survey carried out in Ethiopia, India and Peru in 2023–24. It provides details of the completion rates on the components of R7 that required additional informed consent (a self-administered questionnaire, anthropometric measures, reading comprehension, computerised cognitive tasks, and hair samples).
- “Young Lives R7 Fieldwork Report” (31 March 2025) provides a comprehensive overview of the fieldwork and data collection processes in R7, from planning to execution. It describes the main phases of the data collection process, how the fieldwork teams were organised in each country, and provides a statistical analysis of the survey administration time. It highlights the successes and challenges from the fieldworkers’ perspectives, emphasising transparency, accountability and our commitment to collecting and publicly archiving high-quality data.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following last year’s annual review, a new baseline was set for Milestone 5 based on Milestone 4 actuals and Milestone 6 was revised as per the no-cost extension business case.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The 2024 Annual Review made two recommendations focused on capturing and sharing learning from Young Lives’ experience with longitudinal research methods. The first - finalising a note on the value of longitudinal research - has been completed, with the note published in April 2025. Young Lives has already used the report for engagement with the Gates Foundation and other partners as a tool to promote understanding of and investment in longitudinal research.

The second recommendation - to consider the most effective ways to share the note with FCDO and external audiences - remains relevant and should be carried forward into the final year. As a legacy product, this note provides a strong basis for promoting good practice in longitudinal research across FCDO’s research portfolio and beyond.

Recommendations for the year ahead include:

In the final year, Young Lives should strategically disseminate the longitudinal research note, using internal and external events to share lessons, and where possible embedding insights into FCDO learning and future research guidance.
## D: VALUE FOR MONEY

VfM performance compared to the original VfM proposition in the business case

VfM is assessed using the 5 E’s framework: Economy, Efficiency, Effectiveness, Equity and Cost Effectiveness.

Economy: Measures whether we are buying the right quality inputs at the right price. The programme has successfully leveraged co-funding to expand its scope, reducing the sole reliance on FCDO funding. Notably, the Old Dart Foundation contributed £1.2 million towards fieldwork in Peru and supported an additional wave of qualitative research. The Wellcome Trust provided £560,000 to integrate a complementary mental health research component as part of data collection, including a lived experience module. Furthermore, new funding was secured from FCDO Ethiopia (£180,000) and Irish Aid (£96,000) for round 6 qualitative research in Ethiopia, to bolster R7 quantitative findings, and enable mixed-methods analysis.

Efficiency: Measures how well the programme converts inputs into outputs. YLAW has maintained a strong focus on efficiency in delivering research outputs. During the reporting year, 96 cumulative examples were recorded where Young Lives research contributed to publications and they have continued to maximise co-funding opportunities where possible. This includes a forthcoming joint publication with the Global Coalition to End Child Poverty (with UNICEF, Save the Children, and others). As reported in more detail in Year 5, the team ensured R7 data collection approaches were undertaken as efficiently as possible (completed in April 2024), including through using phone calls for efficient tracking of respondents, and a suite of training materials prepared ahead of fieldwork, considerably reducing the preparation time for conducting training activities and increasing the quality of training and fieldwork activities.

Effectiveness: Considers if the outputs are having the intended effects. The programme’s research continues to be applied by a range of policy and decision-making bodies at both national and international levels. Young Lives evidence directly informed the World Health Organization’s Guidance on mental health policy and strategic action plans, which include three citations from the programme. Research has contributed to changes in policies formulated by country governments, including efforts to secure the right to education for all children in Peru and to inform debates around ending child marriage in India. This demonstrates the programme’s effectiveness in translating research into tangible policy outcomes. There was a recommendation in last year’s annual review for Young Lives to review and strengthen effectiveness measures under VfM. The team have begun monitoring the application of Young Lives research by government and non-government decision-makers through an internal impact tracker.

Equity: Measures how fairly the programme benefits are distributed. Young Lives places strong emphasis on inclusive and equitable research practices. The programme monitors and reports on gender and geographic representation among contributors. In Year 6, 43% of contributors to peer-reviewed publications were from the Global South, with 38% identifying as female. For non-peer-reviewed outputs, 100% of contributors were from the Global South, and 50% identified as female. For the policy briefs, technical reports and headline reports published this year, 43% of contributors were from the Global South with 79% identifying as female. Country teams have all led on at least one of the peer-reviewed publications. The programme has made deliberate efforts to support female and early-career researchers and those based beyond the UK, including through methodological workshops and academic forums. In Ethiopia, academic breakfast meetings have provided a platform for early-career and female researchers to present their research findings and reflections on their experiences as female academics.

Assessment of whether the programme continues to represent VfM

The programme continues to deliver against the milestones and objectives set out in the theory of change. Based on the above assessment, and the return of YLAW research, the programme continues to represent good VfM.

The programme has successfully bid for co-funding, with two new funding streams this year: i) £200,000 seed funding from the University of Oxford Social Science Division to lay the foundations for the Young Lives Research Hub on Climate Change and Environmental Shocks; and ii) new funding from FCDO Ethiopia (£180,000) and Irish Aid (£96,000) to deliver a sixth wave of qualitative longitudinal data collection in Ethiopia (‘Qual 6’) focused on young people’s health and wellbeing in times of crisis. Both projects have been aligned with the YLAW no-cost extension, running for 15 months from Oct 2024 to Dec 2025. The team has been focused on fundraising activities and research applications to competitive grants to continue activities after December 2025, including to the Mastercard Foundation, Economic and Social Research Council, European Research Council, Medical Research Council, Jacobs-Levante Foundation and Spencer Foundation. The team is also working closely with the University of Oxford’s Development Office to identify opportunities to engage with a wide range of donors interested in supporting the Young Lives study moving forward. However, at the same time, the programme will need to shift to closing out activities to ensure there is sufficient time for these.

E: RISK

Overview of risk management

YLAW has an overall risk rating of MODERATE. After mitigation, the residual risks recorded by FCDO are: 5 moderate and one minor. Below is a summary by risk category:

Financial & Fiduciary (MINOR): Oxford University remains an experienced partner with a strong subcontracting capability and links to and oversight of country teams. Full transaction lists are provided to FCDO with Quarterly Statements of actual spend; YL Oxford spot check transactions and request supporting evidence where appropriate. Quarterly finance reports are reviewed by FCDO’s Programme Manager and Research Adviser before issuing payments.

Policy and Programme Delivery (MINOR): The conflict situation in Ethiopia has continued to fluctuate across the Tigray and Amhara regions over the course of the past year. This has been less of a risk in the reporting period as the R7 data collection has been completed but it is continued to be monitored through the programme’s enhanced security protocol.

Public Service Delivery & Operations (MODERATE): Diversification of revenue streams is an ongoing risk for the Young Lives research unit and team beyond the current programme. YL are mitigating this risk through a dedicated fundraising strategy, delivery plan and proactive engagement with potential funders.

Safeguarding (MODERATE): Safeguarding of staff is of paramount concern to YL, especially in FCAS such as Ethiopia. Oxford prioritise engagement with their in-country staff to ensure safety measures are in place to protect personnel. The Country Directors and Oxford Senior Management meet monthly to review Safeguarding. There is a clear protocol which underpins the training provided in country and within the consultation guides and fieldwork manuals provided to staff. This includes enhanced duty of care measures (incl. referral pathways) for both respondents and staff in case of emergency or where a need for support is identified. As YL research involves significant engagement with vulnerable people, a comprehensive safeguarding policy has been developed which is fully compliant with FCDO’s enhanced due diligence requirements. A code of conduct exists which is signed by all YL staff as well as regular mandatory training on safeguarding.

People (MODERATE): The YL team continues to work to secure further funding to maintain the institutional knowledge. However, as the programme enters this final year of funding with FCDO there is a significant risk of retention issues and being able to maintain key staff.

Strategy and context (MINOR): From a sustainability perspective, the programme is now within its final 12 months contractually and currently no funding has been secured for a subsequent phase. Broader reductions to the UK’s Official Development Assistance (ODA) budgets will have no impact on the funding for the current phase of the programme but significantly affect the likelihood of obtaining FCDO funding for future phases.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Programme Management and Governance: YL meet with FCDO on a monthly basis. The FCDO and YL Programme Managers meet monthly to specifically discuss risk, finances, recruitment, and programme management issues. FCDO use quarterly meetings as a high-level forum to discuss progress, strategic direction, technical queries, challenges and successes, and engagement opportunities.

YL internal Management Committee (consisting of senior Oxford staff and Country Directors) meet monthly. The aim of these meetings is to review fundraising opportunities, proposals, the risk register, and showcase and collaborate on work. An Advisory Board (consisting of specialist advisors[6]), also meets bi-annually to provide advice and challenge to YL based on presentation of research progress, emerging evidence, research findings, and developments of the programme’s influencing strategy and fundraising efforts.
[6] Advisory Board Members include: Paul Glewwe, Jere Behrman, Agnes Quisumbing, Nicola Ansell, Deborah Levison, Tatek Abebe, Pauline Rose. FCDO are observers.

Commercial: FCDO hold an Accountable Grant with YL for £9.4m. This was signed in December 2019 and amended in November 2021 to allow for a no-cost extension to March 2025 due to delays associated with the pandemic. FCDO agreed a further no-cost extension until March 2026 to allow YL to deliver enhanced research and produce a legacy report of key findings emerging from 25 years of Young Lives research on Employment, Education and Skills, Health and Wellbeing and Family Lives, plus other activities which would significantly improve the quality of YLAW impact.

Financial Management: This year, YL spent £1.456m against the initially planned budget of £1.449m, an overspend of £7,000 which is less than 1% of an overall variance. There were fluctuations against forecast during the year and the average across the four quarters was 4.3%. This is a very positive position and was impacted by delays in confirming budget allocations in year. There have been delays in submitting the invoices due to staff changes within the partner’s organisation, however that has not caused any issues for programme delivery. Details of the budget compared to spend by quarter below:

	Q1 24/25	Q2 24/25	Q3 24/25	Q4 24/25	Total
Forecast	£349,000	£341,000	£354,000	£413,000	£1,449,000
Actual spend	£357,000	£347,000	£322,000	£430,000	£1,456,000
Variance	2.29%	1.76%	9.04%	4.12%	0.48%

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Progress and performance are monitored through the YL Logframe. Updates are submitted quarterly and the logframe (including milestone targets) is reassessed biannually. The annual review process assesses performance against these and makes recommendations based on learning from the previous year. YL uses its internal management, Steering Committee and advisory board meetings to reflect on its approach, survey design and results.

Evidence and learning

The Young Lives India Country Director presented on disability-inclusive research methodologies used in Young Lives at an internal FCDO seminar as part of the Research and Technology Department’s efforts to strengthen disability inclusion in research programmes.

As Young Lives enters the final phase of its current programme, several lessons have emerged from its approach to longitudinal, mixed methods research and policy engagement. The successful completion of Round 7 data collection, alongside low attrition rates, highlights the value of long-term, trust-based partnerships with in-country research teams and communities. For the year ahead, a priority will be to consolidate and share these lessons widely. This will not only support sustainability and sharing of relevant lessons with other research programmes but also help to position Young Lives as a strong example of evidence to impact in global research.

Date of last narrative financial report	10 June 2025	Date of last audited annual statement	24 March 2025