Contribution Arrangement Amendment Letter

Project Name: Delivering cash assistance to refugees through WFP's food assistance programme in Jordan
Project Number: 301109-401

I refer to the Contribution Arrangement between the Government of the United Kingdom of Great Britain and Northern Ireland acting through the Foreign, Commonwealth, and Development Office (“FCDO”) and the World Food Programme (“WFP”) signed on 20 March 2024 and amended by the Amendment Letter 1/2024 signed on 13 August 2024, the Amendment Letter 2/2024 signed on 18 December 2024 and the Amendment Letter 1/2025 signed on 8 April 2025 (“Contribution Arrangement”).

Following recent discussions, FCDO proposes to increase the amount made available to WFP pursuant to the Contribution Arrangement by £5,500,000 (Five million five hundred thousand pounds sterling).

I propose that the “£23,000,000 (Twenty-three million pounds sterling)” in paragraph 1(e) of the Contribution Arrangement be deleted and replaced with “£28,500,000 (Twenty-eight million five hundred thousand pounds sterling).”

In addition, with regard to the disbursement schedule in paragraph 1(g) of the Contribution Agreement, I propose to uncheck the option “The contribution will be transferred in full” and instead check the following option, with the schedule revised as follows: “The Contribution will be transferred in accordance with the following schedule:

	Payment due date	UK £/Amount
1.	April 2024	£7,000,000
2.	September 2024	£7,000,000
3.	December 2024	£5,000,000
4.	April 2025	£4,000,000”
5.	June 2025	£5,500,000

This letter of amendment will place on record our common understanding of the above change and will come into operation on the date you sign your confirmation below. This letter of amendment will be known as Amendment No. 2/2025.

The terms and conditions of this letter of amendment shall be incorporated in the Contribution Arrangement as though set forth in full therein. Except to the extent specifically amended or superseded by the terms of this letter of amendment, all of the provisions of the Contribution Arrangement shall remain in full force and effect to the extent in effect on the effective date hereof. The Contribution Arrangement, as modified by this letter of amendment, constitutes the complete agreement between FCDO and WFP and supersedes any prior written or oral agreements, writings, communications or understandings of FCDO and WFP with respect to the subject matter hereof.

Please sign both copies of this letter; return one to me and retain the other for your own records.

Signed on behalf of FCDO:
Name:
Position:
Address/Contact Details:
Date:

Signed on behalf of the Partner
Name:
Position:
Address/Contact Details:
Date: