## Annual Review Template

Title: Strengthening Societal and Economic Resilience in Jordan (SSERJ)
Programme Value £ (full life): £95m		Review date: June 2025
Programme Code: 301109	AMP start date: 13 March 2022	AMP end date: 30 April 2027

Summary of Programme Performance
Year	2023	2024	2025	2026	2027
Overall Output Score	A	A	A
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	SSERJ Business Case and Summary / SSERJ Business Case Addendum
DevTracker Link to results framework:	SSERJ Logframe

A. SUMMARY AND OVERVIEW

Description of programme

The Strengthening Societal and Economic Resilience in Jordan (SSERJ) programme, valued at £95m, spans from March 2022 to April 2027. It aims to deliver life-saving humanitarian assistance to Syrian refugees and strengthen Jordan’s social protection system. It is contributing towards achieving the UK Foreign Secretary’s humanitarian, human capital, migration and security priorities. It also aligns with the British Embassy Amman’s Country Business Plan and its campaign goal of enhancing the societal and economic resilience of vulnerable Jordanians and refugees, fulfilling our humanitarian obligations, and fostering social cohesion in Jordan.

The programme has several main elements. First, it is providing essential support to Jordan in hosting a significant refugee population. Jordan is a lower-middle-income country. Since 2012, it has hosted around 1.3 million Syrians and 2.4 million Palestinians refugees. It hosts the second-highest share of refugees per capita in the world, putting pressure on its budgetary and natural resources, infrastructure and labour market. The SSERJ programme is providing life-saving cash assistance to the most vulnerable refugees and host communities to meet our humanitarian obligations, supporting Jordan’s stability and helping prevent unsafe onward migration to Europe and the UK.

Second, in addition to providing immediate assistance, the programme is also working to promote refugee self-reliance and help strengthen the contribution of refugees and vulnerable Jordanians to Jordan’s economy in line with the Jordan compact[1]. It is doing so through enhancing the evidence and promoting the self-reliance of refugees and vulnerable Jordanians and helping extend social protection coverage to these groups. It is also supporting greater alignment of humanitarian and social protections systems. Through working across the humanitarian-development nexus the programme is thus both working to meet immediate needs and pursuing longer term development and sustainability of UK support, with the goal of benefiting refugees and Jordanians alike.
[1] The Jordan Compact represents a new approach to refugees agreed between Jordan and the EU which was signed at the London Conference in February 2016. The compact agreed that in return for billions of dollars in grants and loans and preferential trade agreements with the EU that Jordan would improve access to education and employment for the Syrian refugees it is hosting.

Third, it is working to help the Government of Jordan (GoJ) to build an inclusive, shock responsive and sustainable social protection system. The aim of this is to enhance Jordan’s social and economic resilience which is critical to enable vital economic reforms and maintain stability. It aims to enhance the protection of the most vulnerable which is part of a mature economic development strategy and is important for the delivery of Jordan’s Economic Modernisation Vision (2022-2033)[2]. It is also a core element of a renewed and more sustainable social contract between the state and its citizens.
[2] https://www.jordanvision.jo/en

SSERJ continues to be delivered through its eight components as below:
- Delivering cash assistance to refugees through the World Food Programme (WFP) food assistance programme in Jordan.
- Delivering cash assistance to refugees through the United Nations High Commissioner for Refugees (UNHCR) cash programme in Jordan.
- Economic and inclusion research and evidence.
- FCDO two technical experts' deployment to UNHCR.
- Financial assistance (FA) to the GoJ currently supporting the Estidama++ programme[3].
  [3] Estidama++ Fund – Extension of Coverage and Formalization (Formerly called “Emergency Unemployment and Employment Stabilisation Fund (EUESF)”). The MoU for this project was signed in May 2022 and is implemented by the Social Security Corporation on behalf of the GoJ. The objective of the project is to strengthen the situation of vulnerable workers in Jordan, including refugees, through the extension of workers’ social protection rights, access to a coverage reward and contribution subsidies, and registration in the social security system.
- Technical assistance (TA) for both policy development and system strengthening (the TA Facility is named ‘Shamil’).[4]
  [4] Shamil is a demand-led social protection technical assistance facility delivering analysis, advice and capacity building activities for the GoJ. Shamil is a consortium led by Development Pathways with two national partners, the Arab Renaissance for Democracy (ARDD) and MMIS Management Consultants, and which also draws in additional expertise as required. FCDO oversees Shamil’s work through quarterly programme board meetings, regular bi-weekly catch ups, and reviewing narrative and financial reporting.
- TA support through the International Labour Organisation (ILO), to Jordan’s Social Security Corporation’s (SSC) Estidama++ programme.
- Monitoring, evaluation, and learning (MEL).

Summary supporting narrative for the overall score in this review
The programme scored an A in this year’s annual review. This score is given since the programme met expectations in all four of its outputs. This annual review is covering the period from April 2024 to March 2025. The past year was the third year of the SSERJ programme and accordingly activities have largely moved from their inception phase to a maturer implementation phase, with a corresponding increase in results generated during this year.

Humanitarian programme partners reached their targets of providing 310,000 (via WFP) and 214,000 vulnerable individuals (via UNHCR) with timely humanitarian support to meet their basic needs. The Estidama++ programme significantly increased the number of participants enrolled in the scheme, reaching a total of 40,556 participants which exceeds the end target for the programme of 34,000 participants. It also significantly exceeded its goal of 30% non-Jordanian participants. Shamil provided TA to a range of Government institutions across diverse topics, helping strengthen Jordan’s social protection system in multi-faceted ways. FCDO UHNCR secondees and the Refugee Self-Reliance Initiative generated high-quality evidence to inform policy dialogue in support of the economic inclusion of refugees and other vulnerable groups in Jordan.

Despite positive progress, the programme also encountered several challenges in reaching its output milestones meaning a higher rating is not awarded. For Estidama++, the target gender ratio was not achieved. For Shamil activities, a lack of a host-government focussed strategy and difficulties in securing buy-in from some stakeholders meant that certain planned activities couldn’t be completed or undertaken.

Major lessons and recommendations for the year ahead

Reduced international finance necessitates a revised humanitarian approach. Most UN donors reduced funding commitments this year, affecting the scale and sustainability humanitarian assistance for Syrian refugees in Jordan. In this context the British Embassy Amman should consider how to offer the most effective support, including through predictable multi-year financing and capitalising on a cross-Mission approach and clearly articulated engagement strategy. It should also continue to work with UN partners in Jordan to support and encourage them to continue to adapt their strategies in a proactive way in line with the UN80 reform process. These strategies should continue to evolve prioritising efficiency, advocacy, and sustainable support mechanisms and they should pursue diversified donor engagement and stronger collaboration with local actors to help them continue to meet needs in this context. The FCDO team in Amman will take a proactive and flexible approach to engaging with the UN reform process (known as the UN80 Initiative), including the Humanitarian Reset Initiative and broader restructuring efforts. Through both existing and new programming, the team will support the development of more coherent, accountable, and locally led humanitarian structures. As co-chair of the Humanitarian Donors Group, the FCDO will use its convening role to strengthen donor coordination, align financing with reform priorities, and support the Resident Coordinator system in delivering more integrated and effective humanitarian responses at the country level.

The British Embassy Amman should continue to support the diversification of financial sources for aid to continue to meet needs. In the context of reduced international finance, the British Embassy Amman should continue to explore broader financing options to support the diversification of financial sources for aid. Prospective financial sources could include non-traditional donors, partnerships with private foundations, and new public-private partnerships in specific areas. The aim of this will be to help the GoJ avoid the impact of severe cuts that disproportionately affect refugees and other vulnerable groups. The British Embassy Amman has begun supporting this type of work through the green financing initiative delivered via WFP (under output 4) and it should seek to build on this type of work further.

Protection, health and WASH services have also been reduced and require attention. The sharp decline in international financing—exacerbated by recent U.S. funding cuts has severely impacted the delivery of essential services to refugees in Jordan and the wider region. These reductions, combined with cuts to cash and food assistance (currently the primary focus of the SSERJ programme), are converging to create a rapidly deteriorating humanitarian situation and pending crisis. Without swift and coordinated intervention, the most at-risk populations will face escalating harm. In this context, health services are too critical to fail. Continued UK engagement is essential to prevent further deterioration and to uphold the UK’s global leadership in humanitarian response. The British Embassy Amman will continue to engage with humanitarian actors to ensure that broader needs are addressed. This includes advocating for a flexible, multisectoral approach in future UK humanitarian programming in Jordan—one that aligns with FCDO priorities on resilience, stability, and long-term development. Such an approach must adapt to the evolving landscape and meet the full spectrum of community needs. This should be pursued alongside efforts to promote durable solutions and self-reliance, supporting a sustainable long-term strategy that enables a responsible exit from humanitarian aid while continuing to meet basic needs and prioritise life-saving support.

Negative coping strategies amongst refugees are increasing. Despite WFP and UNHCR meeting their output targets, reduced international finance has coincided with worsening economic conditions in Jordan. The proportion of Syrians facing basic needs vulnerability has not significantly improved—in fact, most Syrian households still struggle to meet basic needs. This has led to an increase in negative coping strategies amongst refugees including child labour, child marriage and debt accumulation. This can lead to a loss of human capital, public discontent and vulnerability to exploitation – drivers of instability. The British Embassy Amman should continue to ensure international partners are monitoring these trends and they are factored into their decisions around the humanitarian response.

New prospects of return to Syria require British Embassy Amman/international response. The change in Syrian Government during the past year has presented new prospects of return for Syrian refugees in Jordan. A large proportion of refugees remain hesitant about returning[5], and only 65,680 have returned since December 2024, and as such there is a need to prepare for their return while continuing to meet needs in Jordan. British Embassy Amman should continue to use its role as co-Chair of the Humanitarian Donor Group (alongside Germany) to ensure that the international community continues to monitor and respond to the support required for the safe and dignified return of refugees. The British Embassy Amman should also continue to work with the GoJ, other donors to Estidama++ and participants in the Social Protection Donors Group to advocate for social security contributions, including for Estidama++ participants, to be able to be easily withdrawn by refugees returning to Syria and to understand how debt is affecting returns. British Embassy Amman Advisers should continue working closely with MENA Syria response teams and explore the options around the establishment of regional knowledge-sharing platforms.
[5] https://www.unhcr.org/media/flash-regional-survey-syrian-refugees-perceptions-and-intentions-return-syria

The British Embassy Amman should continue to encourage a focus on the future of Estidama++. Initial evidence suggests that Estidama++ is successfully attracting vulnerable workers to participate in social security and transition to regular social security at its end and is thus making a positive impact and contribution towards UK priorities. FCDO should continue to work with other donors to encourage the SSC, with support from the ILO, to prioritise during the rest of Estidama++ developing and pursuing a plan to enable the continuation of the scheme after its end in February 2026. This should work towards the goal of it becoming a permanent part of the SSC with a sustainable financing model.

The effectiveness of efforts to build refugee self-sufficiency through including them in national social security systems require continued monitoring. Estidama++ has shown that refugees can be successfully included in Jordanian social security systems – enabling them to achieve self-sufficiency when combined with decent work. However, the British Embassy Amman should continue to work with the SSC, International Labour Organisation and other partners to monitor the impact of changes to work permits on this trend and mitigate any negative trajectories should these arise.

The British Embassy Amman should continue to engage with and support the SSC’s strategic reforms. The ILO, via Estidama++, has provided technical assistance to the SSC to set out a comprehensive reform agenda via its future vision white paper. Proposed reforms could enhance the effectiveness of Estidama++ and also encourage more vulnerable workers, including refugees, to participate in social security without a subsidy. British Embassy Amman Advisers should engage technically with the SSC’s reform process to encourage such reforms to be made in an effective way. The British Embassy Amman should also consider continuing to provide technical assistance to the SSC to make these reforms after Estidama++ finishes if budgets permit.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The SSERJ theory of change (ToC) sets out that the programme’s intended impact is that societal and economic resilience and stability is maintained in Jordan. To achieve this, it is working towards the long-term outcome that Jordan has social protection systems (national and a parallel system for refugees) that help all individuals address risks across the lifecycle and from shocks, empowers women and persons with disabilities and generates economic growth and a stronger social contract.

The ToC articulates that this impact and long-term outcome will be achieved through four main streams of work or outputs and pathways that seek to support vulnerable Jordanians and refugees:
1. Humanitarian cash transfers will be disbursed to the most vulnerable refugees. This critical social safety net enables them to meet their basic needs, contributing to greater income security across the population and through this leading to greater social and economic resilience.
2. Vulnerable workers (majority Jordanian, but also refugees) will be encouraged to join the Estidama++ scheme through which they’ll be provided with subsidised social security. This will help strengthen Jordan’s social protection system by enabling it to better cover and formalise vulnerable workers.
3. Technical assistance (TA), evidence and advocacy will be provided to promote inclusive social protection in Jordan and generate demand for it. This will build the awareness of the decision makers and stakeholders of the value of an inclusive, multi-tiered and shock responsive social protection system and support them to put this in place which will strengthen the resilience of vulnerable Jordanians and refugees.
4. Evidence and TA will also be provided to build an understanding of and demand for the economic inclusion of refugees, women and persons with disabilities. This effort seeks to stimulate policy discussions on how the labour market can offer more opportunities for these groups, leading to enhanced income security and greater societal and economic resilience.
These workstreams are, in addition, being supported by diplomatic and engagement activities of the British Embassy Amman.

The SSERJ programme’s intended impact has remained consistent with that set out and approved in the original business case. In 2023/2024, as reported in the last annual review, the Theory of Change (ToC) was refined in various ways. Firstly, it was expanded to include the additional humanitarian streams of work - humanitarian cash transfer and evidence generation and TA on the economic inclusion of refugees - which were approved through a business case addendum in 2023. It was also enhanced through the provision of a more detailed causal pathway, with increased detail in particularly on the short and medium-term outcomes essential for instigating change. Indicators have also been reassessed and refined to ensure a robust measurement framework for each phase of change. The ToC has remained relevant and not been updated over the past year.

During 2025 the British Embassy Amman is pivoting its portfolio – including in response to the move to 0.3% Official Development Assistance. This will lead to changes in the output activities. These will include relating to the early completion of the Shamil technical assistance facility. With the completion of financial obligations to SSC, and the upcoming end of the current Estidama++ pilot programme in February 2026, it is also expected to lead to a shift away from financial aid to technical assistance/systems strengthening activities. The ToC will be updated in line with these changes. Output 4 of the ToC should also be updated with the language on the economic inclusion of refugees amended to a broader approach of ‘self-reliance’ as it better reflects the political realities in Jordan while still ensuring work is addressing the protracted humanitarian-development challenges through ‘durable solutions’ which are win-win. The ToC will also evolve through an adaptive approach as the programme progresses, to ensure its continued relevance.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The SSERJ programme is now at its mid stage of implementation enabling an initial assessment to be made on whether it is on track to contribute to the expected outcomes and impact. The picture as stands is mixed. Social protection impact and outcome indicators are considered on track. However humanitarian outcome and impact indicators are largely off track due to contextual factors beyond the control of the programme. The programme is still considered to be making an important and positive contribution towards them.

In terms of social protection aspects, data on all outcome indicators is positive. First, Estidama++ is exceeding targets for the number of participants transitioning to regular social security at the end of the scheme- an important metric as it suggests a lasting impact to this scheme. Second, meaningful dialogue is taking place around the institutionalisation of Estidama++ in the SSC. Third, several policy and administrative changes following UK technical assistance have been adopted by Jordan to strengthen their social protection systems. For example, ILO has supported SSC to make changes to strengthen its grievance processes. At impact level, recent data is not currently available on the proportion of the population with social protection coverage – but it is understood this is on a positive trajectory. Estidama++ is making a positive contribution towards this and changes such as the non-contributory pension which Shamil have also engaged around will do so further.

In terms of the achievement of the impact and outcome level objectives, it is important to note that the integration of refugees within certain parts of the national social protection system (for example the tax-financed National Aid Fund) remains not permitted by the GoJ. Currently, the main area where refugees can be included in national social protection systems is in the social security system. As such engagement with SSC is key to extending social protection coverage to refugees to promote self-sufficiency and to make progress towards our humanitarian aid exit strategy. Given the GoJ position, support to refugees not able to work and participate in social security is needed via parallel humanitarian systems and this programme responds to this position via supporting humanitarian systems as well as social protection systems to achieve the impact/outcome. This should be made clearer in future updates to the ToC. Building more comprehensive and stronger national social protection systems, even parts not currently open to refugees, is still important to the objectives of the programme as this helps build resilience for Jordanians and supports Jordan’s stability- also key to our intended impact.

Given the significance of social security in being inclusive of refugees and a route for building their self-sufficiency in line with our humanitarian exit strategy, it is necessary that the impact of increases in social security costs and refugee work permit waiver removal are closely tracked. At present Estidama++ has been a successful pilot with positive results, however, should any negative impacts be observed (which they haven’t yet been) the FCDO team in Amman should work to mitigate them, for example through engaging with the SSC’s structural reform process.

In terms of humanitarian activities, the programme aims to help achieve the outcome of more resilient and sustainable food practices and a reduction in the proportion of refugees meeting needs for basic and domestic items from humanitarian assistance. The aim of this is to have the impact of reduced vulnerability amongst registered refugees, as measured by the proportion of Syrians with high or severe basic needs vulnerability and debt.

Unfortunately, there has been a deterioration in humanitarian[6] indicators since the beginning of the programme and baseline data from 2021 and 2022. Data from the 2024 VAF (collected in late 2023) shows income levels among refugees were lower than two years ago. Similarly, food security has deteriorated with acceptable food consumption dropping in 2023 compared to 2021 (85 to 64% in Azraq camp and 88% to 75% in Zaatari camp and 57% to 54% amongst Syrian refugees living in host communities). Negative food coping strategies are increasingly being used. At the impact level, poverty rates amongst registered refugees increased to 67% in 2023 from 57% in 2021. Similarly, debt levels have been rising and are particularly high for refugees living in host communities. UK humanitarian assistance under SSERJ begun in 2023 as such mostly was delivered after this data was collected. However, these concerning trends are reinforced by recent UNHCR data from Q2 2024, which shows increasing negative coping strategies and persisting high levels of debt and are reinforced by our understanding of trends from engagement with humanitarian partners.
[6] In 2021, 70% of Syrians faced high or severe basic needs vulnerability. As of 2025, the situation remains challenging, with 93% of Syrian households reporting they cannot meet basic needs on their own.

These negative trends are being driven by decreasing donor humanitarian assistance for refugees and global and regional conflicts. However, SSERJ is still considered to be a positive force within this challenging external context and the deterioration of indicators points to an even greater need for UK support. In response, as noted in the previous section, the British Embassy Amman will take the following action: try as far as possible to commit multi-year spending; encourage the UN to diversify donor engagement; pursue innovative finance partnerships; pursue multi-sectoral humanitarian approaches and continue to build refugee self-reliance including through sustainable livelihood opportunities and their inclusion in national social protection systems.

Over the coming year several changes are expected to be made to the programme. The proportion of UK finance SSERJ delivers is likely to be increased to humanitarian components to help offset the deteriorating conditions facing refugees. As envisioned in the business case, the social protection activities the programme is engaged in are also being reviewed at its mid-point.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Given the progress to date and contribution to the ToC, the SSERJ programme should continue. SSERJ represents good value for money based on available data. It remains relevant to delivery of the impact, outcomes and key outputs outlined in the ToC. The programme is yielding positive results at the output level, significantly exceeding some targets, and is well placed to deliver further results in the coming year.

Impact and outcome indicators are positive for social protection aspects suggesting a positive contribution to resilience and stability in Jordan. Impact and outcome indicators have seen some deterioration for humanitarian components due to contextual changes, in particularly the decline of international financing. However, the programme is contributing positively towards these, preventing further deterioration than there otherwise would be. As such, in this context it is more important than ever that the programme continues to provide life-saving cash assistance. Given the protracted nature of the refugee crisis in Jordan it also remains important that, while prioritising cash assistance, work to build self-reliance amongst vulnerable individuals through economic opportunities and social protection also continues. This is needed to promote sustainability in the approach to supporting refugees in Jordan and our long-term exit strategy from humanitarian aid while meeting immediate needs.

The SSERJ programme is delivering against the FS’ priorities of: ‘Development’, via supporting humanitarian and human capital objectives; ‘Migration’, via supporting individuals to stay in their region of origin and preventing unsafe onward migration; and ‘Security’ via contributing to stability in Jordan and the Middle East. It is well-aligned with the British Embassy Amman’s Country Business Plan as well as the overarching mission of the UK in Jordan, by supporting the campaign goal of enhancing the societal and economic resilience of vulnerable Jordanians and refugees, fulfilling our humanitarian obligations, and fostering social cohesion in Jordan. The programme contributes to mitigating drivers of instability, i.e. the macro-economic reforms are showing impact at the micro-economic level with shrinking household incomes for Jordanians and shrinking cash payments to refugees. Coupled with a significant youth population and high unemployment rates, these factors highlight the importance of the programme in fostering a more stable environment. Furthermore, by improving government services the programme aims to strengthen the social contract between citizens and the state. The programme is also seeking to mitigate the impact of shocks, including climatic shocks, which have the potential to destabilise. As regional instability continues, these aims remain key.

The SSERJ programme complements other programmes of British Embassy Amman including its education programming. It supports broader UK objectives around the self-reliance of vulnerable Jordanian’s and non-Jordanians, as well as empowering women and girls and people with disabilities, and strengthening resilience to climate change, which are important strategic priorities for the UK in Jordan. It is also contributing to UK priorities around migration, through meeting needs locally, and to security objectives. Lessons from SSERJ will inform new humanitarian, education and social protection programming under development.

## C. DETAILED OUTPUT SCORING

Output Title	Disbursement of Humanitarian Cash Transfers to the most vulnerable Refugees in Jordan
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s)	Progress
1.1 Number of reached refugees with cash assistance through WFP / add new/old supported HH in the disaggregation.	310,000[7]	310,000
1.2 Number of people who received cash assistance (unique individuals) through UNHCR	214,000[8]	214,000
[7] docs.wfp.org/api/documents/WFP-0000165416/download/
[8] UNHCR Jordan_2024 Annual BN Programme Assessment Report_FINAL (3).pdf

Briefly describe the output’s activities and provide supporting narrative for the score.

Over the reporting period, both WFP and UNHCR continued to effectively deliver humanitarian assistance to refugees in Jordan, despite a constrained operating environment characterised by continued funding shortfalls and rising needs. WFP provides targeted food assistance to the most vulnerable refugees particularly those without access to income or employment through cash-based transfers, enabling them to meet their basic food needs. In parallel, UNHCR delivers multi-purpose cash assistance to similarly vulnerable households, allowing them to cover a broader range of essential needs, including rent, healthcare, and hygiene. These complementary approaches strengthen the humanitarian response by addressing both sector-specific and cross-cutting needs, while promoting dignity, choice, and self-reliance among refugee populations.

These milestones reflect the total caseload managed by UN partners. Through UK support, WFP reached over 332,791 unique beneficiaries[9] while an additional 86,152 refugees were assisted under UNHCR’s caseload.[10]
[9] The figures for UK supported beneficiaries (332,791) are higher than the total caseload (310,000) due to different metrics used. The WFP targets a maximum of 310,000 beneficiaries per month – leading to the 310000 annual figure- but the unique individuals receiving support (as counted in terms of UK support) varies each month leading to a higher number of unique individuals supported over the course of a year than monthly targets. The UK is the third largest donor to WFP in Jordan contributing to the 310,000 figure.
[10] The overlap between the two figures is considered around 90%.

WFP continued to implement its 2023–2027 Country Strategic Plan, focusing on providing unconditional food assistance and supporting national social protection systems. With UK contribution for 2024/2025 financial year, WFP reached over 310,000 refugees (144,350 females and 165,650 males, including 17,971 persons with disabilities) through digital cash-based transfers. These transfers allowed beneficiaries to meet essential food needs, albeit at a reduced level due to cuts in transfer values (from USD 32 to USD 21 per person). Despite difficult trade-offs, WFP was able to reprioritise the most vulnerable, including by suspending assistance for 100,000 refugees based on an evidence-based targeting exercise. Outcome monitoring indicates a worsening in food security, particularly in early 2024, with an increase in severe food insecurity, child labour, school dropouts and debt accumulation among refugee households. WFP responded by reinforcing monitoring efforts and piloting qualitative assessments to inform more targeted support.

Cash for food assistance is crucial because it empowers refugees to make their own purchasing decisions, ensuring they can access culturally appropriate and nutritionally diverse foods that meet their specific needs. This flexibility helps maintain dignity and autonomy, allowing families to prioritize their expenditures based on immediate necessities. Additionally, cash assistance stimulates local economies by increasing demand for goods and services, fostering economic growth and resilience within host communities. Given the ongoing challenges highlighted in the Food Security Outcome Monitoring (Q4 2024 report), such as severe food insecurity and barriers to legal employment, cash assistance remains a vital tool in supporting the basic survival and self-reliance of vulnerable populations. Cash assistance is recognised as one of the best buys in refugee response, delivering cost-effective, dignified support that strengthens local markets and aligns with FCDO objectives on value for money, resilience, and sustainable impact.

UNHCR maintained its core protection and assistance functions for refugees, delivering multi-purpose cash assistance to vulnerable refugee households across Jordan. With the British Embassy Amman’s support, UNHCR was able to uphold cash transfer coverage for over 86,152 refugees (46,534 females and 39,618 males, including 9,206 persons with disabilities), helping them meet basic needs such as rent, food, and health. UNHCR also advanced efforts in protection monitoring, case management, and outreach, particularly for persons with specific needs, including persons with disabilities. However, the agency faced similar budget constraints, leading to reduced coverage and limited ability to meet all identified needs. UNHCR also enhanced inter-agency coordination and accountability to affected populations, including through improved feedback mechanisms and community engagement.

The principal challenge across both agencies remains chronic underfunding, which has limited the scale and quality of assistance and forced difficult reprioritisation decisions. The wider economic context—including rising living costs, limited job opportunities, and inflation—has further compounded refugee vulnerability. Both agencies also reported increased reliance on negative coping strategies among refugees, highlighting the need for stronger integration between humanitarian assistance and longer-term livelihood support.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Both the WFP and the UNHCR have revised their outcome monitoring frameworks and programme approaches. The number of refugees supported has been adjusted using the new beneficiary selection criteria introduced in 2023, alongside changes to transfer values, which have been reduced by both agencies.

The WFP has updated its key performance indicators and adjusted its food security analysis to reflect deteriorating conditions. Meanwhile, the UNHCR has enhanced its vulnerability assessment model and refined targeting based on household-level data. Despite these changes, neither agency has altered the strategic objectives or core components of the British Embassy Amman’s funded projects. Both agencies have adopted adaptive management approaches to maximise impact in a constrained environment.

Programme milestones have been revised in the overarching programme logframe following the 2024 annual review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The findings and recommendations from the last annual review were shared with both agencies. Follow-up discussions were included in the quarterly meetings and field monitoring visits to the camps and host communities.

Lessons learned and recommendations for the year ahead:

- Reduced international finance necessitates a revised humanitarian approach. Most UN donors reduced funding commitments this year, affecting the scale and sustainability humanitarian assistance for Syrian refugees in Jordan. In this context the British Embassy Amman should consider how to offer the most effective support, including through predictable multi-year financing and capitalising on a cross-Mission approach and clearly articulated engagement strategy. It should also continue to work with UN partners in Jordan to support and encourage them to continue to adapt their strategies in a proactive way in line with the UN80 reform process. These strategies should continue to evolve prioritising efficiency, advocacy, and sustainable support mechanisms and they should pursue diversified donor engagement and stronger collaboration with local actors to help them continue to meet needs in this context. The FCDO team in Amman will take a proactive and flexible approach to engaging with the UN reform process, including the Humanitarian Reset Initiative and broader restructuring efforts. Through both existing and new programming, the team will support the development of more coherent, accountable, and locally led humanitarian structures. As co-chair of the Humanitarian Donors Group, the FCDO will use its convening role to strengthen donor coordination, align financing with reform priorities, and support the Resident Coordinator system in delivering more integrated and effective humanitarian responses at the country level.
- Integrating Contingency Planning into UN Humanitarian Strategy: The ongoing UN reform and humanitarian reset initiatives offer a critical opportunity to rethink how international actors respond to protracted displacement. As part of these, and connected to the point above, the British Embassy Amman should work with the UNHCR and WFP in Jordan to encourage them to move beyond reactive communications on underfunding and instead present forward-looking strategies that are aligned with these reform efforts. This includes integrating contingency planning into programme design through scenario analysis, prioritisation frameworks, and mechanisms to sustain core services during funding disruptions. Long-term planning should connect immediate humanitarian needs with resilience-building and regional stability goals. Supporting refugees through targeted interventions prevents harmful coping mechanisms such as child labour and radicalisation, strengthens social cohesion, and contributes directly to national and regional stability. Therefore, such a shift would enable more strategic donor engagement and improve the overall effectiveness and sustainability of refugee responses.

The British Embassy Amman should continue to support the diversification of financial sources for aid to continue to meet needs. In the context of reduced international finance, the British Embassy Amman should continue to explore broader financing options to support the diversification of financial sources for aid. Prospective financial sources could include non-traditional donors, partnerships with private foundations, and new public-private partnerships in specific areas. The aim of this will be to help the GoJ avoid the impact of severe cuts that disproportionately affect refugees and other vulnerable groups. The British Embassy Amman has begun supporting this type of work through the green financing initiative delivered via WFP (under output 4) and it should seek to build on this type of work further.

Protection, health and WASH services have also been reduced and require attention. The sharp decline in international financing—exacerbated by recent U.S. funding cuts has severely impacted the delivery of essential services to refugees in Jordan and the wider region. These reductions, combined with cuts to cash and food assistance (currently the primary focus of the SSERJ programme), are converging to create a rapidly deteriorating humanitarian situation and pending crisis. Without swift and coordinated intervention, the most at-risk populations will face escalating harm. In this context, health services are too critical to fail. Continued UK engagement is essential to prevent further deterioration and to uphold the UK’s global leadership in humanitarian response. The British Embassy Amman will continue to engage with humanitarian actors to ensure that broader needs are addressed. This includes advocating for a flexible, multisectoral approach in future UK humanitarian programming in Jordan—one that aligns with FCDO priorities on resilience, stability, and long-term development. Such an approach must adapt to the evolving landscape and meet the full spectrum of community needs. This should be pursued alongside efforts to promote durable solutions and self-reliance, supporting a sustainable long-term strategy that enables a responsible exit from humanitarian aid while continuing to meet basic needs and prioritise life-saving support.

Negative coping strategies amongst refugees are increasing. Despite WFP and UNHCR meeting their output targets, reduced international financial has coincided with worsening economic conditions in Jordan. The proportion of Syrians facing basic needs vulnerability has not significantly improved in fact, most Syrian households still struggle to meet basic needs. This has led to an increase in negative coping strategies amongst refugees including child labour, child marriage and debt accumulation. This can lead to a loss of human capital, public discontent and vulnerability to exploitation – drivers of instability. The British Embassy Amman should continue to ensure international partners are monitoring these trends and they are factored into their decisions around the humanitarian response.

New prospects of return to Syria require British Embassy Amman/international response. The change in Syrian Government during the past year has presented new prospects of return for Syrian refugees in Jordan. A large proportion of refugees remain hesitant about returning, and only 65,680[11] have returned since December 2024. As such there is a need to prepare for their return while continuing to meet needs in Jordan. British Embassy Amman should continue to use its role as co-Chair of the Humanitarian Donor Group (alongside Germany) to ensure that the international community continues to monitor and respond to the support required for the safe and dignified return of refugees. British Embassy Amman Advisers should continue working closely with MENA Syria response teams and explore the options around the establishment of regional knowledge-sharing platforms.
[11] UNHCR website: Voluntary Returns of Syrian Refugees from Jordan Microsoft Power BI Figure represents the number of voluntary returns by Syrian refugees in Jordan between 8 December 2024 to 10 May 2025.

Output Title	Vulnerable workers (Jordanians and refugees) and businesses informed about and join the social security scheme through the Estidama++ programme
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
No. of individuals benefiting from income support (coverage reward) and/or contribution subsidies who were previously not covered/registered with SSC (disaggregated by gender, nationality, wage, age, sector).	At least 34,000 total / Gender ratio: 34% / Nationality ratio: Agriculture sector 90:10; all other sectors 70:30 / (reporting against targets for 2024)	40,556 total / Gender ratio: 21% female/79% male. / Nationality ratio: 47% Jordanian/53% non-Jordanian. 30% of participants were Syrian refugees.
No of participants reached in outreach and information sessions (Age, sex, migrant status)	At least 600 participants reached each year	606 participants
Percentage of targeted vulnerable workers and employers who receive information on Social Security (Age, sex, migrant status, sector, employment type) and no. of messages sent to male and female vulnerable workers.	100%. / At least 100,000 messages exchanged each year.	100% / 328,629 messages were sent to workers to inform them about registration and payments and more than 51,204 conversations via WhatsApp chatbot were exchanged with existing E++ beneficiaries

Briefly describe the output’s activities and provide supporting narrative for the score.

A score of 'A' has been given as two results significantly exceeded their targets: the number of individuals benefitting from income support/contribution subsidy and messages exchanged with vulnerable workers. Impressive progress has also been made in achieving a high ratio of non-Jordanians/Syrians participating following donor feedback. The target gender ratio was not achieved but it is felt that the level of success in the other indicators warrants this rating.

This output aims to support the formalisation of Jordan’s labour market and enhance the resilience of vulnerable workers, including women and refugees, by supporting the extension of social security coverage to vulnerable groups through the Estidama++ programme. It does this by providing income support (coverage rewards) and subsidising social security contributions to vulnerable groups for a defined period of time (18 or 12 months).[12]
[12] Estidama++ launched in May 2022 and is funded by the UK, Netherlands, and Norway

The Estidama++ project is managed by the SSC, with technical support from the ILO. The implementation of the Estidama++ project’s phase 1 opened in October 2022, running for 18 months, and the phase 2 window was open for applications from September 2023-February 2025, with benefits running for participants for 12 months. The British Embassy Amman participates in joint governance and reporting under the Estidama++ governance structure.

Estidama++ has moved into a mid-stage of implementation over the last year and the results achieved have significantly accelerated over this period. The SSC, with the support of the ILO, had achieved the enrolment of 40,556 total beneficiaries as of December 2024. This is a significant increase in participants from the last annual review where 10,416 workers participated in the scheme. It exceeds the milestone target of 34,000 of this review and end target of the programme. According to projections the programme is on track to reach 46,490 beneficiaries by its end, exceeding the target without additional finance.

In addition to meeting the milestone for the number of individuals enrolling on Estidama++ this year, a further success has been the continued increase in the share of non-Jordanian enrolment. This aspect of the programme was weak in the first SSERJ annual review but following considerable positive efforts by SSC and ILO in response to the British Embassy Amman/donors’ feedback, it has now exceeded targets for enrolling 30% non-Jordanians; 58% of participants at Q3 2024 were non-Jordanians (including refugees and migrant workers) of which 24.9% were Syrian. That said, the programme has performed less positively on gender (21.5% female participants versus a target of 34%). More work is needed through the programme to determine why and put in place mitigations.

There has been a continued focus on outreach and awareness made by SSC/ILO over the past year, guided by a well-structured strategy, towards the purpose of strengthening social security awareness and increasing Estidama++ registration rates. Digital communications reached more than 428,000 users, had 3.3 million views, involved 328,629 messages sent to workers, and 51,204 WhatsApp chatbot conversations with Estidama++ beneficiaries. In person engagement provided 606 participants with social security information. Estidama++ registration reached 11,000 in the two months after a media push showing its positive impact.

Despite much positive progress, the programme continued to experience some challenges. As noted in last year’s review changes to the social security tranche[13] system have meant that costs of contributing to social security have increased. Registration amongst self-employed Jordanians, as well as women, as highlighted above was lower. Efforts to increase outreach and support registration in these groups were pursued.
[13] The tranche system previously provided options on social security pension coverage level and associated payment amount. Options were (10%, 25%, 50%, 75%,100%). The SSC legislative changes made in January 2023 apply only to self-employed (and those on flexible work permits) as these were the workers paying the full social security contribution of 21.75% themselves and therefore the theory was that they may benefit from tranche options that would lower the overall contribution rate. The change removed the tranche system and reinstated the obligation to pay the full 21.75% (100%) noting that most refugees chose the 10% option and thus will face a rising cost when moved to the 100%.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The output indicators remain consistent with last year’s annual review.

Regarding the activities undertaken under this output, the SSC and ILO continued to adjust their activities in response to emerging findings and lessons learned, aiming to enhance the impact of the programme. For example, by revising the eligibility criteria for self-employed workers.

The timeline for the Estidama++ programme was extended, with the end date moving from October 2025 to February 2026. The purpose of this was to keep the application window for phase 2 open for longer to enable more beneficiaries to participate and use the available finance.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

An important recommendation from last year’s review was to provide increased attention to the lessons from this pilot programme and to identify the changes needed to institutionalise the Estidama++ programme within the SSC. The SSC, with support from the ILO, has initiated work on this as part of work to set out its future vision in a white paper. As part of this white paper, the SSC has undertaken extensive dialogue with Government and international partners and proposed plans to institutionalise a contribution subsidy mechanism which is positive.

A further recommendation was to understand attrition rates (how many beneficiaries drop out before the end of the programme). As of the end of 2024, 1,602 participants prematurely discontinued their involvement in phase 1 and 7651 in phase 2. Thus 9,253 out of 40,556 (20.4%) participants had left the scheme early. Rates were highest amongst the self-employed and workers in construction, real estate and agriculture. Women were also twice as likely as men to drop out, which is connected to the prevalence of short-term contracts in the education sector where many women work. Field monitoring found the main cause was work contracts ending and employers halting contributions rather than programme dissatisfaction. This highlights that social security and the subsidy need to be compatible with temporary/seasonal work and communication with employers and employees is key. The British Embassy Amman should continue to encourage SSC/ILO to continue to understand and respond to attrition.

Another recommendation was to monitor the proportion of participants who transition to regular social security after the end of the subsidy, a key outcome level metric of the success of the programme. As of the end of 2024, 85% of 5,471 participants who had finished Estidama++ transitioned to social security compared to the target of 60%. Initial data is thus positive, but more time is needed to fully observe rates given phase 2 is still underway. Refugees, however, as noted above could dropout at the end of phase 2 due to the work permit waiver removal (although a new waiver for agricultural workers is under discussion). No negative impacts on Estidama++ from this waiver removal have been observed at present and Estidama++ is showing positive results but transition rates should be closely followed over the coming year and mitigations pursued as needed. Mitigations would include engaging with the SSC’s structural reform process which is expected to introduce changes to social security that will incentivise participation and thus could help offset any negative trends if they are observed. The UK also participated in an international taskforce which analysed and engaged around these changes last year. The UK can use the relationships generated through this work to support further advocacy on this topic as needed.

Lessons learned and recommendations for the year ahead:

- Ensure social security preparedness for Syrian refugee return. Over the past year, new prospects for the return of refugees in Jordan to Syria have arisen. The British Embassy Amman should continue to work with the GoJ, other donors to Estidama++ and participants in the Social Protection Donors Group to ensure that social security contributions, including for Estidama++ participants, can be easily withdrawn or transferred for refugees returning to Syria and to understand how debt is affecting returns.
- The effectiveness of efforts to build refugee self-sufficiency through including them in national social security systems require continued monitoring. Estidama++ has shown that refugees can be successfully included in Jordanian social security systems – enabling them to achieve self-sufficiency when combined with decent work- in line with our humanitarian aid exit strategy. However, the British Embassy Amman should continue to work with the SSC, ILO and other partners to monitor the impact of changes to work permits on this trend and mitigate any negative trajectories if observed to ensure that as many refugees as possible are able to achieve self-sufficiency via decent work and social security.
- Continue to monitor attrition and transition rates of Estidama++. Attrition levels (number of dropouts) and the proportion of participants transitioning to regular social security at the end of the scheme are key factors determining the success of Estidama++. Initial data is positive but these rates need to be closely monitored over the remainder of the programme and responded to quickly should they go off track.
- Address barriers to women and other hard to reach groups in social security. As noted earlier, there has been a notable drop in rates of participation of women and also challenges around inclusion of self-employed workers and those in agriculture, real estate and construction. The barriers to these groups participating should be fully understood and mitigations put in place for the remainder or the programme and future iterations of the scheme.
- Ensure disaggregation of data on participants by disability. The SSC is not yet able to disaggregate data on participants in Estidama++ by disability status. It should continue to work to do so to enhance reporting.

Output Title	Provision of TA, evidence and advocacy builds an understanding of, and demand for inclusive and shock responsive SP and the efficiency/VfM benefits of aligning national and humanitarian systems
Output number:		3	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
No. of analyses (e.g. political economy), evidence-based and good practice resources, and strategies produced, routinely updated, and disseminated where appropriate.	ILO- 1 global evidence study on contribution subsidies / Shamil - The Capacity Needs Mapping (CNM) and other analysis provides the foundation for TA annual work plans. CNM, Political Economy Analysis (PEA), Stakeholder Strategy and Communications Strategy updated annually. / Shamil (social security) - At least 6 resources/products provided by Shamil to the GoJ and stakeholders (cumulative) / Shamil (social services) - At least 2 resources/products provided by Shamil to the GoJ and stakeholders (cumulative)	ILO- A global study on contribution subsidy, with data from 26 countries. / Completed a CNM for the Ministry of Finance. PEA updated on a quarterly basis using Everyday Political Economy Analysis framework. / Shamil (social security)- 44 (cumulative) resources provided to GoJ (policy papers and presentations) (28 achieved this year) (Details in Annex 1) / Shamil (social services)- 10 resources provided to GoJ (policy papers and presentations) (Details in Annex 1)
No. of capability building sessions for GoJ officials and wider stakeholders relating to inclusive social protection and number of GoJ staff trained.	ILO- 3 capacity building sessions on extension of coverage held with support of the project and 20 social security staff trained to conduct outreach activities each year (reporting on 2024). / Shamil (social security)- At least 8 (cumulative) sessions provided by Shamil to the GoJ and stakeholders, to at least 12 different stakeholders (cumulative). At least 110 GoJ staff trained; 50% women and 1% persons with disabilities. / Shamil (social services) - At least 2 sessions provided by Shamil to the GoJ and stakeholders, to at least 4 different stakeholders (cumulative).	ILO- 6 outreach training workshops for over 134 SSC staff. / Shamil (social security)- 41 (cumulative) sessions to 38 different stakeholders (cumulative) (23 sessions achieved this year). The Global Disability Summit MENA pre-summit and side-event on disability-inclusive social security were attended by approximately 200 and 500 participants from national and international government and non-government organisations (Details in Annex 1) / Shamil (social services)- 6 capacity building activities to 19 different stakeholders (Details in Annex 1)
No. of new or strengthened system elements including e.g. MIS, SOPs, knowledge sharing platforms, payment systems etc. that are GESI sensitive	Shamil (social security) - At least 1 system element strengthened. / Shamil (social services) - Detailed scoping of current social services system capacity is completed.	Shamil (social security)- 7 system elements strengthened / Shamil (social services)- Scoping could not be completed. Draft reports produced on: / 1. Professionalisation of Social Work in Jordan: Vision and Roadmap / 2. Scoping study of Jordan social work / 3. Final reports and presentations on assessments of 3 different sub-system elements were completed (Details in Annex 1)
No. of policy dialogue engagements on inclusive social protection (social security and social services) that are delivered to key stakeholders across GoJ that are GESI sensitive	Shamil (social security)- At least 20 (cumulative) policy dialogue engagements organised by Shamil with the GoJ and stakeholders. / Shamil (social services) - At least 10 policy dialogue engagements organised by Shamil with the GoJ and stakeholders.	Shamil (social security)- 79 (cumulative) policy dialogue engagements / 43 in 2024 (Details in Annex 1) / Shamil (social services)- 15 policy dialogue engagements (Details in Annex 1)

Briefly describe the output’s activities and provide supporting narrative for the score.

The ILO and Shamil exceeded most of their milestone targets. However, one milestone was not achieved leading to an ‘A’ rating being assigned.

Estidama++/ILO
Over the past year, the ILO has continued to provide valuable technical assistance to the SSC in the design and implementation of Estidama++ and foster a productive relationship with them. They have supported the SSC to focus not only on exceeding target enrolment numbers, but also on strengthening SSC systems and generating research to inform future work.

ILO’s support over the past year has continued to help the SSC strengthen their internal systems. This has included supporting the SSC to update Standard Operating Procedures to streamline registration and grievance processes and enhancing grievance management procedures. The ILO also supported SSC to build its capacity to implement the project. This involved providing targeted training to 134 SSC members through 6 sessions focused on improving communication skills, particularly for engaging workers in the informal sector.

ILO has also supported SSC in launching the Visioning White Paper – a strategy to guide the future of Jordan’s social insurance system. It has helped SSC outline reforms, including with the aim of extending coverage to all workers, and engage with the GoJ and partners to receive feedback and generate buy in. ILO has closely coordinated work with the World Bank and IMF. This is important work which has the potential to enhance social security in multifaceted ways including: institutionalising Estidama++ and increasing the efficacy of a subsidy, extending the coverage of social security and improving the long-term financial sustainability of the SSC. It highlights that Estidama++ is not only a pilot contribution subsidy initiative, but also a driver and catalyst for ambitious long term social security reform.

ILO continued to implement the Estidama++ Monitoring, Evaluation, Research and Learning agenda and framework. This involved quarterly field monitoring and external validations and progressing two Randomised Control Trials (RCTs). The first RCT assessed whether information campaigns effectively drive business registrations for social security. The second is measuring the impact of the financial subsidy as well as a child benefit in attracting participation. A comparative study on global best practices with data from 26 countries was completed. Additional studies included an actuarial valuation, joint study with the World Bank on barriers to extending coverage and study on the social protection systems readiness for climate change.

The main challenges over the past year relating to the ILO have remained a lack of timely reporting. Quarterly reports for donors have often been late, in part due to SSC capacity.

Shamil
Technical assistance associated with this output was also provided through Shamil in line with their year 1 workplan. Shamil exceeded or significantly exceeded most of their milestone indicators this year. They provided technical assistance to multiple Government ministries relevant to social protection on a variety of topics, helping strengthen national social protection systems in a multifaceted way (see Annex 1 for their progress details). That said it should be noted that policy engagements counted include activities/meetings so not all may meet the full definition of policy engagement.

Shamil received particularly positive feedback in relation to their work for the Higher Council for the Rights of Persons with Disabilities who valued their support for Jordan in co-hosting the Global Disability Summit. Their support to the National Council for Family Affairs (NCFA) to help launch the National Strategy of Older Persons, which helped achieve a commitment to a social pension for the elderly was also a particular highlight of work.

Shamil has also experienced a number of challenges this year. Most notably, Shamil faced reputational and strategic risks regarding the lack of acceptance of Shamil's proposed strategy from some stakeholders. As a result, several activities could not be completed, including a formal governance structure established, and a milestone indicator not being met. The regional conflict also posed a challenge to the recruitment and mobilisation of consultants.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The timeline for ILO technical support was extended, with the end date moving from October 2025 to February 2026. The purpose of this was to maintain ILO’s ability to provide technical support in line with the extended SSC dates for the Estidama++ programme.

It was decided this year that the British Embassy will pivot its development spend which will result in the early completion of the Shamil Technical Assistance Facility. The remaining months of Shamil will be focused on a responsible exit from activities.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Shamil made continuous efforts to enhance coordination with other stakeholders however this remained challenging given the various approaches to social protection in Jordan. Recommendations for the year ahead are:

The British Embassy Amman should continue to encourage a focus on the future of Estidama++. Initial evidence suggests that Estidama++ is successfully attracting vulnerable workers to participate in social security and transition to regular social security at its end. The British Embassy Amman should continue to work with other donors to encourage the SSC, with support from the ILO, to continue to focus on developing and pursuing a plan to enable the institutionalisation of the scheme within the SSC after its end in February 2026. This should work towards the goal of it becoming a permanent part of the SSC with a sustainable financing model with SSC financing.
The British Embassy Amman should continue to engage with and support the SSC’s strategic reforms. The ILO, via Estidama++, has provided technical assistance to the SSC to set out a comprehensive reform agenda via its future vision white paper. Proposed reforms could enhance the effectiveness of Estidama++ and also encourage more vulnerable workers including refugees to participate in social security without a subsidy. British Embassy Amman Advisers should engage technically with the SSC’s reform process to encourage such reforms to be made in an effective way. The British Embassy Amman should also consider continuing to provide technical assistance to the SSC to make these reforms after Estidama++ finishes if budgets permit.
- The British Embassy Amman should continue to press for timelier Estidama++ reporting. The British Embassy Amman should continue to work with the ILO and SSC to encourage timely and quality reporting.
- Shamil should focus on responsible exit. Following a pivot in the British Embassy Amman’s portfolio Shamil will close over the coming year. Moving forwards the British Embassy Amman should work with Shamil to ensure that ongoing activities are completed successfully and sustainably, that completion is implemented in a way which provides value for money, and that successes and lessons learnt are captured and communicated.

Output Title	Evidence generation, dissemination and TA to decision makers which builds an understanding and demand for enhanced economic inclusion of refugees, women, and people with disabilities
Output number:		4	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of evidence base and good practice resources and products generated and disseminated to key stakeholders including GoJ on economic inclusion (including labour market access by refugees)	UNHCR - At least 2 evidence products completed / Shamil (economic inclusion) - At least 1 resources/products provided by Shamil to the GoJ and stakeholders (cumulative)	UNHCR secondees: / Completed World Bank SWIFT poverty profile on refugees (March 2025). / Econometric analysis of the skills mapping survey. Published infographics on Higher education, non-Syrians' skills ICT, construction, agricultural sectors. / Survey on informal refugee businesses in Zaatari camp. / Provided evidence for refugee work permits recommendations. / IGC grant on cash assistance; MoU signed with Bentley and Emory. / UNHCR Socio-economic Survey: two reports, one-pagers, dashboards. / Contributed to UNHCR socio-economic update reporting: two reports (Q2 & Q4 2024). / Provided data for Annual report. / Shamil completed a Jordan Labour Market Briefing Note.
4.2 Number of capability building sessions for GoJ officials and wider stakeholders and number of GoJ staff trained relating to the challenges faced by women and persons with disabilities in accessing jobs.	N/A	N/A
4.3 Number of policy dialogue engagements on inclusive labour market outcomes that are delivered to key stakeholders across GoJ that are GESI sensitive	Shamil (economic inclusion) - At least 5 policy dialogue engagements organised by Shamil with the GoJ and stakeholders	Shamil held 9 policy dialogue engagements on the topic of economic inclusion. These were with the following institutions: National Aid Fund (1); Ministry of Labour (4); Social Security Corporation (3); Head of the Crown Prince Foundation (1).
4.4 Number of refugees matched to income-generating activities through the two-way referral system.	by June 2025: 2250	Results were: / 4,500 refugees referred for jobs through partnerships with national institutions, NGOs, and private sector companies. / Up to 2,000 refugees positioned to be referred to IT sector opportunities through the Ministry of Digital Economy and Entrepreneurship (MoDEE) initiative.
4.5 Number of people equipped with the skills needed to increase their readiness to participate in the labour market (disaggregated by age, gender, nationality, disability)	by June 2025: 370	Total reached: 429. / - 199 (158 females and 41 males) farmers and MSMEs[14] trained in climate-smart agriculture, increasing awareness of climate risks and resilience strategies. / - 20 Agricultural Credit Corporation (ACC) loan officers capacitated in climate adaptation financing and project evaluation, enhancing ACC’s role as a sustainable finance partner. / - 150 stakeholders (120 refugees, 30 institutions) surveyed, providing evidence on refugee access and attitudes toward agricultural finance. / - 60 youth trained in entrepreneurship, identifying agri-food challenges and proposing innovative, market-informed solutions.
[14] Micro, Small, and Medium Enterprises (MSME)

Briefly describe the output’s activities and provide supporting narrative for the score.
This output continues to drive forward efforts to strengthen the economic inclusion of refugees, women and people with disabilities in Jordan by generating high-quality evidence, delivering technical assistance, and informing policy dialogue. It is delivered via two experienced FCDO Advisors (an Economist and Statistician) which are seconded into the UNHCR, WFP on the Refugee Resilience Initiative, and the Shamil social protection technical assistance facility. The output has been scored ‘A’. This reflects in particularly the strategic impact of UNHCR deployments and the impressive early progress of the refugee self-reliance initiatives.

The programme has significantly advanced economic inclusion outcomes, with 4,500 refugees referred to job opportunities through partnerships with national institutions, NGOs, and the private sector—surpassing the target of 2,250 matches by June 2025—and up to 2,000 refugees positioned for IT sector roles through the Ministry of Digital Economy and Entrepreneurship. Additionally, 429 individuals, including women, youth, and refugees, have been equipped with market-relevant skills in climate-smart agriculture, entrepreneurship, and inclusive finance—exceeding the target of 370—thereby enhancing their readiness to participate in the labour market and contribute to sustainable economic growth.

Technical support to UNHCR
The focus of the FCDO Economist seconded to the UNHCR has been on generating evidence to inform Jordan’s future refugee response. Aims have included enhanced engagement between humanitarian and development actors; improved transparency; and strengthened participation of affected people. This work directly supports the objectives of the Grand Bargain by fostering stronger collaboration between humanitarian and development actors, particularly through joint evidence generation and policy engagement with national institutions. The transparency of the data and analysis—such as the refugee economic contribution estimates—enhances accountability and informed decision-making. Moreover, by highlighting the skills and economic potential of refugees, the initiative strengthens the participation of affected populations in shaping policies that impact their lives, aligning with the Grand Bargain’s commitment to making humanitarian action more inclusive, effective, and sustainable.

A key achievement over the past year has been the publication of evidence products that stemmed from a Refugee Skills Mapping project supported by UK aid. This was completed in partnership with the UNHCR and WFP and provided deep dives on the profile of refugees with a higher education, non-Syrians and those working in the agriculture and ICT sectors. It also involved working with WFP and the Boston Consulting Group to provide analysis on the current economic contribution of refugees to the Jordanian economy (estimated at 2.2% of GDP). The evidence produced has directly informed engagement with the Prime Ministry on inclusive labour market policies.

In addition to the skills mapping project, the deployed FCDO Economist has ensured effective strategic oversight of the Refugee Self-Reliance Initiative and generated a range of other useful evidence and analysis products to support the self-reliance of refugees. This has included completing a World Bank SWIFT poverty profile on refugees, publishing infographics on non-Syrians' skills and sectors, finishing a policy note on refugee businesses and Zaatari camp market study and providing evidence for refugee work permits recommendations. Their expertise has been pivotal in strengthening evidence-based decision-making and shaping policy responses.

The FCDO Statistician deployed to UNHCR has contributed towards this output through providing strategic technical advice to guide UNHCR Jordan towards being more efficient consumers of data. As a result, UNCHR has improved about 20% of the outcome and impact data it monitors. This data is published, is used in proposals and reporting to donors, and in accountability discussions between UNHCR and their funders, and as such FCDO support has driven improvements in the use and allocation of UNHCR resources. The secondee is also helping UNHCR staff to make linkages between UNHCR’s activities to data on outcomes and impacts, which is particularly important given the sharp reductions in aid spending.

The statistician was also pivotal in ensuring the outreach of the socio-economic survey- a key UNHCR product which provides information on refugee circumstances- was much broader and deeper than previous surveys. This helped UNHCR reach a wide range of development partners and implementers so partner dialogue about the refugee situation is more strongly evidence based. They improved the quality and ease of production of figures for advocacy purposes, providing the strategic view of the refugee situation and how their situation was evolving, which UNHCR use with key partners including the Government of Jordan. The statistician has made improvements in the quality of the both the socio-economic survey and the socio-economic update, ensuring the dialogue in Jordan is based upon robust figures. While evidence alone may not drive policy change especially given the complex political landscape, it remains a vital foundation for informed dialogue and sustained engagement.

Shamil
Labour market policies form an important component of social protection. Shamil has contributed to building an understanding and demand for enhanced economic inclusion of refugees, women, and people with disabilities through creating a Jordan labour market briefing. It also held 9 policy dialogues with senior stakeholders of relevant Government Ministries and institutions as follows: National Aid Fund (1); Ministry of Labour (4); Social Security Corporation (3); Head of the Crown Prince Foundation (1). These meetings helped build relationships and discuss areas in which Shamil could provide technical assistance to support their priorities. In the case of the Ministry of Labour and Social Security Corporation, Shamil report that the engagements helped inform thinking on how a multi-tiered social security model can support workers (for example how a tax financed pension tier can support workers in the informal economy) and can help extend coverage across the population. They also report they informed thinking on how disability benefits can support people with disabilities to engage in the labour market by compensating them for the extra costs resulting from disability.

Activities under indicator 4.2 were agreed to be postponed to the following year following challenges in recruiting suitable personnel to take forward activities.

Refugee Self-Reliance Initiative

The British Embassy Amman signed a new contribution agreement with WFP on 14 November 2024 for a new and experimental phase of work aimed at advancing the self-reliance of refugees in Jordan. This phase builds on previous year’s refugee skills mapping exercise and introduces innovative, long-term livelihood interventions designed to enhance refugees’ economic participation and resilience. It pursues our objectives of promoting long term sustainability in how Jordan hosts refugees and is part of our humanitarian exit strategy. At the same time, it is working to achieve UK climate objectives and is bringing in private partnerships into the delivery of support for refugees, in line with the recommendation above on the need to support the diversification of aid sources in Jordan.

Through a collaborative partnership between WFP and UNHCR, this initiative pursues climate-resilient, and inclusive livelihood models. This aims to build upon a predominantly humanitarian cash assistance model by complementing it with approaches that aim to strengthen long-term sustainability, self-reliance, and dignity for affected populations. Through this component, the UK is supporting WFP in piloting a comprehensive package of experimental initiatives, including:
- Climate-smart agriculture trials, introducing sustainable farming techniques adapted to Jordan’s arid conditions.
- Deployment of renewable energy solutions, such as solar-powered irrigation systems, to reduce dependency on fossil fuels.
- Vocational training programs aligned with emerging green economy sectors, equipping refugees with skills for future-oriented jobs.
- Financial inclusion initiatives, including access to microfinance and digital banking tools, to support entrepreneurship and savings which have been enabled through partnerships with private lenders.
- In addition to building skills, these initiatives are designed to actively match refugees with income-generating opportunities particularly in sectors such as climate-smart agriculture, renewable energy, and small-scale enterprise development ensuring that training translates into tangible economic outcomes.
The refugee skills mapping exercise has been instrumental in tailoring these interventions. By generating detailed profiles of refugee skillsets; including those preparing for voluntary return to Syria; it has provided a robust evidence base to inform programming and support reintegration planning.

In parallel, a British Embassy Amman-supported financial inclusion study engaged 120 refugees and 30 financial institutions to explore how refugees can transition from cash-based assistance to climate-resilient livelihoods. The study offered valuable insights into financial behaviours, investment readiness, and market participation pathways.

To further stimulate local economic development, WFP and Cewas[15] delivered entrepreneurship training to 60 Jordanian and Syrian youth across Mafraq, Jerash, Ajloun, and Irbid. Participants identified local agri-food challenges, conducted market research, and developed innovative, community-driven solutions.
[15] Cewas Middle East is the regional branch of Cewas Global, a Swiss non-profit organisation that supports innovation in water and sanitation and other environmental sub-sectors. Cewas offers professional training, coaching, mentorship and market development interventions for green innovators and entrepreneurs while creating improved market opportunities for innovations in water and sanitation, solid waste management, agri-technology, and energy.

Despite staffing shortages and funding constraints, WFP has made notable progress in testing and scaling new models of refugee self-reliance. These efforts represent a bold reimagining of humanitarian programming, integrating climate resilience, financial inclusion (through access to green finance), and innovation into refugee and host-community livelihoods. This approach contributes to longer-term economic stability and sustainable development across northern Jordan and demonstrates UK support towards the climate-refugee nexus. It is part of our approach of pursuing sustainable approaches while meeting immediate needs.

Policy engagement

In addition to these programmatic activities under SSERJ, the British Embassy Amman has pursued refugee self-reliance priorities through diplomatic channels expanding further the UK’s role as an influential actor in Jordan’s refugee and economic policy landscape. This has included its Co-Chair position in the Humanitarian Donors Group. This platform has strengthened the UK’s ability to shape and influence policy decisions and proven effective in lobbying for enhanced refugee economic inclusion and resilience.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The SSERJ logframe has been amended to incorporate the new contribution to the refugee self-reliance initiative, as part of the new phase following the skills mapping project.

Due to the fall of the Assad regime, the UNHCR deployees were flexibly used to generate vital evidence on the socio-economic characteristics of refugees returning to Syria. This included developing questions in the SWIFT poverty survey to look at refugees’ intentions to return, the impact of financial barriers such as debt[16]. The UNHCR/WFP skills mapping data provided evidence on the skills profile of refugees returning to Syria and contributing to the regional refugee returns intentions survey, which explores barriers, needs and intentions for refugee return. This work has supported data driven approaches to future reconstruction efforts and has been shared with key development partners in the region.
[16] In 2025, debt remains a major issue, with many refugees relying on informal loans to cover essential expenses.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

In last year’s review, no recommendations were made for this output, as work was at initial stages.

Lessons learned and recommendations for the year ahead:

The UK’s investment in evidence generation and policy dialogue continues to position it as a credible and influential actor on refugee self-reliance in Jordan. Sustained investment in refugee skills data and evidence is essential. Government stakeholders respond positively to well-evidenced, constructive dialogue. Progress is incremental and depends on long-term relationship building. The British Embassy Amman should continue to engage with the GoJ through trusted platforms and relationships, using evidence to inform and influence policy constructively. Impact is maximised when paired with consistent follow-up and targeted engagement by the British Embassy Amman team.
Technical secondees have delivered significant added value and demonstrated strong value for money. They have contributed to improved strategic policy engagement and programme delivery.
- A clear focus on priorities remains key. The programme remains ambitious in scope, covering a range of thematic areas. However, delivery capacity and funding remain key constraints. Maintain a clear focus on areas where UK support delivers the greatest added value—namely, evidence generation, technical advice, and policy engagement. Streamline the scope of outputs to concentrate on fewer, high-impact areas, reflecting current resource availability.
- Strengthen coordination across UK-funded partners to improve alignment and ensure complementary approaches to economic inclusion.
Credits and loans have increased access to finance, but gaps remain. The Refugee self-reliance has shown that zero-interest loans have improved access to finance for smallholder farmers and agribusinesses. However, gaps remain in tracking beneficiary numbers, loan amounts, and livelihood impacts. Moving forward the project should embed a robust M&E framework within credit access schemes and innovation pilots to improve strategic alignment and support evidence-based scaling of successful initiatives. It should also capture focus group insights, particularly for refugee IT employment tracks, to strengthen programme responsiveness. Ongoing engagement with technical leads is essential to mitigate risks and seize opportunities.
Climate adaption innovations are proving effective. The refugee self-reliance Initiative innovation pilots have improved climate finance access for refugees and vulnerable groups. Prioritising scalable solutions, such as eco-friendly cooking and sustainable energy, will strengthen resilience outcomes.
## D: VALUE FOR MONEY

Key cost drivers and performance

The business case outlined that the inception phase of the programme will develop a VFM strategy. The key cost drivers remain those identified in the inception phase, namely admin fees, average cost per consultant, travel and subsistence costs. In delivering humanitarian support- cash assistance per beneficiary is the key cost driver. Partners (ILO/SSC and Shamil) have established VfM frameworks and metrics and are reporting on these annually with shorter updates provided quarterly for Shamil. The UN agencies currently do not provide FCDO VFM analysis.

VFM performance has improved through the review period, with implementing partners deploying useful cost containment measures and no-cost extensions giving ILO, SSC and WFP longer to deliver results. Over the past year, the British Embassy Amman has contributed £5.2m to the SSC, £647,006 to the ILO, £1.9m to Shamil, £19.5m to UNHCR and £19m to WFP.

In terms of cost drivers, the primary costs associated with funding to WFP/UNHCR were cash transfers to beneficiaries. Similarly, for Estidama++ a key cost was the direct payments to project participants for social security coverage rewards and contribution subsidies which represented 90% of expenditure (excluding research costs). For Shamil, the greatest cost driver has been the TA fund (47%) and staffing costs (33%).

A further difference between components, relevant to cost drivers, relates to the British Embassy Amman’s mode of selecting their implementing organisations. The SSC, ILO, WFP and UNHCR were all chosen due to their position as Government and international organisations with unique mandates that could not be replicated by other organisations. Shamil, by contrast is formed from private sector organisations and was chosen through a competitive procurement process.

VfM performance compared to the original VfM proposition in the business case

The SSERJ programme continues to embed value for money across the 5E’s of FCDO’s value for money framework in all programmatic decisions.

Economy

For the humanitarian component, cash transfers remain the primary cost driver, ensuring direct support to beneficiaries with minimal overhead. The efficiency gains from digital delivery mechanisms, including iris biometric verification, further enhance economic value by reducing fraud risks and operational inefficiencies[17]. The British Embassy Amman’s contribution to WFP financed cash transfers for beneficiaries reached 281,218 direct recipients in total, making 15 JOD payments. UNHCR’s cash assistance for basic needs reached 228,178 beneficiaries in 2024 and the British Embassy Amman’s contribution to UNHCR reached approximately 86,000 beneficiaries between April and December 2024. Around 90% of WFP and UNHCR cash assistance beneficiaries overlap. The British Embassy Amman is contributing a 6.5% administrative fee to WFP, which represents good value for money compared to international benchmarks.
[17] Social Protection & Jobs, policy and technical note. March 2024, No 33.

Comparative studies, including findings from UNHCR cash assistance across the Middle East and North Africa (MENA) highlight how cash transfers have been instrumental in addressing protection risks and ensuring basic needs are met[18]. The evidence continues to highlight the cost-effectiveness of cash transfers over in-kind assistance, with unrestricted cash proving 25–30% more economical. As mobile money adoption grows and financial literacy improves, these benefits are expected to expand, with upfront training costs yielding long-term impact.
[18] https://jordan.un.org/sites/default/files/2022-01/UNHCR%27s%20Cash%20Assistance%20and%20Protection%20Outcomes%20in%20MENA.pdf

The British Embassy Amman continues to finance Estidama++ through two separate channels. It provides financing to the ILO to provide technical assistance support to the SSC to deliver Estidama++ in line with international best practices. ILO use this finance for staffing costs, project procurements and their 13% management fee. The management fee is in line with many other UN agencies and is deemed value for money. The British Embassy Amman continued to provide finance directly to the SSC, which is used for coverage rewards and to subsidise social security contributions for Estidama++ beneficiaries. Providing this finance directly to SSC, instead of via ILO, enables the British Embassy Amman to avoid paying management fees and the creation of parallel systems – representing good economy.

The Estidama++ programme has procured a total of 266 contracts, which is an increase from 178 contracts procured last year. To measure VfM, ILO tracks the number of Request for Quotation (RfQ) and number of Requests for Proposal (RfP) procurement processes followed as a percentage of all contracts issued to gauge the competitiveness of the project’s procurement process. As of December 2024, less than 5% of contracts were made through Direct Selection – a positive indicator of economy. The contracts used included: contracts for services (e.g. research, producing communications such as videos, and venue bookings), contracts for external collaborators (e.g. consultants, translators, photographers), and contracts for goods (e.g. laptops for the project team).

Shamil benchmarked key cost items against comparable programmes to ensure VFM. The project’s Non-Project Attributable Costs (NPAC) were maintained at 4.9 per cent of total expenditure, well below the FCDO average of 6.5 per cent[19]. Shamil implemented several measures to increase economy. This included hybrid delivery formats for workshops and events, which significantly lowered venue and hospitality expenses without reducing stakeholder reach. Interpretation and translation services were brought in-house or handled by bilingual team members, that saved an estimated £1,000 per report and £500 per event. Shamil’s office relocation was deliberately delayed, extending use of a lower-cost space and saving approximately £3,700 over the quarter (Q3).
[19] Source: Cost Recovery: What is means for CSOs, Bond 2016, https://www.bond.org.uk/wp-content/uploads/2022/03/cost-recovery-0216.pdf p10

Efficiency

There is consensus that cash generates cost efficiency gains in the humanitarian system and provides greater choice and dignity while at the same time stimulating local markets[20]. By leveraging financial infrastructures and bypassing intermediaries, assistance reaches refugees faster while reducing inefficiencies associated with in-kind aid and voucher schemes. According to the latest progress reports, 88% of the UK’s contribution to WFP and 91% of contributions to UNHCR effectively reached beneficiaries, demonstrating continued value for money. Digital wallets and remote data collection further optimize operations, reducing transaction costs and enhancing accessibility—particularly for women and persons with disabilities.
[20] K4D,,Cost-effectiveness in humanitarian work: cash-based programming, 2018

WFP and UNHCR have been leveraging mobile cash transfers to enhance the efficiency and reach of their humanitarian aid programmes. WFP's switch from voucher to cash distributions in host communities has facilitated timely and efficient delivery, keeping cost-transfer ratios at reasonable levels[21]. The average daily cost per beneficiary for cash-based transfers (CBTs) in 2021 was USD 0.50. UNHCR's Common Cash Facility (CCF) in Jordan has significantly reduced bank transfer fees from 2.5-5% to 1.67%. This reduction in fees, along with streamlined processes, has improved cost efficiency.
[21] Based on the report of evaluating WFP Jordan Country Strategic Plan 2020-2022

For Estidama++ cost-efficiency is measured by the total cost-transfer ratio (the total cost, including transfers, of delivering one dollar’s worth of transfer to a beneficiary), which was 1.11 in December 2024. When benchmarked against international social protection programmes this represents good VFM where total cost-transfer ratios range from 1.05 to 2.11 depending on the maturity, scale and type of social protection programme.

Shamil reports against a range of efficiency indicators.
- TA projects: MoF 2026-2029 strategy (£33,796), Long-term consultant embedded in the Department of Statistics (£84,757); National Data Centre support (£46,943).
- System strengthening: Scoping work for registration and licensing of social workers (£86,969), operational support and design of disability cash transfers (£22,180)
- Events: National strategy for Older Persons Launch (£48,644)
- Evidence and dissemination: Older persons strategy action plan (£35,940), Scoping Study on Family-Based Care (£16,003)
- Capacity building activities: person days costs for workshops ranged from £17 to £125 per person day cost. This includes GESI strategy support to Higher Council for the Rights of Persons with Disabilities for Global Disability Summit Side-Event on Disability-Specific Social Security (£196,714).

These activities and events are made up of TA fee rates and expenses. Where possible Shamil benchmarked key cost items and delivery structures against comparable programmes to ensure value for money and cost practicality. For instance, the set up of the International Growth Centre’s Office, as part of the Jordan Investment and Economic Reform Advisory Programme was used by Shamil to benchmark the cost of Shamil’s office set up.

Effectiveness

Cash transfers enable adaptive responses to evolving needs, ensuring timely aid delivery while fostering refugee agency. Monitoring of cash assistance underscores how the UNHCR basic needs programme emerges as a crucial lifeline, constituting 67% of refugees’ total income[22]. While the positive impact of the UNHCR basic needs programme on overall well-being is evident, the situation remains precarious, with 57% of families struggling to meet even half of their basic needs and 87% having resorted to emergency or crisis-driven coping strategies in the past 30 days. The complementary roles of UNHCR and WFP reinforce the effectiveness of interventions, and the organisations share the same targeting mechanism for beneficiaries. UNHCR's sectoral reach facilitates integration with broader programming, while WFP’s scale ensures optimized delivery at national levels. This dual approach enhances impact and sustainability.
[22] UNHCR Jordan: 2023 Basic Needs Cash Assistance Post Distribution Monitoring Report

For Estidama++ measures of effectiveness show a significant improvement over the reporting period and increased VFM. VFM effectiveness is measured as the sustainable transition into regular Social Security participation. The enrolment of beneficiaries in Estidama++ has more than doubled since March 2024 from 17,248 to 40,556 beneficiaries in December 2024. This is the result of concerted outreach efforts by ILO/SSC to increase awareness, including increased refugee participation in the scheme. During the same period, the number of Estidama++ beneficiaries that continue to pay into social security more than three months after their subsidy ends has increased from 9% to 86% of beneficiaries. The project is working to ensure the sustainability of results longer-term through outreach and awareness raising activities which build knowledge of the value of social security participation. Through supporting SSC’s reform process, changes will be put in place by SSC to further incentivise participation (e.g. via more attractive benefits packages).

Another measure of effectiveness is the percentage of Estidama++ beneficiaries that have received payment from SSC during a lifecycle contingency. This increased from 39% in March 2024 to 69% in December 2024. During the same period, the percentage of beneficiaries reporting perceived increased income security to deal with lifecycle contingencies increased from 42% to 52%.

Shamil’s activities were cost-effective through convening, demand responsiveness, systems integration and upstream policy framing—roles that could not be easily replicated. The disengagement of a key stakeholder mid-year limited delivery in that portfolio, but resources were reallocated to ensure additionality was preserved elsewhere.

Cost-effectiveness
Humanitarian cash transfers are proven to saves lives and is a FCDO best buy[23] and demonstrate good value for money. Evidence from Iraq and Jordan reinforces this: cash assistance allows households to prioritize expenditures, increases local purchasing power, and stimulates market activity. Multipliers of up to 2.5 indicate substantial economic benefits for host economies.
[23] FCDO Humanitarian ‘Best, Cash transfers when local markets are functioning and delivery at scale is achievable are considered a Great Buy.

Estidama++ assesses cost-effectiveness based on the cost per beneficiary who sustainably transitions to regular social security. To date, a total of 4,675 successful transitions have been recorded out of a target of 20,000 (and 5471 who already finished the scheme). The cost per beneficiary who has sustainably transitioned to regular social security is calculated as $3,906. This metric is artificially high as most beneficiaries have been recently enrolled in Estidama++ and have not had the chance to transition to SSC. The cost will lower as more participants complete the scheme and transition.

Shamil’s work has facilitated some important outcomes. Their engagement with the NCFA encouraged a commitment in the National Older Persons’ Strategy -which was endorsed by the Prime Minister and Cabinet- to introduce a social pension for all elderly persons. Their support to the Higher Council for the Rights for Persons with Disabilities played a valuable role in enabling Jordan to successfully act as a Global Disability Summit co-host- which in turn enabled them to make commitments to improving disability inclusion in Jordan.

Equity

UNHCR and WFP prioritises support for the most vulnerable refugees. This includes the targeting criteria for cash assistance focusing on families that are not able to meet their most basic survival needs and have multiple vulnerability e.g. members who suffer from severe disabilities, debilitating medical conditions and other vulnerabilities. Cash transfers contribute to refugee dignity and social inclusion, reducing stress while empowering beneficiaries with financial autonomy. Recent focus group discussions for WFP and UNHCR beneficiaries highlight the differentiated needs of refugee women, particularly in digital transitions. Continued engagement will ensure inclusivity, mitigating potential barriers faced by marginalized groups. Future agreements with UNHCR and WFP will emphasise standardised disaggregated data collection to strengthen accountability, refine targeting, and enhance programme transparency.

Estidama++ benefited a number of marginalized groups. Around 22% of project participants were women. 30% of participants were also refugees, a group within Jordan with vulnerabilities. At this time SSC is unable to provide disaggregated data on the proportion of participants with disabilities, but this will be further explored moving forwards and field monitoring will be used as an interim tool to track this.

Shamil embedded Gender Equality and Social Inclusion (GESI) analysis across workstreams. Around 84 per cent of activities were assessed as GESI-sensitive and 48 per cent of activities were ranked as GESI transformative. The disability targeting framework was co-designed with persons with disabilities, and the national strategy for older persons involved inclusive consultations that elevated the voices of care workers and older adults. These activities promoted institutional change and inclusive governance practices.

Assessment of whether the programme continues to represent value for money

There is evidence of continued relevance and effectiveness of the SSERJ programme, as well as overall good performance against economy and efficiency measures. The programme continues to represent good value for money and continues to meet the life savings/basic needs of vulnerable refugees and Jordanians.

We recommend WFP and UNHCR develop Value for Money strategies so that there is better monitoring and transparency on the VFM of their cash-based interventions. Understanding cost-effectiveness and the ability to make comparisons with international cost benchmarks is even more crucial for demonstrating impact given the reduction in aid flows to the humanitarian sector. The no-cost extension period for ILO in relation to Estidama++ will be crucial in monitoring whether the programme can achieve the objective of sustainability transitioning beneficiaries into the social security system. Similarly, continuing to engage after the programme ends in February 2026 to support the institutionalization of Estidama++ and its evolution from a pilot initiative to part of the operating model of the SSC will be important. The early completion of the Shamil programme has led to sunk costs and lost potential value. Despite this, proactive mitigation—through careful planning, flexible contracts and structured wrap-up—will help minimise financial wastage.

E: RISK

Overview of risk management

The SSERJ programme currently has 18 active risks identified across the seven FCDO risk categories. These risks are reviewed on a quarterly basis, most recently in March 2025, to reflect changes in the context and programme delivery. Based on these risks, the programme carries an overall residual major risk rating.

Significant new risks have materialised or deepened over the past year with some materialising into issues and impacting the programme at an impact, outcome and output level. The main drivers of risk have been changes to international financing for Jordan, changes in the political landscape of Syria with new prospects for Syrian refugees return which creates certain programmatic risks, the Government of Jordan’s policy and legislative approaches which impact on the effectiveness of several activities, and issues related to the delivery of the Shamil technical assistance facility. Risks, however, in other areas have decreased – particularly relating to the results of Estidama++ which has hit its targets for participants, including refugees, and has shown positive signs that participants are transitioning to regular social security at the end of the scheme. SSERJ is considered operating within risk appetite.

The highest risks over the past year have been in the Strategy & Context and Policy & Programme Delivery risk categories. More information on the risks with the highest residual risk rating (major) is as follows:

Strategy and Context Category Key Risks:
- Reduced international humanitarian financing: A decline in international aid for Jordan is a significant risk and materialised issue to the ability of the SSERJ programme to achieve its intended impact and outcomes. The U.S. Executive Orders and subsequent suspension of foreign assistance funding, which in turn has created risk to funding from other donors via changing the politics of aid, has had a profound and immediate impact on the delivery of humanitarian and development programming in Jordan. As resources for humanitarian assistance have decreased, the vulnerabilities of refugees and prevalence of negative coping strategies have increased affecting the impact and outcome level results the SSERJ programme can achieve. In response the British Embassy Amman is pursuing the recommendations set out in earlier sections, such as working with the UN to adapt to the new context and to diversify funding sources including via public private partnerships.
- Returns to Syria: A change in the political landscape of Syria provides new prospects of return of refugees to Syria. This creates risks around the relevance and preparedness of our humanitarian support, as well as a risk that social security contributions made on behalf of refugees via Estidama++ are lost as refugees return without accessing benefits. The British Embassy Amman is working with UN partners and SSC/ILO to monitor the needs of refugees and promote the withdrawal of social security benefits for departing refugees.
- Policy and legislative approaches: The GoJ recently removed a waiver for work permits, making them more expensive for refugees. Legislation was also introduced which will increase the cost of social security contributions, including for Estidama++ participants on transitioning to regular social security at the end of the scheme. Both changes have the potential to negatively impact the transition and retention of Estidama++ participants in social security moving forwards, although no negative impacts have been observed at present. The embassy is engaging with the SSC and ILO to closely monitor these trends and is also engaging around the SSC’s reform process which has the potential to somewhat offset this negative trajectory. It is also engaging around work permits for refugees.
- Will for use of evidence: There is a risk of limited appetite for the increased use of evidence by Jordan’s Government in making decisions relating to the economic inclusion of refugees, which would affect the impact of certain activities under output 4. To offset the risk the British Embassy in Amman is working alongside other partners to establish links and build connections needed to build demand for this evidence as well as building refugee self-reliance through different avenues including financial inclusion and social security.

Policy and Programme Delivery Category Key Risks:
Sustainability of Estidama++: A risk exists that a suitable plan and financing isn’t available for Estidama++ after the pilot ends in February 2026. The British Embassy Amman is encouraging the SSC and ILO to set out a clear plan for this. Recently Estidama++ was included in the SSC’s future vision reform process and an initial plan for its institutionalisation was shared, however this risk remains at this early stage as a firm commitment for SSC future financing for the scheme has yet been made.

Gender Equality, Disability, SEAH, and Equalities Duties

As outlined in the SSERJ Business Case and Equalities Impact Assessment, the programme continues to track its commitments under the Gender Equality Duty and Public Sector Equality Duty. There have been no significant changes in the assumptions made at the design stage about equalities impacts. The programme continues to pursue activities which are both gender responsive (e.g. measures to include women in social security) and gender transformative (for example GESI sensitive economic inclusion technical assistance activities). However, some operational risks around inclusion have emerged, particularly in light of access barriers for refugees and women in the labour market and the inclusion of women in Estidama++. The equalities impacts of changes to the programme, through an increased focused on humanitarian activities and reprioritisation of social protection activities, will be carefully assessed.

The programme’s risk register includes dedicated entries addressing SEAH and child safeguarding. All implementing partners have institutional safeguarding policies and procedures in place. During Partners Engagement Day hosted by BE Amman in April 2024, a focused session was held on safeguarding, fraud prevention, and risk escalation procedures to reinforce shared standards.

Climate and Environment Risk

In alignment with the Paris Agreement, the climate and environment risk for the SSERJ programme remains low. The programme’s core interventions are not directly contributing to environmental degradation and do not involve infrastructure or land use activities. Nonetheless, as a proactive mitigation step, we will work with partners to encourage climate-sensitive programming—particularly in supporting livelihoods and resilience-building in the refugee response and supporting the development of shock responsive social protection. The Refugee Self-Reliance initiative is already making a positive contribution to the climate and environment.

Due Diligence and Partner Risk Management

Due diligence assessments remain central to the SSERJ programme’s risk assurance framework. DDAs were conducted or refreshed for ILO (2022), UNHCR, and WFP (2023), in close coordination with central teams, including institutional leads and the DDA Hub. The findings and mitigation actions were documented and communicated to partners. We continue to track implementation of action plans, and no material issues have emerged that would warrant a change in our risk assessment.

Our understanding of partner capacities has matured, with regular engagement helping to reduce delivery and fiduciary risk. Nonetheless, we will reassess whether any DDA updates are required in the coming year due to time elapsed or changes in partner operations and capacities. Currently, assurance levels remain proportionate to the programme’s risk profile.

Update on Partnership Principles
The British Embassy Amman reviewed the Partnership Principals Assessment (PPA) in August 2023 based on the comprehensive literature review and peer consultation, the assessment concluded that the GoJ remains committed to the four partnership principles with an upward trajectory with no require for a change in FCDO’s risk appetite.

Annual Statement of Progress

Current level of fiduciary risk and direction of travel since last ASP	Moderate – Stable
Specific assessment of corruption risk and direction of travel since last ASP	Moderate – Stable
Is a full FRA update required?	Yes

Annual statement of progress is not required for programmes when the financial assistance to the government is below £10m. A full FRA will be required in 2025/2026 if needed.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

SSERJ Programme’s eight components cross both the humanitarian and social protection sectors and continue to be delivered by multiple partners including the GoJ (SSC), UN agencies (ILO, UNHCR, WFP) and consultants from the private sector (Development Pathways with two national organisations, ARRD and MMIS).

Commercial Activities

The British Embassy Amman continued to manage the £8m contract with Development Pathways as they concluded their Inception phase in March 2024 and moved to their Year 1 Implementation phase in April 2024 under the brand name “Shamil” delivering TA to the GoJ that is demand led by the government’s different departments in line with the National Social Protection Strategy (NSPS).

Across the year, we also continued to manage the MoUs signed with both the SSC to deliver the Estidama++ programme and the ILO to provide the SSC with technical support needed for the implementation of the Estidama++ programme. Both MoUs are planned to receive a no cost extension as requested by the ILO and approved by donors to finalise disbursements to workers enrolled as part of the registration extension period to early 2025 ensuring the full subsidy period is honoured. Also, this will allow the ILO to consolidate and deliver results from the second Randomised Control Trial (RCT), including analysis, presentation, and policy engagement with SSC and other stakeholders while maintaining a core team to support transition, documentation, and institutional learning, including the uptake of results into SSC’s long-term reform plans.

Following the signing of the Contribution Agreement (CA) with WFP in August 2023, and an amendment in December 2023, an initial disbursement of £3.5 million was made. A new CA was then signed in April 2024 for an additional £7 million, followed by two amendments in August and December 2024 that increased the UK’s contribution to WFP’s food assistance programme in Jordan by £7 million and £5 million, respectively.

Additionally, a Memorandum of Understanding (MoU) was signed with UNHCR in April 2024 to support its Multi-Purpose Cash Assistance programme in Jordan, with an initial contribution of £5 million. This was followed by three amendments: £7 million in August 2024, £5 million in December 2024, and £2.5 million in February 2025.

Furthermore, in June 2024, the programme team, in collaboration with the commercial team, signed a contract with Crown Agents to appoint a Specialist Advisor to the Minister of Planning and International Cooperation (MOPIC) on refugee-related matters. Following the liquidation of Crown Agents in July 2024, a new contract was signed with DAI in August 2024 to continue the consultancy services.

In November 2024, a CA was signed with WFP to enhance refugees’ economic participation in Jordan. The CA, valued at £800,000, was disbursed promptly after signing. Although the CA end date is April 2027, it was agreed that the initial disbursement would cover activities up to June 2025, with any additional funding to be determined based on performance results. In March 2025, WFP requested a no-cost extension for the covered period until December 2025, which was approved by the programme’s Senior Responsible Officer.

Programme Monitoring

As SSERJ is delivered by a wide range of delivery partners, we continue to work very closely with the programme’s implementing partners to monitor progress and ensure they meet their objectives and milestones set out in the logframe.

Estidama++

The Estidama++ quarterly narrative and financial reports through the SSC were constantly delayed. Although we have agreed on a simplified template that provide an overview of progress for the quarter with a consolidated financial sheet, reports were consistently delayed but improved compared to last year.

The ILO’s 2024 annual progress report and financial audited statements were submitted in a timely manner.

Estidama++ Technical Steering Committee (TSC) meetings continued to be chaired by the Director-General of SSC to provide an overall strategic overview and updates on project progress and solicit feedback. The donors and partners were invited to attend two meetings during the reporting period (September and March) however, the March meeting was postponed to May so as to be hosted by the new Director General post the retirement of the previous one.

Shamil

Shamil’s quarterly narrative and financial reporting were delivered on time with an overall good standard that reflected progress against the pre submitted and approved technical activities through the tasking order templates.

The biweekly update meetings with the Shamil team resumed as per the Inception phase allowing very close coordination with the team on the activities being delivered to different government departments and the main highlights and updates. The technical activities identified by Shamil as a response to the GoJ different departments continued to be assessed by Shamil and submitted to the British Embassy Amman through the Tasking Order (TO) workbook for approval, ensuring that activities continue to be relevant to the key objectives of the programme and in line with the NSPS.

Three programme management board meetings were held across this year post the receipt and the review of the progress reports with a pre-set agenda with a presentation by Shamil on the quarter’s main activities and progress, challenges, progress against milestones and plans for the upcoming quarter. These meetings were well received by the British Embassy Amman and the Shamil team as they provided a platform for the full SSERJ programme team to participate as needed.

WFP

The British Embassy Amman maintains regular meetings with WFP to monitor programme progress across both components: cash assistance and refugee economic inclusion. In line with the formal reporting requirements outlined in the signed agreement, WFP is required to submit narrative progress updates every six months. A progress report was submitted by WFP in April 2025.

In addition, field visits were conducted covering both programme components, providing the programme team with the opportunity to engage directly with beneficiaries and discuss implementation progress.

UNHCR

The British Embassy Amman also holds regular meetings with UNHCR to monitor programme performance and receive updates on the refugee situation. As per the MoU, UNHCR is required to submit an annual project report (aligned to the calendar year). However, to ensure alignment with the British Embassy Amman’s reporting needs, it was mutually agreed that UNHCR would submit two reports annually. Accordingly, an interim report covering the period April 2024 to December 2024 was submitted in January 2025. Additionally, progress updates were provided in April 2025 as part of this review process.

Field visits were conducted to meet with cash assistance beneficiaries both in camps and host communities, offering valuable insights into programme impacts.

UNHCR Deployment

The programme team maintains regular engagement with the UNHCR secondees and their supervisors to discuss the progress of secondment activities. The secondees also proactively keep the SSERJ programme team informed and seek their input, ensuring a coordinated and aligned approach to programme delivery.

MOPIC Specialist Advisor

Regular high-level meetings were held with the Specialist Advisor. Given the sensitive nature of the subject matter, outcomes of these discussions were shared selectively within a limited and relevant group to ensure appropriate handling of sensitive information.

Financial Performance

The total programme spend during the FY24/25 was £47,592,036 comprising of the following payments agreed under a commercial contract with DP, contribution agreement with WFP and MoUs with the SSC, the ILO, and UNHCR:

- Two payments disbursed to the SSC in July 2024 and February 2025 with a total of £5.2m
- One payment of £647,006 payment to the ILO in September 2024
- A total of £1,931,806 payments to DP against four invoices accrued for on a quarterly basis based on Shamil’s forecast that is reviewed mid quarterly for better accuracy vs their actual quarterly invoice
- Three payments disbursed to WFP in April, October and December 2024 with a total of £19m
- Four payments disbursed to UNHCR in April, October, December 2024 and March 2025 with a total of £19.5m
- A total of £82,750 payments to DAI for two invoices covering monthly payments from July 2024 to January 2025 based on the agreed payment schedule. These payments cover the contract managed by DAI for the MOPIC specialist advisor on refugees.
Estidama++

The SSC continued to submit the consolidated financial sheet customised to the programme joint account showing funds received (disaggregated by donor), actual spent on payments made to beneficiaries and commitments for the remaining period of the phase for each quarter.

Across the quarters and specifically in Q3, the British Embassy Amman worked very closely with the Estidama++ team at the SSC and the ILO to get clear updates and understanding on the joint account’s financial status in terms of the funds available to cover all the beneficiaries until the end of the programme and its phase two beneficiaries. This was crucial to inform the UK’s last payment of £1.7m that was disbursed into the Estidama++ joint account in February 2025 taking into considerations funds disbursed by the other donors (Norway and Netherlands).

In 2024, Estidama++ total expenditure as direct payments to beneficiaries (covering the contribution subsidies and incentive payments) reached USD 7,707,174.01 significantly exceeding last year’s spend of USD 1,191,662.15 which reflects the programme’s expansion.

Although the last payment was made and we are not forecasting any further payments into the Estidama++ joint account at the SSC, the British Embassy Amman will continue to have an oversight on the spend through the SSC’s consolidated financial sheet on a quarterly basis and will continue to support the ILO through providing TA to the SSC.

The ILO shared their 2024 certified Statement of Income and Expenditure for the Estidama++ fund and the SSC shared their 2023 audited financial statement.

Shamil

Shamil continued with their timely quarterly financial reporting that came with their quarterly invoices and included their forecast for the next quarter. To minimize the variance between the forecasts and actual expenditure, Development Pathways revised their forecasts on a mid-quarterly basis which supported better forecasting accuracy and meeting the financial KPI of keeping the variance to a maximum of 5%. Shamil’s forecasts and invoices reflects costs, standard core team fees and associated expenses, programme activity and TA funds costs.

We are currently in the stage of negotiating Shamil’s forecasted expenditure until the completion of the contract.

UNHCR and WFP

Over the course of the review period (April 2024 – March 2025), the UK contribution to UNHCR was expanded, bringing the total support to £19.5m. Four payments were disbursed during this period. UNHCR has fully expended the funding provided, delivering cash assistance to vulnerable refugees as planned. This demonstrated strong financial absorption capacity and effective programme management under challenging operational conditions.

In the review period, the British Embassy Amman significantly scaled up its support to WFP’s food assistance and refugee economic inclusion programmes in Jordan. Across 2024, four payments were disbursed to WFP, amounting to £19.8 million. WFP has fully utilised all funds disbursed during this period, maintaining continuity of assistance amidst a difficult funding environment. This reflects strong financial performance and effective programme delivery.

In addition to the food assistance support, a separate CA for £800,000 was signed in November 2024 to enhance refugee economic participation. This new phase of UK support aims to advance the economic inclusion of refugees in Jordan by building on last year’s refugee skills mapping exercise. It will enhance refugee’s economic participation through targeted, long-tern livelihood support.

DAI - MOPIC Specialist Advisor

DAI’s financial performance has so far been satisfactory, with invoicing aligned to the deliverables and payment schedule outlined in the contract.

Programme monitoring has included regular meetings with the Specialist Advisor, and early indications suggest that activities are progressing as planned. Given the sensitivity of the role, meeting outcomes and financial details have been shared on a restricted basis within the programme team.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring

The programme’s monitoring approach throughout the review period combined rigorous quantitative and qualitative methods across all implementing partners, including Estidama++, Shamil, UNHCR, and WFP. This ensured that both operational delivery and strategic engagements were underpinned by robust, real-time evidence.
- Estidama++: implemented a comprehensive Monitoring, Evaluation, Research, and Learning (MERL) framework, with real-time dashboards tracking enrolment, retention, and attrition, and quarterly quantitative and qualitative analysis. Field visits and sector-specific monitoring (e.g., in construction and agriculture) informed adaptive interventions. Beneficiary feedback, especially from Syrian refugees and women, was systematically collected and analysed to refine the Estidama++ activities design.
- Shamil: provided technical assistance to national statistical systems, including support for the 2025 Census, the development of a National Interactive Data Centre, and the establishment of a new Poverty Unit within the Department of Statistics. Regular coordination was maintained with government ministries, the Social Security Corporation (SSC), and development partners.
- UNHCR: conducted outcome monitoring via household surveys, including post-distribution monitoring (PDM) for cash recipients and broader surveys on refugee living conditions. The secondment of a statistician supported improvements in MEL practices, enhanced the socio-economic evidence base, and improved the targeting and effectiveness of cash assistance.
- WFP maintained a robust M&E framework aligned with its Corporate Results Framework, conducting bi-weekly on-site monitoring of distribution points, beneficiary contact monitoring (face-to-face and remote), and quarterly Food Security Outcome Monitoring (FSOM). WFP’s complaints and feedback mechanisms allowed for real-time issue resolution, and regular field visits and donor briefings ensured transparency and engagement with the British Embassy Amman programme team.

 Evidence

- Estidama++: Two RCTs evaluated the impact of outreach and financial incentives on social security registration. In-person firm visits increased registration by 14 percentage points, while SMS outreach had a smaller but significant effect. Qualitative research with refugees and women highlighted the importance of flexible payment options and the need to address sector-specific attrition.
- Shamil: Supported the development of the Multi-Dimensional Poverty Index, the national census, and the National Interactive Data Centre, enhancing the breadth and quality of social protection data. Efforts to build the capacity of the new Poverty Unit and improve MIS systems for social protection were central to evidence-driven reform.
- UNHCR: The Joint Data Centre on Forced Displacement’s literature review found that safety in the country of origin is the most critical factor affecting refugee returns. This evidence directly informed the programme’s Theory of Change and future planning, given the ongoing uncertainty in Syria.
- WFP: FSOM data showed a significant deterioration in refugee food security after assistance reductions, with increased food insecurity, child labour, school withdrawals, and household debt. WFP provided disaggregated data by age, sex, and location, supporting the Leave No One Behind agenda and inclusive analysis.

Learning

- Estidama++: operated as an adaptive policy laboratory, piloting and refining interventions based on real-time evidence and beneficiary feedback. During the reporting period Estidama++ successfully scaled up to reach over 40,000 beneficiaries by addressing key barriers for vulnerable workers, especially refugees, women, and those in informal jobs, to accessing social security. Key refinements included redesigning the outreach strategies through combining digital campaigns and face-to-face sessions, enhancing the SSC WhatsApp chatbot, and tailoring communication for employers. This led to a significant increase in registration with more than 11,000 new registrations in two months. The programme also updated Standard Operating Procedures (SOPs) introducing flexible payment modalities and strengthening grievance management. Regular learning reviews, workshops, and capacity-building sessions SSC and other partners ensured that these lessons were institutionalised embedding Estidama++’s contribution subsidy model and outreach approaches into SSC’s long term reform strategy, as captured in the Visioning White Paper.
- Shamil: embedded learning through technical assistance, joint research, and capacity-building workshops with multiple national and governmental bodies including the Department of Statistics (DoS), Ministry of Social Development (MoSD), Ministry of Planning and International Coordination, National Council of Family Affairs, Ministry of Finance, SSC, Zakat Fund, and the Higher Council for the Rights of Persons with Disabilities (HCD). Shamil supported DoS in the design and piloting of the 2025 Census, developed the National Interactive Data Centre, and supported securing 18 data sharing MoUs, aiming to improve how data is being managed and shared across government. For the MoSD, Shamil contributed to drafting operational manuals for the deinstitutionalisation of people with disabilities. The Zakat Fund, with Shamil’s technical guidance, began shifting from paper based to digital beneficiary management. At SSC, gap assessment results led to the procurement of a new business intelligence tool. Shamil’s capacity building efforts included workshops on evidence-based policymaking and Power BI training for DoS and MoPIC staff, directly equipping officials to use data in decision-making. The annual partner surveys showed that 89% of technical committee members reported changes in their work practices and a broader understanding of social protection.
- UNHCR: learning processes were informed by Post Distribution Monitoring (PDM) analysis, community feedback, and contextual risk assessments. Community feedback was used in targeting who receives cash, to improve the communications with refugees as part of accountability to affected populations and influencing the design of activities, such as the provision of the pilot transport service for voluntary returns to Syria. The Post Distribution Monitoring survey confirms that in most cases the delivery of cash is working well.
- WFP: WFP combined its regular quantitative monitoring with qualitative household visits, which provided deeper insights into how assistance reductions affected refugee households. These findings highlighted the urgent need to adjust targeting criteria to prioritise the most vulnerable, reinforce resilience measures, and better incorporate protection concerns into programme design. As a result, WFP increased its focus on engaging directly with beneficiaries and refining programme components to respond more effectively to evolving needs amid funding constraints.
Date of last narrative financial report	UNHCR: January 2025 / WFP: April 2025	Date of last audited annual statement	UNHCR: October 2024[24] / WFP: April 2025[25]
[24] UNHCR’s financial report and audited financial statements for the year ended 31 December 2023
[25] WFP’s 2024 Annual Country Report (ACR) for Jordan

Annex 1: Shamil technical assistance activities over past year

Below is a list of activities delivered and referenced in the outputs in Section C

Output	Indicator	Summary of progress over the past year	Full list of activities achieved against milestones
3	Number of analyses (e.g. political economy), evidence-based and good practice resources, and strategies (e.g. Stakeholder engagement, GESI, Communications, VFM) produced, routinely updated and disseminated where appropriate.	Completed a CNM for the Ministry of Finance. PEA updated on a quarterly basis using Everyday Political / Shamil (social security)- 44 (cumulative) resources provided to GoJ (policy papers and presentations) (28 achieved this year) / Shamil (social services)- 10 resources provided to GoJ (policy papers and presentations)	On Social Security: / 1. Brief on disability-inclusive social security / 2. Accessible brief on disability-inclusive social security / 3. Report on national consultations for the Global Disability Summit (GDS) / 4. Summary of report on national consultations for the GDS / 5. Accessible version of the report on national consultations for the GDS. / 6. Presentations on disability-inclusive social security 7. Summary of report on national consultations for the GDS / 8. Cost-benefit analysis for comprehensive social security in Jordan / 9. Presentation on cost benefit analysis for comprehensive social security in Jordan / 10. Ensuring income security for all Jordanian women in old age: policy paper with Jordan National Commission for Women (JNCW). / 11. Social Security Corporation (SSC) Management Information System (MIS) Gap Assessment Report / 12. Review of Jordan’s MIS for social protection, recommendations and follow-up / 13. Final report, SSC reclassification Phase 2 / 14. Paper on comprehensive social security for SSC/Ministry of Labour (MoL) / 15. Presentations for GDS Pre-summit / 16. Presentations for GDS side-event / 17. Terms of Reference for Business Intelligance (BI) tool procurement / 18. Standard Operating Procedures for Zakat Fund / 19. Multi-dimensional Poverty Index (MPI) programme / 20. Social Accounting Matrix for Computable General Equilibrium model (CGE) / 21. Global experience with realising the right to income security in old age for all members of society: National Council for Family Affairs (NCFA) launch / 22. Nepal’s Experience in Implementing a Universal Pension for the Elderly: NCFA launch / 23. Achieving the right to social security for persons with disabilities: GDS side-event / 24. Fiji’s Disability-Specific Benefits: GDS side-event / 25. South Africa’s Disability-Specific Benefits: GDS side-event / 26. Achieving the right to social security for persons with disabilities in the Arab region: GDS pre-summit / 27. Ensuring income security for persons with disabilities: the role of disability-specific social security benefits: animated video for GDS side-event / 28. National Strategy for Older Persons (2025-2030): animated video for strategy launch / On Social Services: / 1. Report: Scoping Support for the MIS-based Implementation of Deinstitutionalisation of Persons with Disabilities / 2. Business requirements document for social worker registration platform at the Ministry of Social Development (MoSD) / 3. Presentation on disability-inclusive social services / 4. Brief on disability-inclusive social services / 5. Accessible brief on disability-inclusive social services / 6. Report on national consultations for the GDS / 7. Summary of report on national consultations for the GDS / 8. Accessible version of the report on national consultations for the GDS. / 9. Guidelines on De-institutionalisation Including Emergencies: GDS pre-summit / 10. Empowering Lives: Moldova's Path to Deinstitutionalisation
3	No. of capability building sessions for GoJ officials and wider stakeholders relating to inclusive social protection and number of GoJ staff trained	Shamil (social security)- 41 (cumulative) sessions to 38 different stakeholders (cumulative) (23 sessions achieved this year). / The Global Disability Summit MENA pre-summit and side-event on disability-inclusive social security were attended by approximately 200 and 500 participants from national and international government and non-government organisations / (Details in Annex 1) / Shamil (social services)- 6 capacity building activities to 19 different stakeholders (Details in Annex 1)	On Social Security: / 1. GESI Advisory Group meeting - 3 NGO / 2. GDS workshops on disability-inclusive social security / 3. Evidence Based Practice (EBP) training / 4. EBP intro workshop / 5. EBP 3-day workshop / 6. General Population and Housing Census training / 7. Population and Family Heath Survey training / 8. Methods of demographic analysis training / 9. Training on principles of official statistics and fertility measurement / 10. Population projection methods training / 11. Training on education indicators / 12. Follow-up training on the delineation stage for the census / 13. Introduction to Microsoft Project / 14. Follow-up training on Microsoft Project / 15. Presentation on disability-inclusive social security: GDS MENA Pre-Summit / 16. GDS side-event: disability inclusive social security / 17. Intro Capacity Needs Mapping/Strategy workshop for the Ministry of Finance / 18. National Strategy for the Elderly launch event / 19. SSC technical session: Building Comprehensive Social Security / 20. Economic and Social Council technical session Comprehensive Social Security / 21. Financing attendance of Government officials to the International Training Centre of the ILO social protection training to building capacities. / 22. General Confederation of Trade Unions workshop / 23. 3 SSC Reclassification workshops / On Social Services: / 1. 2 national GDS consultation workshops on disability-inclusive social services / 2. Workshop with MoSD Directors and staff from 4 departments on professional social services / 3. Workshop with MoSD Directors and staff from 4 departments on social worker registration systems / 4. Workshop with MoSD professionalisation unit Director and staff on social worker registration platform / 5. Workshop with MoSD Deinstitutionalisation (D-I) unit Director and staff on D-I operations and MIS
3	No. of new or strengthened system elements including e.g. MIS, SOPs, knowledge sharing platforms, payment systems etc. that are GESI sensitive	Shamil (social security)- 9 system elements strengthened / Shamil (social services)- Scoping could not be completed. Draft reports produced on: / 1. Professionalisation of Social Work in Jordan: Vision and Roadmap / 2. Scoping study of Jordan social work / 3 final reports and presentations on assessments of 3 different sub-system elements were completed	On Social Security: / 1. ToRs for SSC to procure a business intelligence tool / 2. Correspondence tables & methodology to reclassify employer/employee data (ISIC/JORSIC) for SSC and other agencies / 3. Design and launch of beta version of Department of Statistics National Data Centre / 4. Standard Operating Procedures for Zakat Fund and 182 Zakat Committees / 5. Design of 2025 census form / 6. Social Accounting Matrix for the Ministry of Planning and International Coordination (MOPIC) / 7. Multi-Dimensional Poverty Index for the Department of Statistics
3	No. of policy dialogue engagements on inclusive social protection / (social security and social services) that are delivered to key stakeholders across GoJ that are GESI sensitive	Shamil (social security)- 79 (cumulative) policy dialogue engagements / 43 in 2024 / Shamil (social services)- 15 policy dialogue engagements	On Social Security: / Royal Court (2) / Head of Crown Prince Foundation (3) / Prime Minister's Advisor (2) / Director General (DG) SSC (6) / DG JNCW (1) / DG Higher Council for the Rights of Persons with Disabilities (HCD) (5) / Minister of Labor (4) / MoSD Secretary General (4) / Minister of State for Economic Affairs (2) / DG NCFA (4) / Economic and Social Council President and SG (3) / Ministry of Political & Parliamentary Affairs SG (1) / Minister MoSD (2) / HRH Prince Mired (1) / Chair & Council Members, Integrity & Anti-Corruption Commission (1) / DG DoS (1) / SG Zakat Fund (1) / On Social Services: / DG HCD (6) / SG MOSD (4) / Minister MOSD (2) / DG NCFA (3)
4	Number of evidence base and good practice resources and products generated and disseminated to key stakeholders including GoJ on economic inclusion (including labour market access by refugees)	Shamil completed a Jordan Labour Market Briefing Note.	Jordan Labour Market Briefing Note in English and Arabic
4	Number of policy dialogue engagements on inclusive labour market outcomes that are delivered to key stakeholders across GoJ that are GESI sensitive	Shamil held 9 policy dialogue engagements on the topic of economic inclusion. See Annex 1 for details.	DG National Aid Fund (NAF) DG (1) / Minister MoL (4) / DG SSC (3) / Head of Crown Prince Foundation (1)