## SSERJ Logframe- 2026 Update
PROJECT TITLE | Strengthening Societal and Economic Resilience in Jordan
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
Strengthened societal and economic resilience in Jordan and stability maintained in Jordan. | Vulnerability among registered refugees | Planned | A high proportion of Syrians (70%) faced either high or severe basic needs vulnerability in 2021 (Source: VAF 2022 report). 89% of refugees in host communities, 83% in Azraq camp and 69% in Zatari camp report living in debt in 2021. (Source: VAF 2022 reports) | N/A | N/A | That figures remain stable at the baseline 2021 levels (given current trajectory shows a deterioration in vulnerability). | N/A | That figures remain stable at the baseline 2021 levels (given current trajectory shows a deterioration in vulnerability).
|  | Achieved |  | N/A | N/A |  | 66% of all registered refugees live below the one-refugee poverty line in 2025 (World Bank (WB) analysis reported in Socio-economic Survey 2026) 93% of registered refugees reported holding debt (compared to 85% in 2023) Levels of indebtedness increased significantly, reaching JOD 1,600 per person - an increase of 27% compared to 2023.
Source: UNHCR’s Vulnerability Assessment Framework (VAF) Reports: Population Survey of Refugees Living in Host Communities and Camps in Jordan https://data.unhcr.org/en/documents/details/93754 https://reporting.unhcr.org/jordan-2022-population-survey-refugees-camps-vaf
Note: - Data will be reported at mid point and end point based on actuals (no milestone estimations) - This indicator is a stability indicator as greater vulnerability may lead to increased poverty and alienation from GoJ (impacts on social contract) and international community
| Impact Indicator 2 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| Proportion of Jordanians with social protection benefit coverage disaggregated by gender and disability | Planned | Population covered by at least one social protection benefit in 2021- 26%. | N/A | N/A | Population covered by at least one social protection benefit in 2025- 27%. | N/A | Population covered by at least one social protection benefit in 2027- 28%.
|  | Achieved |  | N/A | N/A
Source: ILO statistics on social protection https://ilostat.ilo.org/topics/social-protection/ ; Statistical Bulletin of Social Protection Indicators in Jordan; https://www.ilo.org/beirut/media-centre/news/WCMS_908328/lang--en/index.htm
Note: Disaggregated data not currently available for baseline estimation; To be noted that the figure for 2021 represents an anamoly as coverage was temporarily expanded in response to Covid-19
OUTCOME 1 | Outcome Indicator 1 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027) | Assumptions
Jordan has a social protection system that helps all individuals address risks across the lifecycle and from shocks (including climate shocks), empowers women and persons with disabilities and generates economic growth and a stronger social contract | Proportion of refugee households demonstrating resilient and sustainable food practices due to WFP support | Planned | 54% of FHH and 58% of MHH were rated 'acceptable' (rather than borderline or poor) in the Food Consumption Score (FCS) for Syrian refugees in host communities. 88% of Syrian refugees in Zataari camp and 85% in Azraq camp were also rated 'acceptable' in the FCS in 2021 (FCS VAF score for refugees in host communities and camps, 2022 VAF reports). | N/A | WFP: HHs using crisis Consumption Score (CS) should be stabilized or be reduced compared to baseline. Households (HHs) using emergency CS should be stabilized or reduced compared to baseline. HHs using stress CS to be stabilized or increased compared to baseline. HH not using CS should be stabilized or increased compared to baseline. Acceptable FC to be stabilized or exceed baseline | WFP: HHs using crisis Consumption Score (CS) should be stabilized or be reduced compared to baseline. HHs using emergency CS should be stabilized or reduced compared to baseline. HHs using stress CS to be stabilized or increased compared to baseline. HH not using CS should be stabilized or increased compared to baseline. Acceptable FC to be stabilized or exceed baseline | WFP: HHs using crisis CS should be stabilized or be reduced compared to baseline. HHs using emergency CS should be stabilized or reduced compared to baseline. HHs using stress CS to be stabilized or increased compared to baseline. HH not using CS should be stabilized or increased compared to baseline. Acceptable FC to be stabilized or exceed baseline | WFP: HHs using crisis CS should be stabilized or be reduced compared to baseline. HHs using emergency CS should be stabilized or reduced compared to baseline. HHs using stress CS to be stabilized or increased compared to baseline. HH not using CS should be stabilized or increased compared to baseline. Acceptable FC to be stabilized or exceed baseline | • GoJ remains committed to building a stronger and more effective social protection system and financial resources for social protection increase with time. • The UK commitment to partner with Jordan, reflected through continued ODA allocations to social protection programming and thought leadership, maintains the level of funding for SSERJ. • GoJ allocates adequate and appropriate human resources to manage the social protection sector. • Data and evidence generated through the programme in the social protection sector reaches key decision-makers and is sufficiently compelling for them to move towards a paradigm shift in social protection policy. • GoJ will see the value in greater alignment of social protection and humanitarian response due to efficiencies and cost savings in the medium and longer term and adequate financial resources are in place to continue to support refugees who still require income support. • Strengthening the national social protection system and expanding coverage will strengthen the social contract and, as a result, the GoJ will be able to generate greater financial resources from taxation while also strengthening Jordan’s continuing stability. • GoJ will be open to assessing long term costs and benefits of enhancing the redistributive role of the Jordanian Tax System. • External crises will not significantly divert donor attention away from Jordan and that donors will continue to provide financial assistance to those refugees who do not generate sufficient income from the labour market. • The labour market produces enough jobs to facilitate the greater inclusion of more women, persons with disabilities and refugees. • Those refugees who are able to enter the labour market earn a sufficient income so that they do not require humanitarian assistance. • Funding will be provided for a professional social care system to be built. • The SSC can deliver a multi-tiered system and their role in this will be supported by key decision-makers. • Workers on low incomes or businesses perceive that the potential long-term benefits of contributing to the SSC and participation in the formal economy outweigh any short-term costs or risks and will contribute to the SSC over the medium to longer term. • Providing knowledge, awareness and understanding will generate a shift in thinking and will generate political will to create fiscal space for building an inclusive social security system. • Reduced donor contributions to UNHCR's BN cash assistance programme will continue over the life of activity resulting in reduced BN cash assistance caseloads. The cost of living in Jordan will continue to increase, however, this increase will not be offset by higher BN cash assistance transfer values because of inadequate donor funding. • The current situation (donor reductions, macroeconomic situation of Jordan, etc.) does not promise improvements in refugee access to stable employment.
|  | Achieved |  | N/A | N/A |  | Latest results (December 2025) show that 74% of HHs were rated "Acceptable" in the Food Consumption Score for Syrian refugees (83% in camps and 74% in Host Communities), 92% of refugees using coping strategies to ensure the household has enough to eat. In order to meet overall essential needs, 81% of refugee population resorts to harmful Livelihood Coping Strategies (63% in camps or 85% in Host Communities).
Source: WFP monitoring data
Notes: - Livelihood coping strategy vulnerability is a stability indicator since negative coping mechanism can have a corrosive affect on society and may increase crime. -Resilient food practices are those characterized by consistently meeting nutritional needs, maintaining dietary diversity, and ensuring access to an acceptable standard of nourishment.
| Outcome Indicator 2 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| Proportion of households that meet half or more of their needs, for basic and domestic items, with UNHCR cash assistance. | Planned | UNHCR Basic Needs Annual Programme Assessment [2023]: 43% | N/A | N/A | 40% | 40% | 40%
|  | Achieved |  |  |  |  | 37%
Source: UNHCR Annual Programme Assessment , 2025 CBI Annual Assessment 2025
| Outcome Indicator 3 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| Proportion of vulnerable workers who have participated in Estidama++ that have transitioned into regular social security schemes of SSC by the end of the Estidama++ project (disaggregated at least by gender and nationality). | Planned | 0 | N/A | At least 60% (end of phase I - Dec 2023) | At least 60% (end of phase II- March 2024) | At least 60% (end of phase II- December 2025)
|  | Achieved |  | N/A |  |  | 84.2%
Source: ILO Estidama++ Fund – Extension of Coverage and Formalization Project Summary May 2023 and Estidama++ annual progress reports
Note: SSC does not currently have data on the disability status of its insured individual meaning data can not currently be disaggregated by disability.
| Outcome Indicator 4 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| A sustainable model for the extension of social security to vulnerable workers has been institutionalised (e.g. shown by GoJ budget allocation) | Planned | Estidama++ programme is based solely on donor financing | N/A | N/A | Dialogue/discourse around Estidama++ commenced by GoJ | Budget allocations and commitments made by GoJ. This indicator will be assessed in the Final Evaluation (planned for May - August 2026)
|  | Achieved |  | N/A |  |  | A national contribution subsidy was included in the Social Security Corporation's (SSC) Visioning White Paper and Social Security Reform Bill. Donor financing identified for a next pilot phase.
Source: ILO Estidama++ Fund – Extension of Coverage and Formalization Project Summary May 2023 and Estidama++ annual progress reports
| Outcome Indicator 5 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| Number of SSERJ recommended legislative, policy or administrative changes adopted by the Government of Jordan | Planned | 0 | N/A | ILO- N/A Shamil - N/A | ILO- N/A Shamil - At least 1 (cumulative) new or reformed regulatory or administrative changes adopted by government of Jordan to expand inclusive SP | ILO- At least 3 new or reformed regulatory or administrative changes adopted by SSC to facilitate extensions of coverage to vulnerable workers. Shamil - At least 2 (cumulative) new or reformed regulatory or administrative changes adopted by government of Jordan to expand inclusive SP and at least 1 labour market initiative introduced
|  | Achieved |  | N/A | N/A |  | ILO- The indicator was fully met in previous years. Regulatory amendments proposed in Social Security Reform Bill. Technical advice significantly advanced reform discussions through the finalisation of the SSC Visioning White Paper, which informs future amendments The main amendments reported during the project: Estidama++- 1. New Stand Operating Principles (SOPs) were adopted for the second Estidama++ application window. 2. Additional instructions were issued to provide an advance payment to Syrian refugees, to lower the entry barrier after increased social security costs took effect in October 2023. 3.The Social Secuirty Corporation Internal Regulation has been updated to extend coverage to the beneficiaries of Randomised Control Trial 2 (RCT), to include specifically organizations with 10-20 staff members. The benefits include a child allowance of 20-25 JD. Shamil- 1. Chapter on Social Protection & Security for National Elderly Strategy Action Plan 2. Draft Ministry of Finance strategy; emphasises the need to integrate fiscal policy with social protection. 3. National Strategy for Older Persons 2024-30: commitment to introducing minimum income for older persons
Source: ILO Estidama++ Fund – Extension of Coverage and Formalization Project Summary May 2023 and Estidama++ annual progress reports, Shamil logframe intermediate outcome indicators 1.1 and 3.1, UNHCR (tbc)
Notes: -To include changes related to GoJ's social protection system, alignment of systems for nationals and refugees as well as inclusion into the labour market
| Outcome Indicator 6 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| Number of transitioned work-age refugees into employment opportunities and reduction of cash case load - WFP | Planned | 33% of Syrian refugees living in host communities were employed in 2021 (12% of women participated in labour force and 71% of men). (Source, VAF, 2022 report) 24% of refugees between 18-60 in Azraq camp and 28% in Zaatari camp were working in 2021. (Source: VAF 2022 report). | N/A | Percentage of Syrian refugees employed will increase or stabilise according to baseline | Percentage of Syrian refugees employed will increase or stabilise according to baseline | Percentage of Syrian refugees employed will increase or stabilise according to baseline | Percentage of Syrian refugees employed will increase or stabilise according to baseline
|  | Achieved |  | N/A | N/A |  | N/A (Refugees will be employed under the new strategy in the following quarter 2026)
Source: UNHCR’s Vulnerability Assessment Framework (VAF) Reports: Population Survey of Refugees Living in Host Communities and Camps in Jordan https://data.unhcr.org/en/documents/details/93754 https://reporting.unhcr.org/jordan-2022-population-survey-refugees-camps-vaf
| Outcome Indicator 7 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| Proportion of People of Concern (PoC) who self-report positive changes in their income compared to previous year - UNHCR | Planned | 31% | N/A | N/A | 35% | 35% | 35%
|  | Achieved |  | N/A | N/A |  | 5% reported that their income increased, 29% reported that their income stayed the same, and 66% reported that their income worsened.
Sources: UNHCR’s Vulnerability Assessment Framework (VAF) Reports: Population Survey of Refugees Living in Host Communities and Camps in Jordan https://data.unhcr.org/en/documents/details/93754 https://reporting.unhcr.org/jordan-2022-population-survey-refugees-camps-vaf Other UNHCR monitoring and reporting
The recipients of UNHCR basic needs cash assistance are welfare populations (e.g., persons with disabilities, severe chronic medical conditions, elderly persons, caregivers of the prior groups, and single female headed households with children). Therefore, the recipients of the BN cash--which FCDO proposes to support--will not "transition" off of the UNHCR BN cash list. Refugees with work-able adult members are not included in the BN cash list. data for UNHCR socioeconomic update (Jan-Feb 2026)
| Outcome Indicator 8 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| % of beneficiaries with a sustainable source of income after three months from job placement or establishing own business. (disaggregated by age, gender, nationality, disability). | Planned |  | N/A | N/A | N/A | Buy June 25: ≥20%
|  | Achieved |  | N/A | N/A |  | N/A (baseline to be collected by June 2026)
Sources: WFP reports
OUTCOME 2 | Outcome Indicator 2 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027) | Assumptions
Promotion of refugee-inclusive legal and regulatory policy frameworks governing refugee employment, financial inclusion for sustainable livelihood prospects. | # of advocacy products developed and disseminated (disaggregated by type (analytics, policy, factsheets, articles,, and by stage of development (drafted, completed, published, disseminated)) | Planned |  | N/A | N/A | N/A | By June 2025: 10 |  | Engagement and implementation of Cooperating Parnter for referrals and skills development trainings will take place within the agreed timeline.
|  | Achieved |  | N/A | N/A |  | 1 (in development)
Source: WFP Reporting
OUTPUT 1 - Humanitarian Cash | Output Indicator 1.1 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027) | Assumptions
Disbursement of Humanitarian Cash Transfers to the most vulnerable Refugees in Jordan | Number of reached refugees with cash assistance through WFP add new/old supported House Holds (HH) in the disaggregation. | Planned | 546482 | N/A | 219,976 beneficiaries (WFP provides CBT assistance to a total number of 410,000 refugees in camps and communities). | 359,264 beneficiaries (with JOD15 per person per month) | 210924 |  | Camp populations will remain stable at +/- 124,000 individuals. Due to declining funding, UNHCR will gradually reduce its Basic Needs cash assistance caseload in host communities by 15% per year.
|  | Achieved |  | N/A | 219,976 beneficiaries (137,832 beneficiaries with JOD10 per person per month). (82,144 beneficiaries with JOD15 per person per month). | 310000 | 210924
Source: WFP reporting
Notes: -UNHCR and WFP will be supporting many of the same refugees.
| Output Indicator 1.2 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| Number of people who received cash assistance (unique individuals). | Planned | 253258 | N/A | N/A | 214000 | 200000
|  | Achieved |  | N/A | N/A | 214000 | Overall number of refugees reached (April 25-March 26) 195,308 persons (111,853 in camps and 83,455 in urban areas) from 46,014 households (22,778 in camps and 23,236 in urban areas) with the following breakdown: 54,177 boys, 52,684 girls, 34,994 men, and 53,453 women, showing a significant proportion of women and children among those assisted (82%). Among the supported were 16,848 persons with disabilities (PWD). Subset reached through FCDO-funded contributions during the reporting period (April 25-March 26): 85,935 beneficiaries.
Source: UNHCR proposal 2024
Notes: -UNHCR and WFP will be supporting many of the same refugees.
INPUTS (£) | FCDO (£) |  | Govt (£) |  | Other (£) | Total (£) | FCDO SHARE (%)
FCDO (FTEs)
IMPACT WEIGHTING (%) | 30%
OUTPUT 2 Estidama++ | Output Indicator 2.1 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027) | Assumptions
Vulnerable workers (Jordanians and refugees) and businesses are informed about and join the social security scheme through the Estidama++ programme | No. of individuals benefiting from income support (coverage reward) and/or contribution subsidies who were previously not covered/registered with SSC (disaggregated by gender, nationality, wage, age, sector). | Planned | 0 | N/A | 11,500 total Gender ratio: 34% female participants/ 66% male – 20% higher than the ratio for regular SSC participants. Nationality ratio: 70% Jordanian/30% non-Jordanian. | At least 34,000 total (Gender ratio: 34% Nationality ratio: Agriculture sector 90:10; all other sectors 70:30) (reporting against targets for 2024) | At least 34,000 total (Gender ratio: 34% Nationality ratio: Agriculture sector 90:10; all other sectors 70:30) (reporting against targets for 2025) |  | Workers on low incomes or businesses perceive that the potential long-term benefits of contributing to the SSC and participation in the formal economy outweigh any short-term costs or risks and will contribute to the SSC over the medium to longer term.
|  | Achieved |  | 2,842 (of which 50% women and 37% non-Jordanian) Nationality ratio: agriculture sector 33:67 (Jordanian: non-Jordanian), all other sectors 64:36 (Jordanian: non-Jordanian) | 10,416 total (7,447 in phase 2) Phase 2 results Gender ratio: 32% female/ 68% male. Nationality ratio: 53% Jordanian/47% non-Jordanian. 30% of participants were Syrian refugees. | 40,556 total Gender ratio: 21% female/79% male. Nationality ratio: 47% Jordanian/53% non-Jordanian. 30% of participants were Syrian refugees. | 41,578 total Gender ratio: 22.3% female / 77.7% male. Nationality ratio: 47.0% Jordanian/ 53.0% non-Jordanian. 21.7% of participants were Syrian refugees
Source: ILO Estidama++ Fund – Extension of Coverage and Formalization Project Summary May 2023 and Estidama++ annual progress reports
Note: SSC does not currently have data on the disability status of its insured individual meaning data can not currently be disaggregated by disability.
| Output Indicator 2.2 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| No of participants reached in outreach and information sessions (Age, sex, migrant status) | Planned | 0 | N/A | At least 600 participants reached each year (reporting on 2023 calendar year) | At least 600 participants reached each year (reporting on 2024) | At least 600 participants reached each year (reporting on 2025)
|  | Achieved |  | 1150 | Total of 312 participants: 285 participated in face-to-face information sessions and 27 employers/representatives from 27 firms were visited to raise awareness about Estidama++. | 606 participants | 174 participants registration support (SSC services) + 34 participants (direct inperson session). Total of 208 participants
Source: Source: ILO Estidama++ Fund – Extension of Coverage and Formalization Project Summary May 2023 and Estidama++ annual progress reports
| Output Indicator 2.3 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| Percentage of targeted vulnerable workers and employers who receive information on Social Security (Age, sex, migrant status, sector, employment type) and no. of messages sent to male and female vulnerable workers | Planned | 0 | N/A | 100% (reporting on 2023 calendar year) At least 100,000 messages exchanged each year | 100% (reporting on 2024) At least 100,000 messages exchanged each year | 100% (reporting on 2025) At least 100,000 messages exchanged each year
|  | Achieved |  | Outreach activities undertaken through face to face and WhatsApp channels. Type of employment of the respondents: 10.79% employers, 34.52% self-employed, 54.68% wage workers Sex: Male 67.97% and Female 32.03% | 100%. More than 385,000 SMS and 43,000 WhatsApp messages sent to workers and employers to inform them about registration, benefits, and grievances. | 100% 328,629 messages were sent to workers to inform them about registration and payments and more than 51,204 conversations via WhatsApp chatbot were exchanged with existing E++ beneficiaries | 100% of messages sent to workers and employers 28.8% on average reported receiving messages each quarter, sampled from Field Monitoring activities 243,003 digital messages were delivered to Estidama++ beneficiaries, including 195,155 SMS notifications and 47,848 interactions through the SSC WhatsApp chatbot
Source: ILO Estidama++ Fund – Extension of Coverage and Formalization Project Summary May 2023 and Estidama++ annual progress reports
Note: SSC does not currently have data on the disability status of its insured individual meaning data can not currently be disaggregated by disability.
INPUTS (£) | FCDO (£) |  | Govt (£) |  | Other (£) | Total (£) | FCDO SHARE (%)
FCDO (FTEs)
IMPACT WEIGHTING (%) | 30%
OUTPUT 3 Social protection TA and Evidence | Output Indicator 3.1 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027) | Assumptions
Provision of TA, evidence and advocacy builds an understanding of, and demand for, inclusive and shock responsive SP and the efficiency/vfm benefits of aligning national and humanitarian systems | No. of analyses (e.g. political economy), evidence-based and good practice resources, and strategies (e.g. Stakeholder engagement, GESI, Communications, VFM) produced, routinely updated and disseminated where appropriate. | Planned | No systematic and comprehensive assessment of Jordan's social protection system capacity needs, gaps and priorities. Supporting analysis required to effectively engage with GoJ not commenced. | N/A | ILO- 1 legal study Shamil - By March 2024, a detailed Capacity Needs Mapping (CNM) Assessment, TA Mapping Exercise, Political Economy Analysis, Stakeholder Engagement Strategy and Map, GESI strategy and Communications Strategy have been developed. Shamil (social security) - At least 4 resources/products provided by Shamil to the GoJ and stakeholders (cumulative) | ILO- 1 global evidence study on contribution subsidies Shamil - The CNM and other analysis provides the foundation for TA annual work plans. CNM, PEA, Stakeholder Strategy and Communications Strategy updated annually. Shamil (social security) - At least 6 resources/products provided by Shamil to the GoJ and stakeholders (cumulative) Shamil (social services) - At least 2 resources/products provided by Shamil to the GoJ and stakeholders (cumulative) | ILO- 1 report detailing lessons learnt and good practices for Estidama++, 1 costing and fiscal space analysis and 1 study on benefit attractiveness and recommendations Shamil - The CNM and other analysis provides the foundation for TA annual work plans. CNM, PEA, Stakeholder Strategy and Communications Strategy updated annually. Shamil (social security)- At least 8 resources/products provided by Shamil to the GoJ and stakeholders (cumulative) Shamil (social services)- At least 3 resources/products provided by Shamil to the GoJ and stakeholders (cumulative) |  | • Providing knowledge, awareness and understanding will generate a shift in thinking and will generate political will to create fiscal space for building an inclusive social security system. • SSERJ project components will demonstrate a harmonised approach towards social protection and labour market reforms. • That GoJ can absorb additional capacity building efforts, and public servants can participate effectively in activities or pilots initiated by SSERJ.
|  | Achieved |  | N/A | ILO – ILO published a paper on Legislative and Policy Coherence on the Extension of Social Security Coverage in Jordan. Shamil – CNM Assessment, TA Mapping Exercise, PEA, Stakeholder Engagement Strategy and Map, GESI strategy and Communications strategy have all been developed. Shamil – 12 resources provided to GoJ (policy papers and presentations). | ILO- A global study on contribution subsidy, with data from 26 countries. Completed a CNM for the Ministry of Finance. PEA updated on a quarterly basis using Everyday Political Economy Analysis framework. Shamil (social security)- 44 (cumulative) resources provided to GoJ (policy papers and presentations) (28 achieved this year) (Details in Annex 1) Shamil (social services)- 10 resources provided to GoJ (policy papers and presentations) (Details in Annex 1) | ILO- 1- Fiscal space analysis for a national contribution subsidy program, assessing funding availability from reserves and other government stakeholders 2- SSC White Paper on Social Security reforms: visioning exercise on the future of Jordan’s social security system, addressing pressing challenges and laying out a forward-looking intention for how Jordan can build a resilient, inclusive and sustainable social security system that promotes employment and fosters economic growth. 3- Qualitative and quantitative study with the World Bank on incentives for social security participation, generating evidence on behavioural and financial factors influencing participation decisions among self-employed individuals. Four additional research and evidence workstreams pursued including the finalisation of a global study on contribution subsidies. Shamil (social security)- 40 (cumulative) resources provided to GoJ (policy papers and presentations) 4 resources provided to GoJ this reporting year (policy papers and presentations) Shamil (social services)- Cumalatively 8 resources provided to GoJ (policy papers and presentations)
Source: ILO Estidama++ Fund – Extension of Coverage and Formalization Project Summary May 2023 and annual progress reporting; Shamil indicators are based on output indicators 2.1 and 4.1 in the Shamil logframe.
| Output Indicator 3.2 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| No. of capability building sessions for GoJ officials and wider stakeholders relating to inclusive social protection and number of GoJ staff trained. | Planned | Key gaps in understanding across government and other key stakeholders of wider elements of social protection. | N/A | ILO - 3 capacity building sessions on extension of coverage held with support of the project and 20 social security staff trained to conduct outreach activities each year (reporting on 2023). Shamil - (social security) At least 4 (cumulative) sessions provided by Shamil to the GoJ and stakeholders, to at least 12 different stakeholders (cumulative). At least 100 GoJ staff trained; 50% women and 1% persons with disabilities | ILO- 3 capacity building sessions on extension of coverage held with support of the project and 20 social security staff trained to conduct outreach activities each year (reporting on 2024). Shamil (social security)- At least 8 (cumulative) sessions provided by Shamil to the GoJ and stakeholders, to at least 12 different stakeholders (cumulative). At least 110 GoJ staff trained; 50% women and 1% persons with disabilities. Shamil (social services) - At least 2 sessions provided by Shamil to the GoJ and stakeholders, to at least 4 different stakeholders (cumulative). Figures for staff trained on social services TBD based on scoping findings. | ILO- 20 social security staff trained to conduct outreach activities each year (reporting on 2025). Shamil (social security) - At least 12 (cumulative) sessions provided by Shamil to the GoJ and stakeholders, to at least 12 different stakeholders (cumulative). At least 115 GoJ staff trained; 50% women and 1% persons with disabilities Shamil (social services) - At least 4 (cumulative) sessions provided by Shamil to the GoJ and stakeholders, to at least 6 different stakeholders (cumulative)
|  | Achieved |  | N/A | ILO – 3 capacity building sessions attended by government officials relating to extension of coverage efforts on Academy on Social Security (ICT ILO) and the technical seminar on Approaches to the Reform of Social Security systems in the Arab countries (Luxor, Egypt). Over 50 social security branch officials from SSC completed training workshops on raising awareness on social security based on behaviourally informed messages as part of the Randomised Control Trials. Shamil (social security) – 21 sessions provided by Shamil to the GoJ and stakeholders, to 20 different stakeholders (cumulative). 61 GoJ staff trained; 38% women. | ILO- 6 outreach training workshops for over 134 SSC staff. Shamil (social security)- 41 (cumulative) sessions to 38 different stakeholders (cumulative) (23 sessions achieved this year). The Global Disability Summit MENA pre-summit and side-event on disability-inclusive social security were attended by approximately 200 and 500 participants from national and international government and non-government organisations (Details in Annex 1) Shamil (social services)- 6 capacity building activities to 19 different stakeholders (Details in Annex 1) | ILO- Total of 35 officials participated in capacity building activities: Capacity-building for SSC outreach officials, including training workshops reaching 22 officials, aimed at strengthening facilitation skills and improving the delivery of social security information sessions Capacity building through participation of 13 SSC and NAF staff in the Social Security Academy (Turin, September 2025) covering key concepts on social protection systems, coverage extension, financing, and administration. Shamil (social security)- 45 (cumulative) sessions to 38 different stakeholders (cumulative) 3 sessions to 15 stakeholders this reporting year. 615 (cumulative) government & CSO staff trained: 83% GOJ, 17% CSO, 50% women, 1% persons with disabilities 87 government & CSO staff trained: 81% GoJ, 19% CSO, 51% women, 1% persons with disabilities Shamil (social servivces)- 6 capacity building activities to 19 different stakeholders (no activities this year)
Source: ILO Estidama++ Fund – Extension of Coverage and Formalization Project Summary May 2023 and annual progress reporting; Shamil's indicators are based on the Shamil logframe output indicators 1.2, 1.3, 3.2, 3.3, 5.1, 5.2
| Output Indicator 3.3 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| Number of new or strengthened system elements including e.g. MIS, SOPs, knowledge sharing platforms, payment systems etc. that are GESI sensitive | Planned | No systematic and comprehensive assessment of Jordan's social protection system and social welfare system capacity needs, gaps and priorities. | N/A | Shamil - By March 2024, a detailed mapping and mutually-agreed baseline of current SP system capacity is completed; listing of priority areas for strengthening GoJ partners against a vision of what they would like their future capacity to look like. | Shamil (social security) - At least 1 system element strengthened. Shamil (social services) - Detailed scoping of current social services system capacity is completed | Shamil (social security) - At least 1 system element strengthened (social security) Shamil (social services) - At least 1 system element strengthened WB - Design of the Early Warning System (EWS) framework completed and implementation roadmap prepared WB (Accredited Social Work professions)- Accreditation framework and occupational standards designed for selected social work professions WB - Institutional design and staffing plan for the National Social Protection Strategy (NSPS) Implementation Support Unit (ISU) completed WB (National digital systems supporting NSPS implementation)- Functional specifications and development plans for national digital systems prepared WB (Certification and licensing system for social workers)- Certification and licensing framework for social workers designed | WB- Early Warning System established and operational within MoSD WB (Accredited Social Work professions)- 5 accredited social work professions established and operational WB (ISU)- NSPS Implementation Support Unit established and fully functional within MoSD WB (National digital systems supporting NSPS implementation)- 5 digital systems developed and operational WB (Certification and licensing system for social workers)- 200 certified and licensed social workers
|  | Achieved |  | N/A | Shamil – CNM completed identifying priority areas for GoJ partners, incorporated into Shamil’s Year 1 workplan. | Shamil (social security)- 7 system elements strengthened Shamil (social services)- Scoping could not be completed. Draft reports produced on: 1. Professionalisation of Social Work in Jordan: Vision and Roadmap 2. Scoping study of Jordan social work 3. Final reports and presentations on assessments of 3 different sub-system elements were completed (Details in Annex 1) | Shamil (social security)- 4 systems elements strengthened. Shamil (social services)- Cumulatively 1 new system element produced: Business Requirement Document produced for online registration system for social workers WB - -EWS framework designed, and under approval process -Designed for 5 selected social work professions, under review and consultation process -Institutional design and staffing plan for NSPS ISU completed -Specifications and development plans for 3 digital systems prepared and under approval process -Framework was designed pending formal approval
Source: Shamil Inception and annual workplans and progress reporting. Indicators relate to Shamil logframe output indicators 1.1 and 3.1
| Output Indicator 3.4 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| Number of policy dialogue engagements on inclusive social protection (social security and social services) that are delivered to key stakeholders across GoJ that are GESI sensitive | Planned | 0 | N/A | Shamil (social security) - At least 15 policy dialogue engagements organised by Shamil with the GoJ and stakeholders | Shamil (social security)- At least 20 (cumulative) policy dialogue engagements organised by Shamil with the GoJ and stakeholders Shamil (social services) - At least 10 policy dialogue engagements organised by Shamil with the GoJ and stakeholders | Shamil (social security)- At least 25 (cumulative) policy dialogue engagements organised by Shamil with the GoJ and stakeholders Shamil (social services) - At least 15 (cumulative) policy dialogue engagements organised by Shamil with the GoJ and stakeholders
|  | Achieved |  | N/A | Shamil - Achieved: 22 policy dialogue engagements. NB: defined as policy engagement when meeting with Secretary General level equivalent or higher. | Shamil (social security)- 79 (cumulative) policy dialogue engagements 43 in 2024 (Details in Annex 1) Shamil (social services)- 15 policy dialogue engagements (Details in Annex 1) | Shamil- 81 (cumulative) policy dialogue engagements 2 this reporting year. Shamil (social services)- 15 policy dialogue engagements cumatively, none this reporting year.
Source: Shamil Inception and annual workplans and progress reporting. Information relates to Shamil logframe output indicators 2.2 and 4.2
INPUTS (£) | FCDO (£) |  | Govt (£) |  | Other (£) | Total (£) | FCDO SHARE (%)
FCDO (FTEs)
IMPACT WEIGHTING (%) | 25%
OUTPUT 4 Economic inclusion evidence and TA | Output Indicator 4.1 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027) | Assumptions
Evidence generation, dissemination and TA to decision makers which builds an understanding and demand for enhanced economic inclusion of refugees, women and people with disabilities | No of evidence base and good practice resources and products generated and disseminated to key stakeholders including GoJ on Economic inclusion (including labour market access by refugees) | Planned | 0- Limited public interest and awareness of awareness about the importance of the economic inclusion of refugees | N/A | UNHCR secondee deployed | UNCHR - At least 2 evidence products completed Shamil (economic inclusion) - At least 1 resources/products provided by Shamil to the GoJ and stakeholders (cumulative) | Shamil (economic inclusion) - At least 2 resources/products provided by Shamil to the GoJ and stakeholders (cumulative) |  | • SSERJ project components will demonstrate a harmonised approach towards social protection and labour market reforms. • That GoJ can absorb additional capacity building efforts, and public servants can participate effectively in activities or pilots initiated by SSERJ.
|  | Achieved |  | N/A | UNHCR secondee deployed, commencing October 2023. IGC grant on cash assistance granted to the UNHCR. | UNHCR secondees: Completed World Bank SWIFT poverty profile on refugees (March 2025). Econometric analysis of the skills mapping survey. Published infographics on Higher education, non-Syrians' skills ICT, construction, agricultural sectors. Survey on informal refugee businesses in Zaatari camp. Provided evidence for refugee work permits recommendations. IGC grant on cash assistance; MoU signed with Bentley and Emory. UNHCR Socio-economic Survey: two reports, one-pagers, dashboards. Contributed to UNHCR socio-economic update reporting: two reports (Q2 & Q4 2024). Provided data for Annual report. | Shamil (economic inclusion) 3 cumulative resources/products with 2 in the last reporting year: 1. Childcare study report 2. Childcare policy brief
Source: UNHCR and Shamil logframe output indicator 6.1
| Output Indicator 4.2 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| No. of capability building sessions for GoJ officials and wider stakeholders and number of GoJ staff trained relating to the challenges faced by women and persons with disabilities in accessing jobs. | Planned | 0 | N/A | N/A | N/A | Shamil (economic inclusion) - At least 2 (cumulative) sessions provided by Shamil to the GoJ and stakeholders, to at least 12 different stakeholders (cumulative)
|  | Achieved |  | N/A | N/A |  | Shamil (economic inclusion)- Cumulatively 2 sessions. This reporting year, 1 session took place: webinar presentation on results of childcare study to 10 stakeholders. 23 staff trained this reporting year and 26 cumulatively.
Source: Information from Shamil logframe output indicator 5.1 and 5.2
| Output Indicator 4.3 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| Number of policy dialogue engagements on inclusive labour market outcomes that are delivered to key stakeholders across GoJ that are GESI sensitive | Planned | 0 | N/A | N/A | Shamil (economic inclusion) - At least 5 policy dialogue engagements organised by Shamil with the GoJ and stakeholders | Shamil (economic inclusion) - At least 10 (cumulative) policy dialogue engagements organised by Shamil with the GoJ and stakeholders.
|  | Achieved |  | N/A | N/A |  | Shamil (economic inclusion)- 11 policy dialogue engagements. No new activities this reporting year.
Source: Information from Shamil logframe output indicator 6.2
| Output Indicator 4.4 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| # of refugees matched to income-generating activities through the two-way referral system. | Planned | 0 | N/A | N/A | by June 2025: 2250 | by June 2026: 5,250
|  | Achieved |  | N/A | N/A | 4,500 refugees referred for jobs through partnerships with national institutions, NGOs, and private sector companies. Up to 2,000 refugees positioned to be referred to IT sector opportunities through the Ministry of Digital Economy and Entrepreneurship (MoDEE) initiative. | N/A (referral mechanism shifted methodology and will reprise later in the year).
| Output Indicator 4.5 |  | Baseline | Milestone 1 (March 2023) | Milestone 2 (March 2024) | Milestone 3 (March 2025) | Milestone 4 (March 2026) | Target (May 2027)
| # of people equipped with the skills/resources to increase their self-reliance or readiness for participation in the labour market (disaggregated by age, gender, nationality, disability) | Planned | 0 | N/A | N/A | by June 2025: 370 | by June 2026: 868
|  | Achieved |  | N/A | N/A | Total reached: 429. - 199 (158 females and 41 males) farmers and MSMEs14 trained in climate-smart agriculture, increasing awareness of climate risks and resilience strategies. - 20 Agricultural Credit Corporation (ACC) loan officers capacitated in climate adaptation financing and project evaluation, enhancing ACC’s role as a sustainable finance partner. - 150 stakeholders (120 refugees, 30 institutions) surveyed, providing evidence on refugee access and attitudes toward agricultural finance. - 60 youth trained in entrepreneurship, identifying agri-food challenges and proposing innovative, market-informed solutions. | 1,350 refugees and host‑community members (women, men, and youth, disaggregated by age and nationality) were supported through skills development and livelihood‑related interventions.
INPUTS (£) | FCDO (£) |  | Govt (£) |  | Other (£) | Total (£) | FCDO SHARE (%)
FCDO (FTEs)
IMPACT WEIGHTING (%) | 15%

## Change Frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
1 | All | The logframe has been significantly revised to incorporate the new humanitarian components of SSERJ, approved via a Business Case Addendum, and to include more robust indicators reflective of the new programme Theory of Change finalised in early 2024. | SSERJ programme team | 2024
2 | Outcome and output indicators | Outcome and output indicators were added to reflect the agreement with WFP on (Enhancing refugees’ economic participation in Jordan). | SSERJ programme team | 2024-12-01
3 | Output 4.2 | Output indicator 4.2 milestones reduced | SSERJ programme team | 2025-01-01
4 | Output 3 | Adding indicators related to the WB project under output 3 | SSERJ programme team | 2026-03-01
5
6
7
8
9
10