## Annual Review Template
Title: Strengthening Societal and Economic Resilience in Jordan (SSERJ)
Programme Value £ (full life): £95m		Review date: June 2026
Programme Code: 301109	AMP start date: 13 March 2022	AMP end date: 30 April 2027

Summary of Programme Performance
Year	2023	2024	2025	2026	2027
Overall Output Score	A	A	A	A
Risk Rating	Major	Major	Major	Moderate

DevTracker Link to Business Case:	SSERJ Business Case and Summary / SSERJ Business Case Addendum
DevTracker Link to results framework:	SSERJ Logframe

OVERVIEW

Description of programme

The £95m Strengthening Societal and Economic Resilience in Jordan (SSERJ) programme has just concluded its fourth year of implementation. Over the past year, it continued to provide humanitarian assistance to refugees and vulnerable Jordanians, and to contribute to strengthening Jordan’s national social protection system. This supports the delivery of British Embassy Amman’s (BEA) Country Business Plan goal (2025/2026) to enhance the social and economic resilience of refugees and vulnerable Jordanians; increase economic stability and economic opportunities in Jordan.

The key focus of SSERJ over the past year has been on:

1. Assisting Jordan as it continues to host refugees – Jordan hosts one of the largest refugee populations per capita, impacting on public finances, natural resources and infrastructure. SSERJ has continued to fund life‑saving cash assistance for refugees, helping preserve Jordan’s stability and reducing drivers of unsafe onward migration towards Europe and the UK.
2. Supporting pathways to self‑reliance for refugees and vulnerable Jordanians. Beyond immediate humanitarian relief, SSERJ contributed to initiatives that strengthen economic participation and resilience in line with the Jordan Compact[1]. This includes improving evidence on what drives self‑reliance, supporting programmes that enhance economic opportunities, and helping widen access to social protection schemes. The programme also worked to improve the coherence between humanitarian aid and national social protection structures, ensuring that assistance supported both urgent needs and long‑term development.
[1] The Jordan Compact (2016) is a landmark agreement that linked international support to Jordan’s commitment to provide Syrian refugees with access to jobs, education, and services, while strengthening the country’s economic resilience. For more information see here: https://www.refugee-economies.org/our-work-16-21/innovative-practices/jordan-compact.
3. Helping the Government of Jordan (GoJ) build a more inclusive and resilient national social protection system and support the implementation of their National Social Protection Strategy 2025-2033 (NSPS) underpinning Jordan’s Economic Modernisation Vision (2022–2033) and reinforcing a more durable social contract between the state and its citizens.

There are several changes to note that occurred during this reporting period:

- A new component delivered by the World Bank (WB) was approved and added as a new project in Q2 2025. This project supports priority reforms under Jordan’s NSPS 2025-2033 through a combination of government-led implementation and strategic technical assistance (TA).
- During early 2025, the programme undertook a reprioritisation of resources across portfolios, working closely with the GoJ to assess where UK support would have the greatest impact within the social protection sector. Considering these discussions and the reduction of the UK Overseas Development Assistance (ODA) funding to 0.3% of gross national income, the decision was taken to close the Shamil TA component early, with a six-month notice period, in September 2025.
- Several activities finished to their planned end dates, including support to the Social Security Corporation (SSC) and the International Labor Organisation (ILO) for Estidama++ which ended in February 2026. Technical M&E advisory support to United Nations High Commissioner for Refugees (UNHCR) ended in March 2026.
- Technical economic advisory support to UNHCR was reviewed and redeployed to the United Nations Children's Fund (UNICEF) to support with social protection systems strengthening.

The next reporting year will see SSERJ enter its final year as planned from the outset of the programme. Several further changes are planned for the coming year:

- BEA’s new four-year Jordan Humanitarian and Systems Strengthening Programme (JHASS) began in April 2026. Given SSERJ has nearly reached its business case headroom, additional finance to several partners under SSERJ for 2026-2027 will transition to JHASS – notably UNHCR and the World Food Programme (WFP) for cash assistance and the World Bank for social protection. Similarly new deployments for the humanitarian and social protection sectors will start under the JHASS programme.
- A new 11-month project with the ILO is planned to provide technical support to the SSC to promote the social security reform, the institutionalisation of Estidama++ and help to Syrian refugees to access benefits on leaving Syria.

Summary supporting narrative for the overall score in this review

The SSERJ programme is awarded an A following this year’s annual review. This reflects that most result targets were met, with some results exceeded and some moderately not met. Positive results included 41,578 participants enrolled in social security through the Estidama++ programme, 53% of which were non-Jordanian, and over 243,000 digital messages sent to Estidama++ beneficiaries. Furthermore, ILO exceeded the analytical, evidence-based and strategic products target with seven strategic and quality products. Cash assistance through output one mostly met its targets, although these had needed to be revised during the programme. Technical deployments continued to demonstrate value for money.

Major lessons and recommendations for the year ahead

Lessons generated from SSERJ should be applied to the JHASS programme. JHASS will include core humanitarian, education and systems strengthening activities and has been designed to follow on from SSERJ and use lessons from it. Given this programme will continue working on activities implemented under SSERJ it is important that the detailed lessons from SSERJ are applied to it.

UNHCR and WFP need to strengthen their value for money (VfM) strategies and improve the accuracy of Proxy Means Test (PMT) targeting. Progress on developing value for money (VfM) strategies with WFP and UNHCR remains limited. Under the Jordan Humanitarian and Systems Strengthening Programme (JHASS), further efforts could usefully focus on strengthening VfM reporting, including the development of clearer cost-effectiveness metrics and benchmarking for cash assistance.
These considerations also highlight the importance of situating improvements in VfM and targeting within the broader strategic direction of cash assistance in Jordan. In particular, ensuring alignment with the priorities of the Jordan Response Plan (JRP) including sustainability and closer alignment with national social protection systems will be important to support a more coherent and future-oriented approach to cash programming within the overall response.

Programme effectiveness depends not only on delivering assistance to large numbers of people, but also on ensuring transfer values remain sufficient to meet minimum needs over time. This year’s cash assistance activities demonstrated that meeting output targets during periods of reduced humanitarian funding does not prevent deterioration in outcomes when cash assistance coverage and transfer values fall below minimum thresholds. Future programme design must therefore explicitly account for adequacy risks and the protection consequences of scenarios where available donor funding declines significantly.

Embedding transparent prioritisation and monitoring systems from the outset is essential in protracted displacement contexts. Strengthened vulnerability analysis and outcome monitoring improved humanitarian decision-making during periods of funding pressure and reduced coverage and should be treated as core design features, rather than adaptive fixes, in the next programme

FCDO should continue to support work and engage around the future of Estidama++ to promote sustainability. The programme closed having significantly exceeded several key targets. Given the success of the pilot, the aim is to see this operationalised as part of the SSC rather than a stand-alone donor financed project to ensure its long-term sustainability. Progress has been made towards this with a national contribution subsidy included in the SSC’s Visioning White Paper and legal provisions for this within the Social Security Reform Bill but more technical support and engagement is needed to identify, and build will for, national financing. FCDO intends to extend its support with the ILO so it can provide further support on this topic. It should also continue to engage with the GoJ and other donors interested in this initiative and around further contribution subsidy pilots.

FCDO should work with partners to ensure departing Syrian refugees access their social security benefits. As refugees continue to return to Syria, FCDO should continue to work with partners to ensure they access their lump sum payments built through Estidama++ to support them in Syria, while at the same time supporting SSC to identify a long-term approach to cross border working. FCDO’s planned further funding for the ILO will address this.

FCDO should continue to support the SSC to implement its reform vision. Estidama++ made an important contribution to helping the SSC set out its medium/long-term reform agenda. This is a pivotal year for social security reform in Jordan and FCDO should continue to engage to ensure the opportunity for reform which benefits the most vulnerable is grasped. Additional funding for the ILO is planned for this.

Strengthening social security remains important for reducing vulnerability and supporting stability in Jordan but contextual changes mean other forms of social protection may provide better avenues for supporting refugees and reducing humanitarian needs moving forwards. The Estidama++ programme exceeded its targets for reaching Syrians. However, the removal of the work permit waiver for Syrian refugees in Jordan has significantly affected the ability of refugees to work in the formal labour market and thus participate in social security moving forwards, even when subsidised. As such, supporting the shock responsiveness of Jordan’s social protection system and strengthening social care (open to refugees) is deemed a better route for supporting Syrian refugees via national systems and reducing humanitarian needs. Work on these themes began this year via the WB and will continue under JHASS. These contextual changes highlight the importance of combining programming with diplomacy to seek to address contextual and political factors and changes which can affect programme delivery.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The SSERJ theory of change (ToC) sets out that the programme’s intended impact is that societal and economic resilience and stability is maintained in Jordan. To achieve this, it is working towards the long-term outcome that Jordan has social protection systems (national and a parallel system for refugees for support which can’t be provided via national systems) that help all individuals address risks across the lifecycle and from shocks, empowers women and persons with disabilities and generates economic growth and a stronger social contract.

The ToC articulates that this impact and long-term outcome will be achieved through four main streams of work or outputs and pathways that seek to support vulnerable Jordanians and refugees:
1. Humanitarian cash transfers will be disbursed to the most vulnerable refugees. This critical social safety net enables them to meet their basic needs, contributing to greater income security across the population and through this leading to greater social and economic resilience.
2. Vulnerable workers (majority Jordanian, but also refugees) encouraged to join the Estidama++ scheme through which they’ll be provided with subsidised social security. This will help strengthen Jordan’s social protection system by enabling it to better cover and formalise vulnerable workers.
3. TA, evidence and advocacy will be provided to promote inclusive social protection in Jordan and generate demand for it. This will build the awareness of decision makers and stakeholders of the value of an inclusive, multi-tiered and shock responsive social protection system and support them to put this in place which will strengthen the resilience of vulnerable Jordanians and refugees.
4. Evidence and TA will also be provided to build an understanding of and demand for the self-reliance of refugees, women and persons with disabilities. This effort seeks to stimulate policy discussions on how the labour market can offer more opportunities for these groups, leading to enhanced income security and greater societal and economic resilience. However, the current policy environment means the economic inclusion of refugees is a challenging issue which limits expectations on what can be achieved in this workstream.
These workstreams are ongoing, supported by diplomatic engagement activities of the BEA.

The SSERJ programme’s intended impact has remained consistent with that set out and approved in the original business case. In 2023/2024, as reported in the last annual reviews, the Theory of Change (ToC) was refined by:
- Expanding it to include the additional humanitarian streams of work - humanitarian cash transfer and evidence generation and TA on the economic inclusion of refugees - which were approved through a business case addendum in 2023.
- Providing a more detailed causal pathway, with increased detail in particularly on the short and medium-term outcomes essential for instigating change.
- Reassessing the indicators to ensure a robust measurement framework for each phase of change.
Over the past year, output four language on economic inclusion has been amended in line with the recommendation in last year’s AR. This was to change it to ‘self-reliance’ to better reflect the political realities in Jordan while still aligning work with the durable solutions approach[2].
[2] The durable solutions approach is a long-term strategy of the United Nations that enables displaced people to rebuild their lives through return, local integration, or resettlement.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The SSERJ programme is now at an advanced stage of implementation and is moving into its final year. This means we can now better judge whether it will achieve its intended impact and outcome level results.

In terms of social protection aspects, data on outcome indicators is mostly positive. Estidama++ is continuing to exceed targets for the number of participants transitioning to regular social security at the end of the scheme. 84.2% of participants completing the scheme had transitioned to regular social security by December 2025 compared to the target of 60%.

SSERJ recommended legislative, policy or administrative changes have been adopted by the GoJ. The programme has contributed to major policy initiatives for example: the Social Security’s Visioning White Paper which sets out their long-term reform vision; the inclusion of a commitment to introducing a minimum income for older persons into the National Strategy for Older Persons 2024-2030, and the Ministry of Finance’s draft strategy: linking fiscal policy and social protection.

Results on whether a sustainable model for Estidama++ has been institutionalised will be assessed in the final evaluation planned for summer 2026. However, at this stage we know progress has been made with a national contribution subsidy included in the SSC’s Visioning White Paper, and provisions for this included in the Social Security Bill. However, finance from Jordanian sources have not yet been identified and requires further engagement and support. FCDO plans to continue to fund the ILO to provide this. However, finance for a next pilot phase of a contribution subsidy will be provided by KfW and Norway. As such the outcome has not been achieved but there has been progress towards a future phase of Estidama++.

While Estidama++’s outcome results are mostly positive, contextual changes have limited the ability of social security to build refugee self-sufficiency in line with our humanitarian exit strategy. The refugee work permit waiver removed in 2024 has significantly increased costs for refugees to work, formally creating barriers to their social security participation. As such in BEA’s successor programme, the focus will shift to shock responsive social protection and social care services which are considered better able to assist refugees and reduce potential future humanitarian needs.

In terms of humanitarian activities, the programme aims to help achieve the outcome of more resilient and sustainable food practices and a reduction in the proportion of refugees meeting needs for basic and domestic items from humanitarian assistance. The aim of this is to have the impact of reduced vulnerability amongst registered refugees, as measured by the proportion of Syrians with high or severe basic needs vulnerability and debt.

Unfortunately, there has been a deterioration in humanitarian indicators since the beginning of the programme and baseline data from 2021 and 2022. Similarly, food security conditions among refugees in Jordan remain severely constrained. According to (WFP), the overall frequency of food insecurity remains extremely high, with the latest food security outcome monitoring (Q3–Q4 2025 referenced in 2026 WFP briefs) indicating that approximately 50% of refugees in camps and 81% of refugees in host communities are food insecure. These figures reflect a sustained deterioration compared to earlier years and are driven by reduced assistance levels, rising food prices, and limited income opportunities. In 2026, WFP continues to provide reduced monthly food assistance of JOD 15 (USD 21) per person, which covers only part of minimum food needs, while significant numbers of refugees (particularly in host communities) have been excluded from assistance due to funding shortfalls, further exacerbating food insecurity risks[3].
[3] 032026 Jordan Country Brief.pdf

While earlier gains in acceptable food consumption observed before 2022 have not been reversed entirely in camps, negative food‑related coping strategies are now widespread across all locations, including reducing meal portions, skipping meals, and prioritising children’s consumption. WFP warns in its 2026 country briefs that continued funding gaps risk pushing many households from stress‑level coping into crisis‑level coping, especially among refugees in host communities who face higher living costs.

At the impact level, poverty and indebtedness remain persistently high. UNHCR’s most recent consolidated socio‑economic findings (referenced in 2026 operational and statistical updates) confirm that around 66% of registered refugees in Jordan continue to live below the poverty line, a level that has not meaningfully improved since 2023. In parallel, approximately 9 out of 10 refugee households report carrying debt, primarily to meet basic needs such as food, rent, utilities, and health expenses. Debt levels remain particularly acute among refugees living in host communities, where reliance on informal borrowing is widespread and increasingly unsustainable[4].
[4] 5.1.1_Annual_Results_Report

These negative trends are being driven by decreasing donor humanitarian assistance for refugees and global and regional conflicts. In response, humanitarian partners have increasingly pursued cash consolidation and harmonisation approaches to prioritise the most vulnerable households and improve efficiency under reduced funding envelopes. Despite this challenging context, SSERJ has continued to play an important role in mitigating further deterioration in refugee vulnerability and supporting more coordinated humanitarian responses.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Given the progress to date and contribution to the ToC, the SSERJ programme should continue until its planned end date of April 2027. SSERJ represents good VfM based on available data. It remains relevant to delivery of the impact, outcomes and key outputs outlined in the ToC. The programme is yielding positive results at the output level, significantly exceeding some targets, and is well placed to deliver further results in the coming year.

Impact and outcome indicators are mostly positive for social protection aspects suggesting a positive contribution to resilience and stability in Jordan. Impact and outcome indicators have seen some deterioration for humanitarian components due to contextual changes, in particularly the decline of international financing. However, the programme has contributed positively towards these preventing further deterioration than there otherwise would be.

The SSERJ programme has delivered against the FS’ priorities of: ‘Development’, via supporting humanitarian and human capital objectives; ‘Migration’, via supporting individuals to stay in their region of origin and preventing unsafe onward migration; and ‘Security’ via contributing to stability in Jordan and the Middle East through reducing vulnerability and strengthening the social contract. It is well-aligned with the new BEA Country Business Plan (2026-2029) delivering against the goal to ‘Enhance resilience, including for refugees, and promote inclusive national systems to reduce humanitarian need and contribute to stability.’

The final year of SSERJ will primarily consist of additional technical support to UNICEF to further support the implementation of the NSPS; continuing technical support to the GoJ to implement the NSPS via the WB; and additional support to the ILO to help the SSC to institutionalize Estidama++ and pursue its reform vision. The evolution of the programme thus aligns with FCDO’s four shifts to development particularly:

- Service delivery to systems strengthening – financial aid to the SSC has ended with the conclusion of Estidama++ and will not be continued. Instead, support will be provided next year as finance to the ILO for TA for social security systems strengthening. TA to support the GoJ to implement the NSPS will also continue.
- Grants to expertise – Technical support to UNICEF will continue into the next reporting year, providing quality social protection support through UK advisory expertise.

After the end date of SSERJ, certain activities will continue to be supported by BEA under its new humanitarian programme - JHASS. JHASS is a £73 million programme which will last for four years. It is a strategic and integrated programme which combines core humanitarian support (including cash assistance), education support, and systems strengthening activities. JHASS takes a coordinated, holistic approach with built in flexibility - through an Integrated Risk Facility to adapt to shocks - and strong focus on localisation to ensure principled and context specific delivery. It has been designed drawing on lessons from SSERJ and other BEA programmes.

## C. DETAILED OUTPUT SCORING

Output Title	Disbursement of Humanitarian Cash Transfers to the most vulnerable Refugees in Jordan
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of reached refugees with cash assistance through WFP add new/old, supported refugee in the disaggregation.	210,924	210,924
1.2 Number of people who received cash assistance (unique individuals) through UNHCR	200,000	195,308

Briefly describe the output’s activities and provide supporting narrative for the score.

During the reporting period, WFP and UNHCR continued to deliver large‑scale humanitarian cash assistance to refugees in Jordan through established and aligned cash‑based transfer modalities, including digital cash‑based food assistance and multi‑purpose cash assistance (MPCA). Delivery remained fully aligned with the agreed programme design and was supported by strengthened vulnerability‑based targeting, digital payment systems, routine verification exercises and enhanced monitoring of food security, basic needs and protection outcomes.

Implementation took place within a significantly deteriorating funding and operating environment, compounded by major contextual shifts in Jordan’s refugee landscape. Sustained funding shortfalls since mid-2023 required deliberate, evidence-based reprioritisation of caseloads and transfer values, particularly for WFP. As documented in WFP Jordan’s 2025 Annual Country Report, several concurrent factors drove changes in the assisted caseload during the year. Most significantly, approximately 177,000 Syrian refugees voluntarily returned to Syria in 2025, representing around 30 percent of those registered with UNHCR, with nearly 80,000 of the returnees previously assisted by WFP, accounting for a substantial share of the reduction in active caseloads. In parallel, WFP conducted routine individual-level verification and eligibility checks, removing additional households no longer meeting assistance criteria. These changes were further compounded by acute funding constraints, which led to sustained reductions in transfer values back in 2024 (from JOD 23 to JOD 15 per person) and tightened prioritisation towards the most vulnerable households.

As a result, the original milestone of 290,615 refugees under Indicator 1.1 no longer reflected the realistic or operationally agreed scale of delivery for the review period and as such has been updated. WFP ultimately reached 210,924 refugees with cash‑based food assistance, a figure that reflects deliberate programme adjustments—including refugee returns, verification results and funding constraints. UNHCR delivered MPCA to 195,308 unique individuals against a milestone of 200,000, remaining broadly on track despite facing similar financing pressures and tightened eligibility criteria.

Across both agencies, delivery capacity and operational performance remained strong, with continuity of assistance maintained for prioritised households. Caseload adjustments were systematically managed to preserve life‑saving support for the most vulnerable rather than maintaining higher coverage at unsustainable adequacy levels. While overall coverage declined relative to original milestones, this reflects external constraints rather than weaknesses in programme implementation. On this basis, the output is scored A, reflecting effective delivery and responsible adaptive management in an increasingly constrained humanitarian environment.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Over the period under review, no changes were made to the core objectives or delivery modalities of the output. However, significant adjustments were required to programme scale, transfer values, and targeting approaches in response to sustained overall funding shortfalls and changes in the refugee context leading. WFP maintained reduced transfer values at USD 21 per person per month throughout 2025 and implemented an evidence-based retargeting exercise prioritising the most and ultra-vulnerable households. This resulted in a substantial reduction in the assisted caseload, driven by a combination of funding constraints, routine verification and eligibility exercises, and voluntary refugee returns to Syria. In parallel, UNHCR revised its vulnerability scoring and prioritisation framework, introduced quarterly eligibility cycles, and tightened coverage of MPCA to focus on households facing the most acute protection and basic needs risks.

As a result of this review, planned adjustments focus on implementation refinements rather than changes in scope, including further strengthening vulnerability assessment methodologies, improving inter-agency coordination on targeting, and continuing scenario-based planning to manage funding volatility. Where feasible, milestone targets were calibrated to reflect realistic resource assumptions.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress was made against last year’s recommendations to strengthen prioritisation and programme management under reduced international financing. WFP and UNHCR improved vulnerability‑based targeting, enhanced outcome and protection monitoring, and adopted more systematic eligibility reviews and scenario‑based planning. These measures have generated stronger evidence on adequacy, protection risks and trade‑offs, which will directly inform the transition to the next programme phase.

Key lessons to carry forward into the new programme include:

- Programme effectiveness depends on designing for sustained adequacy, not only delivery at scale. This year demonstrated that meeting output targets under severe fiscal constraint does not prevent deterioration in outcomes when assistance coverage and transfer values fall below minimum thresholds. Future programme design must therefore explicitly account for adequacy risks and the protection consequences of under‑funding scenarios.
- Embedding transparent prioritisation and monitoring systems from the outset is essential in protracted displacement contexts. Strengthen vulnerability analysis and outcome monitoring improved decision‑making under constraint and should be treated as core design features, rather than adaptive fixes, in the next programme. Specifically, for JHASS:

- FCDO should build contingency and scenario planning into the programme architecture, including agreed prioritisation frameworks and minimum assistance thresholds, to enable predictable and accountable responses to funding volatility without repeated disruptive adjustments.
- Use joint WFP–UNHCR analysis on adequacy and protection outcomes to shape programme objectives, indicators and financing discussions, ensuring the new programme is grounded in evidence on what is required to prevent harmful coping strategies and protect the most vulnerable.

Output Title	Vulnerable workers (Jordanians and refugees) and businesses informed about and join the social security scheme through the Estidama++ programme
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 No. of individuals benefiting from income support (coverage reward) and/or contribution subsidies who were previously not covered/registered with SSC (disaggregated by gender, nationality, wage, age, sector).	At least 34,000 total / (Gender ratio: 34% / Nationality ratio: / Agriculture sector 90:10; all other sectors 70:30) / (reporting against targets for 2025)	41,578 total / Gender ratio: 22.3% female / 77.7% male. / Nationality ratio: 47.0% Jordanian/ 53.0% non-Jordanian. 21.7% of participants were Syrian refugees
2.2 No of participants reached in outreach and information sessions (Age, sex, migrant status)	At least 600 participants reached each year (reporting on 2025)	174 participants registration support (SSC services) + / 34 participants (direct in person session). Total of 208 participants
2.3 Percentage of targeted vulnerable workers and employers who receive information on Social Security (Age, sex, migrant status, sector, employment type) and no. of messages sent to male and female vulnerable workers.	100% (reporting on 2025) / At least 100,000 messages exchanged each year	100% of messages sent to workers and employers / 28.8% on average reported receiving messages each quarter, sampled from Field Monitoring activities / 243,003 digital messages were delivered to beneficiaries, including 195,155 SMS notifications and 47,848 interactions through the SSC WhatsApp chatbot

Briefly describe the output’s activities and provide supporting narrative for the score.

A score of 'A' has been given as two results significantly exceeded their targets - the number of individuals benefitting from income support/contribution subsidy and messages exchanged with vulnerable workers - while a third did not meet targets. A high ratio of non-Jordanians/Syrians participation was also achieved.

This output aims to support the formalisation of Jordan’s labour market and enhance the resilience of vulnerable workers, including women and refugees, by supporting the extension of social security coverage to vulnerable groups through the Estidama++ programme. It does this by providing income support (coverage rewards) and subsidising social security contributions to vulnerable groups for a defined period of time (18 or 12 months).[5]
[5] Estidama++ launched in May 2022 and is funded by the UK, Netherlands, and Norway

The Estidama++ project is managed by the SSC, with technical support from the ILO. The implementation of the Estidama++ project’s phase 1 opened in October 2022, running for 18 months, and the phase 2 window was open for applications from September 2023-February 2025, with benefits running for participants for 12 months. The programme closed in February 2026. The BEA participated in joint governance and reporting under the Estidama++ governance structure.

Estidama++ moved into its final stage of implementation over the last year. The SSC, with the support of the ILO, had achieved the enrolment of 41,578 workers as of December 2025. This is an impressive achievement since these results exceeded the target of 34,000 without requiring any additional finance. This number is similar to the 40,556 total beneficiaries as of December 2024, since registration was only open for two further months (January and February) in 2025 and the focus shifted from enrolment to the provision of benefits.

In addition to meeting the milestone for the number of individuals enrolling on Estidama++, a further success has been the continued proportion of non-Jordanian and Syrian refugee enrolment. The level of enrolment of Syrian refugees was low in the first SSERJ annual review (June 2023) but following considerable positive efforts by SSC and ILO in response to the BEA/donors’ feedback, it has finished significantly exceeding targets for enrolling 30% non-Jordanians; 53% of participants were non-Jordanians (including refugees and migrant workers) of which 21.7% were Syrian. That said, the programme has performed less positively on gender (22.3% female participants versus a target of 34%). This primarily reflects the low participation of women in Jordan’s workforce and the greater seasonality of women’s work which reduces the incentives to participate in social security. The ratio of 22.3% is broadly comparable with the gender ratio of overall SSC participants. A targeted campaign on women’s rights and access to social security was commenced to improve the participation of women.

There has been a continued focus on outreach and awareness made by SSC/ILO over the past year, guided by a well-structured strategy, towards the purpose of strengthening social security awareness and engagement in Estidama++. Digital communications involved 243,000 digital messages sent to Estidama++ beneficiaries, and 47,848 WhatsApp chatbot conversations with Estidama++ beneficiaries. In person engagement provided 174 participants living in Zaatari and Azraq camps with social security information with a total of 208 reached in person. The target of 600 was not met, since with the closure of enrolment the need to increase participation reduced.

Despite much positive progress, the programme continued to experience some challenges. As noted in last year’s review changes to the social security tranche[6] system have meant that costs of contributing to social security have increased. The work permit waiver removal for refugees has increased the costs and barriers for refugees working in the formal labour market – a prerequisite for contributing in social security. Registration amongst self-employed Jordanians, as well as women, was lower and efforts to increase outreach and support registration in these groups were pursued.
[6] The tranche system previously provided options on social security pension coverage level and associated payment amount. Options were (10%, 25%, 50%, 75%,100%). The SSC legislative changes made in January 2023 apply only to self-employed (and those on flexible work permits) as these were the workers paying the full social security contribution of 21.75% themselves and therefore the theory was that they may benefit from tranche options that would lower the overall contribution rate. The change removed the tranche system and reinstated the obligation to pay the full 21.75% (100%) noting that most refugees chose the 10% option and thus will face a rising cost when moved to the 100%.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The output indicators remain consistent with last year’s annual review.

Regarding the activities undertaken under this output, the SSC and ILO continued to adjust their activities in response to emerging findings and lessons learned and to reflect that the programme was in its final year.

BEA will provide additional funding to ILO to support the SSC with operationalising Estidama++ during the last year of SSERJ. Progress with this work will be reported on as part of the Project Completion Report.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

A recommendation from last year’s AR was to ensure social security preparedness for Syrian refugees’ returns to Syria. This topic was discussed during governance meetings and directly with the SSC to receive clarity and assurance that returning Syrian refugees can access benefits.

Last year’s annual review also noted the need to monitor attrition and transition rates of Estidama++. Attrition levels (number of dropouts) and the proportion of participants transitioning to regular social security at the end of the scheme are key factors determining the success of Estidama++. Current data on transition is positive, but longer-term monitoring beyond three months after the closure of Estidama++ would provide deeper information on the sustainability of the programme’s outcomes.

Last year’s annual review noted the need to address barriers to women and other hard to reach groups in social security. As noted earlier, participation of women has not met targets and there are also challenges around inclusion of self-employed workers- including many refugees. The programme focused on better understanding and addressing the needs of this group, including through supporting a targeted communications campaign for women, but this will need work in future contribution subsidy schemes of the SSC.

Lessons learned and recommended for the year ahead:

- Continue to focus on ensuring returning Syrian refugees access benefits. Ensuring refugees are aware that they can access their benefits as a lump sum before returning to Syria is necessary to ensure FCDO’s investment helps the refugees it was provided for. At the same time, the SSC should work to create a longer-term solution to cross-border working with Syria.
- Continue to monitor transition to regular social security and attrition rates beyond three months after the end of participation in Estidama++. This will provide further data on the effectiveness of schemes like Estidama++ in extending coverage.
- Continue to encourage methods for increasing female and self-employed participation in future contribution subsidies of SSC. The challenges of reaching these groups was a key finding from Estidama++ and points to the need for reform of social security provision to enhance their participation.
These recommendations will be addressed through our planned support to the ILO for technical assistance to the SSC and accompanied by diplomatic engagement.

Output Title	Provision of TA, evidence and advocacy builds an understanding of, and demand for inclusive and shock responsive SP and the efficiency/VfM benefits of aligning national and humanitarian systems
Output number:		3	Output Score:	A
Impact weighting (%):		25	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 No. of analyses (e.g. political economy), evidence-based and good practice resources, and strategies produced, routinely updated, and disseminated where appropriate.	ILO- 1 report detailing lessons learnt and good practices for Estidama++, 1 costing and fiscal space analysis and 1 study on benefit attractiveness and recommendations / Shamil - The CNM and other analysis provides the foundation for TA annual work plans. CNM, PEA, Stakeholder Strategy and Communications Strategy updated annually. / Shamil (social security)- At least 8 resources/products provided by Shamil to the GoJ and stakeholders (cumulative) / Shamil (social services)- At least 3 resources/products provided by Shamil to the GoJ and stakeholders (cumulative)	ILO- / 1- Fiscal space analysis for a national contribution subsidy program / 2- SSC White Paper on Social Security reforms: visioning exercise on the future of Jordan’s social security system / 3- Qualitative and quantitative study with the WB on incentives for social security participation / Four additional research and evidence workstreams pursued including the finalisation of a global study on contribution subsidies. / Shamil (social security)- / 40 (cumulative) resources provided to GoJ (policy papers and presentations) / 4 resources provided to GoJ this year (policy papers and presentations) / Shamil (social services)- / Cumulatively 8 resources provided to GoJ (policy papers and presentations) / No new resources provided to GoJ this year
3.2 No. of capability building sessions for GoJ officials and wider stakeholders relating to inclusive social protection and number of GoJ staff trained.	ILO- 20 social security staff trained to conduct outreach activities each year (reporting on 2025). / Shamil (social security) - At least 12 (cumulative) sessions provided by Shamil to the GoJ and stakeholders, to at least 12 different stakeholders (cumulative). At least 115 GoJ staff trained; 50% women and 1% persons with disabilities / Shamil (social services) - At least 4 (cumulative) sessions provided by Shamil to the GoJ and stakeholders, to at least 6 different stakeholders (cumulative)	ILO- 35 officials participated in capacity building activities. / Shamil (social security)- / 45 (cumulative) sessions to 38 different stakeholders (cumulative) / 3 sessions to 15 stakeholders this reporting year. / 615 (cumulative) Government and CSO staff trained. 87 Government and CSO staff trained this reporting year. / Shamil (social services)- 6 capacity building activities to 19 different stakeholders. No new activities this reporting year.
3.3 No. of new or strengthened system elements including e.g. MIS, SOPs, knowledge sharing platforms, payment systems etc. that are GESI sensitive	Shamil (social security) - At least 1 system element strengthened (social security) / Shamil (social services) - At least 1 system element strengthened / WB (EWS)- Design of the Early Warning System framework completed and implementation roadmap prepared / WB (Accredited Social Work professions)- Accreditation framework and occupational standards designed for selected social work professions / WB (ISU)- Institutional design and staffing plan for the NSPS Implementation Support Unit completed / WB (National digital systems supporting NSPS implementation)- Functional specifications and development plans for national digital systems prepared / WB (Certification and licensing system for social workers)- Certification and licensing framework for social workers designed	Shamil (social security)- / 4 systems elements strengthened. / Shamil (social services)- / Cumulatively and this year, 1 new system element produced: Business Requirement Document produced for online registration system for social workers / WB - EWS framework designed, and under approval process / Designed for 5 selected social work professions, under review and consultation process / Institutional design and staffing plan for NSPS ISU completed / Specifications and development plans for 3 digital systems prepared and under approval process / Framework was designed pending formal approval
3.4 No. of policy dialogue engagements on inclusive social protection (social security and social services) that are delivered to key stakeholders across GoJ that are GESI sensitive	Shamil (social security)- At least 25 (cumulative) policy dialogue engagements organised by Shamil with the GoJ and stakeholders / Shamil (social services) - At least 15 (cumulative) policy dialogue engagements organised by Shamil with the GoJ and stakeholders	Shamil (social security)- / 81 (cumulative) policy dialogue engagements. 2 this reporting year. / Shamil (social services) – 15 policy dialogues cumulatively, none this reporting year.

Briefly describe the output’s activities and provide supporting narrative for the score.

The ILO exceeded their milestone targets, producing more products than anticipated which were also impactful and strategic products. Shamil completed their final activities meeting expectations or exceeding expectations and the WB made progress despite initial delays in approvals. As such an A is awarded.

Estidama++/ILO
Over the past year and the remainder of the Estidama++ programme, the ILO has continued to provide valuable technical assistance to the SSC in the design and implementation of Estidama++. They have supported the SSC to not only operationally deliver Estidama++ but have also played a key role in supporting the SSC to strengthen SSC systems and their future reform vision and have generated significant research to inform future work.

In terms of evidence, strategies and good practice resources the ILO supported the SSC to pursue a rich research agenda, with several high-profile studies and exceeding the milestone target through 7 studies rather than 3. Work continued on the ‘Visioning White Paper’ developed alongside the ILO and WB through which the SSC has set out options for its medium/long-term reform agenda.

In addition, a fiscal space analysis for a national contribution subsidy programme was developed. This assessed funding availability from reserves and other government stakeholders and makes an important contribution to informing GoJ decisions around the future of Estidama++. A qualitative and quantitative study with the WB also progressed looking at the incentives for social security participation.

Four further research initiatives were commenced, including notably a global study on contribution subsidies was finalised and published. This analysed schemes in 26 countries to provide a comparative analysis on schemes and their effectiveness.

The ILO has continued to build the capacity of GoJ officials on inclusive social protection, exceeding their milestone target through training 35 rather than 20 officials. Activities included:
- training workshops for 22 SSC outreach officials
- 13 SSC and National Aid Fund officials participated in the Social Security Academy training.
- 5 SSC staff participating in training to strenghten skills in data management, governance and evidence-based decision making.
The main challenges over the past year relating to the ILO continued to be a lack of timely reporting. Quarterly reports for donors have often been late, in part due to SSC capacity.

Shamil

The Shamil TA facility closed at the end of September 2025, following the decision by the BEA to refocus its development portfolio. As such the period from April -September 2025 focused on concluding ongoing priority work for the GoJ across several Ministries as well as pursuing the operational closure of Shamil. For this reason, the scale of activities compared to the previous year decreased significantly, and certain activities – such as social services products and capability training – were discontinued.

Shamil continued to deliver evidence-based products, strategies and resources in the final months and continuing capacity building of the GoJ. In terms of evidence-based products, Shamil delivered 44 resources to the GoJ cumulatively over the programme and four this reporting year including:
- Capacity Needs Mapping for Ministry of Finance
- Situation analysis: Achieving financial security of older persons in Jordan: Report
- Situation analysis: Achieving financial security of older persons in Jordan: Policy Brief
- National Elderly Strategy Action Plan: Social Protection and Financial Security Pillar
In terms of capability building, cumulatively, Shamil trained 615 government & civil society organisations (CSO) staff across a range of capacity building activities related to inclusive social security. Of those participating, 83 per cent were from the GoJ, 17 per cent were from CSOs, 50 per cent were women, and 1 per cent were persons with disabilities. This reporting year Shamil trained 87 GoJ staff and CSOs. In addition, there were more than 500 participants at a side event on disability-inclusive social security hosted by the Higer Council for the Rights of Persons with Disabilities (HCD) and supported by Shamil at the Global Disability Summit (GDS) held in Germany in April 2025.

This reporting year Shamil helped strengthen four systems elements relating to social protection as follows, concluding work initiated prior to closure.
- National Elderly Strategy Action Plan: Social Protection & Financial section
- Ministry of Finance 2026-29 strategy (draft)
- Business Requirements Document for Zakat Management information System
- Computable General Equilibrium for the Ministry of Planning and International Cooperation (MoPIC) -a model to estimate economy-wide impacts from introducing social security benefits in Jordan.
In addition, on social services they strengthened: Business Requirements Document produced for online registration system for social workers. This presents the technical requirements needed to design an on-line registration system for social workers.

A particular highlight of this period was Shamil’s support to the HCD, with Jordan role Co-Hosting the Global Disability Summit with Germany in April 2025. Shamil supported the HCD to run a well-attended side event on social protection for people with disabilities along with supporting Jordanian Government officials and representatives of Organisations for Persons with Disabilities to attend. That said, issues relating the buy in of key individuals to Shamil’s approach continued to be present and there were differences in the approach used to those preferred by the GoJ.

WB

BEA entered into a new agreement with the WB in August 2025 for a £1.4 million project to run until the end of SSERJ. The aim of this financing was to support the GoJ to implement the new NSPS 2025-2033 and align UK support more closely with the strategic approach of the GoJ to social protection. The project will provide essential grant assistance to complement the WB’s $400 million loan under the Resilient and Sustainable Social Protection (RSSP) Programme. The project has three main components:

1. National systems enhancement;
2. Supporting the national care economy; and
3. Technical assistance and implementation support.
GoJ approvals for this project have taken longer than anticipated. However, with the Grant Agreement signed in January 2026, progress has been made across all the different outputs. The WB and GoJ continued to make progress while waiting for approvals and mobilised the Bank-executed funding in the project to commence activities.

Output 1 aims to strengthen the shock responsiveness of Jordan’s social protection systems. Towards this aim good progress was made with developing the Early Warning System with work on ToRs for the EWS and an MoU prepared for the Ministry of Social Development (MOSD) and National Centre for Security and Crisis Management (NCSCM) to enable collaboration and data sharing around this initiative. Arrangements are also being made with the Royal Geographic Centre to facilitate the necessary GIS tools to be used for the EWS.

Output 2 focuses on the professionalisation of social work to improve the quality of social work and promote economic opportunities for the care workforce. Progress has been made with establishing the Social Work Licensing and Training Centre within MoSD with the detailed design of the centre completed and agreed with the Ministry. Work on the centre has been accompanied by work to develop professional standards for five social care professions which will be an important part of the accreditation process.

Output 3 provides TA and implementation support to the MoSD to strenghten their delivery and coordination of the NSPS. A staffing model for the NSPS Implementation Support Unit has been agreed with five new positions – technical leads of the pillars of the NSPS – four of which will be recruited by the WB with FCDO funding. ToRs for these roles have been agreed and recruitment is underway with an application deadline of 6 May.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

A number of key changes occurred to this output during the past year.

First, the BEA commenced a new project delivered via the WB to support the implementation of the NSPS 2025-2033. New target indicators have been added accordingly under this output.

Second, Shamil closed at the end of September 2025, earlier than originally envisioned due to a reprioritisation in the BEA’s portfolio as outlined earlier in this review. Milestone targets were revised to reflect this change.

Moving forwards, FCDO plans to agree an extension to its work with ILO until March 2027 to provide further support to the SSC to pursue its reform agenda, including operationalising the Estidama++ programme. Further milestone targets will be added the logframe.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

A key recommendation from the last AR was the need to continue to focus on the future of Estidama++ as it nears its completion. This was a focus of the last year with the ILO supporting the SSC with the implementation of its Visioning White Paper reform vision which includes a national contribution subsidy mechanism. The ILO also completed a fiscal space analysis to help the GoJ think through financing options. Last year’s review also recommended that BEA should continue to support SSC’s reforms. This continued through the past year with ILO providing support to the SSC to further progress its Visioning White Paper and develop several further workstreams through analytical support.

Last year’s review also recommended Shamil focus on a responsible exit. A six-month closure period was chosen to enable Shamil to focus on concluding work committed and started for the GoJ and to make the necessary logistical changes surrounding closure.

Recommendations for the year ahead include:

- Continue to focus on the future of Estidama++. Over the coming year, given the success shown by Estidama++ in enrolling and retaining vulnerable workers, FCDO should continue to support the SSC to institutionalise it including through identifying sources of, and building will for, national financing. FCDO intends to extend its support with the ILO so it can provide further support on this topic. It should also continue to engage with the GoJ and other donors interested in this initiative and further contribution subsidy pilots.
- Continue to support SSC’s long term reform agenda. Similarly, FCDO should continue to engage with the SSC’s Vision White Paper reforms to encourage them to be translated into concrete reforms which benefit the most vulnerable. FCDO’s further support to ILO will also assist with this.
- Apply robust political economy to technical assistance. A lesson learnt was the importance of understanding the political economy in the provision of TA, building buy in especially amongst key individuals and aligning approaches with those preferred by the GoJ. This should be applied to ongoing technical support.
- Ensure continued progress with support to the GoJ for the NSPS implementation. This project will deliver ambitious products to a tight timeline as the end of the SSERJ programme approaches and so continued engagement is needed to monitor progress.

Output Title	Evidence generation, dissemination and TA to decision makers which builds an understanding and demand for enhanced economic inclusion of refugees, women, and people with disabilities
Output number:		4	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of evidence base and good practice resources and products generated and disseminated to key stakeholders including GoJ on economic inclusion (including labour market access by refugees)	Shamil (economic inclusion) - At least 2 resources/products provided by Shamil to the GoJ and stakeholders (cumulative)	Shamil (economic inclusion) 3 cumulative resources/products with 2 in the last reporting year: / 1. Childcare study report / 2. Childcare policy brief
4.2 Number of capability building sessions for GoJ officials and wider stakeholders and number of GoJ staff trained relating to the challenges faced by women and persons with disabilities in accessing jobs.	Shamil (economic inclusion) - At least 2 (cumulative) sessions provided by Shamil to the GoJ and stakeholders, to at least 12 different stakeholders (cumulative)	Shamil (economic inclusion)- / Cumulatively 2 sessions. This reporting year, 1 session took place: webinar presentation on results of childcare study to 10 stakeholders. 23 staff trained this reporting year and 26 cumulatively.
4.3 Number of policy dialogue engagements on inclusive labour market outcomes that are delivered to key stakeholders across GoJ that are GESI sensitive	Shamil (economic inclusion) - At least 10 (cumulative) policy dialogue engagements organised by Shamil with the GoJ and stakeholders	Shamil (economic inclusion)- 11 cumulative policy dialogue engagements. No new activities this reporting year.
4.4 Number of refugees matched to income-generating activities through the two-way referral system.	by June 2026: 5,250	N/A (referral mechanism shifted methodology and will reprise later in the year)
4.5 Number of people equipped with the skills needed to increase their readiness to participate in the labour market (disaggregated by age, gender, nationality, disability)	by June 2026: 868	1,350 refugees and host‑community members (women, men, and youth, disaggregated by age and nationality) were supported through skills development and livelihood‑related interventions.

Briefly describe the output’s activities and provide supporting narrative for the score.

Shamil

As noted in the previous chapter, the Shamil TA facility closed at the end of September 2025 and as such the period from April 2025-September focused on concluding ongoing priority work for the GoJ across several Ministries as well as pursuing the operational closure of Shamil. During this closure phase Shamil continued to support the GoJ on economic inclusion.

The products they generated and disseminated this reporting year included a childcare policy and brief. These provided a return on investment analysis of publicly funded childcare. This highlighted the costs and benefits of different options (basic voucher, an age-differentiated voucher, and a fully public centre-based system) and showed the links between care services and labour market inclusion. Shamil also gave a webinar presentation on the results of the childcare study to 10 stakeholder and trained 23 Government staff. Shamil had undertaken work in the previous year of the programme to identify capacity needs for inclusive labour market capacity building and training however, due to the early closure of Shamil, these activities were deprioritised.

Technical support to UNHCR

The FCDO Statistician seconded to UNHCR continued to deliver substantial and sustained impact by strengthening the quality, credibility, and use of UNHCR Jordan’s flagship Socio-Economic Assessment of Refugees in Jordan (VAF) socioeconomic evidence. Leadership across the full VAF survey lifecycle was provided—improving sampling design, questionnaire relevance, ethical safeguards, data quality assurance, and analytical coherence—resulting in more robust, cost‑efficient, and user‑oriented outputs. Through targeted technical assistance, the statistician improved the interpretation and dissemination of VAF findings on vulnerability, cash assistance, and socioeconomic outcomes, supporting evidence‑based dialogue with government, donors, and partners. This has improved the quality and ease of production of figures for UNHCR advocacy purposes, strengthening the understanding of the economic constraints and inclusion needs of refugees, including women and persons with disabilities.

Technical support to UNICEF

During the reporting period, the UNHCR deployee was redeployed to UNICEF to prioritise UK support for refugee inclusion within Jordan’s NSPS 2025-2033. At UNHCR, the deployee focused on analytical work to strengthen the evidence base on refugee vulnerability and return dynamics. This included leading analysis for the poverty SWIFT survey, examining refugees’ debt profiles and how indebtedness influenced intentions to return to Syria. The deployee also developed a skills‑mapping dashboard, analysing the skills profiles of potential Syrian returnees by governorate of origin. This tool supports evidence‑based planning for return and reconstruction efforts and enhances alignment between refugee data, durable solutions planning and national recovery priorities.

The UNICEF deployee provided high value technical expertise that significantly strengthened the quality, credibility, and policy relevance of UNICEF Jordan’s social policy and social protection work, including vital social services towards refugees. The deployee produced a substantive analytical paper for the Social Protection Public Expenditure Review (PER), strengthening both the technical quality and policy usefulness of the PER. This paper now forms the analytical backbone of a forthcoming joint PER publication with the Ministry of Social Development, directly supporting implementation of the NSPS.

Beyond analytical delivery, the deployment demonstrated a clear shift from grant-based support towards embedded expertise and strategic advisory engagement. The UNICEF deployee strengthened evidence to policy impact by supporting dissemination of GAGE endline findings through seminars with Government counterparts and internal UNICEF teams, ensuring research on adolescents’ wellbeing, agency, and experiences of violence informed broader programming discussions. The deployee also initiated technical work on sustainable financing for the Makani programme, including early costing analysis linked to impact evidence and private sector engagement, and contributed to discussions on a social workforce investment case with the Child Protection team. By bridging UNICEF and FCDO priorities, drawing on learning from Estidama++ and informing support to the NSPS and by leading a gender and disability review that informed the Country Plan analysis, the deployee added sustained institutional value. Overall, the deployment moved FCDO engagement decisively from funding delivery towards embedded analytical capability, policy influence, and system level reform support. The deployee also played a central role in UNICEF’s engagement with the Jordan Labour Market Panel Survey, delivering Stata based analysis on National Aid Fund coverage by household type and nationality, highlighting discrepancies in population estimates, and translating complex data into practical insights for research and policy dialogue.

Self-reliance of refugees

Activities under outputs 4.4 and 4.5 built on the 2022 refugee skills‑mapping exercise, which generated a comprehensive database covering tens of thousands of refugees and provided robust evidence on skills profiles, economic potential, and alignment with available labour‑market opportunities in Jordan. This database informed the design of subsequent programming, including skills priorities, sectoral focus (notably agriculture, IT, renewables, and entrepreneurship), and referral mechanisms.

Output 4.4 – Referrals and income‑generating opportunities.

Under indicator 4.4, the programme focused on linking refugees to income‑generating opportunities through referral and matching mechanisms. Prior to adaptive changes introduced in mid‑2025, reported referral volumes exceeded original expectations, with referrals running at more than double initial targets. However, a strategic review of implementation arrangements identified constraints related to quality, suitability of opportunities, and alignment with refugees’ legal status and market realities.

As a result, the automated referral dashboard was paused from mid‑2025 to allow for redesign and improved coherence with evolving livelihood models. While headline referral figures remained high, evidence suggests that conversion into sustained income was limited, reflecting broader structural barriers in the labour market. A revised approach subsequently set a forward target for additional referrals under a more tightly scoped model, prioritising quality and feasibility over volume.

Output 4.5 – Skills development and labour‑market readiness

Under indicator 4.5, the programme exceeded its targets for strengthening labour‑market readiness. During the reporting period:

- 1,350 refugees and host‑community members (women, men, and youth, disaggregated by age and nationality) were supported through skills development and livelihood‑related interventions.
- Training focused on climate‑smart agriculture, entrepreneurship, IT and digital skills, renewable energy, and inclusive finance.
- In parallel, WFP launched preparations for an updated skills‑mapping exercise targeting around 30,000 refugee youth who had turned 18 since the previous mapping in 2023, using phone‑ and online‑based survey modalities.
In addition, WFP supported:

- 350 vulnerable Jordanians and refugees through benevolent loans for adaptive agri‑food projects,
- contributing to the conservation of over 2,000 cubic metres of water, and
- supporting the creation of up to 125 permanent and seasonal job opportunities.
Despite these outputs, evidence indicates that progression from training to stable, sustainable income remained limited for most participants. This reflects persistent constraints, including the fact that over 90% of working‑age refugees lack work permits, labour opportunities remain largely informal and precarious, and assistance reductions have increased household debt and negative coping strategies.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Shamil

Due to Shamil’s early closure targets were adjusted to reflect that they would be only operating for half the reporting year and would be focusing on concluding existing activities.

Technical support

FCDO previously had two technical advisors seconded to the UNHCR in Jordan to provide technical support. One deployment focusing on M&E concluded as planned during this reporting period. Another deployment focusing on economic advice, was redeployed to UNICEF to provide specialist expertise on social protection and will continue into next year. A milestone target for the remaining deployment should be added to the logframe for next year.

Self-reliance of refugees

During the past year, delivery under this output evolved in response to shifting funding availability, learning from implementation, and evidence on what has (and has not) translated into sustainable self‑reliance outcomes for refugees in Jordan.

A key change was the decision in mid‑2025 to pause the automated referral dashboard that had been supporting refugee matching to income‑generating opportunities. This followed a strategic review which flagged concerns around the quality, suitability, and sustainability of opportunities being generated, despite headline referral numbers exceeding earlier targets. While the referral mechanism demonstrated technical functionality, its contribution to sustained income generation remained unclear, prompting a pause to allow further assessment of effectiveness and alignment with revised livelihood approaches. Final analysis of the referral model is still pending.

In parallel, greater emphasis was placed on using findings from the 2022 refugee skills‑mapping exercise to inform the design of a new phase of upskilling and livelihood interventions under WFP’s Refugee Self‑Reliance Initiative. This included a shift towards more targeted skills development in areas such as climate‑smart agriculture, entrepreneurship, and digital skills, as well as preparatory work to expand skills mapping to additional refugee cohorts, including youth turning 18. These adjustments aimed to improve the coherence between profiling, training, and livelihood pathways, although structural labour‑market and policy constraints continued to limit downstream outcomes.

WFP also leveraged complementary private‑sector financing, which enabled a reduction in the level of FCDO funding required while maintaining core delivery during the period. This helped sustain programme activities amid broader funding shortfalls, but did not materially alter the underlying constraints affecting refugee employment and self‑reliance.
As a result of this review, planned changes include:

- Further piloting and refinement of referral approaches with clearer performance parameters and quality thresholds, rather than volume‑based targets;
- Continued expansion of skills mapping to additional refugee cohorts, including youth ageing into adulthood;
- Stronger integration between skills development and climate‑resilient livelihood activities, particularly where these also benefit host communities; and
- Strengthened monitoring, evaluation, and learning systems to better assess whether skills development and referrals translate into sustained income generation, rather than short‑term or informal opportunities.
At the same time, the review highlights that, under current labour‑market, regulatory, and policy conditions in Jordan, self‑reliance programming remains structurally constrained and unlikely to deliver durable outcomes at scale. On this basis, while adaptive changes will continue within existing programmes, FCDO does not plan to continue funding this output in future phases, and learning from this period will inform a strategic shift towards interventions with stronger protection, basic‑services, or policy‑reform impacts.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Last year’s annual review highlighted the benefits of investing in evidence generation and dialogue and of technical secondments. It also recommended streamlining activities and ensuring better coordination across partners working on economic inclusion. Technical secondments, and the evidence they generated continued to make valuable contributions. The closure of Shamil represented a streamlining of activities.

Lessons learned and recommendations include:

Deployments are a highly effective delivery mechanism for strengthening government systems while advancing UK humanitarian priorities, particularly the shift from grant-based funding to the provision of technical expertise. Embedding staff in partner institutions builds practical skills (e.g. in public financial management, quantitative skills), supports the transition from humanitarian to government-led service delivery (including UNICEF handovers in Jordan), and provides valuable on-the-ground insight that has been instrumental in informing UK policy on returns (UNHCR). Secondments also strengthen the link between FCDO research and real-world implementation, improving the use of evidence in decision-making.

## D: VALUE FOR MONEY

Key cost drivers and performance

The key cost drivers remain those identified in the inception phase, namely admin fees, average cost per consultant, travel and subsistence costs. In delivering humanitarian support- cash assistance per beneficiary is the key cost driver. Partners (ILO/SSC and Shamil) have established VfM frameworks and metrics and are reporting on these annually with shorter updates provided quarterly for Shamil. The UN agencies currently do not provide FCDO VFM analysis, which is an area that needs further development.

The SSERJ programme has used resources well, delivered efficiently, achieved increasingly sustainable outcomes, and embedded equity throughout implementation. Evidence across all components indicates clear and strengthening VfM, with several interventions expected to continue delivering benefits well beyond the life of the programme. VFM performance improved through the review period, with implementing partners deploying useful cost containment measures and no-cost extensions giving ILO and SSC longer to deliver results.

In terms of cost drivers, the primary costs associated with funding to WFP/UNHCR were cash transfers to beneficiaries. Similarly, for Estidama++ a key cost was the direct payments to project participants for social security coverage rewards and contribution subsidies which represented 88% of expenditure (excluding research costs), which is small decline from 90% in the previous year. For Shamil, the greatest cost driver has been the TA fund (47%) and staffing costs (33%).

A further difference between components, relevant to cost drivers, relates to the BEA mode of selecting their implementing organisations. The SSC, ILO, WFP and UNHCR were all chosen due to their position as Government and international organisations with unique mandates that could not be replicated by other organisations. Shamil, by contrast was formed from private sector organisations and was chosen through a competitive procurement process.

VfM performance compared to the original VfM proposition in the business case

The SSERJ programme has demonstrated strong overall performance, using resources effectively, delivering interventions efficiently, and achieving increasingly sustainable outcomes, while consistently embedding equity and inclusion throughout implementation. Evidence from across all programme components shows clear and strengthening VfM, with several interventions expected to generate benefits that extend well beyond the programme’s lifetime. VfM considerations are systematically embedded across all programme decisions, in line with the five Es of the FCDO VfM framework (economy, efficiency, effectiveness, cost‑effectiveness and equity). An emissions assessment was not required as part of the original options appraisal.

Economy

For the humanitarian component, cash transfers remain the primary cost driver, ensuring direct support to beneficiaries with minimal overhead. The efficiency gains from digital delivery mechanisms, including iris biometric verification, further enhance economic value by reducing fraud risks and operational inefficiencies[7]. WFP cash transfers for beneficiaries reached 234,700 direct recipients in total and the BEA’s contribution reached 60,161 refugees, making 15 JOD payments. UNHCR’s cash assistance for basic needs reached 191,949 beneficiaries in 2025 and the (BEA) contribution to UNHCR reached approximately 55,257 beneficiaries. The average monthly transfer value for UNHCR’s cash assistance out-of-camp households remained stable at USD 117 per month, while incamp households received an average of USD 46 per quarter. Around 72% of WFP and UNHCR cash assistance beneficiaries overlap.
[7] Social Protection & Jobs, policy and technical note. March 2024, No 33.

Comparative studies, including findings from UNHCR cash assistance across the Middle East and North Africa (MENA) highlight how cash transfers have been instrumental in addressing protection risks and ensuring basic needs are met[8]. The evidence continues to highlight the cost-effectiveness of cash transfers over in-kind assistance, with unrestricted cash proving 25–30% more economical. As mobile money adoption grows and financial literacy improves, these benefits are expected to expand, with upfront training costs yielding long-term impact.
[8] https://jordan.un.org/sites/default/files/2022-01/UNHCR%27s%20Cash%20Assistance%20and%20Protection%20Outcomes%20in%20MENA.pdf

The BEA continued to finance Estidama++ through two separate channels. It provided financing to the ILO to provide TA support to the SSC to deliver Estidama++ in line with international best practices. ILO use this finance for staffing costs, project procurements and their 13% management fee. The management fee is in line with many other UN agencies and is deemed VfM. The (BEA) continued to provide finance directly to the SSC, which is used for coverage rewards and to subsidise social security contributions for Estidama++ beneficiaries. Providing this finance directly to SSC, instead of via ILO, enabled the BEA to avoid paying management fees and the creation of parallel systems – representing good economy.

The Estidama++ programme has procured a total of 347 contracts, which is an increase from 266 contracts procured last year. To measure VfM, ILO tracks the number of Request for Quotation (RfQ) and number of Requests for Proposal (RfP) procurement processes followed as a percentage of all contracts issued to gauge the competitiveness of the project’s procurement process. As of December 2025, less than 7% of contracts were made through Long-term agreements a positive indicator of economy. The contracts used included: contracts for services (e.g. research, producing communications such as videos, and venue bookings), contracts for external collaborators (e.g. consultants, translators, photographers), and contracts for goods (e.g. laptops for the project team).

Shamil benchmarked key cost items against comparable programmes to ensure VFM. The project’s Non-Project Attributable Costs (NPAC) were maintained at 5.4% of total expenditure, well below the FCDO average of 6.5 per cent[9]. Office rental was 6 per cent below comparable donor projects. Shamil achieved economies of scope by combining related outputs and leveraging shared resources across technical areas. For example, joint missions and bundled consultancies allowed consultants to deliver on multiple workstreams within a single assignment. Integrated national consultations brought together stakeholders from several institutions, reducing travel and coordination costs. These approaches increased productivity and ensured VfM through shared delivery structures and minimised duplication of effort.
[9] Source: Cost Recovery: What is means for CSOs, Bond 2016, https://www.bond.org.uk/wp-content/uploads/2022/03/cost-recovery-0216.pdf p10

Efficiency

There is consensus that cash generates cost efficiency gains, digital payment technology increases the potential to reach people quickly and minimise the risks of fraud and loss of resources, making the process more cost efficient[10].
[10] UNHCR, Multi-Purpose Cash and Sectoral Outcomes: A Review of Evidence and Learning

The cost per beneficiary is estimated at 224 JOD per annum. Efficiency gains are driven by leveraging existing financial infrastructures and bypassing intermediaries, enabling assistance to reach refugees more quickly while reducing the inefficiencies associated with in‑kind aid and voucher-based modalities. Cash assistance has consistently been shown to improve VfM in humanitarian contexts and is widely recognised as the preferred modality among refugees. According to the latest progress reports, 88% of the UK’s contribution to WFP and 89% of contributions to UNHCR were transferred directly to beneficiaries, demonstrating sustained VfM and effective delivery. The use of digital wallets and remote data collection further optimises programme operations by lowering transaction costs and increasing accessibility, particularly for women and persons with disabilities.

WFP and UNHCR have been leveraging mobile cash transfers to enhance the efficiency and reach of their humanitarian aid programmes. WFP's switch from voucher to cash distributions in host communities has facilitated timely and efficient delivery, keeping cost-transfer ratios at reasonable levels[11]. The average daily cost per beneficiary for cash-based transfers (CBTs) in 2021 was USD 0.50. In Jordan, efficiency gains have been made through reducing delivery costs such as banking fees, UNHCR's Common Cash Facility in Jordan has significantly reduced bank transfer fees from 2.5-5% to 1.67%[12]. This reduction in fees, along with streamlined processes, has improved cost efficiency.
[11] Based on the report of evaluating WFP Jordan Country Strategic Plan 2020-2022
[12] The average daily cost per beneficiary for cash-based transfers (CBTs) in 2021 was USD 0.50. UNHCR's Common Cash Facility (CCF).

Shamil reports against a range of efficiency indicators.

Technical Assistance projects – System strengthening:
- Scoping and system design for the registration and licensing of social workers, including a draft system assessment, vision and roadmap, and full Business Requirements Document (BRD) and Standard Operating Procedures (£86,969.87).
- Operational support and design of a disability cash transfer, including a diagnostic and reform proposal with inclusive stakeholder engagement; follow-on implementation was halted due to MoSD disengagement (£22,180.57).

Events:
National Strategy for Older Persons launch (November 2024), a high-level national event with 98 participants, delivered efficiently with a workshop person-day cost of £119 (£48,644.44).

Evidence and dissemination:
- Older Persons Strategy Action Plan, developed by a single expert and validated through a jointly delivered workshop with ESCWA, reducing duplication and sharing costs (£80,483.79).
- Scoping Study on Family-Based Care, with background analysis completed and no further commissioning following early programme closure (£16,003.19).
- Labour Market Analysis, delivered through a cost-efficient dual consultancy model (national and international experts), mapping labour policies and stakeholders (£44,269.26).
- Childcare Study, leveraging complementary work by the WB and UN Women to avoid duplication and strengthen strategic relevance (£139,247.09).

Capacity-building activities:
- Capacity-building and consultation activities demonstrated strong cost efficiency, with person-day costs ranging from £17 to £125, depending on modality and inclusions (e.g. refreshments only versus meals and overnight accommodation).
- This includes disability-focused national consultations and evidence-based practice workshops, as well as capacity-building linked to inclusive social services and policy dialogue activities.

These activities and events are made up of TA fee rates and expenses. Where possible Shamil benchmarked key cost items and delivery structures against comparable programmes to ensure VfM and cost practicality. The ratio of direct programme spending to overheads remained high, technical quality was maintained, and adaptive measures (such as hybrid delivery and cross-pillar consultant deployment) ensured that outputs were produced at minimal additional cost and with enduring institutional value

Effectiveness

Cash transfers enable adaptive responses to evolving needs, ensuring timely aid delivery while fostering refugee agency. Monitoring of cash assistance underscores how the UNHCR basic needs programme emerges as a crucial lifeline, constituting 66% of refugees’ total income[13]. While the positive impact of the UNHCR basic needs programme on overall well-being is evident, the situation remains precarious as noted in previous sections. The complementary roles of UNHCR and WFP reinforce the effectiveness of interventions, and the organisations share the same targeting mechanism for beneficiaries. UNHCR's sectoral reach facilitates integration with broader programming, while WFP’s scale ensures optimized delivery at national levels. This dual approach enhances impact and sustainability.
[13] UNHCR Jordan: 2023 Basic Needs Cash Assistance Post Distribution Monitoring Report

For Estidama++, measures of effectiveness show a marked improvement over the reporting period, demonstrating increasing (VfM) as the programme matures. VfM effectiveness is measured primarily through the sustainable transition of beneficiaries into regular SSC participation. By December 2025, Estidama++ had reached 41,578 registered beneficiaries, a slight increase from 41,421 beneficiaries in March 2025, reflecting the programme’s transition from rapid scale-up to consolidation, with continued outreach efforts by ILO and SSC sustaining enrolment levels and ensuring inclusivity, including among refugee populations.

During the same period, the programme recorded a substantial improvement in sustainable social security participation. The proportion of all registered Estidama++ beneficiaries who continued to pay into social security more than three months after their subsidy ended increased from 11.3% in March 2025 (4,695 beneficiaries) to 24.2% by December 2025 (10,056 beneficiaries). Importantly, among beneficiaries who had completed the programme and passed the three‑month post‑subsidy threshold, transition success rates remained high, at approximately 90% in March 2025 and 84% in December 2025, as later cohorts reached completion. This demonstrates strong behavioural change once beneficiaries exit subsidy support, with lower overall transition rates largely explained by beneficiaries still within the subsidy period.

The project continued to strengthen the sustainability of outcomes over the longer term through ongoing outreach and awareness‑raising activities that reinforce understanding of the value of continued social security participation. In parallel, Estidama++ supported SSC’s reform process, with policy and operational changes expected to further incentivise participation, including through more attractive and responsive benefit packages.

Another measure of effectiveness is the percentage of Estidama++ beneficiaries receiving SSC payments during lifecycle contingencies. This remained consistently high over the reporting period, at 93.3% in March 2025 and 90.2% in December 2025 among beneficiaries who requested access to benefits, indicating the effective functioning of social security protection once beneficiaries are enrolled.

During the same period, the percentage of beneficiaries reporting a perceived increase in income security to manage lifecycle contingencies increased from 49.6% to 53.1%, reflecting improving subjective wellbeing and confidence in social security protection as programme exposure deepened.

Shamil demonstrated strong effectiveness by translating technical assistance into tangible policy and system‑level change despite a challenging political context and early programme closure. High‑quality, policy‑relevant outputs, such as operational national strategies, strengthened data and analytical tools, and foundations for professionalising social services were actively taken up by government counterparts. A clear example is Shamil’s support to the National Strategy for Older Persons, which shifted ageing from fragmented initiatives to a government‑endorsed strategy with a costed Action Plan, embedding ageing issues within mainstream social policy and planning and enabling ministries to prioritise budgets, programmes and coordination accordingly.

Cost-effectiveness
Humanitarian cash transfers are proven to saves lives and is a FCDO best buy[14] and demonstrate good VfM. Evidence from Iraq and Jordan reinforces this: cash assistance allows households to prioritize expenditures, increases local purchasing power, and stimulates market activity. Multipliers of up to 2.5 indicate substantial economic benefits for host economies.
[14] FCDO Humanitarian ‘Best, Cash transfers when local markets are functioning and delivery at scale is achievable are considered a Great Buy.

Shamil contributed to several significant policy and system‑level outcomes despite its early closure. It supported the development, launch and operationalisation of the National Strategy for Older Persons, including a costed Action Plan that mainstreams gender, care and inclusion considerations within national social policy. The programme also strengthened the evidence base for reform through a Childcare Return on Investment study and a labour market analysis, providing new fiscal and economic justifications for labour market and childcare policy change. Finally, it laid critical foundations for the professionalisation of social services, including system design for the registration and licensing of social workers and a diagnostic and reform proposal for a disability cash transfer, alongside operational and technical inputs supporting Jordan’s engagement in the Global Disability Summit, such as analytical inputs, national consultations and delivery of a disability‑focused side event, which elevated disability‑inclusive social protection within national and international policy dialogue.

Despite early closure, Shamil delivered significant policy and system‑level outcomes, including supporting the development and launch of the National Strategy for Older Persons with a costed Action Plan, strengthening the evidence base for labour market and childcare reform, and advancing social protection reforms through improved data and analytical tools such as the SSC Business Intelligence system and a national Multidimensional Poverty Index. The programme also laid key foundations for professionalising social services and strengthening disability‑inclusive social protection, including inputs supporting Jordan’s engagement in the Global Disability Summit. While quantitative outcome‑level cost‑effectiveness analysis was not possible, qualitative evidence indicates strong VfM: institutional outputs were delivered at competitive cost, and capacity‑building activities reached over 600 individuals at an average cost of around £300 per participant, with several outputs expected to generate longer‑term fiscal and administrative efficiencies for government counterparts.

Equity

UNHCR and WFP prioritises support for the most vulnerable refugees. Cash transfers contribute to refugee dignity and social inclusion, reducing stress while empowering beneficiaries with financial autonomy. This includes the targeting criteria for cash assistance focusing on families that are not able to meet their most basic survival needs and have multiple vulnerability e.g. members who suffer from severe disabilities, debilitating medical conditions and other vulnerabilities. A recent evaluation of WFP and UNHCR Multi-Purpose Cash programming found that it was gender sensitive, however, there is more to be done to embed this in design to make it transformative[15]. There is limited up‑to‑date evidence on the accuracy of the Proxy Means Test (PMT) targeting mechanism. UNHCR deployees have referenced earlier WB analysis indicating significant inclusion and exclusion errors, highlighting ongoing challenges in accurately identifying the most vulnerable households. Addressing these targeting limitations remains an important area for further improvement for the new humanitarian programme.
[15] Evaluation of the UNHCR/WFP Joint Action for Multipurpose Cash Assistance in Lebanon (2019–2021), (UNHCR and WFP, February 2023).

Estidama++ has benefited a range of marginalised groups, demonstrating strong equity considerations in programme implementation. Women account for approximately 22.3% of total project participants, a share that has remained stable over the reporting period and reflects ongoing efforts to promote female labour market participation in social security schemes. In terms of nationality, the programme has reached a substantial number of non‑Jordanian workers. Syrian beneficiaries who largely overlap with refugee populations in Jordan represent approximately 21.7% of total participants, highlighting Estidama++’s role in extending social protection to groups facing heightened economic vulnerability. In addition, Egyptian workers account for around 29% of beneficiaries, reflecting the programme’s broad coverage of migrant workers in the informal and semi‑formal labour market.

Gender equality and social inclusion (GESI) was systematically integrated across Shamil, with over 80 per cent of activities assessed as GESI‑sensitive. Gender and disability considerations were embedded in system design, capacity‑building and analytical work, rather than treated as standalone activities. This included integrating inclusion requirements into core systems (such as the Zakat Fund MIS, SSC data reforms and the social work registry), conducting inclusive consultations for the National Strategy for Older Persons, delivering fully accessible workshops and public events in partnership with the Higher Council for the Rights of Persons with Disabilities, and applying inclusive analytical frameworks within tools such as the Multidimensional Poverty Index and labour market studies to better capture the needs of vulnerable groups.

Assessment of whether the programme continues to represent value for money

There is evidence of continued relevance and effectiveness of the SSERJ programme, as well as overall good performance against economy and efficiency measures. The programme continues to represent good VfM and continues to meet the life savings/basic needs of vulnerable refugees and Jordanians. The early closure of Shamil constrained the ability to demonstrate full, outcome‑level VfM, as some longer‑term benefits of system and institutional reforms could not yet be realised or measured. Adaptive management and reallocation of resources ensured that funds had minimal financial wastage and delivered VFM.

In the last annual review, we recommended that WFP and UNHCR develop VfM strategies to improve monitoring and transparency of the VfM of their cash-based interventions. This recommendation has not yet been implemented. Given ongoing reductions in aid flows to the humanitarian sector, understanding cost-effectiveness and enabling comparison against international cost benchmarks is increasingly important for demonstrating impact. Under the new JHASS programme, we will work closely with WFP and UNHCR to strengthen and support their reporting on VfM, including improved articulation of cost-effectiveness and VfM metrics for cash-based assistance.

E: RISK

Overview of risk management

During 2025, the programme team continued to manage the risks across the different components based on changes in context and programme delivery. The risks identified in the risk register continued to be used as the main risk management tool and were reviewed quarterly.

As at end of the financial year 2025/26, the programme had 16 active risks in its risk register covering risks under five risk categories: Strategy and Context, Policy & Programme Delivery, Public Service Delivery and Operations, Financial & Fiduciary and Safeguarding.

During the third quarter, the overall risk rating of the SSERJ programme was reduced from Major to Moderate reflecting strengthened programme performance and mitigation measures. This decision also aligns with the closing down of five risks, four of which were associated with the TA contract early close‑out, and one risk related to low uptake of the Estidama++ project which is now considered as overachieved its targets for participants including the transitioning to regular social security at the end of the scheme.

In parallel, two new risks linked to the WB‑implemented social protection project were added that are to reflect evolving delivery and coordination considerations.

Consistent with last year, the highest risks remain to be within the Strategy & Context and Policy & Programme Delivery risk categories. More information on the risks with the highest residual risk rating (major) is as follows.

The humanitarian components continue to operate in a high-risk environment driven by declining global humanitarian funding and worsening socio-economic conditions among refugees. In 2025, reduced funding led to significant cuts in services, including reductions in protection and health assistance, contributing to increased vulnerability and negative coping strategies.

A key risk remains the continued decline in humanitarian assistance, assessed as highly likely with severe impact. Reduced support is associated with rising debt levels, increased harmful coping mechanisms, and potential social tensions, with implications for stability.

Refugee return dynamics to Syria also present operational risks. While returns reduce caseloads, the remaining population is increasingly composed of highly vulnerable households requiring sustained and more targeted support.

Policy-related risks, including changes to work permit regulations and limited political space for refugee economic inclusion, may further constrain progress towards self-reliance objectives.

Mitigation measures have included maintaining predictable funding through agreement amendments, strengthening targeting approaches, and active donor coordination. Despite these efforts, residual risk remains high given the external funding environment.

Update on Partnership Principles (delete this section if n/a)

The BEA reviewed the Partnership Principals Assessment (PPA) in August 2023 and reassessed in 2025, based on which, the assessment concluded that the GoJ remains committed to the four partnership principles with an upward trajectory with no require for a change in FCDO’s risk appetite.

Annual Statement of Progress

Current level of fiduciary risk and direction of travel since last ASP	Moderate – Stable
Specific assessment of corruption risk and direction of travel since last ASP	Moderate – Stable
Is a full FRA update required?	No

Annual Statement of Progress (financial aid programmes only – delete if n/a)

An Annual Statement of Progress or a Fiduciary Risk Assessment (FRA) are not required for programmes that are not disbursing over £10m financial assistance to the government which is the case for this programme now financial aid to SSC has concluded.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The programme’s delivery progressed across both the humanitarian and social protection components (a total of nine components delivered by: the GoJ (SSC), UN agencies (ILO, UNHCR, WFP), consultants from the private sector (Development Pathways with two national organisations, Arab Renaissance for Democracy and Development- ARRD- and MMIS Consulting) and the WB.

Commercial Activities

The programme team continued managing the Shamil contract delivered by Development Pathways throughout its year 2 Implementation phase that started in April 2025. However, in September 2025 the social protection TA component (Shamil) contract delivered by Development Pathways was closed earlier than its scheduled end date following a reprioritisation of outer years 2026/2027 spend aligning with the announced reductions in ODA and the GoJ’s requests.

Partners who continued delivering during 2025 included: the GoJ (SSC), UN agencies (ILO, UNHCR, WFP) and consultants from the private sector (Development Pathways with two national organisations, ARRD and MMIS).

The Estidama++ related Memorandums of Understandings (MoU) with the ILO and the SSC continued during 2025. Although they were scheduled to end in October 2025, a no extension was approved for the project and accordingly two amendment letters were signed to extend their implementation until February 2026.

To mobilise the new WB project for TA provision to the GoJ’s NSPS implementation, a new Administrative Arrangement (AA) was signed with the WB in August 2025 covering the UK’s contribution of £1.4m to the MENA Multi-Donor Trust Fund (MDTF).

Following the existing Contribution Arrangement (CA) with WFP, further amendments were signed during the reporting period (April 2025 – March 2026) to sustain humanitarian assistance. In 2025/26, an additional £4 million was disbursed in April 2025 in addition to £5.5 million was disbursed in June 2025, followed by £2.5 million in January 2026 and a top-up of £600,000 in February 2026, bringing the total UK contribution to WFP’s food assistance programme in Jordan to £31.6 million.

In parallel, the MoU with UNHCR was further amended to respond to increasing humanitarian needs. Additional contributions of £4 million in April 2025, £5.5 million in June 2025, and £2.5 million in December 2025 covering the 2025–2026 period were provided, bringing the total UK contribution to UNHCR’s multi-purpose cash assistance programme in Jordan to £31.5 million.

Additionally, under the economic participation component with WFP, a further £600,000 was provided in November 2025, increasing the total contribution under this component to £1.4 million.

Furthermore, building on the previously established consultancy arrangement to support the MOPIC on refugee-related matters, a new three-month contract was signed with DAI for a further three months to ensure continuity of advisory support.

These amendments ensured continuity of assistance and enabled partners to maintain support to the most vulnerable refugees in a context of declining global humanitarian funding.

Programme Monitoring

Across the components of SSERJ, we continued to monitor progress against pre identified milestones and objectives under the different delivery partners.

Under the social protection scope of work, we continued monitoring the delivery of the Estidama++ project by the SSC and the ILO through; the Technical Steering Committee meetings chaired by the Director General of the SSC, bilateral meetings with the ILO and the SSC, brief progress reporting by the SSC and the ILO’s 2025 annual progress report and financial audited statements.

For Shamil, we continued monitoring against their action plan and pre-approved tasking orders through; their timely quarterly narrative and financial reporting, biweekly meetings, quarterly programme management board meetings and annual progress reporting.

Post the mobilisation of the WB’s project, which involved close engagement with them and the GoJ to design and agree their deliverables, we continued to follow up closely on progress through bilateral meetings with the WB, wider meetings including MoPIC and MoSD in addition to the WB’s first progress update report submitted in March 2026. Through the MENA MDTF, the bank will provide donors with an annual progress report by the 31st of December and a final narrative progress report for the MDTF within six (6) months of the End Disbursement Date (December 2029).

Programme monitoring of the humanitarian components was conducted through regular review of partner narrative and financial reports, complemented by ongoing bilateral engagement with WFP and UNHCR. This included review of bi-annual and interim reports covering the period April 2025 to March 2026, assessing progress against delivery targets, beneficiary reach, and financial expenditure.

Monitoring focused on tracking both delivery and evolving vulnerability trends, including changes in caseload due to refugee returns to Syria, reductions in overall assistance levels, and increasing socio-economic pressures on refugee households. Partners maintained regular re-targeting exercises to ensure assistance remained focused on the most vulnerable populations, with mechanisms in place to replace households exiting the programme and maintain continuity of support.

The programme team maintained close oversight through continuous engagement with partners, including technical discussions on targeting approaches, delivery challenges, and adaptation to funding constraints. This enabled timely identification of emerging risks and informed adjustments to funding allocations and programme priorities.

Monitoring also drew on partner data and external assessments to assess broader outcome trends, including rising debt levels, use of negative coping strategies, and access to basic services. These insights were used to inform programme management decisions and engagement with the wider donor community.

Additionally, the programme team continued to maintain regular engagement with secondees, their supervisors, and the MOPIC Specialist Advisor to review progress and discuss priorities. Secondees proactively keep the SSERJ programme team informed and seek input as needed, supporting coordinated and aligned programme delivery.

Financial Performance

The total programme spend during the FY25/26 was £28,003,662 comprising of the following payments agreed under; commercial contracts with DP and DAI, a contribution agreement with WFP, MoUs with the SSC, the ILO and UNHCR, an AA with the WB:

- No further payments were made to the SSC between April 2025- March 2026 as the payment of £1.7m that was disbursed in February 2025 was the last payment under the MoU;
- One payment of £315,115 was disbursed as a final payment to the ILO in August 2025;
- A total of £679,292.58 payments to Development Pathways were disbursed against four invoices covering the 6 months closing period. Payments were accrued for on a quarterly basis for the first quarter then monthly for July, August and September as per the partner’s request;
- One payment of £1.4m was disbursed to the WB post the signing of the AA in September 2025;
- Four payments disbursed to WFP in April, June 2025 and January and February 2026 with a total of £12.6m (food cash assistance);
- Three payments disbursed to UNHCR in April, June, December 2025 with a total of £12m (multi-purpose cash assistance);
- One payment disbursed to WFP in November 2025 of £600,000 (Economic participation component);
- A total of £95,270 payments to DAI for three invoices covering monthly payments from February to September 2025 based on the agreed payment schedule. These payments cover the reminder of the first contract managed by DAI for the MOPIC specialist advisor on refugees in addition to the new contract signed in July 2025.
Estidama++

The SSC continued to spend on monthly contribution subsidies and quarterly reward payments made to beneficiaries and account for the commitments for the remaining period of the project until February 2026.

Based on the in depth discussions with the SSC towards the end of 2024, that aimed at getting a clear understanding on the joint account’s financial status in terms of the funds available to cover all the beneficiaries until February 2026, it was agreed that there is no need to disburse any more payments taking into consideration the Norway and the Netherlands expected further contributions.

Although the last payment of £1.7m was made in February 2025 we continued to have an oversight on the implementation and continued to support the ILO through providing TA to the SSC. The ILO shared their 2025 certified Statement of Income and Expenditure for the Estidama++ fund.

Shamil

Shamil continued with their quarterly financial reporting, forecasting and invoicing for Q1, however, we approved converting into monthly payments for the last three months of the closing stage to support with their cash flow management during closure. Therefore, monthly forecasts were submitted instead of quarterly for July-September thus minimising the variance between the forecasts and actual expenditure. Shamil’s forecasts and invoices continued to reflect costs, standard core team fees and associated expenses, programme activity and TA funds costs.

Shamil’s last payment was disbursed in October 2025 as the contract officially closed on the 30th of September 2025.

Under Shamil’s contract, there were assets that were procured across the phases of the project. These assets were disposed in line with contractual obligations and Development Pathways followed FCDO’s guidance throughout the asset disposal process. Multiple steps were taken to ensure due diligence, transparency, and accountability before finalising any decisions. The disposal process was divided into two main areas: a vehicle and office equipment.

WB

In September 2025, the WB’s payment of £1.4m was disbursed as one payment contribution for the MENA Regional Umbrella Program 2.0 MDTF. The contribution is used to finance the activities (both bank executed and recipient executed) as set out in the MENA Regional Umbrella Program 2.0 MDTF description aiming at supporting reforms across countries in the MENA region that promote economic growth, foster peace, stability and recovery.

For Bank-executed activities, the Trust Fund funds may be used to finance: (a) staff costs (excluding short-term consultants and temporaries) (b) short-term consultants and temporaries (c) contractual services (d) media, workshops, conferences and meetings (e) travel expenses. For Recipient-executed activities, the Trust Fund funds may be used to finance eligible expenditures in accordance with the Bank's applicable policies and procedures.

The WB maintains separate financial records and accounts for the funds deposited in and disbursed from the MDTF. The WB will provide the donors with an annual single audit report within six months of the end of each its fiscal year.

UNHCR and WFP

Over the course of the review period (April 2025 – March 2026), the UK contribution to UNHCR was expanded, bringing the total support to £31.5m. Three payments were disbursed during this period. UNHCR has fully expended the funding provided, delivering cash assistance to vulnerable refugees as planned. This demonstrated strong financial absorption capacity and effective programme management under challenging operational conditions.

In the review period, the UK contribution to WFP’s food assistance and refugee economic inclusion programmes in Jordan was scaled up. Across the reporting period, four payments were disbursed to WFP amounting to £12.6m, bringing the total support to £31.6m. WFP has fully utilised all funds disbursed during this period, maintaining continuity of assistance amidst a difficult funding environment. This reflects strong financial performance and effective programme delivery.

Furthermore, building on the earlier phase of support to enhance refugee economic participation, a further CA amendment of £600,000 was signed in November 2025. This amendment continues to advance refugee economic inclusion in Jordan, drawing on the outcomes of the refugee skills mapping exercise and supporting targeted, longer‑term livelihood and economic participation interventions.

DAI - MOPIC Specialist Advisor

DAI’s financial performance has been satisfactory, with invoicing aligned to the deliverables and payment schedule outlined in the contract.

Programme monitoring has included regular meetings with the Specialist Advisor. Given the sensitivity of the role, meeting outcomes and financial details have been shared on a restricted basis within the programme team.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

In 2025, the programme continued to prioritise robust monitoring and learning to track progress and inform adaptive management.

Estidama++

In 2025, Estidama++ implemented a robust monitoring framework to track participation trends, beneficiary perceptions, and programme performance. Quarterly monitoring surveys were conducted with waged workers, self‑employed participants, and employers, assessing satisfaction, affordability of social security contributions, outreach effectiveness, and intentions to continue contributing beyond the subsidy period. Monitoring data showed consistently high levels of beneficiary satisfaction and trust in the SSC, while highlighting variation in retention prospects between waged and self‑employed workers.

Programme monitoring confirmed strong retention outcomes, with 84.2% of beneficiaries who completed the subsidy period transitioning into regular participation in the social security system. Exits from the programme were predominantly linked to labour market dynamics—such as employment changes or migration—rather than dissatisfaction with programme design or delivery.

Shamil

Monitoring throughout the life of Shamil tracked progress against the logframe and Theory of Change, with performance assessed against milestone targets, KPIs, and qualitative feedback from counterparts. By September 2025, the project had met or exceeded 16 of 18 milestone targets, with two milestones not set due to early closure and halted engagement with key partners. Performance monitoring confirmed timely submission of contractual deliverables and sound financial management, with expenditure remaining within agreed variance thresholds.
Monitoring of stakeholder engagement and capacity‑building activities showed strong reach and coverage. A total of 615 government and CSO staff were trained (50% women, 1% persons with disabilities), and over 100 policy dialogue engagements were held across social security, social services, and labour market inclusion. While early project closure limited the ability to track longer‑term system change, routine monitoring confirmed effective delivery of planned outputs within a constrained timeframe.

Programme monitoring of the humanitarian components was conducted through regular review of partner narrative and financial reports, complemented by continuous bilateral engagement with WFP and UNHCR. This included bi-annual and interim reporting covering the period April 2025 to March 2026, assessing delivery against targets, beneficiary reach, and financial performance.

Monitoring was further strengthened through quarterly meetings with partners, enabling structured review of progress, risks, and delivery challenges. These were complemented by ad hoc check-ins as needed to address emerging issues and ensure timely follow-up on key actions.

The programme team also conducted field visits to observe programme implementation and gather direct insights on delivery processes and beneficiary experience, providing an additional layer of verification beyond partner reporting.

Monitoring focused on both operational delivery and evolving contextual dynamics, including changes in beneficiary caseloads due to refugee returns, funding constraints, and increasing vulnerability among remaining populations. Partners applied regular re-targeting and verification processes to ensure assistance remained focused.
on the most vulnerable households and that support was continuously reallocated a caseloads shifted.

The secondment of a statistician to UNHCR continued to support improvements in MEL practices, enhanced the socio-economic evidence base, and improved the targeting and effectiveness of cash assistance. For instance, the statistician supported Cash targeting improvements by pinpointing relevant analysis, advising on interpretation and reviewing Basic Needs Annual Assessment outputs for quality and robustness.

Evidence

Estidama++

Evidence generation in 2025 was strengthened through the integration of routine monitoring data, Randomised Controlled Trials (RCTs), external compliance validation exercises, and an independent mid‑term evaluation. The RCTs generated rigorous evidence on the effectiveness of behavioural incentives, outreach modalities, and benefit design in influencing participation in social insurance schemes. External validation exercises assessed eligibility verification, payment processes, and beneficiary prioritisation, confirming strong operational performance while identifying opportunities to further strengthen data management and efficiency.

The mid‑term independent evaluation, completed in 2025, confirmed that Estidama++ is on track to achieve its objectives, demonstrates strong alignment with national social protection priorities, and benefits from effective coordination between the ILO and the SSC. The evaluation also highlighted areas where affordability constraints and labour market instability, particularly among self‑employed workers, continue to affect sustained participation.

Shamil

Shamil generated analytical and operational evidence to inform social protection reform in Jordan. Key evidence outputs included 40 evidence‑based resources on inclusive social security, eight resources on social services, and targeted analytical studies on labour market inclusion, notably a return on investment analysis of childcare, demonstrating strong economic and fiscal benefits of voucher‑based childcare models.

Evidence from a Knowledge, Attitudes and Practices survey conducted in February 2025 showed a 74% average improvement in stakeholders’ understanding of comprehensive social protection concepts following engagement with Shamil, with 100% of respondents affirming the importance of comprehensive social protection for Jordan. Nearly 90% of stakeholders reported changes in their work practices, indicating uptake of evidence‑based approaches.

The project also produced system‑level analytical tools, including a Social Accounting Matrix (SAM) and Computable General Equilibrium (CGE) model, which demonstrated that expanding lifecycle social protection could increase GDP, reduce poverty and inequality, and remain fiscally manageable over time. While some analyses (e.g. multidimensional poverty index) could not be fully published due to data and political constraints, the evidence base remains available to inform future reform.

UNHCR and WFP

Building on programme monitoring, available evidence indicates that while humanitarian assistance continued to be delivered effectively at scale, outcome-level trends for refugee well-being have deteriorated due to external factors, particularly reduced international funding and worsening economic conditions.

Evidence from UNHCR shows increasing levels of household debt, with average debt reaching approximately JOD 1,800, alongside reduced access to essential services and increased reliance on negative coping strategies.

At the same time, funding constraints have led to significant reductions in beneficiary caseloads, with large numbers of households excluded from assistance despite continued high levels of vulnerability.

Data from both WFP and UNHCR further highlights the impact of refugee returns to Syria on programme delivery. While returns have reduced overall caseloads, the remaining population is increasingly composed of highly vulnerable households with limited coping capacity and continued dependence on assistance.

Overall, the evidence suggests that while programme outputs are being delivered effectively, broader outcome trends remain negative due to contextual factors outside programme control.

Learning

Estidama++

Learning from monitoring, evaluation, and research activities informed both programme adjustments and broader policy dialogue throughout the year. Key lessons included the importance of aligning contribution and incentive structures with the income realities of self‑employed and informal workers, the need for sustained and multi‑channel outreach to improve knowledge of social security entitlements, and the expectation of some attrition in a dynamic labour market context.

The mid‑term evaluation emphasised the importance of sustaining programme achievements beyond implementation, including through continued policy dialogue, integration with wider labour market reforms, and strengthened institutional capacity within the SSC. Learning generated through Estidama++ is already informing national discussions on extending coverage, improving affordability, and designing more flexible and sustainable social insurance mechanisms.

Shamil

Learning from Shamil highlights both technical and operational lessons relevant to future TA programming. The project demonstrated that demand‑driven, evidence‑led technical assistance can meaningfully shift stakeholder understanding and policy discourse, even within a relatively short implementation period. Regular policy dialogue and monthly technical engagement meetings were identified as particularly effective in building trust, generating learning, and responding to emerging government demand.

Key learning also emerged around implementation risks. Political economy dynamics, limited access to official data (notably the Household Expenditures and Income Survey), and resistance from some institutions constrained evidence uptake and slowed reform momentum. Early project closure limited sustainability and the consolidation of results, underscoring the importance of securing broad‑based political support early.

Operational learning included the need to avoid overlapping consultant missions, adapt monitoring and evaluation tools to be accessible to persons with disabilities, and invest in clear visual communication tools to explain complex social protection and economic concepts to senior decision‑makers. Overall, Shamil’s learning reinforces the value of combining technical rigour with adaptive delivery and strong stakeholder engagement in fragile and politically sensitive reform contexts.

The evidence highlights that humanitarian cash assistance remains a critical safety net for vulnerable refugee populations in Jordan. Reductions in assistance are directly associated with worsening socio-economic outcomes, including increased debt and greater reliance on negative coping strategies.

A key lesson is the importance of targeting efficiency in a constrained funding environment. As resources decline, precise prioritisation of the most vulnerable households, supported by regular re-targeting mechanisms, has been essential to maintaining programme effectiveness.

The programme also reinforces the need to balance immediate humanitarian support with longer-term approaches to self-reliance. Strengthening linkages between humanitarian assistance and broader social protection and economic inclusion efforts remains critical, particularly as vulnerabilities deepen and funding pressures persist.

Finally, the reporting period has demonstrated the value of adaptive programme management. Flexibility in funding allocations, delivery approaches, and partner engagement has enabled the programme to respond to a rapidly changing context, including shifting caseloads due to refugee returns and evolving needs on the ground.

These lessons will continue to inform programme adjustments and engagement with partners and the wider donor community in the next reporting period.

Date of last narrative financial report	UNHCR: February 2026 / WFP: March 2026 / ILO: March 2026 / Shamil: September 2025	Date of last audited annual statement	UNHCR: October 2025 / WFP: April 2026