## Annual Review Template

Title: Pitcairn Financial Aid 2023/25
Programme Value £ (full life): £15.27mm		Review date: July 2025
Programme Code: 301112	AMP start date: 12/04/23	AMP end date: 31/03/26

Summary of Programme Performance
Year	2023/24	2024/25
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	DevTracker Programme GB-GOV-1-301112 (fcdo.gov.uk)
DevTracker Link to results framework:	DevTracker Programme GB-GOV-1-301112 (fcdo.gov.uk)

A. SUMMARY AND OVERVIEW
Description of programme

The Pitcairn Financial Aid programme aims to assist the Government of the Pitcairn Islands (GPI) bridge the gap between their domestic revenues and necessary expenditure. Through transfers to GPI’s recurrent budget, the programme supports GPI in providing essential services to the people of Pitcairn.

Budget support has been the main form of UK assistance to Pitcairn since 2004. The provision of budget support is in line with the UK Government’s (UKG) obligations to meet the reasonable assistance needs of the citizens of Pitcairn and other aided Overseas Territories. It aligns with the 2012 Overseas Territories White Paper, the UK’s United Nations (UN) Charter obligations and relevant elements of the National Security Strategy (2025) and the Strategic Defence Review (2025).

Support consists of transfers to GPI’s consolidated fund for ongoing operational costs to fund sea access, technical support, and on-island operational costs. Working alongside other UKG programmes on island, this programme aims to increase Pitcairn’s economic self-sufficiency and resilience, and to continue to protect and explore Pitcairn’s pristine marine environment.

Summary supporting narrative for the overall score in this review

The programme is succeeding in ensuring that Pitcairn’s reasonable assistance needs are met. The provision of Financial Aid has been critical in ensuring that key positions are filled, essential services can run and that sea access to the island is maintained.

In terms of the programme’s output level indicators, the Financial Aid programme has scored an A in financial year 2024/25.

Budget management has improved over the course of this review period. Unlike the previous review period, where challenges in budget management necessitated an uplift in the funds made available, spending has remained in line with the allocated budget. Notably, critical sea access to the island has been maintained within spending limits, despite rising fuel costs and global pressure on the shipping supply chain. A major boost to communications came with the installation of Starlink terminals on the island, creating more robust links to and from the island and improving medical and health treatment options available.

Major lessons and recommendations for the year ahead

The GPI and the FCDO will work in partnership to:

- Review Logical Framework (LogFrame) indicators and respective weightings for future years to reflect anticipated needs and strategic priorities. This collaboration will ensure milestones capture what can realistically be delivered and measured.
- Progress the outcomes of the FRA review to mitigate identified risks and enhance the performance of the Pitcairn Island Office (PIO) and Pitcairn Public Service (PPS).
- Proactively review the ongoing viability of the shipping and sea routes, ensuring it is fit for purpose and resilient into the future.
- The GPI, Administrator and PIO will closely monitor budget management to ensure funding is kept within targets and any pressures or potential overspends are captured and swiftly escalated in line with governance processes.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

Processes
Annual financial aid review monitors performance against results framework.
PIO, Administrator and GPI manages budget efficiently and effectively to deliver public services on island. Critical TA posts filled to ensure continued child safeguarding and provision of basic services.
Shipping subsidy covers annual operational costs of the supply ship.

Impact
HMG's obligation to maintain Pitcairn's reasonable assistance needs is met in a cost-effective manner.

Outcome
Efficient and effective management and delivery of public services provision.
Maximise available benefits (especially environmental)

Outputs
1. Sustained budget management, in line with best practice
2. Effective Public Service Provision maintained.
3. Regular, safe and reliable sea access to Pitcairn

Assumptions
The main assumptions are:
No major incidents which impact on government expenditure. This includes diverse exchange rate fluctuations. Evidence - medium
- No incidents in safeguarding. Evidence - medium
- No more than one emergency medivac per year and/or no more than average costs of routine referrals. Evidence - medium
- Ability to attract and retain suitably qualified professionals. Evidence – medium/high
- Stability in fuel prices Evidence - medium
- Vessels able to land in poor weather. Evidence – medium/high

Inputs
Finance – FCDO funding of up to £5.45m. GPI revenues of £0.435m
Resource – FCDO advisory support, programme management, oversight from Administrator on Pitcairn and Deputy Governor and Governor in NZ.
TA - on island to ensure continued child safeguarding and public service provision. Other TA as required.

Financial Aid to Pitcairn is making a critical contribution to assisting GPI deliver essential government services, including through the provision of funds for technical cooperation.

The Programme’s theory of change is still valid, as are the Outcome and Impact level indicators. However, with an ageing population and the absence of school-age children, the safeguarding process will necessarily shift focus to the protection of vulnerable adults.

Reliable and safe sea access remains key: the ship to shore connection through the MV Silver Supporter contract will be improved with the procurement of two new long boats, but it will be important to ensure delivery goes ahead as planned and that maintenance and safety checks continue with the existing, ageing boats.

With the PPS overhaul, overcoming the challenges of filling key public services positions and maintaining effective services will be crucial and an important milestone to monitor over the coming year. As the health and capacity of working age adults declines, it may be necessary to rely on technical assistance with corresponding costs leading to pressure on funding allocations. Medical expenses are also likely to increase with an older, more frail population.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
The programme is on track to continue delivering towards achievement of the expected outcomes and impact by continuing to effectively manage public service provision whilst maintaining HMG’s obligation to provide reasonable needs to the Pitcairn Islands. A newly recruited elderly care manager will assess the Island’s likely future needs for care provision, and provide support to those caring for vulnerable adults. Island access will also be a focus, with PIO staff working steadfastly with FCDO officials to complete the procurement and delivery of two long boats and to identify a suitable replacement crane (and available funding) so that shipped goods can be safely transferred from the boats on to the island.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The Pitcairn Financial Aid Programme enables essential services, including health, to continue. Unlike other aided Overseas Territories which have local revenue streams that help support recurrent budgets, Pitcairn is wholly reliant on Official Development Aid to remain habitable. Critical capital investment, which has been secured for FY 25/26, will work hand in hand with this programme to ensure vital sea access. GPI and FCDO teams will continue to work together to explore opportunities to maximize the benefits of the financial aid allocation, including to identify value for money options which seek to address the challenges posed by the island’s ageing population.

## C. DETAILED OUTPUT SCORING

Output Title	Sustained budget management in line with best practice
Output number:		1	Output Score:	B
Impact weighting (%):		33	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 Government of Pitcairn Islands to reflect the priority recommendations from the Fiduciary Risk Assessment into the risk register.	FRA to be completed by end of Q1 24/25 and appropriate recommendations implemented.	FRA carried out and completed successfully, with Governor/FCDO/Administrator review of actions to be implemented, taking place in Q1 25. Although the full set of recommendations cannot be immediately implemented, the actions to address the risks identified have been put in place. This will form part of the 25/26 milestones and AR. / Partially Met
1.2 Implementation of Annual Audited Statement Recommendations.	Policy reviewed for addressing underlying personal debt issue.	A range of initiatives and actions have been undertaken in response to the recommendations regarding personal debt, including the introduction in April 2025 of a system of zero credit at the Government Store, and continuing implementation of debt recovery agreements. / Outstanding actions concerning medical debt will be addressed in the coming year. / Partially Met

Briefly describe the output’s activities and provide supporting narrative for the score.

The 24/25 financial year saw a great improvement in the Financial Aid budget management. Previous years’ budget overspends, driven mainly by increased off-island medical bills and the impact of a new shipping contract – an essential lifeline to maintain the island’s access to the outside world - have been brought under control. However, with an ageing population, increasingly limited on-island capacity, and potential rising fuel costs these are a constant pressure on the recurrent budget.

The completion of the Fiduciary Risk Assessments (FRA), was a key step in ensuring assurance in key performance areas. The overall scoring of moderate is in line with the previous review and scores trended downwards and towards moderate-minor generally, indicating that risk management has been moving in a positive direction over the past four years. The current Deputy Governor is working with the PIO to ensure working practices withstand financial scrutiny, including development of local financial regulations. The one area of major concern highlighted in the FRA was the sustainability of public finances: Financial Aid will need to provide the majority of financial support to the island for the foreseeable future. Implementation of the appropriate recommendations for the short/medium term will take place in the next annual review period (25/26).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Fiduciary Risk Assessments are required for all forms of Government-to-Government Financial Aid, and the implementation of FRA recommendations remains a priority; therefore, this output has not changed over the course of the year and will continue to be a focus in years to come. Increasing budgetary pressures, including those posed by the island’s ageing population, underscore the importance of improving financial practices to ensure value for money and effective spend.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

- The FRA was successfully completed, allowing a comprehensive overview of risk performance on the island. A key recommendation for the 25/26 review period will be for GPI and FCDO teams to agree which of the FRA recommendations will be addressed as a priority and the appropriate measures which will support successful implementation.
- The GPI will continue to implement budget management practices, including close monitoring of medical spends, to ensure that forecast and actual spend remains within the FA allocation: early identification of potential overspends should enable mitigation, such as the reprioritisation of spends forecast elsewhere in the FA budget.
- Undertake a review and update of the Output Milestones and respective weightings.

Output Title	Public Service Provision Maintained
Output number:		2	Output Score:	A
Impact weighting (%):		33	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number and field of expatriate experts deliver basic services in line with job descriptions	3 expat positions (police, doctor, social worker) deliver in line with JDs. New Police Memorandum of Arrangement in place. Social worker JD re-written to reflect realities on island.	Police and doctor posts in place. Memorandum of Arrangement with NZ Police refreshed 2024. The social worker recruitment closed in January 2024 after it was decided the position no longer met the needs of the community. An elderly care officer – crucial for supporting Pitcairn’s ageing population - has been recruited and arrived in post in July 2025. / Met
2.2 Percentage of children receiving full-time education appropriate to age and needs.	100% boarding school	100% / All school-age children receiving full-time education. / Met
2.3 Percentage of people with diabetes on island who completed a routine check-up during last 6 months	100%	Four islanders have diabetes and three have completed a routine check-up in the last six months (75%). / Partially Met
2.4 Percentage of overweight children and their parents receiving advice on healthy eating habits and implementing guidance on daily/ weekly physical exercise	100%	Indicator to be reviewed: existing indicator is not currently applicable as all children have left the island. / Noting the prevalence of diabetes on the island and the importance of maintaining the health of the ageing population, GPI and FCDO officials will work with the new elderly care manager to agree a new indicator which is suitable and supportive of the island’s existing demographics. / N/A

Briefly describe the output’s activities and provide supporting narrative for the score.

Two expatriate professional positions were in place on the island at the beginning of the review period: a doctor and police officer. A family and community advisor and a teacher had previously been on island but left in the last year. The teacher was no longer needed, as the island’s two school-age children were in full time education in in New Zealand. After it was decided that the former position of Social Worker no longer met the needs of the community, efforts were made to recruit a new position of Elderly Care Manager on a pilot basis for six months. The position was filled by July 2025 (and will be reviewed in the next annual report). Social work provision and advice is still available through an advice line from an organisation based in New Zealand. GPI and FCDO officials will work together to revise the indicators for the next review period.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The recent review and subsequent streamlining of the public service means Output 2 will remain a priority for the coming year. The restructure and challenging recruitment process was completed thanks to the excellent work of the current Administrator. As staff settle into their new roles and responsibilities, it will be important for the GPI and FCDO officials to work with the new Administrator to monitor progress in the coming year.

The indicators which focus on childhood health and education are no longer relevant due to the absence of children on the island. The need to identify new indicators which reflect the recruitment of an elderly care manager, as well realistic measures of health improvements for the ageing population form part of the recommendations for the year ahead.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The FCDO programme team will work with the Administrator and Governor’s Office colleagues to review and agree appropriate indicators, milestones and weightings for the 25/26 financial year which capture: the aims of the public service review and realistic measures of success, including any further expat recruitment; key priorities for the elderly care manager and milestones which reflect interventions and data that the manager is able to source/ collect and share as part of this review. The FCDO programme team will liaise with the Administrator and Governor’s Office to understand how technical cooperation can continue to support the island, noting the changing dynamic of the population.

Output Title	Regular and reliable sea access to Pitcairn supports reasonable needs.
Output number:		3	Output Score:	A
Impact weighting (%):		33%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of times supply ship runs to/from NZ/Pitcairn carrying freight.	4	4 / Met
3.2 Number of times supply ship runs to/from Mangareva/Pitcairn carrying passengers	21	21 / Met

Briefly describe the output’s activities and provide supporting narrative for the score.

The FCDO’s financial support has ensured continued sea access; the shipping service is the largest outlay from the Financial Aid budget. The agreed number of journeys to and from Pitcairn were maintained for this review period.

Maintaining sea access is critical: with no airport, there is no other option for getting people and goods to and from one of the world’s most remote islands. The shipping service also supports tourism, which is Pitcairn’s only major source of revenue. The service also enables a range of technical experts to come to the Pitcairn Islands, including the RSPB and scientists. Although not funded by financial aid and therefore not part of this review, it is worth noting that scientific studies of the Pitcairn Islands continue to increase our understanding of the island’s biodiversity, including vital data capture from the Marine Protected Area (MPA), and offer an important contribution to global climate research.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Although the allocation for the next financial year is unlikely to change the shipping schedule requirements, GPI and FCDO officials will still discuss and agree the frequency and levels of service expected. The teams will also discuss the addition of indicators which reflect the planned procurement of replacement long boats and a crane. Alongside successful delivery of that essential equipment, it will be necessary to agree a plan for maintenance to ensure all items represent value for money, including through longevity of use.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

- The FCDO programme team should work with the Pitcairn Administrator and Governor’s Office colleagues to determine who should be consulted in the review of indicators, milestones and weightings for sea access - ensuring all relevant stakeholders agree appropriate monitoring and evaluation for the 25/26 financial year.
- Discussions between key stakeholders (GPI, PIO, GO, FCDO) should ensure sufficient voyages can be undertaken within the confines of the budget, highlighting risks and mitigation; and consider further indicators which reflect the procurement and maintenance of the long boats and crane.
## D: VALUE FOR MONEY

Key cost drivers and performance

The main cost driver for this programme is the need to maintain sea access to such a remote island. The shipping service operated as expected and on budget. Off island medical and legal fees are another significant contributor to budgetary costs, but referral policies and close scrutiny by the Administrator has helped to bring them under control. However, due to the ageing population and a lack of on-island capacity and expertise, demand for overseas medical support remains high and is likely to increase.

The Fiduciary Risk Assessment, completed in Q1 2025, highlighted key areas of risk and performance within the Public Financial Management sector on Pitcairn. While the public sector review has recently resulted in the rationalisation of roles and should result in a stronger and more efficient on-island system of public sector delivery, financial management practices will continue to be monitored.

VfM performance compared to the original VfM proposition in the business case

Our approach to VfM continues to be based on the 4Es: Economy, Efficiency, Effectiveness and Equity. Performance of the programme continues to be broadly in line with the VFM proposition of the business case. This is evidenced by the instigation of a review of the public service to increase the scrutiny and transparency of GPI spends, which, for example, led to the appointment of a single Procurement Officer who coordinates all orders for off-island goods, and because actual spend has remained in line with the allocated budget over the course of the year.

Assessment of whether the programme continues to represent value for money

The remoteness of the Pitcairn Islands, coupled with limited tourism and revenue, means the provision of financial aid remains crucial to the territory’s survival. Programme funds focus on essential needs only, and the current Administrator is to be commended for leading efforts to rationalize and streamline public services to reduce costs wherever possible. Technical assistance for health, safety and security needs is actively monitored.

E: RISK

Overview of risk management

The key risks to this programme are regarded as moderate after mitigating measures, and the level of risk remains within appetite for providing Financial Aid to the Pitcairn Islands.

The project risks are reviewed on a quarterly basis by the FCDO, Administrator and Governor’s Office.

Annual Statement of Progress

Current level of fiduciary risk and direction of travel since last ASP	Moderate / Stable
Specific assessment of corruption risk and direction of travel since last ASP	Minor / Stable
Is a full FRA update required?	FRA completed in FY 24/25

Audit of the UK offices in New Zealand in late 2025, will include review of the PIO. Yearly MAP exercises allow an overview of the PIO processes for Pitcairn. A new auditor is in the process of being identified for Pitcairn, allowing a fresh look at the financial risks and performance on island.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

The project was delivered within the planned timeframe under the auspices of a Memorandum of Understanding between FCDO and the GPI with an agreed disbursement schedule for funds. Given the limited resources available to Pitcairn, financial aid was disbursed quarterly in advance.

PIO produced monthly expenditure reports as well as quarterly estimates of projected costs. Exchange rate fluctuations between sterling and NZ dollars were closely monitored throughout the year, it was not necessary to provide additional financial aid to supplement the FA budget for the year. There was a tighter grip on the finances over the review period, than in the previous period, which was down to good financial management by all the teams involved.

G: MONITORING, EVIDENCE AND LEARNING

The FCDO Pitcairn programme team is in regular contact with the Pitcairn Administrator, Deputy Governor and the Pitcairn Island Office (PIO) in relation to the delivery and monitoring of Pitcairn Financial Aid.

The FRA has identified some areas to work on over the next reporting period, but there are also others which the FCDO, Administrator and Deputy Governor agreed were not appropriate for implementation on island and would not be implemented.

The FCDO will work together with the Administrator, Governor’s Office, GPI, and PIO to review indicators and strengthen milestones to ensure appropriate measures which reflect the local context. Elderly care will be a key focus for the next review period.

The review process was led by the programme manager, obtaining inputs from FCDO colleagues and the PIO as required.

Date of last narrative financial report	Feb 25	Date of last audited annual statement	May 25