## Annual Review Template

Title: Bangladesh - Collaborative, Accountable and Peaceful Politics (B-CAPP)
Programme Value £ (full life): 27 million		Review date:
Programme Code: 301120	AMP start date: 15/02/2023	AMP end date: 31/03/2028

Summary of Programme Performance
Year	2024	2025	2026
Overall Output Score	A	A	A
Overall programme risk rating	Major	Major	Major

DevTracker Link to Business Case:	D0004195.odt
DevTracker Link to results framework:	S30112031.xlsx

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

Bangladesh - Collaborative, Accountable and Peaceful Politics (B-CAPP) programme aims to support political collaboration, improved accountability, and peaceful politics in Bangladesh. The programme is intended to impact 'more inclusive and peaceful politics and greater accountability of the state in Bangladesh’. It has four outcomes and six outputs, contributing to protecting civic and political space, fostering collaboration, reducing corruption, and mitigating tensions that lead to violence.

1. The programme is implemented by three partners- the Asia Foundation (TAF), with consortium partner Democracy International (DI); the Hunger Project (THP), with consortium member International Foundation for Electoral Systems (IFES), and Transparency International Bangladesh (TIB). B-CAPP anti-corruption interventions are funded alongside complementary investments from other development partners (DPs) in Bangladesh[1].The project also includes a strategic fund for short term opportunities. This year, the fund supported: UNDP, Global Partners in Governance, Alinea, and a small civil society fund managed by TAF.
  [1] The TIB project is co-funded by, UK, Netherlands, Switzerland, and Sweden
2. During the review period the programme team changed the focus of IFES’s work, closing She Leads activities in the Chittagong Hill Tracts (in line with last year’s Annual Review recommendations) and shifting to direct support to supporting the Bangladesh Election Commission election preparedness in February 2026.
3. During this Annual Review period, the partners continued to adapt to the evolving political context following the student-led movement in July and August 2024 which led to the resignation of Prime Minister Sheikh Hasina. Partners used adaptive approaches to respond to changes in the political context, preparations for the February 2026 election and opportunities to work with the Interim Government on key policy reforms. In December 2025 the Interim Government confirmed that national elections would take place on 12 February 2026.
Summary supporting narrative for the overall score in this review [1-2 paragraphs]

1. The review was conducted by two Governance Advisors, one based in DRC and one from the British High Commission Dhaka. It involved desk reviews of partner self‑assessments and virtual interviews in January 2026, shortly before elections.
2. The programme received an A score, showing strong progress across most indicators, with many exceeding milestones. B‑CAPP partners expanded on previous positive engagement with the Interim Government, political parties, civil society, and communities. TAF and TIB supported accountability reforms in migration, media, health, and education through issue-based coalitions and community monitoring. DI and THP created safe spaces for dialogue among parties and communities, helping them address constituent priorities ahead of elections and reduce potential electoral violence. Flexible support strengthened the enabling environment for core programming, including inclusive election organisation and technical assistance on government reforms. Evidence showed B‑CAPP’s overall impact and adaptability in a fast‑changing political context, though some partners need to improve MEL systems.
Major lessons and recommendations for the year ahead [1/2 page]

Contextual changes after the February 2026 elections
- Lesson learnt: The programme has adapted well to a shifting political context. Post‑elections, the political landscape will change again, and the new government may set priorities that differ from the Interim Government
- Recommendation 1: After the elections, partners should review activities based on election results and initial engagement with the new government. This includes assessing the government’s position on TAF/TIB reforms, parliamentary party composition relevant to DI, and implications for THP. By April 2026

Monitoring, Evaluation and Learning
- Lesson learnt: This was the first evaluation of the impact‑level indicator. While the theory of change links accountability, collaboration and peace, aggregating impact across themes is difficult, especially given the predominance of quantitative indicators and limited use of qualitative evidence.
- Recommendation 2: Review impact‑level data collection to integrate quantitative results. Consider disaggregating the impact indicator by pathway/theme or adopting a single measure capturing all outcomes (e.g., quality of civic space). By July 2026.
- Recommendation 3: Review and update the entire logframe for the final two years given the changes in government post elections.
- Lesson learnt: TIB did not generate research to inform adaptation under Output 1.3, leading to reform choices based on historic sectors and overlap with other partners.
- Recommendation 4: TIB should use political economy analysis to select reform areas and avoid duplication with other partners. By May 2026.
- Recommendation 5: TIB has significantly exceeded milestones; higher‑ambition milestones should be set for the next review period. By May 2026.

Sustainability and B‑CAPP’s contribution to UK objectives
- Lesson learnt: Partner self‑assessments did not evaluate the impact indicator. While interviews highlighted results during the review period, they did not address longer‑term impact or sustainability, especially post‑elections.
- Recommendation 6: Develop a clear methodology for collecting qualitative case studies with partners ahead of the next AR. By September 2026.
- Recommendation 7: Set out how B‑CAPP protects and expands civic space over the long term within the broader UK approach. By September 2026.
- Lesson learnt: The programme is a cost‑efficient tool for supporting interim government reforms and advancing UK priorities in migration, health, education.
- Recommendation 8: Clarify B‑CAPP’s role in the British High Commission Dhaka Country Business Plan and its potential to advance wider UK priorities as part of systems level reforms. By May 2026.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]
The B-CAPP theory of change focuses on three governance dynamics in Bangladesh: weak accountability resulting in corruption, partisan polarisation and politically motivated violence. It is based on the three pathways for positive change. The programme aims to promote greater accountability of the state, space for civic engagement, collaboration between political actors, and peaceful resolution of disputes that would otherwise lead to violence.

Following the student-led movement the programme team conducted two theory of change workshops with the partners at the end of 2024 and 2025: the B-CAPP logframe was updated in October 2025 and the Theory of Change was updated in December 2025. The impact statement was not changed and remains the same as articulated in the Business Case. Two output statements were updated to reflect the shift of IFES activities from delivering the She Leads Beginner Module in the Chittagong Hill Tracts to supporting the Bangladesh Election Commission and to reflect additional activities undertaken using the Strategic Fund.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

1. The programme is on track to contribute to expected outcomes and impact. This is the first Annual Review which assesses progress towards the impact statement given the changes to programme activities following the student-led movement. The impact statement is: “More inclusive and peaceful politics and greater accountability of the state in Bangladesh.”
2. The impact indicator is: ‘impact stories indicating attributable BCAPP influence that has led to more collaborative, peaceful politics and greater accountability of the state in Bangladesh’ with a milestone of 4 case studies. Partners provided a number of examples demonstrating the B-CAPP pathways of change, and this milestone was therefore met.
- Accountability: TIB’s approach of combining civic engagement, research and advocacy has supported the authorities to introduce reforms which improve accountability in key sectors. For example, in the land sector, community monitoring reports were generated using TIB’s application PACTApp and TIB used these reports as well as its own policy briefs to successfully advocate for policy reform. This culminated in a joint workshop with the Ministry of Land and local government representatives which produced an action plan for improving land services and institutional governance; during a follow up engagement the Ministry reported progress on 22/25 recommendations.
- Accountability and collaboration: Bangladesh, one of the world’s largest labour‑sending countries, has long seen migrants exploited by unregulated sub‑agents who charge excessive fees and mis‑sell jobs, including to UK‑bound students. Through a coalition of government, recruiters, and migrant groups, TAF supported the development of Bangladesh’s first national rules to regulate sub‑agents, requiring registration, conduct standards, ID cards, and inclusion in a new national migrant database. TAF also supported grievance mechanisms for returnees: in Tangail, 28 community committees have resolved 300+ fraud cases and secured £300,000 total in compensation, creating strong deterrence. The Migration Ministry is now scaling this grievance model nationwide
- Collaboration and peace: DI’s Multiparty Advocacy Forums (MAFs) provided a safe space for political parties to engage with one another, fostering more effective communication across political lines and supporting locally-led collective problem solving. As a result of MAF engagement, aspiring election candidates party representatives publicly agreed to refrain from violence, intimidation, and retaliatory mobilization, with these commitments subsequently communicated within party structures.
- Peace: THP’s Peace Facilitator Groups (PFGs) and Youth Peace Ambassador Groups and Women Against Violence Everywhere (WAVE) platforms successfully promoted peace and stability at the local level by promoting collective action for identifying, preventing, mitigating and diffusing political, religious, ethnic and electoral violence. THP, via the Centre for Alternatives, tracked the average number of violent incidents in sub-districts covered by the project versus non-project areas, which demonstrated an overall lower rate of incidents in project areas. More detailed examples of conflicts resolved elaborated in outputs
1. On the outcome level, there are 13 indicators. The milestone was met for 10/11 and one milestone was exceeded.
2. Outcome 1: focusses on influencing government to improve service delivery and policy making and is contributed to by TAF, TIB, DI, and IFES. It has two indicators, 1.1 focusses on specific reforms made by government 1.2 focusses on government responses to direct request from BCAPP partners. All indicators met expectations, a delay on the target for IFES compensated for by TAF. Examples below:
- Indicator 1.1: TAF advanced its work on fairer labour migration by helping government authorities adopt and institutionalise mechanisms to protect migrant workers from exploitation. Following the government’s decision to adopt TAF‑piloted grievance mechanisms, Grievance Management Committees were established in two local government offices with TAF support.
- IFES is preparing to deliver an election day communications situation room. They have trained Election Commission staff on election-day communications, including how to respond clearly and effectively to unexpected situations. Because the elections were rescheduled from December to February, this milestone remained incomplete during the reporting period.
- Indicator 1.2: TIB supported Active Citizens’ Groups to use the PACTApp for community monitoring, identifying service‑delivery gaps and driving evidence‑based advocacy. Of 9,134 issues raised across education, health, land and other sectors, 8,033 (88%) received responses from local or national authorities.
- DI supported Multiparty Advocacy Forums to raise community issues, 17 of which prompted documented responses from local authorities. Examples include fire safety drills carried out by the Fire Service in Brahmanbaria following advocacy, and an advocacy in Jhalokati that led to an administrative review of childcare services

Outcome 2: focuses on protecting and expanding civic space, including instances of allowing civil society to submit recommendations (2.1), reforms introduced that increase opportunities for citizen engagement (2.2) and instances of cross-party collaboration (2.3). Indicator are contributed to by TAF, DI and TIB, and were all met.
- Indicator 2.1: TIB reported that 111 recommendations stemming from the issues raised via the PACT App were raised with the authorities. Similarly, issue-based coalitions supported by TAF generated 105 recommendations within the package of reforms on media and labour migration.
- Indicator 2.2: TIB reported 28 changes in processes and practices by the authorities. It was not clear from the self-assessment how TIB attributed its research and policy briefs to these changes, however, there were examples including direct responses from the Education and Land Ministries following the submission of monitoring data and TIB policy briefs. TAF also provided a list of 52 policy reforms that were addressed by the government, under its two priority areas.
- Indicator 2.3: DI reported a range of different instances of cross-party collaboration including roundtables, structured follow-up meetings with local authorities, consensus-building dialogues and community-level advocacy workshops and multiparty press conferences.

Outcome 3 ‘competition within and between political parties is conducted more peacefully and inclusively’ has three indicators: 3.1 capturing inclusion of women and youth, 3.2 on reforms which lead to peaceful internal party competition, and 3.3 which covers cross-party cooperation. DI achieved milestone 3.1 and 3.2, and THP exceeded the 3.3 milestone. Examples blow:
- Indicator 3.1, 3.2: DI supported a net increase of 333 women in political party committees, helping shift women from symbolic roles to positions with greater influence. However, women’s nominations to general parliamentary seats remained limited due to centralized candidate selection, financial constraints, and risk‑averse strategies, alongside rising tech‑facilitated gender-based violence. DI highlighted progress in developing a pipeline of women leaders, increased grassroots engagement, and greater involvement of women in campaign management (3.1). They also supported reforms such as secret ballots, behaviour standards, and conflict‑mitigation mechanisms (3.2).
- Indicator 3.3: THP reported that following their training, participants from different peace volunteer mechanisms were using their new knowledge to undertake collective action to mitigate conflicts in their communities, including 1582 conflicts which were resolved by THP-trained Peace Facilitators

Outcome 4 ‘peaceful conflict resolution are used to prevent, mitigate and defuse political, electoral, religious and ethnic violence’ has three indicators: 4.1 satisfaction with tools and techniques used for dispute resolution, 4.2 which covers engagement in peacebuilding activities, and 4.3 on the perceived reduction of political, religious or ethnic violence. THP met all three milestones.
- Indicator 4.1 & 4.2 Through collecting information from the training participants, participants of peace events, youth fair participants, local administration, PFG, YPAG, WAVE, IFP leaders, and journalists, field visit reports, and interviews, commitments, they found that around 62% respondents said they are satisfied with the tools and techniques applied for peaceful dispute resolution at the community level.
- Indicator 4.3: THP, via the Centre for Alternatives, tracked the average number of violent incidents in sub-districts covered by the project versus non-project areas, which demonstrated an overall lower rate of incidents in project areas (see table).
Period	Average number* of incidents per Upazila in MIPS working areas (80 Upazilas in 30 districts)	Average number of incidents per Upazila in Non-MIPS areas in the same districts (223 Upazilas/Thanas)
Jan – Mar 2025	0.74 (Total number of incidents 59)	0.78 (Total no. 174)
Apr – Jun 2025	0.38 (Total no. 31)	0.69 (Total no. 154)

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

B-CAPP partners have made encouraging progress against an uncertain operating environment, exceeding milestone targets across multiple outcome and output indicators. Some milestones were exceeded by a very large margin, which reflects partners’ ability to adapt well to the evolving political context, however, attention is needed to ensure that all partners are capturing evidence linking B-CAPP activities to reforms. The context will continue to evolve, particularly following the elections in February 2026, and attention will be needed to manage the risk that progress is stalled or lost across all three B-CAPP outcomes, and to assess programme impact in the longer term. The programme has played an important role in the wider portfolio and contributed to UK objectives during the Interim Government’s time in office. The review team assessed that the programme should continue, with adjustments made to adapt to the post-elections context in Bangladesh.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]
Output Title	Digestible data-led research and learning are used to shape dialogue on addressing corruption, conflict, promoting collaboration and/or greater accountability.
Output number:		1	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes, down by 5%

Indicator(s)	Milestone(s) for this review	Progress
Number of high-quality research /Investigative reports generated to shape dialogue on addressing corruption, conflict, promoting collaboration and/or greater accountability. / PACTA Indicator-2.1.2: Number of research reports produced.	TIB-10 / THP-3 / TAF-15	TIB-5: Did not meet expectations / THP-4 2 completed and 1 ongoing: Moderately did not meet expectations / TAF-16: Moderately exceeded expectations / IFES - 1
Number of the communication and advocacy activities/materials are carried out to disseminate research findings and recommendations. / PACTA Indicator-2.2.1: Number of advocacy materials developed.	TIB-20 / THP-2 / TAF-16	TIB-20: Met expectations / THP- 2: Met expectations / TAF- 16: exceeded expectations
Number of instances where research and learnings are used to adapt the programme scope, strategy, approach and way of working.	TIB-3 / THP-2 / DI-2 / TAF-3	TIB-1: did not meet expectations / THP-2: Met expectations / DI-2: Met expectations / TAF-4: Moderately exceeded expectations

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output 1 is delivered by five partners - TIB, TAF, THP, DI, IFES and focus on how to generate and use research to inform programming. With a majority of the targets achieved, the Output scored A.

Indicator 1.1: TIB, THP and TAF together produced 25 pieces of research. Highlights are as follows
- TIB produced five impactful research reports[2] that garnered substantial media attention, including on governance of mobile financial services, e-procurement and climate finance.
- THP completed a research on “Local perspectives on reform and… post-revolutionary politics” by David Bergman, and another on “A silence called peace-minorities and exclusion in Bangladesh” by Bath University researchers Joe Devine and Mathilde Maintrot. Another two research projects are ongoing focussed on gender dynamics inside minorities.
- TAF exceeded the target for high-quality research and investigative reports, with 16 products completed against a target of 15. Under their media reform track a study on Tackling Election Disinformation in Bangladesh was completed. In addition, 15 investigative and reports were produced by journalists supported through TAF.

Indicator 1.2: Delivery partners took different routes to disseminate research. TIB developed 20 communication/advocacy materials, including policy briefs, position papers, op-eds and interviews disseminated through national print, electronic, and social media platforms. THP disseminated findings to their dialogue platforms at a local level and to FCDO and likeminded embassies to build international community understanding. TAF organised an event to share the recommendations on disinformation in elections with civil society and government, and all 15 reports were published across leading media outlets including The Daily Star, Prothom Alo Channel 24. In one case, a report exposed corruption in Tangail’s Department of Social Services, the Anti-Corruption Commission formed an investigation committee to pursue the allegations.[3]
[3] Additional successes not measured: TV talkshows and op-eds on the importance of media reform by centre for govenance studies. The fact-checking coalition produced a total of 4,295 fact-checks in 2025, generating 119.41 million in total views. TAF also produced 10 audiovisuals highlighting migrant stories, testimonies and case studies of GMC mediation process following from last year’s research.

Indicator 1.3: All partners demonstrated examples of adapting programming informed by evidence. Based on the recommendations from the THP research they have ensured greater inclusion of religious and ethnic minority groups in peace facilitation groups. DI applied findings from the end of last year’s Behaviour Factor Analysis (BFA) and one Political Economy Analysis (PEA) to redesign stakeholder communication, resulting messaging for senior party leaders focused on incentives and legitimacy. TAF adaptations were based on research, PEA, including adapting trainings to migrants from civil society delivery to government ownership, adapting programme focus on media reform during the changing political context; adapting migration reform to include safer and informed student migration in Sylhet; TIB outputs states they recommended inclusion of women in anti-corruption debates under this output but it is unclear which research informed these adaptations.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

TIB was asked to report on output Indicator 1.3 for the first time this AR period.

TAF’s output indicator for high-quality research was updated to include investigative reports due to their methodological rigor and systematic approach to uncovering critical issues. This change resulted in an increase in the target to 15.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Recommendation	Progress
TIB should tighten the prioritisation of their research, to ensure they remained focus on areas of comparative advantage, with a prospect of policy impact.	TIB revised its Annual Operational Plans for 2025 and 2026, prioritising its research activities to have more policy level impact.
THP should improve explanations of how they use their analysis in their practice. By end of FY 25/26.	Based on research by Bath University they are adjusting trainings, which now incorporate techniques for creating safer dialogue spaces and recognizing when disputes involve underlying political predation or ethnic targeting, equipping peace volunteers to address these nuanced situations identified by the research. The outcome of this is now evident in several areas and has been shared through case stories.

Lesson learned and recommendations
Quick research was able to adapt work post-uprising to achieve significant results. All partners: Post-elections partners should conduct new or update old research to assess how the current context should influence their work. By April 26

Output Title	Citizen volunteer groups are empowered to collect and use data in anti-corruption efforts.
Output number:		2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	Yes, down by 5%

Indicator(s)	Milestone(s) for this review	Progress
Number of tools/ training to collect information is provided to the volunteer groups. / PACTA Indicator-1.1.3: Number of stakeholders trained for actively involved in anti-corruption activities and solutions (training event on PACTApp, App & online software)	TIB-45	TIB-48: Moderately exceeded expectations
Volunteer groups are utilising the app in their community monitoring activities. / PACTA Indicator-1.2.2 (b): Number of community monitoring conducted (# of groups)	TIB-16	TIB-16: Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

This indicator tracks TIBs introduction and use by its volunteer groups of an app (PACTAapp) to monitor corruption in service provision a local level TIBs volunteer groups include Community Concern Committees (CCC – consisting of professionals like journalists and teachers), Youth Engagement Commissions (YES – students and young people engaged on corruption) and Active Citizen Groups (ACGs – respected community members). With both targets achieved, the Output scored A.

Indicator 2.1 and 2.2: During this period, 48 training sessions were conducted for 16 volunteer groups on the use of PACTApp. These sessions involved 1,273 members (649 males and 624 females), including 293 individuals from marginalized groups. The 16 volunteer groups carried out 276 community monitoring activities at the local level using PACTApp, including at local schools, hospitals and land registry offices.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendation	Progress
TIB should improve MEL around tracking how well PACTApp is used by ACGs, e.g., whether monitoring reports are filed by a few active ACGs, prevalence of sector-specific complaint across ACGs. By July/August 2025	The MEL team conducts random checks on how ACGs are using the app at the local level. These checks found that each ACG typically assigns one to four members to input community monitoring data, while other members provide information.

Lesson learned and recommendations
As trainings for the PACTApp are finalised, TIB should assess whether local level advocacy groups continue to input and update of the aggregated recommendations to a national level. By December 26
Output Title	Civil Society and media organisations cooperate to hold decision makers to account.
Output number:		3	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	Yes, down by 5%

Indicator(s)	Milestone(s) for this review	Progress
3.1. Number of issue-based coalitions/groups formed around identified priority issues. / PACTA Indicator-1.1.1: Number of ACG formed.	TIB-16 / TAF-15	TIB-16: Met expectations / TAF-19: exceeded expectations.
3.2. CSOs/coalitions were able resolve problems/grievances in the targeted issue based projects.	TAF- 160	TAF-191: Exceeded expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 is delivered by two partners – TIB and TAF. TAF has two reform coalitions: one focussed on migration and one on Media Reform. TIB focusses on corruption in the health education and land sectors. The output scored A with the overall delivery exceeding expectations on most targets.

Indicator 3.1: For TIB, 16 active citizen groups were formed, comprising 240 community members (Male 121, Females 119, and marginalised 65) who engage on anti-corruption in the health, land and education sectors. TAF formed a total of 19 coalitions and groups, exceeding the milestone target of 15. These coalitions and groups focused on delivering for the two reform tracks – migration and media. They included:
- A fact-checking coalition was formed by Dismislab, Rumor Scanner, and Fact-Watch to coordinate responses to misinformation.
- Rumor Scanner formed 4 coalitions with Jago News24, Bangladesh Pratidin, Jamuna TV, Khoborer Kagoj to build capacity of media outlets on debunking misinformation and strengthening public trust in media.
- Two coalitions brought together journalists, editors, newsroom gatekeepers, mentors, and gender experts to support investigative reporting on issues of public interest.
- Disinformation partner, Factwatch created three community-level groups in Cox’s Bazar and Sylhet to address misinformation at the grassroots.
- 4 youth groups were formed in Chittagong and Cox’s Bazar to raise awareness of migrant rights, reduce fraud, and promote safer migration practices.
Indicator 3.2: Against a target of 160, TAF exceeded the milestone overall by addressing 191 grievances/problems in total, including 146 direct migration-related grievance cases resolved and 45 problems addressed through fact-checking and verification support. The labour migration reform track helped returnee migrants resolve complaints against recruiters and sub‑agents. Supported resolution of 399 cases and resolved 146, recovering BDT 19.1 million (GBP 114,901). The coalition also referred 451 cases to government bodies, with 108 resolved and BDT 14.7 million (GBP 86,780) recovered. In total, 254 cases were resolved and BDT 33.8 million (GBP 201,681) was recovered for migrants. The direct case resolution rate improved from 30% last year to 37% this year, and direct recovery increased from GBP 79k to GBP 115k

The media coalition’s fact-checking partners resolved 45 misinformation problems by debunking false and misleading content which had the potential to cause harm. These issues included false corruption allegations, fake news stories, misleading claims involving police and public safety, AI-generated or edited audio/video/images used for political misinformation, gender-based misinformation, scams using fake announcements, fabricated allegations.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendation	Progress
TAF should increase focus on how the issues they propose selecting maximise contribution to outcomes (improvement of accountability and widening of civic space). By June 2025	A PEA was conducted on the current state of civil society organizations in Bangladesh and provide insights into how to support emerging CSOs in Bangladesh going forward. This is to be finalized next reporting year and will inform support to civil society going forward.

The effectiveness of direct grievance resolution is higher than inside the government. Recommendation:TAF works on how to increase the resolution rate for government and recommend reform in the context of sustainability. By December 2026
Output Title	Youth and women holding democratic values are promoted within political parties with strengthened procedures.
Output number:		4	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No.

Indicator(s)	Milestone(s) for this review	Progress
Number of initiatives for behavioural and/or procedural changes advancing women within political parties.	DI-45	DI-57 exceeded expectations
Number of initiatives for behavioural and/or procedural changes advancing youth within political parties and political movements.	DI-11	DI-11: Met expectations
Number of behavioural and/or internal party procedural changes that promote youth and women's leadership	DI-35	DI-35: Met expectations
Number of initiatives led by women, youth, or community actors aimed at increasing voter awareness and access to electoral information in Bangladesh.	IFES – 7	IFES – 2.6

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 is delivered by DI and IFES. DI continued to engage with political parties and this year, focussing on preparing parties for inclusive participation in elections .In addition, IFES supported voter education together with Swedish and EU funding to support voter turnout among marginalised groups. The output scored A with the overall delivery meeting expectations on all targets.

Indicator 4.1: DI implemented 57 initiatives to advance women’s political participation within political parties. These included:
- Seven national and regional policy reform dialogues with 229 participants
- One strategy dialogue on public funding for women’s political empowerment
- two political communication and campaign management trainings for 52 women to strengthen engagement in party processes.
- Four dialogues using existing political and civil society platforms, engaging 71 participants to build demand for women’s political empowerment, with emphasis on reform, safety, and security.
- 11 multiparty regional dialogues and 17 single‑party dialogues with 368 women leaders across nine regions to promote inclusion within party structures, DI convened.
- 11 Multiparty Advocacy Forum-led dialogues responding to rising digital risks for women politicians
Four hotline activities on online harassment, engaging 454 participants, and supported the establishment of digital risk response cells in two political parties

Indicator 4.2: DI met its annual target by implementing 11 initiatives to advance youth participation and leadership within political parties and political movements. Including:
- four consensus‑building dialogues on student union elections and one national policy dialogue, engaging over 180 young women and men from political parties, student wings, and emerging movements
- five consultations with student wings involving around 70 youth leaders to inform dialogue design during the Dhaka University Central Student Union election period.
- one Youth Leaders Fellowship cycle, engaging 25 youth leaders from the student and youth wings of five political parties
- three youth‑led initiatives addressing citizen issues, enabling young women and men to apply leadership skills through structured advocacy and community engagement.

Indicator 4.3: DI met its target by documenting 35 behavioural and internal procedural changes that strengthened women’s and youth leadership within political party structures. Six Women Inclusion Sub‑Committees were formed enhancing institutional mechanisms for women’s leadership at district and city levels. Additionally, one formal directive was issued to grassroots party units mandating greater inclusion of women in mainstream committees, reinforcing rule‑based expectations for representation. These reforms resulted in measurable leadership gains, with 28 party committees increasing the number of women members.

Indicator 4.4 This indicator captures IFES‑supported civil society voter‑education efforts ahead of the February 2026 election. IFES is working with 12 CSOs nationwide, with a strong emphasis on youth outreach, and strengthened partners through four TOTs in early November—two on inclusive voter education (Nov 3–6) and two on youth‑focused voter education (Nov 9–10 and 11–12). IFES then supported 12 cascade trainings to expand community‑level reach. CSO activities included courtyard meetings on the voting process, street dramas for women in tea‑garden communities, outreach to religious minorities in Sylhet, and mock voting exercises to familiarize voters with casting a ballot.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation	Progress
DI should consult closely with the BHC on the strategic choices around the breadth of support to new political actors through B-CAPP, and aim to find a good balance between breadth and depth. There is a risk DI spreads itself across too many parties and thematic areas. End of April	Regular meetings with BHC staff enabled a balance between breadth and depth, resulting in deprioritising of some partnership and the inclusion of others. The participation is now representative of the Bangladeshi political party context.

This year saw a significant push on women’s political engagement with limited results at a national level, though results at a local level there has been an increase in committee level representation by women. Recommendation: conduct a PEA on women’s political engagement and possibly impactful interventions. By May 2026
Output Title	Local community mediators and political actors are detecting and mitigating tensions that lead to non violence, collaboration and peace/harmony in their communities.
Output number:		5	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Number of volunteers/stakeholders, including women and youth who are trained and/or mentored on addressing conflict/violence and promote harmony.	THP-3720 / DI-532	THP-3946: Exceeded expectations / DI-724: Exceeded expectations
Number of advocacy, awareness raising, conflict mitigation, dispute resolution and peacebuilding activities led by stakeholders	THP- 422	THP-2590: Exceeded expectations.
Instances in which local peace volunteers, including women and youth are able to deescalate/mitigate political/ religious/ ethnic tensions that could lead to potential violence in the targeted areas.	THP-5 / IFES 2	THP-26 Exceeded expectations. / IFES - 3

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 5 is delivered by two partners - THP and DI. This output focusses on mediation and dialogue as a tool to mitigate conflict. In the aftermath of the popular uprising and leadup to elections this has become even more important and partners have pivoted their work to ensure they are working on a conflict sensitive manner. Both partners received additional funding from underspend to focus on peaceful elections allowing it to exceed its targets. The output scored A+ with the overall delivery exceeding expectations on all targets.

Indicator 5.1: THP trained 3946 (106% of target) participants against the target of 3720, through a series of trainings covering facilitation training, youth leadership training and violence against women training for both peace facilitation groups and youth peace facilitators. Participants were chosen in an inclusive manner taking into account gender, religion, political party affiliation, ethnic origin etc.

DI far exceeded its annual target for training and mentoring on conflict mitigation and political harmony, reaching 724 participants against a goal of 532. Activities included youth and senior leadership fellowships, strategic planning sessions, and party-led conflict‑mitigation trainings, all aimed at strengthening accountability and nonviolent political engagement. Multiparty collaboration was further reinforced through a nationwide workshop series involving nearly 200 participants. DI also introduced digital literacy training for party members to promote safer online behaviour and reduce the risk of digital harassment or escalation.

Indicator 5.2: THP facilitated 2,590 stakeholder‑led advocacy, awareness, and peacebuilding actions—over six times the annual target. Peace Facilitation Groups led most community‑level mediation and dialogue efforts, complemented by extensive youth and women’s engagement through fairs, advisory meetings, and national events. Additional peace events, interfaith dialogues, observances, and media‑focused engagements broadened outreach and strengthened local collaboration across districts. As part of project closeout, IFES also delivered a final leadership training for 84 Indigenous women.

Indicator 5.3: THP collected 26 case studies of conflict de-escalation, and IFES while closing down the CHT project collected three stories. THP also developed situation analysis and intervention tools and collected data from field, analysed and prepared reports. Across multiple districts, Peace Facilitation Groups and Youth Peace Ambassadors helped avert serious communal clashes, such as:
- Supporting de-escalation of local tensions in Sitakunda after misinformation about constructing a mosque at a Hindu pilgrimage site sparked unrest.
- Preventing violence in Natore, where tensions between Adibashi and Muslim communities over a land dispute until PFG‑led mediation restored calm.
- PFG interventions brought rival political groups and divided religious or ethnic communities back into dialogue-such as reconciling two political party’s leaders in Fulgaziuniting
- Uniting fragmented Christian denominations in Sunamganj.
- IFES also collected stories of impact, including: a woman securing her father’s agreement to give his daughters a share of family property, another stopping a 14‑year‑old’s child marriage by taking the case to the police and the Headman and one resolving a domestic violence case through coordinated community and legal action.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Recommendation	Progress
DI’s MAFs - local level inter-party dialogue groups - have built trust between political parties as a result of many years of careful training and MAF formation. The sudden shift in the political party landscape means there is a demand to make the MAFs more representative of the current power balance. However, including new actors too quickly may upset the delicate balance inside the MAFS and DI should develop a concrete plan on how to do expand the MAFs carefully.	MAFs -have been adjusted to become more representative of the current political party context, though this change was incremental in a way that did not destabilise the groups. The new members in groups have bene trained in the DI fellowship programmes before joining the dialogue platforms.

Output Title	Selected Government institutions, civic actors and other key stakeholders receive flexible support to deliver accountable and inclusive reforms
Output number:		6	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes, Up 15%

Indicator(s)	Milestone(s) for this review	Progress
Number of projects developed and implemented through the strategic fund to support selected Government institutions and other key stakeholders in the transition context to deliver accountable and inclusive reforms.	TAF-6	TAF-6: et expectation
Number of successful TA interventions and trainings delivered to BEC staff to support reforms processes and procedures (IFES and UNDP)	IFES -3 / UNDP - 5	IFES 3 – met expectations / UNDP – 5 met expectations
Number of campaigns and outreach activities to support improvements to BECs civic and voter education	IFES – 4 / UNDP - 5	IFES 11 – exceeded expectations / UNDP 5 – met expectations
Activities engaged in supporting crisis communications and countering disinformation	Alinea - two rebuttal packages per day published	A total of 540 posts have been published, which is 2.1 per working day – met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 6 captures the activities of the TAF managed strategic fund. This responded to short term opportunities focussed on elections, disinformation and a small-scale civil society fund focussed on new innovative civil society groups focussed on future-resilient civil society. This was implemented by a UNDP multi-donor trust fund on elections, IFES election support (partly measured under output 5) to the Bangladesh Election Commission, Alinea disinformation support, and TAF’s civil society fund.

Indicator 6.1: To support new and youth‑led civil society, TAF delivered five small‑grant projects (£10–20k each). These included: The Reflective Teens engaging 1,800 youth across eight divisions to produce a youth manifesto; Lal Sabuj Society establishing a civic media hub in Barishal; ACTIONIST Foundation running a national digital campaign on technology‑facilitated GBV; Nondita Surokkha expanding legal literacy among marginalised groups; and ODOMMO’19 reducing single‑use plastics in Mymensingh through community campaigns. Global Partners in Governance also provided specialised trainings to political parties.

Indicator 6.2: UNDP delivered five core election‑preparedness trainings: (1) a mock voting exercise informing the BEC decision to extend voting hours from 8 to 9 hours; (2) a regional ToT programme across 10 regions, training 572 officials and certifying 80 resource persons; (3) a two‑day orientation on electoral laws and procedures; (4) digital‑resilience training introducing the disinformation monitoring system, eMonitor+ (5) media trainings with MRDI, UNESCO, and PIB. IFES complemented this support with targeted TA, enabling the BEC to expand digital outreach-producing 55 YouTube videos, 750 Instagram posts, and 1,500 TikTok posts-and supporting website upgrades and design of an online voter‑status platform. IFES also strengthened the PR unit’s capacity to manage these tools.

Indicator 6.3: UNDP ran five voter‑facing campaigns: (1) a voter‑registration campaign with 12 TV announcements and 10 social‑media posts, helping enable 5.8 million new registrations; (2) support for the first‑ever out‑of‑country voting; (3) a CHT voter‑education campaign reaching 80,000 ethnic‑minority voters; (4) a youth campaign producing 58 contents, reaching 5 million people and 16 million+ views; and (5) gender and disability inclusion outreach improving access for women, ethnic minorities, and persons with disabilities. To strengthen staff capacity, IFES delivered 11 trainings, including eight district strategic‑communication trainings for 220 staff (192 men, 28 women), a four‑day leadership training for 25 staff (20 men, 5 women), and two TOTs training 80 core trainers (67 men, 13 women). Several trainings were co‑funded by the BEC, demonstrating ownership and commitment.
Metrics	Results
Total posts published (Facebook page)	540
Average views per post	~10,000
Estimated total reach	~5,400,000

Indicator 6.4: measures disinformation work supported by programme partners Alinea. Through a Fact-check site on Facebook they published 540 posts in English and Bangla, with posts picked across media houses - including English, Bengali, and Hindi outlets - confirming that targeted audiences were reached effectively.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Through the strategic funding BCAPP was able to support IG, civil society and political actors to deliver elections reforms, support disinformation and support small scale civil society actors. This work required intensive management by advisers and programme managers to spot opportunities and contract work. Recommend a lessons learned session for FCDO on this approach. By December 26.
## D: Value For Money

Key cost drivers and performance

The main cost drivers remained staff salaries, logistics costs for the volunteers, consultant fees, training costs and management overheads.
VfM performance compared to the original VfM proposition in the business case

The business case set out initial VfM expectations, and following AR recommendations, the BHC team developed a programme‑wide VfM strategy and indicator framework in September 2024. This clarified how Economy, Efficiency, Effectiveness, and Equity apply within B‑CAPP and proposed indicators to track performance. All partners - except TIB - have since developed and reported against their own VfM indicators, strengthening consistency and accountability.

Programme adaptation also enhanced VfM by redirecting resources where they could deliver the highest impact. The IFES strand pivoted by agreement with FCDO to provide technical assistance to the Bangladesh Election Commission (BEC) ahead of the 2026 polls, concentrating modest funds on national systems (communications, training, operations). Similarly, TIB’s PACTA approach combines civic engagement, research/policy and outreach to translate citizen evidence into policy and practice to support reform. Moreover, several new partners (i.e., UNDP, Alinea and GPG) were added to the programme as part of programme adaptation to support Bangladesh Election Commission (BEC), Interim Government (IG) and mentoring support to political parties.

Economy

DI leverages its in‑house technical expertise to implement activities, conduct evaluations, and provide ongoing political and electoral analysis, reducing reliance on external consultants and saving both time and administrative costs while ensuring timely delivery. Under TIB’s anti‑corruption programme, 10,831 core actors volunteered, conducting 4,573 app‑based monitoring exercises to detect corruption and service delivery gaps at minimal cost. TIB also produced research outputs and policy briefs using internal expertise and redesigned high‑cost surveys to cut data‑collection time and expenses by half while maintaining sample size.
Efficiency

B‑CAPP delivered efficiency by minimising transaction costs, leveraging partnerships, and sequencing activities to maximise outputs. TAF’s media reform partner Dismislab and DI co‑organised a multi-party consultation in Nov 2025 in Dhaka to refine “Guidelines on Best Practices for Online Conduct During Elections,” consolidating inputs on AI use, online abuse of women in politics, and responsible behaviour into one revised product that DI could immediately repurpose for party trainings and wider dissemination. This approach helped reducing duplication and accelerating uptake.

Two TAF reform projects on safe migration and media reform strengthened each other when media reforms partners targeted analytical capacity on misinformation driving unsafe migration. TAF used the findings to inform safe migration reforms through implementing partner WARBE’s ongoing fair recruitment work (2024–2025), avoiding parallel programming while improving relevance and reach. DI brokered collaborations with The Asia Foundation and WARBE in Cumilla, to form a joint steering mechanism that combines MAF’s political networks with GMC’s community mediation and legal expertise.

DI’s adaptive management and ongoing political economy monitoring enabled geographic clustering, better sequencing, and reduced operational costs while safeguarding delivery during periods of volatility. THP engaged with local journalists to amplify peacebuilding efforts, helping disseminate best practices and success stories to wider audiences. Together, these approaches reflect strong coordination among B‑CAPP partners, integration with existing systems, and context‑specific, efficient delivery.

Effectiveness

B‑CAPP demonstrated strong effectiveness by converting coalition initiatives into measurable outcomes, adapting to political shifts, and centring equity and conflict mediation. Under its media reform work, TAF shifted from pursuing reforms to the legacy Press Council to supporting creation of a National Media Commission, aligning with 2024 stakeholder feedback for a more legitimate, sector‑wide accountability mechanism. Fact‑Watch addressed rising gendered disinformation before the election by applying a victim‑centred approach and producing 64 gender‑focused fact checks to counter harmful narratives. DI likewise responded to women leaders’ concerns about online harassment by integrating TFGBV interventions into party structures and collaborating with TAF to develop relevant training content, strengthening institutional responses.

TIB’s research and advocacy contributed to 26 policy changes and 28 process/practice changes across sectors, including amendments to the Representation of the People Order (1972) and related codes of conduct, reinforcing electoral integrity, transparency, and accountability.

IFES has made limited progress toward advancing the programme’s overarching objective of supporting peace building at the local level in the Chittagong Hill Tracts (CHT). Consequently, the IFES component was strategically reoriented to provide targeted technical assistance to the Bangladesh Election Commission (BEC) in preparation for the 2026 national elections. This shift places emphasis on strengthening institutional capacity and enhancing communication systems within the BEC. The pivot reflects a deliberate effort to maximise national level impact with comparatively modest resources.

Equity

TIB exceeded its inclusion targets by engaging 48% women and 22% individuals from marginalised groups among core actors. Across events under the anti‑corruption social movement, 36% of participants were women and 19% were from marginalised communities, demonstrating strong progress on gender equality and social inclusion. IFES embedded inclusion in voter education by targeting women, persons with disabilities, minority and indigenous groups, and first‑time youth voters. It developed an electoral sign‑language lexicon, partnered with civil society for wider outreach, and organised a national youth festival with 350 participants. DI advanced women’s political inclusion by introducing directives, expanding women’s roles in 28 committees, addressing TFGBV through support mechanisms, and strengthening leadership pathways through mentoring, consultations, and capacity‑building.
Recommendations
The programme should further strengthen its Value for Money (VfM) case by ensuring that VfM indicators are applied and reported consistently across all partners. It is also important to continue prioritising interventions where evidence demonstrates the potential for higher returns, thereby maximising impact. Additionally, the articulation of cost‑effectiveness at the outcome level should be sharpened, especially in instances where the programme has undergone adaptations, to clearly demonstrate the benefits of such changes.
E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The overall risk rating for B-CAPP is major in the third implementation period. Risk management across the programme is robust, supported by clear mitigation strategies and regular reviews. Sixteen risks have been registered during the reporting period of which fourteen risks are within appetite and rest of the risks beyond the appetite those were escalated in due time.

Strategic and contextual risk remained significant during the reporting period. Bangladesh’s transition toward the 2026 national election has created uncertainty for programme delivery, as elections often bring unrest, violence, and operational disruptions. External factors such as administrative delays, mobility challenges, varying stakeholder engagement, and pressure on media and civil society further threaten continuity. To manage these dynamics, partner’s risk management framework integrates real-time political risk assessments that track shifting power relations, stakeholder expectations, and the trajectory of institutional reforms. By closely monitoring political developments, engaging proactively with emerging political and bureaucratic actors, and maintaining flexibility in programme design, TAF aims to navigate the uncertainty inherent in this electoral and post-election transition while remaining responsive to evolving reform opportunities. Following the anti‑discrimination movement and major political shifts in August 2024, instability has repeatedly affected implementation. In response, THP introduced new approaches to convene Peace Facilitator Groups (PFGs), Youth Peace Ambassadors (YPAGs), and other local actors, helping strengthen tolerance, collaboration, and community attitudes.

Across all implementing partners, robust safeguarding systems remain firmly in place to prevent and respond to Sexual Exploitation, Abuse, and Harassment (SEAH), supported by strong policies, regular staff training, due diligence measures, and active reporting structures. Overall safeguarding risk is assessed as low, with no incidents reported during the review period. FCDO delivered refresher training on safeguarding against SEAH for all partners in order to further strengthening capacity. Partners continued to monitor and mitigate SEAH related risks through contextual analysis, awareness-raising activities, and dedicated safeguarding personnel. BHC also regularly oversees partners’ adherence to safeguarding standards in line with FCDO’s “zero tolerance” policy.

Fiduciary risk remains well managed across all delivery partners through strong financial controls, rigorous oversight mechanisms, and strict adherence to donor compliance standards. Key financial risks such as fund mismanagement, non‑compliant reporting, asset or liability mismanagement, and failure to achieve value for money are mitigated through robust financial systems, clear procurement procedures, and regular monitoring. Regular audits have returned unqualified opinions, confirming transparency and compliance. Ongoing capacity building efforts, including targeted training on financial management, risk management, and ‑counter fraud‑ measures, further enhance accountability. FCDO provided training on Fraud and Corruption to the main implementing partners during the reporting period.

The B‑CAPP programme maintains a comprehensive risk register that outlines each identified risk along with corresponding mitigation measures. The register is reviewed and updated at least quarterly and more frequently when needed in close consultation with implementing partners and other relevant stakeholder

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]

Performance of Partners: The performance of partners during the reporting period was steady. Regular meetings between BHC and partners helped track progress and address emerging challenges, and all partners consistently submitted quarterly progress reports on time, with overall reporting quality remaining satisfactory. Partners continued to adapt its programme implementation strategies throughout the prolonged period of uncertainty following the political regime change in August 2024, applying an adaptive management approach to adjust field-level implementation modalities, activity plans, and budgets to ensure progress toward the project goal.

Financial management: During this reporting period, a total of £6,026,663 was disbursed to B‑CAPP. In addition, $242,651 was disbursed to TIB from the USAID fund. This was the final USAID contribution, as USAID has now ended its funding support. All fund requests were thoroughly reviewed. The Programme Manager conducted checks in line with ADAMANT principles, followed by reviews from the PRO and SRO before approval. In line with the Accountable Grant Arrangement, the BHC issued quarterly advance payments to implementing partners. Throughout the period, partners submitted fund requests on time and with adequate supporting documentation. The programme team scrutinised all financial reports, forecasts, and budgets against the agreed work plan and updated the FCDO HERA system accordingly.

Commercial: In addition to the existing arrangements, a Contribution Arrangement was signed with UNDP in July 2025 to implement the BALLOT project under the B‑CAPP programme. FCDO also had a Delegation of Agreement with USAID to support TIB’s PACTA project; however, this arrangement ended in January 2025 following a presidential executive order that terminated USAID’s funding.

Assets Management: BHC carried out asset spot checks of its implementing partners and found that all were in order. Partners maintain the asset register properly. All partners have their procurement policy and follow competitive processes for procuring goods and services.

Audit: Annual audits of the partners have been conducted. All annual audits were done by the independent external audit firms. All audits were unqualified and provided a fair view on the project accounts.
G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation The B‑CAPP logframe was developed in consultation with all implementing partners and is reviewed and updated annually in line with AR recommendations. Each direct implementing partner has developed its own Monitoring, Evaluation, and Learning (MEL) strategy to strengthen programme implementation and achieve overall objectives. For example, DI’s MEL team conducts regular site visits to observe activities, engage with stakeholders, and collect data using a standardized tool that captures observations, participant feedback, areas for improvement, and recommendations. TAF and DI follow a BCAPP‑ aligned framework, collecting and verifying data through partner collaboration and field visits, and tracking quarterly progress reports against indicator targets. THP employs a comprehensive monitoring system including input, activity, process, output, and outcome monitoring supported by tools such as Google Sheets, Looker Studio dashboards, KOBO Toolbox, and MIS data entry, alongside ‑success story‑ documentation. Across all partners, BCAPP activities were monitored using qualitative and quantitative methods, with ‑field level‑ validation and systematic data quality assurance. The BHC programme team also conducted multiple field monitoring visits and shared feedback with partners.

Evidence TAF verifies partners’ findings through a structured documentation and evidence gathering process. This includes collecting monthly event calendars and implementation reports, as well as preserving government directives, gazettes, office orders, and relevant publications. The team also tracks media coverage on policy and governance developments linked to programme reform tracks. Tools such as the GMC Case Management tracker are used to monitor labour migration dispute cases at the grassroots level. Reform trackers and policy tools help monitor progress on specific reform areas, while partner-generated field data is compiled and validated throughout the year. TAF has also created a combined logframe progress report drawing from both the ARR and BCAPP logframes to summarise indicator-level progress for annual field reporting and the final programme report. TIB conducted a component-based mid-term evaluation by an external evaluator in 2025. The consultant team interviewed development partners, project staff, visited CCC offices, and conducted FGDs with CCC, YES, and ACG members to assess the relevance, effectiveness, efficiency, and sustainability of anti-corruption initiatives. They also met with local government authorities to gauge the impact of TIB’s work and consulted Dhaka-based staff to understand the organisation’s strategy, implementation approach, and project planning. THP produced number of documentaries on Peace Facilities Group, Wave and Youth. They also have 3142 media coverage on their activities. In the coming year, THP will publish a compilation of case stories, a video documentary focusing on changes/results, impact stories, outcome harvesting report, some audiovisuals on success/change stories, success stories by oriented journalists, and produce regular newsletters, etc., focusing on learning and achievements.

Learning Partners use both formal and informal learning practices to strengthen programme implementation. TAF promotes continuous learning through quarterly reflection sessions, timeline tools, and biweekly scenario planning workshops that help partners anticipate political risks and adapt strategies. TAF reinforces this approach by conducting Theory of Change and project redesign workshops, and by developing learning questions aligned with its ToC to assess effectiveness. DI advances adaptive management by integrating findings from analytical studies, updating its Theory of Change, holding regular staff meetings, facilitating Strategy Testing Sessions, and encouraging cross team collaboration. IFES reinforces learning through structured Pause and Reflect sessions that identify emerging outcomes, evidence needs, and implementation challenges most recently highlighting progress and bottlenecks in BEC support. TIB followed both formal and informal methods to capture lessons, challenges, and feedback to improve programme implementation strategies and activities. The programme captured lessons, best practices, and challenges, which were incorporated into the reports. Civic Engagement maintained a strong communication channel through which results, learning and challenges were shared regularly in addition to periodic review meeting including cluster meeting with field level colleagues. Throughout the year, the PACTApp online tool was used to collect anti-corruption-related data which enhanced the decision-making process for project implementation.

Date of last narrative financial report	TAF: 23/11/2025 / THP: 26/10/2025 / TIB: 28/10/2025	Date of last audited annual statement	TAF: 22/06/2025 / THP: 07/07/2025 / TIB:19/03/2025