## Annual Review Food Security Safety Net Programme

Title: Food Security Safety Net Programme (FSSN)
Programme Value £ (full life): £250,000,000		Review date: 24 July 2025
Programme Code: [AMP ID#] 301125	AMP start date: 24 June 2022	AMP end date: 31 December 2026

Summary of Programme Performance
Year	2023	2024	2025	2026	PCR
Overall Output Score	A	A	A
Risk Rating	Severe	Severe	Severe

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/projects/GB-GOV-1-301125/summary
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW
Description of programme
Yemen remains one of the world’s most severe humanitarian crises, driven by prolonged conflict, economic deterioration, and widespread food insecurity. OCHA reports an estimated 19.5 million people requiring humanitarian assistance and protection services in Yemen, 1.3 million more than last year, and 49% of the Yemeni population are food insecure. These challenges disproportionately affect Yemen’s most vulnerable and marginalised groups, including women and girls, persons with disabilities, the Muhamasheen[1], refugees, migrants and internally displaced people (IDPs). The operating environment is complex, with fragmented authorities including the IRG, internationally Recognised Government in the South and the DFA, De Facto Authority (Houthis) in the North, escalating conflict tensions and significant challenges accessing vulnerable populations and assistance being caught up in local and national conflict dynamics, demanding an increasingly conflict sensitive approach and national conflict dynamics. Despite these challenges, food is available as Yemen’s imports continue, and cash-based assistance remains a critical lifeline for the most food insecure households, allowing people to buy the food they need and with small surpluses, take part in income generating activities to build longer term resilience.
[1] Marginalised community in Yemen, often described as servants.

The Food Security Safety Net Programme (FSSN) is a five-year (2022–2026), £250 million FCDO initiative in Yemen, designed to provide life-saving cash assistance to the most food insecure and vulnerable households, including women and marginalised groups. The Programme aims to reduce famine risk, build resilience, and promote a more efficient, effective, and sustainable response to Yemen’s protracted humanitarian crisis.

FSSN is the backbone of the UK’s humanitarian response in Yemen, providing lifesaving and building the self-reliance of the most vulnerable communities, and promoting greater coordination and value for money among cash actors in the country. FSSN brings together major actors: the World Food Programme (WFP), Yemen’s Social Fund for Development (SFD), and the BRIGHTLY consortium (led by CARE, with international and Yemeni NGOs). Funding is also made available to the World Bank (WB) for emergency shock responsive social protection payments (for flood relief and emergency nutrition needs) and laying the foundation for the resumption of the national social protection programme which is anticipated to eventually replace humanitarian cash transfers. The Programme delivers cash transfers, cash-for-work, and supports community resilience through Village Savings and Loans groups and local councils.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The UK ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations for 26/27 onwards and the impact on programmes are being worked through based on various factors, including impact assessments. FCDO will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- FCDO remains committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.
As a result, the findings of this Annual Review reflect a programme in transition. Reductions in funding combined with conflict dynamics and the complexity of the conflict environment require a strengthened approach to conflict sensitivity enabled delivery, to avoid the Programme inadvertently contributing to conflict, and to maximise its contribution to conflict prevention and peacebuilding.

Summary supporting narrative for the overall score in this review
FSSN partners broadly achieved and, in some areas, exceeded the expected outputs in this reporting period, with particularly strong performance in the delivery of cash transfers which forms the bulk of the output weighing. As a result, the Programme has been awarded a performance score of A, meeting expectations. This is a notable achievement given the complex and continually evolving operational landscape in which partners are delivering humanitarian aid in Yemen.

Major lessons and recommendations for the year ahead
Building an evidence base for cash programming in Yemen continues to prove challenging, due to heightened political and security tensions where reduced assistance can contribute to conflict dynamics, as well as difficulties in coordination between cash actors although there is mounting evidence [2] that cash support can both meet short term needs and provides a foundation for longer term sustainability IF delivered with a deliberate goal of stimulating local economic growth . The UN curated Humanitarian Response Plan for 2025-26 maintains a strong emphasis on cash-based approaches, and beneficiary feedback overwhelmingly endorses cash as the support method of support. Generating robust evidence is essential to determine the most effective way to ensure interventions address food insecurity and promoting long-term resilience of recipients.
[2] The Cash Consortium for Yemen CCY, issued a report in early 2025 detailing the multiplier effect of cash programming by a factor of each $1 in cash assistance creating $2.38 in local economic activity.
To ensure FCDO is delivering maximum impact with our funding, systematic sharing of lessons and good practices across programme partners, and broader humanitarian and development actors in Yemen will be key. FSSN local actors can provide valuable insights at the community level which need to inform operational and programmatic delivery, as well as building local capacity. Continued engagement in regular governance meetings[3] and efforts to follow through with workstreams can help to foster an environment of mutual benefits.
[3] As evidenced by the March 2025 Gov meeting in Amman which was attended by several key actors not actually funded by FCDO

Key high-level recommendations
For a full list of recommendations see Annex A
Recommendation	Timeline
Prepare the FSSN portfolio and its strategic direction for a reduction resulting from 0.3% ODA by exploring and incentivising collaboration and alignment of existing and future programming with similar “humanitarian plus” approaches currently funded by other humanitarian and development donors with a particular focus on enhanced localisation.	Ongoing, with clear indications of direction by October 2025
FSSN to use the remaining fully funded FY 2025-26 to gather evidence to evolve the Programme methodologies of Cash Plus, into a better configured and cross Yemen context approach. This requires internal FCDO collaboration, and external partnerships on coordination, joint programming, and innovation.	By March 2026
Further align FSSN strategic planning with FCDO ERT programmes to enhance knowledge on a blended humanitarian/development approach supporting enhance income generating opportunities to address food insecurity. Build in opportunities to pilot these interventions (fisheries, VSLA support, co-funding opportunities), to support beneficiaries to graduate from humanitarian need to productive activities. Gather evidence in the final year of the Programme, to inform future programming design.	Ongoing
Use the proposed outcome evaluation to generate evidence and learning on which cash approaches, including amounts and modalities, are most effective at meeting needs and building sustainability, and establishing, if possible, what is the trade-off between the two?	Second half of 2025
FCDO and partners to use recent IPC date and HRP estimates of need to assess the degree to which current FSSN partners’ targeting reflects the UN reprioritisation of effort to areas of IPC 4 and 5. If re-targeting is indicated, calculate (where possible) the positive impacts and benefits such re-targeting might bring, together with the opportunity cost of changing targeting criteria in the final full year of FSSN.	Second half of 2025
Explore opportunities to maximise the future strategic influence of the cash coordinator in the Yemen Donor Humanitarian Cash and Social Protection working group and ensuring effective donor coordination and alignment in cash programming. The cash donor coordination function to specifically enable the alignment of BRIGHTLY and other non-FCDO funded cash plus programmes in Yemen and advise / maximise opportunities to link FCDO cash plus funding with the World Bank social protection re-design process to ensure an eventual transition from humanitarian to safety nets.	March 2026
Explore the opportunities to bring Gulf donors into the Cash space by targeted lobbying and use of evidence, building on opportunities such as KSRs interest in a joint funding initiative with WFP in late 2025.	Ongoing
Enhance collaboration and learning between partners using the MERLY programme. FCDO should take a leading role in facilitating regular knowledge-sharing workshops and ensure that lessons learned are actively used to inform operational decisions. Foster better complementarity between BRIGHTLY/ WFP and SFD by leveraging SFD’s local knowledge and BRIGHTLY/WFP’s capacity to scale up development work.	March 2026
With banks increasingly moving to IRG areas, FCDO should ensure partners have an ongoing risk analysis and contingency plan to protect the flow of assistance to DFA areas, ensuring vulnerable populations are not left unsupported.	October 2025
Use the FSSN programme relationships (SFD, WFP), the new FCDO SDA from mid-2025, the Cash Donor Forum, and the FSSN World Bank support to more strategically link humanitarian programming with Shock Responsive and the more predictable UCT Social Protection re-design being led by the WB and UNICEF. Humanitarian allocations and the shape of our future humanitarian programming should be seen through the lens of an eventual transition towards a national SP system which replaces costly and less sustainable humanitarian approaches.	Ongoing but with clear decision required by WB in late 2025 for FCDO orientation for next FY
Use the year ahead to refine ideas for smaller cost but more catalytic and influential activities for example funding the Cash and Markets working Group, the Cash Donor Coordination Forum, a BRIGHTLY/CCY alignment ready for 0.3% portfolio shift.	March 2026
Donor investment in localisation: FCDO should engage more with local organisations to amplify the Yemeni voice and bring community level contextual insights to the forefront of programme decision making, risk management and shaping future programme design for our food security/cash programming. Valuable learnings and insights gained from building local capacity should be systematically shared across donor working groups and implementing partners	Ongoing

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the Programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

FSSN seeks to reduce humanitarian need in Yemen through two outcomes:
1. The most food insecure and vulnerable Yemenis can address their food and basic needs, reducing famine risk and food insecurity.
2. The response to food insecurity is more effective, efficient, and sustainable.
Outcomes and the overall ToC remain valid and unchanged since the Business Case was approved. The most recent Yemen humanitarian response plan (May 2025) confirms that the two problems that FSSN aims to address (reducing famine risk or food insecurity and improving the effectiveness of the food insecurity response) are still relevant.

This year the Programme has adopted common outcome and output indicators across all partners, such as the Food Consumption Score (FCS) and reduced Coping Strategies Index (rCSI), to enable better comparability and learning. There is also a stronger focus on integrating humanitarian and development approaches, supporting transitions to sustainable livelihoods, and strengthening national social protection systems. These changes aim to ensure the Programme remains adaptive, evidence-based, and better aligned with both immediate humanitarian needs and longer-term development goals. There should be consideration of how the Programme can integrate more emphasis on and measure results at output and outcome level around conflict sensitivity and on the ToC element related to contributing to stability, including through conflict prevention and reduction, social cohesion and peacebuilding at all levels.

Describe where the Programme is on/off track to contribute to the expected outcomes and impact.

Impact Indicator: Reduce humanitarian need in Yemen	Milestone(s) for this review	Progress
IPC levels remain stable or reduce (from 4 and 5 to 3)[4] / IPC analysis only available for IRG area population	Stable or reduced numbers of people in IPC 3, 4 & 5 / Oct 2023 - Feb 2024 Phase 5 - 0% Phase 4 - 13% Phase 3 - 32%	October 2024 to March 2025 / Phase 5 – 0% / Phase 4 – 11% / Phase 3 – 34%
Outcome Indicator(s)	Milestone(s) for this review	Progress
Outcome 1: The most food insecure and vulnerable Yemenis can address their food and basic needs, reducing famine risk and food insecurity
1.1 % of households with Food Consumption Score rates of ‘poor’ or ‘borderline’ in all modalities	56%	Total achievement is not yet available as an average should be drawn between partners which is not possible without SFD data. / BRIGHTLY: 33% / SFD: not available / WFP: 74.8% (nationally not representative of WFP beneficiary households only)
1.2 % of households that report crisis or emergency coping strategies (rSCI greater or equal to 19)	41%	Total achievement is not yet available as an average should be drawn between partners which is not possible without SFD data. / BRIGHTLY: 8.8% / SFD: not available / WFP: 73.1% (nationally not representative of WFP beneficiary households only)
1.3 % of target households who report increased income through VSLAs/SHGs and/or direct livelihoods inputs and assets	8%	Not yet available.
Outcome 2: The response to food insecurity is more effective, efficient and sustainable
2.1 Number of meaningful programming changes and adaptions made to increase value for money and overall performance, including the increased capacity of local partners	6	6
[4] Based on latest assessment from the Integrated food Security Phase Classification in the 24/25 performance period.

Image: IPC July to September 2024 Vs IPC October 2024 to March 2025

Outcome 1 (A in ToC) has shown strong progress, with the delivery of cash assistance playing a pivotal role in the success of the Programme. Partners have largely reached their beneficiary targets despite severe access constraints. FCDO-funded cash assistance has been delivered both through national Yemeni institutions and international humanitarian agencies. However, with political and security risks increasingly compromising humanitarian access, particularly in the North, the conflict and ODA context posing increasing challenges for conflict sensitivity, and funds being reallocated to different communities, partners must ensure that funding is targeting the most vulnerable populations and consideration of conflict sensitivity is at the heart of strategy and delivery. The adoption of common outcome indicators (Food Consumption Score and reduced Coping Strategy Index) across partners is a positive step towards harmonized measurement and comparison of impact. Significant progress has been made through collaboration between the TPM provider, FCDO, and partners to create a comparable and consistent approach to measuring effectiveness against indicators across the Programme.

In this reporting period, 82% of households were rated as having a Food Consumption score of ‘poor’ or ‘borderline’ in all modalities, compared to the target value of 58% (outcome indicator 1.1). There is also an increase in households reporting crisis or emergency coping strategies to 59% (from 50.1% in 23/24). It is important to note that 24/25 is the first year BRIGHTLY data has been included in this indicator. To compare WFP data, in 23/24 62.9% of households were rated as poor or borderline, with an increase to 74.8% in 24/25 (indicator 1.1) and 50.1% reported using crisis or emergency coping strategies in 23/24 compared to 73.1% in 24/25. In an increasingly complex operational environment, partners consistently faced issues relating to the fragile economic landscape and volatility of the cash transfer value, and access limitations due to both bureaucratic and political-security reasons.

Outcome 2 (B in ToC) has been more challenging. Significant progress has been made in establishing governance mechanisms to bring FSSN partners and wider humanitarian actors together to share learnings and encourage greater coherence across the cash response in Yemen. A significant example being the establishment of the Cash Donor Coordination Forum[5]. It is becoming clearer how these collaborations are resulting in synergies between partners on the ground, and how learnings are being incorporated into programme delivery. Now in the third year of the Programme, FCDO can invest in systematic follow-up of governance and coordination actions, and the intent to contribute to stability, and explore ways to measure and articulate success against this outcome. This year, FCDO worked with partners to report against common indicators, increasing comparability across the Programme’s activities and creating a strong foundation to generate evidence-based decisions.
[5] Established in early 2025 with STAAR CMP, to run until Dec 2025.

Justify whether the Programme should continue, based on its own merits and in the context of the wider portfolio
The FSSN Programme and Theory of Change remain relevant in Yemen, where humanitarian needs are intense and growing[6], and almost half the Yemeni population are food insecure. The Programme is well designed in its approach, bringing together local actors, humanitarian agencies, and development experts to forge a sustainable, long-term link between humanitarian aid and development objectives. This joint approach not only enhances the effectiveness of the response and its value for money but also promotes greater self-reliance among beneficiaries. Given the scale of need and the Programme’s contribution role in coordinating and strengthening the response, its continuation is vital for alleviating suffering and supporting long-term recovery and peacebuilding in Yemen. Moreover, the FSSN portfolio provides opportunities to align our humanitarian orientation towards that of the more developmental Economic Recovery Teams’ income generation work both in terms of current and future programming. As FCDO moves into the 0.3% ODA era, such linkages and synergies are increasingly necessary and desirable.
[6] The recent HRP estimated over 19 million people were in need of humanitarian assistance in mid 2025, of which over 17 million are food insecure, 5 million are internally displaced. The mid year IPC, published at the point of writing this AR estimates the food insecurity figure will increase to 18.1 million over the next 6 months. Recent US cuts have removed over $700 million from the humanitarian response, air strikes on port facilities have dramatically reduced the importation of food supplies to the north.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Most vulnerable are able to address immediate needs
Output number:		1	Output Score:	A+
Impact weighting (%):		50	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1. total # of people receiving unconditional cash transfers[7] (number of all individual recipients receiving assistance each year)	925,190	Met expectations / 935,309
1.2. # of new people receiving unconditional cash transfers (number of new individuals recipients added each year)	12,721	Substantially exceeded expectations / 19,069
1.3. # of unconditional cash transfers delivered	2,981,495	Moderately exceeded expectations / 3,295,167
[7] SFD’s CFN is included in this indicator.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output measures the number of beneficiaries provided with unconditional cash transfers by WFP, SFD and BRIGHTLY with FCDO funding. In this setting cash transfers are calculated as a percentage (usually 70%) of the minimum food basket, as agreed by the Food Security and Agriculture Sector. This has changed over the year driven by a number of factors including availability of food, import challenges due to air strikes on Yemeni port facilities and food inflation. Despite heightened security risks to staff and difficulties accessing targeted locations this year, partners have achieved their performance targets on these indicators, therefore this output has been scored A+, meeting FCDO expectations.
- WFP provided unconditional cash transfers to 912,092 beneficiaries in the reporting period.
- In Q3-2024, WFP finalised a full biographic data update of its entire caseload ensuring that only beneficiaries meeting the inclusion criteria were provided with cash assistance.
- WFP reported improvement among cash beneficiaries’ food consumption levels, with negative coping strategy scores dropping from 62% in Q4-2024 to 53% in Q1-2025.
- The BRIGHTLY consortium provided unconditional cash transfers to 9,965 beneficiaries in the reporting period.
- BRIGHTLY’s Post-Distribution Monitoring results demonstrate that the proportion of households with acceptable food consumption has risen to 59.2% from 10.8% (baseline), signifying a positive trend in enhancing dietary diversity and stability.
- SFD provided unconditional cash transfers[8] to a total of 13,252 beneficiaries.
  [8] SFD’s cash for nutrition has a soft conditionality of attending monthly awareness sessions.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Indicator 1 has been split into 1.1 and 1.2 tracking total number of people and new people each year to reduce the risk of double counting.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendations from the previous AR:
1. There is a continued lack of evidence on the impacts of different durations, values and modalities of cash transfers. FSSN has started building an evidence base by tracking a set of common indicators across cash delivery partners. These will be monitored regularly and form the basis of an independent outcome evaluation in late 2025. An indicator on this area could be considered for Output 3. Progress: FCDO has worked with partners to develop common logframe indicators that allow for results aggregation. These will build a more consistent picture across the Programme and allow the comparison of partner performance and cash modalities. Using the same outcome indicators will also help continuity with the successor to FSSN for 2027 onwards.
2. FCDO should continue to interrogate targeting, cash transfer values and other approaches with partners. Progress: Ongoing.
Lessons learnt:
- Whilst common indicators aid comparative analysis across different designs and approaches, there are still gaps in understanding the full causal chain requiring additional evidence to inform decision making. Each context in which our partners deliver is unique, and results may not be generalisable. For example, access constraints are significantly different in DFA and IRG areas, but by better understanding these differences, and effects, decision making for future programmes will be improved.
- Different approaches between partners on managing transfer value changes need to be understood better by FCDO to ensure reporting against indicators are comparable across the Programme and are achieving the best possible value for money.
- Adaptability of programming and fast responsiveness to changes in the operating environment, particularly around conflict sensitivity and security risks, is important to allow consistency in delivery. Being able to reallocate funding is important, often for reasons of changing access and evolving need, e.g. IPC analysis but partners must ensure this is still targeting the most food insecure people in order to achieve the long-term impact of reducing famine risk and food insecurity.
Recommendations
- Continue to work with partners to harmonise reporting against indicators with a stronger narrative, to build a strong evidence base for changes in food consumption scores and the subsequent impact of these changes.
- Use the upcoming outcome evaluation and increase in referrals across FSSN partners to better understand each partner's approach to transfer value changes and if there are any opportunities for complementarity in these approaches. Partners sharing learnings on how they manage transfer value changes can help mitigate impact to beneficiaries and allow for more consistent reporting across the Programme. This is particularly relevant when considering how best to maximise the more sustainable outcomes from the “humanitarian plus” approach of using cash transfers as the foundation for improved livelihoods.
- With banks increasingly moving to IRG areas, FCDO should ensure partners have an ongoing risk analysis and contingency plan to protect the flow of assistance to DFA areas, ensuring vulnerable populations are not left unsupported.

Output Title	Reduce Famine Risk: Cash based assistance enables households, communities, and local organisations to address the root causes of food insecurity and mitigate future famine risk.
Output number:		2	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1. total # of beneficiaries receiving cash-for-work/conditional/long-term cash transfers to improve food security (number of all individual recipients receiving assistance each year)	9,856	Substantially exceeded expectations / 12,993
2.2. # of beneficiaries receiving cash-for-work/conditional/long-term cash transfers to improve food security (number of new individual recipients added each year)	1,577	Moderately exceeded expectations / 1,575
2.3. total # of new beneficiaries actively participating as members in the Village Saving and Loans Associations “VSLAs” /Self Help Groups “SHGs” (number of new members added each year)	3,230	Substantially did not meet expectations / 2,686
2.4 # of VSLA members receiving VSLA inputs and assets	1,574	Substantially did not meet expectations / 1,180
2.5 # of households receiving livelihoods inputs and assets.	6,167	Met expectations / 6,029
2.6 # of pregnant and lactating women, women with children under 5 years old, women with children with disabilities under 17 years old receiving Cash for Nutrition	8,427	Substantially exceeded expectations / 13,252

Briefly describe the output’s activities and provide supporting narrative for the score
This output measures the longer-term impact on households and communities to address the root causes of food insecurity and mitigate future famine risk. WFP, SFD and BRIGHTLY met or exceeded target number of beneficiaries receiving cash-for-work where participants are paid to undertake beneficial projects, and longer-term cash transfers to improve food security where a proportion (usually 70%) of the minimum food basket is provided in 45-day cycles to allow beneficiaries to purchase basic food for survival. However, VSLA targets were not fully achieved, which was largely attributed to access constraints in the North and delays in obtaining permit approvals with local authorities,

WFP:
- WFP reported an improvement among cash beneficiaries’ inadequate food consumption levels – dropped from 62% in Q4 2024 to 53% Q1 2025
- The marginal improvement in food consumption among Cash Based Transfer (WFPs classification of cash assistance) beneficiaries during Q1, compared to in-kind recipients, can be attributed to prevailing economic challenges, which affect cash-receiving households. In the IRG areas, the Yemeni Rial (YER) hit a historic low in March 2025, reaching YER 2,351/USD by the end of the month, losing 30 percent of its value against the US dollar year-on-year. This resulted in a necessary increase to the transfer value of CBT moving into mid-2025 and was endorsed by the inter-agency Cash and Markets Working Group.
- By Q1-2025, WFP’s remote monitoring beneficiary feedback system noted that satisfaction was higher among cash recipients with 76% reporting satisfaction with the amounts received in Q1. This is largely due to the increase in the transfer value to YER 17,500 from YER 11,500. Additionally, nine out of ten households reported using the cash to purchase food with 73% indicating that the food lasted up to three weeks.
- Overall food insecurity in Yemen remained increasingly high in Q1-2025 with roughly 57% of households reporting being unable to meet their minimum food needs as of March.
BRIGHTLY
- The Cash for Work (CFW) component met 99.9% of its planned target. Livelihood support reached 107% of the planned beneficiaries. The success against these indicators can be explained by the increased allocation of savings and exchange rate towards UCT, CFW, Livelihoods and CASH Plus activities.
- The BRIGHTLY partners supported VSLA groups and had collectively saved a total of 30,837,600 Yemeni Rials (equivalent to 57,532 USD). The groups are preparing to enter the loaning phase, marking a key step toward community-led financial empowerment and sustainable economic self-reliance. Establishing VSLA and similar self-help groups in the challenging context is a significant achievement. The year ahead will hopefully see consolidation and increasing benefits as the new structures settle down and evolve.
- Some of the consortium partners faced challenges accessing target locations in the North, only reaching 78% of their VSLA targets. Necessary approvals from local authorities often took longer than anticipated and required careful handling by implementing partners. It should be remembered the period under review coincided with the large-scale detentions of NGO and UN staff members by DFA, making the negotiation of sub agreements risky for implementing partners.
SFD:
- A total of 75 VSLAs were established during the year, with 54% being women groups. SFD slightly underachieved its targets for the number of active VSLA participants and members receiving inputs and assets, which was primarily driven by delays in permit acquisition and restricted access to certain areas, similar challenges as were experienced by BRIGHTLY, (see above).
- To mitigate operational challenges, SFD launched four new cash-for-work projects, surpassing the original log frame targets by 38%. However, this expansion may have led to an estimated 20% overlap in beneficiaries.
- In response to flash flooding on the west coast in mid-2024, emergency cash assistance was provided to 7,463 women under the Cash for Nutrition programme, essentially a cash top up for particularly vulnerable households.
- The integration of cash-for-work and cash-for-nutrition interventions with VSLAs has demonstrated significant added value. These combined efforts have:
  - Enhanced the capacity of VSLA members to save and circulate financial assets, compared to previous interventions without cash components.
  - Increased financial literacy and awareness, driving greater community demand for VSLAs. VSLAs are self-selecting, so demand is seen as a positive result of their reputations.
  - Stimulated local economic activity through improved cash flow and turnover, thereby increasing the likelihood of success for beneficiaries launching small businesses and achieving improved financial self-reliance.
The approach remains valid, demand for and the successes of VSLA groups are positive results. SFD is using their experiences in this reporting period to expand the VSLA approach bringing several associations together and elevate them to the status of small micro banks to maximise impact and access further forms of financial support. 2025-26 will see this approach expanded and evolved.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Output indicator 2 was split between 2.1 and 2.2, tracking both beneficiaries as a total and new beneficiaries, to reduce the risk of double counting. Although it is not possible to avoid this risk entirely as beneficiaries may receive assistance from two partners, but without unique identification it is not possible to alleviate this. Output 2.4 was also amended (2.4 has moved to 2.5 with 2.4 now captures VSLA members (not households) who are receiving inputs or assets.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
For a full set of recommendations and detailed progress see Annex B.
Recommendations from the previous AR:
- As already noted, programme activities are weakly evidenced in Yemen. This is particularly true of Output 2 activities. FCDO should now prioritise evidence generation. Progress: Ongoing. Tetra Tech, the new MEAL provider will prepare a proposal for an outcome evaluation of FSSN in late 2025/ early 2026, in time to inform the redesign of the FSSN approach
- BRIGHTLY should provide remaining inception details as soon as possible including Theory of Change, Localisation approach, Monitoring, Evaluation and Learning approach, and the graduation approach that remains unclear. Progress: These documents have all been drafted and submitted to FCDO. Key policies have been approved and are now being implemented.
- BRIGHTLY should ensure and commit to FCDO that the sustainable impact on household incomes of livelihoods activities will be assessed and evidenced, including for periods after the end of the intervention, and full reporting provided to FCDO. Progress: MERL strategy to be revised and to include more clarity on the evaluation approach.
- All current FSSN partners show limited performance and prioritisation of gender and inclusion. FSSN is well set up to share best practice, and the planned addition of Women’s Rights Organisations should strengthen this. But FCDO should continue to press partners and use TPM partners to provide analysis and good practice. Progress: BRIGHTLY has conducted a gender analysis to form the basis for increased gender/social inclusion in year 3. The WRO pilot under CARE was launched towards the end of this review period and will be assessed in AR 2025-26.
- FCDO, with the support of the TPM provider, should support partners on strengthening gender and inclusion aspects of their Output 2 programming, particularly CFW. Progress: FCDO investigated SFD’S GESI approach in the cash for work initiative, which revealed a more thorough approach than previously known. FCDO recommended that SFD tracks the effectiveness of these measures and capture learning.
Lessons learned:
Whilst direct cash transfers are critical for immediate response, early evidence suggests multi-modal approaches combining and layering cash transfers with additional interventions such as livelihoods support, VSLA formation, community development, training and social inclusion activities, not only address immediate food insecurity but also deliver greater impact in terms of resilience, sustainability and community empowerment. FSSN has a relevant combination of partners and opportunities to achieve real impact, both by evolving the individual approaches, but also by improving the coordination internally, and crucially with external humanitarian and development actors. Developing a balance of influencing and delivering programmes will ensure FCDO is well placed to remain highly relevant once 0.3% ODA implications are felt.

Recommendations:
- To strengthen the relevance and effectiveness of cash transfer programming, greater emphasis could be placed on collecting and integrating beneficiary feedback. This participatory approach helps deepen understanding of community needs and realities, while also contributing to a stronger evidence base for adaptive programming. The new TPM programme (MERLY) will give opportunities to collect this where possible, however this is only likely to be in the IRG areas, due to DFA constraints.
- FCDO should work with partners to establish two-way communication channels with VSLA members, enabling the collection of valuable feedback regarding capacity-building activities, effectiveness of training, areas for improvement, and the evolving needs of participants—ensuring that support remains responsive and community-driven. Reports from SFD particularly now contain more anecdotal examples of successes and challenges.
- FCDO should encourage and facilitate FSSN partners to work collectively to coordinate internally on referring beneficiaries across the portfolio between BRIGHTLY, SFD and WFP to ensure the best sustainable outcomes, making the geographical layering of cash transfers with livelihoods opportunities more effective and so reducing the numbers dependent on humanitarian assistance.
- FSSN should actively work with the FCDO Yemen Economic Recovery Team to introduce their development programmes and pilots to FSSN beneficiaries, capitalising on the opportunities for humanitarian beneficiaries to transition to more sustainable income generating activities, e.g. the Mercy Corps Fishery pilot.
- FSSN should actively explore and enable alignment between elements of its current programme with non-FCDO funded humanitarian and development programmes including the CCY Cash Consortium for Yemen, which has a very similar approach. CCY and BRIGHTLY partners, and importantly their main donors, FCDO, EU, and ECHO are all very keen to see this happen.
- FSSN to use the remaining fully funded FY 2025-26 to gather evidence to evolve the Programme methodologies of Cash Plus, into a better configured and cross Yemen context approach. This requires internal FCDO collaboration, and external partnerships on coordination, joint programming, and innovation. Collaboration between FSSN and the ERT VSLA support programme in design will allow evidence to be gathered and the case for Cash Plus to be strongly maintained.
- Use the year ahead to refine ideas for smaller cost but more catalytic and influential activities for example funding the Cash and Markets working Group, the Cash Donor Coordination Forum, a BRIGHTLY/CCY alignment.
- Explore the opportunities to bring Gulf donors into the Cash space by targeted lobbying and use of evidence, building on opportunities such as KSRs interest in a joint funding initiative with WFP in late 2025.
- Use the FSSN programme relationships (SFD, WFP), new FCDO SDA arriving in mid-2025, the Cash Donor Forum, and the FSSN World Bank support to more strategically link humanitarian programming with Shock Responsive and more predictable UCT Social Protection re- design being led by the WB and UNICEF. Humanitarian allocations and the shape of our future humanitarian programming should be seen through the lens of an eventual transition towards a national SP system which replaces costly and less sustainable humanitarian approaches.

Output Title	Cash assistance is made more efficient and effective towards alleviating food insecurity amongst the most vulnerable populations.
Output number:		3	Output Score:	B
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1. % of complaints/incidents resolved annually	91%	Met expectations / 90%
3.2. Partners incorporate Social Inclusion/GEWE, conflict sensitivity, and other cross-cutting issues into programme activities and report on how these improve effectiveness.	6	Met expectations / 6
3.3. Partner log frame milestone achievement rates (annual)	90% for each indicator	Moderately did not meet expectations / BRIGHTLY: 88%[9] / SFD: 89%[10] / WFP: 77%[11]
3.4. # of collaborations between partners - governance mechanisms support FSSN partners to collaborate and give greater power to national and local organisations, to achieve a more effective and sustainable response	2	Substantially exceeded expectations / 4
3.5. Donor Cash Coordinator delivers inception report and workplan within agreed timeframe	Workplan and Inception Report Approved	Met expectations Workplan and inception report approved in November 2024 and inception report approved in February 2025
3.6 Number of gender sensitive initiatives funded by WROs	WRO/WLOs have been selected following agreed process	Moderately did not meet expectations / 7 WRO/WLOs were selected, but they did not fully follow the selection process
3.7 Number of shock-affected households which receive top-ups	36,605	N/A
[9] Missed indicators are on multi stakeholder coordination, VSLAs and women in leadership roles in community structures.
[10] Missed indicators are on VSLA results and female beneficiaries receiving long term CFN), outcome data not available at time of writing.
[11] Missed indicators are on food consumption scores, nutrition content and adequacy of feedback mechanisms.

Briefly describe the output’s activities and provide supporting narrative for the score.
This output seeks to measure whether the efficiency and effectiveness of cash assistance was improved through strengthened accountability and feedback mechanisms, social inclusion and Gender Equality and Women Empowerment (GEWE), conflict-sensitivity, and collaboration across FSSN partners and beyond. The WRO pilot, designed to select and disburse funds, was started and made significant progress but at the point of this AR it is too soon to fully judge its outcomes. The mechanisms are now in place.

This output scored a B. Whilst there was significant progress made in establishing governance and coordination mechanisms, a number of indicators listed above failed to fully meet expectations or did not have the data to report against the indicator. A score of B is justified in these circumstances.
- Under the BRIGHTLY consortium, 9,076 complaints were received through Complaints and Feedback Response Mechanisms (CFRM), of which 18% of these reported through local implementing partners. 98.8% of these complaints were successfully resolved within the agreed BRIGHTLY Feedback and Accountability Mechanism SOP.
- There is evidence of improved governance and coordination mechanisms across the Programme partners in the last year. This includes eight coordination meetings initiated by BRIGHTLY with key stakeholders to for multi-sectoral collaboration and coordination with the Cash Consortium in Yemen (CCY, Social Fund for Development (SFD), UNICEF, WFP, Food Security and Livelihoods Cluster (FSAC), and the Nutrition Cluster. Contact was also made with the Cash and Markets Working Group (CMWG) and the World Bank to support the referral pathway to the unconditional cash social protection programme, under re-design during his review period. These high-level strategic discussions have been bolstered by ongoing technical level discussions and joint planning meetings to synchronise activity timelines, address implementation barriers and joint risk anticipation and mitigation. A key indicator, not measured by BRIGHTLY itself, but none the less highly relevant, is the high frequency of non-FCDO funded implementation agencies referring positively to their coordination with BRIGHTLY structures. This is particularly relevant to the wider focus of the humanitarian architecture on referrals of beneficiaries and potential beneficiaries between different consortiums and stakeholders.
- Governance meetings with FCDO and programme partners have encouraged lesson learning and information sharing, however the workstreams generated from these discussions need to be followed up to ensure these learnings are applied at implementation level and synergies are taken advantage of where possible. The FCDO team will discuss with partners on the best way to take this forward, including potential check ins throughout the year or setting up working groups. A good example of this is beneficiary referrals from BRIGHTLY to SFD, highlighting the opportunities for interoperability between partners to achieve these indicators.
- Under output 3.2 examples include rapid gender analysis completed under BRIGHTLY to explore the participation and power dynamics effecting women and girls in decision making structures which helped identify entry points for developing community action plans aligned with its transition and localisation strategy. Under SFD support to 6,494 women to utilise e-wallets has improved financial inclusion for those that are not able to travel to access paying agents, through training and incentives to engage.
- Under output 3.4 SFD and BRIGHTLY have coordinated to strengthen joint planning and coordination on overlapping intervention and geographical areas, including referrals of beneficiaries from BRIGHTLY’s UCT programme to SFD’s CFN programme. BRIGHTLY has also built its relationship with the Cash Consortium for Yemen (another consortium led by DRC, funded through ECHO) to support referrals of beneficiaries and data sharing.
The Donor Cash Coordinator function centrally funded by STAAR gained approval for the workplan in November 2024 and the inception report in February 2025. Significant progress towards improved coordination and common messaging between FCDO, ECHO, Sweden, Australia began towards the ed of the review period and continues to grow in influence in mid-2025. Early steps towards closer alignment between BRIGHTLY and CCY (Echo funded) began in early 2025 and are now gaining real momentum, as did WB engagement with cash donors. Regarding indicator 3.6: seven Women’s organisations were selected by CARE however they did not fully follow the selection criteria. Regarding indicator 3.7: Due to administrative delays the World Bank top ups will be delivered in the following reporting period.

This output’s activities gained momentum more slowly than the main elements of FSSN, but are now making steady and innovative progress, laying the foundation for more joined up working between humanitarian donors, a far better understanding of the value of WRO/WLOs, and their unique opportunities to help FSSNs overall goals. We plan to keep the focus in the subsequent review period, building knowledge and evidence for the re-design and evolution of FSSN in the 0.3% ODA context where smaller but more influential and catalytic initiatives may take greater precedence.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Three new indicators have been added to output three, including 3.5, 3.6 and 3.7 to reflect new activities. Output indicator 3.1 has also been reworded from ‘% of complaints/incidents responded to annually’ to ‘resolved annually’ to ensure partners are reporting those that are resolved.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendations from the previous AR:
Given its increasing importance as the Programme matures, FCDO should increase the weighting of Output 3 (which assesses activities to deliver reform) in the logframe and widen its indicators to better capture the breadth of FSSN work. Progress: The addition of three new outputs indicators to reflect World Bank, WRO and cash coordinator activities have been added.

Recommendations:
- Donor investment in localisation: FCDO should engage more with local organisations to amplify the Yemeni voice and bring community level contextual insights to the forefront of programme decision making, risk management and shaping future programme design. Valuable learnings and insights gained from building local capacity should be systematically shared across donor working groups and implementing partners. Formulation of basic localisation indicators in the logframe should be considered for the remaining FSSN period.
- TPM action-based workshops with partners require FCDO follow up and oversight to ensure learnings are taken forward. These could be channelled through the governance meetings with a delivery plan to manage progress on an ongoing basis.
- There should be consideration of how the Programme can integrate more emphasis on and measure results around conflict sensitivity and on the ToC element related to contributing to stability. This can be achieved through undertaking a review of current conflict sensitivity practice and capacities amongst implementing partners, and ensuring all partners put in place a conflict sensitivity plan, with support from the YON Conflict Adviser, including how they are implementing their own organisational conflict sensitivity policies and guidance where relevant, and how they can maximise their contribution to conflict prevention and peacebuilding through the ‘Triple Nexus’ lens.
- Build capacity of the FCDO programme team to engage with implementing partners on conflict sensitivity and to assess conflict sensitivity as part of regular reviews and reporting, including through TPM via MERLY.

## D: VALUE FOR MONEY
Approach
This year saw the establishment of value for money indicators and agreement of these across partners to aid comparative analysis. This is the first year that partners are reporting on several of these indicators which will inform any adjustments required in future years. In addition to quantitative measures a set of guiding questions aligned with the five Es, has been established. These questions have been disseminated to partners to promote consistent and comprehensive data collection and analysis, thereby enabling a clearer assessment of performance and impact.

Partners have varying focus on VFM, with SFD having engaged independent advice to conduct a VFM assessment, across all its programming, this supports the evidence available. BRIGHTLY, SFD and WFP have reported VFM indicators in its annual report although with limited narrative on rationale behind data from BRIGHTLY and WFP.

VfM performance compared to the original VfM proposition in the business case
The Business Case asserts that the scarcity of data also means that VfM arguments of the associated interventions continue to be limited and the Business Case sets a priority for the Programme to work on building up the data and strengthening the methodologies for assessing the VfM of humanitarian cash transfers and social protection programmes, including in emergencies, which currently focus on effectiveness and speed of response, this will be aided by the agreed indicators. The following assumptions were made in the business case:

Economy
That under the World Bank UNICEF operating costs would be at 8% and transaction fee for banks 2.5%. Activities with UNICEF under the World Bank have not yet commenced so it has not been confirmed what the operating costs are.

Efficiency
WFP: that 82% cash programming would go directly to beneficiaries and the use of SCOPE (WFP’s beneficiary information and transfer management platform) reduces costs by harmonising beneficiary registration and reducing staff costs. Over the course of 24/25 73%[12] of cash programming goes directly to beneficiaries, challenging the assumption in the Business Case. FCDO continues to advocate for WFP to utilise mobile money to transfer funding to beneficiaries given the relative success of this under SFD and the likely improvement in VFM. WFP is commencing a pilot in 2025 of transferring directly to beneficiary bank accounts and will then test mobile money transfers.
[12] 27% covers indirect costs including all overheads.
BRIGHTLY: that 73.9% of funds would go directly transferred to beneficiaries under its unconditional cash and cash for work activities. However, under the Programme 84% is transferred directly to beneficiaries compared to costs to deliver, going beyond the assumption. Further investigation will need to be done to understand how the cost transfer ratio is calculated to support this conclusion of increase efficiency.
SFD: that 80-85% would go directly to beneficiaries under cash for nutrition and cash for work activities where 86.5% goes directly to beneficiaries compared to costs to deliver. As with BRIGHTLY further investigation will need to be done to support this improved efficiency than envisaged.

Effectiveness
SFD: the nutritional conditions would be improved through support. SFD does not collect data on food consumption scores for beneficiary households due to authority restrictions on data collection so it is not possible to examine this assumption.
WFP: Retargeting and biometric registration would improve efficiency of funding as it would target the right people. WFP commenced a retargeting exercise in 2024 applying updated inclusion and exclusion criteria which has led to a reduced caseload, improving the efficiency. WFP has finalised the revision of the beneficiary list and is now launching registration for pre-identified vulnerable households due to be completed by the end of 2025. This has seen the number of beneficiaries decrease from cycle three in 2024 with 912,092 to 781,644 in cycle one of 2025. This has allowed for an increase in amount transferred to beneficiaries (increasing from 13,500 YER to 17,500 YER). Since 2023, WFP has not been able to utilise biometrics for validation of beneficiaries because of authority limitations in both DFA and IRG areas.

Equity
World Bank: that the use of Washington Group Questions and MIS to monitor grievances and identify challenges would support efficiency and equity. Additionally that the World Bank would use the first week of disbursements to serve the remote archipelago of Socotra, home outreach services for the most vulnerable and they would establish female only payment sites. The World Bank has not yet delivered activities with FCDO funding but these assumptions will be discussed and tracked.
SFD: that support would be split between host and IDP communities.
NSFD reporting disaggregates IDP beneficiaries although they are of limited coverage. 155 out of 13,252 IDPs received CFN in the reporting period
NGO: the delivering through NGOs would reach harder to access areas. With the commencement of the MERLY programme in YON

Cost effectiveness
The two cost effectiveness assumptions in the Business Case are based on cross sector evidence which continues to be valid. The pending outcome assessment will provide further evidence of the FSSN programme to support analysis.
Increased aid efficiency and cost effectiveness through cash reform, including a more sustainable and predictable response to food insecurity paving the way for a nationally owned and financed social protection system in the future. Every US$1 invested in building people’s resilience, through safety nets and/or income-generating activities, will result in up to US$3 in reduced humanitarian aid and avoided losses.
Investing in early response and resilience is significantly more cost effective than providing ongoing humanitarian aid and that the Programme will decrease humanitarian need through preventative efforts.

Key cost drivers and performance
The primary cost drivers across our partners include cash-based interventions such as cash for nutrition and cash for work, as well as investments in development activities like Village Savings and Loans Associations (VSLAs).

Economy
  - % of funding to Yemeni partners
Whilst this indicator is measured at economy it also supports assessment of the sustainability of interventions. Increased funding through Yemeni partners alongside capacity support improves the likelihood of sustained localised support beyond the Programme (effectiveness and cost effectiveness).

BRIGHTLY: On average BRIGHTLY partners channelled 32% of its funds through Yemeni partners. SCI had the highest % of 27.7% with Oxfam as the lowest at 11.5%.
SFD: 100% given that it is set up as a Yemeni organisation.
WFP: three out of four of WFP’s partners are Yemeni organisations but only a small amount of total funding goes to downstream partners, in the reporting period this equated to around 2%.
CARE (WRO): 67% provided to WROs as grants

The partnership with SFD continues to support a more sustainable investment, given its alignment with a longer-term social protection system through engagement with the World Bank. The nature of the CARE WRO programme is to provide grants to local organisations and this continues to support efforts towards a more efficient and effective cash response. The standard challenge of localised support is ensuring capacity to deliver against donor requirements, the CARE pilot specifically addresses this issue and given the ongoing contextual challenges it is recommended support to local organisations through this capacity building mechanism is continued after the pilot.

Given the variation between BRIGHTLY partners of funds channelled through Yemeni partners it is likely there could be greater sharing of best practice. BRIGHTLY has provided some strong qualitative examples of its efforts towards localisation within the Programme, including the development of a strategy including bringing in an external consultancy to support capacity assessments of local partners and develop tools to improve compliance (risk management and financial management). Local partners also benefited from BRIGTHLY trainings on VSLA, safeguarding and protection pathways. Several of these localisation efforts were delayed to 25/26 due to competing priorities, particular leadership roles in the BRIGHTLY technical working groups and involvement in strategic decision making, these will be reflected on in the 2026 annual review. These efforts improve the cost effectiveness of the FSSN Programme.

Whilst WFP delivers through three national NGOs there is limited reporting on capacity building efforts. WFP has flagged they provide continuous training including PSEA and gender mainstreaming. FCDO will work with WFP to update the delivery chain map to ensure amounts flowing through second tier partners is transparent. There is a balance to be made between delivering results at scale and efforts toward localisation and the FSSN mix of partners continues to support maximising efforts on both fronts.

  - Indirect Costs[13]
    [13] Indirect costs include expenses which support the overall delivery of the Programme including overheads, NPAC, monitoring, central salaries. These can be calculated differently between organisations so comparisons are not always possible.
BRIGHTLY: 23% on average for partners, with SCI as the highest ay 37% and Oxfam at the lowest at 12%. Interestingly these two partners have the corresponding highest and lowest for funding through Yemeni partners, which could be linked in terms of additional resource required.
SFD: 14.5% which equated to £2,479,013.34 was spent on indirect costs, comprising 7% to project shared costs and 7.5% to operational costs. The SFD approved budget includes 10% for project shared costs so an improvement in efficiency is noted. There is discrepancy between what SFD includes as project shared costs and FCDO’s standard practice on this as well as other partners approach. FCDO and SFD to discuss classification of costs to support comparative analysis for VFM.
WFP: 26.7%[14] on implementation costs.
[14] All funding that is not received by beneficiaries
CARE (WRO): 31% was spent on indirect costs (£43,669), whilst this is comparatively higher the nature of the activities under this component would lead to greater indirect costs as technical support to organisations for capacity building would have incurred greater salary costs.

  - NPAC (part of indirect costs) or fee
With the large decrease in BHA funding in Yemen that several partners were previously supported by FCDO will need to maintain close oversight on NPAC %s. These are set in partner budgets but can fluctuate over the course of the Programme.
BRIGHTLY: The NPAC for the consortium was 8.4% of the total spend for the year at £1,456,849.83. CARE has the highest % of NPAC at 11.64%, Oxfam at 6.34% and YFCA 6.54% are the lowest across the consortium.
SFD: Further discussions are due to ensure alignment on classification of project shared costs.
WFP: 6.1% support cost similar to INGOs calculation of NPAC.
World Bank: Whilst FCDO funding that was disbursed in 24/25 will be utilised on activities in 25/26 that are yet to incur cost, the FCDO funding will incur a fee to the World Bank and UNICEF as two multilateral partners. However, even as a combined cost this is a fairly average % compared to other delivery partners. The World Bank charge for recipient executed activities 5% (£60,085), the UNICEF charge is at 3% (£35,001). The portion of the funding that is Bank executed (analytical activities) is charged at 12% (£13,887). Therefore, a total of £108,973 (7.8%) will be spent on fees.
CARE (WRO): 4.2% (£5,843.58) in line with agreed budget.

  - Cash Transfers (also effectiveness)
The amount of cash assistance provided by all partners are set by the Food Security and Agriculture Cluster (FSAC) rates which vary between IRG and DFA areas given the differing exchange rate. The FSAC rate There is a wide range in value amounts to beneficiaries across partners set out below. Without SFD reporting at outcome level it is difficult to assess whether there are greater gains in food insecurity as a result of higher amounts or more frequent payments. This should be assessed as part of the MERLY outcome assessment to understand if there are variations linked to these two varying factors. For outcome indicator 1.1 WFP has seen lesser deterioration in household food consumption scores being rated as poor or borderline with 74.8% compared to BRIGHTLY’s 89%. Outcome indicator 1.2 however sees better results for BRIGHTLY with percentage of households reporting crisis or emergency coping strategies at 44% compared to WFP’s 73.1%. It is not possible to draw a direct correlation with cash frequency and amounts (both being higher for BRIGHTLY) to these outcomes given the variations in methodology (BRIGHTLY also delivering cash for work).

Cash disbursement per round
	BRIGHTLY	SFD	WFP
Unconditional cash/Cash for nutrition	YER 58,000 in DFA areas per household per month / YER 140,000 in IRG areas (on average six rounds in one year) per household	YER 20,000 per month in DFA areas per household per month / YER 37,000 per month in IRG areas per household per month	YER 13,000 (first two rounds) per beneficiary / YER 17,500 (last two rounds per beneficiary) with four cycles funded by FCDO in 2024/5 only in IRG areas
Cash for Work/Livelihoods	Average four-six rounds in one year / YER 64,000 in DFA areas / YER 154,000 in IRG areas	$82.6[15] per month on average (over a sixth month period)	N/A
[15] Received in YER against the fixed USD amount.

The variation in cash transfer amount and the associated outcomes for beneficiaries will be assessed in the upcoming outcomes assessment to be completed by MERLY.

  - Charge by financial service providers to deliver cash
BRIGHTLY: 2% average for UCT and CFW.
SFD: CFN = 4.5% average CFW = 1.76% average
WFP: $0.66 per transaction and $1 for mobile transfers which equates to just under 1% but no detail available for bank to FSP so a comparison cannot be drawn with SFD. WFP drives competition by re-tendering each year assessing coverage and fees charged by banks.

The variations in charges by FSP (including banks) should be discussed between partners to understand if lower fees can be sought.

Efficiency
Cost transfer ratio UCT/CFN
There are still variations in methodologies and reporting between partners and further work will be done ahead of the next annual review to harmonise this.
SFD = 13.5% (13p per £1 to beneficiary)
BRIGHTLY = 16% (16p per £1 to beneficiary)
WFP = 22% (22p per £1 to beneficiary)[16]
[16] WFP reported that $23,491,595 funds went to beneficiaries which is 73.3% of the total budget based on WFP confirmation of receipt of $30,094,353 (after overhead) in 24/25.
World Bank (costs not incurred yet) = 23% (23p per £1 to beneficiary)

SFD (13,252 beneficiaries) and BRIGHTLY (69,735 beneficiaries) as NGO/INGOs have lower CTRs for unconditional cash transfers, demonstrating greater efficiency in delivery, likely because of utilisation of mobile money (SFD) and bank transfers to a greater extent than WFP (912,092 beneficiaries). The relative reach of WFP and anticipated reach of the World Bank should deliver economies of scale; however the challenges of vaster geographical coverage will incur higher costs.

Cost transfer ratio CFW
SFD = 21% (21p per £1 to beneficiary), this is expectedly higher than SFD CFN as it includes costs for supervision, tools and materials to deliver income support and community assets. SFD spent £5,551,239 in 24/25.
BRIGHTLY = 16% (16p per £1 to beneficiary). This is the same cost as delivering unconditional cash which is inconsistent with supporting work activities and therefore needs further investigation.

% of beneficiaries receiving transfers through mobile money
SFD’s awareness raising and incentives to utilise value for money support its figures in beneficiary adaption. SFD offered a $10 reward for opening an e-wallet and a $10 incentive for every three transactions completed within a ten-day period. 6,627 individuals from rural communities were supported through engagement with 98% of these being women (the majority of beneficiaries are women). For beneficiaries with limited formal education (40% of participants) extended awareness sessions were provided. 98% of e-wallet users are women, this is a higher % than those who are beneficiaries, showing that this is a preferred method for women. A total of 4,835 beneficiaries has opened e-wallet accounts with 131, 892 transactions. It will be important to see if beneficiaries continue to use e-wallets without the payment incentives and how many beneficiaries out of the 4,385 who opened e-wallet accounts are actually using them. SFD’s independent VFM assessment established that 42% of beneficiaries remain active once incentives stop.

Challenges include lack of ID documents among some beneficiaries, limited smartphone ownership, inadequate SMS coverage from e-wallet providers in some areas (11 providers were employed to generate as much range as possible), and poor or absent mobile network coverage in some areas.

WFP also conducted a cost efficiency analysis on its cash programme which recommended pursuing digital transfers to make cost savings. WFP’s pending pilot utilising bank transfers and mobile money is encouraging given the evidence that this is the most efficient model of cash delivery and has the added benefit of preparing beneficiaries for future inclusion in the re-designed social protection programme being worked up by the World Bank, UNICEF and SFD.

BRIGHTLY has referenced geographical accessibility, network coverage, device availability and digital literary as barriers to utilising mobile money as a delivery method. However, given the success of mobile money under SFD in rural areas there may be benefit in cross learning between partners.

Verification/Targeting Processes
World Bank: For the shock responsive top up round that was funded by IDA from the World Bank 115,000 households were reached as opposed to the planned 31,000. This was a result of authorities not allowing the payment to sub district households, but that whole districts had to be covered. The transfer value was therefore reduced (as opposed to increasing the total budget), likely making the transfer less impactful for households. This suggests that more households were reached that did not initially qualify for the payments as a proportion of the total, than those that did qualify. For FCDO funding, an updated proposal from the World Bank setting out how targeting and verification will be improved through authority and community relationships.
WFP: WFP utilizes a two-step sequential targeting method comprising "geographical and community-led targeting" to accurately identify severely food-insecure households. Geographical targeting is based on Famine Risk Monitoring (FRM) results and population figures from the Central Statistics Organization (CSO), which help pinpoint districts at the district level using the Integrated Food Security Phase Classification (IPC) and the World Health Organization's (WHO) Global Acute Malnutrition (GAM) rate thresholds.

Effectiveness
% of cash used for food and other immediate needs
BRIGHTLY: 66.8% of cash used for food and immediate needs
WFP: 90% of cash used for food
SFD: Due to security concerns and delays in obtaining the necessary permits, SFD was unable to collect data on FCS for this performance period.

UCT cash transfer value as % of minimum food basket
The minimum food basket assumes a minimum daily requirement of 1,676 Kcal/person/day and the MFB is 80% of this as Yemen is a protracted crisis, 20% of food needs are expected to be met through other livelihood means. The rate is set by the Food Security and Agriculture Cluster in Yemen. The value assumes a seven-person household and has increased over 24/25 as a result of the economic situation. The basket was 131,500 YER in the South, moving to 171,000 YER in March 2025, and 65,000 YER in the North, per month.

BRIGHTLY:
  - UCT DFA: 58,000 YER per month equating to 89% of the MFB.
  - UCT IRG: 140,000 YER per month equating to 106% of the MFB.

SFD:
  - CFN DFA: 20,000 YER per month equivalent to 30.8% of the MFB
  - CFN IRG: 73,000 YER per month equivalent to 55.5% the MFB.

WFP: Reported at 87% but this assumes eight cycles in a year. In 2024 WFP delivered four cycles of 122,500 YER in the South, assuming a 7 member household (where WFP delivers cash) which equates to 62% of the MFB across the year taking into account the number of cycles.

Capacity building of local partners
The evolving Yemeni context sees a downward trend in funding to the humanitarian crisis which further emphasises the need for sustainable delivery mechanisms. This coupled with an increasing need for national and local knowledge to delivery in the complex political and security landscape, reiterates the importance of capacity building of local partners and improved localisation in delivery.
Under BRIGHTLY there is a localisation TWG led by YFCA which has produced a strategy and workplan, jointly with second tier local partners. Second tier partners’ engagement in TWGs has been limited and should be a priority going forward, including fulfilling the commitment to co-chair these groups where possible. These partners have benefitted from a total of seven formal trainings and workshops run by BRIGHTLY on VSLAs, referral pathways, GBV and child protection, health and safety and safeguarding and protection pathways during the reporting period. In the coming year FCDO will plan to improve its engagement with second tier partners to inform monitoring of capacity building efforts.

WFP has three Yemeni organisations as part of its delivery chain but has not reported on any capacity building efforts with these partners. FCDO will engage with WFP in the following year to understand WFP’s capacity assessment of these partners and building efforts where needed.

With SFD as a national Yemeni organisation FSSN’s continued investment demonstrates a commitment to the sustainability of a long-term social protection solution for Yemen. FSSN’s investment in the World Bank in 24/25, supports its oversight and capacity building role with SFD.

The WRO pilot through CARE has been designed to build capacity of local organisations to support the response to the food insecurity crisis. WRO involvement in project design also supported empowerment of the organisations and locally led interventions tailored to needs. Capacity building began with a capacity assessment through surveys and interviews to identify gaps and informed selection on learning topics including strategic planning, MEAL, financial sustainability and compliance and risk management with both leadership and technical staff to maximise the benefit to the institution. Pre and post tests were deployed to assess the effectiveness of the training with an overall knowledge gain of 38%. There were some challenges reported on the application of INGO policies being applied to local organisations which are not adjusted for local processes including on Ramadan working hours. Additionally, feedback has suggested other methods of capacity building beyond training would be helpful as the organisations have received a lot of training. These challenges were not reported by CARE in its reporting so would suggest a need to improve the follow up with the WROs to improve future interventions.

Equity
The indicators used to measure FSSN’s equity are:
% of beneficiaries which are women
BRIGHTLY: 37% of household beneficiaries were women headed.
SFD: 75% of beneficiaries were women, with cash for nutrition solely targeting women headed households.
WFP: 49% of household beneficiaries were women headed.
WRO: 100% of beneficiaries, aside from targeted men for awareness raising which was 12 out of 25.

% of beneficiaries living with a disability
BRIGHTLY: 4% of household beneficiaries have a disability
SFD: 19% of beneficiaries have a disability
WFP did not share data on number of beneficiaries who have a disability which is not aligned with the use of the Washington Group Questions or screening criteria and needs to be rectified.
WRO: 0% however under one WRO women with children with disabilities were targeted which suggests the reporting does not capture this and will be addressed in future.

SFD’s ability to reach a greater % of people with disability is perhaps a reflection of the benefit of a national organisation with long term ties to communities, where disability is taboo and families will often hide children with disabilities during surveys. This reach and reporting needs to improve for other partners particularly in a context where people with disabilities are heavily marginalised. Without an assessment of the number of people with disabilities in Yemen and data gaps it is difficult to compare PwD beneficiaries against the population but the global assumption of people with disabilities is 15%,[17] suggesting a limited reach to those with disabilities through the FSSN programme.
[17] WHO estimate of 15% of global population living with disabilities

For future reporting FCDO will request disaggregated data for IDP and ‘Mahamasheen’ beneficiaries where possible.

Assessment of whether the Programme continues to represent value for money
The Programme is largely delivering in line with the VFM assessment in the Business Case. Key monitoring over the coming year will be the management of exchange rate variations by partners given ongoing economic challenge and the relative value to households,

E: RISK
A structured and proactive risk management process is maintained and monitored by the YON FSSN programme team. This includes a bimonthly review by the PRO, highlighting updates from the Programme managers, and quarterly review by the SRO. These reviews focus on each risk category, assessing risk appetite and ratings, and monitoring the status and actions required to address both emerging and ongoing risks. Ad hoc risk discussions are covered in weekly meetings, including evolving risks and those that may require escalation in line with the FCDO YON escalation framework. Additionally, monthly updates from partners are incorporated into overall risk assessments and inform the YON monthly Programme Board risk oversight.

Throughout the reporting period, the overall risk rating for the Programme was ‘severe’, in line with the rating at approval stage. Risk appetites per category have not changed over the past year but were reviewed as part of a cross-portfolio review in November 2024. The appetites for strategy and context, policy and programme delivery and reputational risks remain eager. Appetites for safeguarding and financial and fiduciary risk are receptive, and people and public service delivery and operations at cautious. Currently one risk remains outside the Programme’s risk appetite (safeguarding category) and has been escalated accordingly (see below for details).

The humanitarian response in Yemen faces a complex array of risks that could impede the delivery of the Programme. The following risks have been particularly relevant over the course of the reporting period, with some evolving into issues[18]:
[18] FCDO monitors issues in the same framework as risks and these are therefore included.

FTO Designation of Ansarallah (known as the Houthis) by the US - Major
On March 4th the US Department of State announced the redesignation of Ansarallah at an FTO. This intention was announced in January but no updates on general licenses were given until 5th March to exclude humanitarian activity from the FTO designation. This designation created risks that cuts across financial and fiduciary, policy and programme delivery and strategy and context appetites, with risks at severe. All delivery partners had to reassess their ability to deliver in DFA areas, with the risk of prosecution given the delay in general licenses, and subsequent residual risk utilising telecoms and banking infrastructure. CARE took the decision to withdraw its operations and offices in the North of Yemen and is subsequently working through the implications for the BRIGHTLY programme, although the other consortium members delivering in DFA areas continue to do so. Given CARE’s head offices are located in the US the FTO prosecution risk for CARE was increased with continued operations in DFA. With this departure the management of the risk around asset disposal procedures is being overseen with CARE. The residual risks to the Programme include:
1. Ongoing increased tension with the US and potential retaliation by the Houthis, increasing the safeguarding risk to delivery partner staff as well as access challenges to deliver activities. This could also lead to further withdrawal of partners and limited humanitarian access in the North.
2. A chilling effect to DFA infrastructure particular on banks and imports has an impact on funding flows as well as availability of basic goods, driving inflation which challenges programme delivery and financial management. Several banks have relocated their headquarters to IRG areas and CBY Aden has begun a third-party certification process to support compliance with the US FTO designation. This signifies a further stratification of the IRG DFA financial systems and potential risk of blocked transfers between the two areas although there has been limited changes thus far. There is also a risk of blocked transfers from international banks to banks who do not move their headquarters to IRG areas due to a perceived none compliance with the designation.
To address these risks, there is increased engagement with partners on the related risk management and mitigations include: i. Increased frequency of payments where appropriate, reducing the amount of UK Aid funding held in accounts that could be blocked from withdrawal ii. Utilisation of the FCDO TPM to test financial flows against the delivery chain maps of partners iii. Renewed security assessments by partners to support staff safety and increased oversight of live situations iv. Reduction of staff or withdrawal in certain areas when appropriate v. Reallocation of activities where access is restricted in the long term, in line with Programme priorities. There is a wider impact of the designation that increases the humanitarian needs in DFA areas, combined with the decrease in donor funding (see risk 5) risks challenge to the FSSN theory of change activities on graduation and livelihoods from cash support. The FTO designation and reduction of assistance heightens the need for conflict sensitivity in the response, as there is greater competition for scarce resources.

Limited access to deliver programme activities - Major
The access risk is classified as severe and covers safeguarding and programme delivery categories as a result of limited access to geographical areas or approvals for specific activities for delivery partners, which hampers the ability to reach beneficiaries. Contributing factors include ongoing conflict, security restrictions, limitations on data collection-based activities (biometrics, situational assessments, MEAL), detention of delivery partner staff (see risk 4), restrictions based on US FTO designation and subsequent retaliation. Over the course of the year this has resulted in delays in approvals for delivery, particularly for BRIGHTLY in DFA areas, and blocked activities including monitoring efforts by SFD and BRIGHTLY. This has required adjustments of workplans and in some cases changes in activities’ location or nature which has also impacted forecasting and financial management. The FTO designation meant CARE had to withdraw from the DFA areas, eventually retargeting its funds in new locations in the IRG areas, with FCDO agreement. Save The Children also withdrew its main office from Sa’naa, and relocated to Aden, but as its BRIGHTLY programming was already in IRG areas this did not have a detrimental effect on delivery. The remaining BRIGHTLY partners in DFA areas, Oxfam, NRC and YFCA, are able to deliver and meet the needs of beneficiaries. At the point of writing FCDO judges that BRIGHTLY remains viable and delivery targets are able to be reached.

To mitigate these risks partners build relationships with authorities where possible and test what works for approvals processes. The ability to remain and be seen to be impartial is critical for negotiating and maintaining access and is an important element of conflict sensitivity that can be better captured in reporting. Partners also support OCHA’s Access Advocacy through information sharing with the Humanitarian Access Working Group. Additionally, FCDO encourages partners to increase localisation of activities to national/local based NGOs where these partners are more likely to have local contextual knowledge and improved access. These combined strategies aim to ensure continued support to vulnerable populations amid a complex access environment.

Aid Diversion - Major
The risk of aid diversion under the fiduciary category is rated as severe with funds potentially being misappropriated or diverted for illicit and other purposes, undermining the intended impact and eroding donor trust. With increasingly complex financial structures, delivery chains and challenging economic environment the aid diversion risk requires ongoing oversight. There has been an increase in fraud case reporting during the course of the performance year 19 fraud cases were reported, up from 11 the previous year, however this is likely a result of increased emphasis from FCDO on the importance or reporting potential cases, as opposed to increased incidents of fraud. The partner governance meeting in February supported assessment and sharing of mitigations of key risks in the delivery chain, including financial service provider, disbursements of cash, verification of beneficiary lists, and deductions by communities or authorities following cash payments to beneficiaries.

The following are mitigations against the aid diversion risk i. FCDO TPM of cash distribution ii. Assessment of partner financial management and structures through due diligence assessments iii. Partner verification of beneficiary identification (for more detail see Section D) iv. Going forward, FCDO TPM will also look to assess the alignment of partner financial management with the processes asserted under FCDO due diligence assessments. A sector wide review of the perceptions of the risks of diversion was commissioned by the HC/RC in late 2024 and published in early 2025 with FCDO acting as part of the reference panel. Several recommendations including the establishment of a Risk Management Unit within the UN structure and a strengthening of the Joint Operating Principals will be elaborated on once adopted at HCT level. Further actions will follow.

Safeguarding of delivery staff - Major
The key safeguarding risk under the Programme during the performance year has been the safety of partners’ staff which is a severe risk, particularly in conflict zones or areas with authority interference, where staff may face threats or violence. During the performance year several delivery staff members have been detained by authorities in DFA areas with no basis. The first round of detentions occurred in June 2024 and since then the sector has reduced activity in DFA areas to broadly that of life saving only. One CARE staff member has recently been released from detention, but further detentions have also been made with no releases so far. This is beyond the Programme’s risk appetite for safeguarding as has been appropriately escalated. CARE has withdrawn activities from DFA areas as a result of the FTO designation as well as the ongoing threat to staff. A further safeguarding risk as a result of increased attacks in DFA areas particularly arial bombing. All staff have remained unharmed but this has also led to the withdrawal of some individuals out of DFA areas and cessation of activities when necessary.

FCDO continues to support delivery partners to adapt programming where staff are not safe, emphasising this as a priority. Partner management of this risk includes ongoing security assessments by the partner to ensure appropriate measures are in place, such as risk assessments, security protocols, building community relationships and contingency planning as well as building relationships with authorities to ensure approvals for activities before commencement and liaison following any interference. Some activities have not had approval from authorities, particularly those including beneficiary data collection and this has meant an adaptation of activities and cessation in some cases. This has included BRIGHTLY suspending MEAL assessments in Saada due to authority approval rejection and SFD pausing operations of its MEL call centre for much of the year due to new requirements for DFA verification of MEL tools.

Donor Funding Decline - Major
The risk of fund reduction, particularly due to the significant reduction in US funding and FCDO’s planned reduction from 26/27 to 0.3% of GNI globally, has immediate and long-term effects to the continuity and effectiveness of the humanitarian response in Yemen. This risks the sustainability of the FSSN programme impact as well as success of shorter-term impact of activities, in terms of moving beneficiaries away from reliance on cash support as prioritisation may be given to meeting basic humanitarian needs only. Additionally, external to programme activities there will likely be an ongoing increase in humanitarian needs with the reduction in funding and economic decline impacting basic needs. The ceasing of the bulk of WFPs food assistance programmes in the North will add to the growing food security challenges. The annual spending reviews for HMG also created uncertainty for partners, with budgets for 24/25 only announced in March 2024 and a subsequent delay in some activities. Delays in confirmation of 25/26 budgets has also impacted partner delivery in the earlier part of the current performance year as well as budgets that are lower than maximum amounts in agreements, particularly for SFD and BRIGHTLY, risking non fulfilment of results anticipated in proposals.

FCDO has worked to inform partners of budget allocations as soon as these are communicated to YON, confirming a smaller amount in April 2025 for example to provide some certainty and then a final amount later in May. Following reductions in BHA funding in early 2025 FCDO engaged with partners to understand impacts to their operations and in particular to key sector gaps to understand if there are discrete areas where FCDO can support to support short term disruption. FCDO subsequently was able to disburse a further £400,000 to UNHAS. FCDO continues to explore alternative funding opportunities, such as co-funding arrangements with Gulf donors and foundations, to diversify sources of financial support. Ultimately however in 25/26 FCDO and delivery partners will need to assess an update the approach which will be informed by the 26/27 allocations information that will be due later in 2025 and assess the validity of the Theory of Change as a result of this, in the context of a reduced funding landscape.

Deteriorating Humanitarian Context - Major
A deteriorating humanitarian situation in Yemen significantly escalates existing risks. Increased hunger, malnutrition, disease outbreaks, and mortality create a dangerous cycle of vulnerability. The breakdown of essential services like food security, healthcare, and water access further compounds the drivers of conflict and suffering, undermining prospects for recovery and long-term stability.

Yemen’s economy further deteriorated during the reporting period with suspensions by the IRG Central Bank of DFA linked banks accessing the SWIFT system and DFA’s retaliation ban of 13 IRG linked banks, deepening economic fragmentation and subsequent divergent currency values: YER 530/USD in the North vs. YER 1,840–2,560/USD in the South. In the South, Yemeni Rial sharply reduced household purchasing power. The sharp depreciation of the Yemeni Rial in the South severely eroded household purchasing power, forcing over 60% of families to spend the majority of their income on food. This contributed to escalating food insecurity and alarming rates of Global Acute Malnutrition (GAM), with 22% in Hajjah and 40% in Hodeidah (IRG-controlled). These dynamics, compounded by high inflation, rising food prices, fuel shortages, and the cessation of oil exports from the South, exacerbated household vulnerabilities and increased reliance on negative coping mechanisms. The parallel banking systems, inconsistent monetary policy, and suspension of financial transfers have further impeded humanitarian cash-based programming and financial access for local partners. This severely challenges the sustainability of FSSN interventions as well as the proportion of the vulnerable population it supports (if an increasing number of people fall into vulnerability).

To mitigate the deteriorating humanitarian situation, supports Yemeni organisations such as SFD, and WROs, contributing to the implementation of a localization strategy through various partners. Communities have been further empowered through a range of development activities, including IGAs, VSLAs, and SMEDs to become resilient in the face of future shocks. FCDO supports coordination among humanitarian actors (through output 3 and wider efforts) to support the improvement of the efficiency and effectiveness of humanitarian support to reach those most in need effectively.

Forward look
In the coming performance year key risks set out in the section will continue to require close monitoring, in particular the deteriorating political context and declining donor funding, heightened conflict sensitivity risks and needs, and potential need to adapt the FSSN approach as a result. Additionally, the evolving impact of the security situation and US FTO designation to the operations of delivery partners, in particular bank liquidity. This will require continued close engagement delivery partners by FCDO as well as ongoing assessment of the context through analysis and partner reporting.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
The FSSN Programme continues with the three main delivery partners SFD, BRIGHTLY and WFP in 2024/25, in addition FCDO has commenced an administrative arrangement with the World Bank, through an existing agreement under another programme in the YON portfolio. Additionally, FCDO has commenced an accountable grant to CARE for a pilot to support local women’s rights and women’s led organisations. The challenging contextual shifts during the performance year, including detentions of staff, the US FTO designations, evolving insecurity and economic turmoil has impacted partner’s ability to deliver.

The FSSN Programme Team has had significant changes over the course of the performance year with a new SRO and PRO joining the team in August and October respectively, a new programme manager joining in January. This has inevitably seen a change in historical knowledge and relationships established under the Programme. Partners have been supportive of new FCDO team members, providing introductory sessions and re explaining decisions as required. This has however inevitably required a period of adjustment and re-establishment of relationships and ways of working.

Partner Delivery Performance
BRIGHTLY: BRIGHTLY’s ability to respond to the cholera outbreak in April 2024 and flooding impacts on Al Zuhra and Hajah district in August 2024 is a good demonstration of contextual adaptability. As a consortium there have been challenges in managing a complex delivery context, including aligning financial management expectations. Requests from BRIGHTLY to FCDO around changes in activities or reallocation of budget due to savings have often not included the correct information or allowed for enough time to review or address questions from FCDO. This suggests a need for an improvement in the understanding of requirements and ways of working. There have also been delays in submissions and some challenges in clarity of information during meetings. This has improved towards the end of the performance year with clearer communication on results that are on track and those that are behind. In 25/26 FCDO and BRIGHTLY will work to establish a way of working document to ensure expectations are agreed and to support efficient engagement. In terms of formal reporting BRIGHTLY has largely met agreed deadlines although at times these have been delayed without updates. This is likely reflective of the complexities of managing across a consortium as well as staffing changes within the Programme Management Unit, but improvements are expected given the stage of the Programme.

SFD: SFD has generally provided timely reports; however, the reporting can lack depth needed to present a full picture of progress and accurately reflect the efforts made on the ground and in some places is hard to follow. In some cases, this has delayed the finalization of the reports, as it required additional comments and follow up meetings to address feedback. SFD ensure that relevant staff, from management to field workers, are involved in program meetings and actively participate even in ad hoc meetings which helps support communication and coordination. Furthermore, they proactively discuss risks and update the delivery chain. At times there have been varying information provided by different members of SFD on live risks, which is likely reflective of the challenging nature of the Yemen context, however it would be beneficial for SFD to ensure internal alignment ahead of discussions with FCDO.

CARE-WRO pilot: CARE has been responsive and willing to participate in meetings, fostering open communication, although more advanced preparation between project colleagues ahead of meetings with FCDO would be beneficial. While their commitment is evident, there have been some delays in deliverables and reporting, which have impacted project timelines. As they are currently implementing a pilot project, this phase is a valuable learning opportunity. It’s recognised that there is room for improvement to enhance efficiency and timeliness moving forward.

WFP: WFP has continued a strong relationship with FCDO during the performance year, with transparency on contextual challenges. Whilst the contribution agreement under the FCDO central framework agreement sets the parameters for streamlined reporting WFP colleagues have supported increased engagement with monthly and quarterly meetings, as well as quarterly reports. With the new agreement for 25/26 reporting is streamlined to biannual in line with the Grand Bargain but quarterly and monthly meetings will support ongoing engagement. WFP has also supported understanding of financial flows of FCDO funds. The framework agreement limits the types of fraud and safeguarding cases that WFP is required to report to FCDO but WFP has been proactive in flagging potential fraud cases to FCDO and in open communication on the risk areas in the delivery chain.

There was a significant delay in the disbursement of £1,000,000 for UNHAS (through the WFP CA) due to challenges around requirements for the UN to state its position on the Mahram issue.

World Bank: As a key partner, the World Bank plays a significant role in the program’s overall framework as they are updating the UCT cash disbursements to support a modernised social protection system to support transition away from short term cash delivery. FCDO aimed to contribute to the implementation of shock-responsive top-ups of UCT under the Yemen Emergency Social Protection Enhancement project which will start by September 2025, after being delayed due to the IDA restructuring. These shock responsive payments targeted households in districts that are disproportionally exposed to conflict and climate-related shocks including flooding and drought. However, the World Bank and UNICEF were not able to establish a grant agreement in time for the cash cycle in December 2024. UNICEF therefore utilised IDA funds instead for this activity, with FCDO funding due to be utilised in 25/26 for the next payment cycle for shock responsive top ups. FCDO will need to maintain close monitoring to ensure the funding is utilised in a timely manner and extend the agreement with the World Bank to cover this period.

Assessment of partner organisation approaches to conflict sensitivity, and sharing lessons and good practice between partners, and reporting on conflict sensitivity, has been limited. Conflict sensitivity understanding among the FCDO programme team can also be strengthened.

Finance
There has been a level of funding uncertainty within the FSSN programme as a result of HMG annual spending reviews. The reduction in funding as a result of the drop to 0.3% GNI for FCDO has been communicated to partners for 26/27 but exact budgets are yet to be confirmed. This will likely require an update to partner proposals given that they were based on assumed higher levels of funding. There were delays in confirmation of budget for 24/25 that did not happen until March 2024, given FCDO budget uncertainty, impacting activity timeliness for some partners.

During the 2024/2025 fiscal year, FCDO spent £63,732,016, through five partners under the FSSN program. The initial budget for FSSN was up to £67 million but with underspend from partners over the course of the year budget was reallocated to other programmes in the YON portfolio. The table below sets out the agreements with each partner and amount disbursed in 2024/25. Funding disbursements are based on the disbursement schedule in the relevant agreement, alongside updated spend rates forecasting from partners. All payments are made in advance with a justification for this from each partner. Ahead of each disbursement a review is made of the spend under the previous disbursement and the budget forecast for each partner to ensure payments are not made in advance of need.

During the financial year the Yemen Kuwait Bank (YKB) was sanctioned by the US in January 2025 following an assessment of links with Ansarallah (Houthis). Given the potential impact on this blocking international transfers to YKB and subsequent liquidity issues partners who were utilising YKB were required to withdraw all funds which was limited to allocated amounts on a weekly basis. All FCDO funds were withdrawn by the end of the financial year. All partners continue to utilise multiple banks to reduce the risk of liquidity of one bank impacted delivery.

FCDO conducts regular financial meetings with partners to review spending patterns and identify potential risks to delays and underspending. This proactive engagement ensures timely interventions, promotes transparency, and supports the effective and efficient use of resources throughout the Programme cycle.

Partner	Agreement / Duration	Funding Arrangement	2024/2025 Funding Disbursed	Date of last narrative financial report	Date of last audited annual statement
WFP	27 May 2024 – 31 Mar 2025	Contribution Agreement	£27,776,000	May 2025	05/05/2025
SFD	17th Aug 2022 – 31st December 2026	Memorandum of Understanding	£17,090,503	May 2025	31/12/2024
BRIGHTLY Consortium	1st Apr 2023 - 31st Dec 2026	Accountable Grant	£17,302,669	May 2025	09/09/2024
CARE	1st Dec 2024 – 31st Jul 2025	Accountable Grant	£171,459	May 2025	09/09/2024
World Bank	1st Sep 2024 – 31st Mar 2025	Administration Arrangement[19]	£1,391,385	N/A	N/A
Technical Assistant Support	Under CMP BASIC Programme with Mott MacDonald	Contract	£56,547[20]	N/A	N/A
			£63,732,016
[19] The Administrative Arrangement is held by the Economic Resilience Team in YON but FSSN contributes funding as the Social Protection programme falls under the same Trust Fund.
[20] This funding does not come from the FSSN budget and is therefore not included in the total figure.

BRIGHTLY: BRIGHTLY inform FCDO of budget savings as a result of the changes in the FSAC cash rates in January 2025 however it became evident that these savings occurred in April 2024.
Ongoing delays in approvals from authorities are reported throughout the year but these do then not seem to be reflected in updated realistic work planning. However, in January BRIGHTLY proposed a condensing of UCT rounds with approval from FSAC to cover for those that had been delayed, to 16–17-day rounds. Forecasting over the period has not reflected discussions around risk and a low burn rate averaging 75% by January was of particular concern. BRIGHTLY overspent by around 3.5% in 24/25, this therefore impacts the 25/26 allocation and reflects ongoing challenges with budget management.

CARE-WRO: CARE achieved a burn rate of approximately 82% resulting in an underspend of around 18% of the allocated budget. CARE faced challenges in full utilizing the budget as initially planned linked to delays in implementation. This meant that underspend for 24/25 had to be reallocated to other partners outside of the Programme as they happened in the last quarter of the financial year. CARE improved upon the underspend originally forecast in 24/25 in the remaining quarter of the performance period.

SFD: SFD has shown improvements in financial management practices; however, there is still a need to ensure greater accuracy in their payment requests. SFD’s burn rate stands at 81%. The overall budget was reduced from £18 million to £17,090,503 following the detention of SFD staff in June, which triggered a temporary suspension of FCDO funding, due to disrupting field operations and pausing project activities. SFD maintains proactive oversight of potential budget reallocations, particularly in response to contextual challenges and beneficiary needs. They also actively respond to requests for clarifications or adjustments to support FCDO payment disbursement, helping to prevent delays in spending and activity implementation, however, many of these clarifications and adjustments could be avoided if SFD improved the accuracy of their payment requests.

WFP: FCDO’s funding to WFP was staged throughout the year, due to delays in confirmation of YON’s budget. This challenged WFP’s ability to plan cycles around donor funding. For 25/26 FCDO has been able to confirm its total budget by end of May 2025 which should support improved planning. All disbursements and fund utilisation has been in line with the agreement, with WFP able to absorb an uplift in funding in November 2024 of just over £3 million due to additional available funds from FCDO. Due to the framework arrangement with WFP, there is limited detail shared in the high level budget for FCDO funds, which restricts oversight. In late 2024 FCDO successfully helped advocate for Australian Aid to supplement FCDO cash funding for an additional round of CBT.

World Bank: The Administrative Arrangement is held by the Economic Resilience Team in YON but FSSN contributes funding as the Social Protection programme falls under the Yemen Resilience, Recovery and Reconstruction MDTF Trust Fund. This could risk a reduced level of engagement with the FSSN programme team from the World Bank but there has been a supported level of engagement with Bank colleagues to ensure FCDO is updated on progress to the development of the redesigned UCT programme by the World Bank with UNICEF and SFD.

G: MONITORING, EVIDENCE AND LEARNING
The FSSN Business Case envisaged a contract under the Programme to deliver a Technical Assistance Facility (TAF) which would provide support to delivery partners and FCDO on three areas:
1. Sector Strengthening: Deliver elements of the Cash and Social Protection Donor Working Group six priority areas and action plan and improve including coordination between FSSN partners
2. Building the evidence base: Ensure programme delivers against its long term vision through strengthening the evidence base for more cost efficient programming in future and improve cash reform throughout the Programme
3. Monitoring and Evaluation: Undertake a longitudinal evaluation of the Programme as well as ongoing monitoring of delivery to support adaptations to programming

Following programme approval FCDO existing centrally managed programmes (CMP) and YON TPM programme has been used to fulfil the majority of these activities to improve value for money and agility. This includes:
Sector Strengthening: Under the Better Assistance in Crises (BASIC) CMP a contract delivering the Social Protection Technical Assistance Advice and Resources Facility (STAAR) is established. In November 2024 STAAR commenced funding of a donor coordinator for cash and social protection programming role to support the FSSN programme and Yemen cash coordination sector (output 3.5). This role currently runs for nine months at which point STAAR of FSSN may continue funding depending on progress. So far this function has been welcomed by donors, implementers and WB alike. Of particular relevance is the exploration, led by the cash coordination team of an alignment and future merging of the Brightly programme with the CCY consortium in late FY 2024-25

In addition to sector coordination FSSN partner coordination can further support shared learning, pathway referrals and avoid duplication. Partners are encouraged to engage with each other over the course of the Programme and report on examples of where this has benefited delivery. FCDO also plays a role in supporting this cohesion through governance meetings which brings all partners together (in person where possible) over several days (see below for further details). Six governance meetings have taken place over the course of the Programme with the latest in February 2025 (see below). These governance meetings have varied in focus linked to the stage of the Programme and context. To support the remaining coordination between partners and programme strategy a terms of reference should be developed for governance of the Programme.

Building the evidence base: Also under the BASIC CMP the Institute of Development Studies (IDS) is undertaking research examining why, how and when to use social protection approaches in different crisis contexts to deliver more effective social assistance so that vulnerable people cope better with crises and meet their basic needs. One of the key themes for BASIC research is how to improve systems for design and delivery and Yemen is one of the four priority focus countries. FSSN works closely with the BASIC IDS research to align priorities for research, in line with evidence gaps identified in the FSSN Business Case. Research areas so far include the value for money of localisation, VSLA set ups and assessment of the capacity of local systems. This work continues to inform the WBs approach to the social protection/UCT redesign work leading to an information sharing event in late 2025 to be hosted by SFD. As the BASIC programme comes to an end in 2026 a priority is to support engagement with these research pieces from across the Yemen cash sector to inform programming and system adaptation.

Monitoring and Evaluation: FSSN draws on the YON third party monitoring contract under the Tahseen programme to monitor delivery across partners. In 24/25 four monitoring visits were conducted by Tahseen across BRIGHTLY, SFD and WFP (further details below on findings). The Tahseen programme came to an end in March 2025 and a new programme ‘MERLY’ was established and is currently in inception. MERLY will also deliver an outcome assessment for FSSN to assess evidence of the extent to which the Programme is delivering against the intended outcomes, and its contribution to these (as opposed to external factors). This assessment will support the analysis of the evidence base generated by FSSN to inform any successor programming in Yemen. MERLY could also be used to support partners in reviewing and strengthening their conflict sensitivity including analysis and monitoring.

Monitoring and Evaluation
FCDO has established a FSSN Monitoring and Evaluation (M&E) framework to align monitoring activities, oversee findings from TPM and track evidence gaps and new research. The Framework sets out the methods used to monitor partner results in line with the log frame, through quarterly and biannual reports, regular meetings and annual reporting. In November 2024 the FSSN Team undertook a review of the FSSN logframe to reflect recommendations from the 2024 Annual Review and learnings over the previous year (specific changes are noted in relevant output sections). The 2024/25 Annual Review is the first year that partner output and outcome reporting methodology is aligned, to be able to make aggregate results and targeting. Whilst this is challenging in some activities it has largely been possible.

Given that FCDO is not present in Yemen relationships with partners are crucial to understanding challenges and progress in programme delivery, especially given a rapidly evolving context. The FSSN Team meets with all partners on a monthly basis and utilises longer quarterly meetings to discuss quarterly reports and more strategic challenges. In the coming year it will be useful for rationalise some of these meetings to avoid duplication, for example there are currently three different monthly meetings with SFD that can be rationalised into one. Partner reporting occurs on a quarterly basis (for SFD, BRIGHTLY and CARE) and on a biannual basis for WFP, as per the framework agreement. These reports assess progress against logframe and meetings allow for FCDO to interrogate programme progress and assess adaptations as required. When possibly FCDO meets with partners in person but this is limited as many are (importantly) based on Yemen or outside of Amman. To deepen understanding and ensure contextual relevance, FCDO staff also travel to Yemen to visit partners directly. These field visits allow for a closer, more nuanced understanding of the on the ground situation, which enhances the overall effectiveness of monitoring activities.

Key FCDO TPM Findings and Recommendations for 24/25
With the new MERLY programme in YON a change to the approach of TPM will include a joint meeting with FCDO, the partner and the TPM to agree priorities to recommendations for partners. The following findings and recommendations are being taken forward by partners, with some resolved before the end of the performance year:

SFD
- Support engagement of female beneficiaries in cash for work and cash distribution through the engagement of female agents (as requested by beneficiaries).
- Issue clear guidelines to cash for work consultants on participant selection, including vulnerability criteria to be used in the event that there are more applicants than the CFW projects can accommodate.
BRIGHTLY
- Include children under five and lactating women as specific cohorts in analysis to track
- Assess conflict sensitivity or social cohesion issues that might arise as a negative perceptions of inclusion errors in targeting.
- Provide support for beneficiaries with disabilities to access cash distribution sites in a more consistent way.
WFP
- Explore ways to more actively inform beneficiaries of changes in targeting or reduction in assistance to avoid confusion and tensions with communities.
- Ensure financial service provider agents are dismissed if found to be retaining cash at outlets.

No TPM has been undertaken on the World Bank and CARE WRO as FCDO funding was not utilised by the World Bank in 24/25 and the CARE WRO activities commenced at the end of the Tahseen programme.
FSSN Annual Governance Meeting
In February 2025 FSSN held an annual governance meeting to bring all delivery partners together, encouraging coordination, identify synergies, support the longer term transition to a strengthened nationally owned system for social protection and for FCDO to update on priorities and direction. The meetings took place over two days in Amman, and experienced great engagement from the range of partners, including guest sessions run by FAO Syria and UNICEF. The meetings were also an opportunity for the donor cash coordinator and the new MERLY team to meet with delivery partners and build their understanding of challenges and opportunities going forward. / The agenda covered strategic partner updates, safeguarding and gender within FSSN, transition approaches, referral mechanisms and coordination, aid diversion risk management and aligning social protection and humanitarian programming in Yemen (presentation of research). / Part way through the meetings HMG announced a reduction in ODA to 0.3% of GNI from 26/27. The gathering of partners allowed for a strategic discussion and immediate questions on the potential impacts of this to the sector and the Programme. / Key next steps include: / WFP to reach out to all partners and donors to incorporate their inputs into WFP's strategic planning process for the next country strategic plan. / FSSN partners to improve data sharing in order to avoid the risk of duplication. / FCDO to follow up with UNCEF to get the final version on the SPSF after being endorsed by the government and DFA. / Partners urged to align programming with existing national social protection systems and laws. / FCDO and FSSN partners to explore opportunities for more systematic sharing of safeguarding lessons learned and good practices across the Yemen response. / Partners should consider ways to link participants to VSLA initiatives more systematically. / SFD and SCI to arrange a learning session on mobile money and e-wallets, and invite any other interested actors.

Partner Monitoring
BRIGHTLY: In 24/25 BRIGHTLY finalised its MEAL strategy to support ongoing assessment against the Theory of Change as well as measuring performance across the consortium. BRIGHTLY has run baseline surveys for cash for work and unconditional cash at the beginning of the delivery year to track the impact of activities on beneficiaries including food security and resilience. BRIGHTLY conducted its own monitoring visits observing cash distribution and livelihood activities. BRIGHTLY also conduct post distribution monitoring utilising a standard household questionnaire to assess the process and short-term impacts of activities to inform outcome level assessment of Food Consumption Scores and Coping Strategies Index. BRIGHTLY’s feedback and accountability mechanism received a total of 9076 complaints of which 98.8% being successfully resolved. BRIGHTLY has not shared analysis of themes from these complaints or changes to programming activities as a result.

SFD: SFD conducted 31 monitoring visits in the reporting period, two highlighted in reporting are to Taiz Governorate and to Hadramaut Governorate. The visits have confirmed reported results but SFD has not reported any subsequent amendments to activities or challenges found. In addition the safeguarding team conducted 113 field visits assessing the grievance redress mechanism run by SFD. SFD also conducted a social safeguards assessment was conducted through 14 field visits interviewing 96 female beneficiaries. Findings were generally positive focusing on engagement of women and PWDs with activities particularly cash for work. Given SFD’s long standing relationships with communities this is unsurprising but could also be reflective of SFD conducting its own surveys which challenges the independence of the assessment and increases likelihood of beneficiaries answering positively. A total of 2708 complaints were received through this mechanism with 86% having been resolved. The majority of complaints are focused on equity of targeting.

In some cases monitoring exercises were jointly conducted in coordination with SFD and the TPM, ensuring transparency and shared understanding. Both parties convened to review and discuss the findings, identify strengths and areas for improvement, and collaboratively develop key learnings and recommendations to enhance program performance.

WFP: WFP conduct monitoring visits through WFP TPM and run a community feedback and response mechanism. WFP has mapped out systematic issues reported through these mechanisms 63% of CRM calls were from beneficiaries not aware or entitlements or the time and place of distributions This suggests the CRM mechanism plays an important role in supporting access to WFP cash distribution. WFP reporting shares high level details of changes to the Programme as a result of monitoring including lower awareness of CRM amongst women leading to exploration of possibilities for direct community engagement through women’s groups but more detail on programme adaptions will be beneficial to include in future reports.

Learning
Monitoring over the course of the year and partner reflective learning has facilitated lessons and insights between partners and FCDO:
Mobile Money: Utilizing mobile money services has significantly benefited communities by reducing the need for physical travel to distribution sites, enhancing women’s financial inclusion by ensuring direct and secure access to funds through their own mobile wallets especially for underserved communities. Mobile money may also contribute to lowering the risk of aid diversion, ensuring that assistance reaches the intended beneficiaries especially in high-need areas with limited resources by following a systemized process managed by the financial service provider, which includes verifying official IDs, ensuring the accuracy of beneficiaries’ personal information, and maintaining transparent, auditable transaction records For example, SFD has integrated Mobile Money into programs such as CFW, CFN, VSLAs, and SMED. This was achieved through awareness campaigns, incentives, and partnerships with 11 e-wallet firms, as well as by hiring field influencers and consultants to support implementation at the community level.

Community engagement: Effective community engagement is crucial when transitioning from emergency response to recovery phases, and to avoid negatively impacting conflict dynamics. Inclusive and transparent participation fosters trust, ensures that community perspectives are integrated, and helps in setting clear criteria for graduation from aid programs. For example, during testing of its transition strategy, BRIGHTLY encountered resistance from communities and authorities regarding eligibility criteria. Through negotiations with community members, a modified approach was developed, underscoring the importance of transparent community engagement for successful implementation.

Need for (SOPs) in service mapping: The development and endorsement of Standard Operating Procedures (SOPs) for service mapping are essential for coordinated humanitarian response. The need became evident following the termination of the General Food Distribution program by the World Food Programme in the North. Clear SOPs, endorsed by all humanitarian clusters and partners can improve coordination, streamline referrals, and ensure continuity in such transitions. Stakeholders including UNICEF and the World Bank have a critical role to play in supporting the Government of Yemen to strengthen national social safety net systems and facilitate the development of SOPs in coordination with different humanitarian actors and service providers.

Enhancing safeguarding with cultural sensitivity: Communities respond more positively and effectively to safeguarding initiatives when the terminologies align with local culture values, particularly in conservative contexts. Collaborating with community elders and religious figures can facilitate acceptance and participation. Tailoring language and messaging to resonate with community norms enhances trust and encourages community led- safeguarding responses. BRIGHTLY’s safeguarding mapping exercise shows that communities would respond more positively to terminology that matches more conservative values and are developing new materials to adapt to this.

Managing administrative delays: The time required to secure clearance for activities often exceeds expectations, leading to delays in implementation. To mitigate this, establishing internal deadline systems for obtaining approvals is important. When deadlines are missed, having alternative plans pre-prepared, such as shifting projects to locations with fewer administrative constraints while ensuring that activities are still provided to the intended target group of beneficiaries will help maintain project momentum and responsiveness.

Recommendations for year ahead
1. Pursue a no cost business case amendment to support ability to fund the cash coordinator if required, as well as other discreet areas of work aligned with FSSN objectives
2. Review the ToR for FSSN governance meetings.
3. Work with BASIC Research to establish a dissemination and engagement with products across the sector.

Annex A – 24/25 Recommendations
	Recommendation	Timeline
Future Strategy
1	Prepare the FSSN portfolio and its strategic direction for a reduction resulting from 0.3% ODA by exploring and incentivising collaboration and alignment of existing and future programming with similar “humanitarian plus” approaches currently funded by other humanitarian and development donors with a particular focus on enhanced localisation.	Ongoing
2	FSSN to use the remaining fully funded FY 2025-26 to gather evidence to evolve the Programme methodologies of Cash Plus, into a better configured and cross Yemen context approach. This requires internal FCDO collaboration, and external partnerships on coordination, joint programming, and innovation.	March 2026
3	Further align FSSN strategic planning with FCDO ERT programmes to enhance knowledge on a blended humanitarian/development approach supporting enhance income generating opportunities to address food insecurity. Build in opportunities to pilot these interventions (fisheries, VSLA support, co-funding opportunities), to support beneficiaries to graduate from humanitarian need to productive activities. Gather evidence in the final year of the Programme, to inform future programming design.	Ongoing
4	Explore opportunities to maximise the future strategic influence of the cash coordinator in the Yemen Donor Humanitarian Cash and Social Protection working group and ensuring effective donor coordination and alignment in cash programming. The cash donor coordination function to specifically enable the alignment of BRIGHTLY and other non-FCDO funded cash plus programmes in Yemen and advise / maximise opportunities to link FCDO cash plus funding with the World Bank social protection re-design process to ensure an eventual transition from humanitarian to safety nets.	March 2026
5	Explore engagement with FCDO agricultural and climate experts to assess the impact of climate change on livelihoods and food security in Yemen, and how these may be driving conflict thus effecting the transition from humanitarian assistance to long-term resilience. Integrate these learnings to create a causal pathway and build evidence on the ways in which cash assistance interventions can better support these needs in the long term.	March 2026
6	Use the FSSN programme relationships (SFD, WFP), the new FCDO SDA from mid-2025, the Cash Donor Forum, and the FSSN World Bank support to more strategically link humanitarian programming with Shock Responsive and the more predictable UCT Social Protection re-design being led by the WB and UNICEF. Humanitarian allocations and the shape of our future humanitarian programming should be seen through the lens of an eventual transition towards a national SP system which replaces costly and less sustainable humanitarian approaches.	Ongoing but with clear decision required by WB in late 2025 for FCDO orientation for next FY
Gulf Partnerships
7	Explore and support closer alignment with the Saudi King Salmaan Relief organisation to jointly fund WFPs Targeted Emergency Food Assistance (TEFA) approach, complementing cash (FCDO) and in kind (KSA) approaches.	October 2025
8	Explore the opportunities to bring Gulf donors into the Cash space by targeted lobbying and use of evidence, building on opportunities such as KSRs interest in a joint funding initiative with WFP in late 2025.	Ongoing
Monitoring and Learning
9	Enhance collaboration and learning between partners using the MERLY programme. FCDO should take a leading role in facilitating regular knowledge-sharing workshops and ensure that lessons learned are actively used to inform operational decisions. Foster better complementarity between BRIGHTLY, WFP and SFD by leveraging SFD’s local knowledge and BRIGHTLY/WFP’s capacity to scale up development work.	March 2026
10	FCDO and partners to use recent IPC data and HRP estimates of need to assess the degree to which current FSSN partners’ targeting reflects the UN reprioritisation of effort to areas of IPC 4 and 5. If re-targeting is indicated, calculate (where possible) the positive impacts and benefits such re-targeting might bring, together with the opportunity cost of changing targeting criteria in the final full year of FSSN.	Second half of 2025
11	Use the proposed outcome evaluation to generate evidence and learning on which cash approaches, including amounts and modalities, are most effective at meeting needs and building sustainability, and establishing, if possible, what is the trade-off between the two?	Ongoing
12	Partners to establish improved two-way communication channels, enabling the collection of valuable feedback from VSLA members regarding capacity-building activities, effectiveness of training, areas for improvement, and the evolving needs of participants—ensuring that support remains responsive and community-driven.	Ongoing
13	Continue to work with partners to improve reporting against agreed value for money indicators for comparative analysis to inform funding decisions and programme adaptations.	December 2025
14	Continue work to improve accountability to affected populations by ensuring robust complaints and feedback mechanisms are in place and accessible to targeted communities. To strengthen the relevance and effectiveness of cash transfer programming, greater emphasis could be placed on integrating beneficiary feedback. This participatory approach helps deepen understanding of community needs and realities, while also contributing to a stronger evidence base for adaptive programming. Work with MERLY to enhance reporting on beneficiary engagement with these feedback mechanisms.	March 2026
Partner Management and Coordination
15	Review and support the BRIGHTLY consortium programme management unit to assess the effectiveness, adaptability and responsiveness of finance and governance mechanisms, support joint decision-making, learning, and rapid response to emerging needs.	March 2026
16	Explore possibilities for partners to leverage private sector funding to complement existing resources and create a more reliable funding base, with the aim of eventually transitioning FCDO’s focus on more sustainable economic development outcomes.	Ongoing
17	With banks increasingly moving to IRG areas, FCDO should ensure partners have an ongoing risk analysis and contingency plan to protect the flow of assistance to DFA areas, ensuring vulnerable populations are not left unsupported.	October 2025
18	Increase engagement with Women’s Rights Organisations (WROs) building on the current WRO pilot, to strengthen gender inclusion. Allocate new resources and support for partners to enhance their Gender Equality and Women’s Empowerment (GEWE) efforts.	Ongoing
19	Better understand each partner's approach to transfer value changes and if there are any opportunities for complementarity in these approaches. Partners sharing learnings on how they manage transfer value changes can help mitigate impact to beneficiaries and allow for more consistent reporting across the Programme. This is particularly relevant when considering how best to maximise the more sustainable outcomes from the “humanitarian plus” approach of using cash transfers as the foundation for improved livelihoods.	October 2025
20	FCDO should encourage and facilitate FSSN partners to work collectively to coordinate internally on referring beneficiaries across the portfolio between BRIGHTLY, SFD and WFP to ensure the best sustainable outcomes, making the geographical layering of cash transfers with livelihoods opportunities more effective and so reducing the numbers dependent on humanitarian assistance.	December 2025
21	Governance meetings with FCDO and programme partners have encouraged lesson learning and information sharing, however the workstreams generated from these discussions need to be followed up to ensure these learnings are applied at implementation level and synergies are taken advantage of where possible. The FCDO team will discuss with partners on the best way to take this forward, including potential check ins throughout the year or setting up working groups.	December 2025
Governance
22	Review the ToR for FSSN governance meetings to support partner coordination and shared learning.	October 2025
23	Pursue a no cost business case amendment to support ability to fund the cash coordinator if required, as well as other discreet areas of work aligned with FSSN objectives.	December 2025
24	Work with FCDO BASIC Research to establish a dissemination and engagement with products across the sector.	November 2025
Sector Coordination and Engagement
25	Use the year ahead to refine ideas for smaller cost but more catalytic and influential activities for example funding the Cash and Markets Working Group, the Cash Donor Coordination Forum, a BRIGHTLY/CCY alignment.	March 2026
26	FSSN should actively explore and enable an alignment between elements of its current programme with non-FCDO funded humanitarian and development programmes including the CCY Cash Consortium for Yemen, which has a very similar approach. CCY and BRIGHTLY partners, and importantly their main donors, FCDO, EU, and ECHO are all supportive of this.	March 2026
27	Donor investment in localisation: FCDO should engage more with local organisations to amplify the Yemeni voice and bring community level contextual insights to the forefront of programme decision making, risk management and shaping future programme design. Valuable learnings and insights gained from building local capacity should be systematically shared across donor working groups and implementing partners	Ongoing

Annex B – 23/24 Recommendations
	Recommendations	Action	Status
1	FCDO should consider setting minimum funding levels for each partner with additional funding linked to performance on driving improvements in the FSSN and wider humanitarian response.	This is not in line with the current FCDO annual finance allocations, where partner allocations are only confirmed year on year and additional funding is not available to allocate over the course of the year because certainty is needed on forecasting. When and if additional funding does become available this is allocated both on performance but also on ability to spend given the short-term nature of the allocations. For 25/26 there is consideration for maintaining a pot of funding to allocate to respond to emergency needs and in response to financial performance.	Closed
2	Logframe Recommendations i. FCDO should ensure that sufficient skilled resources are available to refine, gather and analyse outcome reporting. ii. FCDO should make logframe outcome milestones more ambitious and focused on the key programme aim of moving people out of the worst category of food insecurity. Given its increasing importance as the Programme matures. iii. FCDO should also increase the weighting of Output 3 (which assesses activities to deliver reform) in the logframe and widen its indicators to better capture the breadth of FSSN work.	Following the 23/24 annual review FCDO engaged with all partners to align reporting against outcomes to support FCDO analyse. / FCDO conducted a logframe review in October 2024 which included updates to milestone outcomes in line with sector standards. / Output three has three additional indicators to reflect additional activities including funding to the World Bank, the cash coordinator and the WRO/WLOs pilot. However, the weighting of output 3 was not increased given the relative funding amounts compared to other outputs. This should be reconsidered following this annual review.	Closed
3	All current FSSN partners show limited performance and prioritisation of gender and inclusion. FSSN is well set up to share best practice, and the planned addition of Women’s Rights Organisations should strengthen this. But FCDO should continue to press partners and use TPM partners to provide analysis and good practice, with support from the SDA. FCDO should support partners on strengthening gender and inclusion aspects of their Output 2 programming, particularly CFW.	SDA has analysed improvements on GESI in partners' reporting in Q2 and Q3 and followed up with best practice sharing through a session at the governance meeting in February 2025, particularly supporting women to participate in CFW. / Relevant logframe indicators are now disaggregated to support tracking of programme reach. / Deep dive on GESI in cash for work with SFD revealed more in-depth approach on GESI than previously known, including gender specialist working on CFW. / The Women’s Rights Organisation component under CARE commenced in December 2024, providing capacity building and funding to seven local WROs.	Ongoing
4	With the YON Economist (and team), FCDO should strengthen the VfM framework, based on learning from this year, with a focus on economy and efficiency, with exchange rates and cost transfer ratios as key metrics.	The VFM framework was established in 2024 and indicators were agreed with partners, including methodology to harmonise reporting across the five Es. This annual review has highlighted progress on this as well as areas of improvement.	Closed and replaced with AR 2025 19
5	FCDO should delay the due date for future AR by at least one month, to allow more effective dialogue and exchange with partners following their annual reporting.	This delay was approved by the Programme Board in September 2024.	Closed
6	FCDO and partners should continue to discuss synergies between FSSN partners and activities when working in the same locations. There is scope to pilot collaborations, for example handing over beneficiaries from WFP humanitarian to SFD resilience programming.	Consider how this can be part of the governance meeting in Feb. India and Will to discuss how this will be completed / LD this was an action point from the last governance meeting - SFD offered to host a meeting between all the partners to discuss. Brightly, SFD and WB are having discussion between themselves beyond the scope of FSSN. We need to keep up with these. The Governance meeting will be a good opportunity to endorse this approach.	Closed and replaced by AR 2025 22
7	FCDO will relaunch the recruitment of the donor cash coordinator and Humanitarian Cash and Social Protection donor coordination group.	Recruited through STAAR (a centrally managed facility) and the team commenced work in November 2024 with the phase one inception completed in Q4 24/25. See output three for further detail.	Closed
8	FCDO and partners should discuss whether it may be possible or appropriate to increase FSSN footprint in new or emerging severely food insecure areas. FCDO should consider the trade-off between efficiency and predictability, and flexibility towards new needs, particularly when authorisations have high transaction costs.	FSSN partners base their programming on greatest need (through IPC assessments, prioritising IPC 4 and 5), ability to access and operational deconflicting. FCDO continues to support partners in this process, including improved coordination and increasingly aligns additional funding to target areas with the greatest humanitarian need. In the past year BRIGHTLY’s crisis reserve has supported response to flooding impact in new geographical areas. The US FTO has challenged partners ability to deliver in areas DFA areas, although many have continued to do so.	Closed
9	FCDO should actively disseminate already completed research work to encourage learning and reform and prioritise developing evidence to support reform in the wider sector.	BASIC Research working on a dissemination plan to commence in Q3 of 24/25, this is replaced by recommendation 24 in this Annual Review	Closed and replaced with AR 2025 24
10	Partners should communicate any financial issues as promptly and clearly as possible. This includes over or underspends for the financial year, even if only minor.	Engagement over the course of 24/25 with all partners have set out FCDO’s accounting timelines and improved monitoring on partner burn rate. This led to reallocation of partner funding in Q4 where there was ongoing underspend at high risk. Partners continue to be encouraged to continue with transparency and realistic forecasting to support management across the year.	Closed
11	Partners should maintain and strengthen contingency plans for potential access/interference scenarios, including in case of disruption of Bank operations.	The US FTO has brought many banking and access risks to reality. Partners have worked on varying scenarios, with FCDO supporting information sharing and risk management. More detail on this is set out in the risk section.	Closed and replaced by AR 17
12	Partners should report exchange rates, at least on a quarterly basis. FCDO should compare and investigate instances of abnormal rates and facilitate practice exchange.	Partners report on an ad hoc basis, and at a minimum quarterly, exchange rate gains and losses. Actual exchange rates vary day to day, particularly in IRG areas, but partners use controls to agree with FSPs during payment rounds. FCDO continues to assess partner delivery chains to beneficiary level with corresponding risk management to oversee exposure and mitigate accordingly.	Closed
13	Partners should provide comparable VfM data (e.g. cost to transfer ratio data, FSP rates). FCDO should incentivise the provision of this information, through annual budget allocations if necessary.	See recommendation 4.	Closed and replaced with AR 2025 11 and 19
14	Partners should provide or consistently ensure sex, age and disability disaggregated data (SADDD) as well as disaggregating IDPs and Muhamasheen as marginalised groups, as a first step towards better analysis of the gender and inclusion aspects of SFD programming.	Through engagement with partners, FCDO has agreed priority indicators for disaggregated data to inform areas for greater prioritisation. This delivered greater disaggregation on sex and IDPs during this reporting cycle. There are still gaps on PwD reach and reporting which FCDO continues to be worked on with partners.	Ongoing – still require PwDs data
15	Partners should ensure they are sharing lesson learning across all FSSN partners, including in innovative areas like mobile money.	Several coordination opportunities over the past year have supported lesson learning between partners including the FSSN partner meetings in February 2025. A lesson learning approach is to be reflected in the updated FSSN programme MEL strategy. The logframe also encourages shared coordination and lesson learning under indicator 3.4, in addition to existing structures including the FSAC and CMWG.	Closed and replaced by AR 2025 19,20,21 and 22
16	FCDO should continue to review with SFD the Cash for Nutrition approach, particularly the added nutritional value of extending the age range beyond 24 months/1000 days. Benefits should be prioritised during pregnancy and up to age 2 (instead of 5 currently) which have by far the largest impact on malnutrition.	FCDO has agreed with SFD’s approach but are awaiting a clear rationale is included in the Social Health Protection strategy.	Ongoing
17	SFD should review targeting of their Cash for Work activities following Tahseen indications that many beneficiaries were not from among the most vulnerable.	SFD noted this finding as in line with prior findings in June 2023. However, they have requested further details to better understand the effectiveness of the CfW targeting strategy, given other indicators suggest households targeted are in need of the cash assistance, including the high reported share of cash assistance spent on food, and food security indicators at community level displaying acute needs. Tahseen are to produce a one pager setting out targeting issues and disaggregated findings. As the Tahseen contract has completed the new TPM contract, once commenced should further investigated and assess this finding.	Ongoing
18	FCDO should carefully monitor SFD financial forecasting and ensure promised improvements in accuracy are realised.	Further work has been ongoing with SFD over the review period with some improvements in number of errors. Monthly reporting is very useful and enables a clear understanding of spend for SFD and FCDO. However, there are often mistakes, FCDO encourages SFD to quality assure reports before sending to FCDO.	Closed
19	WFP needs to provide more information as to why no fraud or safeguarding reporting was received by FCDO during the period in review and resolve the issue as soon as possible.	FCDO has reiterated the requirements in the framework arrangement between FCDO and WFP that require reporting of any fraud and safeguarding cases that warrant an investigation. WFP has improved its reporting over the past year, but efforts are ongoing on maintaining this.	Closed
20	FCDO should monitor WFP performance (and consider funding levels) with regard to: a. Implementation of WFP’s retargeting. b. Resolution of the WFP pause in northern Yemen and its focus on Southern urban areas. c. Provision by WFP of sufficient financial data to allow value for money analysis.	WFP’s retargeting process commenced in the review period and is due to be completed by March 2026. This is WFP’s first exercise since 2018 and is crucial to ensuring the most vulnerable are targeted for assistance at a time when resources are depleting. The retargeting exercise is working through community committees and engaging with authorities to reduce challenges. / WFP resumed food distribution in the North, FCDO contributions continue to be for cash in the South. / WFP has agreed to report against FSSN VFM indicators annually, although these were not included in the annual report data was provided in follow up.	Closed
21	WFP should complete their VfM analysis of in-kind vs cash in Yemen; FCDO should coordinate and lobby other donors, particularly Gulf donors on the benefits of cash programming or at least providing resources for a full food package; and WFP should look at instituting hybrid in-kind and cash transfers.	WFP’s VFM analysis was shared in February 2025 with FCDO, ongoing engagement with Gulf donors to set out this evidence. In February 2025 the FCDO funded cash donor coordinator has commenced through the cash donor coordination forum to support key approaches on key.	Ongoing
22	WFP should also increase cash transfer values, ensuring better alignment with in-kind assistance. WFP is unintentionally undermining acceptance of cash in Yemen by providing a lower value of cash transfers compared to in-kind aid. This should be rectified as soon as possible even if through reducing caseload, and through more regular updating of transfer values (aligning closer to in-kind packages).	During the review period WFP increased the transfer value from 11,500 YER to 17,500 YER per person, in cycle 5 and 6 of 22024, to better align with the in-kind assistance. This now means as a % of the MFB WFP is equating to 62% across 2024 given that there were six cycles. There is an ongoing trade off between reaching the most people vs an adequate transfer value to meet basic food needs. WFP continue to review this within a landscape of reduction in funding.	Closed
23	BRIGHTLY should consider reducing cash transfer values (to 50% of the minimum food basket) either initially or for those remaining on cash transfers after 6 months, while continuing to closely monitor the impact on food security outcomes. Coverage can then be expanded.	FSAC guidance is now that UCT should cover 80% of MFB. For the review period BRIGHTLY’s value amounts were: / i. UCT DFA: 58,000 YER per month equating to 89% of the MFB. / ii. UCT IRG: 140,000 YER per month equating to 106% of the MFB. / Given the graduation to livelihoods approach and BRIGHTLY’s market assessments the value amount remains a BRIGHTLY decision.	Closed
24	BRIGHTLY should propose clear parameters for when, where and how shorter-term transfers for emergencies may be triggered (e.g. for new IDPs).	BRIGHTLY has developed a Crisis Modifier Activation Request, which outlines detailed activation processes for various emergency scenarios in Yemen, including droughts, cyclones, earthquakes, floods, coastal floods, tsunamis, epidemics, and armed conflict/IDP influxes. This document includes clear parameters and step-by-step procedures for triggering short-term cash transfers during emergencies to ensure timely and effective responses. The activation process has been designed to address specific triggers and is aligned with the program's objectives to support vulnerable populations during crises.	Closed
25	BRIGHTLY should provide remaining inception details as soon as possible, including: Theory of Change, Localisation approach, Monitoring, Evaluation and Learning approach, and the graduation approach that remains unclear (especially: plans for beneficiaries who continue to meet vulnerability criteria after 12 months of cash transfers; approach to assessing beneficiaries to move onto livelihoods programming; and plans to assess whether livelihoods programming has reduced the vulnerability of beneficiaries and what action would be taken if beneficiaries continue to meet vulnerability criteria).	All inception documents have now been received and approved.	Closed
26	BRIGHTLY should ensure and commit to FCDO that the sustainable impact on household incomes of livelihoods activities will be assessed and evidenced, including for periods after the end of the intervention, and full reporting provided to FCDO.	The BRIGHTLY MERL strategy sets out the qualitative and quantitative monitoring of impact. This will also be supported by the FCDO evaluation of the FSSN programme.	Closed
27	BRIGHTLY needs to improve coordination and management within the consortium. It should significantly improve its financial management and forecasting to properly manage the consortium's budget and spending. Alongside, it should plan more realistically to deal with challenges that could cause uncertainty in delivery schedules.	There has been an improvement in BRIGHTLY’s management over the course of the year with improved financial tracking, although underspend and reporting continued to be an issue with funding having to be reallocated in Q4 from BRIGHTLY to other partners as a result of a low burn rate and FCDO judged unrealistic forecasting. Continued efforts on improving coordination between the PMU and FCDO are ongoing including a document setting out financial reporting expectations and BRIGHTLY updating its governance structure (assessing number of TWGs).	Ongoing
28	For recurrent and predictable underspends due to the continued depreciation of the Yemeni Riyal (YER), BRIGHTLY should propose a more systematic approach, which could include more regular updates of YER transfer value; review points and budget reallocations at 6th and 9th months of the year; clear parameters on effective uses of underspends in the second half of the year.	BRIGHTLY has implemented a more cohesive approach to address recurrent underspends caused by YER depreciation. The measures include reviewing transfer values in line with FSAC guidance, quarterly budget reviews with partners, regular exchange rate analysis, and working with FCDO to align priorities for underspend reallocation.	Closed replaced by AR 2025 15