## Annual Review Template

Title: Community-Led, Responsive, and Effective Urban Health Systems – CHORUS
Programme Value £ (full life): £7,972,870		Review date: August 2025
Programme Code: 301132	AMP start date: 18/03/2020	AMP end date: 30/04/2026

Summary of Programme Performance
Year	2021	2022	2023	2024	2025
Overall Output Score	A	A	A	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	N/A
DevTracker Link to results framework:

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

CHORUS (Community-led Responsive and Effective Urban Health Systems) is a research consortium bringing together partners from Africa (Ghana and Nigeria), South Asia (Nepal and Bangladesh), and the UK (Universities of Leeds and York, and the London School of Hygiene and Tropical Medicine). Its core aim is to improve the health of the poorest urban residents in low and middle-income countries by reducing health inequities and building sustainable capacity in health systems implementation research.

CHORUS operates through four research pillars:
1. linking different health providers
2. fostering multi-sectoral collaboration
3. Responding to the double burden of communicable and non-communicable diseases, and
4. directly engaging with the urban poor.
These pillars are supported by capacity building, research uptake, strong programme management and governance. Each country has two major projects, with activities co-designed and implemented in partnership with communities, health professionals, and city-level decision-makers.

The two overarching aims of CHORUS are:
1. The co-production of gender-responsive, pro-poor interventions that are designed, implemented, evaluated and used in policy and practice (outputs 1 & 2)
2. The development of capacity to conduct and administer high quality health system research (outputs 3 & 4).
This review covers the fourth full year of implementation, and the fifth year of the programme and was conducted through a review of CHORUS progress reports and partner meetings, augmented by a programme visit to Bangladesh by the FCDO programme team. FCDO procured a mid-term evaluation (MTE) of each of its seven Research Programme Consortia (RPCs), the findings of the CHORUS evaluation augmented this annual review.
Mid-Term Evaluation of FCDO RPCs
In 2024, FCDO commissioned Tropical Health to undertake a mid-term evaluation of the seven programmes which make up the RPC portfolio, alongside an assessment of the model overall.

The MTE included the evaluation of the CHORUS programme, using a mixed methods approach to assess findings against the judgement criteria established for each Evaluation Question (EQ) from various data analysis methods. The time period of assessment was from 2020 to mid-February 2025.

The evaluation assessed the effectiveness and relevance of their approach against the theory of change, and the quality of the research produced. It included five EQs, looking at: the relevance of CHORUS’ research to policy; the extent intended outputs are on being delivered and are on track to contribute to outcomes; the extent CHORUS are efficient in using available resources and building an equitable partnership; the sustainability of the consortium; and the extent value for money is being delivered. Some findings from the draft report have been included throughout this annual review.

The inception report and the final report will be published upon completion.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

This year, CHORUS has exceeded or met its intended milestones, resulting in an overall score of A+. This demonstrates the considerable progress made in driving forward all eight of its research projects moving towards results becoming available, without losing its focus on capacity building and research uptake. CHORUS exceeded targets in its most important output, the design, implementation and evaluation of gender-responsive pro-poor interventions (Output 2.1) and in disseminating co-produced research to key stakeholders (Output 1). CHORUS made significant progress on producing journal articles (Output 3), which was highlighted last year as an area for CHORUS to prioritise. CHORUS met all other milestones as detailed further in Section C. Examples of key results achieved this year are below with a full list found at Annex 1:
- In Nepal, HERDi’s research and influencing resulted in improved linkages and referral processes within the Pokhara Metropolitan City health service, specifically with pharmacies into the wider infrastructure, to strengthen noncommunicable disease (NCD) management and care for the urban poor who often rely on pharmacies for accessing health services.
- In Bangladesh, the ARK Foundation’s research has increased the numbers of individuals in urban contexts being diagnosed with NCDs which should support improved treatment and management. They achieved this by improving the collection and reporting of comprehensive urban health data, which integrating this into DHIS2, including data on third gender and diabetes, through adapting the Simple App, which had previously only been used in rural settings.
- The Nigeria team are improving health services available to the urban poor in Enugu as a result of influencing the Enugu Ministry of Health to establish an Urban Health Desk with designated budget, responsible for strengthening governance and coordinating the linkages between informal providers and the formal healthcare system.
- Already delivering on a core objective of building the evidence base around improving health of the urban poor, the CHORUS programme has to date published 19 journal articles and had a further five accepted, including a scoping review of the extent to which informal healthcare providers in slums are linked to the formal health system in Sub-Saharan Africa.

CHORUS has made substantial progress in its main year of delivery, alongside engaging effectively in the MTE, including sharing substantial quantities of documentation with the MTE partner and joining several KPIs, group discussions and workshops to input information and discuss findings. The MTE concluded that ‘CHORUS’s embedded implementation research approach has ensured high contextual relevance and meaningful stakeholder participation. This has positioned the programme well within the urban health systems and stakeholder networks, increasing the likelihood that research findings will be used in policy and practice’.

Major lessons and recommendations for the year ahead [1/2 page]

The MTE provided an important opportunity to reflect on the progress made and lessons learned by the CHORUS programme for both FCDO and the consortium and to plan and prioritise activities for the final full year.

The main lessons learned this year include:
- Flexibility within project plans has been vital particularly given rapid and unexpected contextual changes for example political upheaval in Bangladesh and elections in Ghana.
- Stakeholder engagement and research uptake: the embedded approach CHORUS has taken to its research, distinct to each country, including embedded staff in government structures and government staff as Innovation Fund (IF) holders, has proved vital in ensuring projects respond to local needs and have a stronger likelihood of uptake. Research uptake requires continued engagement with system stakeholders, including technical support to help them to understand, synthesize and utilise data and evidence.
- Capacity strengthening: Small projects led by early career researchers can have large impacts, although mentors need to be clear on responsibilities and adequately engage early career researchers to optimise these relationships. The high volume of papers has placed a heavy workload on already stretched early career researchers meaning that CHORUS may have fewer high impact academic papers being published.
Future Recommendations
The MTE provided ten recommendations for CHORUS to implement to maximise chances of success, which are listed in Annex 1, alongside FCDO’s response. The conclusions and recommendations have been discussed by CHORUS and FCDO as part of the evaluation process and provide a basis for this annual review’s recommendations:

1. CHORUS to develop and implement a prioritised implementation timeline for the final year of the programme and continue to closely monitor and manage timescales in Year 6 – August 2025 - CHORUS have already moved forward with developing this and are now in the process of implementation.
2. CHORUS to prioritise protected time for data analysis and publication writing and submission – Ongoing – CHORUS have already held and are planning more analysis and writing workshops.
3. CHORUS to complement quantitative outcome reporting with detailed qualitative case studies describing the policy changes that have occurred and CHORUS’s contribution to these – Final programme report – CHORUS already developed videos and effective at qualitatively explaining progress, however this will be especially important in the final report.
4. CHORUS to develop a How-to-guide for its embedded research approach – end of programme – CHORUS and FCDO agreed that learnings will be incorporated into existing publications and will develop a standalone paper if time.
5. FCDO and CHORUS to finalise contract amendment 4 to reflect necessary and previously agreed budget realignment – Dec 2025.
We will work with CHORUS to prioritise the recommendations against the remaining period of the programme, completing in April 2026.

Progress against recommendations from last year:
2024 Recommendation	Progress
CHORUS to closely monitor and manage timescales in Year 5. Project 1s must be supported to complete implementation and move towards analysis. Project 2s must be supported to move to implementation. CHORUS must be proactive to ensure that progress continues in line with projected timescales. Ongoing	On track – CHORUS has prioritised dedicated time to come together and focus on intensive work, arranged data analysis workshops and reviewed project timelines at regular project meetings and follow up actions closely tracked.
CHORUS to continue efforts to meet milestones for publications, anticipating the extra demand in supporting early career researchers. Ongoing	On track – CHORUS has started a publication ‘buddy’ scheme to support early career researchers, held writing workshops, prioritised manuscript progress in meeting agendas and scheduled dedicated writing time. As such, CHORUS now has 19 papers published, 5 accepted and a further 20 submitted to journals.
CHORUS to ensure forecasting practices are improved to meet expected deadlines and the minimum target of 10% variance. By Q3 2024/25	Forecasting exceeded the 10% variance throughout Q1-3, however improved in Q4, bringing the overall variance down to 6.8% underspend and within the minimum target of 10% variance.
CHORUS to ensure that recommendations following the mid-term evaluation, likely to take place in Year 5, are acknowledged and acted upon. By end 2025.	CHORUS and FCDO joined several meetings with the MTE partner to discuss recommendations and have already agreed those to prioritise (which are reflected in the recommendations for this annual review). CHORUS has already acted upon several of the MTE recommendations.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

CHORUS developed a Theory of Change (ToC) during its inception period, which remains valid to the research implementation. The MTE concluded that the CHORUS ToC remains appropriate, viable and relevant with a coherent causal pathway and is underpinned by clearly articulated assumptions. The MTE found that a strength of the ToC is in its integrated structure, whereby activities are not separated into discrete pathways of change; instead all activities are represented as contributing collectively to outputs, which then contribute to a single outcome. This highlights the interconnections between activities and expected results, however, presents a challenge in validating the contribution of specific pathways to the overall outcome.

No changes to the ToC have been made since the previous revisions in November 2023, outlined in the diagram below in red, which were documented in the 2024 annual review.

CHORUS continues to aim to influence urban health systems policy and practice to better meet the needs of the urban poor: improving health and reducing poverty, contributing to SDGs 1,3,6, and 11. Highlighted in yellow, some activities and outputs have experienced delays over the programme, influenced by external events such as elections and climate change impacts. Where contextual factors have caused delays, mitigations have been undertaken and the overall programme remains on track. Such risks are factored into the ToC pre-emptively, and mitigations continue to evolve throughout the programme’s development.

The CHORUS research cycle has five stages:
1. Needs assessment and solution generation by communities.
2. Analysis of data, literature, politics, economics and environment.
3. Co-creation of health system interventions.
4. Implementation research – including barriers and reach.
5. Evaluation of effectiveness and impact.
Capacity development by CHORUS is through two stages:
1. Capacity assessments – to develop a deeper understanding of the assets and needs of communities and healthcare providers
2. Capacity strengthening – to enhance the skills of partner teams to deliver research and have a sustainable impact.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

The programme outcome is:
Enhanced relationships and capability to generate and use high quality research evidence to inform and influence multisectoral health system interventions, policy and programme decisions and implementation at local, national, and international levels to improve the health of the urban poor and slum dwellers.
The outcome is measured by two outcome indicators:
1. Policy and programme decision making at national or local level influenced by research of CHORUS members driven by population needs (assessed using case studies).
2. Changes to urban health systems attributed to CHORUS findings and engagement (international, national, or local level) (assessed using case studies).
In the fifth year of the programme, progress slightly exceeded the expected milestone for the first outcome indicator. At this stage it was expected that policy and programme decisions at country level would be influenced sixteen times, whilst current progress has seen seventeen instances influenced by CHORUS research. For example, one of the Nigerian projects influenced a sub-national government to identify strategies to include traditional birth attendants in its referral system in their annual operational plan. In Nepal, continued engagement with Pokhara Metropolitan City has led to three million Nepalese rupee being allocated in municipality funding for noncommunicable disease (NCD) screening in the annual workplan and budget, which could lead to more diagnoses and therefore improved management of these diseases for urban poor. Additionally, CHORUS members contributed to the WHO Urban Health Capacities Assessment and Response resource kit, using CHORUS lessons to review and inform content. This resource profiles capacities at individual, organizational and systemic levels and their role in achieving urban health goals across sectors and the capacity assessment aspect helps multisectoral teams understand to what extent they possess these capacities, what this means for achieving their urban health goals and how to respond. This resource will help health systems in workforce and resource planning to meet the health needs of the urban poor.

Progress met the expected milestone for the second outcome indicator with four changes to urban health systems attributed to CHORUS findings and engagement. In both Nepal and Nigeria, CHORUS findings and engagement has led to the establishment of Urban Desks within government ministries of health with the aim of driving policy towards, and securing resource and budget for, achieving the health goals of the urban poor by government. In Bangladesh, CHORUS findings led to the integration of the NCD National Protocol on the Management of Hypertension and Diabetes training within healthcare providers’ capacity strengthening activities.

The full list of influences and changes at outcome level influenced by CHORUS can be found at Annex 1.

The programme is expected to contribute to the impact:
Improved health (SGD 3,6) and reduced poverty (SDG 1) in urban communities (SDG 11) through improved and responsive health systems.
CHORUS has developed two impact indicators:
- Use of primary care services at city level (% of the urban population accessing formal primary health care).
- Catastrophic costs of health care of the urban/slum population (% of population spending more than 10% of their total income on healthcare).

CHORUS has established baseline figures for each country and both indicators, which is an important step that required considerable time and effort to achieve. Due to the periodic frequency of national surveys and the availability of data, which are beyond the control of the CHORUS programme, providing full sets of mid-point and endline data will not be possible within the CHORUS programme duration. CHORUS Project 1 evaluations will provide data on the reach of the designed interventions to low-income populations disaggregated by gender and age. Based-on this data they will be able to model the reach of the intervention if scale-up is achieved as planned. The findings of this modelling will provide valuable information on the expected impact of CHORUS interventions on the health outcomes of the urban slum populations and urban poor in the cities where it is currently working, as well as urban areas across each country. CHORUS plans to share the information with policy makers and partners to demonstrate the potential benefits of investing in scale-up of the health system interventions developed and tested by CHORUS.

The MTE concluded that CHORUS is ‘on track to contribute to its intended outcomes, having informed national and sub-national policies on urban health governance, NCD management, and multi-sectoral collaboration’.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The programme has scored an A+ having met or exceeded most of its outputs in its fifth year. This year, the programme has exceeded or met expected outcome milestones, as demonstrated by the influence of CHORUS research on urban health policy and programme decision making, and the MTE concluded it is on track to contribute to its intended outcome targets. It may however face challenges in achieving all its publication targets, which is common in research programme timescales.

The CHORUS programme remains highly relevant and needed. There remain critical research gaps in urban health, particularly in poor communities and for women and girls, and the work being implemented by CHORUS should make a direct contribution towards FCDO’s approach to global health. Furthermore, CHORUS focuses on working in partnership and collaboration with organisations in the Global South. Now in its final full year of implementation and given its ongoing successes and outputs to date, it is clear and justified that CHORUS should continue.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Research co-produced and effectively disseminated to research users
Output number:		1	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Engagement (individual, workshops etc) of stakeholders in agenda setting, collaborative research and co-production of interventions and other CHORUS activities: i) number of stakeholder workshops and meetings; ii) types of stakeholder (e.g. unique stakeholders involved in each project in each country including community, NGO, types of provider, local, national government, academic by country)	50 / 30	Exceeded / 67 / 68
Number of research uptake products produced and made publicly available. Includes: Policy briefs, policy blogs/vlogs, podcasts, media articles, policy recommendations, guidelines and other RU products	70	Exceeded / 92
Participation of CHORUS team members in events and outputs on global urban health at: i) ALL regional and national; and ii) ALL global level; iii) South partners in regional and national; iv) South partners at global level	20 / 30 / 18 / 24	Exceeded / 32 / 32 / 32 / 26
Number of communication products disaggregated by: i) number of website hits; ii) number of unique users of website; iii) views of website outputs; iv) proportion of website hits from LMICs	10,000 / 2,500 / 2,000 / 55%	Exceeded / 12,487 / 3,934 / 3,894 / 59%

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Output 1 has exceeded all expectations. Since the last Annual Review, each indicator saw an increase in target milestones to reflect CHORUS’ strong performance and CHORUS exceeded the new increased milestones. As the programme moves towards completion, the publication and dissemination of outputs and outcomes grows in importance to ensure that maximum impact can be achieved. The performance across each indicator reflects the strong position CHORUS is in to deliver impact. Output 1 has scored an A+.

Output 1.1
For each sub-indicator milestones were exceeded, with CHORUS hosting 67 stakeholder workshops and meetings, with 68 different types of stakeholders. Of the 67 stakeholder engagement activities, 15 were through Innovation Fund projects. CHORUS notes a strong range of stakeholders across the public sector who were engaged, as well as third sector groups. Key examples include:
- Improved coordination between the Ministry of Health and Family Welfare (MoHFW) and the Ministry of Local Government in Bangladesh, which supported the training over 200 health professionals in Dhaka.
- As part of Nepal project 2, engagement by Pokhara Metropolitan City with the local government in the Budhanilkantha municipality, Kathmandu, has led to extra funding for the Urban Health Data Hub, which will collect multi-sectoral data.
CHORUS has maintained their strong stakeholder engagement this year, which has supported outcomes and the overall progress of the research and should have positive impacts on research uptake into practise.

Output 1.2
CHORUS has produced 92 research uptake products to date exceeding the cumulative target of 70 by the end of Year 5, with 34 outputs produced this reporting year. Thirty of the 34 produced this year were LMIC partner led, rather than centrally led, 64% led by female researchers and 58% were led by early career researchers demonstrating CHORUS’ commitment to greater localisation, capacity strengthening and equity. The cross-CHORUS Research Uptake Team have made good progress this year by successfully operationalising the CHORUS Research Uptake Strategy. Examples of outputs produced this year include: a web article published with Policy Leeds, a University of Leeds unit which builds relationships between policy professionals and researchers to inform public policy development, on how, through working with communities, we can address issues relating to the plurality of healthcare providers (i.e. a mix of state and non-state providers) in urban settings; a news article published in a Bangladeshi outlet, so likely to lead to policy impact there, on 'The role of youth in the fight against Air Pollution' in Bangladesh; and a video on the critical role of pharmacies as the first point of contact for urban residents.

Indicator 1.3
All sub-indicator targets were exceeded this year with all attendees at regional and national events from LMIC-based partner organisations, and 26 of the 32 attendees at global level events. This highlights CHORUS’ impressive networks and engagement with partners and focus on capacity strengthening and equity of opportunities. CHORUS had strong attendance at the 8th Symposium on Health Systems Research in Japan in November 2024, including several presentations and posters of CHORUS research and a side meeting for attendees working in research, policy and practice in urban health systems, with the aim to increase CHORUS’ network for synergising research, advocacy and collaboration. LMIC-based CHORUS partners participated in several national, regional and global meetings and events. For example, the Nepal PI selected by the Ministry of Health and Population to join the Nepali delegation to the World Health Assembly (WHA78) in May 2025 and the ARK Foundation PI was selected to serve on the Bangladesh Interim Government’s Task Force on 'Re-Strategising the Economy and Mobilizing Resources for Equitable and Sustainable Development'.

In January 2025, the FCDO programme team attended CHORUS’ annual partners meeting, hosted in Bangladesh. As a part of this, FCDO and CHORUS representatives sat on a panel during a policy dialogue event which focused on strengthening urban health systems through private-public partnerships, attended by officials from the Ministry of Health, Ministry of Finance, and Local Government, and receiving media attention. For the event, a briefing was produced to detail findings from each partner country. Other key events attended in 2024/25 included:
1. International Conference on Urban Health: CHORUS presented on topics such as equitable urban primary healthcare.
2. European Congress on Tropical Medicine and International Health
Output 1.4
CHORUS has exceeded targets for all sub-indicators except one for the interactions with their communication outputs. Number of website hits has increased substantially since last year as well as unique users and views of website outputs. This could be because of the new CHORUS website, which was developed this year to improve navigation and functionality. According to CHORUS reporting, a disproportionate number of website hits are from HICs with only 42% from LMICs against a 55% target, despite the research being focused in LMICs. CHORUS explained that this was due to increased engagements in the USA and the Netherlands following global events and networks built with researchers in these countries. However, when factoring in website hits for CHORUS pages and outputs on Herdi (Nepal), ARK Foundation (Bangladesh), and HPRG (Health Policy Research Group, Nigeria) websites, the total number of hits was 20,945 and 59% of users were from LMICs.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Changes to the logframe were discussed during the annual partners meeting in Bangladesh and finalised later. For indicator 1.1, the number of stakeholder workshops and meetings (i) increased from 30 to 50, and (ii) increased from 25 to 30. For indicator 1.2, the milestone of uptake products produced increased from 45 to 70. For indicator 1.3, milestones increased by 18 to 20 for (i), 15 to 30 for (ii), and 13 o 24 for (iv). For indicator 1.4, the milestone for (iii) doubled from 1,000 to 2,000. CHORUS exceeded each increased milestone. Following this review, final output milestones will be reviewed to maintain ambition in the final year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Progress on previous recommendations:
- CHORUS should again review the expected milestones for Year 5 to reflect current high performance and ensure that targets are sufficiently ambitious. End 2024 – completed and approved by FCDO.
- CHORUS should continue to focus on capturing outputs and engagements, developing the draft case studies and making them publicly available. Ongoing – CHORUS has made good progress on this and will continue in the final year.
- CHORUS to redesign its website to improve functionality and navigation. End 2024 – Completed.
CHORUS has steadily progressed in the reporting period, increasing engagement, uptake and communication products, and event attendance. At this stage, the programme is expected to pivot towards engagement due to having a greater body of research. Improvements compared to the previous year on each of the output indicators demonstrate that work is being done to improve research uptake to have a greater influence over policy in line with the theory of change.

CHORUS to prioritise research uptake activities and producing products to deliver strong outcomes and subsequent impact, in line with the theory of change – Review progress Dec 2025.

Output Title	Gender-responsive pro-poor interventions designed, implemented and evaluated
Output number:		2	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of gender responsive pro-poor and pro urban slum projects: / i) designed; ii) implemented; iii) with evaluated interventions	i) 8 / ii) 5 / iii) 3	Exceeded / i) 8 / ii) 8 / iii) 4
2.2 Number of projects funded from the CHORUS Central Innovation Fund based on criteria (led by early career researchers, based in LMICs, cross-country)	17	Met 1 year early / 17
2.3 i) Of the people consulted during the needs assessment and co-creation phase of the large projects: i) % that are women; ii) % that have partner defined characteristics (e.g. disabled, LGBTQi, vulnerable ethnic group); iii) Of the population covered by interventions %/# classified as living in urban informal / slum settlements	i) 45% / ii) 35% / iii) 74%	Met / i) 45% / ii) 35% / iii) 74%

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

CHORUS has exceeded or met expectations for output 2, exceeding targets in arguably the most important indicator of the programme. At this stage in the final year of research, Output Indicator 2.1 is of particular significance. By advancing the remaining research projects beyond the expected milestone, the likelihood of strong outcomes and completing the research on time increases. In addition, CHORUS awarded all 17 Innovation fund projects one year ahead of schedule. As such, Output 2 has scored A+.

Output 2.1
CHORUS exceeded this output and has now initiated all eight of their projects, with two in each country. This is a significant step in ensuring progress remains on track in the run up to programme completion. All project 1s (one in each of the four countries) are at implementation and evaluation stages, whilst project 2s have initiated data collection. By the end of year 5, Ghana project 2 entered the second and final phase of data collection; Bangladesh project 2 completed most data collection; Nepal project 2 entered the census data collection stage with data collection for the health survey to follow; and Nigeria project 2 expected to begin data collection in April 2025. This represents a tight turnaround to evaluate project 2s in Nigeria and Nepal, however, completion of the evaluation remains within the timeframe of the programme.

The MTE highlighted the relevancy of CHORUS research, making the delivery and evaluation of all research projects pressing to ensure this high-quality research delivers maximum impact.

The table below gives an overview of each project, the stage of delivery and which of CHORUS’ four pillars the project addresses:
1. Linking different health providers.
2. Multi-sectoral collaboration.
3. Responding to the double burden of communicable and non-communicable diseases.
4. Direct engagement with the urban poor.
Lead Partner	Project Summary	Pillar/s addressed	Country	City
Projects in Intervention Evaluation
ARK Foundation	Evaluates adaptation protocols for diabetes and hypertension for use in urban dispensaries and clinics. Data is recorded through the adapted ‘Simple App’ for better delivery of care to the urban poor.	1&3	Bangladesh – Project 1	Dhaka
University of Ghana	Linking communities, local government and health workers to support health promotion and prevention policies at the household level in urban poor neighbourhoods.	2&4	Ghana – / Project 1	Accra
University of Nigeria	Developing health system linkages between the public and informal sectors for improving the equitable provision and use of appropriate essential health services in urban slums.	1&4	Nigeria – / Project 1	Onitsha and Enugu
HERD International	Strengthens the delivery of non-communicable disease programmes for the urban poor at the primary health care setting.	1&3	Nepal – / Project 1	Pokhara
Projects in Implementation Stage
ARK Foundation and BRAC University, JPGSPH	Developing strategic purchasing models and the capacity strengthening of purchasers in Urban Bangladesh.	1&4	Bangladesh – / Project 2	Dhaka, Khulna
University of Ghana	Implementing public-private Networks of Practice to improve the coverage of health services in urban poor populations.	1&3	Ghana – / Project 2	Accra
University of Nigeria	Mainstreaming health to address communicable diseases, non-communicable diseases and maternal and child health issues in urban areas.	1&2&3	Nigeria – / Project 2	Enugu
HERD International	Strengthening urban health systems through a co-designed Urban Health Data Hub.	2&3&4	Nepal – / Project 2	Kathmandu

Output 2.2
A total of 17 Innovation Fund projects have now been funded, with all projects awarded by Year 4, one year ahead of expected timelines. The Innovation Fund has become a strong mechanism for CHORUS to develop research capacity of early career researchers working across a diverse range of quantitative and qualitative methods, from healthcare financing to a rapid ethnography on inequities. The successful early career researchers gain from mentorship and wider access to upskilling opportunities from within the programme. Simultaneously, the Innovation Fund has supported the work of CHORUS, including informing some of the research projects.

Output 2.3
CHORUS has continued to demonstrate its commitment to ensuring that their research is inclusively framed with 35% of those consulted during the needs assessment and co-creation phase being either people with a disability, from the LGBTQi community or a vulnerable ethnic group. There has been no change to data since the previous annual review when project 1s completed needs assessments. Fully updated figures for each of the eight projects is expected once all project 2s have completed their needs assessment and co-creation processes. The data on the demographics of those consulted across the programme will be referenced against the demographic reach that the interventions achieved from each project 1.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Milestones for this year were increased for Output Indicator 2.2 and 2.3. For 2.2 the number of projects funded from the CHORUS Central Innovation Fund increased from 15 to 17 since the target of 17 was achieved in Year 4. For 2.3 the number of people consulted that were from urban informal or slum settlements increased from 40% to 74% to reflect that this target had been achieved in Year 4. Following this review, final milestones will be reviewed to maintain appropriate level of ambition.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Progress against previous recommendations
1. Review milestones to ensure they are aligned to ambitions and suitably challenging. End 2024 – completed and approved by FCDO.
2. Ensure that projects move accordingly into the implementation and evaluation stages as per the workplan. Ongoing – Good progress made with two additional projects designed, five additional projects in implementation and 4 projects being evaluated since last annual review.
3. Additional support may be required for ethical approval for IFs in light of recent delays. TBD – all IF awards made and projects underway.
Again, CHORUS has advanced in line with the programme trajectory, fully implementing the expected research and funding LMIC-led research projects. All projects have had the research study begin implementation or evaluation, with all of the project 1s in the intervention evaluation stage. The progress made on this key milestone demonstrates an increased likelihood that CHROUS will deliver stronger outcomes as more time can be spent on policy uptake efforts.

Recommendations for year ahead:
- CHORUS to continue progress to complete the evaluation of all projects and Innovation Funds - End of the programme.
- CHORUS to provide more detail on the disability aspects of its GESI focus in the end of programme report.
Output Title	Strengthened capability to conduct high quality health systems research
Output number:		3	Output Score:	A+
Impact weighting (%):		30	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Accepted (and Published) Journal articles: i) Total; ii) High impact journals (Q1 Scimago subject ranked journals); iii) Female first author; iv) First author from LMIC; v) early career researchers first author; vi) Published journal articles	i) 20 / ii) 12 / iii) 8 / iv) 18 / v) 12 / vi) 15	Exceeded / i) 24 / ii) 18 / iii) 9 / iv) 22 / v) 19 / vi) 19
3.2 Number of externally funded grant or consultancy proposals by / CHORUS partner researchers (not partner leads): i) submitted; ii) / successful	i) 5 / ii) 2	Exceeded / i) 7 / ii) 3
3.3 Action Learning Groups (ALGs) active as measured by i) ALGs meeting regularly with engagement across all partners; ii) Regular ALG attendees; iii) support documents produced by ALGs	i) 5 / ii) 35 / iii) 5	Met / i) 4 / ii) 56 / iii) 5
3.4 Individual capacity strengthening support provided through i) PhDs; ii) mentorships and/or secondments; iii) training events and products; iiib) number of training events/products with southern leadership; iv) number attending training (1 day +) v) number attending webinars or short (less than 1 day) training events	i) 2 / ii) 37 / iii) 29 / iiib) 20 / iv) 210 / v) 460	Met / i) 2 / ii) 37 / iii) 33 / iiib) 26 / iv) 198 / v) 247

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

CHORUS exceeded or met all expectations for output 3 and as such this output has scored A+. The MTE concluded that CHORUS has ‘strong multidisciplinary collaboration, capacity strengthening and knowledge sharing’ by effectively ‘integrating expertise from the Global North and South’. This output scored A+ reflecting CHORUS’ commitment to research uptake and capacity strengthening.

Output 3.1
In Year 5, CHORUS brought the total number of journal articles published up to 19, above the milestone of 15, whilst a further five have been accepted by journals. Eighteen of these publications have been accepted by high impact journals. This shows significant advancement since last year’s review, when only seven had been published. CHORUS demonstrated their commitment to capacity strengthening, in line with FCDO priorities, with 91% of published and accepted manuscripts being LMIC-based partner-led, and 79% being led by early career researchers. The gender milestone has also been met; however, CHORUS still remain below an equal split, with only 38% of articles being female led. We expect CHORUS to continue progress on delivering accepted and published journal articles as the programme moves towards closure.

Output 3.2
CHORUS partner researchers have done well to exceed the targets for submitting funding proposals and being successful in these in the challenging ODA landscape in 2025. These challenges are reflected in the lower targets set for this year. Applications to UKRI’s Economic and Social research Council and NIHR have been successful.

Output 3.3
Action Learning Groups (ALGs) are an important aspect of CHORUS’ capacity strengthening whereby individuals from across country teams work together to encourage and enable learning on specific aspects of the RPC. These ALGs have been running since the beginning of CHORUS and during FCDO’s visit to Bangladesh, we saw how well established these are and how well these groups help to connect teams across the RPC. Four of five ALGs met monthly or quarterly this year including: Research Uptake; Qualitative; Gender and Intersectionality; and M&E. The Systematic Review ALG paused following the successful completion and submission of two cross-CHORUS systematic reviews, however the group reformed to support Innovation Fund holders undertaking scoping reviews. The Qualitative ALG was particularly active this year to support the consortium with various aspects of data collection, evaluation and analysis of results. The Gender and Intersectionality ALG has also been active completing a review of its gender and equity strategy and supporting teams in obtaining, capturing and analysing comparable gender and equity data.

Output 3.4
CHORUS progress against this output was mixed. CHORUS continues to support two researchers through PhDs and 37 with mentorship or secondments. This year, out of 37 training events/ products, 33 of these were led by LMIC-based partners, exceeding expectations. Despite not meeting milestones for this year, CHORUS has seen an increase compared to last year of number of individuals attending training over one day (iv) and numbers attending training less than one day (v). Cumulatively, CHORUS has supported 581 individuals through training events over one day and 1263 under one day (though some may have attended more than one event over the course of the programme).

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Milestones for each output indicator have been reassessed since last year. For output indicator 3.1, the number of accepted journal articles has been reduced to reflect a new approach due to the short remaining period of work, CHORUS have prioritised papers to ensure delivery within the final year. The other sub indicators saw increases to reflect exceeding performance in the previous year. Following this review, final milestones will be reviewed to maintain appropriate level of ambition.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Progress on previous recommendations
1. Continue publication support strategy but also look for ways to expedite where possible and consider other types of documents (e.g. policy briefs) where peer-reviewed articles are less appropriate. Ongoing – CHORUS has made good progress by holding writing workshops and protecting time for writing papers as well as producing literature beyond peer-reviewed articles.
2. Ensure that findings from the mid-point capacity assessment are put into place and monitor for impact. Ongoing – Progress has been made, with the capacity assessment finding a positive change in researchers’ capacity in methodological, thematic, and research governance areas since CHORUS began, however noted challenges with implementing capacity strengthening activities due to busy schedules. CHORUS plan to conduct an end-point capacity assessment.
3. Develop a cross consortium working group to draw out the lessons and recommendations from the system level activities conducted and ensure implementation of findings. Ongoing – CHORUS is planning on producing a paper summarising key lessons from the RPC, including its successful embedded approach to share with other research groups.
CHORUS has made strong progress on the number of accepted journal articles delivered, particularly in the number published in high-impact journals, which increased from three last year to 18. Similar increases in participation and delivery of capacity strengthening work have also been seen.

Recommendations for year ahead:

- CHORUS to prioritise publications that are most likely to deliver outcomes in the final year of the programme. – By programme closure.
- CHORUS to provide an update to FCDO on recommendation 3 from last year (Develop a cross consortium working group to draw out the lessons and recommendations from the system level activities conducted and ensure implementation of findings) – Dec 2025.

## D: VALUE FOR MONEY

Key cost drivers and performance

CHORUS’ main cost drivers remained similar to last year with personnel costs and direct costs of research remaining the highest drivers, with direct research costs increasing to 35% of total costs as research projects moved into the implementation stage in Year 5. Personnel costs remained the highest accounting for 46% of total spend. There was an increase in expenditure by LMIC-based partners with a split of 68%, compared to 65% in Year 4, in line with higher direct project spending during this reporting period.

VfM performance compared to the original VfM proposition in the business case
CHORUS exceeded many of its output targets this year whilst providing value for money. CHORUS continue to demonstrate strong Value for Money (VfM) and to perform well compared to the original VfM proposition in the business case. CHORUS remains committed to economy, efficiency, and effectiveness throughout delivery to ensure overarching value for money.

Economy
CHORUS has delivered VfM through implementing money-saving measures. Consideration was given to achieving an appropriate balance of in person and online engagements, and value was maximized through the doubling up of events e.g. the annual partner meeting in Dhaka dovetailed with data analysis workshops, finance and governance meetings, and policy and media engagements, to save on travel costs.

Efficiency
CHORUS has demonstrated efficient use of project planning templates and tools across the consortium, including M&E logs, gender and equity tools, and the Reach, Effectiveness, Adoption, Implementation and Maintenance (ReAIM) framework templates, which have contributed to efficient, effective working and comparative results. There is increased use of AI to improve efficiency without compromising quality and integrity e.g. the use of Covidence in systematic and scoping reviews for Innovation Fund Round 2 holders and exploring automated coding functions of NVivo for evaluations. There is also ongoing collaboration with the ReBUILD for Resilience RPC to jointly develop resources sharing lessons on gender and equity in health research, which demonstrates strong sharing of resources across FCDO programmes for shared priorities.

The MTE found that ‘CHORUS has also implemented a range of strategies to maximise resources, to enhance the efficiency of the research-to-uptake cycle and the proportion of funds going to LMIC partners is commendably high.’

Effectiveness
CHORUS’ close engagement with city and national governments throughout the programme lifecycle has enabled success in strengthening urban health systems to meet the needs of low-income urban residents and will be beneficial for research uptake. The Innovation Fund projects are a strong example of VfM as, despite small amounts of seed-funding (£50k in round 1 and up to £20k in round 2), 17 Innovation Fund projects have all been able to collect valuable primary data on under-researched urban health topics aligned to CHORUS aims; have more than one publication in development and multiple outputs and engagements for each project; several have influenced policy and action at city, national or global level; and all the early career researchers leading the projects have built their research and project management skills. This represents a major contribution of CHORUS to developing urban health research leaders of the future, all from the global south.

The MTE concluded that ‘CHORUS is broadly on track with its output delivery’ though has faced delays on several of its workstreams due to contextual factors, but ‘has nonetheless already influenced urban health policies, strengthened LMIC research capacity, and generated quality, context-relevant research’.

Equity
CHORUS’ distributed leadership, horizontal management, cross partner knowledge exchange and peer learning have helped to establish equitable partnerships across the consortium. CHORUS has ensured representation and inclusion in central working groups from all partners, and early career researcher participation is actively encouraged. Of the 92 Research Uptake outputs to date, 86% are LMIC-based partner led; 64% are female led, and 58% are led by an early career researcher. Of the 24 accepted and published peer reviewed manuscripts, 38% have a female first author; 91% have an LMIC partner first author; and 79% have an early career researcher first author.

Data and information on the third gender is also now being captured by some of the projects, representing progress in the visibility of health needs for this marginalised group. CHORUS is also exploring the feasibility of creating a mobile application to support the gender and equity checklist, currently being developed by the Gender and Intersectionality ALG, for easy use whilst conducting fieldwork and at all stages of research.

The MTE concluded that ‘its consistent integration of GESI both in research and internal structures, further reinforces its commitment to inclusive, system-strengthening outcomes across diverse LMIC contexts’.

Assessment of whether the programme continues to represent value for money
‘CHORUS has demonstrated significant value through its contributions to urban health research, policy engagement, capacity strengthening, and its approach to equity (MTE). Collectively, these factors indicate a high potential for sustainable impact and value for investment, justifying continued investment.

E: RISK

Overview of risk management

CHORUS continues to follow a comprehensive approach to risk management with The University of Leeds (UoL) as lead partner maintaining the risk register for the programme which is regularly monitored by the UoL Oversight Committee. Risk is reviewed by the FCDO on a quarterly basis and the risk register is recorded on AMP. The only change to risk category ratings have been no changes to the risk ratings in Year 5, with the mitigation strategies for each risk remaining relevant. The overall risk level remains ‘Moderate’, falling within FCDO risk appetite.

Strategy & Context	Policy & Programme Delivery	Public Service Delivery and Operations	People	Safeguarding	Financial & Fiduciary	Reputation	Overall
Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Minor	Moderate

Strategy and Context – Moderate
Risk in this area remains moderate reflecting insecurity across project areas due to unrest, violence and extreme weather causing project activities to slow or pause. Government changes following the unrest and protest in Bangladesh in 2024 have caused delays in data collection for projects with stakeholders being unavailable, increased security risks for staff and curfews / internet outages in place. The annual partner meeting was also postponed from September 2024 to January 2025. Mitigation strategies included adapting fieldwork timeframes; moving to online interviews (where required); compiling up-to-date intelligence on security and demonstrations; and use of community guides when conducting fieldwork. The situation is now more stable and rapid advocacy has been successful to ensure stakeholder support. Floods in Kathmandu in September 2024 caused delays to an Innovation Fund project, and elections in Ghana in December 2024 brought changes to key project stakeholders, including District Health Directors (DHDs) from project areas.

The funding context for health research has changed substantially this year due to the near dismantling of all USAid funding streams in 2025 and the UK Government announcement of a reduction of the ODA from 0.5% to 0.3% GNI. Though these have not directly impacted CHORUS, they may have indirectly affected CHORUS’ networks and may have implications for research uptake due to stretched government budgets.

Policy and Programme Delivery – Moderate
Due to the co-design approach of CHORUS’ research there is a heightened importance to ensure that stakeholders remain interested, and research remains relevant. Elections and political changes in Bangladesh and Ghana prompted structural and personnel changes within key stakeholders, risking disengagement in research. CHORUS mitigated this by rapid advocacy with new personnel, deepening engagement with wider teams, and early identification of potential successors.

Public Service Delivery and Operations – Moderate
There remains a risk around partners not adequately understanding FCDO priorities. The close working relationship between FCDO and CHORUS is an effective mitigation to ensure that the programmes processes are understood and compatible with FCDO expectations.

People – Moderate
This risk rating has increased from Minor last year as there is an increased risk to staff retention linked to programme/contract end dates as individuals look to secure longer term employment. Staff departures would increase pressure on other colleagues as it will be difficult to recruit for very short-term roles. High workloads remain across all teams with the start of Project 2s, in conjunction with project 1s and Innovation Fund projects. Regular review of teams, capacity and timeframes is required to mitigate.

Safeguarding – Moderate
Safeguarding continues to be a moderate risk, particularly with the implementation of new IF projects, new participants and co-researchers. Safeguarding training is mandatory for all staff. There have been no reported safeguarding concerns during this reporting period.

Financial and Fiduciary – Moderate
Risk remains moderate, with further strengthening of financial oversight and support for partners taken place. Regular follow-up audits and capacity visits have been conducted to ensure compliance, including a visit by the UoL Finance team to the ARK Foundation in Bangladesh, January 2025. A follow up audit (conducting internally by UoL Faculty Research team) is planned with HPRG and will report back to the Oversight Committee.

Reputation – Minor
Reputational risk from controversial findings or relationship problems is of minor significance to CHORUS. Nevertheless, effective due diligence and programme management practices mitigates the reputational risk from potential fraud incidents.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

General Programme Management
The relationship between CHORUS and FCDO continues to be positive and was further strengthened with FCDO engagement at the annual partner meeting in Dhaka in January 2025 which proved highly useful in developing the partnership, enhancing CHORUS understanding of FCDO priorities and sharing CHORUS research progress, objectives, uptake and management. ARK Foundation now has regular meetings with the FCDO Bangladesh Health Advisor, and support from the Deputy High Commissioner raised visibility for CHORUS in Bangladesh. The Ghana team have also built connections with the new FCDO Health Advisor. CHORUS and FCDO hold productive quarterly meetings to discuss programme updates, arising issues and risk.

Issues remain with the timeliness of CHORUS’ financial reporting, with quarterly forecasts and invoices delayed and received on average 10 weeks post quarter end which falls outside of the standard 6-week receipt date as agreed in the contract. CHORUS has acknowledged this issue and placed increased focus on finances at their Executive Committee meetings and has implemented processes to expedite reporting times. The Finance Manager at the UoL, supported by the CHORUS Programme Manager, spent five days with the ARK Foundation finance team (post annual partner meeting) to review finance policies, discuss how these are implemented in practice, and collaboratively identify any areas for strengthening.

Forecasting improved in the final quarter of Year 5, falling within the desire maximum 10% variance, however all other quarterly forecasts recorded variances of over 10%. The highest variance is on the direct project budget line which was primarily due to delays in project implementation and the extension of timelines for certain activities. Capital expenditure also saw an underspend which is aligned with the delays in research work being pushed into later years, affecting the procurement of assets. A recommendation from Year 4’s Annual Review requested CHORUS improve forecasting practices by Q3 of Year 5 to meet previously agreed standards. This was achieved in Q4.

Aside from forecasting and reporting timelines, CHORUS’ programme management standards remain high, transparent and consistent, with issues raised in a timely manner.

Financial Performance
The total CHORUS expenditure as at the end of Year 5 was £5,802,841 (73%) against a total programme budget of £7,972,870. Financial forecasting and reporting have improved as annual variance across Year 5 has reduced to -6.8% (£169,136) underspend against annual budget from -18% in Year 4. This was primarily driven by an increase in direct programme costs being spent during this period as projects moved into implementation stage. Cumulatively to the end of Year 5, there is an overall underspend of £907,058 compared to the corresponding budget, which was caused primarily by project delays in Year 3 and 4.

Financial management continues to be of key importance as we move into the final stages of the programme. Payments are made quarterly in arrears following the provision of a valid invoice and supporting narrative reports which are consistently of a detailed quality.

Commercial Considerations
CHORUS continues to deliver on agreed outputs in alignment with the contract terms. Transparency measures have been met, with details published to IATI’s portal. CHORUS complies with the Supply Partner Code, ensuring transparency and adherence to contractual terms.

A fourth contract amendment is required for budget reprofiling due to underspend resulting from project delays in Years 3 and 4, which has been verbally agreed. This includes carryover into Years 6 and 7 to allow the programme to deliver its research in full. The fourth contract amendment process has been drawn out throughout Year 5 due to delays in CHORUS providing accurate historical figures and an FCDO-implemented pause to progression due to uncertainties around Year 6 budgets and possibility of no-cost extensions across all RPCs. Recent discussions in FCDO has resulted in the decision to move ahead with this contract amendment in 2025.

Asset Management
CHORUS has maintained an up-to-date asset register, with annual checks and compliance with FCDO asset policies. All assets are purchased and maintained according to purchasing policies, with approvals given upon request. The latest asset register was provided by CHORUS in May 2025. At this stage in the project, FCDO would not expect further asset purchases without robust justification and a clear plan for disposal. An asset disposal plan will need to be agreed in Year 6 which maximises VfM and aligns with FCDO policies.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

The annual funders meeting in Dhaka was the first time FCDO visited the CHORUS programme. This was an opportunity to engage with key members of the programme and partners from Nepal, Bangladesh, and Ghana (the Nigeria team could not attend due to visa issues). Following, FCDO and CHORUS worked together to review the remaining workplan and the logframe to ensure accurate and appropriate tools for monitoring were being used.
‘The Mid-Term Evaluation (MTE) of the CHORUS Research Programme Consortium (RPC) was commissioned to assess the programme’s progress, effectiveness, and impact to date. The evaluation recognises that CHORUS is broadly on track to achieve its objectives, is delivering strong and relevant research that is already contributing to policy and programme changes.

FCDO considers that the evaluation, conducted by Tropical Health, provides a thorough and balanced review of CHORUS performance and we agree with the overall conclusions. This assessment is informed and supported by an independent, external reviewer assigned by our Evaluation Quality Assurance and Learning Service (EQUALS). FCDO recognize CHORUS as a high-performing RPC that is delivering against intended outputs and outcomes’.

FCDO Management Response to the RPC MTE of CHORUS

In the reporting period, a mid-term evaluation has been undertaken of CHORUS, which provided a positive review of the programme, alongside points of learning and recommendations to maximise impact in the final year of implementation.

Evidence and Learning
There have been no major changes in the available evidence that have implications for CHORUS research and the MTE found that the research produced by CHORUS continues to be relevant and needed. With results now becoming available from the research, CHORUS has had a total of 24 articles accepted by journals with 19 already being published, including a scoping review of the extent to which informal healthcare providers in slums are linked to the formal health system in Sub-Saharan Africa. The Nigeria team have published several articles including a reconnaissance study into the nexus between informal and formal health service providers in Nigeria’s urban slums and a study assessing knowledge of hypertension and diabetes mellitus among informal healthcare providers in urban slums in Southeastern Nigeria. The Bangladesh team published an important paper on a cross-sectional study assessing socioeconomic and health vulnerabilities among urban slum dwellers. Not only is CHORUS producing numerous papers from the research, the publications are of high quality, as demonstrated by 18 of these being published in journals with a Q1 ranking, the highest in the SCImago Journal Ranking. The full list of published articles and corresponding journals can be found at Annex 2.

The CHORUS programme has a strong focus on GESI and capacity building as demonstrated through its decentralised approach to consortium leadership, the priority it places on supporting early career researchers and its approach to publications:

Publications with:
Female lead author	37.5% (9/24 papers)
LMIC-based lead author	91% (22/24 papers)
Early career researcher lead author	79% (19/24 papers)

Though CHORUS exceeded the target of eight for papers led by a female lead author, most publications have been led by male authors, demonstrating that work is still needed to address the gender imbalance.

CHORUS’ strong emphasis on cross-consortium learning and capacity strengthening continued in Year 5. The six research Action Learning Groups (ALGs) focus on strengthening and knowledge-sharing for different aspects of research, alongside the Gender and Intersectionality ALG, which has been particularly proactive in Year 5. Relationships have been established between Innovation fund holders working on the same thematic area to encourage dynamic learning, supported by a new ALG established to facilitate sharing of best practice. Five ALGs are led by non-UK partners.

In the final year of the programme, with CHORUS progressing each of the projects to implementation and evaluation, the benefits of the co-creation and embedded approaches to research were celebrated by the MTE and have provided lessons as FCDO considers other RPCs and its future approach to applied research.

Date of last narrative financial report	28th May 2025	Date of last audited annual statement	19th May 2025

Annex 1 – Policy changes at outcome level influenced by CHORUS
Project / Country	Brief Description of policy changes influenced	Policy / Programme decision, or both	Policy / Programme Decision at regional / national / sub-national / local or city level	Links
Nepal Project 1	Needs assessment data and the ward maps and overall gap analysis using health facility readiness was used to inform the annual work plan and budget of PMC	Policy	City	https://chorusurbanhealth.org/pathway-to-impact-establishing-partnerships-to-respond-to-ncds-in-urban-nepal/
Nepal Project 1	Embedded researchers input on evidence driven synthesis using routine HMIS data, technical assistance to PMC health team and strengthened health review - informing evidence driven annual workplan and budget of PMC	Policy	City
Bangladesh Project 1	Needs assessment data informing the costing of the urban health strategy - Rumana Huque	Policy	National
Bangladesh Project 1	Following effective introduction of Simple App to include urban health data in DHIS2, decisions have been taken to scale up use across government outdoor dispensaries across Dhaka and Khulna (with ARK support) - evidenced through case study	Both	Sub-national	https://chorusurbanhealth.org/pathway-to-impact-improving-patient-ncd-data-in-urban-bangladesh/ https://chorusurbanhealth.org/blog-arks-simple-solution-to-the-urban-data-dearth/
Ghana Project 1	CHORUS Ghana engagement has led to a request from PPME GHS to be able to include CHORUS data as they revise the CHPS policy and implementation manual.	Both	national
Nigeria Project 1	The MoH in Enugu has agreed to set up a desk to coordinate the linkage between the informal health providers and the formal health system	Policy	State
IF Ghana - HiAP	In Ghana, the IF project on Health in All Policies (HiAP) has triggered cross sectoral engagement at district level		District	https://chorusurbanhealth.org/blog-using-health-in-all-policies-as-a-key-strategic-tool-for-improved-health-outcomes-in-a-poor-urban-context-in-ghana/
Nepal Project 1	The HERDi needs assessment findings and collaboration with PMC influenced PMC in taking action to link with pharmacies to strengthen NCD management and care		City	https://chorusurbanhealth.org/pathway-to-impact-establishing-partnerships-to-respond-to-ncds-in-urban-nepal/
Cross CHORUS - Urban Health CS WHO	Urban Health Capacities Assessment and Response resource Kit	Policy	Global	https://iris.who.int/bitstream/handle/10665/379325/9789240098244-eng.pdf?sequence=1 https://www.who.int/teams/social-determinants-of-health/urban-health/urban-health-capacity-assessment-and-response
Nepal Project 1	The evidence generated in the Nepal has been used to draft the procedural guidelines on Health Facility and Management Committee (HFOMC )to improve its governance of local health facilities.	Policy	City
IF Ghana - HiAP	The IF study stakeholder engagement acted as a catalyst for the municipality’s MPCU to expand its membership from 13 to 20 members representing social and economic sectors within the local government setting and whose actions and inactions impact health.	Both	Municipal	https://chorusurbanhealth.org/blog-using-health-in-all-policies-as-a-key-strategic-tool-for-improved-health-outcomes-in-a-poor-urban-context-in-ghana/
Nigeria Project 1	The intervention from Project 1 has influenced a sub-national govt to identify strategies to include traditional birth attendants in the referral system in their annual operational plan	Both
Ghana Project 1	An Urban Health Desk was established at PPME, Ghana Health Services, to coordinate with the CHORUS team for data capture, collaborate on intervention co-creation and the training resources, and prioritise urban health issues at the national level.		National
Nepal Project 1	Continued engagement with PMC has led to NPR 3M allocated in municipality funding for NCDs screening in the annual workplan and budget.		Municipal
Nepal Project 1	Project 1 implementation has customised the PEN package for private pharmacies, influencing sustained practice beyond the project lifespan in PMC.		Municipal	https://herdint.com/update/urban-health-system-strengthening-pen-package-training-to-health-workers/
Nepal Project 1	Project 1 has recorded NCD data from pharmacies to the government DHIS-2 health information system.		Provincial
Nepal Project 2	Stakeholder collaboration on Project 2 has resulted in the commitment of municipality for next four years, and funding of NPR 3M for collecting local data through surveys and research, with the goal of informing the development of the Urban Health Data Hub and the Family Health Folder.		Municipal
Project / Country	Brief description of changes to urban health systems influenced	Policy / Programme decision, or both	Policy / Programme Decision at regional / national / sub-national / local or city level	Links
Bangladesh Project 1	Integration of the NCDC National Protocol on the Management of Hypertension and Diabetes training within DNCC healthcare providers’ capacity strengthening activities.	Both	City
Bangladesh Project 1	Scale up of the use of the Simple App to strengthen NCD data into Government Outdoor Dispensaries and urban PHC centres in Dhaka and Khulna.	Both	Sub-National	https://chorusurbanhealth.org/blog-arks-simple-solution-to-the-urban-data-dearth/ https://chorusurbanhealth.org/pathway-to-impact-improving-patient-ncd-data-in-urban-bangladesh/
Bangladesh Project 1	Advocacy for integrating the third gender and data on diabetes through the Simple App.	Both	Sub-National
Nigeria Project 1	Establishment of an UH Unit within Enugu MoH. This is now included in organigram and with designated budget. The Unit is to strengthen governance and coordinate the linkages between the informal providers and the formal healthcare system, strengthening governance and	Both	Sub-National	https://www.youtube.com/watch?v=TtS8q1SK4fA https://www.linkedin.com/posts/health-policy-research-group-unn_urbanhealth-healthsystems-primaryhealthcare-activity-7324504422112280576-rxru/

Annex 2 – CHORUS Publications
	Manuscript title	Journal	Scimago rating	URL	Female 1st author	LMIC Partner Led	Early career researcher 1st author
Published	The role of the private sector and government responses in the COVID-19 pandemic: experiences from four health systems	Frontiers for Public Health	Q2	https://www.frontiersin.org/articles/10.3389/fpubh.2022.878225/full https://www.frontiersin.org/journals/public-health/articles/10.3389/fpubh.2022.915330/full	Yes	Yes	Yes
	Stakeholders perspectives and willingness to institutionalise linkages between the formal health system and informal healthcare providers in urban slums in southeast Nigeria	BMC Health Services Research	Q1	https://www.readcube.com/articles/10.1186/s12913-022-08005-2	No	Yes	No
	“Domains of deprivation framework” for mapping slums, informal settlements, and other deprived areas in LMICs to improve urban planning and policy: A scoping review	Science Direct, Computers, Environment and Urban Systems	Q1	https://www.sciencedirect.com/science/article/pii/S019897152200014X?via%3Dihub		No	No
	Contextual influences on private sector participation and contribution in COVID-19 response in Nigeria	Frontiers of Public Health	Q2	https://www.frontiersin.org/articles/10.3389/fpubh.2022.915330/full	Yes	Yes	Yes
	Assessment of Public-Private Partnership (PPP) Models in Health Systems in Least Developed, Low Income and Lower-Middle-Income Countries and Territories: A Protocol for a Systematic Review	Health Care: Current Review Vol 10 Issue 8, No 1000306	Q2	https://www.researchgate.net/publication/363924394_Assessment_of_Public-Private_Partnership_PPP_Models_in_Health_Systems_in_Least_Developed_Low_Income_and_Lower-Middle-Income_Countries_and_Territories_A_Protocol_for_a_Systematic_Review	Yes	Yes	Yes
	Strengths, disconnects and lessons in local and central governance of the response to the first wave of COVID-19 in Ghana	Ghana Med J 2022; 56(3) supplement: 85-95	Q4	https://pubmed.ncbi.nlm.nih.gov/38322743/	Yes	Yes	Yes
	Association between media exposure and maternal health service use in Nepal: A further analysis of Nepal Demographic and Health Survey-2022	Plos One	Q1	https://journals.plos.org/plosone/article?id=10.1371/journal.pone.0297418	No	Yes	yes
	To What Extent Are Informal Healthcare Providers in Slums Linked to the Formal Health System in Providing Services in Sub‑Sahara Africa? A 12‑Year Scoping Review	Journal of Urban Health Springer	Q1	https://link.springer.com/article/10.1007/s11524-024-00885-5	No	Yes	yes
	Assessing knowledge of hypertension and diabetes mellitus among informal healthcare providers in urban slums in southeastern Nigeria	Discover Public Health Springer	Q1	https://link.springer.com/article/10.1186/s12982-024-00143-8	Yes	Yes	No
	Informal–Formal Healthcare Services Delivery Nexus in Nigeria’s Urban Slums: A Reconnaissance Study	Taylor & Francis Online - Journal of Social Service Research	Q2	https://www.tandfonline.com/doi/full/10.1080/01488376.2024.2371859	No	Yes	?
	Enhancing the role of mass media in the translation of evidence from health policy and systems research in Nigeria	Health Research Policy and Systems	Q1	https://health-policy-systems.biomedcentral.com/articles/10.1186/s12961-024-01267-8	No	Yes	Yes
	Institutionalizing linkages between informal healthcare providers and the formal health system in Nigeria: what are the facilitating and constraining contextual influences?	Health Policy and Planning	Q1	https://academic.oup.com/heapol/advance-article/doi/10.1093/heapol/czaf009/8003620?searchresult=1	No	Yes	No
	A scoping review of the roles of stakeholders and coordination mechanisms for enhanced multi-sectoral and multi-level interventions in COVID-19 response in Nigeria	Health Research Policy and Systems	Q1	https://health-policy-systems.biomedcentral.com/articles/10.1186/s12961-024-01276-7	Yes	Yes	Yes
	Assessing informal healthcare providers' knowledge of diagnosis and treatment of malaria and diarrhoea: evidence from urban informal settlements in Southeast Nigeria	Frontiers of Public Health	Q1	https://www.frontiersin.org/journals/public-health/articles/10.3389/fpubh.2025.1556996/full	Yes	Yes	yes
	Solving delayed referrals of childbirth cases from unskilled to skilled birth attendants in Nigerian urban communities: A case study of exploration of new frontiers	Journal of Midwifery	Q1	https://www.sciencedirect.com/science/article/pii/S0266613825001159	No	Yes	Yes
	Inequities in Household out-of-pocket spending among urban slum dwellers in Southeast Nigeria	International Journal of Public Health	Q1	https://www.ssph-journal.org/journals/international-journal-of-public-health/articles/10.3389/ijph.2025.1607969/full?utm_source=Email_to_authors_&utm_medium=Email&utm_content=T1_11.5e1_author&utm_campaign=Email_publication&field&journalName=International_Journal_of_Public_Health&id=1607969	No	Yes	Yes
	Comparative Analysis of the out of pocket health expenditure in case of chronic and acute disease affected households in Bangladesh	Plos One	Q1	https://journals.plos.org/plosone/article?id=10.1371/journal.pone.0320429&?utm_id=plos111&utm_source=internal&utm_medium=email&utm_campaign=author	Yes	Yes	Yes
	Assessment of socioeconomic and health vulnerability among urban slum dwellers in Bangladesh: a cross-sectional study	BMC Public Health	Q1	https://bmcpublichealth.biomedcentral.com/articles/10.1186/s12889-024-20425-9#citeas	No	Yes	yes
	Choice of Primary Health Care Providers among Population in Urban Areas of Low- and Middle-Income Countries – A Protocol for Systematic Review	BMC Systematic Reviews	Q1	https://systematicreviewsjournal.biomedcentral.com/articles/10.1186/s13643-024-02714-x	No	No	Yes
Accepted	Understanding health seeking in urban slums, their drivers, and implications for formal primary health care services in Nigeria: findings from a reconnaissance exploration	Urban Studies	Q1		No	Yes	Yes
	Social Determinants and risk factors associated with non-communicable diseases among urban poor in Nepal: A comparative study of poor, middle and rich wealth categories of urban population using STEPS survey	PLOS One	Q1		No	Yes	Yes
	Contributions of Community leaders as gatekeepers towards improving access to health services in urban areas	Discovery Social Science and Health	Q2		No	Yes	Yes
	Protocol Paper: Developing an Urban Deprivation Index in Nepal: A Protocol for Data Review, Measurement, Visualization, Capacity Building, and Real-World Application in Urban Poverty Alleviation - secondary data, delpha approach, methods	Plos One	Q1		No	Yes	Yes
	Building linkages between private pharmacies and primary care to improve treatment of diabetes and hypertension in an urban city of Nepal: A protocol for implementation research study	Implementation Science Journal	Q1		Yes	Yes	Yes

## Annex 3 – FCDO Management Response to MTE Recommendations

Recommendations	FCDO response
1. How-to Guide: CHORUS should develop a how-to guide for its embedded research approach and disseminate it to appropriate audiences.	Agree
2. Develop a prioritised implementation timeline: CHORUS should create a detailed Gantt chart for the final year that outlines and prioritises remaining activities. This should be accompanied by open discussions with FCDO to assess feasibility and, if needed, recalibrate expectations to ensure realistic planning.	Agree
3. Prioritise protected time for data analysis and publication writing: Set aside dedicated writing retreats or protected time blocks to focus on finalizing key dissemination products, such as academic publications, policy briefs, and knowledge-sharing materials.	Agree
4) Improve the quality of outcome reporting: In alignment with its current plans and logframe, CHORUS should systematically complement quantitative outcome reporting with detailed qualitative case studies. These could be supported by engaging visuals, such as short videos or podcasts.	Agree
5) Support health system learning: CHORUS should treat early policy uptake as an opportunity for system learning, by establishing structured feedback mechanisms of emerging evidence from the evaluations with policy makers—including partial successes or challenges—to support real-time course correction and enable programme and policy alignment with evidence over time.	Agree
6) Outcome harvesting: FCDO should commission an outcome harvesting evaluation to support early career researchers in analysing the quality and impact of their work—including on their career trajectories—and to document good practices and lessons learned for informing future RPCs and similar research programmes.	Partially agree – would be beneficial, but not a priority.
7. Explore opportunities for inter-institutional research partnerships beyond the existing framework through co-mentorship of IF grants.	Agree
8. Increase capacity strengthening and staffing to handle multiple systems, rules and institutional ways of doing things required to handle the project financial and administrative management issues. Increased inclusion of financial aspects in EC meetings.	Agree
9. include work package on research institution system strengthening for finance/grant/operational management in future funding.	Partially Agree – FCDO will be discussing future commissioning and modality in the future.
10. Consider how to mitigate risks accompanying high ambition: / CHORUS: CHORUS should engage in scenario planning to strategise what can be reasonably achieved within the existing RPC timeframe, while continuing with its existing efforts to improve budget forecasting and utilisation. / FCDO: Consider going forward whether there is a risk that challenges related to the contractual arrangements, combined with budget utilisation targets, might have unintended consequences, incentivising RPCs to be less ambitious with partner selection, research scope, and managerial arrangements and consider how to mitigate such a risk.	Agree - FCDO will be discussing future contracting modality in the future, dependent on internal FCDO commercial guidelines at the point of time.