## Annual Review Template

Title: ReBUILD for Resilience (ReBUILD)
Programme Value £ (full life): £7,682,203		Review date: 21/09/2025
Programme Code: 301133	AMP start date: 18/03/2020	AMP end date: 30/04/2026

Summary of Programme Performance
Year	2021	2022	2023	2024	2025
Overall Output Score	A	A+	A+	A+	A+
Risk Rating	Moderate	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:
DevTracker Link to results framework:	Logical Framework

A. SUMMARY AND OVERVIEW

Description of programme
ReBUILD for Resilience (ReBUILD) is an international consortium of organisations from Lebanon, Myanmar, Nepal, Sierra Leone and the UK which examines health systems in fragile settings experiencing violence, conflict, pandemics and other shocks and how health systems respond. Its aim is to produce high-quality, practical, multidisciplinary research which can be used to build health systems resilience and improve the health and lives of many millions of people. The primary research question is ‘How do we develop resilience capacities to ensure responsive, effective, inclusive, gender-equitable and sustainable health systems in fragile and shock-prone (FASP) settings?’ This short video gives a programme overview.

ReBUILD’s research framework is grounded in a view of health systems as complex, adaptive systems. There are three types of research taking place:
- Learning sites: Medium- to long-term research platforms in a specific district or geographical area. This embedded approach facilitates trust and collaboration between researchers and health managers, the co-creation of actions and knowledge with local stakeholders and the emergence of locally relevant themes. Sites use participatory action research (PAR) cycles to investigate barriers, adaptations and responses to adaptations.
- Thematic research: Topic-led research building on priorities and opportunities identified in the Inception Phase, financed through partner budgets, the Responsive Fund and external co-financing. This aims to achieve balance across themes, partners and recognise different contexts and team capacities. Themes include non-state actors in health; gender; community health workforce; governance, coordination and partnership; political economy and health financing.
- Synthetic and collaborative work: Includes literature reviews, scoping reviews, policy briefs and cross-cutting analysis or re-analysis of existing work to draw out trends and lessons. These are supported by ‘core’ ReBUILD staff time, with some funds from the Responsive Fund[1].
  [1] The Responsive Fund is accessed at any time through an internal application process, open to all partners and associate partners, as a mechanism to conduct research at the request of a policy maker, or to conduct research that may lead to multiplier funding. Applications are reviewed by a selection panel made up of CMC members and one external reviewer. Selection criteria include alignment with ReBUILD’s overall research question, theory of change and resilience framework, expertise of team, potential for impact, value for money, capacity strengthening and ReBUILD values.

Summary supporting narrative for the overall score in this review

The programme has scored an A+ exceeding three and meeting one outputs this year. This strong performance was confirmed by the independent evaluation of the programme conducted this year which concluded that despite working in complex, conflict-affected and unstable settings, ReBUILD has produced a large, contextually diverse and high-quality body of evidence, which is being taken up at different levels leading to some specific changes in policy and practice. The final synthetic phase of work is expected to offer considerable added value. Significant work remains to complete, disseminate and support uptake of remaining research studies and synthesis work but appropriate steps to mitigate risks and maximise outputs are being taken.

Cumulatively, ReBUILD has published 40 peer-reviewed articles (38 open access), and is conducting 51 research studies in 14 fragile and shock prone countries. Thirty-seven of these research studies consider gender and 17 disability. Cumulatively, a total of 34 studies have been completed and over 200 non-peer reviewed outputs produced including a six-part podcast series. ReBUILD consortium members continue to actively disseminate findings with a strong presence as Health System Global Research Symposium (Nov 2024) as well as meaningful engagement with local, national and international policy makers captured in the case studies.

This year research highlights include:
- In Nepal, the first learning site is implementing it’s third cycle of participatory action research (PAR). Learning site 2 is underway across ten municipalities in Kapilvastu district. The responsive fund study on climate change and health systems is ongoing in collaboration with CHORUS.
- In Myanmar, Two Responsive Fund studies on health seeking behaviour of migrants and internally displaced people and on mental health and wellbeing needs of young people have been completed with manuscripts drafted. A third responsive fund study on health systems readiness for disability inclusion at township level was implemented and is now at analysis stage.
- In Lebanon, activity was disrupted by the ground invasion by Israel into Lebanon. Consequently, in consultation with FCDO, the decision was taken not to establish a second learning site. The team have instead continued to focus on analysis and manuscript development from learning site one, analysis and manuscript development of a responsive fund study on ‘Close-to-Community (CTC) providers addressing gender norms and power dynamics’ and initiation of a follow-on study on ‘Empowering female informal CTC providers: Advocacy challenges and opportunities of a support group lobbying for their rights within the health system’.
- In Sierra Leone, the learning site study is implementing the second cycle of PAR in two districts. Three papers have been submitted from the first cycle. The Responsive Fund study on ‘Strengthening community health systems: A collaborative approach to addressing Kush use in Kailahun district Sierra Leone’ is underway.
Year 5 saw diverse capacity strengthening activities including a three-part series on artificial intelligence in research, mental health awareness and research techniques, and artistic methods for just health systems. On-the-job training in podcasting was delivered at the Global Symposium on Health Systems Research in November 2024 as well as focused support for the Nepal team who have delivered the first episode in their Nepali language series. One-to-one mentoring, especially for newer team members in LMICs, intensified to support data analysis and writing. The annual partner health check survey confirmed the effectiveness and positive reception of these capacity strengthening efforts. The independent evaluation found that ReBUILD has established a culture of mutual learning and used multi-directional, needs/capacity-based and embedded approaches to significantly enhance consortium and external stakeholder capacity to produce, adapt and use evidence.

ReBUILD has reached the synthesis stage of its research uptake and communications strategy. The consortium is maximising the large body of health systems research generated over the last five years through analysis and reanalysis of existing work as part of their synthetic work stream. ReBUILD had a strong presence at November’s Global Symposium on Health System Research, presented at a webinar with WHO and the World Bank, and presented findings at other relevant conferences in Turkey and Zimbabwe. Ten journal articles, once policy brief, two toolkits, 17 blog posts on current health systems crises (including in the Occupied Palestinian Territories and Yemen), as well as a six part podcast series on health systems in fragile settings were produced.

Major lessons and recommendations for the year ahead
Issue/Lesson	Recommendation
ReBUILD have demonstrated strong delivery despite contextual volatility. They are on track to deliver outputs by 30 April 2026 but risk reducing vfm as a result of curtailed time for synthesis of findings across contexts and dissemination of the substantial body of evidence generated.	FCDO to consider ReBUILD’s request for a no cost extension to support completion of analysis, write up and dissemination. If approved contract to be amended in Q3 2025/26.
The mid-term evaluation identified several recommendations for ReBUILD during the remainder of the grant period. Those considered high priority have been included here.	By March 2026 document learning regarding: / -key aspects of research design including the use of learning sites in unstable settings. / -capacity strengthening approaches with emphasis on good practice for capacity strengthening in FCAS / -approach to fostering equitable partnerships
	By November 2025 ReBUILD to enhance sustainability (and exit) planning by developing a comprehensive strategy for the continuation of research efforts, including efforts to secure follow-up funding, to ensure long-term impact and sustainability of work beyond the current funding cycle. This should be linked to the Y6 research uptake and comms plans.
	FCDO and ReBUILD to work together to hold a learning event in Y6 with other funders and stakeholders to amplify ReBUILD’s work and future investment in health system resilience research in FASP settings and provide opportunities for dissemination of research findings across FCDO health staff and advisors, to support learning and integration of policy and practice-relevant findings.
	Attention should be sustained with regards to completing, publishing and disseminating cross-country synthetic work, while continuing to maximise opportunities for RU. The RPC should continue to ensure a regular process for reviewing the status of and prioritising remaining work in the final year, in line with anticipated impact and feasibility.
Research uptake and comms plans exist but should be refreshed in light of contextual changes in stakeholders and identified windows of opportunity in order to maximise programme outcomes	By November 2025 deliver a comprehensive research uptake and comms plan across each country and globally including products and meetings to share findings.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

ReBUILD aims to build health systems resilience in fragile settings (experiencing violence, conflict, pandemics and other shocks) and so improve the health of many millions of people, by producing high-quality, practical, and multidisciplinary health systems research. Research is complemented by capacity building and research uptake strategies that are designed to increase the ability of key stakeholders to generate and use research evidence at local, national and international levels.

As part of the mid-term evaluation, ReBUILD reviewed the Theory of Change with the independent evaluators. The Theory of Change remains valid, the assumptions still hold, particularly at the lower levels. However, as identified in previous consortium discussions as well as during the evaluation, volatile national and global contexts, including reductions in aid and the reform of global health and humanitarian architecture, make higher level outcomes and impact more difficult to achieve.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

ReBUILD has effectively delivered planned outputs and there is evidence that it is contributing to intermediate and higher-level outcomes in line with the ToC. Key outputs include a body of high-quality, policy-relevant and equity-oriented research and contributions to developing new models and tools for health system resilience in FASP settings. These include 51 diverse research projects covering 14 countries, and 40 publications. ReBUILD has also met or exceeded planned capacity strengthening outputs at the individual and organisational levels, while capacity strengthening at the environmental level has been conducted via embedded research and RU approaches. ReBUILD has contributed to some specific changes in practice and policy, some of which have enhanced attention to gender equality. The programme is on track to further contribute to outcomes assuming the timely completion and dissemination of remaining work, particularly synthetic studies.

ReBUILD has already contributed to some specific changes in practice and policy. At local and subnational levels, these include contributions to health system guidelines and changes in the use of evidence for decision-making in multiple contexts. Changes have been especially well-evidenced in Lebanon and Nepal. The external evaluation found evidence that ReBUILD’s work has contributed to increased awareness of the importance of evidence-based planning and use of evidence for decision making in Lebanon, Nepal and Sierra Leone. Learning site work (involving embedded researchers) has helped local knowledge users understand what research is and how it is used. Some policy or practice changes have enhanced attention to GESI, as both a result of the research and as part of the research process. For example, ReBUILD contributed to empowering female CTC providers, producing films that have helped to facilitate dialogue on the needs of female Community Health Workers in Lebanon and Nepal. At national level, examples of policy impact include leveraging ReBUILD’s work to contribute to the Nepal Health Sector Support Strategy, Health Financing Strategy, and the HRH strategic plan. At the global level ReBUILD has make significant contributions to the Future of Global Health Initiatives culminating in the Lusaka agenda and continue to support ongoing monitoring, as well as supporting WHO’s work programme and tools on political economy thinking to health financing.

Key risks to continued research uptake include unstable contexts, policymaker changes, and the current global context of reduced aid financing which will make future research impacts more challenging. A short no cost extension is recommended to support the completion of planned synthesis work, enhance the dissemination of the large body of research produced in order to increase the achievement of outcomes.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme has scored an A+, having exceeded three and met one outputs during the past year, despite notable contextual challenges in Lebanon and Myanmar and wider implications for partners of reductions in aid funding. ReBUILD has demonstrated strong value for money (a finding confirmed by the external evaluation) by effectively conducting extensive equity-oriented research, influencing policy and fostering strategic partnerships and strengthening capacity effectively. ReBUILD’s research remains highly relevant to informing policy and practice at local, national and global levels in an area of growing importance given the prolonged nature of crises and compounding shocks. Nevertheless, a three-month no cost extension is recommended to increase value by enabling the completion of synthesis work across all study locations and to maximise dissemination of the large body of research to sub-national, national and international stakeholders.

ReBUILD’s work remains highly relevant to FCDO research and health priorities at global and country level including on strengthening health system resilience in FASP settings particularly protracted crises, on integration of climate considerations in health systems and on supporting inclusive and data-driven health system decision making.

## C. DETAILED OUTPUT SCORING

Output Title	Coherent and timely body of high quality, policy-relevant, gender-transformative, equity-oriented research and evidence synthesis on local FASP health systems
Output number:		1	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	N/A

Indicator(s)	Milestones / (cumulative)	Progress / (cumulative)
Number of approved research projects at: / a) Design stage / b) Implementation stage / c) Analysis stage / d) Completed	38 / 38 / 38 / 34	Partially exceeded / 51 / 48 / 47 / 34
Number of research projects that address: / a) Gender or women/girls / b) People living with disability / c) Equity, justice and power	a) 22 / b) 9 / c) 26	Substantially Exceeded / 37 / 17 / 35
Number of peer-reviewed research publications: / a) Lead or co-author based in LMIC / b) Female lead or co-author / c) Female LMIC-based lead or co-author / d) Open access / e) Total	31 / 34 / 19 / 35 / 35	Partially exceeded / 31 / 34 / 20 / 38 / 40
Number of activities in collaboration with other groups, organisations and projects, including FCDO RPCs	14	Exceeded / 32

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has been ‘exceeded’ with ReBUILD exceeding all milestones. In total the programme is undertaking 51 research projects of which 34 have been completed with 13 at analysis stage, one in implementation and three in design. In Year 5 ReBUILD completed a total of completing 10 studies and has initiated new studies in Bangladesh, Syria, Sierra Leone and Sudan. The Responsive Fund mechanism will be closed in Q1 Year 6 to ensure all studies are completed within the timeframe. Of the 51 research projects 37 address gender, 17 disability, and 35 themes of equity, justice and power.

 A cumulative total of 40 externally peer reviewed papers have been published (38 of which are open access), including 10 papers in Year 5. Of the 40 papers, 27 (68%) include an LMIC based author or co-author, 34 (85%) a female lead or co-author and 20 (50%) a female LMIC based lead or co-author. Example of peer-reviewed research published in Year 5 include papers on:
- Assessing the role of non-state actors in health service delivery and health system resilience in Myanmar which highlights the role of non-state actors during crisis and provides insights on how the resilience capacities built over time by these actors has informed the response to the latest crisis.
- Approaches, enablers and barriers to govern the private sector in health in low- and middle-income countries: a scoping review which synthesised evidence on the approaches used to govern private sector delivery and financing of healthcare in LMICs, the effectiveness of these approaches and the key enablers and barriers to strengthening governance.
- Political economy analysis of health financing reforms in times of crisis: findings from three case studies in south-east Asia the paper highlights similarities and differences in recent health financing reforms in Nepal, Thailand and Indonesia. It reflects on whether and how crisis can be used to progress universal health coverage and analyses the strategies used by reformers to benefit from potential windows of opportunity.
- The effectiveness of the Sierra Leone health sector’s response to COVID-19: a quantitative analysis which found that Sierra Leone’s COVID-19 response highlighted both achievements and challenges. While leadership structures, workforce dedication, and community health worker contributions were notable strengths, gaps in communication, resource availability, and community trust limited the overall effectiveness of the response. Strengthening communication channels, investing in workforce training and resources, and enhancing community engagement strategies are critical for improving preparedness and response in future health emergencies.
ReBUILD has continued to collaborate with other groups, organisations and projects across diverse topics and platforms. Activities include ongoing work with CHORUS on climate change and health system resilience in Nepal and on developing a guidelines on mainstreaming gender and equity in applied health systems research; working with the Health Systems Global Thematic Working Group on Health Systems in FCAS; collaborating with WHO on a series of products on health financing (see output 2); working with NGOs to develop an operational guide for health system strengthening and co-hosting a Gender Meetup with JHU and BRAC University at the Health System Research Symposium.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The Year 4 Annual Review recommended that logframe milestones were reviewed and revised with a particular focus on output 1 and 3. Following further discussion on the planned synthetic analysis it was agreed that output 1 targets could remain as originally proposed. These should be reviewed in Year 6 to ensure they reflect progress to date and the totality of studies now underway.

Year 5 has seen an increase in synthetic products (academic papers and briefs) which draw together learning across the research projects in eighteen different areas including on health workforce, climate change, disability, gender and equity, the role of non-state actors and the political economy of reform. This will continue to be a focus in the final year of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The Year 4 Annual Review recommended that ReBUILD, working with the Consortium Advisory Group and FCDO, should prioritise long-list of potential synthesis topics and ensure this work remains a focus for the remainder of the programme to draw together learning across different contexts. ReBUILD has circulated a prioritised list of synthesis papers and briefs it is planning to produce by the end of the programme to the CAG and FCDO. This includes producing cross-country papers for a special issue of Social Science and Medicine – Health Systems. Synthesis work is a large part of the ReBUILD work in Year 6 and has the potential to add value to the large body of research produced. A short no cost extension would support the completion of this work as planned.

It was also recommended that ReBUILD build on work undertaken in Nepal and Bangladesh on climate change to expand this theme and examine opportunities for synthesis, comms and research uptake. In response Year 5 has seen an increasing focus on climate change within ReBUILD’s work. In May 2024 ReBUILD with associate partner Oxford Policy Management (OPM) presented a webinar, attended by over 70 participants, to share experiences on supporting climate-resilient health systems, drawing lessons for both the policy and facility levels including from a previous FCDO regional programme Action on Climate Today Programme in South East Asia. This was followed by a policy brief and a blog post that brought together learning on ‘climate mainstreaming’ in the health sector from three projects undertaken by OPM to understand what mainstreaming means in practice and identify lessons for policy and implementation change.

HERD supported the Ministry of Health and Population to conduct a workshop (February 2025) for key stakeholders working on climate change and health. The responsive fund study on understanding climate change and health systems in Nepal, in partnership with CHORUS, is ongoing and Shophika Regmi (HERD) will present on policy gaps and implementation challenges in Nepal at the ISQUA conference in October 2025.The programme has also initiated a responsive fund study in Bangladesh analysing urban communities’ capacities to cope with various climatic and non-climatic stressors while focusing on gender-specific health vulnerabilities. A cross-country paper on climate change resilience (supporting health system capacities for absorption, adaptation, transformation) is underway for inclusion in the special edition of Social Science and Medicine – Health Systems.

In line with the Year 4 Annual Review recommendation ReBUILD associate OPM have conducted a three-part AI training series (June-July 2024) attended by over 40 people which introduced AI, AI tools (including challenges and ethical issues) and opportunities to apply AI to ReBUILD work. Partners are testing applications of AI, including for the synthesis of information for review.

The independent evaluation of the programme found that ReBUILD has already produced a body of policy-relevant and equity-oriented research and contributed to developing new models and tools for health system resilience in FASP settings in line with its ToC. Work on evidence synthesis is ongoing. Productivity has been facilitated by strong partners and networks, and strategic use of associate partners and of the responsive fund. ReBUILD has effectively adapted to significant contextual changes and promoted care to ensure the safety of researchers and participating communities while working in unstable and conflict-affected settings. The quality of research was rated as very good with especially high scored on relevance, research design, research implementation and user engagement.

Output Title	New methods and models for applications in FASP settings
Output number:		2	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone / (cumulative)	Progress / (cumulative)
Number of papers, products or tools that include new methods and models for application in FASP settings: / a) Peer-reviewed / b) Non-peer reviewed / c) Total	6 / 3 / 9	Met / 7 / 2 / 9

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has been ‘moderately exceeded’. A cumulative total of nine papers, products or tools with new methods and models have been developed of which seven have been peer-reviewed. This year ReBUILD researchers delivered two new papers/products/tools with new methods and models, of which one were peer-reviewed. Sophie Witter (QMU) co-authored a blog laying out new indicators for monitoring financial alignment of donor funds at country level: Money Talks: The Lusaka Agenda Financing Alignment Indicators | Center For Global Development and also led the drafting of a tracker to ensure accountability of delivery on the Lusaka Agenda: The Lusaka Agenda Tracker: What Gets Measured Gets Done | Center For Global Development.

Although not considered as including new methods or models, it should also be noted that Sally Theobald (LSTM) and Sushil Baral (HERD) worked with the FCDO supported Knowledge for Development and Diplomacy (K4DD) programme to produce the Six Guiding Principles to Support Equity in Global Health Programmes.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output during the past year. No changes are proposed as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from the previous annual review on this output. It is noted that new methods and models produced have, generally, been applicable to a range of LMIC settings, including FASP. ReBUILD should consider where new methods and models specific to FASP settings may also be required. ReBUILD could also consider reflecting on their approach to managing ethical approval of research in FASP under this output.

Output Title	Targeted audience-specific research uptake materials and processes, alongside strategic alliances for engagement
Output number:		3	Output Score:	A+
Impact weighting (%):		35%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone / (cumulative)	Progress / (cumulative)
Number of non-peer reviewed outputs aimed at supporting the use of ReBUILD and related research in policy and practice. Disaggregated by: / a) Policy briefs; / b) Reports and working papers; / c) Audio-visual and infographics; / d) Blogs; / e) Other	115	Exceeded / Total: 202 / 10 / 14 / 95 / 83 / 0
Number of unique page views on ReBUILD website, where the individual is: / a) UK based; / b) LMIC based; / c) Based elsewhere; / d) Total unique page views	26,000 / 37,000 / 26,000 / 89,000	Exceeded / 32,132 / 40,815 / 30,995 / 103,942
Number of unique downloads on the ReBUILD website, where the download is: / a) UK based; / b) LMIC based; / c) Based elsewhere; / d) Total unique downloads	7,000 / 11,500 / 14,200 / 30,000	Exceeded total – not met sub milestone c / 10,231 / 15,116 / 10,421 / 35,768
Number of research uptake and dissemination activities	70	Exceeded / 87
Evidence demonstrating how FCDO funding has been used to engage and/or influence national or international expert panels/working groups/policy makers	7 case studies	Met / 7 case studies

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has been ‘exceeded’ with four indicators exceeded and one met. ReBUILD is at a stage in the programme where it’s focus on research uptake and communication is increasing. Over the past year ReBUILD has generated an additional 98 non-peer reviewed outputs (of which 59 were reports or working papers), 26 research uptake and dissemination activities and two case studies documenting engagement and influence with NGOs and policy makers. The ReBUILD website received over 33,000 unique view and 11,000 unique downloads this year.

As reported in last year’s annual review, ReBUILD launched a new podcast series in April 2024 producing six episodes. Additionally, a four-part series reflecting on themes from November 2024’s Global Symposium on Health System Research was produced. ReBUILD utilised the symposium as a key dissemination opportunity presenting nine posters, five panels, eight oral presentations and hosting a film and audio capacity development workshop and gender meet-up. ReBUILD research was also presented at the Climate and Health Africa Conference in October 2024, Liverpool School of Tropical Medicine’s 125th Anniversary event in Liverpool in November 2024, and at the Nepal Health Research Council’s 11th National Summit in April 2025. A paper was presented to KIT on early recovering and reconstruction in the Occupied Palestinian Territories and ReBUILD also presented in three webinars on health financing organised by the Global Financing Facility, the World Bank and WHO.

Two case studies have been developed this year, providing evidence that ReBUILD has engaged and influenced national policymakers in Nepal and NGOs and CSOs in FCAS. In Kapilvastu district ReBUILD strengthened coordination, learning and policy engagement by establishing a multi-tier coordination mechanism to enable dialogue, collaboration and joint problem solving across three tiers of government (federal, provincial and district) and among the ten municipalities as part of its second learning site. This has led to increased commitment to addressing maternal mortality, increased cross-municipality learning and early indications of local government integrating health activities into their annual plans. ReBUILD has also co-developed principles and practices for health system strengthening in fragile settings for NGOs operating across the humanitarian-development spectrum. They have developed practical recommendations on ‘how to do’ health system strengthening in FCAS based on the collective experiences of implementing and funding agencies. Further dissemination events are planned, targeting FCDO’s health advisers and NGO members of the UK-wide Action for Global Health networks, as well as more widely through the FCAS Technical Working Group and academic publications.

ReBUILD has an extensive research uptake and communications plan for Year 6 at a country and global level. This was developed collaboratively during the 2024 annual meeting in Sierra Leone.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The Year 4 Annual Review recommended that logframe milestones were reviewed and revised with a particular focus on output 1 and 3. Following further discussion indicator targets for output 3 were increased. Output 3 milestones for Year 6 will need to be revised upward noting that several of these have been met in Year 5.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The Year 4 Annual Review recommended that where context allows, ReBUILD should enhance national level advocacy by strengthening engagement with national government and operational agencies, to complement ongoing work at local and global level. Sierra Leone was highlighted given changes in the government and research partner. Over the last year the ReBUILD team in Sierra Leone has engaged with both current and former Directors of Policy and Planning at the Ministry of Health and Sanitation and initiated efforts to strengthen feedback loops between community-level work and national policy planning. This is assisting ReBUILD in aligning work with national priorities and ensuring its relevance to ongoing health system reforms. In Lebanon, the team have focused on engagement at the municipality level, however, with the formation of the new government in February 2025 this approach is being revised for Year 6 stakeholder engagement plans. In Myanmar where engagement with the national government remains unfeasible since the 2021 coup the team continue to engage with UN, international NGO and civil society organisations as well as via technical working groups. In Nepal, the team engages frequently with the Ministry of Health and Population at a national and subnational level, Kapilvastu municipality and district as well as international partners.

In line with the Year 4 Annual Review recommendation ReBUILD associate OPM have conducted a three-part AI training series (June-July 2024) attended by over 40 people which introduced AI, AI tools (including challenges and ethical issues) and opportunities to apply AI to ReBUILD work. ReBUILD should continue to consider opportunities to utilise this for supporting research uptake.

A key lesson identified this year through the independent evaluation of the programme is that ReBUILD has demonstrated that it is possible to conduct high quality research and facilitate research uptake in complex and unstable settings and that a flexible approach and continuous adaptation has been key.

Output Title	Environmental, organisational and individual capacity built in FASP settings to produce, adapt and use evidence
Output number:		4	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	N/A

Indicator(s)	Milestones / (cumulative)	Progress / (cumulative)
Number of individuals who demonstrate an increased capacity in the production, adaption and use of evidence (individual level)	24	Exceeded / 30
Evidence demonstrating that ReBUILD has strengthened capacity at the organisational level (case studies)	3	Met / 3

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has been ‘exceeded’ with one indicator exceeded and one met. Over the past year ReBUILD has supported an additional 10 people to increase their capacity in the production, adoption and use of evidence bringing the cumulative total to 30. ReBUILD researchers have facilitated session on health justice and disability inclusion. External trainers have also facilitated sessions on artificial intelligence and on mental health wellbeing. As mentioned above, an audio and video training workshop was held at the Global Symposium on Health System Research complemented by production of a four-part podcast from the symposium. Nine individuals took part in the workshop and podcast creation. In Year 5, seven capacity strengthening fund applications were submitted and approved for consortium members across different disciplines. Activities included conference attendance, research and writing skills, communications skills and introducing project management tools. Six of the seven applicants were early career researchers. Where new skills have been learned, the knowledge has been cascaded to other consortium members through virtual capacity strengthening sessions.

No new case studies on organisational level capacity strengthening were produced this year. This is in line with the cumulative milestone for output indicator 4.2 which was 3 case studies for Year 4 and remained 3 case studies for Year 5. A further case study is expected in Year 6.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output over the past year. As ReBUILD has already achieved the cumulative Year 6 milestone for output indicator 4.1 this will be reviewed and revised upwards in line with planned capacity strengthening activities for the remainder of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The Year 4 Annual Review recommended that the research uptake and communications team should continue to utilise diverse platforms to disseminate programme findings and to strengthening the capacity of ReBUILD consortium members to undertake these projects internally. During Year 5 the research uptake and communications team have led a wide range of activities including a podcast series, blog posts, panel discussions, conferences presentations and webinars. Capacity strengthening in research uptake and communications has included podcast training for ReBUILD team members before and during the Global Symposium on Health Systems Research, and support to HERD in developing and launching a Nepali language podcast series on health systems and resilience in Nepal, communications training for IfD team members as well as continuous support on writing blogs and policy briefs. HERD have also been supported to produce

The Year 4 Annual Review also recommended that ReBUILD to explore how Artificial Intelligence (AI) can be used to enhance the programmes work in relation to 1) capacity strengthening 2) synthesis and 3) research uptake and communication. As reported above ReBUILD held a three part AI training series June-July 2024. This provided an introduction to AI, AI tools (including challenges and ethical issues) and explored how AI could be used in ReBUILD work. ReBUILD will continue to explore the potential to use AI to support research communication and uptake.

The independent evaluation highlighted that ReBUILD has established a culture of mutual learning and used multi-directional, needs/capacity based and embedded approaches to significantly enhance consortium and external stakeholder capacity to produce, adapt and use evidence. Capacity-strengthening of local knowledge users, policymakers, and practitioners in some contexts will likely be a key legacy of ReBUILD, fostering locally driven, evidence-informed decision-making to enhance health system resilience.

ReBUILD has already planned to document lessons learned regarding capacity strengthening approaches (including at the environmental level to produce and use evidence) and should continue to prioritise this work. Emphasis should be placed on documenting good practices for capacity strengthening in FCAS; for example, regarding the safeguarding of researchers and participants.

## D: VALUE FOR MONEY
The ReBUILD programme continues to demonstrate strong VfM in it’s fifth year of implementation by conducting extensive equity-oriented research, influencing policy, fostering strategic partnerships and strengthening capacity effectively. Despite notable contextual challenges particularly in Lebanon and Myanmar the programme has continued to demonstrate the ability to adapt research plans in volatile settings, to use the Responsive Fund mechanism flexibly and to seize opportunities for global collaborative work. Despite budget under-utilisation, ReBUILD has demonstrated strong cost control and improved efficiency through co-financing and embedded research models. These findings have been reflected in the independent evaluation of the programme.
Looking ahead to 2025/26, ReBUILD aims to further maximise value for money by expanding virtual dissemination, and prioritising high-impact, policy-relevant research through collaboration, joint workshops, and integration of research findings into national policy planning and reform processes.
Economy: In Year 5 the programme spent £1,557,930.21 (77.5%) against a total forecast of £2,011,666.00 resulting in an underspend of £453,745.79 This was primarily the result of delays to research activities for example in Myanmar and Lebanon as a result of the volatile security situation. The largest cost category remained personnel reflecting the labour-intensive nature of research, capacity building and stakeholder engagement. As part of the fourth contract amendment ReBUILD made strategic reallocations within the budget utilising reduced travel expenditure to support staff time on the growing body of research projects. Rising inflation across all ReBUILD partner countries has led to increased unit costs. In response, LSTM have worked closely with partners to ensure that value for money principles continue to guide all financial decisions and programme delivery.
Throughout the year, meetings have predominantly been held online, with travel undertaken only when essential and planned using the most cost-effective routes. Conference attendance has remained highly selective. ReBUILD had a strong presence at Health Systems Global in November 2024 facilitating increasing brand visibility and discussion and dissemination of findings.
The independent evaluation noted multiple practical examples of ReBUILD maximising resources including use of institutional and project co-financing and use of a centralised administrative support model.
Efficiency: Over the past year, ReBUILD has continued to produce a robust and policy-relevant body of research through its learning sites, responsive fund studies and increasingly it’s synthetic work. The independent evaluation noted that leveraging co-financing and embedded research models have increased efficiency. The consortium’s adaptive management and risk mitigation strategies ensured continuity of operations and delivery of outputs despite notable volatility in Myanmar and Lebanon and funding uncertainty created by the delayed contract amendment. In Lebanon the AUB team have not moved ahead with a second learning site due to delays as a result of volatility and access constraints. Instead they will prioritise write up from learning site one and a follow-on responsive fund study on close to community providers.
The virtual delivery of most capacity strengthening activities has enabled broader participation, reaching a more diverse group of stakeholders across partner countries. Training has also been cascaded by participating individuals. Additionally, ReBUILD’s visibility has been enhanced through participation in events funded by other programmes or organisations, which has helped raise the profile of ReBUILD without placing additional demands on programme resources.
Effectiveness: The reach of ReBUILD’s research continues to expand with growing traffic to its website and engagement on digital platforms. Despite working in complex, conflict-affected and unstable settings, ReBUILD has produced a large, contextually diverse and high-quality body of evidence, which is leading to some specific changes in policy and practice. At local and subnational levels, these include contributions to health system guidelines and changes in the use of evidence for decision-making in multiple contexts. Changes have been especially well-evidenced in Lebanon and Nepal. Key ReBUILD’s work has contributed to increased awareness of the importance of evidence-based planning and use of evidence for decision making in Lebanon, Nepal and Sierra Leone. The final synthetic phase of work is expected to offer considerable added value and will likely have broad influence assuming it is completed as planned and that the uncertain global context proves sufficiently conducive to health systems strengthening initiatives.
The Mid-Term Evaluation viewed ReBUILD as having effectively delivered strong value for money by effectively conducting extensive equity-oriented research, influencing policy, fostering strategic partnerships and strengthening capacity. One of the most important conclusions regarding their VFM was that ReBUILD has demonstrated that is possible to conduct high quality research and facilitate research uptake in complex and unstable settings.
Equity: The programme is, by design, equity focused; it aims to improve access to and utilisation of effective and equitable health care for poor, vulnerable and marginalised communities and individuals living in FASP settings. Equity has been promoted in terms of both processes, the policies and operationalisation of the consortium, as well as through outcomes, with 37 research studies incorporating a gender focus, 17 research studies focused on disability inclusion and evidence of influence on policies which have enhanced attention to gender equality. The programme applies a gender, equity and justice lens to both the research process and team composition, ensuring that these principles are reflected in decision-making and delivery.
ReBUILD has continued to use an annual consortium survey and structured discussions at the annual meeting in September 2024 to reflect on its governance and partnership principles, supporting continuous improvement in equitable decision-making and management. Capacity strengthening activities in Year 5 have included a focus on disability inclusion training, leadership and communication skills for people with disabilities, and the revitalisation of women's groups and community health volunteers.

E: RISK

Overview of risk management
The overall risk level remained moderate and is within RED’s tolerance for risk, but there were spikes in specific areas due to external shocks, such as the Lebanon-Israel conflict, ongoing civil unrest and an earthquake in Myanmar, and concerns about the dismantling of USAID. The Consortium Management Committee (CMC) discusses risk monthly and reviews the risk register quarterly. The consortium demonstrated agility by adapting workplans, maintaining regular communication, and reallocating resources as needed. Safeguarding remains a moderate risk, with proactive measures in place. Financial controls are robust, with no significant control weaknesses identified. Staff turnover has been low, attributed to strong, equitable partnerships and regular engagement. A new risk was added in Year 5 reflecting the dismantling of USAID and possible implications for the consortiums work given the dependencies of health systems on US funds. Two risks were closed following review – one on delays regarding ethical approval (no new studies planned) and the transition of the partner in Sierra Leone given the length of time the new partner has now been in place. As ReBUILD enters a busy Year 6, the risk environment remains dynamic with continued operational and security concerns in Myanmar and a stabilising situation in Lebanon.

Overview of project risk and mitigation

Strategy & Context	Policy & Programme Delivery	Public Service Delivery and Operations	People	Safeguarding	Financial & Fiduciary	Reputation	Overall
Major	Moderate	Moderate	Moderate	Major	Major	Moderate	Moderate

Strategy and Context – Major
ReBUILD operates in fragile, and conflict affected settings. The past year has seen continued risks to ReBUILD activities and staff in Myanmar and Lebanon. In Lebanon, ground invasion by Israel (September and December 2024) prevented travel both within and outside the country and have resulted in plans for a second learning site to be deprioritised. The recent election of a president in Lebanon has brought some stability, but caution remains. In Myanmar, ongoing conflict, limited electricity, and an earthquake in March 2025 have exacerbated the fragile environment and forced the team to adapt workplans frequently. This year the dismantling of USAID has been added as a new risk with the potential to undermine programme outcomes and impact as a result of aid programming becoming more constrained.

Policy and Programme Delivery – Moderate
ReBUILD manages several risks in this category through established consortium-wide processes, regular reporting, and meetings to keep activities on track and address issues promptly. Some planned activities have been delayed as a result of contextual factors outside of the programme’s control. ReBUILD will need to continue to prioritise completion of studies, synthetic work and dissemination. A short no cost extension is recommended to complete synthesis and dissemination activities in order to enhance vfm. The contract amendment process was protracted and only finalised in February 2025. This created some challenge for ReBUILD which operated for a sustained period with uncertainty regarding requested changes to budget, activities and staffing. The challenge created by managing research programmes operating in fragile contexts using a contract modality has also been highlighted by the independent evaluation.

Public Service Delivery and Operations – Moderate
The programme is not involved with the delivery of consular services or the delivery of internal operations which support core business and wider HMG. However, the consortium adapted to challenges by maintaining close contact with partners, adapting travel and workplans and implementing remote and flexible working arrangements. Robust risk management systems were maintained.

People – Moderate
The main risk is staff turnover potentially delaying research and programme delivery. However, turnover has been minimal during the reporting period, with only a few role changes or staff movements across partners. The consortium’s equitable partnership approach is thought to have contributed to stability. Partnership values were reviewed in September 2024.

Safeguarding – Major
All partners understand ReBUILD’s duty to mitigate safeguarding risks and report any safeguarding concerns. At the September 2024 annual meeting, a dedicated session was held to discuss safeguarding concerns from the past year, reinforce the roles of safeguarding focal points, and review reporting procedures. Safeguarding focal points communicate quarterly, and all partners have completed safeguarding risk assessments. The environment in Lebanon and Myanmar have remained insecure and the programme has adapted travel to research sites and planned activities to maintain staff safety.

Financial and Fiduciary – Major
ReBUILD continues to demonstrate strong financial management and governance. A budget amendment was signed off in February 2025 as part of the programme’s fourth contract amendment. Inflation and currency fluctuations continue to be managed and have not impacted delivery. However significant disruptions, particularly in Myanmar and Lebanon, have resulted in delays/cancellation of activities and underspend on the FY24/25 budget. The SRO has agreed carryover of only a small portion of this underspend into the final 13months of the programme. A further budget amendment will be undertaken which will reflect the revised total contract value and no cost extension period if approved.

Reputational – Moderate
LSTM remains a valued and experienced research partner within the ReBUILD programme. The institution brings a strong track record of working with FCDO and demonstrates robust governance and ethical oversight. Its established systems and policies ensure compliance with FCDO standards, particularly in relation to financial accountability, safeguarding, and the appropriate use of funds. LSTM’s understanding of donor expectations and its commitment to transparency and responsible stewardship of resources help to mitigate reputational risk for the programme.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Delivery: ReBUILD is co-led by LSTM and QMU. LSTM has overall contractual and management oversight of the research programme consortium. Partners include American University of Beirut, Lebanon; Burnet Institute, Myanmar; HERD International, Nepal; and the Institute for Development, Sierra Leone. There are two affiliate partners Oxford Policy Management and International Rescue Committee. The transition of partners in Sierra Leone has been managed well and the risk relating to delivery has now been removed from the risk register. Partnership principles and management processes were reviewed in September 2024 to maintain equity and engagement across all partners.

ReBUILD has exceeded its delivery targets for the year, demonstrating strong performance across all output indicators. This is despite Output 3 targets being revised upwards following the Year 4 Annual Review. The programme’s management approach enabled rapid adaptation to contextual risks, such as the conflict in Lebanon (September and December 2024) and ongoing conflict, operational challenges and the earthquake in Myanmar. In response to emerging challenges, workplans were adjusted to account for security risks, with remote working arrangements and the engagement of local consultants ensuring continuity of operations in Lebanon. Adaptations have included adjusting research timelines around political events and security concerns, as well as making use of the Responsive Fund to redirect resources to emerging research priorities and opportunities that could be implemented despite contextual challenges.

Regular working group meetings and a quarterly research forum are used to advance research studies and uptake activities which has supported progress on cross-country products and joint conference presentations in Year 5.

FCDO continues to receive timely quarterly narrative and financial reports from ReBUILD and meets quarterly to discuss progress and resolve challenges. The Consortium Advisory Group (CAG) only met once in 2024/2025 but is due to meet in July 2025. Some CAG members are engaged in specific pieces of ReBUILD work or have offered expertise on different topics, including reviewing proposals to the Responsive Fund.

ReBUILD have an ambitious programme of research studies, products and dissemination planned for Year 6 with some write up and dissemination including for the second learning site in Nepal expected to be curtailed by existing contract timelines. ReBUILD have requested a three month no cost extension to the programme to maximise the delivery of cross-country synthesis work and dissemination activity at sub-national to global level. The SRO and PRO have reviewed this request and recommended from an impact and VfM perspective.
Commercial: A fourth contract amendment between FCDO and LSTM was finalised in February 2025 reprofiling the spend while retaining the original contract value. This followed a protracted process because of FCDO staffing changes, pressure on commercial resources, and the extent and nature of requested budget changes. Headline amendments made include update to the named CEO, and reprofiling of the budget including addition of new posts to support delivery, adjustment of time allocations for some staff, and movement of funds between partners. An exit plan was also developed in line with FCDO requirements. ReBUILD have requested a three month no cost extension. If approved a fifth contract amendment will be undertaken and the remaining budget reprofiled.
Financial Performance:. As of 31 March 2025, ReBUILD has spent £5,118,287.61 (66%) of the £7,682,203 contract value. In Year 5 (April 2024-March 2025) the programme spent £1,557,930.21 (77.4%) against a total forecast of £2,011,666.00 resulting in an underspend of £453,735.79. This was primarily the result of delays to research activities for example in Myanmar and Lebanon as a result of the volatile security situation. ReBUILD has requested to carryover £80,000 from FY24/25 to support activities that were delayed but will be delivered in FY25/26. FCDO are reviewing this alongside the request for a three month no cost extension. If approved this and a revised overall contract value will be reflected in a fifth contract amendment.

Invoicing has been paid quarterly in arrears and provided on time every quarter. LSTM has demonstrated effective financial management control supported by a robust due diligence system and spot checks on quarterly expenditure with partners to ensure compliance with the programme and budget guidelines. Despite efforts to adapt research plans, the combination of external shocks, political instability, and contract amendment delays have affect budget utilisation rates and have resulted in notable variance from budget forecasts. Disruptions at country level have not only affected overall budget utilisation but also the proportion of the budget going to LMIC partners, since in-country work could not progress at the intended pace. However, even in the context of systematic underutilisation of budget the programme has shown sustained attention to cost control.

Partner Performance: LSTM has demonstrated strong programmatic and financial management and the consortium has continued to apply adaptive management to external shocks. Partners submit monthly and quarterly narrative reports which are reviewed at monthly CMC meetings where all partners are represented. The monthly CMC meetings have been used to support inclusive decision making including on the difficult decision to not pursue the second learning site in Lebanon. All partners continue to deliver against planned research, capacity strengthening and research communication and uptake activities.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring
ReBUILD maintained a comprehensive and adaptive monitoring and evaluation system, underpinned by regular field visits, monthly and quarterly reporting, and participatory engagement with stakeholders and beneficiaries to discuss ongoing research activities, co-design new research studies and research uptake plans. Learning loops, supported by sense-making meetings and participatory action research, ensured that the programme remained responsive to evolving local contexts. The Responsive Fund has also been used effectively to enable research response to emerging opportunities and priorities.
ReBUILD held it’s annual meeting in Sierra Leone in September 2024. This provided the opportunity for consortium members to visited learning sites in Moyamba and Kailahun,. Plans for the SRO and PRO to attend were revised due to personal circumstances but FCDO’s Health Adviser in Sierra Leone attended. The annual consortium survey findings were discussed, supporting the review of equitable partnership principles and further strengthening inclusive decision-making and management processes.
FCDO receives quarterly financial and narrative reports from ReBUILD and holds quarterly meetings to review programme delivery and address emerging issues including conflict in Lebanon, civil unrest and an earthquake in Myanmar. In addition, FCDO participates in the semi-annual gCAG meetings, which provide technical and strategic advice to the programme. Following the Year 4 Annual Review, indicators for output 3 were revised upwards.
A major MEL milestone in Year 5 was the independent evaluation of the programme, commissioned by FCDO to support learning and accountability. The ReBUILD consortia engaged closely with the independent evaluators between November 2024 and April 2025. This evaluation provided an external assessment of ReBUILD’s relevance, effectiveness, efficiency, sustainability and value for money. The annual review process itself has been led by the SRO and PRO, incorporating some of the findings and recommendations from the evaluation.
Evidence
This is a research programme which in and of itself is generating evidence relevant to building more responsive, effective, inclusive, gender-equitable and sustainable health systems in fragile and shock-prone settings. The breadth of this evidence is captured in the programme’s theory of change and logframe and commented on in Section C of this review. Disaggregation of data is occurring. Integration of ‘leave no one behind’ into the research agenda itself is clear, and gender equality, disability and social inclusion continues to be a key theme embedded within the programme (see output indicator 1.2). Routine application of a gender equity and justice lens within research projects was confirmed by the independent evaluation/

The independent mid-term evaluation rated the quality of research generated by ReBUILD as very good, based on a sample of three completed research projects led or co-led by core partners in a range of countries. All three projects scored well across criteria, with especially high scores on relevance, research design, research implementation and user engagement.
Evidence generated is disseminated through policy briefs, synthesis documents and presentations, ensuring accessibility for decision-makers and supporting the translation of research into action at national, regional and global levels. ReBUILD has contributed to some specific changes in practice and policy, some of which have enhanced attention to gender equality. ReBUILD is on track to further contribute to outcomes assuming the timely completion and dissemination of synthetic work.
Learning
Over the past year, the ReBUILD programme has demonstrated resilience and adaptability in the production of a body of policy-relevant and equity-oriented research and development of new models and tools for health system resilience in FASP settings. ReBUILD has effectively adapted to significant contextual changes and promoted care to ensure the safety of researchers and participating communities while working in unstable and conflict-affected settings. This has included adaptation of research plans in Lebanon to focus on findings from the first learning site and opportunities to expand on responsive fund research, as well as adaptation of plans and timelines in Myanmar in response to ongoing unrest and the earthquake.
By design, the consortium was also set-up to allow funding of opportunistic studies via the Responsive Fund[2]. This flexibility has allowed ReBUILD to respond to emerging topics at both country and global levels. Examples of research topics that emerged inductively have been the role of non state actors (case studies in Myanmar and Afghanistan), exploring health system resilience in post-conflict Tigray following the close of the humanitarian period the role of the diaspora in health system resilience, and the implications of reducing aid budgets for FASP settings. ReBUILD has also been responsive to FCDO demands for evidence and developed new research questions in response to country needs. Examples include exploring climate change (in Nepal and Bangladesh) and disability inclusion in Myanmar. The independent mid-term evaluation has recommended FCDO encourage strategic use of flexible funding mechanisms, such as a responsive fund, to support adaptation for research and research uptake in future research consortia.
[2] The Responsive Fund is open to all partners and associate partners via an internal application process, as a mechanism to conduct research at the request of a policy maker, or to conduct research that may lead to multiplier funding. Applications are reviewed by a selection panel made up of CMC members and one external reviewer. Selection criteria include alignment with ReBUILD’s overall research question, theory of change and resilience framework, expertise of team, potential for impact, value for money, capacity strengthening and ReBUILD values.

Conclusions from RPC Mid-Term Evaluation
- ReBUILD has set forth an ambitious, timely, policy-relevant and equity-focused research agenda and a strategic approach for achieving it, combining locally-relevant research with synthetic work for wider impact across FASP settings.
- Despite working in complex, conflict-affected and unstable settings, ReBUILD has produced a large, contextually diverse and high-quality body of evidence, which is leading to some specific changes in policy and practice.
- The final synthetic phase of work offers considerable added value and will likely have broad influence assuming it is completed within the RPC timeframe as planned and that the uncertain global context proves sufficiently conducive to health systems strengthening initiatives.
- ReBUILD has demonstrated that it is possible to conduct high quality research and facilitate RU in complex and unstable settings. Key to ReBUILD’s success has been a flexible approach and continuous process of adaptation and learning with regards to the research, RU and overall functioning of the consortium.
- ReBUILD has established a culture of mutual learning and used multi-directional, needs/capacity-based and embedded approaches to significantly enhance consortium and external stakeholder capacity to produce, adapt and use evidence.
- ReBUILD's strategic partner selection and collaborative approach have fostered a strong, well-balanced consortium that has enabled the efficient delivery of significant outputs, multi-country studies and synergies.
- ReBUILD has built an equitable partnership with inclusive governance and management structures that promote transparency, shared leadership, and decision-making. The initiative has shown strong commitment to ongoing consultation, reflection, and action to improve and sustain these practices. While collaboration with individual CAG members on specific outputs has been effective, the group as a whole has lacked a strategic focus.
- ReBUILD’s achievements in strengthening capacity, fostering strategic partnerships, and significant efforts in RU and communications have created a robust foundation for securing future investment and building a legacy in research on health system resilience in FASP settings.
- ReBUILD has delivered strong VfM by effectively conducting extensive research, influencing policy, fostering partnerships, and maintaining cost-efficiency across fragile settings, despite financial and contextual challenges.
- Research in volatile contexts will inevitably carry a higher risk of underspend and a higher need for flexible research funding. A key performance indicator (KPI) of 10% budget variance may be inappropriate in this context. The commercial contract modality presents certain limitations, particularly in relation to the flexibility of moving funds and the time required to process contract amendments. These factors have contributed to inefficiencies and operational challenges across the consortium.

Date of last narrative financial report	April 2025	Date of last audited annual statement	December 2024