## Annual Review Template

Title: Affordability of Food & Finance in Yemen (AFFY)
Programme Value £ (full life): £19m		Review date: July 2025
Programme Code: 301137	AMP start date: 11 May 2022	AMP end date: 31 March 2026

Summary of Programme Performance
Year	2023	2024	2025
Overall Output Score	A	A	A
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	D0001182.odt
DevTracker Link to results framework:	To be added

## A: SUMMARY AND OVERVIEW

Description of programme

Yemen’s protracted conflict has resulted in one of the world’s most severe humanitarian and economic crises. The economy remains fragile, drained of foreign reserves, cut off from oil revenues, and weakened by economic warfare and institutional fragmentation. Hard currency shortages and limited policy capacity have in part driven the costs of food and basic goods higher, placing millions at risk of famine. This undermines Government of Yemen (GoY) legitimacy and provision of effective service delivery. Reducing food insecurity requires addressing these structural drivers of economic collapse alongside humanitarian interventions.

The UK’s Affordability of Food and Finance in Yemen (AFFY) programme, now in its third year, is the principal instrument for supporting macroeconomic stabilisation and institutional recovery. Building on the previous UK Conflict, Security and Stability Fund (CSSF)-supported Economic Stabilisation Project II, AFFY works in Government of Yemen (GoY)- controlled areas only to deliver coordinated technical assistance to key Yemeni institutions—including the Central Bank (CBY-Aden) and Ministry of Finance (MoF)—while also supporting data generation, donor engagement, and early-stage economic recovery. It operates across four strategic pillars: (1) data and analysis to inform decision-making; (2) macro-fiscal and monetary reform support; (3) policy coordination via the Executive Bureau (EB); and (4) donor influence through platforms such as the World Bank-administered Yemen Fund (YF). AFFY is central to the delivery of FCDO’s Country Business Plan Pillars 1, 2 and 3 and complements wider international efforts to preserve economic governance.

Summary supporting narrative for the overall score in this review

The AFFY programme has maintained a strong performance trajectory in FY2024/25, delivering on its mandate despite rising political and operational constraints, including the Red Sea attacks by the Houthis, the US FTO designation of the Houthis as a terrorist organisation and the continuous politicisation of the banking sector. The programme’s resilience and ability to continue to deliver is particularly notable in the context of escalating economic warfare, where economic tools are increasingly used as instruments of political pressure, undermining institutional functionality and private sector stability.

The programme maintained an overall “A” score. Performance was strong across most outputs, particularly those contributing to macroeconomic stability and donor coordination. Continued progress within this programme will depend on deeper political engagement and conflict sensitivity, strengthened delivery partnerships, and improved institutional ownership across key government entities.

Key achievements include the World Bank Yemen Fund’s transition into a key recovery instrument with increased donor contributions and technical delivery mobilising over $26 million to date in recovery financing since its inception; sustained macroeconomic reform support to the CBY and MoF including public finance management reforms, capital adequacy requirements and regulation and AML/CFT regulations under challenging economic and political conditions. There has been evidence-based policy engagement through the Executive Bureau and IGC partnership including policy diagnostics on remittances, fisheries, and electricity; enhanced economic data transparency through the Yemen Economic Tracking Initiative (YETI) —the only publicly available real-time economic data source in Yemen. The piloting of a small-scale livelihoods initiative on solar cold-chain systems in the fishery sector with promising early results and an expansion of the pilot. While some disruptions—particularly to MoF support under PRAGMA affected consistency of delivery, these were mitigated through proactive adjustments to the support provided, diplomatic engagement on the political challenges and the reallocation of resources.

Major lessons and recommendations for the year ahead

Key lessons
Strategic diagnostics are most effective when paired with early operational planning. While the YF delivered high-quality diagnostics such as the Climate Change and Development Report (CCDR), Financial Sector Diagnostic (FSD), and Aden (electricity) Master Plan (AMP), stakeholders consistently noted that these products gained traction only when linked to concrete planning processes or follow-up technical assistance. The CCDR, for instance, triggered donor interest and sectoral dialogues because it was immediately followed by climate resilience initiatives. This illustrates that diagnostics must not be treated as standalone outputs but as strategic entry points that require downstream investment pathways and national validation.

Political engagement is critical for policy reforms. Reform implementation in Yemen cannot rely on technical design alone; it must be supported by sustained political engagement, based on a strengthened approach to understanding the political economic, conflict and gender dynamics. PRAGMA’s experience with the MoF (Ministry of Finance) and the Yemen Fund experience demonstrates that technical consensus is insufficient when institutional incentives and accountability mechanisms are weak. For example, the Aden Masterplan provided a technical solution to the electricity issues in Aden but lacked understanding of the political economy to deliver ambitious reform in the electricity sector. Donor agencies, including FCDO, must proactively engage with senior political actors to convert technical plans into actionable policy reforms, as a prerequisite to technical engagement.

Contextual adaptation matter. Delivering training and policy inputs to GoY line ministries is most effective when grounded in Yemen’s operational context. Support needs to be customised to GoY needs, such as considering the absorption capacity of staff and recognising the role of political dynamics when designing policy inputs – vested interests exist both in the recruitment of civil servants and their willingness to enact or follow through on training and policy advice.

Donor dependency threatens institutional continuity. Despite delivering high-value outputs, Executive Bureau’s (EB) ability to retain advisors and sustain momentum continues to be an issue due to over dependency on a single donor (FCDO) funding its activities and limited diversification in funding sources. The EB has lacked contingency plans or financial buffers, and has only recently prioritised expanding its donor base, exposing its structural fragility given FCDO and wider donor cuts. Future technical support should include sustainability strategies—such as phased cost-sharing with GoY and other donor partners, or/and a move towards national budget integration—to reduce aid dependency and preserve institutional continuity.

Data-driven trend monitoring is essential. UN Verification and Inspection Mechanism for Yemen’s (UNVIM) inspection volumes offer a unique window into Yemen’s economic activity and port functionality. Tracking fuel and cargo flows over time can serve as a proxy indicator for economic resilience and recovery trends. However, measuring higher-level outcomes such as the disruption of illicit smuggling networks remains a challenge without clear, attributable metrics.

Key Recommendations
FCDO and programme partners should invest in regular and problem/institutional-specific political economy, conflict sensitivity and gender analysis to better understand the political dynamics and apply this to ensure AFFY and its partners are strategically and operationally responsive and conflict sensitive to risks/opportunities, while integrating it into monitoring, evidence and learning (MEL) approaches. FCDO should engage with partners to ensure they have a strengthened approach to the areas above, including that the requisite expertise is firmly embedded, including sharing lessons and best practice.

Preparing for a lower ODA and development-oriented operating environment. AFFY should scale up (in line with its theory of change) to test how its support for livelihoods-focused programming could be delivered in the future UK Spending Review period (26/27 - 28/29). Use 25/26 to develop a new programme that will begin in 26/27 (subject to ODA funding) to help transition from humanitarian to durable development solutions while strengthening their resilience and ability to deliver for the people of Yemen in GoY controlled areas. In addition, identifying ways to move along the humanitarian-development-peace nexus. In doing so, AFFY should also expand its network of delivery partners to reduce operational risks and over-reliance on a narrow group of implementing partners.

Prioritise operationalisation of flagship diagnostics grounded in the political economic reality of Yemen. WB should prioritise follow through on high-impact reports—such as the Aden (electricity) Master Plan and Financial Sector Diagnostic—by integrating their recommendations into grant financing, technical assistance and private sector funded activities. This can involve preparing policy notes, funding catalytic pilots, providing implementation support to national authorities and expanding institutional capacity building to cover IT and infrastructure within public institutions to deliver the full effect of key reforms.

A shift towards recipient-executed projects to enhance impact and ownership. The WB should prioritise a shift from primarily Bank-executed diagnostic activity to recipient-executed projects. This approach builds national ownership, strengthens institutional capacity, and ensures that diagnostics translate into tangible delivery. While more complex to embed reforms within Yemeni systems, it is more likely to achieve long-term impact.

Leveraging FCDO’s political role to complement the World Bank’s technical engagement. FCDO Yemen should use its diplomatic access and political influence to support high-level buy-in for reforms advanced through the YF. Strategic engagements with senior government counterparts can help reinforce traction and strengthen national ownership of policy and institutional change.

Ensure UK’s financial contributions to YF are directed towards delivering UK priorities in Yemen, while also holding the GoY accountable for implementing policies/reforms. FCDO should agree new set of indicators to measure and verify UK-funded activities delivered under YF are directly delivering against UK priorities in Yemen.

Improve reform uptake and momentum through political-level engagement through Yemen Partner Technical Team (YPTT) and Yemen Partner Group (YPG) structures. FCDO should engage senior Government of Yemen (GoY) and Presidential Leadership Council (PLC) counterparts to ensure that agreed reforms are implemented and not blocked by internal resistance. Direct advocacy and follow-up should accompany technical support.

Engage political leadership to elevate EB’s role. The EB’s contributions must be better understood and leveraged by Yemen’s political leadership. FCDO should engage the Prime Minister’s Office and PLC to clarify the EB’s strategic role, increase visibility of its contributions, and promote its integration into core government decision-making frameworks.

FCDO should explore alternative UK funding for UNVIM. In the context of transition to a lower ODA budgets and prioritising supporting humanitarian cash recipients’ graduation from humanitarian assistance, FCDO should explore alternative ways and resources beyond AFFY to support UNVIM.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change infers that if FCDO invests in capacity building support to key economic institutions in Yemen, they will be preserved and strengthened, and progress will be made on immediate economic de-escalation issues. This in turn will contribute to short-term economic stability and reduce humanitarian needs, while increasing the likelihood of a sustainable peace process that gives due consideration to the economic drivers of conflict and economic incentives for peace. The AFFY Theory of Change was created on the assumption of no minimum level of capacity building, and that any support FCDO can provide to Yemeni institutions can support the overall desired impact. In addition, with FCDO investing in establishing the World Bank Multi-Donor Trust Fund (Yemen Fund - YF) donors will make contributions, increasing the likelihood of creating incentives for peace, and for eventual reconstruction, recovery, and reform programmes succeeding and benefitting the whole of Yemen. Thus, the YF becomes an effective forum for the international community to engage with the Yemeni authorities on reconstruction and development—given its usage as a mechanism to engage with GoY institutions on the ground through capacity building activities, in addition to providing the financing architecture, and the international donor support to effectively address the wide range of risks to Yemen’s long-term stability. Additionally, UK coordination with likeminded partners and participation within donor working groups enables FCDO to understand the landscape of development activity taking place in Yemen and closely monitor this to reduce the risk of duplicating efforts.

In FY 2024/25, AFFY programme continued to operate under the original Theory of Change as articulated in the approved business case, with no changes to the impact or outcome(s) indicators. However, serval amendments were made to indicators under all outputs in AFFY log-frame. This includes adding new indicators i.e. indicators for activity delivered through Mercy Corps or amending existing ones i.e. USAID/PRAGMA, WB, ACAPS and IGC to reflect changes in context, activity being delivered and delivery mechanisms. Additionally, revisions to the ambition of targets took place to reflect Government of Yemen (GOY) capacity and advice received from implementing partners.

The programme logic remains grounded in the premise that strengthening Yemen’s macroeconomic institutions, reducing political and economic frictions, and improving access to external financing will enable the GoY to mitigate economic shocks, sustain basic service delivery, and reduce food insecurity over time. To maintain and accelerate momentum, a one-year extension has been requested for FY2025/26 to scale up delivery in line with GoY priorities and supported by the UK’s recent Yemen Country Development Diagnostic (CDD), Joint Analysis of Conflict and Stability (JACS) and FCDO Yemen’s 2024 Gender Equality and Social Inclusion strategy. The extension focusses on a gradual shift from humanitarian aid to economic development and resilience and a strengthened approach to conflict sensitivity and gender. This extension — accompanied by deeper coordination with the IMF, World Bank, and key delivery partners through the Yemen Partners Technical Team (YPTT) structures — will ensure AFFY remains an agile, gender and conflict sensitive high-impact platform capable of responding to Yemen’s pressing needs while aligning international financing with reform and recovery goals.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The AFFY programme is on track to contribute to its expected impact from the data available. The programme’s impact is measured by the percentage of the population in IPC Phase 3–5 (emergency food assistance levels) in areas under the control of the GOY (due to Houthis restrictions that prevent IPC data reporting from areas under their control). The latest report, for the period October 2024 – March 2025, states that 45% of the analysed Yemeni population will likely experience high acute food insecurity (IPC phase 3+) [4,634,928, a marginal increase from 4,558,000 in FY2023/24]. Whilst this is an improvement from the 55% baseline in the AFFY logframe which was based on IPC levels projected from June-December 2022, subsequent IPC reports have only shared data from GoY controlled areas; data from Houthi-controlled areas have not been available since the October-December 2022 report. As around 70% of Yemen’s population resides in Houthi-controlled areas, impact at this stage will be better determined once the relevant data becomes available. However, according to the 2025 Yemen Humanitarian Response Plan covering the whole of Yemen, 19.5 million people (1.3m more than last year) face severe food insecurity (IPC Phase 3 and above), and 6 million experience emergency levels (IPC Phase 4). From this data, food insecurity has not decreased (significantly), but rather stagnated and is at risk of further deterioration as humanitarian spend is cut and the delivery of food aid continues to be constrained in the north.

Given the transition to a lower ODA environment and the continued high levels of needs in Yemen, AFFY should test how to accelerate graduation of beneficiaries of humanitarian cash assistance through income-generating activities and livelihoods activities.

Progress against the AFFY programme’s outcomes are as follows:

Outcome 1: Reducing volatility of the Yemeni rial in the south and ensuring that monetary emissions remained within targets. AFFY’s TA to the Central Bank of Yemen’s (CBY-Aden) supported the implementation of reforms such as a rules-based monetary policy framework ensuring base money growth remained below GoY targets. This contributed to exchange rate avoiding sharp spikes and helped reduce day to day volatility – however the rial continues to depreciate and is currently well above the programme target of 1500 YER to USD. AFFY TA to CBY-Aden resulted in the reviving and modernisation of the FX auction systems. This improved liquidity of hard currency and supported GoY in monitoring the circulation of the Yemeni rial in the market. The Yemeni rial continues to depreciate driven by worsening trade imbalances as oil exports remain halted, constricting oil revenues, while customs revenues have fallen widening the fiscal deficit.

Outcome 2: Confidence in institutions to manage resources and deliver reforms is strengthened, and access to external finance is improved. AFFY support built capacities within CBY-Aden and MoF in area such as Monetary Management Reform; Foreign Reserves and Exchange Management; Payments Systems Reform; AML/CFT; Bank Supervision; Access to Finance; Revenue Forecasting; Tax Policy; Tax Administration; Debt Planning and Management; and Budgetary Planning and Budget Implementation. All essential in building confidence in GoY’s institutional capacities and supported Yemen in the mobilisation of external finance. As a result, foreign exchange reserves available to CBY-Aden reached USD 775 million, exceeding the programme’s target of USD 600 million—largely driven by KSA’s disbursal of USD 1 billion. On the other hand, two outcome targets were missed. USD 432 million in Special Drawing Rights (SDRs) were converted by end-December 2024 below the planned USD 462 million. In addition, USD 7.5 million in frozen bank reserves were unfrozen against a target of USD 9 million.

Outcome 3: Reduced economic frictions through economic de-escalation between the parties. Fuel flows through Yemen’s seaports remained relatively stable despite the escalation in Red Sea hostilities. The volume of fuel imports exceeded 2.2 million metric tons, surpassing the programme’s annual target and suggesting economic frictions in a key part of the economy have not materialised. However, the US FTO designation of the Houthis in March 2025 and strict rules around fuel importation render the volume of fuel imports as an indicator of economic friction between the parties meaningless. The outcome indicator on fuel flows will be replaced and instead show support to economic activity which reduces economic frictions.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The AFFY programme should continue implementing activities in 2025/26 through a one-year extension to support the HMG’s Yemen objectives and the broader humanitarian system in Yemen. AFFY has had demonstrable impact on three of the current Country Business Plan Campaign goals: 1) promoting a sustainable, inclusive, de-escalation and resolution of the Yemen conflict, including through the Yemen Peace Process; 2) alleviating the humanitarian crisis, rebuilding resilience and supporting early recovery; 3) preventing further economic deterioration whilst supporting economic stability and recovery. AFFY is delivered in coordination with other Yemen FCDO programmes, including humanitarian (food security), conflict stabilisation, and monitoring and evaluation activities.

The programme also supports UK’s continued leadership on the economy, influence international financial institutions including the IMF, and strengthened our strategic partnership with key partners, including the US and Saudi Arabia, and likeminded donors.

## C: DETAILED OUTPUT SCORING

Output Title	Newly established YEMEN FUND is well-developed & funded: leading to key assessments, improved coordination & laying groundwork for recovery
Output number:		1	Output Score:	A
Impact weighting (%):		72	Weighting revised since last AR?	Yes, up from 50

Indicator(s)	Milestone(s) for this review	Progress
Number of additional donors contributing to the trust fund	2	2, Met expectations
World Bank Results Framework milestone achievement rates (annual)	At least 80% of output level indicators achieved	83% of output level indicators were achieved; met expectations:
World Bank evidence pieces that are published and disseminated, i.e. WEE, CCDR, AMP	6	9; Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

In its third year of implementation, the Yemen Fund (YF) - managed by the World Bank as a Multi-Donor Trust Fund - delivered significant institutional, analytical, and coordination outcomes transitioning from foundational setup to delivering sectoral depth, strategic influence, and growing alignment with recovery priorities in Yemen. During FY2024/25, the YF disbursed across four interlinked strategic pillars:
Inclusive service delivery & governance - Under Pillar 1, the YF provided technical support to the Social Fund for Development (SFD) that enhanced social protection systems, integrating climate- and gender-sensitive approaches into Cash-for-Work and Cash-for-Nutrition programs while promoting long-term resilience. This equipped SFD and its partners to deliver improved food security and livelihoods support. Additionally, The YF enabled the GoY to conduct a comprehensive payroll assessment, which informed ongoing reform priorities and supported the design of internal systems. Under this pillar, the YF provided technical support to MoEE* laying the groundwork for a 20-year electricity master plan and private sector engagement strategy. Finally, the YF delivered detailed resilience assessments of urban and rural water and sanitation infrastructure, identifying critical gaps in institutional capacity and promoting a shift from emergency response to sustainable development. Meanwhile, it offered a climate-risk-informed assessment of Yemen’s road network, vital to food security.

Equitable economic opportunities & jobs - Under this pillar, the YF worked on revitalizing the financial sector, enabling private sector growth, supporting women’s entrepreneurship, and enhancing youth employment prospects. The YF helped strengthen the CBY-Aden institutional capacity, focusing on regulatory reforms, AML/CFT* compliance, and financial inclusion. This included developing a financial inclusion roadmap with the Arab Monetary Fund and advancing digital payment infrastructure. The YF facilitated the adoption of a widely referenced Financial Sector Diagnostic and informed the design of a major IDA-financed Financial Market Infrastructure Project scheduled for 2025. Moreover, the YF provided technical support to national institutions—including PMO*, MOPIC*, and sectoral ministries—on investment planning and Public-Private Partnership (PPP) readiness. Activities included a review of State-Owned Enterprises (SOEs), development of a PPP policy framework, and multi-sector trade competitiveness analysis to boost exports and reduce food import dependency. High-level engagements facilitated by the YF including convening a meeting in Geneva between GoY and WTO to discuss Yemen’s position in relation to the WTO Trade Facilitation Agreement led to Yemen’s re-entry into WTO mechanisms and the launch of a Trade Facilitation Agreement ratification process. On gender, the YF targeted women’s economic empowerment, building on the “Power in Perseverance” report published in June 2024 thanks to YF, and conducted stakeholder consultations and workshops to address systemic barriers to women’s entrepreneurship. Building on these efforts, FCDO will continue to support GoY to help it unlock private sector led growth which is integral to creating jobs. The banking sector remains the backbone of business activities in the private sector and supports investment flows, and we will continue to support the CBY-Aden. Support to other national institutions will also continue to create the enabling environment for economic opportunities and jobs.

Green reconstruction - Under this pillar, the YF worked on strengthening climate-informed development and addressing Yemen’s pressing water security challenges. The Country Climate and Development Report (CCDR), launched at COP29 in December 2024, provided a strategic foundation for aligning climate resilience with national development priorities. The CCDR generated broad engagement from government, civil society, academia, and the private sector. It has since been adopted as a national strategy and is already influencing World Bank operations, particularly in the water and food security sectors. The CCDR also marked a symbolic milestone—the first World Bank report officially presented in Yemen in a decade—signalling renewed engagement and trust with the GoY.

Transition & programme enablers - Under this pillar, the YF strengthened the foundational systems and enabling environment necessary for effective programming, institutional resilience, and peacebuilding. YF advanced national statistical capacity by supporting the Central Statistical Organization (CSO) in producing core data products such as Consumer Price Index (CPI), poverty, and population estimates—critical for planning and targeting interventions. YF also helped operationalise the Household Budget Survey (2025) and fostered a community of practice among donors through the Data and Information Group under the Yemen Partners Technical Teams (YPTT). Complementarily, a portfolio-level Monitoring Agent (MA) was initiated to improve data collection and oversight, while the Yemen Economic Monitoring grant deepened macroeconomic analysis and informed key policy discussions, including the “Peace Dividends” framework with the Office of the UN Special Envoy of the Secretary-General for Yemen (OSESGY) to support conflict resolution and de-escalation. This support to OSESGY is now a stand-alone grant to provide on-demand ad-hoc support OSESGY’s peacebuilding efforts. Efforts to integrate conflict sensitivity, gender equity, and environmental safeguards were also significantly scaled. The establishment of the multi-sector Yemen Peacebuilding Support (PBS) Facility and the development of the Peace and Inclusion Lens (PIL) handbook further established a framework for systematising an integrated, multi-sector approach to incrementally incorporating peacebuilding objectives into the design process of new WBG operations in Yemen. The YF was used to delivered training to over 200 practitioners on labour risks, sexual exploitation and abuse/sexual harassment (SEA/SH), and operational safeguards, enhancing capacity for inclusive and responsible project delivery.

In FY24/25, the YF mobilised over USD 26 million in contributions welcoming one new donor, Switzerland, joining the UK and the Netherlands as contributors, growing total donor engagement to three. These additions signify strong donor confidence in the YF’s governance model and strategic relevance. The onboarding of a new donor was realised through strong bilateral engagement and visibility of flagship products, such as the CCDR and FSD*.
The YF delivered and publicly disseminated nine major knowledge products in FY2024/25. Flagship products demonstrated strong uptake: Yemen Climate Change and Development Report (CCDR) COP29 was adopted by the GoY, presented to the Prime Minister, and influenced water and energy programmes. The FSD* led to operational changes within the Central Bank of Yemen related to licensing, AML/CFT*, and digital finance. Moreover, the diagnostic informed the World Bank’s payment system reform project, due to be IDA-funded and launched later in 2025. The Women’s Entrepreneurship study shaped plans for vocational business centres and was cited at major forums. Additional assessments—on the private sector, payroll, water, and statistics—fed into future IDA programming and shaped Government of Yemen strategies. Dissemination was enhanced through structured events, such as the donor roundtables and technical presentations held in Jordan and remotely. The growing influence of these products has improved the fund’s profile as a strategic knowledge and reform partner. As a result, YF is actively laying the foundations for long-term recovery programming, including integration with IDA pipelines and national systems planning.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

For FY24/25 the target for indicator 1.1 was amended from “1 additional donor contributing to the trust fund”, to 2. The Netherlands joining the YF in FY23/24, earlier than expected, and Switzerland joined in FY24/25. Impact weight of output 1 was revised upward from 50% in Year 2 to 72% in Year 3 to reflect the growing share of resources from AFFY towards the YF as the main delivery lever.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR are as follows:

1.1. Given the unpredictability of programming in Yemen, the WB suggestion of embedding contingencies into the YF’s workplan merits consideration if it can be worked within FCDO programming rules. Achieved, the YF has proactively integrated adaptive programming and contingency measures into its operational model, responding to the recommendation to account for Yemen’s unpredictability. YF applied phased and hybrid approaches, allowing reallocation of funds from paused to active activities.
1.2. WB continued to manage the YF in a flexible manner and adapt when strands are not moving forward, such as reallocating spend. Achieved, YF’s phased, and hybrid approach allowed for funds to be reallocated from delayed or paused activities to more feasible or higher-priority interventions. This flexibility was supported by continuous monitoring, risk assessments, and adaptive management strategies that ensured timely programme delivery despite Yemen’s highly fluid operating context.
1.3. FCDO Yemen revised Indicator 1.1 on the number of conversations with potential donors. This was fit for purpose when the YF first launched, but now that new donors have joined it is important to update how we measure progress with potential donors beyond the number of discussions. Achieved.
1.4. FCDO assessed YF annual review progress against the Results Framework as it is in November, 6 months before AFFY’s annual review is due. Achieved.
Lessons Learned:

  1. Strategic diagnostics are most effective when paired with early operational planning. While the YF delivered high-quality diagnostics such as CCDR, FSD, and AMP, stakeholders noted that these products gained traction only when linked to concrete planning processes or follow-up technical assistance.

  1. Multi-donor trust funds can be a resilient delivery mechanism in fragile settings but require careful political analysis to ensure effective and conflict sensitive delivery. The YF model proved particularly effective in Yemen’s politically fragmented context by enabling pooled funding, shared risk, and coordinated delivery. YF’s governance through the Partnership Council ensured donor visibility and inclusive oversight. However, the politically fraught environment of Yemen means activities in politically sensitive areas, such as customs or electricity, require upstream consideration of the political feasibility of a settlement that allows progress in these areas, an emphasis on the political dialogue and bargaining aspects, and a strong focus on conflict sensitivity.

  1. National ownership is strengthened through early government engagement and policy co-creation. Outputs that were co-developed with Yemeni institutions—such as the Fisheries PPP Framework or the Aden (electricity) Master Plan—showed greater policy relevance and potential for uptake. This reinforces the importance of not only consulting line ministries, but embedding them in the research design, validation, and dissemination phases. Co-ownership fosters legitimacy and improves prospects for institutional adoption, even in contexts with weak implementation capacity.

  1. Leveraging the one World Bank approach. Stronger collaboration between the WB and IFC is opening pathways for joint analytics and potential private sector investment. Closer engagement between the WB and IFC has fostered integrated approaches, particularly relevant for private sector revitalisation and financial inclusion efforts.

Recommendations for Year Ahead:

  1. Prioritise operationalisation of flagship diagnostics grounded in the political economic reality of Yemen. WB should prioritise follow through on high-impact reports—such as the AMP and FSD —by integrating their recommendations into grant financing and technical assistance pipelines. This may involve preparing policy notes, funding catalytic pilots, providing implementation support to national authorities and expanding institutional capacity building to cover IT and infrastructure within public institutions essential for the delivery for key reforms.

  1. A shift towards recipient-executed projects to enhance impact and ownership. The WB should prioritise a shift from primarily Bank-executed diagnostic activity to recipient-executed projects. This approach builds national ownership, strengthens institutional capacity, and ensures that diagnostics translate into tangible delivery. While more complex to embed reforms within Yemeni systems, it is more likely to achieve long-term impact.

  1. Deepen synergies and partnership with FCDO and other Yemen-Focused partners, such as the UK Integrated Security Fund’s Technical Assistance Facility for Yemen (TAFFY). WB and FCDO should improve complementarity, transparency and information sharing across World Bank-managed instruments and FCDO/other donor instruments/vehicles by mapping overlaps and identifying shared reform entry points. This is particularly important in cross-sectoral and politically sensitive areas such as energy access, public finance and key policy reforms identified under the Government of Yemen two-year priority plan. Regular structured discussions to align analysis and understanding and establish coordination platforms between fund managers, under the relevant structures such as Yemen Partners Group (YPG) and the Yemen Partners Technical Teams (YPTT).

  1. Leveraging FCDO’s political role to complement the World Bank’s technical engagement. FCDO Yemen should use its diplomatic access and political influence to support high-level buy-in for reforms advanced though the YF. Strategic engagements with senior government counterparts can help reinforce traction and strengthen national ownership of policy and institutional change.

  1. Ensure UK’s financial contributions to YF are directed towards delivering GoY priorities. FCDO should agree new set of indicators to measure and verify UK-funded activities delivered under the YF are directly delivering against GoY priorities.

Output Title	Delivery of capacity building to support improved macroeconomic functions of key institutions
Output number:		2	Output Score:	A
Impact weighting (%):		11	Weighting revised since last AR?	Yes, down from 25

Indicator(s)	Milestone(s) for this review	Progress
Targeted training sessions with CBY staff on monetary policy development and implementation	16	18; Met expectations
Targeted training sessions with MOF staff on fiscal policy development and implementation	10	15; Moderately exceeded expectations
ERLP Performance Indicator key milestone achievement rates (annual)	At least 80% of key milestones achieved	86% of key milestones achieved; Met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

Building upon several years of successful collaboration between FCDO and USAID, with Pragma as implementing partner, AFFY co-financed the delivery of the Economic Recovery and Livelihoods Programme (ERLP). The ERLP provided targeted technical and institutional support to the CBY-Aden, the Ministry of Finance (MoF) and Tax Authority.

In FY24/25, the support focused on delivering against key areas such as: Monetary Management Reform; Foreign Reserves and Exchange Management; Payments Systems Reform; AML/CFT*; Bank Supervision; Access to Finance. Additionally, TA addressed strengthening critical areas including; Revenue Forecasting; Tax Policy; Tax Administration; Debt Planning and Management; and Budgetary Planning and Budget Implementation. The progress of these in improving macroeconomic functions in key institutions was primarily captured through the last indicator (“milestone achievement rate”).

Support to Central Bank Yemen - Aden

Reforms delivered under this support have been crucial in strengthening the Central Bank in the South and helping it manage severe macroeconomic pressures. While the currency has continued to depreciate —largely due to external factors such as trade imbalances, fiscal deficits, and the suspension of oil exports beyond the program’s scope—our support for monetary policy, FX auctions, and regulatory reforms has mitigated against extreme volatility. Strengthened bank supervision, AML/CFT compliance, and plans to modernise payments systems have also reinforced confidence in formal financial channels, safeguarded stability, and improved Yemen’s integration with regional financial systems. Together, these measures demonstrate the critical role of institutional reform in building resilience, even in a highly constrained environment.
Reforms/Activities delivered under this programme included the following:
1. Monetary management and FX policy: PRAGMA supported the implementation of a rules-based monetary policy framework, ensuring base money growth remained below GoY target (7.7%), contributing to exchange rate stability. FX auction systems were revived and modernised, with over USD 354 million sold to banks in 2024. These interventions directly absorbed liquidity and supported import financing, alleviating inflationary pressures.
2. Bank supervision and risk management: The Supervisory Risk Matrix was expanded to 26 banks and 200 exchange houses, accompanied by an upgraded capital adequacy framework in line with Basel II/III standards. Over 200 inspections were completed, surpassing annual targets and improving regulatory compliance across the banking sector. These reforms are essential for restoring confidence in the formal financial system.
3. AML/CFT compliance: Comprehensive guidelines were introduced for financial institutions, real estate agents, and insurers. The Financial Intelligence Unit (FIU) gained regional recognition by chairing the MENA/FATF forum. These reforms help reduce illicit financial flows and enhance Yemen’s alignment with international financial standards.
4. Payments systems reform: The IBAN rollout and PSP licensing framework were launched to modernise the national payments ecosystem. Integration with the BUNA regional platform supports secure cross-border transactions and strengthens Yemen’s access to international financial infrastructure.
5. Macro-financial statistics: The CBY was supported in producing monthly and quarterly economic bulletins, improving policy transparency. Capacity-building in macroeconomic modelling and inflation forecasting has enhanced the central bank’s role in evidence-based policymaking
Support to Ministry of Finance and Tax Authority
Reforms delivered under this support helped the Ministry of Finance and Tax Authority build a stronger, more transparent, and accountable fiscal framework—essential for Yemen’s long-term stability and recovery. By introducing medium-term expenditure planning, strengthening budget execution, and improving oversight of public spending, the government is better able to align resources with priorities and deliver value for money in key sectors. Enhanced debt management systems and greater transparency in State Owned Enterprises (SOE) performance are reducing fiscal risks and laying the groundwork for sustainable public finances. Treasury reforms, including the rollout of the Treasury Single Account and e-salary payments, are improving control over cash flows and ensuring more predictable, timely payments to public employees. Together, these measures reinforce institutional capacity, promote trust in public financial management, and enable the government to use limited resources more effectively to support essential services and economic resilience.

Reforms/Activities delivered under this programme included the following:

1. Budget planning and MTEF: A Medium-Term Expenditure Framework was introduced across key service sectors, integrating capital and recurrent spending and improving fiscal discipline. Cost-benefit analysis tools were embedded into investment planning processes, enabling the prioritisation of strategic capital investments.
2. Public expenditure efficiency: The Public Expenditure Efficiency Unit (PEEU) conducted expenditure reviews in health, energy, and education, with international benchmarking. This work underpins improved budget execution and value-for-money analysis.
3. State-owned-enterprise (SOE) oversight: A new SOE database and monitoring tools were developed to track performance and propose reform pathways for key utilities. Preliminary legal reform recommendations were shared with MoF, offering a roadmap for restructuring underperforming entities.
4. Debt management: Full deployment of the DMFAS sysm enabled joint CBY-Aden and MoF tracking of domestic and external debt. This contributes to greater fiscal transparency, risk management, and compliance with donor and creditor reporting requirements.
5. Budget execution and treasury reform: Key reforms included the rollout of the Treasury Single Account (TSA), expanded e-salary payment systems, and improved coordination with banks on payroll processing. These measures enhanced expenditure control, cash flow predictability, and payment integrity.
The continuation of such hands-on technical support and institutional mentoring remain vital for building credibility, improving service delivery, and attracting external assistance in Yemen’s complex recovery landscape specially during the current contextual environment i.e. US FTO designation of the Houthis as a terrorist organization.

The US FTO designation of Houthis in early January 2025, combined with cuts in US development assistance to Yemen, had significant consequences for the continuity of technical support provided to the CBY-Aden and MoF. This decision resulted in the immediate suspension of USAID-funded programming under the ERLP. The withdrawal of US financial backing disrupted planned advisory engagements, created critical technical voids, and left both institutions without timely expert guidance on navigating new compliance requirements related to the FTO designation.

The experience of supporting Yemen’s economic institutions underscores both the vital role and the inherent challenges of technical assistance in a fragile, politically fragmented context. While support to CBY-Aden demonstrated meaningful progress where institutional leadership was strong, reforms within the MoF stalled amid weak political will, internal tensions, and abrupt funding cuts. The sudden suspension of USAID support further highlighted the fragility of gains and the need for predictable, coordinated assistance. Continued, well-coordinated technical support to the MoF remains critical to advancing fiscal reforms and improving public financial management. However, this must be anchored in stronger political buy-in and clear institutional commitments. Future assistance should prioritise targeted, realistic reforms, formal knowledge transfer strategies, and closer alignment with national priorities. Sustained engagement, coupled with dialogue at senior political levels, is essential to unlock reform momentum and ensure lasting impact.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

For FY24/25 indicator 2.2 for “training sessions with MOF staff on fiscal policy development and implementation” amended from 7 to 10 to match the number of sessions requested by MoF. Impact weight of output 2 was revised down from 25% to 11% to broadly match the share of resources allocated for this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR are as follows:

  1. FCDO have held five engagements with the MoF this year and should aim to hold quarterly meetings with them. Achieved, FCDO conducted semi-annual official engagements between the Minister and his team.

  1. FCDO Yemen should decide on whether supporting capacity building within the MoF should remain a priority going forward considering resistance to reforms and set our own threshold for continuing to programme with the political context [REDACT IN PUBLIC VERSION]. Achieved, FCDO Yemen identified support to MoF as essential to strengthen GoY macroeconomic stability and financial status. Therefore, despite USAID reduction of funding during 2024, FCDO allocated additional financing to support MoF delivered through ERLP.

  1. AFFY Programme team should engage with the political team to better understand the rationale behind the MoF’s resistance to reforms, and if there are any risks to HMG working with the MoF [INTERNAL RECOMMENDATION]. Partially Achieved, AFFY programme team and Political team will need to engage more frequently to better understand resistance to reforms within MoF and different entities within GoY including PLC and cabinet.

Lessons Learned:

  1. Political engagement is critical for policy reforms. Reform implementation in Yemen cannot rely on technical design alone; it must be supported by sustained political engagement. PRAGMA’s experience with the MoF demonstrates that technical consensus is insufficient when institutional incentives and accountability mechanisms are weak. Donor agencies, including FCDO, must proactively engage with senior political actors to convert technical plans into actionable policy reforms.

  1. Localisation and contextual adaptation matter. Training and policy inputs were most effective when grounded in Yemen’s operational realities. CBY-Aden recommended greater involvement in expert selection and tailoring of international models to national legal frameworks. Regional experts and Arabic-speaking trainers also proved more impactful.

Recommendations for Year Ahead:

  1. Improve reform uptake and momentum through coordination and political-level engagement using YPTT/YPG* structures. FCDO should engage senior MoF and PLC counterparts to ensure that agreed reforms are implemented and not blocked by internal resistance. Direct advocacy and follow-up should accompany technical support.

  1. Institutionalise local ownership and expert selection. FCDO should ensure future support, should ensure Yemeni counterparts are involved in the design and staffing of technical assistance. Local expert selection (including Arabic speakers and regionally experienced experts), context adaptation, and alignment with legal frameworks should be built into delivery protocols.

  1. Tailor organisational reforms to institutional realities. Organisational restructuring proposals—such as those for the Tax Authority—should reflect the existing capacity constraints of Yemeni institutions. Recommendations should prioritise incremental, phased implementation strategies that are co-designed with local leadership and grounded in political economy realities.

  1. Embed knowledge transfer into all support streams. Technical assistance must go beyond short-term delivery and embed structured knowledge transfer mechanisms, including mentoring, toolkits, handover plans, and implementation roadmaps. This is especially important in technical areas such as banking supervision, FX policy, and tax reform.

Output Title	Delivery of capacity building support to Executive Bureau that results in changed thinking or policies and increased appreciation for the value of evidence in policymaking more broadly that can be attributable to this work
Output number:		3	Output Score:	A
Impact weighting (%):		5	Weighting revised since last AR?	Yes, down from 10 to 5

Indicator(s)	Milestone(s) for this review	Progress
Number of Executive Bureau workstreams to support IGC projects and EB’s broader work	3	3, met expectations
Number of reports (and where relevant policy briefs) produced by IGC and EB embedded experts	6	6, met expectations
Number of meetings held with government, multilaterals, and relevant international working groups/conferences to disseminate key findings	7	7, met expectations
Number of areas identified under each topic in need of further work (mini research agenda	6	6, met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

The International Growth Centre (IGC), under the AFFY programme, has served as the principal implementing partner providing technical assistance to Yemen’s Executive Bureau (EB) – an institution under the Prime Minister’s Office tasked with supporting policy reform and acceleration of aid absorption. Through this partnership, IGC supports policy design, sectoral research, and embedded technical advisory to strengthen the EB’s strategic and institutional capacity. Throughout FY2024/25, IGC’s support focused on advancing three reform workstreams—electricity, fisheries, and remittances—alongside strengthening the EB’s institutional capacity and technical advisory function.

In the electricity sector, IGC and EB finalised and disseminated the flagship report “Electrifying Taiz”, developed a pre-proposal to fund the infrastructure rehabilitation in Taiz, supported the Public Electricity Company (PEC) in regulatory review for private sector participation in electricity generation and distribution, and engaged national and regional stakeholders including the PEC, MoEE*, SDRPY*, and Masdar*.This informed policy dialogue, helped mobilise donor interest, and culminated in preparations for a national workshop to discuss sector-wide reforms. However, progress on the privatization of infrastructure rehabilitation in Taiz has faced political pushback and limited buy-in from the Ministry of Electricity reflecting deeper governance challenges in the sector. Overcoming these obstacles and securing stronger commitment will be critical to translating such reforms into tangible outcomes. Future support should prioritise high-level political engagement and stakeholder alignment to build consensus and commitment around electricity sector reforms. This includes targeted dialogue with the Ministry of Electricity and key actors to address resistance, understand incentives, and foster shared ownership of reform priorities.

In the fisheries sector, IGC delivered a comprehensive Public-Private Partnership (PPP) report and policy brief shared with MoAIF* and international partners. It also pivoted toward climate resilience in fisheries, producing a geospatial analysis, launching new research in partnership with the University of Chicago, and facilitating cross-country learning visits with Oman. These efforts built initial PPP capacities within EB and MoAIF* laying necessary foundations to scale up PPP capacities cross-ministerial support to GoY through the Yemen Fund.

Finally, the remittances workstream was initiated to assess institutional and structural barriers to flows; activities included survey design, data collection with CBY, stakeholder consultations, and a multi-stakeholder roundtable to validate findings.

IGC also embedded multiple policy advisors within the EB, who provided technical support on strategic planning, M&E systems (notably for MoAIF), donor project monitoring, and policy advisory work across key sectors. The EB’s internal capacity was bolstered through the development of its 2025 Strategic Plan, a monitoring dashboard, and enhanced coordination mechanisms with ministries and donors. Outputs were consistently shared in Arabic and English, with strong receptivity from line ministries including MoEE*, MoAIF*, MoPIC*, and the PMO*. For instance, the EB supported MoAIF* in the development of an M&E system used by the ministry to monitor donor investments in agriculture and fisheries in Yemen. Overall, this support improved the EB’s capability to interact with donors and co-ordinate support with line ministries. The EB will take this experience further under the Yemen Partners Group/Yemen Partners Technical Team structures in cohering donor support as GoY representatives.

Despite the embedded model’s success, challenges included staff turnover within the EB, limited availability of ministry counterparts, and delays in workshop approvals due to political sensitivities. The electricity workstream, for example, faced delays due to undercalculated misalignment with Ministry of Electricity priorities and lack of political buy-in.

Embedded experts within EB played a crucial role in bridging gaps by adapting to evolving institutional contexts and sustaining progress during moments of uncertainty. Although IGC tried to mitigate these challenges through early coordination with local authorities, field visits, and flexible sequencing of deliverables, delivery against “Electrifying Taiz” funding pre-proposal for infrastructure rehabilitation did not materialise.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

For FY24/25 indicator 3.1 for “Number of Executive Bureau workstreams to support IGC projects and EB’s broader work” was amended from 2 to 3 to reflect IGC/EB action plan. Likewise, indicator 3.3 for “Number of meetings held with government, multilaterals, and relevant international working groups/conferences to disseminate key findings” was amended from 9 to 7 to reflect engagement needs. Additionally, indicator 3.4 for “Number of areas identified under each topic in need of further work (mini research agenda)” was amended from 4 to 6 based on advice from IGC.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR are as follows:

  1. IGC should leverage FCDO for support in disseminating project outputs, such as reports and assessments, (if needed at more senior levels) within the Government of Yemen and the international community. Achieved, IGC leveraged FCDO support in disseminating number of IGC/EB outputs including remittances report in a national workshop co-chaired by CBY-Aden; the Electrifying Taiz report in number of donor engagements including OECD/EU PPP sessions.

  1. IGC should work to minimise the financial risks for the EB; as the experts rely on FCDO funding for salary payments, if the IGC cannot guarantee that the experts will have a role then they will go elsewhere. FCDO Yemen budget and allocation cycles create financing gaps within EB. It is recommended that IGC manages the expectations of the embedded experts about potential funding gaps and submit programming proposals in good time to minimise disruptions. It is also recommended that IGC works on developing a strategy and ensure sustainability of impact after FCDO funding ends. Not Achieved, this should be prioritized by EB moving forward and if we continue to fund EB via the IGC then we should ensure this is in place as a priority.

  1. FCDO should discuss shortening the policy development timeframe (where feasible) with IGC, as this will help GoY officials convert them into delivery/action plans. Not Achieved.

  1. When updating the logframe for year 3, FCDO and IGC should mutually agree on a target that measures the impact from this component. Not Achieved, should be prioritised in FY25/26if we proceed with funding IGC/EB.

Lessons Learned:

  1. Embedded technical advisors enhance institutional resilience. IGC’s embedded model enabled real-time policy response and enhanced strategic planning capabilities within the EB. The presence of full-time advisors fostered deep institutional trust, supported adaptive problem-solving, and contributed to continuity despite political volatility and staff turnover. This model proved particularly effective in coordinating cross-ministerial engagements and responding to shocks such as the FTO designation and Red Sea crisis.

  1. Mitigating limited political engagement and weak institutional relationships. While the technical quality of the reports and policy outputs were consistently high, there was a notable disconnect between these deliverables and the political economy context in which reforms must be implemented. The EB and IGC teams often lacked the influence or convening power needed to generate sustained political buy-in, limiting the uptake of policy recommendations and slowing progress on sectoral reforms, particularly in politically sensitive areas such as electricity. This points to a broader structural issue: successful delivery in Yemen’s complex operating environment requires implementing partners who not only bring strong technical expertise, but who also possess the political acumen, contextual understanding, and networks necessary to navigate shifting dynamics and influence decision-making at multiple levels.

  1. Donor dependency threatens institutional continuity. Despite delivering high-value outputs, FCDO and broader donor aid cuts disrupted EB’s ability to retain advisors and sustain momentum. The EB lacked contingency plans or financial buffers, exposing its structural fragility. Future technical support should include sustainability strategies—such as phased cost-sharing, hybrid financing, or stronger more sufficient national budget integration—to reduce aid dependency and preserve institutional continuity.

Recommendations for Year Ahead:

  1. Reprioritise EB support to the activities that can reasonably and directly advance the delivery of the GoY’s two-year priority plan, through the YPTT structures. Any reinstatement and/or extension of international and local advisory support to EB needs to be clearly linked to advancing the GoY’s strategic goals and priorities. This should include mechanisms for translating policy outputs into action plans with clear ministry ownership, implementation timelines, and feedback loops.

  1. Engage political leadership to elevate EB’s role. The EB’s contributions must be better understood and leveraged by Yemen’s political leadership. FCDO should engage the Prime Minister’s Office and Presidential Leadership Council to clarify the EB’s strategic role, increase visibility of its contributions, and promote its integration into core government decision-making frameworks.

  1. Build financial sustainability plans for EB. Given the volatility of donor funding, FCDO should work with the EB to co-design financial resilience plans, including budget reprioritisation, pooled technical assistance, and multi-donor contingency frameworks to ensure continued delivery under fiscal shocks.

Output Title	Data on economic indicators for Yemen made available to FCDO and the public
Output number:		4	Output Score:	A
Impact weighting (%):		2	Weighting revised since last AR?	Yes, down from 5 to 2

Indicator(s)	Milestone(s) for this review	Progress
New modules developed for the web-based economic database and interactive dashboard	2	2, met expectations
Web-based economic database maintained and effectively utilised as evidenced by the number of YETI website visits	3,500	3,534, met expectations
Number of YETI stakeholder engagement sessions held with the international community to disseminate key analysis	4	11, moderately exceeded expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

ACAPS has supported FCDO Yemen in developing and maintaining the Yemen Economic Tracking Initiative (YETI). This partnership contributes to Outcome 1 of the AFFY programme by generating robust economic evidence to inform FCDO’s programming and influencing efforts in the absence of a physical UK presence in Yemen. YETI, hosted on an online platform, has over the years become a critical repository of independent, up-to-date, and policy-relevant economic indicators and qualitative insights. It has supported evidence-based decision-making by UK officials and the broader humanitarian-development-peace nexus actors in Yemen, including the World Bank, IMF, and UN agencies by leveraging its analysis and data to support publications such as the Joint Monitoring Report, a bimonthly update on food and nutrition security crisis risks.

In FY24/25, two key modules on the YETI web-based platform were enhanced: the Import Module and the Integrated Phase Classification (IPC) Module. The Import Module now enables users to visualise quantities of imports disaggregated by port of origin and commodity type, while the IPC Module facilitates long-term trend analysis by geographical and temporal parameters. These improvements have significantly increased the analytical capabilities of the platform and enriched policy engagement on food security and trade dynamics.

YETI data was featured in the World Bank's 'Yemen’s Compounding Burdens' report (March 2025), IMF Yemen mission analysis, WFP food security assessments, and the Joint Monitoring Reports led by FAO, WHO, UNICEF, and the World Bank.

ACAPS held 11 stakeholder engagement events over the year—well surpassing the annual target of 4. These included technical presentations to the IMF, World Bank, and Yemen Cash and Market Working Group. Bilateral discussions were held with UN Resident Coordinators, OSESGY, and sectoral working groups. Feedback from these engagements informed platform enhancements, including a mock-up dashboard for port of origin analysis.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

For FY24/25, indicator 4.2 for “Web-based economic database maintained and effectively utilized, evidenced by YETI website visits” was amended from 4000 to 3500 as there was a change in the methodology used to assess visits. Likewise, indicator 4.3 was changed from “number of regular econ narrative updates” to “number of yeti stakeholder engagement sessions” to reflect activities. Impact weight of output 4 was revised down from 5% to 2% to broadly match the share of resources allocated for this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no Recommendations from the previous AR.

Lessons Learned

There are no lessons learned from this financial year.

Recommendations

  1. Prioritise long-term maintenance and sustainability planning. Given YETI’s institutional maturity, the upcoming fiscal year should focus on maintaining core modules, preserving backend stability, and planning for long-term sustainability. This includes exploring diversified funding models and streamlining technical staffing.

Output Title	UNVIM extends current operations and continues to provide a monitoring and inspection service
Output number:		5	Output Score:	A
Impact weighting (%):		6	Weighting revised since last AR?	Yes, down from 10 to 6

Indicator(s)	Milestone(s) for this review	Progress
Extension of contracts for a period of two (02) months	n/a
Payment of Utilities for the UNVIM Office in Djibouti for two (02) months.	n/a
Verification and Inspection, including reviewing documents, screening, inspection, seizure/ disposal	100% of vessels and no delays	100% of vessels and no delays – met expectations

Briefly describe the output’s activities and provide supporting narrative for the score.

The United Nations Verification and Inspection Mechanism for Yemen (UNVIM), implemented by UNOPS, plays a critical role in enabling the unimpeded flow of commercial shipments—including fuel, food, and humanitarian cargo—to Yemen’s Red Sea ports not under the control of the Government of Yemen. This mechanism remains vital for mitigating the country’s humanitarian crisis by ensuring commercial lifelines continue to function despite conflict-related constraints.

During FY2024/25, AFFY programme funded UNVIM operations for December 2024 to March 2025. During that period, UNVIM conducted 126 vessel inspections in Djibouti’s territorial waters, showing a marginal increase compared to 124 inspections during the same period last FY. A total of 134 clearance requests were submitted, and 1,295 verifications were issued—marking a notable increase in administrative output when contrasted with the 2024 monthly average of only 42 verifications.
Despite sustained operational delivery, UNVIM faced significant structural and financial constraints. Persistent funding instability continued to undermine the Mechanism’s technical and managerial capacity. This was exacerbated by a financial suspension order issued by the U.S. State Department in January 2025, which added a further USD 500,000 gap to an already constrained 2025 budget. Short-term contracting arrangements prevented the recruitment and retention of qualified international personnel, leading to prolonged vacancies in key positions such as Project Manager, Deputy Project Manager, and Reporting Specialist. These gaps weakened institutional capacity, slowed reporting, and increased the risk of operational discontinuity.

On a more positive note, stakeholder engagement intensified during the quarter. UNVIM hosted several high-level visits—including delegations from the United States, Turkey, and the UK—highlighting its transparency and strategic relevance. Monthly reporting was also resumed following the onboarding of a new Reporting Specialist in February and an Information Management Officer in March, which may help address previous lags in reporting output.

Looking ahead, UNVIM’s continued ability to deliver on its mandate will depend heavily on securing long-term funding, stabilising its leadership team, and improving coordination with clearance and port authorities. Without these structural improvements, operational gains may prove difficult to sustain.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In FY24/25, impact weight was revised up from 5% to 10% in April 2024 and then revised down again from 10% to 6% in March 2025 to broadly match share of resources allocated to this output.

In May 2025, following FCDO Maritime Security Advisor advise, all indicators under output 5 were amended as following:
- indicator 5.1 was amended from 'Extension of contracts for period of two (02) months' to 'Vessels inspected with no delays to shipping beyond that required to conduct the inspection'
- Indicator 5.2 was amended from 'Payment of utilities for the UNVIM Office in Djibouti for two (02) months' to 'Number of vessels discharged per year'
- Indicator 5.3 amended from 'Verification and Inspection, including reviewing documents, screening, inspection, seizure/ disposal' to 'Time taken to clear vessels'
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR are as follows

  1. FCDO, using the Maritime Security Advisor to implement, should engage UNOPS to set new oversight and reporting responsibilities to make sure donors are suitably appraised of how donor funds are spent and whether that investment is achieving strategic goals. Partially Achieved, YON Maritime Security Advisor worked collaboratively with UNOPs to set new reporting standards to improve donor visibility and alignment with strategic goals. However, while the quality of reports improved more needs to be done to increase both reporting frequency and timeliness of reports. For reporting to effectively inform policy and operational decisions, it must be issued when most needed—particularly during periods of heightened maritime disruption or donor engagement. Ensuring reports are timely and responsive to evolving contexts remains a critical area for continued improvement.

  1. FCDO should encourage other countries to fund UNVIM to ensure a broader coalition, supporting UNVIM’s long term funding stability. Not Achieved.
Lessons Learned
  1. Data-driven trend monitoring is essential. UNVIM’s inspection volumes offer a unique window into Yemen’s economic activity and port functionality. Tracking fuel and cargo flows over time can serve as a proxy indicator for economic resilience and recovery trends. However, measuring higher-level outcomes such as the disruption of illicit smuggling networks remains a challenge without clear, attributable metrics.
Recommendations
  1. UK should explore alternative UK funding for UNVIM. In the context of transition to a lower ODA budgets and prioritising supporting humanitarian cash recipients’ graduation from humanitarian assistance, FCDO should explore alternative ways and resources beyond AFFY to support UNVIM.

Output Title	Successful piloting of an inclusive, climate resilient Market Systems Development approach
Output number:		6	Output Score:	B
Impact weighting (%):		4	Weighting revised since last AR?	n/a

Indicator(s)	Milestone(s) for this review	Progress
Number of participants (or businesses) trained in technical and business support for managing and maintaining cold storage facilities	35	35 – met expectations.
Preliminary findings enable developing a plan for a longer-term intervention towards upscaling	1	Did not meet expectation. The short 4.5-month implementation window limited the ability to draw robust conclusions or demonstrate sustainable outcomes.

Briefly describe the output’s activities and provide supporting narrative for the score.

The pilot, implemented by Mercy Corps under the AFFY programme, aimed to reduce post-harvest losses, improve incomes, and strengthen resilience in the fisheries sector through a market systems approach. The pilot focused on equipping 35 small-scale fish traders with solar-powered cold chain solutions and delivering tailored technical and business training. All 35 selected traders completed a structured training programme in cold chain operations, business management, and financial literacy. Each trader received a cold storage package, including solar panels and batteries; mobile traders also received tuk-tuks for transportation. 88% of traders integrated the equipment into daily operations, reporting reductions in spoilage and increases in seasonal sales. Several traders began formalising their businesses, and early signs of job creation were observed.

In parallel, Mercy Corps developed a proposal for multi-year scale up programme. However, FCDO assessed the proposal as falling short as the 4.5-month implementation period was deemed insufficient to draw robust conclusions to inform a comprehensive scale-up. Alternatively, a one-year second phase to the pilot focused more directly on livelihoods rather than full-scale market system development agreed to be the step forward.

Phase II pilot, to be supported under AFFY’s extension year, will target the fisheries sector in Aden and Hadramout. It will introduce stronger training components for fisheries cooperatives and incorporate access to finance mechanisms, allowing for a more grounded understanding of delivery challenges and opportunities. This staged, iterative approach will help test solutions more robustly before scaling further.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In FY 24/25, Output 6 was added as a new output to deliver against a pilot to promote inclusive, climate-resilient market systems in Yemen’s fisheries sector. Under this new output two new indicators were created:
- Indicator (6.1): Number of participants (or businesses) trained in technical and business support for managing and maintaining cold storage facilities
- Indicator (6.2): Preliminary findings enable developing a plan for a longer-term intervention towards upscaling.
For FY 25/26, FCDO programme team will revise this output and using advise from FCDO Humanitarian Advisor will set proper indicators to measure progress against Phase II of this Pilot.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Lessons Learned

  1. Context-responsive equipment design. Equipment must be adapted to the operational scale and product types of different traders. Future phases should offer modular or larger refrigeration units tailored to trader profiles. MC need to collaborate with equipment vendors to explore options for developing or sourcing modular or custom-built larger refrigeration units that better match the needs of traders.

  1. Financial and gender inclusion require dedicated strategies. More tailored financial products and greater inclusion of women—particularly in fish processing and storage—are needed to fully realise equitable impact.

Recommendations

6.1. Broaden women’s participation. Mercy Corps should (when applicable) target women for roles in processing, storage management, and cooperative leadership.

6.2. Let Scale with systems in mind. Mercy Corps should aim to strengthen consumers’ awareness (e.g. through campaigns), financial access (e.g. tailored blended financial products for small-scale traders), modular cold storage options (e.g. best suited to the diverse traders’ needs), cold chain servicing networks, embed local repair ecosystems, and build vocational pathways.

D: VALUE FOR MONEY

Key cost drivers and performance

Measures are included for the variety of programming covered under the YF along with the fund’s administrative costs, as well as the fees for technical funded activity under the IGC component. In the previous AR, the fee rates of the consultants funded under the USAID’s Economic Recovery and Livelihoods Programme (ERLP) were examined by FCDO’s Procurement and Commercial Department and deemed to be competitive.

VfM performance compared to the original VfM proposition in the business case

The performance against the VfM framework for year three is as proposed in the Programme Business Case. FCDO uses the ‘5 Es’ framework (economy, efficiency, effectiveness and equity, including gender equality, disability and leaving no one behind) to ensure that its funding maximises impact. With a relatively small budget (compared to humanitarian programming) the programme helped further HMG’s economic country campaign goals on Yemen and represents good VfM within the overall FCDO Yemen context and programme portfolio.

Economy
- AFFY continued to utilise USAID’s existing ERLP programme with Pragma, a ready-made intervention without the costs associated with an open procurement process, with USAID undertaking the administrative costs. ERLP’s buy-in mechanism has worked well for both FCDO and Pragma; this was exemplified this year with additional UK funding providing assurance to the Yemen MoF that ERLP support would continue. Across the Yemen donors this is unique work, and FCDO has been able to fund a specialised strand of this, with UK funding clearly earmarked against specific areas within the ERLP workplan.
- FCDO funding to the IGC provides high-quality work at a low cost. This year, a little over half the budget was spent on embedded experts in the Government of Yemen’s Executive Bureau; the head of the EB maintained close contact with FCDO and flagged funding concerns as they arose. The IGC manages its budget carefully, with FCDO in close contact at year-end to check they were on track for year-end spend. Using FCDO funding, IGC delivered research requested by the Government of Yemen using specialist technical and regional experts’ quality assured by the LSE’s academic rigour.
- This year, in October 2024, Switzerland became the third donor to the YF after the UK and the Netherlands. AFFY’s anchor funding to the YF has leveraged in more resources. Switzerland funded Recipient-Executed activities Microwork for Youth Pilot Programme; and while the UK’s Food Security Safety Net Programme funded the Yemen Cash Transfer Shock Response to Floods. This increased the level of total funding to the YF, supporting the shift towards more recipient-executed interventions and programmed new workstreams within it.

Efficiency
FCDO funding to USAID’s ERLP is an efficient use of funding as the UK can select which elements of the workplan to fund. The UK funding builds a proven model to improving institutional capacity, given the expertise of Pragma’s consultants and their presence in Yemen. As a result, the UK can more efficiently fund the outputs (targeted, capacity building work) with the CBY and MoF in-person, than it would bilaterally. This also provides FCDO invaluable insight into on-the-ground dynamics within both institutions.
- For a modest amount (£137k), FCDO funding to ACAPS is efficient as a range of actors utilise YETI – humanitarian organisations, OSESGY, WB and Government of Yemen. YETI is also used as a foundation for other analytical products and supports Yemen’s economy through providing data to government decision-makers and consequently supports in developing livelihoods. These factors render YETI an excellent value for money tool for providing quantitative data. AFFY’s funding to YETI also complements FCDO Yemen’s MERLY* M&E programming with ACAPS, with one financing the dashboard and the other financing analysis, such as flash analytical pieces delivered during the Red Sea crisis.
- FCDO funding to the YF is highly efficient as the fund’s four pillars cover capacity building, evidence generation, green reconstruction planning and internal monitoring. The YF reduces the transaction cost for the GoY interacting with the International Community by establishing a framework for donors to work within and improving the uptake (by aligning assistance with national systems), promoting national ownership and ultimately improving the likelihood of durable improvements by embedding long-term capacity building within GoY institutions. Channelling support through the Yemen Fund strengthens GoY capacity by aligning assistance with national systems, reducing fragmentation, and promoting ownership. Unlike bilateral delivery, it embeds long-term capacity building within institutions and lowers transaction costs for government engagement. In addition, by using a YF, this gives FCDO significant breadth in programming for both capacity building of Yemen’s government ministries, and generates evidence, such as the Financial Sector Diagnostic and the Aden (electricity) Master Plan that can be disseminated with donors and inform programming across the network.

Effectiveness
- FCDO funding to USAID’s ERLP remains a highly effective use of funds, with the UK funding specific strands within the workplan, with subsequent revisions to the workplan being covered by this. Alongside complementing diplomatic engagement with the US and UK on Yemen’s economy, it also grants FCDO invaluable insight into dynamics on the ground within the CBY and MoF, updates on internal government reforms, and provided the programme team direct engagement with the most senior levels within the CBY and MoF.
- FCDO funding to the International Growth Centre (IGC) provides high-quality work at a low cost. Yemen’s Executive Bureau (EB) views UK funding to IGC as critical in developing their capacity and enabling them to build on their knowledge and research; this also grants FCDO invaluable insight into research being undertaken within government ministries such as electricity, agriculture, irrigation fisheries and remittances, and learning first-hand how FCDO funded research is being received by senior officials up to Ministerial level.
- FCDO’s support to UNOPS funds UNVIM and provided the organisation with crucial funding jointly with the EU, US, and Japan to counter the smuggling of illicit goods entering Yemen. The AFFY programme contributed £0.5M, complementing ISF Yemen’s £0.5M.
- FCDO’s seed funding to the YF played a cost-effectiveness role in enabling large-scale development finance i.e. IDA financing in critical areas such as food security, economic growth and job creation, public finance management, and enabling private sector-led growth in economically vital sectors.
- YF outputs help to maximise the value for money of FCDO’s wider programme portfolio and the WB’s large (~$600m) International Development Association (IDA) investments in Yemen. In addition to this, the YF’s technical assistance, capacity building and evidence-generating activities is a valuable mechanism to coordinate support and deliver capacity building to GoY institutions.
Equity
- Yemen is experiencing a food affordability crisis (not one of availability), rendering the poorest and most vulnerable households the most likely to suffer economically. The poorest households are likely to benefit indirectly from AFFY’s support to stabilise economic conditions and improve GoY institutional capacity, as well as directly through reforms (such as improving salary payment mechanisms), and improving electricity coverage in Taiz and Aden. YF evidence products, such as the Financial Sector Diagnostic, and Aden (electricity) Master Plan are also used to inform FCDO and international programming.
- Equity is embedded within USAID programming as a mandate for PRAGMA. Although gender programming can be difficult given that PRAGMA cannot choose whom they work with or how the GoY implements their suggestions. However, PRAGMA does press for gender equity when engaging their counterparts and encouraging GoY representatives to include female representation. However, given the acute and urgent needs for capacity building, FCDO judged it was necessary to prioritise capacity development over establishing ways for greater inclusion of women. The programme team look forward to a new Social Development Adviser joining in summer 2026 to review AFFY’s gender/inclusion approach.
- YF advanced women’s economic empowerment by partnering with local organisations and business councils to identify barriers facing women entrepreneurs and develop actionable policy solutions. It also integrated gender and inclusion analysis into grant design, including in WASH and private sector revitalisation activities. Through targeted consultations, YF engaged disadvantaged groups to ensure their needs informed program design, reinforcing its commitment to inclusive, locally anchored recovery.
- YF prioritises gender, disability, regional equity, and citizen engagement across design and implementation. Products like the Women’s Entrepreneurship study directly informed how to make interventions more inclusive. For public-facing visibility, the YF launched a dedicated website and knowledge products, though caution is advised given Yemen’s fragility. Future communications should be purpose-driven and harmonised with wider donor strategies to avoid harm.

Assessment of whether the programme continues to represent value for money

Overall, the AFFY programme and its components continue to represent good value for money. With a relatively small budget (relative to humanitarian programming) the programme has helped further FCDO Yemen’s campaign goals, objectives towards economic stabilisation and recovery, and represents good VfM within the overall FCDO Yemen context and programme portfolio. Additionally, the programme effectively satisfies the FCDOs ‘5 Es’ framework with clear evidence demonstrating that the programme is economical, efficient, effective, and equitable.

E: RISK

Overview of risk management

The risk rating for AFFY remained major throughout the third year of implementation. From November 2023 to December 2024, the programme team has not been able to visit Yemen, due to risks to staff safety. This has restricted FCDO access and partner presence in project locations, and programming was therefore managed remotely, which raises our risk exposure from a delivery and fiduciary perspective. The programme team plans to resume monitoring visits in 25/26 security situation permitting. FCDO accept the need to take on risk, albeit with the appropriate monitoring and mitigation measures in place to achieve results. This involves a bespoke quarterly risk review led by the PRO with the YON Risk lead and the SRO. These reviews focus on each risk category, assessing risk appetite and ratings, and monitoring the status and actions required to address both emerging and ongoing risks. Ad-hoc risk discussions are covered in weekly meetings, including evolving risks and those that may require escalation in line with the FCDO YON escalation framework.

Given the UK’s sustained public commitment to economic recovery and reform in Yemen, and the volatile context meaning the reform agenda could be deprioritised with little warning, FCDO has a higher appetite for strategy and context, reputational and delivery risks under the AFFY programme. Risks within these categories were mitigated by ensuring continued engagement with key donors, the UN Office of the Special Envoy of the Secretary-General for Yemen (OSESGY) and international financial institutions (World Bank) to ensure activities were aligned.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Throughout the year, FCDO were kept well-informed of progress through both formal and informal reporting. All programme partners provided quarterly narrative progress reports, except for the WB which provided an annual report as agreed, and UNVIM. These were largely on time and to a very high standard. The Development Director and programme team attended two Partnership Council meetings held by the WB over the reporting period; both held in person in Amman. The programme team held monthly catch ups with the WB when required outside of these meetings, and with other partners typically on a weekly or bi-weekly basis to discuss progress. In addition to meeting with direct implementing partners, FCDO maintained dialogue with downstream partners and beneficiary organisations such as Pragma, the EB, CBY and MoF.

The AFFY programme team was advised by FCDO Yemen’s Maritime Security Advisor to provide UNVIM with funding for FY24/25 similar to that in recent two years on AFFY for emergency cover. AFFY’s flexible funding mechanism enabled it to provide UNOPS with £500k of emergency funding this year for UNVIM, covering December 2024 – March 2025. AFFY programme team conducted regular check-ins with both UNOPS and FCDO Yemen’s ISF programme team for more substantial reporting.

The AFFY SRO and PRO lead all partner relationships except for the engagement with UNOPS which was held by FCDO Yemen’s Maritime Security Adviser. An interim financial report was submitted and UNOPS confirmed their end of year spending position, but AFFY did not receive progress reports – until May 2025

Most outputs met or exceeded expectations. The FCDO programme team do not have any significant concerns regarding the progress of AFFY’s outputs in the third year of implementation and will work closely with partners in the coming year to address the recommendations from this review and will revise logframe targets as addressed in Section B of this review.

Financial and Commercial Performance

The FCDO programme team set out clear expectations for financial reporting at the start of the year and received reporting in both timeliness and quality from most partners. In addition to providing formal financial reporting as required, partners provided monthly expenditure updates which allowed the programme team to identify and mitigate deviations from the forecast in advance. For partners who were paid in quarterly instalments such as ACAPS and IGC, each invoice was accompanied by a financial report with a forecast, providing an excellent point of reference for monitoring spend.

In the third year of AFFY, the programme spend was £8,304,450 against a budget of £8,314,450 with a variation of £10,433.

Partner	Agreement / Duration	Funding Instrument	2024/2025 Funding Disbursed	Date of last narrative financial report	Date of last audited annual statement
ACAPS (YETI IV)	29 Aug 2022 – 31 Mar 2025	Accountable Grant	£137,982	March 2025	N/A
IGC (Executive Bureau support)	01st May 2022 – 31st Mar 2025	Accountable Grant	£416,468	March 2025	N/A
Mercy Corps (MSD)	10th Nov 2024 - 31st Mar 2025	Memorandum of Understanding	£350,000	May 2025	N/A
USAID (CBY & MoF TA)	07th Jun 2022 – 31st Mar 2025	Memorandum of Understanding	£900,000	September 2024	N/A
World Bank (MDTF)	25th May 2022 – 31st Mar 2025	Administration Arrangement	£6,000,000	March 2025	N/A
UNOPS (UNVIM)	1st Dec 2024 – 31st Mar 2025	Memorandum of Understanding	£500,000	March 2025	N/A
			£8,304,450
[note] Mercy Corps will submit the final financial report in June 2025
[note] No additional financial and progress reports beyond these dates due to USAID stop work order
[note] Financial information on MDTF accessible via the Development Partner Centre

There were no commercial contracts under AFFY in the third year of implementation. The agreements used to deliver the programme were either a Memorandum of Understanding or Administration Agreement.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

The FCDO Yemen Economy & Recovery Team was not able to undertake any visits to Yemen given regional security concerns. However, the programme team continued to closely monitor progress against outputs through on-line and in-person meetings in Amman/Riyadh with key stakeholders such as the CBY-Aden, MoF and EB and implementing partners including IGC, PRAGMA/USAID, ACAPs, Mercy Corps and WB which. The AFFY programme team along with FCDO Yemen’s Development Director took part in two WB Partnership Council Meetings in Amman, which included representatives from the Netherlands, Switzerland, and EU. The latter as observer with a view for potential future donations to the YF. These meetings enabled all sides to discuss progress to date, overcome obstacles and plan ahead.

Additionally, AFFY programme team sought advice from FCDO MENAD Regional M&D adviser on AFFY logframe and had discussions on a Monitoring & Evaluation plan for the programme. The new YON Conflict Adviser will provide support on strengthening the conflict sensitivity of the programme, including drawing on MERLY in this area. The AFFY programme team will prioritise updating the logframe, and developing an M&E plan for FY 25/26 to reflect activities under programme one-year extension and to inform the future transition to a new Business Case from next FY.

Learning

Over the past year, the AFFY programme has employed a combination of structured reporting reviews, bilateral partner engagement, and internal cross-team consultations to capture lessons and strengthen implementation. While these processes have yielded valuable insights, several gaps in reporting formats and communication mechanisms have hindered timely learning and programme oversight.

One of the key challenges identified relates to the inconsistency and infrequency of partner reporting. Implementing partners have used varied templates, with reporting timelines ranging from quarterly to annual submissions. In particular, the YF and UNVIM delivers reporting on an annual basis, limiting the FCDO team’s ability to track progress and draw lessons throughout the year. This has resulted in repeated follow-up requests to partners, consuming significant time and slowing the feedback loop.

To address this, the team has identified a need to standardise reporting templates as much as possible and agree upfront on the frequency and structure of submissions. This would help ensure that all partners report against agreed log-frame indicators and submit clear, comparable data that reflects the scope and depth of activities delivered under AFFY. For example, indicators related to private sector development and financial inclusion currently lack specificity, and do not always capture the qualitative improvements achieved by the YF. Revising these indicators and co-developing them with implementing partners would strengthen evidence gathering and enable more meaningful programme analysis.

Another learning area is the need for stronger, more regular engagement between FCDO technical advisers and World Bank Team Leads delivering across the different grants under the YF. Improved collaboration between FCDO’s private sector and economic advisers and the leads of the electricity, governance, and financial sector grants could help identify synergies and reduce duplication across parallel workstreams. Early dialogue on planned activities would also help surface opportunities to align with other UK-funded programmes, including through potential joint interventions or shared data.

Looking ahead, the team will prioritise:
- Developing a common reporting framework across AFFY partners to improve the quality and usability of programme data;
- Revising key log-frame indicators to better capture cross-sector outcomes and partner contributions;
- Enhancing internal cross-team learning by identifying crosscutting themes that can inform broader FCDO Yemen programming;
- Improving real-time visibility of YF activities through more frequent structured discussions and joint planning sessions with the World Bank.
These learning objectives will be embedded in next year’s programme management approach and used to inform design and delivery adjustments across AFFY programme.