## Annual Review

Title: LIGHT (Leaving no-one behInd: transforming Gendered pathways to Health for TB)
Programme Value £ (full life): £7,903,834		Review date: 18/10/2025
Programme Code: 301138	AMP start date: 18/03/2020	AMP end date: 30/04/2026

Summary of Programme Performance
Year	2021	2022	2023	2024	2025
Overall Output Score	A	A	A+	A+	A++
Risk Rating	Moderate	Moderate	Minor	Minor	Minor

DevTracker Link:	DevTracker Programme GB-CHC-222655-LIGHT

A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]

An estimated 10.8 million people fell ill with tuberculosis (TB) globally in 2023, an increase from 2022, reversing a long-term downward trend as stated in the World Health Organization's 2024 Global Tuberculosis Report. Most affected are adult men (aged from 15 years onwards) at 6.0 million cases vs 3.6 million women and 1.25 million children (see figure from WHO 2024 Global TB Report). Globally, an estimated 1.25 million people died from TB in 2023. Although this represents a slight decrease from 2022, TB is once again the world’s leading infectious disease killer.

To research interventions addressing the gender disparity in TB incidence, Leaving no-one behind: transforming Gendered pathways to Health for TB (LIGHT) is a six-year cross-disciplinary global health research programme led by the Liverpool School of Tropical Medicine (LSTM) working with partners in Kenya, Malawi, Nigeria, Uganda and the UK. LIGHT aims to support policy and practice in transforming gendered pathways to health for those with TB in urban settings to improve health and wellbeing, socio-economic and equity outcomes and to prevent the spread of TB. The research programme will do this by enabling and supporting global and national policy environments and health systems to improve sustainable, equitable access to quality TB services and medical products, to reduce TB mortality and morbidity among men, women and children.

LIGHT:
- Generates new evidence to improve male access to quality TB healthcare services in urban environments and to more effectively prevent the spread to the wider population, particularly women and girls.
- Strengthens capacity to generate evidence and promote demand for services.
- Engages effectively with key stakeholders.
- Conducts monitoring, evaluation and learning throughout the programme.
LIGHT’s team is described in this short video. This Annual Review describes the 5th (penultimate) year of the research consortium.

LIGHT’s partners are depicted here:

Summary supporting narrative for the overall score in this review [1-2 paragraphs]

LIGHT has substantially exceeded expectations and has performed as model research programme consortium in its three output areas. For its research output, it has generated considerable and pivotal evidence, which is complete to a large extent, as evidenced by the many research publications already available. This includes, for example, the IGNITE project in Uganda which used participatory approaches to identify interventions in Uganda in search of the ‘missing men’, and the DESTINE project, which focused on gender disaggregation of TB care in Nigeria or the comparative evaluation of diagnostic means in Malawi (cautioning against using the less laboratory resource intensive QIAreach QuantiFERON-TB test in comparison to the gold standard which remains significantly more sensitive). Other research took a much more cross-cutting approach and modelled the population level impact of increasing TB treatment coverage addressing determinants of risk in men in Kenya, Malawi, Nigeria and Uganda.

Critically, LIGHT’s capacity strengthening (under output 2) impacted not only directly on its research skills and expertise but also helped to influence government policy, such as Nigeria’s National Strategic Plan (NSP) for TB Control 2021-2026. Importantly, LIGHT was also able to train media journalists (45) in Nigeria, which led to more adequate, accurate and evidence-informed health reporting in the country. Such reporting skills support journalists to bridge the gap between scientific research and the public understanding of complex health topics such as TB. It also is a stepping stone towards fighting mis- and disinformation around health topics.
LIGHT’s media training also helped journalists to advance their careers, such as a Health Journalist who won the AFIDEP 2024 Special Media Award on TB and Gender by reporting on TB-HIV related stigma and gender inequalities.

In its third output on research uptake, LIGHT has again outperformed against expectations in producing a range of parliamentary briefs for various countries but also the research using innovative photovoice, which have culminated in photovoice booklets. LIGHT researchers have in various countries increasingly been invited to take part in national and regional strategic debate and thus had direct influence using LIGHTs generated evidence. For example, LIGHT is now part of the taskforce for the Division of TB and Lung Diseases in Kenya to streamline and structure TB and Lung Health, Research and Dissemination activities for the future National Strategic Plan.

Given the penultimate year of LIGHT, we did not adjust the milestones (upward) following last year’s AR in order to reflect fairly on the overall progress of the programme, as work on most outputs has started already much earlier in the course of the programme.

Major lessons and recommendations for the year ahead [1/2 page]

As evidenced in the previous paragraphs and in Section C below, LIGHT, through its capacity building enjoyed major impact not only on its partners’ research skills but also in national strategies and guidelines. This has helped the uptake of the evidence generated by LIGHT. The LIGHT team has also maximised on its partnership with Southern research partners who form core parts of the consortium and carrying the LIGHT evidence and influence national and regional debate.

LIGHT is well underway to achieve its stated objectives, and, ultimately, impact.

Recommendations

LIGHT should, in its final year, concentrate on the consolidation and dissemination of evidence.

In addition, to the extent possible and within the power of the consortium, LIGHT should gather data and evidence to demonstrate on how it has met its impact indicators in addition to its generated outputs and outcomes.

Finally, it is clear that LIGHT will leave a positive legacy as has been expressed already by FCDO’s independent Mid-Term Evaluation (MTE). The LIGHT team could further expand their considerations on how to maximise this legacy and sustainability of LIGHT’s generated evidence.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

LIGHT’s Theory of Change remains unchanged and valid to achieve its stated aims and objectives. The emphasis on researching gendered approaches towards diagnosis and treatment of TB remains highly important in order to reduce the global TB burden. LIGHT thus aims to have an impact on reduced transmission, catastrophic costs and adverse TB treatment outcomes (mortality and case fatality) from TB resulting from a more effective, gender-sensitive health policy and practice response.

LIGHT aims to contribute to the impact through the following outcome: Global and public health policies, programmes, organisations and initiatives in target countries adopt or strengthen TB prevention and control policies and strategies, based in part on LIGHT evidence, such that they are gender-sensitive, pro-poor and able to support introduction and scale-up of new TB-related products by 2025 to meet global TB targets.
LIGHT aims to leave no-one affected by TB in sub-Saharan Africa behind. The research programme does this by enabling and supporting global and national policy environments and health systems to improve sustainable, equitable access to quality TB services and medical products, to reduce TB mortality and morbidity among men, women, and children. TB affects people of both sexes in all age groups, but there are more men than women with TB and dying from TB.
There were no changes to impact statements; and, following minimal changes to the wording of the outcome statement in previous years to clarify the role of LIGHT, there have been no further changes to the Theory of Change or logframe in the reporting year. Equally, the number and wording of the outputs have remained valid.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]

LIGHT has performed highly throughout its lifetime and is expected to meet the defined outcome and contribute to the impact within the allocated budget originally planned. The impact indicators have been set for the end of the programme and LIGHT will need to seek evidence on how far these have been achieved with LIGHT’s contribution.

The indicators for measuring progress towards the outcome were
1. Number of TB policies, guidelines or manuals/operational handbooks adopted or strengthened to incorporate gender responsive components resulting from LIGHT evidence and research uptake, evidenced at the a) National level, b) Regional level, and, c) International level, as reflected in LIGHT case studies; and,
2. Case studies demonstrating progress over time from engagement towards adoption of LIGHT recommendations into country and international guidelines, drawing on the successful delivery of LIGHT output.
Both indicators have been substantiated by relevant case studies with more cumulative case studies than originally anticipated: For (i) one additional case study was available this year (with a cumulative total of 5 (target 3). For (ii) one additional case study was showcased in the reporting period (with cumulative achievement of 9 (target 7). Overall, as is also evidenced in Section C below, global and public health policies, programmes, organisations and initiatives in target countries are starting to adopt and strengthen TB policies and strategies based on LIGHT evidence. This is demonstrated, for example, by the influence of LIGHT on WHO to improve their data reporting practices and country TB strategies and guidelines.

This programme is well on track to show strong impact as evidenced by exceeding outcomes already. The programme is in line with the UK’s ambition towards global health and development as well as furthering the evidence to fight the global TB epidemic.

LIGHT, along with all other Research Programme Consortia in the Global Health Research Team has been evaluated externally. This evaluation assessed LIGHT as a “high performing RPC, successfully delivering outputs and contributing to strategic initiatives.” Key factors to its success were described as “strong strategic planning and stakeholder engagement (particularly with LMIC government stakeholders) to keep research relevant”, and, “rigorous capacity strengthening for quality research and evidence translation for different audiences”. It was also commended for its “strong leadership”, which enabled “adaptation to challenges and capitalising on opportunities”. The evaluation also highlighted “strong VfM” and a likelihood “to leave a positive legacy”. There were only very few areas with room for improvement, including an “opportunity to further enhance equity of overall and financial management […] to create an even more equitable partnership”.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio [1 paragraph]

The Programme is highly contributory to the UK’s research agenda for diseases of poverty and leaving no-one behind. Given its overwhelming achievements, the programme, which has entered its final year, should continue. FCDO is in discussions with the programme to extend the programme duration for 5 months to allow for publication and dissemination of some of its findings.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	New evidence-based on the options and approaches for 1) maximising the numbers of marginalized adolescent, young adult and adult males accessing health care services; 2) increasing TB diagnosis, care and prevention among marginalised adolescent, young adult and adult males; and 3) improving health and social outcomes for people living in high TB burden settings.
Output number:		1	Output Score:	A++
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Cumulative milestone(s) for this review	Progress
1.1 Number of research projects aligned to LIGHT's Research Framework	a) Design stage: 0 / b) Implementation stage: 0 / c) Analysis stage: 4 / d) Completed: 0	Substantially Exceeded / a) Design stage: 0 / b) Implementation stage: 1 / c) Analysis stage: 4 / d) Completed: 5
1.2 Number of open-access externally peer-reviewed conference abstracts, research publications and synthesis products, aligned to the DORA principles.	a) Lead author based in LMIC: 7 / b) Female lead author: 7 / c) Female LMIC-based lead or co-author: 7 / d) Research publications: 9 / e) Other research products (incl. conference abstracts and posters): 11	Substantially Exceeded / a) Lead author based in LMIC: 34 / b) Female lead author: 33 / c) Female LMIC-based lead or co-author: 25 / d) Research publications: 20 / e) Other: 50
1.3 Number of tools, innovations, national and global guidelines, and processes that include consideration of LIGHT’s new approaches to support interventions with gender components, including replicable innovations and additionality.	5	Exceeded / 8 in total

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

Overall, LIGHT has substantially exceeded expectations for this output, demonstrated especially by the high count of published papers.

For indicator 1 (substantially exceeded): At the end of Year 5, most LIGHT projects are either well into the analysis phase or completion, which is expected at this stage. One project which was only recently added is in implementation. This project will explore experiences and views among participants in Blantyre, Malawi. The overall number of projects far exceeded the anticipated number and progress through the phases was progressed significantly further in this reporting year.

For indicator 2 (substantially exceeded): During the reporting year, 8 of LIGHT’s papers (out of 20 submitted manuscripts) have been published, most in high-impact journals. While LIGHT already exceeded targets in the previous reporting year, the number and importance of the publications this year alone have been outstanding. Several of these papers are demonstrating ground braking novel evidence that will be critical in the understanding of the global TB prevalence and how to address these.

1. Co-creation of a gender responsive TB intervention in Nigeria: a researcher-led collaborative study-BMC Health Services Research
2. Finding the Missing Men with Tuberculosis: A Participatory Approach to Identify Priority Interventions in Uganda-Health Policy and Planning
3. Low concordance between QIAreach QuantiFERON-TB, a novel interferon gamma release assay, and QuantiFERON-TB Gold Plus, in a population-based survey in Blantyre, Malawi-Journal of Clinical Microbiology
4. Gender disaggregation of the tuberculosis care cascade in Nigeria: a four-year retrospective study 2018 - 2021-Public Health Action
5. Scaling-up symptom-agnostic, community-wide screening towards global tuberculosis elimination: opportunities, challenges and lessons from history. - International Journal of Infectious Diseases (IJID)
6. Sex Differences in the Risk of Mycobacterium Tuberculosis Infection: A Systematic Review and Meta-Analysis of Population-Based Immunoreactivity Surveys-The Lancet Infectious Diseases
7. Comment to The Lancet Public Health on Mass incarceration as a key driver of gender disparities in tuberculosis-The Lancet Public Health
8. Comment: Addressing the growing TB disease burden in England - The Lancet Respiratory Medicine

Four of these eight papers have a female first author and include female co-authors based in LMICs. One paper has a female first author from LMICs, and two papers have a male first author from LMICs.

Two further papers are in pre-print status (not included in the count towards the indicator).

LIGHT have also had 15 conference abstracts accepted at major conferences and symposia (out of 38), with 10 of those at international and 5 at national events. This included a panel: Provide comprehensive care to all people with or at risk for TB and Leprosy. Strengthen multisectoral accountability. 6 of 7 posters were also accepted.

For the third indicator under this output (exceeded), LIGHT report two additional examples of tools, innovations, national and global guidelines, and processes that include consideration of LIGHT’s new approaches:
1) In September 2024, a two-day workshop was conducted to co-create gender-responsive messages aimed at increasing men’s uptake of TB services in Uganda in response to the finding that TB is four times more prevalent among men than women, who are significantly less likely to seek diagnosis and care. Participants drafted over 30 messages focused on masculinity, nutrition, and rights-based access to TB services and care. They also developed targeted message packages for male populations vulnerable to TB for key decision makers. The team in Uganda is now pre-testing the drafted messages before finalising and sharing with NTP.
2) The National TB Control Programme in Nigeria domesticated the WHO recommended Multi-sectoral Accountability Framework for TB known as MAF-TB for tracking the role of all sectors in achieving the country's commitments of the UN High Level Mission 2023. TB stakeholders including the LIGHT partner ZRC as well as LIGHT staff member participated and influenced the drafting the final document.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes have been made to the indicators of this output. The indicators remain highly relevant to monitor progress of this programme and demonstrate the excellent progress LIGHT have been able to achieve.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

Last year’s recommendation suggested – where political economy analyses were still outstanding - to demonstrate a deeper analysis in the political economy of the barriers beneath the absence of gender disaggregated data and approaches and what approaches could look like that would address these barriers more consistently. No further political economy studies have been added in this reporting year, however, some of the publication detail a very deep analysis of the gender differences in TB prevalence and how these can be addressed. To this end, LIGHT have fully taken on board our suggestion.

Output Title	Strengthened individual, institutional, and multi-stakeholder networks/platforms capacity in LIGHT countries to produce, adapt, translate, and use evidence and manage research.
Output number:		2	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Cumulative milestone(s) for this review	Progress
2.1 Number of people WITHIN the Consortium accessed training and learning and demonstrate an increased capacity in evidence production and translation and management of research.	220	Substantially Exceeded / 491 in total
2.2 Number of events where STAKEHOLDERS OUTSIDE the Consortium demonstrate increased capacity.	6	Substantially Exceeded / 14 in total
2.3 Number of events that strengthened INSTITUTIONAL capacity	7	Exceeded / 14 in total
2.4 Number of CASE STUDIES that demonstrate implementation of new training activities	4	Exceeded / 6 in total

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

LIGHT’s performance exceeded expectations for this output.

Described by indicator 1 (substantially exceeded), capacity building is taken very seriously within the LIGHT consortium and, during the reporting year, 94 instances of training were attended by consortium staff (cumulative over 5 years, 491 of a target of 220). During the first five years, LIGHT facilitated 387 training and learning events for people from within the LIGHT Consortium. 37 Males from LMICs, 41 Female from LMICs, 4 Males from HICs and 12 females from HICs attended training on covering grant writing, qualitative research, effective communication training, Systematic Reviews and Meta-Analyses in Healthcare, programming, and modelling. LIGHT also put an emphasis on the principles of safeguarding, gender mainstreaming, and Code of Conduct and ran a 2-day training for LIGHT staff at one of the partners in Nigeria (2-3 May 2024).

For indicator 2 (substantially exceeded), LIGHT delivered 5 multi-day training events targeting stakeholders outside the Consortium in this reporting period, bringing the cumulative total to 14 overall:
1. Training TB researchers on science communication to influence policy and practice (Uganda, June 2024): 29 attendees (11 M + 18 F). The training aimed to help researchers develop appropriate communication strategies for research projects, prepare communication products tailored to decision-makers, effectively deliver communication products (incl. policy briefs/memoranda for advocacy, social media, etc).
2. Photovoice training for researchers (Malawi, April 2024): 5 attendees (2 M + 3 F) underwent a training on how to conduct the photovoice study. The training included a simulation of a photovoice study to gain practical skills before the main study. The training was attended by LIGHT staff as well as from representatives from the Ministry of Health and the Ministry of Gender.
3. Five-day Capacity Training Workshop on Manuscript Development for Monitoring and Evaluation (M&E) officers across Nigeria and TB Researchers (Nigeria, October 2024): 33 attendees (20 M + 13 F) attended this workshop organised by ZRC in collaboration with the National TB and Leprosy Programme (NTBLCP).
4. Training of Media Journalists (Nigeria, September 2024) attended by 45 journalists (29 M + 16 F) to improve TB knowledge and reporting practices of health media journalists in Nigeria.
5. Photovoice Training for researchers and co-researchers (Uganda, February 2025): 10 attendees (2 M + 8 F) underwent a training on how to conduct the photovoice study in Uganda. The training was facilitated by MLI and by the LIGHT Gender & Equity Post-Doc and focussed on TB transmission, testing and treatment, as well as study protocol, recruitment, camera handling and photography techniques.
One of LIGHT’s partners (ReSoK) also organised three online continuous medical education (CMEs) events for medical staff from all over Kenya. These sessions have not been counted towards the achievement of this indicator as LIGHT’s role was limited. It does, however, demonstrate that LIGHT represents an important platform for partners to gather experts and provide training beyond the Consortium. A total of 1032 medical staff attended the sessions on TB State of the Art: Updates on diagnosis and treatment of TB in adults; Management of DRTB: What is new; TB state of the Art: Treatment of TB in children and adolescents.

For indicator 3 (Exceeded), LIGHT report on institutional capacity strengthening through 3 events in the reporting year: A governance training for board members at ReSoK (Nairobi, Aug-Oct 2024) was attended by 12 attendees. The training focused on Strategic Planning Processes with emphasis on the key objectives’ development with follow-up on the continuation and completion of strategic plan development. A training on Safeguarding, Fraud and Risk management at ReSoK (Nairobi, Aug-Oct 2024 was attended by 28 Project Assistants, 5 Project Officers, and 4 Finance & Administrative staff from ReSoK. The training was conducted by AMREF with LIGHT’s support. An internal Capacity Training Workshop on Manuscript Development and scientific writing skills (Abuja, 4-7 Oct 2024) was attended by 23 ZRC staff and students.

To support indicator 4 (exceeded), two additional case studies showing implementation of new training activities were submitted in an Annex to the report: Case Study 3 Enhancing media reporting on TB and Gender: LIGHT’s strategic engagement across four countries. And Case Study 4 Equipping Nigeria’s M&E officers to publish rigorous TB data in scientific platforms.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

No changes were made to this output in the reporting period. The Programme has shown great progress on all indicators, building sustainability beyond the programme duration through both individual and institutional capacity building. No changes are planned to this output for the remainder of the programme.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

This output has progressed well and beyond expectations and will help both to sustain research capacity beyond the programme’s duration as well as uptake of LIGHT’s generated evidence. It also supported governance of programme partners and safeguarding strengthening institutional capacity. Evidence-informed Decision Making (EIDM) training also resulted in the production of 4 policy briefs by government TB programmes. Notably, LIGHT’s training of media journalists led to demonstrably more adequate, accurate and evidence informed health reporting in Nigeria. LIGHT should be particularly commended for this achievement in light of increasing mis- and disinformation and should feel encouraged to share this skillset and training with other RPCs where appropriate and possible.

Output Title	High-quality LIGHT evidence products are influential in key policy discussions (showing how gender sensitive and/or specific policies can provide a strong driver for better access to TB diagnosis, care and prevention and health system integration.
Output number:		3	Output Score:	A++
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Cumulative milestone(s) for this review	Progress
3.1 Number of analyses (landscape analyses, stakeholders’ analysis, evidence, policy, political economy) delivered to inform and refine Research Uptake and communications strategies	7	Substantially Exceeded / 19 in total
3.2 Number of communications products aimed at engaging, informing, and influencing diverse stakeholders at national, regional, and global level	30	Substantially Exceeded / 109 in total
3.3 Number of examples of LIGHT Consortium engaging and/or influencing national, regional, or international expert panels/working groups/policy makers or networks.	a) Global / Regional: 6 / b) National: 14	Substantially Exceeded / a) Global / Regional: 25 in total / b) National: 48 in total

Briefly describe the output’s activities and provide supporting narrative for the score. [max 1/2 page]

LIGHT also substantially exceeded expectations for output 3.

Related to progress indicator 1 (substantially exceeded), LIGHT published five briefs that inform and refine Research Uptake and Communication Strategies:
1) Gender Equitable Solutions to Help End Tuberculosis Parliamentary briefing (Nigeria)
2) Parliamentary Brief for Malawi: "Towards Gender-Responsive Approaches to Ending TB in Malawi"
3) Parliamentary briefing Uganda "Towards Gender-Responsive Approaches to Ending TB in Uganda”
4) Gender Equitable Solutions to Help End Tuberculosis NEAPACOH Parliamentary briefing
5) A Health System Strengthening Approach to Person-Centred TB Care: Insights from Participatory Research with Healthcare Workers and Policymakers in Nairobi, Kenya

Additional/previous briefs by LIGHT are available on their website.

For indicator 2 (substantially exceeded), LIGHT has published 15 outputs in the ‘Communication’ category (see pie chart below). Effort is particularly focussed on producing audio-visual material (examples below; a full list is available in LIGHT’s Annual Report, Annex 6).

Videos published on LIGHT’s Consortium YouTube channel include:
- Jasper Nidoi, Early Career Researcher on the LIGHT Programme
- A Participatory Qualitative Study in Kenya
- 18th Joint Annual Scientific Health Conference (JASHC) 16-18 Oct 2024
- The LIGHT Consortium at The Union World Conference on Lung Health 12-16 Nov 2024
- The LIGHT Consortium commemorates World TB Day 24 Mar 2025
Three Photovoice booklets published on the LIGHT website:

- Putting people first: A participatory study with TB healthcare workers and policymakers in Nairobi, Kenya
- Uncovering lived experiences of young men and women affected by TB: a Photovoice study in Lilongwe, Malawi
- Gender-responsive tuberculosis prevention & care: a photovoice study Karu local government area Nasarawa State, Nigeria
Blogs and infographics have been produced in addition, not captured here in the indicators.

With regard to indicator 3 (substantially exceeded), LIGHT hast engaged and influenced policy debate and guidelines at global, regional and national levels.

At global and regional level 9 new engagements and 25 in total have been recorded. This included:
- LIGHT senior staff invited to take part to the WHO Meeting on TB Screening in Geneva (Oct-2024).
- LIGHT meeting with Chairpersons of the Parliamentary Health Committees - Anglophone Region - Global TB Caucus emphasising political leadership, resource mobilisation, regional collaboration, and innovative frameworks as central to addressing TB (Zambia). Oct-2024
- Post-NEAPACOH follow-up meeting to track progress on commitments made in Feb-2024 and advocate for resources and continued capacity-building efforts for legislators to use evidence-based policymaking (Zambia). Oct-2024
- 5th Africa TB Summit with parliamentarians from 18 African countries (Abuja). LIGHT supported the organisation of the summit, lobbied for the inclusion of social determinants such as stigma and gender disparities into the agenda, and gave a presentation on Gender Equity in TB Care (press coverage and here). Dec-2024
- ZRC lead invited to the Stop TB global meeting in Turkey (“United in Advocacy to End TB”) as academia representative for Nigeria (Jan-2025).
- MLI lead appointed to the WHO TB vaccine TAG for a 3-year term (Jan-2025).
- LIGHT work presented at the WHO Civil Society Task Force on Tuberculosis (CSTF), Feb-2025.
- 16th NEAPACOH conference during which the LIGHT team presented LIGHT’s research, showcasing the evidence from all LIGHT’s countries. A call for gender-responsive TB interventions for men was made (Mar 2025).

At national level, 18 new engagements were recorded in LIGHT’s annual report. As a prominent example LIGHT is now part of the taskforce for the Division of TB and Lung Diseases in Kenya to streamline and structure TB and Lung Health, Research and Dissemination activities for the future National Strategic Plan.

Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

There was no change to this output during the reporting period. LIGHT has increased its engagement and influence both at national, regional and global levels and is a reputable voice for gender considerations in addressing TB prevention, diagnosis and treatment.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

In the previous Annual Review, we suggested that LIGHT focus on its own outputs and focus, which has been adopted.

## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

The LIGHT Consortium continues to uphold FCDO principles of Value for Money (VfM) across all operations. VfM is assessed through the four key pillars: economy, efficiency, effectiveness, and equity, with a focus on sustainability and impact maximisation.

Economy
- Procurement of materials (e.g., educational flyers, banners) for TB awareness campaigns in Nigeria was conducted via competitive local sourcing, ensuring cost savings without compromising quality.
- Budget allocations were regularly reviewed and adjusted, with reductions in non-essential consumables and capital expenditure, and leveraging complementary funding from other consortia to cover staff costs, reducing overall programme spend.
Efficiency
- Resource sharing, travel optimisation, and streamlined procurement processes have led to cost reductions and improved operational efficiency.
- In Kenya, community feedback meetings were consolidated by engaging TB Champions and administrators, reducing the need for multiple events and saving time and resources.
- The Consortium has successfully leveraged AI to maximise efficiency in research and administration.
Effectiveness
- LIGHT demonstrated increased efficiency in translating research into policy uptake through improved research design, data collection, and knowledge sharing.
- In Uganda, appointing project officers to support LIGHT activities (rather than transferring funds to NTLP) enhanced engagement and effectiveness in developing the National Strategic Plan, ensuring gender was included as a key component.
Equity & Sustainability
- Programmes specifically targeted marginalised and peri-urban communities, ensuring inclusivity and fair access to health information.
- Gender and equity were mainstreamed into planning, implementation, and monitoring, with training planned for Makerere Lung Institute staff and disability inclusion measures (e.g., accessible ramps).
- LIGHT monitors gender parity in capacity building and research activities, seeking affirmative action for marginalised groups where appropriate.

FCDO partnered with Tropical Health to carry out a Mid-Term Evaluation of LIGHT in order to understand and assess its overall success. In its conclusion regarding VFM for LIGHT, it states that LIGHT has consistently demonstrated robust value for money and is well positioned to leave a lasting impact. The programme’s design enables the delivery of pertinent research, underpinned by effective engagement with stakeholders at every level. Intended outputs have been achieved through strong leadership, strategic use of resources, and ongoing capacity building among partners. LIGHT has already shaped important strategic initiatives, and the foundations are in place for its research to inform future policy and planning. This solid performance across efficiency, effectiveness, equity, and economy provides a strong basis for sustainability beyond the current FCDO funding.

The LIGHT programme continues to represent strong Value for Money. It delivers on economy, efficiency, effectiveness, and equity, with robust financial management and risk controls. The programme adapts to feedback, maximises impact, and maintains transparency, ensuring that UK aid investment is well-managed and delivers sustainable results.

E: RISK [½ to 1 page]

Overview of risk management [1/2 page]

The LIGHT programme maintains a comprehensive risk register reviewed monthly by the Programme Management Working Group (PMWG), which are submitted quarterly. The overall risk rating for Year 5 (2024/25) was assessed as ‘Minor’, with all risks within the LIGHT and FCDO risk appetite.

Strategy and Context	Policy and Programme	Safeguarding	Public Service Delivery and Operations	Financial and Fiduciary	Reputational	People
Minor	Minor	Moderate	Moderate	Minor	Minor	Moderate

- Strategy and Context (Minor): Risks mainly around political instability, civil unrest and extreme weather events. These are monitored through regular partner check-ins, election schedule tracking, and real-time updates. Travel risk assessments are mandatory, and activities are adapted to avoid high-risk periods or locations. Recent violent demonstrations in Kenya led to postponed travel, and upcoming general elections in Malawi (September 2025) may pose inflation risks, flagged to the Finance Manager.
- Policy and Programme Delivery (Minor): Risks include delays in ethical/protocol approvals, turnover of in-country leads, and concerns about research outputs being robust or taken up into policy. These are managed proactively, with no anticipated increase in impact.
- Public Service Delivery and Operations (Moderate): Although unlikely impacting this programme, the risk of wider ODA funding reductions (not only from the UK) may negatively impact uptake and implementation of LIGHT’s findings.
- People (Moderate): Staff turnover remains a concern and is increasing as the funding period ends, although all vacancies have been filled and new staff onboarded.
- Safeguarding (Moderate): The rating is reflected as ‘moderate’ by LIGHT, which we concur with. Mitigation includes regular safeguarding training, monthly reviews, and embedding safeguarding in all research protocols.
- Financial and Fiduciary (Minor): Risks include demonstrating Value for Money (VfM), fraud/misuse of funds, and exchange rate fluctuations. These are managed through regular reporting, cost-reduction strategies, and procurement efficiency.
- Reputational (Minor): No change; research topics are not controversial, and findings are not expected to be contentious.

The LIGHT programme’s risk management systems are robust and responsive, with risks actively monitored and mitigated. Political instability and inflation (especially in Malawi) were key risks for 2025, but the programme is well-prepared to adapt activities as needed. Safeguarding and financial management remain priorities, and lessons from previous years have strengthened overall risk management.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Financial Overview

The LIGHT Programme’s original budget was £7.9m, with total spend as of 31 March 2025 at £6.0m. There is an underspend of £402,737.60, which will not be rolled over. The budget for Year 6 is £1.4m, and for Year 7 is £58k. Personnel costs are the largest expenditure (74.5%), followed by programme costs (13.8%) and travel (6.3%). All budget lines show healthy balances, with no significant overspend or financial risk identified.

Financial Management and Reporting

The consortium has maintained accurate financial forecasting, with FCDO variance limits largely respected. Communication with partners regarding budget spend and progress has increased, and spot checks on partners’ quarterly expenditures have been initiated to ensure compliance with project and budget guidelines. This has improved clarity and traceability of payments for partners. The system for financial management includes quarterly emails to partners summarising their financial situation and proposed disbursements, which has improved transparency and efficiency.

To strengthen financial transparency and accountability regarding expenditure, variances, and fund transfers to partners, LIGHT have implemented a structured system of quarterly communications. At the end of each quarter, LIGHT provide each partner with a tailored summary of their financial position, based on their submitted financial reports, along with a detailed explanation of proposed disbursements. This enhanced process has significantly improved the clarity of financial information, facilitated more effective communication, and enabled partners to accurately track payments through their respective banking and finance offices.

Personnel cost has been the most significant cost for the programme so far, at 74.53% with programme costs at 13.79% and travel at 6.26%. The total amount spent (GBP) as per 31-Mar-2025 can be seen in the table below:

Budget Lines	Total Budget	Reported Spend	Remaining Balance	Budget Balance %
Fees	5,682,457.05	4,491,219.21	1,191,237.84	21%
Travel	556,406.12	377,240.32	179,161.80	32%
Equipment	153,846.57	134,716.62	8,129.95	5%
Programme Costs	1,293,983.82	830,673.62	463,310.41	36%
Overheads	217,144.21	180,995.62	36,148.59	17%
TOTAL	7,903,833.76	6,025,845.18	1.877,988.58	24%

Delivery and Commercial

In Year 5, several changes occurred in staff composition and full-time equivalent (FTE) allocations. In April 2024, the Gender & Equity Post-Doctoral Research Associate reduced their hours to 50% FTE after securing a British Academy grant as Principal Investigator and successfully applying for the LSTM career track. In May 2024, the LIGHT RU Manager at LSTM increased their FTE to 80%. In November 2024, the MLI lead was promoted to Principal of the Makerere University College of Health Sciences (MakCHS). In January 2025, the Research Uptake Manager (RUM) at AFIDEP Malawi resigned and was replaced by a new RUM. Similarly, the RUM at AFIDEP Kenya resigned in January 2025 and was replaced by a new RUM, who will commence in May 2025 on a consultancy basis.

For Year 6, several planned changes in staffing and FTE allocations are anticipated. In April 2025, the LSHTM Lead adjusted her FTE to 61% following the conclusion of the LSHTM-based researcher contract, while the MLI Research Uptake Manager increased her FTE to 40% to support the intensified efforts required for translating research into policy and practice during the final year of LIGHT. In May 2025, the Health Economist at LSTM secured a new position, resulting in a reduction of their commitment to LIGHT to 20% FTE. In June 2025, a qualitative researcher will be appointed at MLW (Malawi) to investigate knowledge, perceptions, and attitudes towards TB infection, as well as willingness to receive TB interventions as part of the BeatTB initiative. This researcher will begin at 50% FTE in June and transition to full-time from July until the end of LIGHT. Additionally, the LIGHT Communications and Policy Engagement Manager at AFIDEP Malawi was replaced. In August 2025, the Research Uptake Manager at AFIDEP Malawi resigned and was succeeded by a new RUM.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

The LIGHT programme’s monitoring and evaluation is guided by its Theory of Change and Logframe. These frameworks focus on three main outputs: Research, Capacity Strengthening, and Research Uptake, and are used to track progress towards the programme’s impact of reducing TB transmission, catastrophic costs, and adverse treatment outcomes through gender-sensitive health policy and practice

Throughout the review period, the LIGHT Consortium implemented a robust system of monitoring activities, including regular field visits, reviews, and extensive engagement with stakeholders and beneficiaries. Key activities included:

Quarterly financial and technical reporting: Partners submitted detailed reports, which were reviewed to ensure alignment with project implementation. Spot checks on partners’ quarterly expenditures were conducted to ensure compliance with project and budget guidelines. Each partner received a clear summary of their financial situation and proposed fund disbursements, improving communication and enabling partners to trace payments within their organisations.

Field visits and stakeholder engagement: The LIGHT CEO visited Uganda and Malawi, and ZRC in Nigeria conducted a two-day mid-term review meeting with the Local TB Action Group (LTAG), sharing findings and co-creating materials for community engagement. Monthly meetings with the Community Scientific Advisory Board in Malawi facilitated ongoing dialogue with local TB officers, discussing diagnosis and treatment success data.

Beneficiary feedback: Participatory studies such as the photovoice project in Malawi and Uganda captured the lived experiences of young people affected by TB, highlighting economic and psychosocial challenges. These insights informed the design and delivery of interventions and advocacy materials

In Year 5, LIGHT completed an external independent mid-term evaluation. The evaluation highlighted effective value for money (VfM) through cost-reduction strategies, increased efficiency in research translation, and robust systems for financial management. The evaluation also noted the positive impact of capacity strengthening and community engagement on programme outcomes. Lessons learned from the evaluation informed subsequent programming decisions, particularly in prioritising sustainability and maximising impact

Evidence

In 2025, LIGHT completed and published several research projects, including TB prevalence surveys, modelling studies, and participatory research across Kenya, Malawi, Nigeria, and Uganda. These studies have provided new insights into gendered pathways to TB care, social determinants of risk, and barriers to access for marginalised groups.

Notably, Nigeria’s National Strategic Plan (NSP) for TB now includes a new objective focused on “Human rights and gender considerations in provision of quality TB services”, directly attributed to LIGHT’s evidence and advocacy. This marks a strategic shift towards more inclusive, gender-responsive TB programming.

The evidence base has expanded to include qualitative and quantitative data, peer-reviewed publications, conference presentations, and policy briefs. There is a strong focus on implementation research, capacity strengthening, and research uptake, with outputs influencing policy and practice at national and regional levels

LIGHT’s approach aligns with the ‘Leave No One Behind’ agenda, ensuring that marginalised and vulnerable groups are included in research, policy, and programme activities. LIGHT’s monitoring data and research outputs are disaggregated by age, sex, geography, and, where possible, disability and other relevant variables. For example:

- TB prevalence surveys in Malawi and Kenya are disaggregated by age and sex, revealing higher exposure and risk among men and young people.
- Participatory studies and photovoice projects highlight the experiences of young men and women, including economic, educational, and psycho-social impacts.
- Disability inclusion is addressed through infrastructure improvements (e.g., ramps at clinics) and monitoring participation in research and capacity building by gender and other characteristics.

LIGHT’s approach aligns with the ‘Leave No One Behind’ agenda, ensuring that marginalised and vulnerable groups are included in research, policy, and programme activities.

Learning

LIGHT has facilitated almost 400 training and learning events for consortium members over five years, with 94 training activities in Year 5 alone. Topics included grant writing, qualitative research, communication, systematic reviews, programming, and safeguarding. A 2-day safeguarding training was held for staff in Nigeria.

Participatory Events and Workshops: LIGHT organised a wide range of learning events, including Evidence-Informed Decision Making (EIDM) Training of Trainers, media science cafés, media breakfasts, and parliamentary briefings. These events brought together policymakers, researchers, journalists, and TB stakeholders to share evidence and co-create solutions

Capacity Strengthening Workshops: Targeted training for Monitoring & Evaluation officers, TB researchers, and media professionals was delivered, focusing on research design, scientific writing, policy communication, and ethical research conduct. These workshops included practical exercises, peer review, and mentorship

Stakeholder Engagement: Ongoing engagement with national TB programmes, parliamentary committees, and regional bodies (e.g., NEAPACOH, WHO AFRO) ensured that lessons and evidence were translated into policy and practice.

Internal Reflection and Peer Learning: Reflective discussions, scenario-based exercises, and feedback sessions were integrated into training programmes to consolidate learning and identify actionable steps.

Sustained engagement and capacity strengthening have established LIGHT as a trusted technical partner, enabling greater influence on national TB strategies and policy processes. Active involvement in NSP reviews and policy briefings has demonstrated the importance of timely, accessible evidence for informing national priorities and driving gender-responsive TB programming. Involving TB survivors, healthcare workers, and communities in research and advocacy has generated richer, more relevant evidence and fostered ownership of solutions.

Conclusions from Mid-Term Evaluation

- LIGHT is a high performing RPC, successfully delivering outputs and contributing to strategic initiatives. Key success factors are a) Strong strategic planning and stakeholder engagement (particularly with LMIC government stakeholders) to keep research relevant; b) Rigorous capacity strengthening for quality research and evidence translation for different audiences; and c) Efficient leveraging of RPC partners to share and apply research across contexts.
- Strong consortium leadership has been a crucial foundation: It has supported successful capacity strengthening of RPC partners and a positive working relationship across the RPC. Strong management has also enabled adaptation to challenges and capitalising on new opportunities/ positive unintended outcomes.
- LIGHT has shown strong VfM to date and is likely to leave a positive legacy: It has been successfully designed to deliver relevant research through strong engagement at all levels; it has delivered intended outputs through effective leadership and leveraging and capacity strengthening of partners; it has already influenced key strategic initiatives and conditions are in place for research to contribute to future policies and plans. This strong performance across efficiency, effectiveness, equity and economy all support longevity beyond the current FCDO grant
- LIGHT’s integration of gender is robust and may offer insights at a critical time for GESI in development work: its framing of gender-responsive TB research has been accepted at global and national levels by different stakeholders, and its inputs into wider debates on masculinity within and beyond TB and health are especially relevant in the current development context.
- LIGHT’s internal governance and processes are seen as mostly transparent, supportive and equitable, but there is an opportunity to further enhance equity of overall and financial management across Northern and Southern partners and create an even more equitable partnership.
- LIGHT has learned to navigate FCDO’s contracting and budget requirements relatively well, but the nature/requirements of the current commercial contract is seen as a particular challenge both for Lead and Partner organisations, constraining LIGHT’s ability to adapt to contextual challenges.

Date of last narrative financial report	Aug 2025	Date of last audited annual statement	Nov 2024