## Annual Review Template

Title: Responding to the need of Women and Children in Yemen
Programme Value £ (full life): £160,000,000		Review date:
Programme Code: 301140	AMP start date: 05/07/2023	AMP end date: 13/03/2027

Summary of Programme Performance
Year	23/24	24/25
Overall Output Score	A	A+
Risk Rating	Severe	Severe

DevTracker Link to Business Case:	Link
DevTracker Link to results framework:	Link

Scoring your programme

The Annual Review assesses and rates outputs using the following scale. The Aid Management Platform (AMP) and the Programme scoring calculator will calculate the overall output score, taking account of the weightings and individual output scores.

Description	Score
Outputs substantially exceeded expectation	A++
Outputs moderately exceeded expectation	A+
Outputs met expectation	A
Outputs moderately did not meet expectation	B
Outputs substantially did not meet expectation	C

A. SUMMARY AND OVERVIEW
Description of the Programme
This annual review covers Year Two (April 2024-March 2025) of The Women and Children (W&C) programme (one of two flagship UK humanitarian programmes in Yemen) with a budget of £160m over 4 years. The Programme has expanded in scope since last year with the addition of IOM as a partner, adding a focus on migrants, IDPs and their health and protection.

This programme has scored A+. Despite an extremely challenging operating environment over the reporting period, partners have all achieved significant delivery for the most vulnerable in Yemen. The Programme remains both relevant and achievable over its final two years, however FCDO must now refocus resources to meet the 0.3% target and budget restrictions will require some difficult decisions to be made in the coming months.

The Programme is intended to deliver against two outcomes:
1. Reduce preventable disease and death in women and children by providing primary health care (PHC) and nutrition, water hygiene and sanitation, and sexual and	reproductive health services, to the most vulnerable in Yemen.
2. Increase protection for women and children by preventing and responding to gender-based violence, assisting and protecting people in conflict.

The Programme intends to deliver the impact for Women and Children to survive and thrive in Yemen. This aim is to achieve this through three outputs investing in 1) systems 2) services and 3) protection and delivered through a flexible approach with a strong emphasis on monitoring, evaluation, accountability, research and learning.
The context in Yemen has been extremely volatile over this reporting period and the complex and protracted humanitarian crisis continues. Yemen has seen fluctuating conflict dynamics, internal displacement, deteriorating socio-economic conditions and further cholera outbreaks (which saw the country experience the world’s highest number of cholera cases in 2024 with more than 800 related deaths). Furthermore, collapsing public services and the withdrawal of most humanitarian actors from the North have all increased vulnerability, with the North having the most severe needs. The number of people in need of humanitarian assistance has increased from 18.2 million in 2024 to 19.5 million in 2025 but the amended Humanitarian Needs and Response Plan (HNRP) targets only 8.8m people. Over 17 million people, nearly half of Yemen’s population, are estimated to be acutely hungry. In the North, prior to December 2024 over 330,000 people were suffering with severe acute malnutrition (SAM). Compounding the dire humanitarian situation in Yemen further, over 300,000 migrants left Ethiopia and crossed Djibouti to transit through Yemen to work in the Gulf in 2024; double the number of migrants who cross the Mediterranean. The Eastern Corridor is Africa’s busiest migration route and numbers doubled between 2022 and 2024.
[note] Epidemic of Violence: Violence Against Health Care in Conflict, 2024. Safeguarding Health in Conflict Coalition Annual Report
[note] Humanitarian Needs and Response Plan 2025
[note] Source: Nutrition Cluster, via FCDO Yemen Health Adviser

The more urban North is controlled by the Houthis, and the less populated and more rural South is controlled by the Internationally Recognised Government (IRG). Yemen’s peace process has stalled and the ongoing fragmentation with dual power centres, continues to challenge coherent policy and service delivery. Service delivery has been further hampered by the threat of detention for humanitarian workers and the ‘brain drain’ as people leave Yemen. The fragile health system has further suffered with incidents of violence against, or obstruction of, health care reported throughout 2024.

The environment remains challenging in terms of effective protection. Whilst conflict incidents impacting civilian and civilian structures have decreased slightly from the previous year, the number of fatalities and injuries has remained almost the same (see the Civilian Impact Monitoring Project (CIMP) reporting, below). The response requires a high degree of conflict sensitivity in its programming and this needs to be factored into any future programme revision/re-design. Women and girls face particular vulnerabilities. Yemen is rated 176 out of 177 countries on the Women Peace and Security (WPS) Index.  Women face increasing levels of violence, early and forced marriage, restricted freedom of movement.
[note] WPS Index Executive Summary

Through the past year, the humanitarian response has faced three major concurrent shocks; humanitarian aid worker detentions, US Foreign Terrorist Organisation (FTO) designation and USAID funding cuts. In June 2024, the Houthis reportedly detained over 50 humanitarian workers, some of whom were former diplomatic staff for Western Embassies in Sana’a. 23 of these staff were from the UN and INGOs, including W&C BC partners. The UN responded with a ‘programme criticality’ exercise where development funding was deprioritised, whilst lifesaving and life-sustaining activities in the North, were retaining activities. In January 2025, there was a new round of detentions in Sa’dah Governorate (in the North of Yemen). Unfortunately, one WFP staff member died in detention. The UN then made the decision to suspend all operations in Sa’dah as they could no longer justify the risks of operating. Around the same time the US started to terminate humanitarian funding and then in March 2025 it designated the Houthis a Foreign Terrorist Organisation (FTO). These combined events meant all the W&C programme’s partners faced challenges to some extent.

- The RISE consortium (IRC and local partners) came onboard at the end of the first year of the Programme but had to cease operations in the North in March 2025 due to the US FTO designation. IRC made the decision to de-risk as a US based organisation, feeling the level of liability was higher than they could effectively manage. They were one of 11 US based INGOs that did the same. As such, FCDO reprogramming was sought in February and approved the same month with a reduced budget. The RISE consortium has also had to suspend operations with the two Yemeni NGOs operating in the North, ‘Building Foundation for Development’ (BFD) and Abs Development Organisation (ADO).
- UNICEF suspended all operations in Sa’ada Governorate in March 2025 following the death of a UN staff in custody following a wave of detentions, along with all other UN agencies. UNICEF also reallocated activities in the North in September 2024 to continue programming lifesaving interventions, including normal operating of the Primary Healthcare Care facilities (including the treatment of malnourished children and vaccinations services), but deprioritising other activities following a further deterioration in the operating context and US funding cuts. UNICEF had previously requested reprogramming in September 2024 to respond to the UN ‘programme criticality’ exercise to cease development activities (capacity building, solar panels for health facilities and water network repairs) but continue lifesaving and life sustaining activities.
- During this reporting year, two sub projects were delivered by UNICEF, a $3m partnership with the Kuwait Fund to support a combined 290 PHCs that the World Bank could no longer support, and a $10m joint project with KSrelief to respond to the resurgence of cholera. Both started in Q3 of the financial year and finished at the end of March 2025. During this reporting period the Programme also began funding the Civilian Impact Monitoring Project (CIMP) via UNICEF to monitor the incidents of conflict impacting civilians.
  [note] Kuwait Fund for Arab Economic Development - UK and Kuwait agree new partnership to provide vital aid in Gaza and Yemen - GOV.UK
  [note] King Salman Humanitarian Aid and Relief Centre - KSRelief, UK Foreign Office to Expand Cholera Response in Yemen
  [note] civilianimpactmonitoring.org
- IOM, after starting operations with the Programme in October 2024, had to cease activities in Sa’dah and were significantly impacted by the termination of US funding in early 2025, losing substantial support and having to significantly cut staff and restructure.

The barriers and challenges partners experienced this year have had a detrimental effect on achieving several milestones, but partners were adaptable and resilient, activities did continue, and partners continued to deliver with achievements recorded below.

Summary supporting narrative for the overall score in this review
The Business Case for this programme states that ‘’The W&C programme aims to tackle the greatest causes of excess mortality and suffering amongst women and children in Yemen (malnutrition, direct causes of maternal and newborn deaths, disease and gender-based violence), supporting over one million women children annually’’.

In this reporting period the Programme has performed better than perhaps could have been expected, given the challenges faced. Activities contributing to all aspects of the ambition above have been fulfilled and the addition of IOM to the Programme with a focus on another highly at-risk group; African migrants, attempting to traverse the country to find work eventually in the Gulf has only enhanced the Programme’s humanitarian relevance and focus on the most vulnerable.

The Programme scored highly due to significant achievements in each of its three outputs - service delivery, health systems and protection, despite the three major challenges outlined above. These achievements included meeting the ambition stated in the Programme Business Case to provide services to over 1 million women and children annually. This reporting period there were over 1 million outpatient primary health care (PHC) consultations (amounting to approximately half of all PHC outpatient care in Yemen for this period), an average of 87.3% cure rate for children with moderate and severe malnutrition was achieved, over 500 PHC facilities were supported via training and equipment to utilise the district health information system, over 92,000 people received community based mental health and psychosocial support (MHPSS) services, nearly 9,000 people receiving Gender Based Violence (GBV) response services.
[note] 2.4 million outpatient consultations were provided in IDP and host communities, source: OCHA’s Assistant Secretary General for Humanitarian Affairs and Deputy Emergency Relief Coordinator, speech to the UN Security Council 12 June 2025.

Lessons and recommendations from the last (first) AR have been largely met
[note] Women and Children Programme 23-24 Annual Review
  - Partnership management: Providing predictable, but also flexible funding. This has been achieved with funding reprogramming requests met, and flexible funding provided, including to UNICEF for their cholera response and to RISE for the flooding response from July to September 2024. A budget reallocation allowed for emergency cash provision through the pre-positioned Emergency Preparedness and Response Mechanism (EPRM) across the flood-affected governorates of Taiz, Hajjah, and Hodeidah. 1,600 (349 female-headed and 1,251 male-headed) highly vulnerable households received critical cash assistance, enabling them to meet immediate needs for food, shelter, and essential items. Post-distribution monitoring results indicated high beneficiary satisfaction (94%), confirming the relevance and perceived value of the assistance. However, 6% of the respondents indicated that the amount of cash provided was insufficient for larger households, highlighting a need for future consideration of family size variations within assistance packages. The Internal Risk Facility (IRF) has proved a valuable asset this year and without it the partnership with the Kuwait Fund, to pick up 290 PHCs that the World Bank could no longer fund, and the cholera scale up with KSrelief would not have been possible.

  - Establishing best practice with FCDO Yemen’s other major humanitarian Food Security Safety Net (FSSN) programme, utilising FCDO’s global technical expertise to strengthen portfolio level risk registers. The W&C Programme has drawn on significant technical expertise from across the network, including central humanitarian WASH adviser, Senior Governance Advisers, Health Advisers, Conflict Advisers, Economists and Humanitarian Protection Advisers, to challenge and support delivery and risk management. A comprehensive review of the programme risk register was completed in January, escalating major and severe risks to the Programme Board for monthly review. The Programme PRO works across both FSSN and W+C programmes to align risk management and draws on the FCDO Yemen economist for advice on related risks. This has been particularly relevant for the implications of the FTO on the banking sector. Partner discussions on risk are a key part of all meetings and PMs meet with the PRO bi-monthly to discuss key shifts that are then escalated to the SRO. Doing so enabled coherence and consistency in FCDO’s approach to the UN-led ‘programme criticality’ exercise in deprioritising some activities in the North to safeguard implementing staff. As per below, with the support of the new Conflict Adviser in the FCDO team working with partners, there is a need to consider ways to strengthen conflict sensitivity good practice across the Programme.

  - The use of a Technical Assistance facility in Y2 to place candidates in key coordination positions within the international response. Key investments this year included support to the Protection Cluster’s CIMP work after UNHCR ceased their funding. In the 6 months with UK funding, CIMP has tracked all civilian impacts from the conflict and published a dataset of civilian casualties monthly, issued a 6 monthly report and an annual report. They tracked 586 civilian casualties during the reporting period, of which 179 were fatalities, including 18 children (further analysis below under Outcome 3). This partnership is being continued into FY 25/26. The Technical Assistance facility also funded 4 months of the Interagency Gender Adviser through the Standby Partnership, seconded to UN Women. This role struggled to make a meaningful impact on many issues in the original terms of reference in the short time it was funded. FCDO Yemen won’t continue to fund this role until it is clearer how it will successfully navigate the streamlined coordination architecture.

  - Requesting UNICEF take a Programme over Project approach to the different funding streams. This is increasingly being delivered. FCDO Yemen has stepped up its engagement with the World Bank and Gavi and push UNICEF to present the overall PHC situation, not just the facilities being directly funded by FCDO. In May 2025, FCDO and the World Bank undertook a joint monitoring visit of a PHC facility in Aden and will shortly hold a workshop with the Ministry of Public Health and Population (MoPHP) and key donors to look at PHC and wider health financing.

  - A programme logframe revision, including standardised shared indicators. This took place in March 2025 and was supported by the regional results advisor.

A revision of the RISE consortium’s Theory of Change, suggested by FCDO’s Violence Against Women and Girls (VAWG) helpdesk to articulate the relationship between Gender Based Violence (GBV) response and prevention more strongly. This revision was initially resisted by the RISE consortium, who felt it was not needed. However, following the three major shocks to the humanitarian response outlined above, a workshop on adapting IRC’s global framework for the Yemen context was planned. Unfortunately, it has recently been postponed due to conflict in the region but will be rearranged for the coming months, possibly to be held online.

  - Consider meeting the emerging needs of migrants in Yemen though a partnership with IOM. This was successfully achieved and IOM’s partnership with FCDO started in October 2024.

  - In Y2, the Programme team need to develop an approach to delivering, measuring and evaluating FCDO Yemen’s localisation objectives through the Women and Children Business Case and monitor this through the Programme logframe. This has not yet taken place. The RISE consortium has made significant progress in driving localisation objectives, but it is not yet captured in the logframe. This has been deprioritised as the team, and partners have focussed on adapting to the three main concurrent shocks realised over the past year.
Major lessons and recommendations for the year ahead
Lessons
The Programme has been flexible this past year, as it was designed to be, and as per the recommendation of the last Annual Review (see below). This allowed the Programme to take on support to IOM to meet the health and protection needs of migrants and allowed partners to reallocate funds, such as for the flooding and cholera outbreak. The IRF enabled the Programme to support Primary Health Care facilities that the World Bank had to drop. factored into the Programme facilitated this. All partners spoken to for this review appreciated FCDO’s flexibility and understanding and FCDO has cemented itself as a respected donor in Yemen. The Programme has also brought in other donor partners to fund priority action and has worked cohesively to do this, hoping to set a precedent (see lesson below). This approach has been very successful.

Specifically, FCDO’s programming and strategic inputs on health have all placed the FCDO as a central actor and achieving what is set out in the Business Case. This includes joint funding with the World Bank, Gavi and Kuwait Fund on PHC and with KSrelief on Cholera, encouraging the cholera task force and appeal, undertaking joint donor monitoring missions, and planning a PEA analysis of the health sector. In doing so, the programme is delivering on the business case commitment to “incentivise the UN and our implementing partners to pursue intersectoral prioritisation through the cluster system to integrate and prioritise interventions where there is highest need and pursue joint planning and monitoring”. FCDO should now capitalise on these achievements, including the success of an aligned approach with the donors above, and its support for the Yemeni MoPHP (see recommendation 6).
[note] With the World Bank to a Primary Health Care facility, and KSrelief to a Cholera treatment center, both in Aden in May 2025.

Successful working with programme downstream partners has been most noteworthy in the RISE project and there are lessons to be learnt that all three W&C programme partners could share. Over 60% of the RISE project’s Y2 resources were channelled through local and national actors. Building on individual Partner Capacity Assessments (PCAs) conducted at the outset of the program, IRC delivered targeted capacity-strengthening activities in Year 2 covering both organizational development needs as well as technical priorities as part of the project design. Beyond direct support to their consortium partners, IRC established a strategic partnership with the ICVA (International Council of Voluntary Agencies) as part of RISE to strengthen localised humanitarian coordination in Yemen. Among their broader focus areas, ICVA provides technical support to the National NGO Forum in Yemen, supports the participation of local NGOs in international fora and training and works directly with their 10 Yemeni National NGO members (including RISE members ADO and BFD) to increase their networking and access to capacity strengthening opportunities. As part of wider efforts to support localization, IRC and FMF also co-chaired the OCHA Country-Based Pooled Fund (CBPF) NGO Dialogue Platform, shaping the November 2024 donor Guidance Note Promoting Inclusive and Locally Led Action Through Humanitarian Pooled Funds. (See recommendation 10c).

The Programme Business Case still stands. The theory of change is still relevant, as is the overall programme ambition. The Business Case stated: “This programme will incentivise the UN and our implementing partners to pursue intersectoral prioritisation through the cluster system to integrate and prioritise interventions where there is highest need and pursue joint planning and monitoring.” This has been very evident in health, both systems and delivery, but perhaps less obvious in protection. The question now is how to remain relevant and reaching the most in need in Yemen as budgets are reduced, discussed below.
Recommendations
A) Capturing programme progress
The Programme logframe, and partners’ individual logframes need close revision to ensure partners achievements are being captured appropriately and accurately. This includes for example, adding in UNICEF PHC utilisations rates to Outcome Indicator 1.1 and capturing more effectively IOM’s protection progress/impact. Partner’s logframes need to detail in a ‘notes’ column exactly what is being measured and how and this needs to be shown in the master programme logframe. Additionally, partners should explain how they are using their disaggregated data for the benefit of those they assist and breakdown disability data by age/gender/type of disability where feasible. The Programme logframe may need less indicators but carefully chosen ones that are likely to be appropriate when/if extra programming is added, such as happened this year with the Kuwait joint project and the Cholera response. This will help ensure standardisation of reporting. at the Outcome level, the indicators for 2.1 and 2.2 should be examined to determine if they can be used as realistic proxy measures of impact on declining GBV risk and improved protection of civilians, respectively. This will be of value to the Programme Monitoring (MEL) Framework the Programme is developing. The development of this framework should be prioritised. By end September 2025. A full list of issues noted with the Programme logframe and partner’s logframes has been made available to the FCDO Yemen programme team.

The Third-Party Monitoring capacity has clearly enabled the Programme to be confident in partner’s reporting, as Yemen remains difficult for FCDO staff to visit widely. However, the TPM does not monitor all Programme logframe indicators and this should be addressed as part of the MEL framework development. Additionally, the TPM needs to be able to effectively conduct their monitoring in the North, as well as the South. By end August 2025

In the immediate future, the conflict sensitivity challenges are only mounting for the humanitarian response. Funding reductions and narrower targeting themselves require conflict sensitive handling. Whilst conflict sensitivity and do no harm are woven throughout the Programme and partner approaches, there is a need for a strengthened, more deliberate approach across the Programme, with capacity building and lessons and good practice sharing. A workshop to look at these issues, alongside promoting localisation (see recommendation 6, below) may be considered. By end December 2025.
B) Enhancing the current programme
Expand on the lessons being learnt from all partners about effective working with national NGOs, especially to improve service provision in the health sector. FCDO Yemen may want to consider holding a workshop to explore how localisation can be promoted, especially in light of US and FCDO funding reductions and further deterioration in security. Along with a focus on conflict sensitivity (recommendation 3) this would generate valuable learning and promote ideas for both the current programme and a future humanitarian Business Case. By October 2025.

The planned Health Sector Political Economy (PEA) Analysis may present a key opportunity to build on UNICEF’s work on sustainable PHC financing and help to develop a shared vison for health in Yemen with donors and the Government of Yemen. It could also strengthen a conflict sensitive approach and build on other partner work, such as IOM’s work to examine the existing normative framework for migration. By end December 2025.
C) Planning for reduced funding, and design of the next Business Case
Planning for the last year of this programme
FCDO should use the planned meeting on the health sector it is convening in Aden in early September to ensure partnerships with other key health sector donors, such the World Bank and Gulf donors are maintained and strengthened. This meeting may find it useful to examine the likely impact of the ‘Humanitarian Reset’ on Yemen, in order to help plan for FCDO’s budget reduction and the follow-on Business Case. Difficult funding decisions will need to be made imminently in order to plan for 26/27 and also for the next humanitarian Business Case for the follow-on programme. With US withdrawal, FCDO is well placed to take a convening role with Yemeni authorities, donors and operational agencies to map out who is best placed to fund what in the health sector. With diminishing global resources for humanitarian aid and a ‘humanitarian reset’ underway at the highest level of the UN, razor sharp priorities need to be identified but the burden must be spread between those who offer genuine advantage in terms of support and those who prove operationally advantageous. The planned PEA of the health sector will help in this analysis. By the third quarter of the year.

For the next Business Case
Consider how to retain programming flexibility in the next Business Case as it is designed.
Whatever shape the Programme takes in future, retaining flexibility within the Business Case for unexpected events will be key, as has been shown this year with the additional activities FCDO was able to support as crises emerged. For a country that is prone to conflict, extreme hunger and disease outbreaks, the capacity to respond quickly, effectively and at scale should be retained, especially as fewer other donors are likely to have this ability in future.

With imminent funding constraints FCDO may want to take some time to consider reframing the scope of the Programme for the next Business Case. One option may be to decide if a focus on only PHC going forward is a viable/desirable option, especially as the biggest PHC donor in Yemen - the World Bank - is likely to be scaling down its support and currently looking at geographical prioritisation of its 2,200 supported facilities in order to do this. FCDO would need to decide whether current partners, new partners or a mix, or a situation where partners work together, each working to their own strengths within a defined scope of activity, would be most effective.

Whatever is decided, support for the Yemeni MoPHP through UNICEF should continue as a sustainable way to support the Government. Good relationships with authorities mean that existing FCDO partner UNICEF can help shape policy across the country, whilst partners RISE and IOM have the local partner relationships and the technical capacity to work at facility level, where direct beneficiary contact happens. Focus could/should remain on assisting the most vulnerable, amongst the millions in need.

The protection focussed activities of RISE and IOM are key humanitarian interventions, especially in such a complex conflict context with high levels of physical insecurity. GBV activities have ceased in the North, but protection concerns have not decreased and restarting some protection activities in the North would seem to be a priority for the near future. A protection risk audit could help to identify which of the activities supported currently have the greatest protective impact and an examination of conflict sensitivity in FCDO programming would be of value to this. By November 2025.

Other ideas to consider as thinking for the next Business Case (post 2027) are suggested below and could be expanded in an options paper the Programme team will develop in the coming months (including using the points from these recommendations and from Section B).

The humanitarian coordinator has mentioned that an area-based coordination model could be implemented in Yemen. Whilst some think this is unlikely, FCDO should re-examine the efficacy of current humanitarian coordination across Yemen and determine if it is best placed to suggest changes/adaptions to the humanitarian community. This has perhaps started with FCDO support for an NGO coordinator in the South.

Is scaling up cash programming viable for FCDO? The UN has expanded cash programming to reach more than 580,000 people in 2024). ‘’Food is available, but people are poor so don’t have cash to buy it’’. Meanwhile 50% children are stunted. As FCDO Yemen’s other programme (FSSN programme) has a cash element and preventing malnutrition is a theme common to both programmes, could both be re-examined for where there are other mutual aims that could be capitalised on? For example, a joint effort on cash for nutritional improvement? The Business Case states: “Alongside the UK’s Food Security Programme in Yemen, this Programme will seek to prevent famine in Yemen. Through the two programmes we will ensure a comprehensive response to famine risk drivers supporting integrated nutrition, protection, health and WASH in addition to food security”. With the need to reduce budgets could the ambition of this statement be retained, in part through cash for nutrition?
[note] Mr. Tom Fletcher, Under-Secretary-General for Humanitarian Affairs and Emergency Relief Coordinator – Briefing to the Security Council on the humanitarian situation in Yemen, 11 December 2024 | OCHA.

Support pooled funding for greater localisation? The Yemen Humanitarian Fund channelled over 60 per cent of funding through local organizations, including those led by women, in 2024.Whist UK previously removed support, could there be value in examining if health/protection outcomes could be enhanced via supporting national agencies through the fund?

Could the Programme focus more on health system support? Could/should it look at secondary and tertiary level care?

All of point 10 by late Autumn 2025.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the Programme’s theory of change (ToC), including any changes to outcome and impact indicators from the original Business Case.

There have been no changes to the Outcome and Impact from the original Theory of Change, and both are still valid, as are the steps to achieving them. Despite the programming changes this year, mostly the reallocation to lifesaving activities only in the North and suspension of the RISE consortium activities there, the logic of the Theory of Change holds fast for Yemen and remains appropriate during a time when needs continue to increase. The IOM project, added this year, was an appropriate addition within the focus of both the outcomes and all three outputs.

The key assumptions identified in the Business Case which underpin the theory of change are:

ToC Assumption	Situation as of March 2025
In the scenario of continued conflict or political progress and peace, the humanitarian consequences of the war will continue to further deplete people’s coping mechanisms over the lifetime of the Programme.	This assumption holds. The humanitarian situation is deteriorating on many levels.
Key donors like the World Bank continue to support the Ministry of Health and Yemen’s health system can be maintained and deliver essential services with donor support.	This assumption only partially holds - the World Bank hasn’t substantially reduced their funding, but we do expect IDA funding for their PHC programme to reduce in October 2025.
Despite constraints, humanitarian agencies continue to be able to operate in hard-to-reach areas, including where there is greatest need.	This assumption partially holds with a substantial decrease in presence in the North of Yemen due to access constraints, staff safety, US FTO designation and USAID cuts. 11 INGOs have left the North and the UN has withdrawn from Sa’dah, with only MSF, and a small number of agencies operational now. Furthermore, the South also remains a difficult operating environment for humanitarian actors.
Specialised and local implementing partners are able to deliver GBV services as part of an integrated health programme and do no harm.	This assumption holds. The RISE consortium had navigated the restrictions of local authorities to deliver GBV services, but some planned GBV services have been suspended as RISE had to relocate from North to South due to US FTO designation.
FCDO is able to support the hiring of female staff to deliver health, SRH and specialized GBV services and mitigate the Mahram issue through joined-up diplomacy and local engagement through partners.	This assumption partially holds but is at risk. Key partners take different approaches to mitigating for Mahram but report they are still able to implement and deliver, albeit sometimes with workarounds.
Implementing partners working with local organisations are able to employ women and this is not undermined by media campaigns and policies aiming to dissuade women from working for humanitarian organisations.	This assumption holds at the time of writing.

Within the logframe some issues to consider include:
1. Impact 1 indicator on child mortality is predicated to decrease 1 percentage point per year. Given the uncertainty in the UN’s IGME trend estimates, it may be worth revisiting this indicator making it more specific, as the IGME data allows.
2. At the Output level, focussing on system strengthening, services and protection allows the Programme to have a good reach across the areas that can have an impact on women and children’s ability to thrive. The Programme may wish to consider adding measures now to be able to examine progress to impact, above that already planned. For example, FCDO has supported innovative mortality estimation work previously, this could perhaps be employed again to compare with the under 5 mortality data that is currently identified as the marker for measuring progress on Impact indicator 1.
3. IOM’s protection work is not captured in the current programme logframe, only their work on migrant health. A significant amount of their efforts in this partnership with FCDO are on migrant rights and protections and the consultant review this year of the Yemeni legal and policy architecture relevant to migrants is a starting point for more deliberate efforts on migrant rights, if FCDO wishes to pursue.
4. In Y3, the logframe will have a new indicator measuring the time to mobilise emergency funding. Populating this indicator on emergency funding, given this reporting period has seen two extra sub projects funded to meet emergency needs is recommended.
5. Consider introducing conflict sensitivity strengthening in the logframe and ToC. It will be useful going forward for the Conflict Adviser to examine the ToC assumptions for conflict sensitivity and if there is any evidence to show the Programme/partners are successfully applying conflict sensitivity.
6. See also specific logframe indicator and milestone points in Recommendations.
And within the Programme:
1. The Third-Party Monitoring (TPM) appears to be of value, not least to help provide the evidence to assess how far activities are leading to outputs, however its analysis has sometimes been questioned. It was only able to monitor in the South due to access restrictions. FCDO Yemen’s TPM supplier will change for Y3 of the W&C Business Case following the closure of the last agreement and the new supplier is expected to work in both North and South Yemen. IOM is collecting large amounts of service user feedback, could this be incorporated, or at least its findings acknowledged? Where the findings agree, it will bolster the TPM validity, where they don’t, FCDO should explore why. It is encouraging that partners refer to the TPM conclusions in their annual reporting, although the TPM team received no comment/feedback. The team working on the W&C Business Case should lean into the design of the new FCDO Yemen TPM project and feed in lessons learnt. The team are currently considering how best to undertake a review of conflict sensitivity practice and opportunities to strengthen, across programmes, including potentially drawing on the TPM facility.
2. The ToC states there will be strong emphasis on research and the Business Case reflects that the Programme will generate evidence on improved community and facility health approaches, what works to prevent violence against women and girls and the drivers of morbidity and mortality in areas of greatest need. Accordingly, health and nutrition research and use of evidence is flagged as an activity in the ToC but, except for some small-scale research by RISE on NCD’s (Non-Communicable Diseases), there doesn’t appear to be other research underway or planned, aside from some VFM analysis and a potential protection audit suggested in this report. Research and analysis is critical to ensure activities and intended outcomes are evidence-based and thus have the greatest impact. This is also true for examining the conflict sensitivity of projects within the Programme. The plan to invest in PEA of the health sector to guide programme engagement would seem a good use of programme funding, for example.
Describe where the Programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact Indicator(s)	Milestone(s) for this review	Progress
Under 5 mortality rate (Deaths per 1,000 live births)	38.25	N/A
Universal Health Coverage service coverage index (SDG 3.8.1)	42	N/A

Outcome Indicator(s)	Milestone(s) for this review	Progress
1.1 Health care utilisation rate (disaggregated) - Nutrition (SAM, MAM), Primary Health Care, SRH, vaccinations, Integrated Management of childhood illnesses (IMCI), basic baby delivery (BEmONC) - midwife - outpatient visits per person per year	0.7	0.5
1.2 Number of health care facilities delivering the Minimum Service Package (MSP)	717 / 5 - IOM / 57 - IRC / 655 – UNICEF	716 / 5 - IOM / 56 - IRC / 655 - UNICEF
2.1 Women and girls facing GBV risks	6.4m	6.2m
2.2 Number of civilian casualties - number of fatalities, injuries and incidents reported each month, totalled for the reporting period.	<1,281 total civilian casualties / <401 fatalities / < 880 injuries	1,272 total civilian casualties / 350 fatalities / 922 injuries
[note] Source for milestone is the 2024 Humanitarian Needs Overview (HNO), and for progress the 2025 HNRP.

The logical flow from activities to outputs to outcomes and then impact is sound, and the Programme is still on track to contribute to both outcomes by programme end which will contribute to the stated impact. This is in no small part due to the efforts and flexibility shown by partners during these last 6 months when the already challenging operating environment has altered considerably. For example, IOM has been working to highlight the issues around effective migration management, and to ensure the services to the host population are not affected by those targeting migrants/IDPs, all the while maintaining a conflict sensitive approach. UNICEF used some of its own funds to be able to launch a cholera response and is now working with authorities on a PHC financing strategy to try and put in place a sustainable system. RISE, as part of their relocation and to scale up response to the flooding crisis in 2024, took on 5 new geographical areas and 2 new partners (these were two of IRC’s pre-existing emergency response partners but outside the RISE consortium structure).

Indicator 1.1 This milestone was reported on only by the RISE consortium and was not quite reached. At the onset of the RISE project baseline findings indicated a critically low utilisation of health services across targeted locations, with an average utilisation rate of 0.34 outpatient consultations per person per year. Over the course of this reporting period, the consortium has worked to improve facilities and the services on offer, making trained staff available and trying to ensure consistent supply of medicines. However, the delayed rollout of services in Houthi-controlled areas due to protracted sub-agreement approval processes presented a problem and delays in operationalising facilities constrained service access and uptake. Despite these operational challenges, the increase from 0.34 to 0.5 reflects a positive trend in health-seeking behaviour as well as the pull of PHC services with adequate staff and medicines. When the Programme logframe is revised, UNICEF data should be merged for this indicator as UNICEF is the main PHC provider in Yemen.
Indicator 1.2 Substantive progress on this indicator means the MSP has been rolled out in over 700 FCDO supported facilities this reporting period. Both the milestone and the progress reported includes an attributed 145 facilities that were supported with FCDO funding as part of the joint project with Kuwait.
Indicator 2.1 The estimated number of women and girls facing GBV risks come from the UN’s Humanitarian Needs Overview/Humanitarian Needs Response Plan. Whilst the figures are an estimate it is hoped overtime that the combined efforts of Yemini authorities, civil society and humanitarian actors will lead to a decline in those at risk but proving this effect will be challenging and FCDO Yemen may wish to relook at this indicator.
Indicator 2.2 The number of civilian casualties is taken from the data of the Civilian Impact Monitoring Programme, a newly added activity under the partnership with UNICEF this reporting period. It is hoped that figures will steadily decrease overtime. As with Indicator 2.1, proving this association will be difficult.

Source: CIMP monitoring data

Source: CIMP monitoring data
Planning for next year is going to have to consider the reduction in budget that Yemen will face and whether activities and outputs can be maintained to still meet the theory of change and both outcomes. Much will depend on the scale of the budget cuts and the conflict sensitive adaptation of the Programmes. See recommendations, above.

Justify whether the Programme should continue, based on its own merits and in the context of the wider portfolio

The Programme is undoubtedly having an impact on the health and protection of the people of Yemen and migrants who find themselves stranded there. It should continue as it is achieving results in meeting critical humanitarian needs. The Programme is also playing a part in cohesive governance, particularly through work in the health sector, such as UNICEF’s work to design and help implement PHC policy, including sustainable financing for the PHC services across the country. IOM’s work with the Government of Yemen on migration management being another example.

The reduction in funding from next year onwards means that further thinking is required now to determine if the ToC can still be met in part, or in whole. Now is also the time to think forward to how the Programme can support and enable early recovery. Ideas can be explored as part of the health workshop that will take place later this year and as part of the options paper suggested in Recommendation 10.

Going forward and considering the next Business Case, it will be important to have both the W&C Business Case and the FSSN Business Case speak more closely to each other and to align around shared priorities and outcomes. This will be key for meeting humanitarian needs more efficiently, in line with the vision for integrated programming foreseen in the W&C Business case. Joint planning and vision will also be key when looking at support to activities that will bolster early recovery and Governmental capacity to effectively manage basic services. The combination of integrated primary healthcare, nutrition and food security and WASH in a programme that is conflict sensitive can only mean better immediate and longer-term outcomes for the people of Yemen.
[note] “Alongside the UK’s Food Security Programme in Yemen, this Programme will seek to prevent famine in Yemen. Through the two programmes we will ensure a comprehensive response to famine risk drivers supporting integrated nutrition, protection, health and WASH in addition to food security”.

## C. DETAILED OUTPUT SCORING

Output Title	More women, children, and vulnerable groups (migrants) have safe and improved access to integrated life-saving health, WASH, SRH and nutrition services. (service provision)
Output number:		1	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Indicator’s Rating
1.1 Number of total outpatient consultations (RISE, UNICEF, IOM)	1,033,286 / RISE 278,291 / UNICEF 725,000 / IOM 40,000	1,109,229 / RISE 416,724 / UNICEF 641,580 / IOM 50,925	Met expectation
1.2a Percentage of children treated for malnutrition (MAM, SAM) Cured / (RISE, UNICEF)	>75%	87.3% av / UNICEF SAM 92.7% RISE SAM 85.2% RISE MAM 84.2%	Moderately exceeded expectation
1.2b Percentage of children treated for malnutrition (MAM, SAM) Defaulted / (RISE, UNICEF)	<15%	9.9% av / UNICEF SAM 4.7% / RISE SAM 10.8% / RISE MAM 14.3%	Substantially exceeded expectation
1.2c Percentage of children treated for malnutrition (MAM, SAM) Deceased / (RISE, UNICEF)	<3%	0.33% av / UNICEF SAM 0.8% / RISE SAM 0.1% / RISE MAM 0.1%	Substantially exceeded expectation
1.5 Number of deliveries attended by skilled (trained midwives) health personnel (RISE)	5,422	4,024	Substantially did not meet expectation
1.6 Number of beneficiaries who start a family planning method (RISE)	19,118	10,602	Substantially did not meet expectation
1.7 Number of health facilities with sustainable access to WASH (UNICEF)	159	157	Met expectation
[note] UNICEF report on number of beneficiaries against this indicator which means there is a minimum of 641,580 consultations. UNICEF has likely delivered a much larger number of consultations but the target was not set to reflect this. FCDO will work with UNICEF to align reporting for 25/26.

Briefly describe the output’s activities and provide supporting narrative for the score.
This multisectoral output has scored A+ and is on track, but some indicators have not achieved their planned results this year largely due to RISE facing delays in providing service provision. All three partners are playing a vital role in service delivery, with UNICEF reaching over 62% of all PHCs in both the North and the South through the joint World Bank, Gavi and FCDO support, and continuing as a vital partner of the MoPHP. UNICEF later supported up 290 PHCs that the World Bank had to drop this year through the joint UK-Kuwait Fund project. As a result, indicator 1.1 milestone was increased, and the progress was accordingly raised. RISE adapted quickly to relocation from the North, taking on two new districts in the South, while IOM continued targeting migrant and IDP populations despite needing to shift operations from Sa’dah.

Indicator 1.1 Over 1.1m PHC consultations were made, and the milestone was met. IOM had to relocate their PHC provision for migrants and IDPs from Sa’dah governate towards end of the reporting period and continued support via Migrant Response Points as well as static facilities. IOM’s support also included mental health and psychosocial support. UNICEF’s support to PHC facilities remained key to delivery of the Minimum Service Package of health and nutrition services. Amongst other UNICEF activities 10 PHCs across six governates were upgraded to provide Basic Emergency Obstetric Services. UNICEF milestone and target include those from the joint Kuwait Fund PHC project this year (325,000 milestone and 255,791 progress).

In January 2025, the TPM agency conducted field visits to 13 UNICEF supported PHC facilities and seven RISE supported PHC facilities and found that for the key performance indicators RISE supported facilities were all rated ‘green’, whereas UNICEF supported facilities had issues in relation to deliveries/ante-natal care, provision of Primary Healthcare Kits, WASH facilities, reporting, feedback, and facility quality. The TPM also visited a selection of IOM supported PHC facilities and found generally positive results, but with flags on the provision of full health screening, referrals and some users saying their healthcare needs had not been met.
[note] Partner have been provided with the reports for their information and comment. No comments were received.

It is worth noting that TPM found that 6 of 13 UNICEF PHC facilities did either not have registers or up to date registers whilst all RISE facilities had up to date registers. Accurate recording of patient data is fundamental to any kind of healthcare provision and could be thought of as a proxy for the level of accuracy and conscientiousness that health care providers operate with. This issue should receive attention as a priority. It was also of concern that most UNICEF facilities visited didn’t have a forecasting system at facility level, whilst most of the RISE supported facilities did. One of the key reasons for donors insisting on disaggregated data is to allow for more accurate forecasting. This saves, time, money, avoids waste and results in better patient treatment and therefore outcomes.
[note] Given the scale of UNICEF’s PHC operations (over 3,200 facilities), supplies are managed centrally through a push system based on kits with quantification at central program level. However, UNICEF has recently stared supply chain system strengthening which will include forecasting and quantification. This is not done at each PHC rather at central/governorate and district level.

Indicators 1.2 a–c All milestones were exceeded, reflecting effective community outreach and facility-based care. The milestone for percentage of deaths amongst children being treated was substantially exceeded (less than the predicted overall number).

Indicator 1.5, (births attended by skilled health personnel) and Indicator 1.6 (family planning uptake) were not fully achieved, despite RISE’s ongoing investment in facility-level quality improvement. RISE met problems with gaining permissions in Houthi controlled areas and found that a preference for home births impacted the number of women presenting for delivery in a facility. Problems were also encountered with family planning uptake as access to contraceptive methods is highly restricted in Houthi controlled areas.

Indicator 1.7 (WASH access at health facilities) was not achieved at two facilities but within the 5% range to represent expectations met. UNICEF rehabilitated 157/159 facilities in this reporting period across 16 governorates. To ensure sustainability, UNICEF established Water Committees for each water supply facility/system that had been upgraded and provided training on operation and management of water systems, system troubleshooting, financial management, and resource mobilization.

Despite just missing the target for this indicator, a review of UNICEF’s WASH activities by FCDO’s Humanitarian WASH adviser concluded that UNICEF had successfully completed all formally re-aligned WASH activities for 2024/5, as well as successfully completing activities under the cholera response top up grant (November 2024-March 2025).

As part of the extra funding possible because of the IRF, the cholera joint project, co-funded by FCDO and KSrelief, allowed UNICEF to significantly strengthen outbreak response capacity and PHC coverage in high-risk areas. UNICEF supported four Diarrhoea Treatment Centres and 46 Oral Rehydration Corners, delivered 400 AWD kits (supplemented by 250 kits provided in-kind), and reallocated funds to procure additional IMCI supplies, benefitting an estimated 300,000 children under five. Training was provided to 658 health workers on case management and Infection Prevention and Control, and 66 rounds of joint supportive supervision enhanced adherence to treatment protocols and improved reporting quality. These timely interventions helped sustain health services amid overlapping cholera with outbreaks combined with sever acute malnutrition in the west coast. The joint funding also enabled support for mobile and outreach teams, extending the reach of PHC in underserved areas.
[note] Acute Water Diarrhoea Kits for Cholera Treatment
[note] Integrated Management of Childhood Illness

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The biggest change to this output has been relocating some activities from North to South in early 2025 due to the detention of humanitarian workers, US withdrawal of funding and subsequent designation of the Houthis. UNICEF and IOM had to reduce to lifesaving activities in the North whilst RISE was forced to move all activities to the South to reduce liability to the FTO designation. There has also been an upscale in the number of PHC facilities supported due to the joint project with the Kuwait Fund and the extra funding to UNICEF through the joint project with KSrelief for cholera response activities.

Several logframe changes for Output One have been recorded in the logframe change tab in January 2025. Some have been deleted to reflect the logframe revision to align indicators between partners, others have had their language tweaked, but none are significantly different. 1.1 and 1.5 are new indicators added since last year. These changes were made in response to the emphasis on lifesaving activities as mentioned above.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

In the previous Annual Review (the first for this programme) the following recommendations were made:
During the forthcoming logframe revision, the Programme will strengthen the measurement of improved access to health and WASH services, building on the recommendations in FCDO Yemen’s recently developed Gender, Equality and Social Inclusion (GESI) strategy.

Progress
The logframe revision in March 2025, has introduced indictors to strengthen the measurement of access to health services but the WASH indicator needs further revision. Looking forward, FCDO’s Humanitarian WASH adviser has made detailed recommendations for UNICEF’s WASH activities for 25/26 but also presented over-arching areas to focus on as programme budget considerations become more pressing. These include UNICEF reducing the level of new WASH construction, increasing WASH activities that focus on community engagement, sanitation and hygiene and Cholera outbreak preparedness and strategic response.

The Programme will need to look at its contribution to prevention of SAM and potentially expand the reach of SAM management services to additional health facilities with UNICEF.
      Progress
Minimal progress was made this year beyond what was already planned due to the competing priorities of a cholera outbreak and focussing on acute malnutrition treatment rather than prevention.

We will work with UNICEF to ensure a public health emergencies strategy is better integrated next year. Emphasis will be placed on conducting vaccination campaigns, enhancing capacity building, and developing response planning with the line ministries, inter-sector mandated leads (e.g. World Health Organisation) and implementing partners.

Progress
Progress has been focussed on utilising the shared leverage of FCDO and KSrelief to improve cohesive preparedness, reporting, and planning from the two mandated cholera leads, UNICEF and WHO. Some progress has been made there and as numbers of cholera cases begin to increase again in 2025, the response feels more prepared and ready than 12 months earlier.
Lessons learned this year
  1. The PHC service provision supported by FCDO, and the partnerships with Kuwait Fund, KSrelief, the World Bank and Gavi have worked extremely well and have given UNICEF the opportunity to further advance common health policy development for Yemen.

  1. As with several other programme indicators, Output 1.1 needs revision after discussion with all partners as to how this progress is captured and how it is clearly reported. The process of verifying reporting on this indicator also highlighted that when IRF is used, the indicators for the new projects need to align with the existing programme logframe indicators so progress is able to be amalgamated where appropriate.
Recommendations for next year

Expand on the lessons being learnt from all partners about effective localisation/working with national staff members and NGOs, especially to improve service provision in the health sector. FCDO Yemen may want to consider holding a workshop to explore how localisation can be further promoted, especially in light of US and FCDO funding reductions and further deterioration in security. By September 2025.

The Programme should capitalise on relationships built with UNICEF and MoPHP and in the next year, work on developing a shared vision for health in Yemen among the Government of Yemen and key international donors.

Output Title	Health systems (locally and nationally), are preserved and have the capacity to deliver maternal and child healthcare and respond to disease outbreaks.
Output number:		2	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Indicator’s Rating
2.1 Number of PHCs supported to deliver Basic Emergency Obstetric and Neonatal Care (BEmONC) and community outreach. / (UNICEF)	10	10	Met expectation
2.2 Number of primary healthcare workers trained on community management of acute malnutrition (CMAM), infant and young and child feeding (IYCF), & community engagement. / (UNICEF)	560	200	Substantially did not meet expectation
2.3 Number of community social and health workers and volunteers trained on nutrition, referral procedures, and community engagement. / (RISE)	665	521	Substantially did not meet expectation
2.4 Number of facilities upgraded to District health information system (DHIS2), especially in relation to maternal, new-born, and child health and nutrition. (UNICEF)	401	654	Substantially exceeded expectation
2.5 Percentage of health service delivery sites out of stock of any tracer drug on any day during the last month (RISE)	5%	25%	Substantially did not meet expectation

Briefly describe the output’s activities and provide supporting narrative for the score.
This output scored B. Partners contributed to strengthening essential service delivery across primary health care facilities by enhancing the availability of skilled birth attendants, expanding health worker training, improving reporting and improving pharmaceutical management. These efforts were aligned with broader national strategies and complemented by other donor support such as the World Bank. Despite not meeting three of the indicators there is a good argument for rating this output a B, given that 2.1 was met, 2.4 substantially exceeded and 2.3 and 2.5 being somewhat out of partner’s control due to the context.

Indicator 2.1. The TPM confirmed that of the 3 UNICEF facilities visited that had been provided with the basic Emergency Obstetric and Newborn Care (BEmONC) package, all reported they were using the common standards including proving skilled attendants at births. These facilities, primarily located in the South, were 3 of 10 PHC facilities across both North and South Yemen upgraded by UNICEF. These upgrades are conducted in parallel with World Bank support to ensure harmonised service delivery. Additionally, UNICEF reported 40 midwife trainers were trained to deliver BEmONC training.

Indicator 2.2. A mix up meant that UNICEF was not aware of the milestone for this indicator. That has now been corrected.

Indicator 2.3 This indicator was not achieved due to the suspension of training activities in Houthi-controlled areas. The suspension was linked to detentions in the North and a subsequent shift in operational focus to lifesaving interventions, which deprioritised capacity-building components.

Indicator 2.4 This milestone was substantially exceeded as UNICEF upgraded 654 facilities to be able to report on the DHIS2 this period. This included extra facilities it had taken on during the reporting period with FCDO-Kuwait Fund support. At this point the milestone should have been updated, but as this didn’t happen the original milestone has been far exceeded. UNICEF reported only one FCDO/UNICEF supported facility of the enhanced total of 655 missed the upgrade. However, the TPM found that of the 13 UNICEF facilities visited 2 reported they do not provide DHIS II updates as they hadn’t been trained on it.

Indicator 2.5 During this reporting period two medicines (oral rehydration salts and zinc) were out of stock for two months in 13 of 52 RISE supported facilities. This was due to the Red Sea crisis delaying delivery to Yemen. Other medications were able to be procured through a prequalified national supplier, however these suppliers also ran short on some supplies. The TPM found that there were minimal stock outs of the four essential drugs and commodities, in the seven facilities visited but 4 of the 7 reported shortages of Amoxicillin, Ciprofloxacin, Misoprostol, amongst a few others. The consortium mitigated this by directly procuring other tracer drugs, resulting in minimal service interruption. This reflects growing system resilience and improved stock management practices within supported health facilities. RISE may want to revise the methodology for this indicator as the progress is disproportional to the stockouts, and the length of time of the stockouts, that occurred.

Map of all FCDO supported PHC facilities during FY2425.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The output order has been changed from last year but all these indicators were already in the logframe, although some have been adjusted slightly. All indicator changes have been captured in the Programme logframe change tab.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There are no relevant recommendations on these indicators from last year’s annual review.

Lessons learned this year
One major lesson learnt has been the criticality of supporting the Yemen MoPHP to take leadership and ownership of Primary Healthcare in Yemen. FCDO has engaged substantially with the Minister of Health in Aden and in Riyadh, including in meetings with His Majesty’s Ambassador to Yemen. FCDO Yemen has launched a Political Economy Analysis of the healthcare sector and intends to hold a workshop with key health donors and the Ministry in the coming months to work through options and opportunities for long-term financing of health provision in Yemen at a time of decreasing external development financing. A recommendation is to take this forward and develop a shared vision for health in Yemen among the Government of Yemen and key international donors.

Recommendations for next year
For the year ahead, the work already underway on PEA analysis of the health sector could perhaps be expanded. It could build on UNICEF’s work on sustainable PHC financing and help to develop a shared vison for health in Yemen with donors and in order to help strengthen IRG governance capacity.

Output Title	Women, children, families and communities have improved access to protection services and vulnerable groups (women headed households, PLW, children under 5, displaced persons, al-Muhamshin) are provided with assistance and protection in new emergencies.
Output number:		3	Output Score:	A+
Impact weighting (%):		40%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress	Indicator’s Rating
3.1 Number of people receiving community based mental health and psychosocial support (MHPSS) services (RISE, UNICEF, IOM)	82,265 / RISE 33,265 / UNICEF 48,000 / IOM 1,000	108,816 / RISE 11,708 / UNICEF 94,237 / IOM 2,871	Substantially exceeded expectation
3.2 Number of people receiving child protection and GBV response services (disaggregated by child protection/GBV) (RISE)	18,921	14,769 / (Child protection 6,013, GBV 8,756)	Substantially did not meet expectation
3.3 Number of individuals trained in child protection and concepts, activities, or interventions for GBV prevention and response (disaggregated by CP and GBV) (RISE)	261	291 / (Child protection 142, GBV 149)	Moderately exceeded expectation

Briefly describe the output’s activities and provide supporting narrative for the score.
This output scored A+. The only indicator which did not reach its progress target was 3.2, discussed below.

Indicator 3.1 RISE’s underachievement on this indicator was due to delays receiving approvals (sub-agreements) from the Houthis to begin operations in the North, as well as some delays in approvals in the South during the original mobilisation period of the Programme. Funding initially planned for these activities was reallocated in Q2 to enable RISE to scale up the emergency flood response. At review, targets will likely reduce substantially next year due to lack of access to the North. UNICEF was able to reach children in over 41 districts with activities such as individual and group counselling. IOM exceeded their target for this indicator providing mental health promotion and support group sessions, amongst other activities. Additionally, Psychological First Aid remained part of their broader healthcare package, and 20 healthcare providers were trained this reporting period on WHO’s Mental Health Gap Action Programme. 62 migrants with advanced mental health needs were referred for specialised help. The TPM found MPHSS services provided in 2 of 13 UNICEF facilities visited, including outreach services. Where it was available it was highly valued by staff and communities. 3 of the 7 RISE facilities had MHPSS services, and all 3 also did outreach. For IOM the TPM found MHPSS services available at all sites, bar one hospital. Services were fully available to migrants at all sites. All 5 migrant health points provided community outreach, but none of the other sites visited did.

Indicator 3.2 RISE’s underachievement was due to delays in establishing women and girl’s safe spaces in Houthi controlled areas due to protracted negotiations with the authorities on receiving approvals to operate. This also took place in the South. The GBV and child protection services that were provided were delivered from 8 community centres, 28 women and girls safe spaces, 7 safe healing and learning centres and 30 health facilities. Additionally, RISE reached 55,538 individuals with GBV community awareness sessions, looking at early marriage, peaceful coexistence and access to services. TPM didn’t report on this.

Indicator 3.3 RISE attributed the overachievement on this indicator to high demand for capacity building across the 7 governates they work in. More participants were accepted in than planned, but with no impact on session quality. Training included refining standard operating procedures for GBV and child protection case management, setting standards for women and girls community centres and community and service mapping. TPM didn’t report on this.

Describe any changes to this output during the past year, and any planned changes as a result of this review
During the course of this annual reporting period, FCDO Yemen launched the IOM Health and Protection programme for migrants, scaling up the work IOM was already undertaking through ECHO funding. Currently, the logframe only captures the health results from the project. The logframe should be revised to capture the protection results and the progress/impact of their work on conflict sensitivity.

Due to UNHCR’s decision to cease funding the Protection Cluster’s ‘Civilian Impact Monitoring Project’ FCDO stepped in to ensure the survival of the project, which feeds into multiple protection of civilian monitoring, verification and reporting mechanisms and is used by Humanitarian Mine Action actors to prioritise locations for clearance. It should be captured in the Programme logframe.
[note] civilianimpactmonitoring.org

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

1) Localisation. A significant component of FCDO Yemen’s localisation policy priority will be delivered through the IRC led RISE Consortium and localisation is further supported through the systems strengthening component of Output 3. In Y3, the W&C team need to develop an approach to delivering, measuring and evaluating FCDO Yemen’s localisation objectives through the W&C Business Case.

Progress: This recommendation has yet to be fully achieved (see this year’s recommendation 4).

2) Last year’s Annual Review noted that ‘’This year, we successfully onboarded an NGO consortium called Reducing Illness, Violence and Abuse through Systematic Empowerment (RISE) to the W&C Programme. As part of this Annual Review, FCDO conducted a review from the FCDO’s central Violence Against Women and Girls (VAWG) Helpdesk of the inception period of this NGO consortium. The helpdesk recommended a Theory of Change review to articulate the relationship between Gender Based Violence (GBV) response and prevention more strongly. FCDO Yemen will partner with the VAWG helpdesk to take this forward with the International Rescue Committee (RISE) led RISE Consortium in Y2.’’

Progress: See below.

Lessons learned this year include:

1) Both RISE and IOM have benefited from the inputs of FCDO’s Violence Against Women and Girls Helpdesk this reporting period through monthly engagement. A Workshop had been planned for June 2025 to examine how RISE’s global framework for GBV can be more specifically adapted for the Yemen context (see last year’s recommendation above) and it might lead to a tailoring of RISE’s activities. The workshop was unfortunately delayed due to regional conflict dynamics impacting Jordan, where the workshop was planned. Currently RISE’s activities on both GBV and protection remain more response than prevention focussed, and this should be a point for discussion going forward.

2) IOM have been enthusiastic for the helpdesk’s support, but funding cuts prevented a visit from IOM HQ to work on adapting their global GBV framework for Yemen. As tailoring is important FCDO may want to track if this workshop can be re-planned in the coming months.

3) IOM has proved a valuable partner to have brought on board this year as shown by their ability to conduct an ’audit’ of Yemen’s policy framework on migrants, which has well placed them to make suggestions for policy enhancement. Raising the plight of the migrants in Yemen is a key protection activity as these people remain highly vulnerable and without any assistance. IOM’s conflict sensitivity approach will be of value to share with other partners.

Recommendations for this year

1) The Programme logframe should be revised to capture the protection results and the progress/impact of IOM’s work on conflict sensitivity.
## D: VALUE FOR MONEY
The Business Case cited evidence that there are systemic, structural, and operational constraints associated with calculating value for money in any complicated humanitarian response like Yemen.  It advised implementing a relatively simple model of selecting high level indicators and tracking them against cost over time.  A key recommendation is to agree common indicators for partners to report against annually to support comparative analysis. The development of a VFM framework has progressed in Year 2 and should be finalised in quarter two of FY 25/26 providing a more structured evidence base for assessing partner delivery whilst aiming to not increase burden on partners. There is some information available for analysis for this review, set out below.

VFM considerations have driven partner selection decisions, as outlined in the Business Case. UNICEF were selected as the main delivery partner on the basis that they are the mandated lead and only actor able to provide health services, nutrition and WASH services at scale across Yemen. Their level of influence, experience, track record, evidence of delivery and cost effectiveness were all considered as key VFM criteria. The selection process for an NGO consortium had a focus on VFM including ‘maximising resources and benefits towards beneficiaries and reducing administrative costs and overheads’, as an assessment criterion. The RISE component also has a significant focus on local NGO delivery (with sustainability benefits) with a structured approach to localisation over the implementation period. With all partners now mobilised (IOM in October 2024) there is now more comparative data, especially at economy level to make an assessment.

Key cost drivers and performance
The primary cost drivers remain as envisaged in the Business Case, health worker incentives and the varying scope and scale of the Minimum Service Package (MSP) delivered by UNICEF and RISE.

Minimum Service Package
The input costs per facility to deliver the MSP is a key economy and efficiency VFM indicator for the Programme. The MSP is a health delivery mechanism aimed at strengthening the access and availability of health care services and strengthening the health system in Yemen. In line with their mandate, UNICEF (655 facilities) focuses on four core components of the Minimum Health Service Package, including child and women's health, vaccination, and nutrition, with the fifth, MHPSS in a smaller number of facilities. However, RISE (56 facilities) covers the entire eight components, which also includes general clinical services, including non-communicable diseases, MHPSS and expanded WASH, requiring more substantial financial support per facility. IOM supports five primary health facilities where they deliver the MSP to the same specification as RISE.

The average cost per facility for RISE is £67,772 (around $93,000 for comparison). Given the difference in specification of the MSP delivered, UNICEF’s costs are lower than RISE. At programme design (2022) UNICEF had estimated that the cost per primary health facility would be $10,000 per year, however this year the average cost was $43,700 per facility. The costs increased over the course of the year by around 20% from $34,996, partly due to improvements to the PHC kit costs following TPM feedback that 41% of facilities found that kits did not fully meet needs. In addition, the Red Sea Crisis drove up costs of importing medication to Yemen which has driven the total cost of delivering the MSP upwards. IOM average cost is £12,000 per health facility but the FCDO TPM conducted did not assess these facilities directly against the MSP. It did however find that three of the five facilities visited did not provide migrants with health screening during the visit. Conversely four of the five facilities had migrants reported that their healthcare needs were met as a result of services. Further assessment of IOM health services against the MSP should be a priority for 25/26 MERLY monitoring.
[note] Costs shown in USD as variations in exchange rates from GBP to USD

TPM assessments of service patient satisfaction and facility reporting on service availability demonstrates the benefit of the higher costs to deliver the comprehensive MSP. Challenges in UNICEF facilities include stock outs, stretched capacity, birth attendance and ante natal support. With further FCDO TPM planned in FY 25/26 a focus on improvements in service provision from UNICEF will be tracked to assess whether it is possible to increase this using the basic MSP. It is inconsistent to compare this cost to other contexts given the variations in markets and geographies. A further element is to compare patient outcomes as a result of treatment in these facilities (effectiveness) which will be tracked as part of the VFM framework and through TPM in the coming year. So far under output 1.2a both UNICEF and RISE have exceeded the target on % of children treated and cured for malnutrition (SAM) but with a higher % for UNICEF of 92.7% compared to 85.2% for RISE but with limited information across health outcomes comparisons are not yet possible.
[note] The variations and relatively small sample size of FCDO TPM should be noted. 13 UNICEF facilities reflects under 2% of facilities, five facilities for RISE is 13%.

The Business Case assumed that over the course of the Programme RISE would have a proportionate increase (compared to UNICEF) of health facilities where it is delivering the MSP and therefore a cost per facility would reduce due to economies of scale, based on experience in other contexts. FCDO will therefore aim to track the MSP cost in RISE facilities between years going forward.

Incentive payments
Another key cost driver is payments to health workers to staff facilities, which varies depending on the job (midwives, doctors, medical assistants, vaccinators etc). UNICEF’s condition for payment includes four field visits per month. UNICEF incentives range from $25 (health manger where salaries are regularly paid) to $600 (doctor where salaries are not being paid regularly in rural areas). UNICEF reduced the incentive rates per month for the categories of roles receiving $160 to $140 in governorates where salaries are not being paid. In governorates where salaries are being regularly paid this payment goes down to $25. For RISE (aligned with approach agreed by INGOs) monthly payments range from $400 to $92 with variations between conflict and hard to find roles. To support a sustainable approach, partners agree rates with the ministries of health to increase the likelihood that ministries will be able to take over payment in the future. FCDO TPM has not monitored the potential impact in variance of incentives between partners or that health workers are receiving the payment as expected. This should be a priority for MERLY in 25/26.

Efforts are underway to align incentive systems to a structure previously used by the Ministry of Public Health and Population (MoPHP), in line with the systems strengthening approach promoted in the Business Case. Although no UK funding passes through government systems, linking payments to MoPHP practices supports longer-term sustainability. The Programme continues to work with the Health Cluster and humanitarian partners to push for harmonised compensation standards while managing inflationary pressure or disincentivising staff retention in remote areas.

VfM performance
[note] All RISE consortium figures are reflective of Feb 15th 2024 to March 31st 2025.
Beyond the two key cost drivers above there are several additional indicators across FCDO’s 5E framework.

Economy
Indirect vs direct costs
Indirect costs in this context refers to any funding not spent on beneficiary activity including overheads, monitoring, salaries and NPAC. These are calculated differently between organisations, so comparisons are not always possible. Currently there is inconsistency in partner reporting on indirect costs, with some including all staff salaries and others allocating these to activities. Over the next year FCDO will work with partners to improve consistency on this to allow for comparison.

NPAC fees or overheads
[note] Non -Project Associated Costs – Non-Project Attributable Costs (overheads) are costs that are not feasibly allocable to a single project (NPAC). These costs are incurred by an organisation in order to support the projects that it runs – for example administration and support, equipment, space and premises costs, and activities that relate to the whole organisation and partly support the project but also support other projects.
In general, NPAC and overheads have been incurred in line with the amounts agreed in budgets at proposal stage which for UN partners are set by FCDO central agreements. IOM continues to offer the best VFM under this measure at 7%.
- IOM: 7% this equated to £130,841 in 24/25, in line with the framework agreement held between FCDO and IOM centrally.
- RISE: 8.32% this equated to £853,875 with the large majority of this to IRC as the lead consortium partner. This is in line with the NPAC agreed in the budget. 24/25 split across the Consortium as follows:
  - IRC £486,579
  - BFD £174,324
  - ADO £98,962
  - FMF £94,010

UNICEF: 8% in 24/25 in line with the framework agreement held between FCDO and UNICEF centrally. 24/25 split across as follows:
  - Main contribution: £2,080,000
  - Kuwait Fund Partnership £96,000
  - Cholera/KSrelief Partnership: £316,120

Economies of scale for procurement (vaccines and ready to use therapeutic food (RUTF))
Procurement and input costs have generally remained in line with projections, with global inflation placing upward pressure on key commodities (notably RUTF and medical supplies). Where possible, partners have drawn on long-term agreements to mitigate short-term cost increases. In the coming year FCDO will request examples of economics of scale benefits or challenges to this in the context.

Incentive Payments (see above section)

Efficiency
Output delivery has been broadly on track with many exceeding expectations however there are several outputs that have not achieved targets including 1.5, 1.6, 2.2, 2.3, 2.5 and 3.2. Whilst there is rationale for underachievement partners and FCDO should consider whether investment is still efficient where there are long term barriers to results achievement. Partners were able to reallocate funding, when the move to only lifesaving activities in Houthi controlled areas was instituted, from training activities (output 2.1 and 2.2) which has resulted in responses to emergency situations including cholera and flooding impacts.

  - Health facilities meeting minimum standards
Beneficiaries reported challenges with meeting needs when utilising UNICEF PHCs with four out of 13 facilities visited by the FCDO TPM unable to meet the needs of people seeking services, due to lack of supplies and facilities receiving more patients than it could cater for. Similarly of the UNICEF PHCs visited by the FCDO TPM there were minimal stock outs of essential medicines and supplies, with facilities reporting issues with the primary healthcare kit. All of the RISE facilities reported that they were able to meet the needs of people seeking services and reported minimal stock outs of essential medicines and supplies although four out of the seven facilities visited did have shortages of several essential drugs. However, output 2.5 found 25% of RISE facilities had stock outs of tracer drugs.

It is unsurprising that RISE facilities have fewer issues with meeting service need given the more comprehensive MSP delivered. However, RISE has reported that 75% of health facilities meet 80% of the standards within a PHC assessment tool (against a target of 94%). This is a huge improvement compared to the baseline of 2%. In FY25/26 RISE will expand supportive supervision, quality assurance systems and enhance service standards for onboarded or previously underserved facilities to improve this figure. It is currently not possible to compare beneficiary numbers between partners in terms of reach of services (outpatient consultations – output 1.1) as some partners report number of consultations and some number of beneficiaries (who may have had more than one consultation), this will be adjusted in the upcoming logframe review.

  - Minimum Service Package (see above section)
Effectiveness/Cost effectiveness
A key outcome (1.2) on number of healthcare facilities delivering the MSP has been achieved which is a strong demonstration of outputs successfully delivering against this outcome. However, the utilisation rate (1.1) has been marginally missed. Challenges to effectiveness include:
1. Dependency of donor funding - all funding to PHCs relies on donor support, with a reduction in donor funding challenges to maintaining levels of basic care are ongoing (particularly in Houthi controlled areas). A PHC investment analysis has been commissioned to develop a localised sustainable financing model in Taiz, the pilot is currently underway.
2. Scarcity of health workers – as a result of prolonged conflict there are a limited number of trained healthcare workers especially in rural areas. Partner efforts to train health workers is ongoing but limited given prioritisation (in Houthi controlled areas) and limited educational background to meet minimum requirements.
3. Harmful socio-cultural barriers are particularly prevalent in delivering and accessing GBV services, in addition an antivaccination movement by politicians in Houthi controlled areas which saw a pause in vaccination importation. The antivaccination campaign has largely ceased.
4. Approval processes by authorities in IRG and DFA areas are subject to delay and changes in requirements, as well as detentions in Houthi controlled areas restricting access. Houthi authorities suspended aid operations on several occasions in 2024/25. Approvals for downstream partners have also been delayed due to overlapping authorities in the South and following the dissolution of SCMCHA in DFA controlled areas.
Key effectiveness indicators include:

  - Response to emergencies
The inclusion of the flexible fund has enabled timely responses to outbreaks, including support through UNICEF to respond to the cholera outbreak in 2024. Within existing budget RISE was able to respond to the cholera crisis in April 2024 treating 3,125 suspected cholera cases and scaled up community engagement on prevention reaching 72,000 individuals with critical hygiene messages. Additionally, RISE responded to widespread flooding from July – September 2024 in Taiz, Hajjah and Hodeidah through the provision of critical cash assistance to 1600 vulnerable households, under the Emergency Preparedness and Response Mechanism (EPRM) to prevent further descent into crisis, guided by FSAC policies. The EPRM is a RISE mechanism that prepositions local partners to respond to emergencies and has proved its validity over the past year. Additionally following the withdrawal of US funding, RISE flexed to cover the Aden governorate under RISE, to fill a critical gap left in protection services. IRC had already been delivering these activities but with the withdrawal of US funding hard fought gains in protection outcomes were at risk of being lost.

  - Joint funding
The flexible fund also allowed FCDO to increase the effectiveness of the Programme by supporting co-funding efforts. The £3,951,500 support to the cholera response through UNICEF was match funded by KS Relief. Additional £1,200,000 funding was also added by FCDO, matched with Kuwait to support a further 290 PHCs following World Bank withdrawal of funding. Supporting nontraditional donors to contribute in line with priorities is a strong contribution to the effectiveness and sustainability of the Programme, especially in the context of reduction in traditional donor funding.

  - Localisation efforts
Through all three partners who support PHCs capacity building of PHC staff continues under key activities, however in Houthi controlled areas training activities were largely de-prioritised as they are not lifesaving.

RISE’s logframe tracks the number of local actors with strengthened capacity and resources to lead service delivery but this is not reported on until the final year given the phased implementation. However, RISE has several examples of supporting localisation efforts, including engaging For People Foundation and Fuqom Coastal Women’s Association to deliver in Aden following the US’s withdrawal of funding. This required strengthening institutional capacity. RISE has highlighted challenges in localisation in areas including Ramyah where the absence of health and protection actors means beneficiaries require financial support to access distant services offered by MSF and DRC. 60% of RISE funding went through local and national Yemeni actors, supported by Partner Capacity Assessments conducted at the beginning of the Programme and subsequent capacity strengthening activities including pharmaceutical quality assurance, finance training, development of GBV and CP case management SOPs and MEAL training. IRC has also partnered with the ICVA who provide technical support to the national NGO forum in Yemen. In January 2025 IRC/ICVA undertook a needs assessment to inform the design of capacity strengthening for Yemeni CSOs with trainings being delivered in 25/26.

Within the RISE consortium, FMF and BFD required support to develop GBV and child protection response capacity given they are health actors without specialized protection experience. IRC led efforts to build their capacity in establishing and operating various forms of safe spaces. This took place in locations including Al Dhale’e (IRG), Abyan (IRG) and Hodeidah (Houthi controlled) where IRC itself was operational and its field based staff were able to monitor, support and provide regular side-by-side assistance to partners. However, similar results were not observed in areas where IRC was not operational and consortium partners were solely responsible, despite remote support and routine field visits from IRC staff. This learning has influenced IRC’s protection capacity approach for Y3.

UNICEF’s mandate and relationships with ministries of health continues to benefit sustainability. UNICEF has provided technical assistance to both ministries of health in Sana’a and Aden to improve consistency in quality of care and successfully facilitated several essential guidelines including community based maternal newborn care, in line with WHO recommendations. Similarly, UNICEF with WHO has also worked with ministries to update the integrated management of childhood illness (IMCI) guidelines, training 328 health workers on the updated guidelines. Through FCDO funding UNICEF supported the strengthening of data systems for improved monitoring, planning and implementation.

IOM as the co-lead for the Refugees and Migrants Multi-Sector cluster has met with the Ministry of Foreign Affairs and Expatriates to discuss migration governance advocating for a collaborative response to the needs of migrants, progress should be monitored over the coming year as the Programme end draws closer. IOM continues to build partnerships with local health authorities supporting health activities in local health units and Rada’a Central Hospital in Al Bayda which has seen a strengthening of authorities’ supervisory role. IOM has also secured access to secondary healthcare services for migrants for free in public hospital (Ibn Khaldoon Hospital and Al Hay’ah Hospital).

Cost Effectiveness
The Business Case envisaged support to Yemen ministries to preserve health systems as a key cost-effective activity, including support to availability and accuracy of health and nutrition data and national capacity to respond to outbreaks. All delivery partners continue to deliver within the ministries of health systems including utilising incentive structures, supply chains and policies. Additionally expanding coverage of the MSP in high priority geographical locations represents excellent VFM. The last year has seen a huge achievement in delivering the MSP to 716 PHCs. This is an increase from 23/24 (401 PHCs) with additional funds to UNICEF, commencement of IOM and RISE activities, which is reflective of the increased investment in 24/25 (£78m compared to £38m in 23/24).

The de-prioritisation of non-life saving activities in Houthi controlled areas, as a result of detentions of humanitarian workers, particularly training of health workers, challenges the cost effectiveness of the Programme given that these activities are directly linked to sustainability. FCDO continues to work with the UN and other donors to advocate for the release of detained staff to allow for a resumption of all activities.

Equity
  1. Reach of activities to vulnerable groups
IOM: Given IOM primarily targets migrants, a marginalised group in Yemen, the project is well placed to improve equitable access to services, with examples of successful advocacy to improve access to health services including hospitals for free care. IOM does not systematically report logframe results with a gender breakdown and should work to do this for 25/26. However from their annual report, of the 50,925 primary healthcare consultations mor than half were female. IOM reported support to 510 people with disabilities (PwDs).

RISE: RISE’s monitoring of reach to marginalised groups is strong. Out of all outpatient consultations 53% were female, 0.3% were PwDs and 11% were IDPs. For nutrition services, 47% were girls under SAM and 3% under MAM. RISE has committed to improving malnutrition screening with an emphasis on girls to continue to improve equity. In terms of protection services, 86% of women and girls safe space activities were led by women and girls from communities, which reflects a high level of empowerment and agency although engagement of males particularly addressing GBV is important where possible, to address route causes.

UNICEF: UNICEF beneficiaries were generally well split between female and male. It would be beneficial if UNICEF disaggregates results in its logframe between marginalised groups to be able to track over the course of the Programme, with FCDO agreeing prioritised indicators where this is particularly relevant. There are continued challenges of increasing the number of female health workers which is a cross sector issue, UNICEF trained 20 females (out of 48) facilitators on updated guidelines on early screening and referrals for PwDs under five, as part of the updated to IMCI guidelines. This also demonstrates effort to improve screening for children with disabilities. Of facilitator health workers trained on updated case management 141 were female (out of 376).

Without an assessment of the number of people with disabilities in Yemen and data gaps it is difficult to compare PwD beneficiaries against the population but the global assumption of people with disabilities is 15%. Compared to reported figures from IOM and RISE there is a consistent limited reach to PwDs leading to a need to either improve disability assessments or outreach. UNICEF has not reported PwDs reached which should be tracked where possible going forward as well as an assessment of how to better reach PwDs.
[note] WHO estimate of 15% of global population living with disabilities.

  1. Targeting and geographical reach
With around 5000 health facilities in Yemen, UNICEF covers 65% (funding from the World Bank covering 2200, FCDO and other donors), INGOs around 15% and roughly 800 facilities are not funded. With US withdrawal funding this will be challenged. UNICEF continues to rely on the Composite Child Deprivation Index (CCDI) to inform geographic targeting of facilities. The CCDI uses the data generated through the MICS and includes an assessment of child welfare at the district level, incorporating 15 diverse indicators. It provides a comprehensive overview of child well-being status, focusing on health, nutrition, WASH, protection, and education sectors, as well as the availability of necessary interventions in a multisectoral approach. UNICEF is proposing an updated approach based on geo-analysis as referenced in Output 1 which is likely to improve efficiency of coverage.

Assessment of whether the Programme continues to represent value for money
The evidence from Year 2 suggests that the Programme continues to represent good value for money. The Programme’s VfM rationale as articulated in the Business Case continues to hold. As part of the wider Yemen Office portfolio, the Programme continues to deliver strategic results that align with UK priorities on humanitarian need, gender equality, and localisation. The priority for the coming year is to build evidence for comparative metrics to ensure best possible returns to investment for the communities served.
E: RISK
Overview of Risk Management
Over the past year, Women and Children programme has operated in an extremely volatile and complex environment, requiring active and adaptive risk management. FCDO Yemen maintained a structured approach to risk through quarterly reviews with partners along with ad hoc assessments in response to changing circumstances. Internally, bi-monthly reviews with the PRO, highlighting updates on a quarterly basis to the SRO (and ad hoc where necessary). These reviews focus on each risk category, assessing risk appetite and ratings and monitoring the status and actions required to address both emerging and ongoing risks. Monthly Programme Boards held by the Development Director focus on key risk shifts and any escalation requirements in line with the FCDO Yemen escalation framework.

The Programme risk rating appetite remains in line with that at approval stage as ‘severe’. Partners continue to deliver in an incredibly challenging environment, adapting to new restrictions and external changes over the course of the year. Risk appetites per category have not changed over the past year but were reviewed as part of a cross portfolio FCDO Yemen review in November 2024. The appetites include eager for strategy and context, policy and programme delivery, and reputational risks, receptive for financial and fiduciary, and safeguarding and a cautious appetite for public service delivery and operations and people.

Currently one risk remains outside the Programme’s risk appetite (safeguarding category) and has been escalated accordingly (see below for details). The humanitarian response in Yemen faces a complex array of risks that could impede the delivery of the Programme. The following risks have been particularly relevant over the course of the reporting period, with some evolving into issues:
[note] FCDO monitors issues in the same framework as risks and these are therefore included.

FTO Designation of Ansarallah (known as the Houthis) by the US - Major
On March 4th the US Department of State announced the redesignation of ‘Ansarallah’ as an FTO. This intention was announced in January but no updates on general licenses were given until 5th March to exclude humanitarian activity from the FTO designation. This designation created risks that cuts across financial and fiduciary, policy and programme delivery and strategy and context appetites, with risks at severe. All delivery partners had to reassess their ability to deliver in Houthi areas, with the risk of prosecution given the delay in general licenses, and subsequent residual risk utilising telecoms and banking infrastructure. The risk was heightened for IRC (as the RISE consortium lead) as a US based agency who took the decision to withdraw operations in Houthi areas and relocate offices to IRG areas (along with 10 other INGOs with US headquarters). With this departure the management of the risk around asset disposal procedures is being overseen with IRC. FCDO is now assessing options of continued delivery of key protection and health activities in Houthi areas andt he residual risks to the Programme include:
- Ongoing increased tension with the US and potential retaliation by the Houthis, increasing the safeguarding risk to delivery partner staff as well as access challenges to deliver activities. This could also lead to further withdrawal of partners and limited humanitarian access in the North.
- A chilling effect to Houthi infrastructure and trade with the North, impacting banks and imports which would hamper funding flows and availability of basic goods, driving inflation which challenges programme delivery and financial management. Several banks have relocated their headquarters to IRG areas and CBY Aden has begun a third-party certification process to support compliance with the US FTO designation. This signifies a further stratification of the IRG/Houthi financial systems and potential risk of blocked transfers between the two areas although there have been limited changes thus far. There is also a risk of blocked transfers from international banks to banks who do not move their headquarters to IRG areas due to a perceived non-compliance with the designation.
To address these risks, there is increased engagement with partners on the related risk management and mitigations include:
- Utilisation of the FCDO TPM to test financial flows against the delivery chain maps of partners
- Renewed security assessments by partners to support staff safety and increased oversight of live situations
- Withdrawal of activities where delivery is no longer possible and reviewing how best to continue delivery
- Reduction of staff or withdrawal in certain areas when appropriate. There is a wider impact of the designation that increases the humanitarian needs in Houthi areas, combined with the decrease in donor funding (see risk 5) risks challenge to the Programme theory of change.

Limited access to deliver programme activities – Major (Programme Delivery), Severe (Safeguarding)
The access risks are classified as severe and major as a result of detentions of delivery partner staff, ongoing conflict, security restrictions and restrictions based on US FTO designation and subsequent retaliation.

The key safeguarding risk under the Programme during the performance year has been the safety of partners’ staff which is a severe risk, this is beyond the Programme’s risk appetite for safeguarding as has been appropriately escalated. Challenges include conflict zones and authority interference, where staff may face threats or violence. During the performance year UN and NGO staff were detained in Houthi controlled areas with no basis shared. The first round of detentions occurred in June 2024 and since then the sector has reduced activity in Houthi areas to broadly that of life saving only. This included a substantial reduction in RISE and a change in UNICEF activities under the Programme, including cessation of MHPSS and case management activities, capacity building of PHC staff, solarisation and water supply upgrades. Funding was reallocated to emergency response support, upgrading of three PHCs (part of the West Cost response), WASH interventions, and diarrhoea treatment centres (nine priority facilities). In January 2025 the UN also paused activities in Sa’dah due to further detentions, including sanitation activities under this Programme delivered by UNICEF and IOM support to Munabbih hospital, a health facility providing urgent treatment to migrants.

Challenges to delivery by authority interference has hampered partners’ ability to implement activities effectively, and to reach the most vulnerable beneficiaries. An anti-vaccination movement in Houthi areas, led by the Houthis has disrupted effective primary health care services delivery, especially in hard-to-reach areas. The antivaccination sentiments have had a spillover effect in the IRG controlled areas and as a result of all these challenges, immunization coverage in 2023 and 2024 has declined by over 12%, and outbreaks of vaccine-preventable diseases such as polio and measles continue to spread across the North with a spillover effect to the South.

The Houthis have suspended activities at several points over the course of the year, introducing new requirements and mandating NGOs to share staff structures and involve local authorities in recruitment processes. OCHA are in negotiation to reverse these measures. Sub agreement approvals with NGOs were delayed due to overlapping authorities and inconsistent structures in both South and North.

FCDO Yemen continues to support delivery partners to adapt programming where staff are not safe, emphasising this as a priority. Partner management of this risk includes ongoing security assessments by the partner to ensure appropriate measures are in place, building community and authority relationships and reprogramming where necessary. FCDO continues to work with partners to ensure safeguarding policies are in place, accessible to communities, and that complaints mechanisms are functional. The ability to remain and be seen to be impartial is critical for negotiating and maintaining access and is an important element of conflict sensitivity. Partners also support OCHA’s Access Advocacy through information sharing with the Humanitarian Access Working Group. FCDO encourages partners to increase localisation of activities to National NGOs who are more likely to have local contextual knowledge and improved access. These combined strategies aim to ensure continued support to vulnerable populations amid a complex access environment.

Donor Funding Decline - Major
The risk of fund reduction, particularly due to the significant reduction in US funding and FCDO’s planned reduction from 26/27 to 0.3% of GNI has immediate and long-term effects to the continuity and effectiveness of the response in Yemen. This risks the sustainability of the Programme impact as well as success of shorter-term impact of activities. Additionally, external to programme activities there will likely be an ongoing increase in humanitarian needs with the reduction in funding and economic decline impacting basic needs. For UNICEF the decline in US funding impacts critical lifesaving nutrition services which were dependent on the nutrition pipelines solely funded by the US. Increasing needs and decreasing funding will challenge the outcomes and impact of the Programme and progress will need to be closely monitored.

FCDO has worked to inform partners of budget allocations as soon as these are communicated to FCDO Yemen, confirming a smaller amount in April 2025 for example to provide some certainty and then a final amount later in May. Following reductions in BHA funding in early 2025 FCDO Yemen engaged with partners to understand impacts to their operations and key sector gaps to understand if there are discrete areas where the Programme can support to support short term disruption. Under RISE savings made from the reprioritisation exercise in Houthi areas were utilised to provide essential protection services gaps in Aden where BHA funding had been disrupted.

Deteriorating Humanitarian Context - Major
A deteriorating humanitarian situation in Yemen significantly escalates existing risks. Increased hunger, malnutrition, disease outbreaks, and mortality create a dangerous cycle of vulnerability. The breakdown of essential services like food security, healthcare, and water access further compounds the drivers of conflict and suffering, undermining prospects for recovery and long-term stability.

Yemen’s economy further deteriorated during the reporting period with suspensions by the IRG Central Bank of Houthi linked banks accessing the SWIFT system and the Houthi’s retaliation ban of 13 IRG linked banks, deepening economic fragmentation and subsequent divergent currency values: YER 530/USD in the North vs. YER 1,840–2,560/USD in the South. The sharp depreciation of the Yemeni Rial in the South severely eroded household purchasing power, forcing over 60% of families to spend the majority of their income on food. This contributed to escalating food insecurity and alarming rates of Global Acute Malnutrition (GAM), with 22% in Hajjah and 40% in Hodeidah (IRG-controlled). To mitigate the risk of deteriorating humanitarian situation, FCDO Yemen prioritize predictable funding for partners, moving to a multiyear agreement with UNICEF, building on the multiyear agreements with IOM and IRC.

Further major risks in the Programme include aid diversion and safeguarding of beneficiaries given the challenging context of operation. Mitigations to these have remained consistent to previous years and in line with FCDO and partner best practice. Partner reporting on fraud cases has increased, most likely as a result of FCDO advocacy to partners to improve reporting, rather than an actual increase in cases but this will continue to be monitored. Safeguarding case reporting has remained limited and in the coming year FCDO will work with partners to explore thresholds of reporting.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
The Programme has engaged key implementing partners: IOM, UNICEF, and RISE. Through UNICEF the Programme supports CIMP and during the FY funded an Interagency Gender Advisor, hosted by UN Women through the Standby Partnership. Overall, partners have demonstrated strong performance in both delivery and financial management. All four direct delivery partners adhered to the agreed reporting schedules, submitting narrative and financial reports on time and in line with FCDO standards.

The W&C Programme Team has had changes over the course of the performance year with a new PRO joining the team in October and a new Programme Manager in February. This has inevitably seen a change in historical knowledge and relationships established under the Programme. Partners have been supportive of new FCDO team members, providing introductory sessions and re explaining decisions as required. This has however inevitably required a period of adjustment and re-establishment of relationships and ways of working.

Table 1: Project and implementing partner information
Partner	24/25 Spend	Type of Agreement	Dates
UNICEF Main Agreement	£26,200,000	Contribution Arrangement	01/04/24 – 31/03/2025
UNICEF Cholera KSrelief joint Response	£3,951,500	Contribution Arrangement	01/11/24 - 31/03/25
UNICEF Kuwait Fund PHC	£1,200,000	Contribution Arrangement	30/09/24 – 31/03/25
UNICEF CIMP	£110,748	Under a contribution arrangement with UNICEF	07/10/2024 to 31/03/2025
RISE	£10,176,829	Accountable Grant	15/02/24 – 31/03/27
IOM	£2,000,000	Memorandum of Understanding	01/10/2024 to 31/03/2027
Red R	£47,285	Accountable Grant	N/A
Total	£43,686,362
[note] A further agreement has been established with UNICEF running to March 2027.
[note] Contribution also made by KSRelief to support WHO cholera response
[note] Contribution also made by KFD total funding to $3,000,000
[note] The agreement with CIMP falls under the UNICEF contribution arrangement with CIMP as a second tier partner.
[note] This is the timeframe for the standby partnership role not the whole AG
[note] This agreement is managed under the Humanitarian Emergency Response Operations and Stabilisation (HEROS) Centrally Managed Programme utilising the Standby Partnership mechanism, with funds contributed from the Women and Children Programme for the position with UN Women.

Partner Delivery Performance
Engagement and oversight with partners (UNICEF, IOM) can be limited by what is provided from in the central framework agreements (between FCDO and UN agencies) and subsequent bilateral contribution arrangements which means reporting is streamlined, and budget detail is also limited. However, IOM and UNICEF have both provided for additional engagement which allows for adaptative programme management, as required given the context.

UNICEF: In line with the agreement UNICEF provides biannual progress reports, along with quarterly meetings to discuss contextual challenges and progress. UNICEF reporting gives strong strategic context including progress across the sector given UNICEF’s mandate, going forward it would benefit from additional focus on aligning the narrative to the results framework. There are four agreements with UNICEF during 24/25. There are challenges in overseeing several different agreements with UNICEF especially where activities overlap. This was done as additional funding was linked to joint contributions with KSreflief and Kuwait Fund. It is recommended where possible going forward that if agreements need to remain separate that it is agreed that reporting is streamlined to collate results where possible. In 25/26 UNICEF and FCDO Yemen have signed a multiyear agreement which should also improve transition between years and reduce the risk of a gap in services.

RISE: All quarterly reports have been submitted on time and in line with agreed templates with excellent narrative on the impact of contextual changes and programming adjustments. IRC has shown a proactive approach in managing the consortium, sharing performance challenges with FCDO and providing plans for improvements where necessary. With the withdrawal of IRC from Houthi areas there have been challenges in communications with partners that are subsequently no longer receiving funding through the Programme. Going forward, it is recommended that FCDO has more frequent (quarterly) engagement with other consortium members to RISE to ensure there is space for direct feedback and contextual updates.

IOM: IOM provides high level quarterly progress updates and more detailed biannual reports in line with template agreed through the Grand Bargain. Beyond what is required in the agreement, IOM quarterly meetings have been transparent on the challenges faced over the course of the year and how adaptations have been made. Going forward it will be useful for IOM to include reflection on challenges to delivery in reporting and a more detailed VFM assessment.

Finance
In financial year 24/25 the Programme spent £43,686,362 including £5,800,000 held at risk. The FCDO held the at-risk budget due to uncertainty of total allocations to the Yemen budget which were then released in November 2024 following an assessment of needs and partner spend. £4,157,133 was absorbed by the Programme from across the FCDO Yemen portfolio as result of underspend.

The IRF at the beginning of the year allowed for additional funding to be allocated to partners to respond to emergency situations. This included £5,151,000 to UNICEF which stewarded in matched funding from Kuwait Fund and KSrelief to respond to the cholera outbreak in 2024 and enhance the numbers of PHC facilities reached through the main UNICEF agreement. This contribution leveraged a further $6.5m USD in funding to priority areas within the response.

Partner Financial Performance
FCDO was not able to confirm FY24/25 allocations until March 2024 and some at risk funding not allocated until November 2024. This is an improvement in previous years and for FY26/27 onwards FCDO will resume multiyear allocations. From a financial management perspective, the partners have generally maintained a high standard in reporting accuracy and budget forecasting. Most partners provided financial reports in a timely manner, with clear breakdowns of expenditure against planned budgets.

- UNICEF: UNICEF has continued to be flexible in absorbing additional funding to respond to emergency support requirements (cholera support). They have spent or committed all FCDO funds by the end of the financial year. UNICEF’s VFM reporting is limited
- RISE: The initial allocation to RISE for 24/25 was £14,000,000 however this was reduced to £10,176,829 as a result of a low burn rate in quarter one due to challenges in setting up project sub-agreements. RISE’s adaptations in quarter four with some restricted activities and reallocation of spend to alternative areas shows good financial adaptability. RISE has also provided comprehensive VFM reporting with some refinement needed on data but demonstrative of strong transparency and improvement efforts.
- IOM: IOM has fully utilised the allocation of £2,000,000 in 24/25. VFM reporting from IOM is included in the annual report but is limited to minimal economy measures. A priority for FCDO is to establish consistent metrics with partners, including IOM in 25/26 but to restrict this to data that is already available to IOM to avoid additional burden.
Coordination between partners is largely through the relevant sector clusters. The Programme avoids creating additional coordination mechanisms that undermine those already existing that involve a wider range of relevant actors that are not funded through this programme. However, there are benefits to be made through ongoing adaptation and learning where partners are delivering similar activities. Exchanging lessons and good practice on conflict sensitivity could be a particularly beneficial area.

G: MONITORING, EVIDENCE AND LEARNING
Monitoring
FCDO is establishing a Women and Children monitoring framework to align monitoring activities, oversee findings from TPM and track key learnings. The Framework will set out the methods used to monitor partner results in line with the log frame, through quarterly and biannual reports and regular meetings. Whilst monitoring activities have been ongoing since the start of the Programme, the Programme team was carrying staff gaps which have now been filled, allowing for a more detailed framework. In November 2024 the Programme Team commenced a review of the logframe to establish indicators the partners jointly report on and ensure milestones are set where possible for the remaining years of the Programme. This review has been complex given the differences in individual partner logframes and the need to align differing activities under indicators. The Year 2 Annual Review is the first year that partner output and outcome reporting methodology is aligned and reflects the main partners to the Programme. Several learnings have emerged through the process of this review, reflected in Section C and will be utilised to do a further update of the logframe but ensuring it remains streamlined and manageable.

Given that FCDO is not present in Yemen, relationships with partners are crucial to understanding challenges and progress in programme delivery, especially given a rapidly evolving context. The W&C Team meets with all partners on a quarterly basis and utilises longer biannual meetings to discuss reports and strategic challenges. Meetings allow for FCDO to interrogate programme progress and assess adaptations as required. When possible FCDO meets with partners in person, but this is limited as partners are based in Yemen, with some of the FCDO team also based outside of the region. To deepen understanding and ensure contextual relevance, FCDO Yemen staff also travel to Yemen to visit partners directly. These field visits allow for a closer, more nuanced understanding of the situation, which enhances the overall effectiveness of monitoring activities.

Field visits
Engagement with local partners, community leaders, and service users provided critical insights into the relevance and accessibility of services, particularly in the context of the triple crisis (detentions, shrinking humanitarian space, and funding reductions). One W&C monitoring visit took place in FY 24/25 (June 2024), the most recent visit took place in May 2025, where FCDO Yemen undertook joint monitoring of facilities with the World Bank and KSrelief.

Third Party Monitoring
Given the absence of FCDO from Yemen a cross FCDO Yemen third party monitoring contract under the Tahseen programme is drawn on for all programmes in the portfolio. In 24/25 two monitoring visit were conducted by Tahseen.

In January 2025 a monitoring visit was conducted with a sample of seven RISE supported health facilities and 13 UNICEF supported facilities in IRG-controlled areas, focusing on service availability, facility conditions, and data management and reporting. A set of KPIs were agreed to assess the partners delivery against. RISE was rated ‘green’ in all categories whereas UNICEF had notable issues in relation to deliveries/ante-natal care, the Primary Healthcare Kit, WASH facilities, reporting feedback and facility quality. This is likely reflective of the wide-ranging reach of UNICEF support to facilities (655) compared to RISE (56), and the more comprehensive support provided through RISE, at an increased cost per facility. The Tahseen report did not make recommendations for next steps to address findings in the report, this will be apriority for the coming quarter to agree actions with partners based on the report. Further monitoring visits can then support assessment of improvements made as a result.

The second monitoring visit conducted by Tahseen in quarter four of 24/25 included a survey of migrants (111) at the Daar Saad migrant response point in Aden to assess knowledge of and access to IOM supported facilities as well as on site surveys of two hospitals and one health unit. The following sets out key findings and actions agreed:
1. Health screening: At an IOM response point 96% of migrants received a health screen but this dropped to 0-30% at IOM support hospitals and health units. Follow-up may be useful at health facilities to ensure that they provide a general health screening for migrants seeking care.
2. Referrals/Follow-up: Variations in levels of comprehension of how to follow up on referrals was found with a low rate of 65% at one site. IOM should check with MRP and Ras Al-Ara Hospital to ensure that they understand the importance of referral follow-up and that they have adequate resources to do so. This may include a further assessment of what may be prompting lower rates at these facilities.
3. Needs met: One facility had a concerning level of migrants who felt their healthcare needs had not been met following support (94%). IOM should follow up with this unit to assess what may contribute to poor service ratings, considering referrals and a lack of essential medicines.
4. Barriers: Given the range of barriers cited for the migrant response point, IOM may wish to review this regarding language, documentation, discrimination, and harassment.
5. Training: IOM to conduct specific training for migrant services in all facilities, with updated training on protection and healthcare for the MRP and Habban Hospital.
The Tahseen programme came to an end in March 2025 and a new programme ‘MERLY’ was established and is currently in inception. The W&C team has been engaged during the MERLY inception to agree a workplan for 25/26 that includes more frequent monitoring visits to partner activities and cover both North and South, with a target of 6. Priorities for the MERLY programme will include verification of incentive payment receipt by health workers, assessing safeguarding protocols against findings from FCDO due diligence assessments of partners.

Partner Monitoring
UNICEF: UNICEF conducts its own TPM with the last round in Oct-Nov 2024 and include the following key findings of PHCs:
- 99% received operational budgets, primarily used for hygiene and utilities.
- 96% received per diems for outreach activities.
- 91% received Yemen PHC kits, though only 59% reported kits fully met needs. The FCDO TPM supports this finding, with the assessment showing that there were minimal stock outs of essential medicines, but facilities reported issues that the primary healthcare kit was inadequate with key missing items for natal care and typical medication requirements. UNICEF has subsequently deployed a consultant to conduct a comprehensive review of the supply chain system at the PHC level and contents of the PHC kits compared to their needs and is working on the development and procurement of the revised Yemen customised PHC kit.
- 92% of beneficiaries were satisfied with services. The FCDO TPM did not directly assess patient satisfaction, but the report found that nine out of 13 facilities visited did not have feedback mechanisms and four of the 13 facilities stated they were unable to meet needs of people seeking services due to lack of supplies and capacity overload, a clear point for improvement.
RISE: RISE conducted a baseline assessment in the targeted governorates in August 2024 to establish baseline values for selected indicators as well as to gather contextual information, identify influencing factors, and provide recommendations for programmatic decisions. In 24/25 RISE tracked progress through a total of 255 MEAL field visits including 201 in Houthi controlled areas and 54 in IRG areas. The field visits served to verify the presence and engagement of nominated health workers at targeted PHC facilities, ensuring that designated staff were both present and actively participating in project activities. RISE also used these visits to assess implementation progress and review the quality and accuracy of reporting tools, including registers and records, ensuring proper documentation and data reliability. Four visits were undertaken to cash distribution points in Hajjah, Hodeidah, and Al Mahwit. These visits aimed to validate the beneficiary targeting, assess the distribution processes, collect critical feedback from beneficiaries, and ensure the safety and protection of clients at the distribution sites.

Beneficiary Feedback
IOM: IOM, through its TPM, conducted two satisfaction surveys with migrants. Data was collected between January and February 2025, via face-to-face interviews with migrants that received assistance. 96-98% of the respondents were satisfied with the assistance provided at the migrant response points, and 96% also reported that the project helped reduce the vulnerabilities they face. None of the respondents reported being excluded from receiving the services, and all respondents (100%) reported that they were treated with respect. Furthermore, a total of 79-90% of respondents said that assistance was provided in a safe, accessible, accountable, and participatory manner. Whilst the FCDO TPM found that at migrant service points a high level of beneficiary comprehension of feedback mechanisms was observed, two supported hospitals had 0-10% of migrants knew how to provide feedback or register a complaint about services provided. No beneficiaries had received feedback on issues that they had raised, with only 25% having provided feedback and 2% a complaint, demonstrating the need for IOM to improve awareness of complaints mechanisms at all supported facilities, not just migration response points, and to ensure follow up to complaints.

RISE: RISE conducted 94 awareness sessions reaching a total of 1,171 beneficiaries (610 female) to support an understanding of the client responsiveness and accountability framework along with the distribution of materials. RISE subsequently received 1,451 feedback items with 34.4% of these requesting further information and 29.7% requesting assistance. It is not clear from RISE reporting what adaptations were made from this beneficiary engagement and this is being followed up on by FCDO.

UNICEF: Through technical assistance and co-facilitation, UNICEF supported key community engagement coordination mechanisms—including the national Community Engagement and Accountability to Affected Populations Working Group and the Social and Behaviour Change Working Group in the South, to promote a system that places communities at the centre of humanitarian and development responses. UNICEF has a Complaints and Feedback Mechanism that covers all UNICEF programmes, with the primary channel being a call centre with toll-free number and a dedicated email address. Between 1 April 2024 and 31 March 2025, UNICEF’s Complaints and Feedback Mechanism (CFM) received 23,358 grievances including inquiries and feedback, although it is not possible to disaggregate these for FCDO funded activities. At the time of reporting, 94% of these records are closed, 4% are under review and 2% remain open. For better comparative analysis it will be useful for UNICEF to report to FCDO the analysis of themes across these items and categorisation between inquiries, grievances and feedback.

Learning
UNICEF, RISE and IOM have provided strong narrative for the lessons learnt over the course of programme delivery. Lessons that are consistent between partners include:
- Strengthening protection capacity sharing
- Community based protection systems.
A key learning from the implementation period has been the effectiveness of community-based approaches in improving access to and utilization of health services among both host and migrant populations. IOM’s experience with Community Health Volunteers (CHVs) in Rudum district in Shabwah governorate has shown that empowering local actors, particularly those who are trusted within their communities, can significantly improve health-seeking behaviours and early detection of health risks. Building on this success, IOM is planning to expand the CHV model to other locations—such as Aden, Lahj and Al Bayda. As part of this expansion, IOM will enhance the approach by including members of the migrant community within the CHV team.

Key learning over the 24/25 from FCDO includes:
Adaptability is critical: The Programme’s ability to pivot in response to the triple crisis (detentions, shrinking humanitarian space, and funding reductions) has been a key success factor. Flexibility in delivery models and decision-making processes has enabled continued service provision in high-risk areas.
Strengthen the use of community feedback in partner delivery adaptation.
The need for a more deliberate approach to conflict sensitivity across the Programme team, partners and the Programme team.

Date of last narrative financial report	IOM:30 May 2025 / RISE: 14 May 2025 / UNICEF: 30 Apr 2025	Date of last audited annual statement	IOM: 31 December 2024 / RISE: 30 September 2024 / UNICEF: 31 December 2022

Annex A – Full list of recommendations for the Women and Children Programme

	Recommendation	Timeline
1	The Programme logframe, and partners’ individual logframes need close revision to ensure partners achievements are being captured appropriately and accurately. This includes for example: / Adding in UNICEF PHC utilisations rates to Outcome Indicator 1.1 / capturing more effectively IOM’s protection progress/impact. / Partner’s logframes need to detail in a ‘notes’ column exactly what is being measured and how and this needs to be shown in the master programme logframe. / Additionally, partners should explain how they are using their disaggregated data for the benefit of those they assist and breakdown disability data by age/gender/type of disability where feasible. / The Programme logframe may need less indicators but carefully chosen ones that are likely to be appropriate when/if extra programming is added, such as happened this year with the Kuwait joint project and the Cholera response. This will help ensure standardisation of reporting. / At the Outcome level, the indicators for 2.1 and 2.2 should be examined to determine if they can be used as realistic proxy measures of impact on declining GBV risk and improved protection of civilians, respectively. / The Programme logframe should be revised to capture the protection results and the progress/impact of IOM’s work on conflict sensitivity. / It is currently not possible to compare beneficiary numbers between partners in terms of reach of services (outpatient consultations – output 1.1) as some partners report number of consultations and some number of beneficiaries (who may have had more than one consultation) / Compared to reported figures from IOM and RISE there is a consistent limited reach to PwDs leading to a need to either improve disability assessments or outreach. UNICEF has not reported PwDs reached which should be tracked where possible going forward as well as an assessment of how to better reach PwDs.	End of September 2025
2	The Third-Party Monitoring capacity has clearly enabled the Programme to be confident in partner’s reporting, as Yemen remains difficult for FCDO staff to visit widely. However, the TPM doesn’t monitor all of the Programme logframe indicators and this should be addressed as part of the MEL framework development. Additionally, the TPM needs to be able to effectively conduct their monitoring in the North, as well as the South.	End of August 2025
3	In the immediate future, the conflict sensitivity challenges are only mounting for the humanitarian response. Funding reductions and narrower targeting themselves require conflict sensitive handling. Whilst conflict sensitivity and do no harm are woven throughout the Programme and partner approaches, there is a need for a strengthened, more deliberate approach across the Programme, with capacity building and lessons and good practice sharing. A workshop to look at these issues, alongside promoting localisation (see recommendation 6, below) may be considered.	End of December 2025
4	Expand on the lessons being learnt from all partners about effective working with national NGOs, especially to improve service provision in the health sector. FCDO Yemen may want to consider holding a workshop to explore how localisation can be promoted, especially in light of US and FCDO funding reductions and further deterioration in security. Along with a focus on conflict sensitivity (recommendation 3) this would generate valuable learning and promote ideas for both the current programme and a future humanitarian Business Case	October 2025
5	The planned Health Sector Political Economy (PEA) Analysis may present a key opportunity to build on UNICEF’s work on sustainable PHC financing and help to develop a shared vison for health in Yemen with donors and the Government of Yemen. It could also strengthen a conflict sensitive approach and build on other partner work, such as IOM’s work to examine the existing normative framework for migration.	End of December 2025.
6	FCDO should use the planned meeting on the health sector it is convening in Aden in early September to ensure partnerships with other key health sector donors, such the World Bank and Gulf donors are maintained and strengthened. This meeting may find it useful to examine the likely impact of the ‘Humanitarian Reset’ on Yemen, in order to help plan for FCDO’s budget reduction and the follow-on Business Case. Difficult funding decisions will need to be made imminently in order to plan for 26/27 and also for the next humanitarian Business Case for the follow-on programme. With US withdrawal, FCDO is well placed to take a convening role with Yemeni authorities, donors and operational agencies to map out who is best placed to fund what in the health sector.	Third quarter of the year.
7	Expand on the lessons being learnt from all partners about effective localisation/working with national staff members and NGOs, especially to improve service provision in the health sector. FCDO Yemen may want to consider holding a workshop to explore how localisation can be further promoted, especially in light of US and FCDO funding reductions and further deterioration in security.	September 2025
8	The Programme should capitalise on relationships built with UNICEF and MoPHP and in the next year, work on developing a shared vision for health in Yemen among the Government of Yemen and key international donors.	Ongoing
9	For the year ahead, the work already underway on PEA analysis of the health sector could perhaps be expanded. It could build on UNICEF’s work on sustainable PHC financing and help to develop a shared vison for health in Yemen with donors and in order to help strengthen IRG governance capacity.	March 2026
11	The development of a VFM framework has progressed in Year 2 and should be finalised in quarter two of FY 25/26 providing a more structured evidence base for assessing partner delivery whilst aiming to not increase burden on partners. To include: / Common VFM indicators for partners to report against annually to support comparative analysis / track the MSP cost in PHCs across partners between years going forward. / Currently there is inconsistency in partner reporting on indirect costs, with some including all staff salaries and others allocating these to activities. Over the next year FCDO will work with partners to improve consistency on this to allow for comparison. / request examples of economics of scale benefits or challenges to this in the context.	September 2025
13	With the incoming new TPM provider Women and Children assessments to include: / potential impact in variance of incentives between partners or that health workers are receiving the payment as expected. This should be a priority for MERLY in 25/26. / compare patient outcomes as a result of treatment in these facilities (effectiveness) which will be tracked as part of the VFM framework and through TPM in the coming year. / a focus on improvements in service provision from UNICEF will be tracked to assess whether it is possible to increase this using the basic MSP	Ongoing to March 2026
14	If UNICEF agreements remain separate that it is agreed that reporting is streamlined to collate results where possible.	Ongoing