## Saving Lives in Sierra Leone Phase 3 Annual review
(October 2024 – October 2025)

Title: Saving Lives in Sierra Leone Programme Phase 3
Programme Value £ (full life): £35m		Review date: October 2025
Programme Code : 301141	AMP start date: 09/08/2023	AMP end date: 31/03/2028

Summary of Programme Performance
Year	2024	2025
Overall Output Score	B	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	Business case and summary
DevTracker Link to results framework:	Logframe

Acronyms and abbreviations

CHC	Community Health Centre
DHMT	District Health Management Team
DHS	Demographic and Health Survey
EPD	Ending Preventable Deaths
FHC	Free Healthcare Initiative
GNI	Gross National Income
GoSL	Government of Sierra Leone
ISSV	Integrated Supportive Supervision
KMC	Kangaroo Mother Care
MoH	Ministry of Health
MPDSR	Maternal and Perinatal Death Surveillance and Response
NGO	Non-Governmental Organisation
NMSA	National Medical Supplies Agency
ODA	Official Development Assistance
PHC	Primary Health Care
PHU	Peripheral Health Unit
RMNCAH-N	Reproductive, maternal, neonatal, child and adolescent health and nutrition
SCBU	Special Care Baby Unit
UNICEF	United Nations Children’s Fund
WASH	Water, Sanitation and Hygiene

A. SUMMARY AND OVERVIEW

Description of programme
The Saving Lives in Sierra Leone 3 programme (SL3) supports system strengthening and delivery of quality health services at national level through essential commodities procurement for the Free Healthcare (FHC) Initiative; supports the functionality of Special Care Baby Units (SCBU), saving the lives of premature, low birthweight and sick newborns; as well as supporting health service provision within six districts in Sierra Leone – Kono, Kenema, Kambia, Moyamba, Bombali and Western Area Urban. SL3 is a £35m UK investment which aligns to Sierra Leone’s Health Sector Strategic Plan (in place to 2025) and builds upon its predecessor programmes SL1 and SL2 where significant progress was made to End Preventable Deaths (UK EPD Strategy – now called ‘Healthy Women, Children and Newborns’(HWCN)). SL3 is expected to further reduce mortality and morbidity of women, girls and children by improving the quality, availability, equity and accessibility of reproductive, maternal, neonatal, child and adolescent health and nutrition (RMNCAH-N) services. SL3 helps to strengthen health systems, improve access to medicines, improve service delivery and quality of care through training, mentoring and empowering communities to demand quality, inclusive and accountable health services. The programme components are delivered through two linked delivery mechanisms:

1. The United Nations Children’s Fund (UNICEF) procures and oversees the distribution of commodities nationally (medicines and medical equipment) and oversees support to 16 Special Care Baby Units (SCBU).
2. A consortium of six local and international Non-Governmental Organisations (NGOs) led by Concern Worldwide (referred to herein as ‘Concern’) is providing support to the District Health Management Teams in six districts covered by UK funding.
As with previous UK support, the programme is flexible and closely linked to centrally managed programmes to respond to health emergencies.

Planned reduction in UK ODA will result in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

About changes to UK ODA:

- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow

Summary supporting narrative for the overall score in this review
This second Annual Review of the SL3 programme awards a score of A – Outputs met expectations, recognising strong progress over the past 12 months despite a challenging operating environment. While last year’s review noted delays in programme inception, SL3 has overcome many of those hurdles in implementation, with measurable delivery across key output indicators. The programme’s narrower scope under SL3 compared to SL2, resulting from reductions in Official Development Assistance (ODA), has enabled a more focused mandate and the delivery of low-cost, high-impact interventions to strengthen RMNCAH-N at national and district levels. However, this reduced scope has also limited progress in governance, system strengthening, and coordination between national and district levels. System strengthening takes time, and this coupled with the focus on service delivery over the past year means system strengthening gains have been limited.

SL3, however, continues to support Ministry of Health (MoH) priorities and has positioned the UK as a key health sector partner. It has also served as a platform for other UK investments, including outbreak response and water, sanitation and hygiene (WASH) in healthcare facilities. Key achievements this year include:
- UK support to SCBUs has been pivotal in achieving a neonatal survival rate exceeding 90%. This is a landmark achievement for the past year of the programme that builds on sustained and incremental improvements in survival in SCBUs over the three phases of the Saving Lives programmes since 2018.
  [note] The baseline survival in SCBUs at the 2018 initiation of UK support was 78%
- Support for the Maternal and Perinatal Death Surveillance and Response (MPDSR) in the six focus districts has been a major success. The Review identified a high degree of ownership at both District and MoH levels, with improved understanding of factors in preventable death and learning from the reviews feeding into quality improvement work delivered through other SL3 components.
- With continued UK backing, the Free Health Care Initiative (FHC) has enabled the health system to consistently provide essential medicines and medical supplies for maternal and child health services, in the last 12 months achieving considerable sustainability gains in last mile distribution.
SL3 has been well positioned to align with GoSL’s priorities, with MoH feedback collected for the review noting the programme has delivered substantial results to contribute to the reduction of maternal and child mortality in Sierra Leone. Engagement with MoH is stronger in some areas than others, but the Annual Review noted broad MoH support for reinforced national ownership, greater strategic coherence, and prioritising organisational capacity building within the MoH going forwards. This aligns well with the UK’s refreshed approach to global health with a focus on system strengthening. However, the ability of the programme to influence government investment in health and in ownership of health system strengthening work appears to be limited, not least in the context of programme reductions over time and the very challenging fiscal space for MoH. The ability of SL3 to act as a platform for coordinating and strengthening the donor community, to rally donors around MoH strategic health system planning is also limited, reflecting that the programme has started to deliver results and impact at a time of growing global fragmentation and the reducing ODA landscape across bilateral and multilateral donors.

Major lessons and recommendations for the year ahead
Major lessons:
1. Sustained progress, but fragile gains. Sierra Leone continues to face challenges in Universal Health Coverage (UHC), driven by limited domestic resource allocation to health, high out of pocket expenditure, gaps in quality and availability of data, human resources for health challenges and poor healthcare infrastructure including lack of availability of equipment and water and sanitation facilities. Despite these challenges, Saving Lives has achieved notable improvements in health outcomes over three phases. However, these gains are at risk due to planned reductions in ODA: the intended impacts of the programme as originally designed are now unlikely to be realised through to 2028. Limited MoH capacity and ownership, especially for flagship initiatives such as SCBU and FHC, threatens sustainability.
2. Shift from service delivery to system strengthening. Macroeconomic conditions and debt repayments are severely constraining Sierra Leone's financing for health. This has been exacerbated by wider cuts to ODA affecting partners in Sierra Leone. USAID, which planned to implement a programme in five of the 10 districts not covered by SL3, is yet to start programming. At the same time, the UK’s development strategy, rooted in a modern development partnership with Sierra Leone, will now move fully to system strengthening further away from strengthening district delivery, necessitating a substantial change in approach for the programme. Given the lack of sustainable national financing for health or partners to step in, this requires careful prioritisation of critical services to be supported through transition.
3. Fragmented donor landscape. Profound fragmentation among donors in Sierra Leone is impacting the ability of donors to deliver coherent programmes and limiting MoH’s ability to draw on the donor community for support. An important example of this is in the fragmentation of procurement and distribution of essential healthcare medications across several bilateral and multilateral mechanisms.
4. Uncertain policy environment. The expiration of key national health strategies in 2025 creates uncertainty. Investments in health systems strengthening must be long-term, adaptable, and aligned with government priorities but there has not been evidence of strong demand from MoH for specific system strengthening activities.
5. Need for resilience building. The mpox emergency, declared in Sierra Leone in January 2025, stretched healthcare resources and impacted delivery of SL3 and GoSL’s health sector strategic plan more widely. Sierra Leone is highly vulnerable to the health impacts of climate change and health security threats, and these compounding impacts are likely to continue to be felt.
Major recommendations for the year ahead:
1. BHC and partners to review the theory of change and logframe to capture the transition of the programme through 2026, including identifying priority interventions to continue and those to responsibly exit. Both interventions being continued and those being exited through FY 26/27 require agreed sustainability plans. This would be supported by a thorough political economy analysis for the focus districts (and wider ecosystem to capture dependencies) to identify opportunities to embed these activities over time. Programme decisions should be communicated to partners at the earliest opportunity to support responsible exit.
2. BHC should use all levers, including as a leading global multilateral donor, to leverage multilateral investment in medication procurement in Sierra Leone, as this transitions to GoSL ownership over time.
3. BHC should develop a clear vision for a cohesive package of UK support to Sierra Leone’s health system, across bilateral and multilateral investments, Centrally Managed programmes (CMPs), other UK Government Department investments and non-investment support and influencing, engaging across BHC, for the remainer of the SL3 programme. UK should use all levers to support development and delivery of health sector plans, including strengthening progress towards greater domestic health financing. This support should be based on discussions with MoH on their priorities.
4. BHC should provide targeted technical assistance to the Ministry of Health to support the development of key strategic frameworks — including the National Health Sector Strategic Plan (NHSSP), health financing strategy, HRH roadmap, and RMNACH strategy — as prioritised by the Ministry. Addressing fragmentation may support stronger MoH leadership, therefore this should be complemented by diplomatic engagement to leverage UK influence and encourage alignment among multilateral and bilateral health partners with national plans. This will strengthen national ownership, improve coordination, and ensure external investments are coherent and responsive to Sierra Leone’s priorities.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
The programme’s intended impact is a reduction in preventable deaths among women, adolescent girls, and children in Sierra Leone by improving access to quality healthcare and advancing Universal Health Coverage (UHC). It focuses on strengthening national and district-level health systems while empowering communities to demand better services. To achieve this, five interconnected outputs are delivered across three strategic strands: national systems strengthening, district-level improvements, and community engagement. The five outputs are: reforming health policy and planning; enhancing access to medicines and medical equipment; improving service delivery and care quality; building health workforce capacity through training and mentorship; and fostering community partnerships to ensure inclusive, accountable healthcare access. This logic is rooted in FCDO’s approach papers on Ending Preventable Deaths (2021) and Health System Strengthening (2021) including a focus on Primary Health Care (PHC). A sixth output was not reported beyond the first year with subsequent adjustments to weighting for the other outputs. There have been no changes to the Theory of Change or Impacts and Outcomes in the logframe this year.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
Key health indicators in Sierra Leone continue to show improvement, maintaining the positive trajectory established during Phases 1 and 2 of the Saving Lives programme. Under SL3, significant progress has been made. At impact level, maternal mortality, under-five mortality, and neonatal mortality have all declined from baseline, continuing sustained improvements seen in earlier phases. However, not all outcome indicators are on track. The proportion of women attending at least four antenatal care visits is below target and the 2025 milestone for the proportion of births delivered in health facilities was missed. All other milestones have been met, with Outcome 2 targets significantly exceeded (Table 1).

Table 1. Progress against Impacts and Outcomes
Impact/Outcome	Indicator	Milestone (Mar 25)	Achievement / (Mar 25)
Impact: Fewer preventable diseases and deaths among women, adolescent girls and children in Sierra Leone	Maternal mortality ratio	435 per 100,000 live births	435
	Under-five mortality rate	95 per 1,000 live births	94
	Neonatal Mortality Rate	29 per 1,000 live births	29
Outcome 1: Increased availability, access and utilization of quality RMNCAH-N services	Antenatal care 4+ visits - percentage of women (aged 15-49 years) attended at least four times during pregnancy by any provider	80%	68%
	Proportion of births delivered in a health facility	87%	86%
	Decrease in number of Maternal Deaths notified in target districts	199	218
	Improved survival of small, pre-term newborns (1.5 - 2.0KGS) in Special Care Baby Units	89%	90%
	Increase in modern contraceptive prevalence rate (mCPR)	26%	59%
Outcome 2: MoH at the district level has improved capacity to deliver accountable, respectful, responsive and people-centred health services, in accordance with national guidelines	Percentage of individuals accessing primary health care services at health facilities who express satisfaction with both the qual / ity of services and attitude of healthcare workers. In 6 SLP3 districts	50%	93%
	Percentage of health workers who can identify a behaviour they have changed in line with respectful and dignified care. In 6 SLP3 districts	60%	92%

Several assumptions underpinning the Theory of Change are being challenged. Where outcome milestones have been missed - attendance at antenatal care and facility deliveries - these depend on influencing deep structural drivers. Although SL3 addresses some of these, the current output-to-outcome logic may need revisiting. Disaggregated data from SL3 districts should be analysed to better understand these gaps and refine outcome measures. Data limitations - such as the delayed DHS and reliance on less robust UN modelling - undermine the ability to track progress accurately. Under the 2023 Business Case, the non-SL3 districts were expected to receive equivalent support funded by the World Bank and USAID. However, the USAID-funded initiative has not commenced with five districts currently lacking health system strengthening support, posing a barrier to achieving national-level impact. System strengthening depends on sustained investment to convert outputs into meaningful outcomes and long-term impact. The sharp reduction in funding from SL2 to SL3 - and further cuts within SL3 - will limit the effectiveness of these efforts. While the Annual Review confirms that the current outcome and impact measures reflect the programme’s health priorities, the associated milestones need to be revised to better align with the programme’s reduced scope and broader health funding landscape in Sierra Leone. Reflecting the programme’s focus on women and people with disabilities, SL3 is flagged as significant on gender and disability markers. Work over the past 12 months has had considerable focus on both areas, however planned scaling back of activities is likely to have an impact particularly on disability inclusion focused work.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Sierra Leone has some of the worst maternal and child health indicators in the world. Health remains a development priority for FCDO, including a focus on improving the Health of Women, Children and Newborns (HWCN, formerly EPD) and a key human development objective in the BHC Country Business Plan. SL3 is BHC’s flagship programme contribution to these objectives in Sierra Leone. Ongoing support to build and maintain progress on improving health outcomes in Sierra Leone is justified given the challenging fiscal space for GoSL to deliver this work and availability of funding from other donors. The value of the programme was summarised well in a statement from a healthcare leader captured by the review team at the launch of the third party monitoring report for FHC distribution: “I want to pass on how grateful we are…I know the benefits of the £7m from [the] UK…that are felt by the women and children of Sierra Leone, as they are not able to help themselves”. During the field visit to a District Hospital, a hospital leader fed back that under SL3 “the work is visibly felt in the hospital”. Given demonstrated improvement in programme delivery from inception through to implementation, assuming the programme remains within risk appetite and consistent with VfM parameters, it should continue.

BHC’s funding context has changed since the original business case was approved, and the programme now needs to transition, continuing as currently structured to the end of March 2026, with specific activities then closing during FY2026/27, seeking to ensure a responsible exit. Substantial changes will be required to the Logframe, and work to review the programme and prioritise activities has already begun, with a focus on the highest impact priority system strengthening work, and the next steps both for the programme through transition and beyond after programme closure are captured in the major recommendations in this review.

## C. DETAILED OUTPUT SCORING

Output Title	Increased early detection of complications and appropriate preventative action for pregnant women and children.
Output number:		1	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	Increased from 10% after removal of Output 6

Indicator(s)	Milestone(s) for this review - Mar 25	Progress - Mar 25
1.1 Proportion of mothers that are referred from CHC levels to hospitals with CRADLE warning signs and recorded blood pressure and pulse rate. In 6 SLP3 districts	12%	36%
1.2 Number of women with hypertension in pregnancy detected with CRADLE at facility level. In 6 SLP3 districts.	320	690
1.3 Average minimum dietary diversity score - pregnant and lactating women. In 6 SLP3 districts	79%	85%
1.4 Increase in SCBU staff attendance at high- risk deliveries [Emergency Caesarean Section delivery].	>30% in 3 hospitals	60%
1.5 Increase in number of functional Kangaroo Care Units in (16) hospitals, and utilisation. / 1. Number of units achieving a score >15 using the WHO KMC progress monitoring tool / 2. Utilisation of KMC [percentage of admissions with birth weight 1.5-2Kg in KMC compared to SCBU admissions]	3 units / >10%	6 units / 13%
1.6 Number of blood banks that have a minimum quantity of blood available at all times (100% of daily inventories to be above 1/365 part of 1% catchment population of the blood bank). (Six districts where SLP3 have oversight)	4	5

Briefly describe the output’s activities and provide supporting narrative for the score
Indicators 1.1 and 1.2. CRADLE devices are a key SL3 funded intervention to support recognising hypertension in pregnancy. Output indicators covering use of CRADLE, documentation, and identification of risk using the devices have been greatly exceeded as at March 2025. In the Annual Review, MoH noted insufficient evidence of the value of the CRADLE device, recommending an alternative focus on promoting awareness of maternal danger signs and a need for stronger referral and transport systems. However, the field visit in particular found evidence these are strongly supported by frontline staff, functioning devices were available and these were being used to identify and refer high risk women, down to the community level. The intervention is also supported by DHMTs, with the review team being told it was “very important that we maintain the CRADLE”.
[note] MoH have recognised value of CRADLE at the national health summit with a resulting objective to nationalise and embed use of CRADLE in Sierra Leone going forwards

A training of trainers approach is being implemented by partners to expand coverage of CRADLE training, and quality assurance supervision is in place. Evidence from the review found CRADLE has improved care seeking from women concerned about their blood pressure and improved documentation (in turn improving data quality), alongside detection and referral of women at risk. Challenges persist, including availability of the wider suite of tools needed to detect and manage hypertension in pregnancy (including urine test strips, referral registers), however the broad success of the intervention has led to demand for the CRADLE approach in the other ten districts and from the National Emergency Medical Service (NEMS) and pre-service training support from nursing schools. Given output indicators have greatly exceeded present milestones, as this activity will be prioritised for the year ahead, more ambitious milestones should be set in recognition of and to demonstrate the wider impact of this intervention.

Indicator 1.3. Progress is being made on dietary diversity, evidenced by the indicator being exceeded at the March 2025 milestone, and this is being supported through monthly cooking demonstrations run at under 5 service clinics and antenatal sessions. Good testimonials have been reported by users, with attendance at the sessions increasing over time, and evidence of dietary shifts attributable to the programme including increased use of orange flesh sweet potatoes. Tools, seeds and saplings have been provided to establish backyard gardens at primary healthcare units, although these have had mixed engagement. Where garden committees have been established, and DHMTs are showing ownership of these gardens, they are likely to be sustainable. One key achievement of the implementing partner is the roll out of the national recipe book, establishing a consistent approach to dietary diversity across districts.

Indicator 1.4. Increase in SCBU staff attendance at high-risk deliveries reflects the combined impact of targeted capacity-building and strengthened collaboration between newborn and maternity care teams. The Post Basic Certificate in Neonatal Nursing (PBCNN) programme aims to embed mentorship and practice across maternity units and this continuous mentorship, reinforced throughout the year, appears to have fostered greater confidence and readiness among staff to support high-risk births. Partners report skill improvement in neonatal resuscitation, breastfeeding support, and early identification of danger signs, encouraging proactive involvement of staff at SCBU during deliveries. Additionally, many SCBUs have institutionalised staff presence in theatres and labour wards within routine duty schedules.

Indicator 1.5. KMC has been implemented since the first quarter of 2025, supported by guidelines, protocols and training, with registration to monitor uptake. The number of units is growing, with the intervention starting in six units (shown in the March 2025 milestone) and a plan to spread to 17 units by March 2026. During the field visit, it was noted that KMC uptake was decreasing, driven largely by structural barriers to mothers remaining in hospital for the duration of the intervention including a lack of food provision in the hospital, however the overall output indicator at March 2025 shows a modest improvement in KMC uptake across the six districts. This underlying figure may mask discrepancies between facilities and should be disaggregated further. Additional barriers may be more stubborn to change, including a reported cultural opposition to KMC among doctors that would take time to influence. During the field visit, staff noted they had ongoing support with KMC via the Concern mentorship programme. UNICEF is also providing ongoing mentorship and coaching frequently at all 17 hospitals with SCBUs, with full involvement of MoH teams.
[note] Discussions with the review team noted that traditional clinical norms in Sierra Leone include caring for neonates in incubators, reducing opportunities for KMC

UNICEF report a planning assumption that one to two years further embedding the KMC intervention would lead to expanded coverage. To support this, UNICEF have enhanced the post-basic nursing course, adding three days comprehensive KMC training to support disseminating this approach. Given this intervention will be prioritised for the next 12 months of the programme, a better understanding is required of the barriers to uptake coupled with a detailed plan for addressing these barriers and a rigorous plan for building sustainability, given funding for this intervention up to two further years is uncertain.

Indicator 1.6. Sierra Leone has faced persistent shortages of blood bags and reagents over the past 12 months, which has limited availability of blood stocks and the effectiveness of blood drives, although blood drives have been able to restart through the second half of this reporting period. When blood is collected, wastage is high due to a lack of pre-donation testing, which is prohibited under national blood donation policy. Alternative measures for increasing the availability of blood for use peri-partum (including donations by pregnant women themselves, relatives, or blood drives among staff) are not consistently used. National coordination around blood banks is also lacking, with a key technical working group not meeting since 2024. Specific issues reported by DHMTs around procurement of refreshments for blood drives should be relatively easy to overcome but will need to be addressed to build sustainability into this output.
[note] Approximately 20-25% of blood is discarded

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no changes to this output during the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from 2024 AR	Progress in past 12 months
The national blood service in Sierra Leone continues to have stockouts of commodities. Its central management is weak and will jeopardise improved results in maternal health if severe haemorrhage during labour and severe malaria in children cannot be addressed with blood supply. The programme – both delivery partners and BHC staff – should work with other donors to support the GoSL to develop these systems, noting significant progress was made in SL2 but not sustained.	Although blood drives have been running in the target districts (with a current supply of reagents and blood bags) and blood banks have achieved a minimum quantity of blood available as of June 2025, the national blood system remains weak with a lack of national oversight and no evidence of stronger systems around national blood availability identified in this review.
The ability of MoH to manage data and report on outcome indicators for SCBUs and KMC Units requires further training, quality assurance and monitoring. Data on outcomes for small and vulnerable babies is needed to determine the quality of care for these babies, particularly the proportion of eligible babies who are benefiting from KMC. Planned visits to facilities with senior MoH staff will alert to constraints in delivering effective care, particularly as the management of babies moves from UNICEF to MoH staff to deliver.	The quality of data available on SCBUs, and the ability of MoH to manage and monitor these data, has improved since SCBU data has been integrated into DHIS2. The quality of data on coverage of KMC remains uncertain.
Attendance at deliveries by staff skilled in recognising and supporting high-risk deliveries will require further discussion with MoH and staff in the SCBU and maternity units. Advocacy by BHC and UNICEF for improved care is ongoing and essential.	Advocacy on attendance at high risk deliveries and improved care has continued through this reporting period.
Given concerning food and nutrition poverty and security indicators, BHC should commission a review of nutrition markers for the programme, to identify evidence-based interventions for SL3, and for wider programming. This is planned through TA support made available by the central FCDO EPD programme.	The recommended review of nutrition markers was not completed in the past year. Given the direct work on nutrition will be ending during the next reporting period, it is not recommended to conduct the review of nutrition markers at this point.

Recommendations for the year ahead for this output are:
1. BHC and partners to review the theory of change and logframe to capture the transition of the programme through 2026, including identifying priority interventions to continue and those to responsibly exit. Both interventions being continued and those being exited through FY 26/27 require agreed sustainability plans. This would be supported by a thorough political economy analysis in the focus districts to identify opportunities to embed these activities over time. Programme decisions should be communicated to partners at the earliest opportunity to support responsible exit.
2. Priority interventions to be continued should be discussed with MoH to ensure alignment.
3. BHC and partners should develop a specific plan for scaling up and further embedding the KMC intervention over the next 12 months including understanding structural barriers to uptake and designing specific approaches to address these, alongside a clear plan for building sustainability.
4. Partners should continue to build on the CRADLE device intervention, noting MoH concerns about a lack of focus on stronger referral pathways, using the CRADLE devices and training as an entry point to wider system strengthening on recognising high risk women and structuring referral mechanisms.
5. BHC to consider revising milestones for the CRADLE device component to reflect greater ambition in coverage and use of this intervention.
6. BHC and partners to engage proactively with MoH and donors to reinstate national leadership on the blood bank system, including working with MoH and districts to develop a resilient plan for ongoing support to blood drives.

Output Title	Increased access to quality of care with improved supply of medicines and diagnostic/treatment equipment.
Output number:		2	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	Increased from 10% after removal of Output 6

Indicator(s)	Milestone for this review - Mar 25	Progress - Mar 25
2.1 Proportion of FHCI commodity items delivered in-country within a four-months of raising purchase orders	75%	76%
2.2 Months with stockouts of 5 tracer SCBU commodities. / 1.ampicillin iv / 2.phenobarbitone iv / 3. 50% glucose iv / 4. gentamicin iv / 5. 24G iv cannulas	<30%	26% / 75% / 20% / 5% / 5%
2.3.1 Monthly FHCI supply chain/ operations meetings held with NMSA to review procurement status, pipeline, and first mile distribution plans with minutes available. / 2.3.2 Wider availability of mSupply (view only) to MOHS and stakeholders to give visibility to national and District level stock. / 2.3.3 Quarterly supply chain monitoring visits conducted in district medical stores with reports on storage, inventory status and management available.	1. Greater that 6 FHCI Operations/Supply Chain meetings held (Over 8 months) 2. mSupply view available to DMOs / 3. All 14 DMS visited and assessment made and reported	1. 7 meetings held / 2. Available / 3. All 14 districts visited
2.4 Number of facilities receiving last mile distribution of RMNCAH commodities based on monthly stock level reporting within three weeks of 1st mile distribution. In 6 districts (n=541) PHUs	520	528
2.5 Availability of functional SCBU equipment per year. Measured as % of each equipment item against SCBU recommended per unit (by MOH) on size of unit. / 1. IV pump / 2. Radiant warmer / 3. Pulse oximeter / 4. Oxygen concentrators (or filled cylinders)	>50%	72% / 75% / 67% / 67% / (June 2025)
2.6 Develop functional maintenance systems/programs with hospital maintenance staff and SCBU staff at 16 hospital SCBUs as measured by quarterly Preventative and Corrective Maintenance (PCM) reports	Baseline (5) plus 5 Hospitals conducting maintenance with at least one valid report each quarter submitted	12 Hospitals
2.7 Availability of functional CRADLE devices at CHC and hospital level in 6 SLP3 Districts.	75%	100%
2.8 Competent, salaried staff in 16 SCBUs / 1. Reduction in unsalaried staff supported with a UNICEF Stipend with BHC support. / 2. Numbers of students completing and passing the post-basic certificate in neonatal nursing training, and working subsequently in SCBUs	Baseline minus 50% (66) / 20	80 / 25

Briefly describe the output’s activities and provide supporting narrative for the score
Indicator 2.1 and 2.2. In tranches one and two of the FHC procurement, only 20% of items were delivered within three months although the overall indicator was met as of March 2025. Partners noted delays in confirming and receiving payments as a critical factor underlying delays, with tranche 2 procurement added on to an incomplete tranche 1 procurement hampering efficient delivery through this system. Tranche 3 was funded through underspend on tranches 1 and 2, allowing a much quicker procurement process, and although there were ongoing delays experienced for tranche 3, the challenges were significantly reduced as the system appears to be more bedded in. Only four of five tracer medications achieved the milestone of stockouts for less than 30% of months, missing this milestone.

Broader issues also persist in procurement and distribution of medications. MoH quantification of the FHC initiative notes up to a £28m funding gap for supplies over the next two years, and it is unclear how this gap will be met. Fragmentation in national distribution of commodities, with different distributions for FHC, SRHR commodities via UNFPA and malaria, TB and HIV commodities via the Global Fund, was noted as a challenge – NMSA reflected to the review team that planning just one national distribution was like “strategizing for military warfare” with the number of actors involved across partners and donors. The quantification itself represents a positive step toward MoH ownership of procurement, allowing procurement to be better based on what is actually needed at district level. Procurement will be supported under SL3 through 2026 then scaled back. Given the importance of the FHC initiative to providing basic healthcare nationally in Sierra Leone, urgent work is needed to work with partners and MoH to establish a sustainability plan.

Indicator 2.3. The three sub indicators that measure progress toward a stronger system for procurement and supply were met, suggesting progress being made in national leadership of FHC supply. Regular logistics meetings were useful for disseminating supply chain activities and providing a transparent platform to own improvements. Actions arising from the third-party monitoring reporting have also been adopted, and the review team attended the launch meeting for the TPM report in October 2025, noting across the three TPM reports during implementation of the programme there have been system level improvements.

Indicator 2.4. Last mile distribution of FHC commodities has delivered as expected, evidenced by post distribution surveys. Additionally, a substantial sustainability gain was made in the transition from a private contract to Government ownership, reducing the costs of last mile distribution from £100k to £14k, building NMSA and District ownership, stronger coordination at national level and successful policy influencing. NMSA is exploring scaling this approach to the other 10 districts, but in discussions with the review team noted that vehicle maintenance costs need to be accounted for. Partners noted the need for advance notice to support this new approach to last mile distribution given the coordination involved.

Despite this, stockouts persist in some cases. Data quality is a persistent issue, despite wider use of mSupply, and mechanisms do not exist for redistribution of excess supply or advance warning of potential stockouts. mSupply is being used at district level, although NMSA plan to roll this out to over 1,000 Peripheral health units (PHUs) in 15 districts. Embedding these systems will require ongoing technical leadership from NMSA as well as resources to supply the hardware required. The SL3 funded capacity building work with NMSA on commodities is well received, but at a scale that is likely to have only limited impact in the context of significant staffing shortages at NMSA. NMSA noted to the review team the potential role BHC could play in advocating with MoH for increased resources for NMSA and for the procurement and supply system.

Indicators 2.5, 2.6 and 2.8. Support for SCBUs, during SL3 and through the previous Saving Lives phases since 2027, continues to be a key success for the programme, and the past 12 months has been used to continue to build sustainability into this approach. Since January 2025, SCBU data has been integrated with DHIS2, allowing better remote visibility and use of data with more useful disaggregation. UNICEF has now supported MoH on two data quality audits, noting data quality has significantly improved over this time, allowing trends in outcomes to be identified and acted on. This data is also used to inform MPDSR reviews. A system wide equipment management system is also now in place, which is a strong indicator of progress on what has been a persistent issue. However, availability of spare parts continues to limit any equipment maintenance strategy, with no functioning supply chain nationally. Risks were identified during the field visit to the SCBU, where oxygen concentrators originally procured under SL1 were now reaching the end of their usable life after seven years, suggesting a cliff edge may be coming in availability of functioning equipment. Over the life of the programme, the number of volunteer nurses in SCBUs has reduced from over 200 to 80 this year: the milestone for this has been missed, and although the third cohort of the post-basic nursing course will be completed this year there will continue to be gaps. However, achievement of this milestone has been a challenge due to circumstances outside the control of the programme, including competition for government salaries. In addition, SL3 support for international consultants working with SCBUs will end in March 2026 with no current plan for MoH to continue this.

Indicator 2.7. Availability of CRADLE devices has exceeded the milestone. Narrative on CRADLE as an intervention is covered in detail under Output 1. Although two milestones were narrowly missed, the review team judged the overall output met expectations for the resulting in a score of A.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no changes to this output during the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from 2024 AR	Progress in past 12 months
There is a limited HR capacity within the National Medical Supplies Agency (NMSA) to meet its mandate, with district stores not following SOPs and inadequate processes in place to monitor. There is a need to focus on building transparent and accountable processes, with timely systems for quarterly allocation and distribution. There are opportunities for BHC and other donor programmes to support this with TA, noting that Global Fund, UNICEF and UNFPA also use the same supply chain resources to distribute, so co-loading and shared distributions could create cost efficiency. This should be explored further.	NMSA has been supported with technical assistance delivered by a national consultant. This has been well received with evidence it is leading to systems being strengthened, including the links between national and district levels.
Prior to further procurement (due in December) an MOU with MoH should be agreed and signed. This would set expectations for the accountability mechanisms by NMSA and MoH, as well as defining the role of UNICEF in supporting this.	The procurement MoU between UNICEF and MoH was agreed and signed during this reporting period.
Whilst UNICEF sees its role in providing technical assistance, it should also support assurance of the data on stockouts and advise on mitigation measures to ensure planned distributions are made on time. Technical support on prioritising quantification and procurement of the most lifesaving commodities, with enough provided to contribute to a ‘buffer stock’ in district medical stores is an essential part of protecting against stockouts. Good advance distribution planning is needed to improve the availability of drugs through regular meetings on FHC operations and logistics.	Regular meetings on FHC operations and logistics are underway, and the situation regarding stockouts and buffer stocks has improved through SL3 support.
There is a limited pool of experience (and capacity in NMSA) in drugs procurement and distribution in Sierra Leone. BHC should work with other donors to continue institutional capacity building within the National Medical Supplies Agency (NMSA) with the focus on partnering around transparent, accountable and timely systems. Alternate supply routes should also be explored.	Institutional capacity building with NMSA is ongoing under SL3, and should continue as a priority going forwards.
BHC should plan its support to the health commodities supply chain with a holistic view, advocating for a single national plan, and bringing other donors on board to support a more efficient, cost effective supply chain. This should keep in mind the overall cost of the full supply chain and encourage working with other donors to burden share.	Although work on a more efficient, cost effective supply chain is ongoing, progress on this has been limited. This work should remain a focus for BHC going forwards with NMSA.
The removal of volunteers from the health workforce is an important issue that continues to require strong advocacy at the level of the CMO and Minister, with the risk that capacity developed will be lost. For SCBUs, volunteers were planned to have transitioned to MoH salary by March 2025, yet few have been appointed so far.	Although progress has been made on removal of volunteers from the workforce, this has stalled, with insufficient new graduates coming through the SL3 funded training courses to fill vacancies.
The BHC support to the post-basic neonatal course is planned to finish in 2025. This is an important route to providing the quality of nursing care needed to maintain newborn survival. BHC has invested in the development of the course curriculum (in SL2) and means should be explored with MoH to ensure it continues.	There is currently no plan in place for MoH to take on funding for the post-basic neonatal course, therefore this remains at risk going forwards.
BHC should make a clear distinction between technical assistance (TA) that provides gap-filling and that which builds capacity, continuing to prioritise the latter and ensuring there are staff available within the District, working at an appropriate level, whose capacity can be built within the lifespan of the programme and continue the work moving forward. This relates to all areas where support provided but particularly to SCBU support, NMSA, and mentoring.	Although technical assistance under SL3 has been designed to build long term sustainability, this takes time and structural barriers such as availability of staff, culture and domestic funding will require sustained investment.
Maintenance and repair of medical equipment remains a major challenge for the health sector. The SL3 programme should work with the MoH to develop a pragmatic preventative maintenance strategy for maintaining equipment building on the work done in SL2 and the monthly reporting of equipment functionality in facilities.	A preventive maintenance strategy for equipment is now in place under SL3
Visits to SCBUs and medical stores have identified that issues are not being reported through expected reporting processes, which should be reinforced. Joint visits to facilities, coordinated by MoH with UNICEF, Concern and BHC should be prioritised.	Joint visits to SCBUs to reinforce monitoring requirements have been conducted during this reporting period.

 Recommendations for the year ahead for this output are:

1. Under SL3, the UK should work to convene donors to align distribution mechanisms under stronger NMSA leadership, including coordinating additional donor support for technical assistance within NMSA.
2. BHC should use all levers, including as a leading global multilateral donor, to leverage multilateral investment in medication procurement in Sierra Leone, as this transitions to GoSL ownership over time.
3. The programme should consider continued, targeted, priority technical assistance support to NMSA on strengthening procurement and distribution nationally and in districts, including drawing down on central expertise offers for this.
4. Partners should work to capture and further scale sustainable approaches to district owned last mile distribution, streamlining this (including vehicle costs) with other district activities to build sustainability.
5. BHC to consider a national review of data systems and quality to identify critical data gaps that can be addressed through targeted technical assistance, drawing on central expertise as required.
6. BHC should work with partners and MoH to develop a sustainability plan for SCBUs after the end of SL3 funding, including a plan for equipment maintenance and functionality without funded international consultants and volunteer nurses. This should include discussions with MoH on wider issues facing staff salaries and opportunities for UK support, sensitive to current fiscal challenges.
7. BHC should develop a clear vision for a cohesive package of UK support to Sierra Leone’s health system, across bilateral and multilateral investments, CMPs, OGD investments and non-investment support and influencing, engaging across BHC. UK should use all levers to support development and delivery of health sector plans, including strengthening progress towards greater domestic health financing.

Output Title	Improved community engagement and knowledge to seek health (RMNCAH and nutrition) services
Output number:		3	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review - Mar 25	Progress - Mar 25
3.1 Number of community amplifiers trained to deliver key health messages / In 6 SLP3 districts - cumulative	110	654
3.2 Awareness of Services - Percentage of respondents who are aware of a minimum of 3 available RMNCAH-N services. In 6 SLP3 districts	50%	96%
3.3 Percentage of supported health facilities with functional client feedback response mechanisms, including safeguarding. In 6 SLP3 districts.	60%	Not available
3.4 Knowledge of maternal pregnancy danger signs - Percentage of pregnant women who know at least 2 danger sign s during pregnancy. In 6 SLP3 districts.	60%	92%
3.5 Number of RMNCAH-N outreach sessions conducted in the project catchment areas / In 6 SLP3 districts.	No milestone set	16

Briefly describe the output’s activities and provide supporting narrative for the score
Indicators 3.1, 3.2, 3.4 and 3.5. Very strong performance was reported against the March 2025 milestone for community amplifiers, outreach, knowledge and awareness in the six targeted districts. Given the wide reach of this activity, it is now essential the programme plans to leverage this network and the greater awareness it has delivered, to deliver priority messages and health improvement going forwards relating to the ongoing activities funded under SL3 (such as KMC).

RMNCAH-N outreach sessions, led by community health centre action plans, have been conducted in each target district (at least two per month) during the reporting year. Community Health Centres (CHCs) use these outreach sessions to identify gaps in knowledge among community members and plan outreach to address these gaps. This process is supported by community dialogue meetings that feed in to facility management committees. The implementing partner is working with MoH to strengthen these committees, noting they have achieved successes in improving community healthcare infrastructure and mobilising resources under SL3. Monthly radio programmes are being delivered, although during the field visit the review team were not confident of the DHMTs’ links with radio stations (providing radio messaging through only one of five radio stations in the district) and the broader impact of radio engagement is uncertain. During the field visit for this review, the DHMT cited a 20% reduction in malaria cases and the ending of the mpox outbreak in the district as a result of “robust community engagement”.

Over 500 health workers have been trained under SL3 to provide family planning services, and a demand generation approach through community sensitisation has been implemented across the six districts. Family planning is a key component of RMNCAH-N, with the DHMT noting “family planning is the strategy we are using to reduce maternal deaths”. Evidence given to the review team suggests demand for family planning services in the focus districts is very strong. Implementing partners noted that Community outreach was disability inclusive (although the review team did not observe any outreach). There are challenges: at the primary healthcare unit visited by the Annual Review team, staff noted demand was high in response to outreach, with levonorgestrel implants the most popular choice of contraceptive method, but on the day of the visit there was no stock of these available. There have been persistent issues with confidentiality during counselling, and quality of counselling itself, leading to later refusal of contraception, although the implementing partners are working to address this. These barriers are exacerbated for women with disabilities and the programme outreach on FP includes the targeting of people with disabilities. Current practice prevents under 18s from accessing family planning without a parent/caregiver being present, leading to refusal to provide services at primary healthcare units despite national work through SL3 on an MoU with GoSL on consent in this age group.

Indicator 3.3. Client feedback and response mechanisms are functioning however data were not available for the proportion of health facilities with functioning mechanisms, therefore it was not possible to report against the KPI. In-depth work is ongoing however to make progress against the milestone including community sensitisation around ways to report complaints such as the live national hotline. For example, draft protocols to support CFRM have been developed and work to build leadership at MoH and community sensitisation is underway.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no changes to this output during the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
No recommendations (only one learning point) were made for this output in last year’s Annual Review.
Recommendations for the year ahead for this output are:
1. BHC and partners should plan to leverage the strong network of community engagement and outreach developed under SL3 going forward to amplify health messages for the priority interventions that are continuing under SL3 next year, including in support of KMC, MPDSR and CRADLE.
2. From the evidence in this review, policies on consent may be a barrier to access to family planning for some groups. BHC should consider drawing down on central expertise to support advocacy with GoSL on sexual and reproductive health and rights, including advocacy on changes to policy and protecting against rollback.
3. BHC to review the indicators for measuring progress on the CFRM component and work with partners on a plan for building national ownership of CFRM going forwards.

Output Title	Improved HRH capacity to deliver comprehensive quality and inclusive RMNCAH-N services
Output number:		4	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	Increased from 10% after removal of Output 6

Indicator(s)	Milestone(s) for this review (Mar 25)	Progress
4.1 Percentage of reported maternal deaths investigated within 48 hours and subsequently reviewed in an MDSR committee meeting not later than 30 days of incident occurrence. In 6 SL3 districts	80%	17%
4.2 Average Score on Gender Role Attitudes (GRA) scale among HCWs trained in Gender transformative approaches. In 6 SL3 districts	50%	60%
4.3 Percentage increase in healthcare workers' knowledge and understanding of disability and inclusion principles in line healthcare service provision. In 6 SL3 districts	20%	67%
4.4 Number of health workers that have knowledge of the Sexual and Reproductive Gender Based Violence Referral and Response Pathway. In 6 SL3 districts	60%	0%
4.5 Number of health workers receiving mentorship/coaching on different components of RMNCAH-N in the 6 target districts. (102 CHCs) Total active at time point	110	Not available
4.6 Proportion of CRADLE trained HCWs who passed all the 17 steps of the competency checklist at CHC and hospital level. In 6 SL3 districts	25%	38%

Briefly describe the output’s activities and provide supporting narrative for the score
Indicator 4.1. MDSR, expanded to MPDSR during the last 12 months of the programme, is being implemented in the six focus districts through weekly meetings. The Annual Review observes, however, that investigations are not always happening within 48 hours and a substantial gap between performance and expectations leading to a missed milestone as at June 2025. This is in part due to deaths occurring in hard to reach areas, but also reflects delayed inception of this programme activity. In addition, some review reports were noted to be of poor quality, but this was overall improving. Although at early stages of implementation and underperforming against the key coverage indicator, MoH buy-in to and recognition of the importance of the MPDSR system has been achieved, and learning from these reviews is being filtered down through other SL3 mechanisms, including the district In-Charges meetings and through training and cascade mentoring down to PHUs. A major finding from MPDSRs across districts is delays in referrals, suggesting a common area for greater sensitisation.

This intervention is relatively new, and culture change will take time to deliver, however evidence from the Annual Review suggests fertile ground for culture change over time. An important observation was made by the District Medical Officer during the field visit: the DHMT uses community feedback mechanisms to link the MPDSR process back to the community “[when getting feedback] the community are pleased, because otherwise they don’t know what is happening to their pregnant women”. This suggests further opportunities for sensitisation.

The success to date of this system has led to development of a template which can now be scaled to the other 10 districts, strengthened by SL3 support to the national MPDSR focal point. Availability of skilled staff to investigate and act on MPDSR reports, lack of internet connectivity and some gaps in links between District and national level were reported as ongoing challenges. MoH commitment to sustain this system is currently strong.

Indicator 4.2 and 4.3. Gender transformative approaches and disability inclusion are key programme approaches under SL3, and the programme is flagged as significant on gender and disability markers. Progress on gender role attitudes has achieved the March 2025 milestone. Disability inclusion is being delivered at multiple levels: health centre action plans to increase health worker knowledge (the work with healthcare workers has greatly exceeded the milestone for this period), community level outreach to influence positive health seeking behaviours for people with disabilities, and working to strengthen the capacity of six Organisations for Persons with Disability (OPDs) to implement provisions of the 2011 Disability Act, to advocate for, and drive forward adoption of disability inclusive infrastructure, which to date has not been widespread. In this context, the programme would benefit from considering approaches to drive improvements in disability inclusive infrastructure and consider how the improved knowledge and understanding of disability inclusive principles among healthcare workers can now be leveraged for sustained improvements in disability inclusion. Whilst disability inclusion has been a common and significant thread through the district and community level work under SL3 over the past 12 months, scaling back of activities in the next year is likely to limit disability inclusion work, and the marker should therefore be reviewed.

Indicator 4.4. As at March 2025, no progress has been made on health worker knowledge of the Sexual and Reproductive Gender Based Violence Referral and Response Pathway. The programme should consider the extent to which progress under this indicator will be achievable during the next 12 months of the programme given the focus on transition and scaling back activities.

Indicator 4.5. The progress indicator for indicator 4.5 was not available at the time of the Annual Review. The SL3-supported clinical training and cascade mentorship approach appears to be highly valued by staff. The review team identified during the field visit that the SLEWS tool was well embedded at the district hospital, had buy in from staff, and was leading to a culture change around data-driven decision making, multidisciplinary working and effective escalation and referral. Given the shortage of doctors, however, and lack of effective referral mechanisms from the community to the hospital (including a lack of transport) there is a critical question regarding the long-term impact of this change in clinical documentation. The degree to which the mentors have been able to build skills among hospital and primary healthcare staff to sustain and embed training is also uncertain. In particular, staff appear to be leaning heavily on training from the clinical mentors for support on many aspects of care, including training in SCBUs. During discussions for this review, it was noted that “the mentor is very active [but faces] challenges with attitudes”, largely the willingness of staff to engage with clinical mentorship and continuous quality improvement. At the SCBU visited by the Annual Review team, UNICEF training had not been provided this calendar year. Further issues highlighted during the Annual Review field visit included a lack of dedicated time for training, and lack of adequate facilities for training in the hospital setting. Sustainability of the SLEWS approach will require embedding the tool in national training curricula, which is currently being planned and developed by consortium partners.

Indicator 4.6. Progress on staff competence with CRADLE was strong. Narrative regarding the CRADLE intervention is covered in more detail under Output 1.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Other than a move from MDSR to MPDSR, there were no changes to this output during the past year.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from 2024 AR	Progress in past 12 months
The SL3 programme should explore how to ensure that monthly MDSR review meetings are held, possibly setting a fixed day in which the MDSR is run, and competing activities precluded. This has been discussed with MoH.	MDSR (now MPDSR) meetings have now been well established with a consistent meeting slot. The milestone was missed due to deaths not being investigated within 48 hours in some districts, although most deaths are subsequently reviewed within 30 days.
Child death audits (number of meetings in hospital held monthly) should be considered in the next log frame revision, and support provided at District level to effectively implement.	Child death audits have been considered, although these will be challenging to implement given the larger number of cases and therefore additional resources required to action this recommendation. The focus to date has been on establishing MPDSR, whilst the child death audits remain under review.
The logframe indicator for MDSR will be widened to MPDSR to reflect the inclusion of perinatal deaths in the planned revision by MoH. A tool developed by Concern to score the quality of MDSRs should be implemented, and good practice shared nationally.	MDSR has been expanded to MPDSR, and learning from the approach is being shared nationally.

Recommendations for the year ahead for this output are:
1. BHC and partners should leverage the current MoH focus on MPDSR to embed and sustain this system through the programme’s transition. A review articulating the impact and effectiveness of this system would support advocacy with MoH to continue support MDSR and PDSR after programme completion.
2. BHC and partners should review the current status of disability inclusive infrastructure and identify targeted improvements that are needed to improve access.
3. BHC should review the ongoing value of work on the Sexual and Reproductive Gender Based Violence Referral and Response Pathway in the context of reducing programme activity over the next 12 months, and consider how to build Ministry leadership on embedding understanding of the National Referral Protocol.
4. BHC should review the use of disability (and gender) markers in the programme under the scale back of activities in the next 12 months.
5. BHC and partners should agree a plan for sustainability around training and mentorship after the end of SL3 funding for this activity.

Output Title	DHMT and hospital staff have increased capacity to take a greater leadership role in national health systems including emergencies and provide feedback on progress and implementation of strategies for effective delivery of quality and inclusive RMNCAH and nutrition services
Output number:		5	Output Score:	A+
Impact weighting (%):		25%	Weighting revised since last AR?	Increased from 20% after removal of Output 6

Indicator(s)	Milestone(s) for this review (Mar 25)	Progress
5.1 Proportion of suspected outbreak reports from health facilities to the DHMTs investigated by surveillance lead within 48 hours. In six SL3 districts	80%	100%
5.2 Proportion of Health Facilities who meet WHO's minimum standard for timeliness and accuracy of surveillance data. In six SL3 districts	85%	90%
5.3 Number of district management members who complete the leadership and management training pilot. In six SL3 districts	No milestone	None
5.4 Number of DHMTs with a list of health facilities prioritised for support based on district data. In six SL3 districts	6	6
5.5 Proportion of PHU in-charges meetings where analysed data is discussed. In six SL3 districts	50%	92%
5.6 Number of districts organizing joint planning and budgeting based on their local data, national strategies and performance monitoring. In six SL3 districts.	4	6
5.7 Number of DHMT members receiving technical assistance in planning, delivering and evaluating the quality and RMNCAH-N services. / Data to be disaggregated by DHMT position, district, consortium member and the technical assistance. / In six SL3 districts	20	115
5.8 Number of district management team members who participate on disability inclusive M&E training. In six SL3 districts	36	52

Briefly describe the output’s activities and provide supporting narrative for the score
Indicator 5.1 and 5.2. All suspected outbreak reports from health facilities to the DHMTs were reported as investigated by the surveillance lead within 48 hours, and 90% of health facilities met WHO minimum standards for timeliness and accuracy of surveillance data, achieving against these milestones. However, data on the number and nature of the reports were not available for this review making these difficult to interpret. In the previous annual review it was recommended to revise output indicator 5.1, in the context of low or no numbers of reports available to quantify the effectiveness of this system. Responsibility for surveillance sits with districts and will therefore potentially be improved through strengthening district management and operation, and surveillance teams are involved in investigation and response to maternal and child deaths. However, the output indicator as currently structured does not capture well the role of surveillance in RMNCAH-N, and it is not clear which programme activities are directly contributing to this part of the system or which outcomes will be addressed: the underlying logic for this part of this output is unclear. The programme should consider whether to expand programme activity into health system strengthening for health security more concretely, and if so, establish a set of output indicators that would better capture the programme’s role in strengthening the detection, investigation and response to disease outbreaks, and the outcomes this would expect to deliver. Going further, the programme should consider diagnostic work to understand the key climate and health security vulnerabilities affecting districts and planning future primary healthcare strengthening activities under SL3 around addressing these vulnerabilities. BHC can draw down on the central expertise offer to support this.

Indicators 5.3, 5.4, 5.5, 5.6, 5.7 and 5.8. Across a broad range of different types of support being offered by SL3 to DHMTs to strengthen their capacity for leadership, monitoring, quality improvement of services, planning, budgeting and using data, all five indicators with milestones were exceeded, representing a strong first year of implementation for the programme. Health leadership training has been designed for healthcare leaders at DHMTs, Hospitals and Councils under the health executive programme, however this has not yet been implemented. During the field visit to the DHMT, the District Medical Officer noted the SL3 support was “very very key…giving maximum satisfaction to do your job”. The DHMT reported higher confidence in particular in approaching the Council and MoH with issues.

SL3-supported Integrated Supportive Supervision (ISSV) in each of the six focus districts has been highlighted by DHMTs as a success, providing opportunities for DHMTs to take leadership of their own oversight of primary healthcare units with some degree of buy in. However, implementing partners noted considerable work was needed to fully embed and sustain this model, which is donor led and lacks national policy leadership. Support to ISSV is also resource intensive, with efficiencies found by linking ISSV visits with last mile distribution activities. The overall impact of this system and likelihood of it being sustained is uncertain.

Monthly In-Charges meetings are being supported under SL3 and are well attended by staff from across PHUs. The meetings are found to be a useful forum for data review and cascading training, including responding to the MPDSR reviews. Feedback included that the meetings are too short to cover data in full, and an additional quarterly data review meeting at the CHC/PHU level would be valuable.

The Annual Review field visit identified challenges in the relationship between the DHMT and implementing partners, with the DHMT reporting that without being provided a budget ceiling for their operational fund, they were unable to take ownership of it and use it for their planning. Delays in receiving payments also act as barriers to the leadership on planning and budgeting. Concern reflected to the review team that work was underway with DHMTs to make plans for sustainability of these interventions in anticipation of cuts to programme funding, and although districts are working currently to build in these measures this work has not yet concluded.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
There were no changes to this output during the last 12 months.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from 2024 AR	Progress in past 12 months
Reporting and timeliness of outbreaks on the log frame should be modified to reflect the infrequency of reportable events and the availability of disaggregated data on surveillance through the Integrated disease surveillance reporting (IDSR) processes. Output 5.1 could be removed from the logframe, and the timeliness (but not accuracy) captured per district.	Output 5.1 has remained in the Logframe, with reporting on timeliness of surveillance reports including in this review period.
The district planning and budgeting process is complex and often delayed. The SL3 district programme should work with the District Council and the DHMTs to facilitate information flow on budgeting and annual work plans. Furthermore, BHC should continue to advocate for the release of MoH funds in a timely manner for defined district activities, and for operational funds to NMSA. SL3 district NGO partners should support the MoH to start the process in May each year (FY Jan -Dec) to allow sufficient time for planning and approval of the plans.	Information flow on budgeting and plans has not substantially improved during this reporting period, which is captured in the narrative above.
The log frame indicator for PHU In-charge meetings should be modified to reflect the frequency of meetings, with >75% of planned meetings occurring across the year.	The log frame indicator for PHU in-charge meetings was not modified following last year’s review. As this activity is ending it is not recommended to modify this.
Recognising that the fiscal space for government is low, BHC should continue to influence the GoSL to increase investments in health. This should be done working closely on public financial management with other BHC teams, DHMTs, local councils and programmes to better understand the constraints in execution and to advocate for better budgeting processes on health.	Work continues to support GoSL to increase spending on health, however the funding context remains very challenging. A further recommendation on this has been captured in this review.

Recommendations for the year ahead for this output are:
1. BHC to consider diagnostic work to understand the key climate and health security vulnerabilities affecting districts and plan future primary healthcare strengthening activities under SL3 addressing these vulnerabilities. BHC can draw down on the central expertise offer to support this.
2. BHC and partners to advocate with MoH to support ISSV and streamline this with other district level activities going forwards.
3. BHC to work with partners to agree a plan for sustainability of the district management support activities going forwards, including a VfM review that makes recommendations on improving efficiency and effectiveness.
## D: VALUE FOR MONEY (1 page)

Key cost drivers and performance
The key cost drivers this year remain the supply and distribution of medicines and the cost of staff for implementing partners. In the SCBUs, there has been a reduction in funding for international paediatricians and there remains one international consultant working on training and capacity building in Kangaroo Care [which we consider fair VfM as this is an upfront investment in the rollout of a low cost, high impact methodology]. Despite reduced funding, Concern (through reduction in last mile distribution costs) and UNICEF and MoH staff have worked hard to improve cost effectiveness and improve neo-natal survival in the SCBUs. Survival rates reached 89% for the first time during the reporting period and has since reached 90% - a significant achievement.

We continue to seek the best VfM possible in the procurement and supply of medicines and commodities. However, reduced funding available for procurement is naturally affecting the efficiency of the activity, offset partially this year by an unfilled international supply chain post. There is still work to do in reducing international staff costs and this will happen as we transition to a leaner, highly focused programme in the final year of the programme. Increasing the capacity of NMSA, DPS, MoH and district healthcare staff to manage the supply chain and healthcare delivery in districts will also remain a focus.

VfM performance compared to the original VfM proposition in the business case
Outcome targets for three out of five indicators have been surpassed with one target missed and one very narrowly missed. This is an indication that delivery of outputs are effective in contributing to outcome delivery. Concern’s approach to VFM continues to focus on metrics to measure effectiveness per outcome achieved and the economy of overheads used to train and mentor healthcare workers. More work is needed to understand why an outcome on increased antenatal visits missed its target despite output targets related to community messaging, outreach and health seeking behaviour being exceeded.

The year under review was the first full year of implementation and there has been good progress on indicators which highlight the economy and efficiency of programme activities which have been delivered within cost and in some areas for less cost than expected. For example, UNICEF oversight of SCBU management ensured that output delivery contributed to an increased outcome survival rate, despite the costs to deliver being less than in the first year of the programme.

A VfM strategy which measures programme metrics was planned for Year Two of the programme. The BHC team has not yet completed this strategy but Concern has provided their approach and metrics against which they measure the VfM of the interventions. As the programme reduced in the next year, the BHC team will discuss how best to monitor the VFM, including the impact of reduced activities on the original assumptions in the business case. This will include a revision to the Logframe.

The programme is in part equitable by design in that it is focused primarily on Maternal and Child Health. There is a challenge on equity nationally when comparing district support with other districts not supported by the programme. This part of the design was done at the request of MoH but on the assumption that other donors would cover fully the other 10 districts. Training and messaging to challenge cultural norms and increase access to family planning, maternal and child health services to vulnerable women, children and people with disability is ongoing. Concern is also working with MoH to increase patient/client understanding of their rights to safe and dignified care.

Assessment of whether the programme continues to represent value for money
Although the VFM strategy/metric was not completed by the BHC team within the reporting period, the programme is continuing to provide life-saving health services to women and children and it is possible to track where the VfM measures against business case expectations. The programme supports efforts to ensure that women, children and newborn’s health needs are prioritised to contributing to a focus on maternal, under-five and neonatal mortality. The UK’s longstanding investment in the health system in Sierra Leone coincides with significant reductions in maternal and child mortality, it is fair to assume that reductions in the programme may lead to an increase in mortality statistics if GoSL does not prioritise domestic funding to health. For this reason, we conclude that the programme continues to represent VfM.

From April 2026, the programme will reduce in scope in response to a reduction in ODA/GNI. Though discussions are ongoing with MoH, the programme is likely to focus fewer IP resources on three activities – KMC, Cradle warning and MPDSR. We will move from supporting these areas of work in six districts to supporting MoH in leading across the country. We have considered VfM in focusing on these interventions. They are relatively low cost to deliver and will maintain a focus on high impact reductions in maternal and neonatal deaths. They will require less IP resources to deliver them and the consortium size will reduce providing increased efficiency in contributing to outcomes.

Recommendations for the year ahead
The programme team should ensure that changes to the programme scope are implemented in line with FCDO’s Programme Operating Framework rules and guidance.

E: RISK

Overview of risk management
Risk appetites across the each of the seven risk categories all cautious or receptive. Financial and fiduciary risk appetite is receptive, reflecting both the lifesaving nature of the programme and that fraud and corruption are a reality of delivery in this resource-constrained context. Policy and Programme Delivery risk appetite is also receptive, allowing us to be adaptive to new ways of delivering to improve results. The year saw a renewed focus on maternal and child deaths, led by the MoH. There is a risk that reductions experienced in both impact indicators will reverse given tight fiscal constraints on MoH and donors. The programme is working to mitigate these risks through close collaboration with a surveillance network, monitoring and reviewing deaths and working on the ground to introduce improvements for labour wards, paediatric wards and SCBUs.

Financial and fiduciary risk is a key focus in managing our risks and we continue to work with partners, the MoH and NMSA to improve financial management systems on the ground. Concern has a robust financial system for approving expenditure within the districts and UNCIEF has established a third-party payment agent to manage funding for NMSA centrally. We have firmly established two third-party monitoring organisations to help us to understand where the strengths and weaknesses are in the supply chain for medicines.

Safeguarding of beneficiaries remains a concern in district delivery and for SCBUs. In this reporting period, we received just two suspected safeguarding concerns around missing children, reported by a partner which were later amended to issues between family members – both infants were unharmed. In the six districts supported by the programme, community messaging is strong in assuring communities of their right to experience respectful and safe healthcare services. After establishing an operational Feedback and Complaints Response Mechanism, Concern is working with MoH to embed the system and we expect the mechanism to be handed over and rolled out more widely across the health sector before the end of the programme. The BHC programme team discusses regularly safeguarding risks as part of wider risk management and specifically as progress on the FCRM and Community of Practice is discussed.

Concern has completed two safeguarding training sessions for all staff, and in response to an assessment of safeguarding systems appointed safeguarding focal points in each district to support ongoing safeguarding training, reporting and to support MoH on safeguarding at district level. Nationally, an independent safeguarding consultant has been appointed to identify and address safeguarding gaps at MoH and Ministry of Social Welfare, to support progress towards building a safeguarding platform. A safeguarding training of trainers approach, developed by Concern, is being prepared for handover to MoH. A challenge to this has been ensuring the safeguarding approach aligns to existing national laws and policies. Concern has worked with MoH and other partners to establish a safeguarding Community of Practice where challenges and successes can be discussed.

The Strategy and Context risk is increasing. Fiscal constraints in particular are a concern and despite clear signals indicating the declining availability of donor funding for health, the MoH is only now beginning to move on the need to increase domestic funding to health. MoH capacity at directorate level to lead the programme appears to be improving but UK access to decision makers within the MoH continues to be challenging despite proactive attempts to address at all levels. We are hoping for an increase in MoH-led convening and coordination of partners to discuss operational challenges as a result of funding constraints going forwards and this will be a focus for BHC staff in the next year.

One Policy and Programme risk which is materialising with time is fire risk at health facilities and stores. Last year, there was a fire within a district medical store in Western Area Rural and in a KMC unit in Ola During Children’s Hospital Western Area Urban. This year experienced a further fire in an SCBU in Makeni, Bombali. Though staff managed to evacuate the babies during the fire, three babies later died, in part due to the complications of the move to a temporary SCBU in another hospital. Poor infrastructure, electrical and firefighting capability means fire remains a risk. In this case, equipment was provided by UNICEF several years ago with partial funding from the programme. The team will estimate losses attributable to the programme and seek to write off any residual losses at the earliest opportunity. We will seek to support improvements to the new SCBU before the end of this financial year.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.
The Saving Lives in Sierra Leone Phase 3 programme is implemented by UNICEF through a Contribution Arrangement (CA) and the Concern Worldwide-led Consortium (with Helen Keller International, Humanity Inclusion, SEND SL, Kings Global Health and Welbodi Partnership) through an Accountable Grant.

During the review period, BHC held quarterly partners’ meetings with all implementing partners and two steering committee (SC) meetings with MoH colleagues, hosted by the Deputy Chief Medical Officer and the Director of Reproductive and Child Health at the Ministry of Health. Access to senior management within the Ministry continues to be a challenge and as a result, Steering Committees which should focus on strategic issues have tended to focus on general progress and in-depth discussions where issues arose in the run-up to the meeting.  Monthly and quarterly partners’ meetings were used to discuss operational challenges, convey corporate messages and discuss current and emerging risks affecting programme delivery. Partners noted that they value quarterly meetings with BHC, however the steering committee meetings lacked engagement from senior MoH leaving them less useful for taking forward action points.
Delivery against planned timeframe

NGO CONSORTIUM
Operationally, the NGO consortium is delivering against its objectives. The majority of outputs are progressing well and Concern partners within districts have continued to maintain excellent relationships with DHMT, hospital and CHC colleagues. A key development in this period was the assumption of responsibility for last mile distribution of medicines and the Concern team in Freetown have worked really well with NMSA to manage the transition, bringing better value for money with the new delivery method.  The Consortium Coordination Unit is working well with downstream partners and the MoH centrally and they have been heavily involved in the national drive to reduce maternal and child deaths.

UNICEF
The UNICEF team is responsible for the supply and distribution of medicines to district hubs and also supporting 16 SCBUs across the country. There has been good progress in working towards more sustainable SCBUs. A medical equipment functionality system is fully embedded and operational. Neonatal admissions and survival data is also working well and feeding into the MoH drive to reduce child deaths. Progress is being made in difficult circumstances towards transferring staff from programme stipends to government salaries even if slightly behind schedule.

For part of the reporting period, the UNICEF team were without a health procurement and supply chain specialist. The arrival of a new specialist embedded within NMSA saw improvements in the hands-on support to NMSA in managing the mSupply medicines management system and this in turn added to assurance and led to improvements in the data on which NMSA manages the quantification and distribution of medicines. None the less, challenges remain in the districts and further improvements in stock management processes in the districts will be a focus in the next reporting period. A third-party monitoring contract conducting a review of all facilities and stores in 10 districts contributed to improving understanding of stock management issues. Third party monitoring is also taking place in the other six districts contracted through Concern.

Quality and timeliness of narrative and financial reporting

NGO CONSORTIUM
Concern submitted four quarterly reports covering the period to June 2025 – all either submitted on time or to pre-agreed later deadlines. Reporting contains progress made in key areas of implementation, successes and challenges experienced during each quarter. A key challenge for Concern was managing the forecasting of expenditure by downstream partners and both monthly and quarterly forecasts of expenditure have been consistently over-estimated. Coordination of partners to address financial management and variances continues to be challenging. The BHC team builds in leeway as part of our monthly financial process but we continue to discuss further improvements periodically. Concern noted to the reviewer that the increased monthly scrutiny adds to the burden of reporting, with requests for monthly financial reporting on top of quarterly reports, that was not contracted from the outset of the programme. However, monthly financial forecasting was a requirement set out in the Terms of Reference and the programme responsible owner asserts that the CCU finance manager cannot properly manage the finances without regularly monthly management of the downstream partners.

UNICEF
In line with the FCDO UNICEF framework arrangement, the team submitted two progress reports within the reporting period. In the periods between reports, UNICEF updated on progress quarterly in time for the partners meetings and also when key milestones such as the purchasing the next tranche of medicines and commodities.  The Contribution Arrangement was amended twice to update the funding allocated in the reporting year as was agreed at UNICEFs request at the start of the programme. With the exception of procurement of medicines where pre-paid funds are spent in line with a procurement schedule, the remaining funding is applied fairly uniformly in line with spend for staff and overheads. Some funds approved for spend within the reporting period weren’t spent this year due mainly to vacant staff positions and efficiencies in operating costs. UNICEF is working with the BHC now to allocate that funding to activities to support the programme’s outcomes going forwards.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Joint Field Monitoring Visits with implementing partners and MoH colleagues were conducted in Kambia, Moyamba and Western Area Rural, the latter wasn’t joined by any senior member of the MoH which highlighted the ongoing challenge of access to senior management. The BHC team also visited Kono, Tonkolili, Kenema and Bombali as opportunities arose. Visits focused on SCBUs, maternity wards, District Medical Stores, and Community Healthcare Centres which highlighted the challenges encountered by health staff to deliver care in the resource constraints environment. Community members are often consulted during monitoring visits – sometimes as part of a wider group session and also by talking quietly to individual service users to look into their challenges and understanding of the services they can access.

General stock management at DMS level seems to have improved, particularly in the use of mSupply to help manage the stock needs prior to national quantification exercises and distribution of stock.

Evidence
Proper collection, management and analysis of data remains challenging in Sierra Leone’s low capability and low resource environment. Despite this, there has been a good drive this year to embed the systems to manage equipment and patient data within SCBUs and also to tackle child and maternal deaths across the country. Patient data on neo-natal survival and maternal deaths is provided directly to the Directorate of Reproductive and Child Health which is helping to directly tackle where issues are consistently arising. Previously multilateral systems for modelling data were relied upon to estimate changes in maternal and child mortality but for now, real-time data is being provided as evidence for action. The provision of third-party monitoring (TPM) from central to lower-level facilities is also adding to the evidence needed to improve supply chain management nationally. This monitoring is funded by the programme and is unlikely to continue once the programme ends, However, the use of Facility Management Committees made up of members of the community provides an opportunity for community challenge and as a practice, it is likely to outlast the end of the programme.

Learning
Third party monitoring of the supply chain throughout the 16 districts has been shared periodically with district management teams and central MoH. Issues with the management of medicines within each district are shared candidly with teams and both challenges, successes and solutions are discussed in group meetings after distributions.

The MoH has driven a focus on maternal and child deaths this year. Data is provided on a weekly basis and district teams are required to attend a weekly meeting to discuss localised trends and to learn from presented review outcomes. This is helping to drive accountability and learning from deaths as they happen. Perinatal and child deaths have been folded into the maternal death surveillance and review process but it is proving difficult to incorporate due to funding constraints and adopting the change. The requirement to review maternal and child deaths within 30 days is particularly challenging, even in the districts where the programme funds investigations and reviews. This remains a sustainability challenge unless the MoH mandates and funds the reviews going forwards. The programme will continue to provide funding for MPDSR in the six supported districts for a further 17 months.

The funding provided to support SCBUs and in particular for three international paediatricians has reduced this year and BHC are encouraging the transition from international support to nurse-led management supported by hospital doctors as needed. This is a source of concern for MoH who have advocated for continued programme funding for international paediatricians, but we know that survival rates have increased this year despite the reduction and that the most successful SCBU for child survival is led by a nurse without support from an international paediatrician. The MoH has We are also encouraging the adoption of intermittent and where possible, continuous kangaroo care to try to reduce reliance on expensive SCBU equipment for neonatal survival.

The barriers to sustainability will be a priority in the final 17 months of the programme. Due to ODA constraints, the funding available for SL3 will reduce significantly in 2026. This will necessarily impact on activities the programme supports within districts and in particular, the programme will no longer fund the SCBUs and the supply of medicines. Instead, the programme will focus its support on low cost, high impact activities such as the increased use of the cradle device for pregnant women, the expansion of Kangaroo Care to all SCBUs and enabling a focus on MPDSR in all 16 districts. BHC and IPs will work closely with MoH to support them in managing the transition and working to reduce the barriers to providing sustainable improvements in healthcare across the entire country.

Date of last narrative financial report	June 2025	Date of last audited annual statement	March 2025