## Annual Review Template

Title: FCDO Research Commissioning Centre
Programme Value £ (full life): £25,000,000		Review date: 26/08/2025
Programme Code: 301165	AMP start date: 26/08/2022	AMP end date: 31/05/2028

Summary of Programme Performance
Year	2023	2024	2025
Overall Output Score	A	B	A
Risk Rating	Moderate	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003696.odt
DevTracker Link to results framework:	To be published

A. SUMMARY AND OVERVIEW

Description of programme

The Foreign, Commonwealth & Development Office (FCDO) Research Commissioning Centre (RCC) has been established to deliver a new model for efficient delivery of high-quality research funded by FCDO. The RCC operates as a cross-thematic research platform, focusing on best practice in commissioning, equitable partnerships, and research uptake. The new FCDO research delivery model aims to provide more equitable and streamlined access to funding opportunities, academic expertise, and research outputs through alignment with best practice across the global research, science, and technology sector.

The RCC consortium is led by the International Initiative for Impact Evaluation (3ie) in partnership with University of Birmingham as an academic lead partner, alongside a wide network of academic institutions and partners, including from the Global South. Collectively, the consortium represents wide-ranging sectoral expertise to deliver mission-driven research in FCDO priority areas. The RCC commission and manages research funded under the RCC Business Case as well as research funded by other business cases. This involves supporting the Research and Senior Academic Advice Programme (RESAAP) to manage seven existing Senior Research Fellows recruited by the RCC, as well as support recruitment for new roles in the upcoming reporting year.

A separate programme component is delivering a public-facing Global Research and Technology Development (GRTD) website as a single portal for FCDO R&D funding opportunities, research outputs including results and impacts, and provides news, updates, best practice, and guidance for researchers applying for funding, currently limited to commissions managed by the Research Commissioning Centre. This work was begun by the Centre for Agriculture and Bioscience International (CABI) who were subcontracted by 3ie and is now delivered by 3ie. The RCC has successfully launched the GRTD website (www.grtd.fcdo.gov.uk) in January 2025, which has received positive feedback and is now focusing on enhancing content and user experience. The RCC enters now a period of consolidation and scaling, with the RCC responding to a changing aid landscape and evolving FCDO priorities, with ever stronger needs to deliver efficiencies and savings.

Summary supporting narrative for the overall score in this review

Since last year’s annual review, the RCC has made significant progress towards its objectives, using for the first time a fully developed logframe to track performance. The programme achieved an A rating, establishing a strong foundation for measuring results against specific targets in the coming year. The initial results achieved during the reporting period will serve as a baseline for future targets. FCDO also assessed this year’s programme performance based on successful delivery of the workplan and last year’s annual review recommendations, all of which were met or on which significant progress has been made, including the launch of the GRTD platform, development of the Equity Action Plan, and improvements to financial management. The RCC has also strengthened its governance and engagement structures in response to previous feedback and has improved risk management and reporting. Outstanding actions relate to finalising the RCC financial model and cost recovery approach, which remain urgent. These are in progress and will be prioritised in the coming year. For more detailed progress against the full list of recommendations please go to Annex A.

In addition, the RCC continues to demonstrate effective responsiveness and adaptability to deliver FCDO priorities. In some cases, this has seen RCC turn around tight requests in very short timelines: for example, organised within a month a successful Climate and Nature Roundtable. At the end of the reporting period, the RCC has a £5m multi-year research programme underway, 18 separate projects are either live or completed, and it has launched the pilot for the Impact Fund. The evidence suggests that the RCC has delivered high-quality research outputs across five projects that were well-received by stakeholders, contributed to policy discussions, and demonstrated academic rigour and relevance. The RCC has also demonstrated flexibility and responsiveness, adapting to a changing aid landscape and FCDO needs, while embedding best practice, equity, and Value for Money (VfM) across its operations. The RCC also successfully developed and soft-launched the GRTD website in January 2025, marking a significant milestone in enhancing FCDO-funded research communication and accessibility.
Key target achievements include:
- Portfolio Delivery: 18 projects commissioned across a broad thematic spectrum (Climate, Economic Growth, Food and Agriculture, Health, Politics and Conflict, Tech and Innovation, Expertise and Science Advice as well as specific research needs at Posts), with 5 final outputs published on GRTD and 1 open-access journal publication.
- GRTD: Launch of the GRTD website, supporting FCDO efforts in embedding an RCC identity.
- Complex projects: Evidence-Informed Policymaking (EIPM) programme launched, with 350 Expressions of Interest (EoI) in total, of which 63% were from the Global South.
- Impact Fund: Pilot launched, with strong engagement from FCDO and downstream partners.
- Southern Engagement: 72% of projects include LMIC/Global South researcher(s); 3 grants led by Global South institutions.
- Efficiency: 87% positive user feedback on the new Grant Management System (SmartSimple).
- Governance: New engagement structures with FCDO and consortium have been implemented, including establishment of a Steering Group to guide the RCC strategy and direction.
Figure below provides a high-level overview of RCC achievements in numbers that are covered in more depth in the other sections of this review.

Major lessons and recommendations for the year ahead
Lessons Learned
Process Improvements: Comprehensive mapping and analysis of processes and templates have led to systematic improvements, such as the introduction of Stakeholder Engagement and Evidence Uptake Plans (SEEPs) for structured dissemination of research findings, sole-sourcing approaches, and Project Overview Documents.

Adaptive Project Management: Flexibility in processes and terms, such as advance payments and sole-sourcing, has enabled the RCC to overcome challenges and meet diverse needs in demand. In addition, a light-touch process for fast-tracked commissioning was developed in order to handle projects with time-sensitivities.

Publication process: Some occasional issues and delays on projects related to formatting, review and editing of outputs led to introducing standardised process and sharing of key project templates from the outset to ensures clarity and efficiency across RCC.

Effective Communication: Improved governance structures and engagement frameworks have strengthened relationships, and strategic presentations have enhanced communication and trust. However, more work is required to clearly define the RCC Triangle Model and added value.

1. Sector engagement: There are, at present, many groups and networks addressing a wide range of topics relevant to research commissioning and research partnerships. Some groups and networks are more useful than others, with differing perspectives—UK-focused versus international. The RCC plans to consolidate learning from these engagements, identifying which are beneficial and which are not, to optimise efforts and ensure maximum advancement of RCC objectives.
2. Strategic Direction: Establishing an RCC Steering Group and increasing sector engagement have been essential for navigating changes and maintaining strategic direction.

Value for Money (VfM) Trade-offs: The extent to which FCDO teams are willing to fully outsource tasks and responsibilities to the RCC varies based on the scope and scale of commissioned research. Consequently, reducing transactional costs for FCDO can’t be applied universally to all research projects. Therefore, the RCC's VfM approach must be nuanced, acknowledging situations where teams may need to balance trade-offs between achieving efficiency and ensuring effective research outcomes.
Recommendations for the year ahead
#	Recommendation	For	Work Underway/Planned	Action Needed
1	Strengthen Collaboration, Engagement, and Feedback	Both RCC & FCDO	Regular reporting to FCDO on strategic engagements (e.g. BRINN, other funders) is working well. Positive engagement sessions with FCDO in June 2025 set a strong example of open, responsive partnership.	Formalise a joint engagement and feedback framework, including scheduled meetings, structured reporting, and an annual survey for all grant holders and FCDO users.
2	Develop Comprehensive Uptake, Impact and Learning Function	RCC	Stakeholder Engagement and Evidence Uptake Plans (SEEPs) are in place and the Impact Fund is being piloted. Initial lessons-sharing activities (e.g. pilot learning events, sharing best practices from recent commissions) are a strong foundation.	Expand and formalise a systematic process for supporting research uptake , tracking impact across the RCC portfolio and disseminating lessons and best practice from commissioning to FCDO and partners (reflecting proposal and inception report commitments).
3	Promote Coherent Policies, Standards, and Identity	Both RCC & FCDO	Work on developing RCC policies and standards is progressing well. Early steps to promote RCC’s role within GRTD (e.g. participation in BRINN working groups) are positive.	Joined up work with FCDO is required on developing and promoting consistent GRTD R&D policies, standards (e.g. publishing and open data), and branding, including organising FCDO Strategic Partners Forums to further embed RCC within the GRTD identity.
4	Streamline Operational Processes and Guidance	RCC	SmartSimple grant management system has been rolled out and received positive feedback for its intuitive interface and improved tracking. New operational guides are being integrated, with recent updates already shared with users—commendable proactive approach.	Accelerate full embedding of SmartSimple, ensure consistent use across the project lifecycle, and complete integration of all new RCC guides into a single, up-to-date RCC User Guide and Operations Manual, including rolling out checklists for programme initiation and closure.
5	Finalise and Communicate VfM and Management Fee Model [HIGH PRIORITY]	RCC	VfM framework and financial model are being finalised, with recent cost recovery tracking and savings identified during commissioning. Sliding scale model has been piloted with several FCDO teams, providing useful feedback—excellent progress.	Refine the RCC's costs and charges for awards funded from outside the RCC's grant agreement; clearly communicate the ‘sliding scale’ for modes of engagement with FCDO teams. These will be critical factors to ensure sustainable demand.
6	Maintain and Update the Equity Action Plan	RCC	Equity Action Plan is in place, with recent updates reflecting partner feedback and new EDI metrics—demonstrates real commitment to EDI.	Implement a structured schedule for regular reviews and updates to ensure ongoing relevance and effectiveness.
7	Review and Align Logframe Indicators	Both RCC & FCDO	Ongoing discussions between RCC and RESAAP to align indicators and avoid duplication, with recent workshops held to clarify focus areas—good collaboration.	Conduct a joint review of both log frames to ensure clear delineation of focus areas and consider relocating indicator 5.4 to Output 2 if appropriate.
8	Accelerate GRTD Platform Development	FCDO (with RCC support)	Progress on the GRTD platform is ongoing, with RCC providing regular content updates and technical input—these contributions are valuable.	FCDO to allocate a dedicated strategic resource to accelerate development, strengthen accountability, and ensure consistent RCC communication via the GRTD site.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case

The programme’s Theory of Change aligns well with its overarching impact goals, focusing on improving FCDO’s research pathway to achieving development impact and wider UK government objectives through better informed policy-making and innovation, resulting in real change for individuals in the FCDO target geographies. The desired progress towards these goals will be measured at outcome level across three areas:
- Outcome 1: RESEARCH AND INNOVATION UPTAKE. High quality global research managed and delivered by the RCC is used by academics, policy-makers, and other decision-makers.
- Outcome 2: THE RCC IS RECOGNISED FOR EFFICIENT AND EQUITABLE COMMISSIONS. RCC’s approaches for commissioning represent best practice and lead to efficient and equitable relationships delivering research agendas and solutions that are relevant to local communities, mainly in the Global South.
- Outcome 3: GLOBALLY RECOGNISED IDENTITY AND COHERENT PORTFOLIO. GRTD research priorities, opportunities, investments, outputs, and results are recognisable and become more coherent under a single identity.
The specific approaches at output level involve:
- Generating quality evidence and technical support to support FCDO needs and priorities;
- Increasing uptake and dissemination activities through RCC targeted processes and strategic funding;
- Leveraging diverse expertise from across the sector by improving access to funding opportunities through GRTD communication and strategic engagement with consortium partners; and
- Accelerating access to relevant research through more streamlined and equitable commissioning practice, building on the recommendations from the Independent Review of Research Bureaucracy, lessons learned and best practice from the sector.
Assumptions
The original assumptions still apply in the face of challenges around ability to maintain a sustainable commissioning model. These risks have been reflected within the programme risk register. The summary of the assumptions and their assessment in this reporting period is as follows:
1. Use of research in decision making will support effective policy and poverty reduction: This area is regarded as sensitive to assumptions and potential biases. Consensus evidence indicates that the use of research leads to more effective interventions and positive impact. The FCDO has asked the RCC to commission the Evidence-Informed Policymaking research, to address knowledge gaps in this area and improve the use of evidence in policy and decision-making.
2. Uptake of research is contingent upon effective access to, and understanding of, research: The RCC will develop and implement a targeted approach to dissemination and uptake of research, including through the new Global Research and Technology Development brand and website. The website aims to improve communication and access to research results and outputs funded by FCDO. In addition, the RCC launched in April 2025 a strategic Impact Fund to enhance FCDO-funded research uptake and impact.
3. There is a sustained demand from FCDO to use the RCC: The demand for the RCC services will depend on the availability of FCDO funding and the reputation of the RCC as professional, trusted and effective commissioning mechanism route for research. In the last reporting period, RCC has shown increasing credibility and effectiveness as a commissioning mechanism with more clearly articulated offer and streamlined processes and templates. However, defining the costing model and delivering value for money might be more challenging under current fiscal pressures where ODA budgets are reduced.
4. The RCC attracts high quality research expertise: Responses to calls have been strong, and the RCC is reaching a diverse range of local researchers on research calls, with many high-quality proposals received (within both one and two-stage processes).
5. The RCC has appropriate capacity to respond to FCDO’s priorities: Following the RCC restructure in May 2024, resulting in recruiting a fulltime Managing Director alongside other priority roles, the RCC significantly increased capacity to deliver consistent quality results at pace accelerating the progress towards a ‘scale and sustain’ phase.
6. The RCC effectively commissions and disburses funding: Tackling risks around this assumption is a priority, as this is where the FCDO expects to see measurable and increased efficiency and effectiveness.
7. The RCC demonstrates effective and robust approach to due diligence and risk management: The RCC undertakes structured assessments of their financial systems, internal controls, and governance structures. All grantees must submit project-specific risk registers and regular monitoring is integrated into the Grant Management System (GMS). Compliance measures include anonymous reporting forms, updated safeguarding policies, and refined risk escalation processes. These efforts support informed funding decisions, promote partner compliance, and ensure responsible delivery of RCC-funded projects.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The RCC programme is largely on track to contribute to its expected outcomes and impact. The RCC projects have published its first set of final outputs and presented at academic forums, demonstrating good performance in generating high-quality evidence. The programme has also actively engaged with sector groups, implemented best practices, and successfully involved Global South researchers and institutions. Additionally, the RCC has shown agility and responsiveness to FCDO demand, with regular engagement and contributions from senior academics and subject matter experts. The GRTD platform has been successfully launched, with positive user experience for the GMS. The Impact Fund has been launched in April 2025, but the establishment of the Open Access Fund has been put on hold pending FCDO policy finalisation.

Key achievements at outcome level include contributing to policy discussions and practices, with three case studies presented in text boxes below. These examples highlight how RCC research is actively shaping policy discussions and practices, providing evidence-based insights to inform strategic decisions and programme implementations. In November 2024, the RCC implemented templates for Stakeholder Engagement and Evidence Uptake Plans (SEEP), with versions for short-term and longer-term projects. The SEEP supports early engagement strategies and informs key log frame outcome and output indicators. The RCC also begun embedding the Equity Action Plan within RCC process and more widely leading, with early evidence showing positive outcomes for the reach of RCC commissions in the Global South and the representation of LMIC researchers on RCC projects.

Climate Change Impact on Rail Operations in Turkey:

This project evaluated the impacts of climate change on Turkey’s railway infrastructure, identifying critical segments susceptible to climate-induced hazards. The study engaged stakeholders through workshops, seminars, and high-level events, presenting findings to technical experts, academics, and policymakers. The project culminated in tailored information packages shared with stakeholders, ensuring informed uptake and broader technical interests. The findings have contributed to policy discussions on climate resilience and infrastructure planning in Turkey.

Evidence-Informed Policymaking (EIPM) Programme:

The EIPM programme delivered a pathfinding paper, conceptual framework, and measures database to inform an open call for proposals. The Expressions of Interest stage for Strand 2 received 145 applications, with 63% from the Global South. The programme aims to generate actionable evidence on enhancing evidence use in policymaking, which can inform the RCC's approach to research impact and advance wider sector learning. The conceptual framework and measures inventory have been instrumental in shaping the scope of funding rounds and have been referenced by applicants in their research designs.

Health Impact of Investments in Vertical Programmes and Healthcare System Strengthening:

This project, led by Imperial College London, compared the health benefits of vertical programmes for diseases like HIV, TB, Malaria, and Vaccine-preventable diseases versus strengthening healthcare systems in Malawi. The study used a modelling approach to quantify the health impact of each strategy. The findings have shaped the narrative for the multi-year spending review of the Global Health Directorate in FCDO, justifying a move towards a more integrated health systems approach. The results have informed strategy implementation papers and concept notes for new health system strengthening programmes.

The RCC will continue working on developing a quality assurance framework to formalise research standards for grantees, including ethics, data protection, and methodological rigour, by following best practices or creating bespoke guidance. It will cover standards and processes for various research designs, such as impact evaluations and systematic reviews, and outline domains of expertise for quality assurance within and outside the RCC consortium. An initial draft was presented at the RCC away day in March 2025 and is being revised based on feedback. The framework will include templates, process documents, and public-facing guidance for applicants and grantees to set clear expectations about research standards.

Planned actions for the year ahead include evaluating the Impact Fund pilot and developing robust research uptake measurement to support grantees in maximising impact. Launching the Open Access Fund remains an objective although this depends on FCDO’s progress in finalising updates to its open access policy. The RCC will continue to consult, implement and monitor the Equity Action Plan, with a focus on increasing Global South leadership and participation. This includes focusing on strengthening consortium governance by fully implementing new engagement structures and expanding Global South membership. The RCC will also focus on improving its value for money proposition, GRTD communication and maintaining regular engagement with consortium members and FCDO teams. These actions aim to further enhance the programme's effectiveness, efficiency, and impact, ensuring it remains aligned with strategic priorities. The RCC will continue to review staffing and financial models to ensure the RCC continues to improve VfM and progress towards a sustainable costing model. Further work in the coming reporting period will involve reviewing the Theory of Change to further define impact, outcomes, and refine existing outputs in line with emerging evidence.

The key challenges for the RCC in coming year will relate to navigating the changing aid landscape with UK ODA budget reductions, addressing uncertainties in the pipeline of work, and establishing the RCC as a sustainable, trusted partner for new programming that delivers value for money amidst financial model decisions and strategic shifts. Conversely, significant opportunities exist in consolidating research funding through the RCC, improving relationships across RED teams, delivering large-scale programmes like Evidence-Informed Policymaking (EIPM), and leveraging the RCC's research budget to support high-priority research. By focusing on these opportunities, the RCC can strengthen its position and continue to deliver impactful research despite the challenges.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the analysis of outcome and output achievement, theory of change, and VfM analysis, the RCC represents satisfactory and increasingly better value for money. The programme demonstrates good performance in delivering high-quality, impactful research, engaging with diverse stakeholders, and adapting to changing FCDO needs and lessons learned. While there are areas for improvement, such as increasing open access publications, enhancing engagement with FCDO and consortia partners, effective implementation of the Southern Engagement Strategy and stronger VfM offer, the evidence suggests that the programme should continue its operations with a focus on these enhancements, particularly to drive effectiveness and efficiency. Regular monitoring should be conducted to ensure ongoing alignment with strategic priorities and focus on enhancing its effectiveness and value for money.

## C. DETAILED OUTPUT SCORING

Output Title	RESEARCH QUALITY. Research programmes managed by the RCC and technical hub produce high quality outputs in prioritised areas of interest to the FCDO.
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 # of projects with final outputs published on GRTD	Baseline	5
1.2 # of papers accepted for open access publication (including revise and resubmit) in a journal	Baseline	1
1.3 # of presentations of RCC-funded projects at academic conferences, seminars, industry events or in relevant policy forums	Baseline	8

Briefly describe the output’s activities and provide supporting narrative for the score

This output scores an A for RCC producing a number of academic publications, systematic reviews, and presentations at events.

Output 1.1 and 1.2
Many of the projects commissioned through the RCC, or delivered by the RCC’s own Technical Hub, are now reaching the latter stages of the project lifecycle, where the research findings are being synthesised and final reports or other complementary outputs completed. Below is the list of FCDO-funded outputs produced and published (or soon to be) under the RCC in this reporting period:
1. Mapping the Shadow Economy (Alexandru Ioan Cuza University): Systematic review report published in May 2025.
2. Evidence-Informed Policymaking - Strand 1 (3ie): Pathfinding paper, conceptual framework, and inventory of measures published in April-May 2025.
3. Evidence-Informed Policymaking - Systematic Review (PACE): Systematic review pre-print published on GRTD website, awaiting final journal acceptance from Campbell Systematic Reviews.
4. Understanding the impacts of El Niño and the Indian Ocean Dipole in the Indo-Pacific (University of Greenwich, Natural Resources Institute): Systematic review and brief published in April 2025, with a blog to be published in June 2025.
5. Food loss reduction in developing countries (University of Greenwich, Natural Resources Institute): Systematic scoping review, promising interventions paper, and landscape report published in May 2025.
6. Impact of climate change on rail operations in Turkey (ISSD Bilişim Elektronik Eğt. San. Ve Tic. A.Ş.): Executive summary planned for August 2025.
7. AI and Agriculture (Athena Economics): Rapid evidence review and systematic review planned for August 2025.
8. Supporting Pastoralism and Agriculture in Recurrent Protracted Crises Fragility and Agriculture Resilience Evidence (3ie): Evidence gap map planned for September - November 2025.
9. Thanzi la Onse (Imperial College London): Academic report planned for August - September 2025
Output 1.3
The RCC and its awardees participated in a range of engagement activities with key stakeholders at project level where research was presented or discussed, including those which are listed below:

- El Niño & Positive Indian Ocean Dipole Impacts Seminar (Nov 2024): Final findings were shared online by University of Greenwich and partners, with participants from FCDO, Leeds, and Red Cross Crescent Climate Research Centre.
- Food Loss Reduction Seminar (Nov 2024): University of Greenwich highlighted research on post-harvest loss interventions, attended by major international development agencies and universities.
- Climate Change & Rail in Turkey (Nov 2024 – Feb 2025): ISSD presented systematic review findings at a major Turkish rail conference, followed by a seminar and a high-level closure event with national and sector stakeholders.
- Evidence-Informed Policymaking Events (Mar – May 2025): Preliminary and final outputs from EIPM Strand 1 research were presented at seminars and conferences, including the Impact Funders Forum, British Academy, and a major event in Nairobi.

In addition, the RCC has organised 10 workshops with FCDO and key stakeholders to discuss preliminary findings and inform the final research reports across different projects. This includes a presentation of findings to FCDO and research hubs in May 2025 on the Behavioural science portfolio review led by Magenta.

Describe any changes to this output during the past year, and any planned changes as a result of this review

This is the first reporting year in which logframe has been fully developed and data has been collected in a systematic way.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

N/A

Output Title	COMMISSIONING PROCESSES REFLECT BEST PRACTICE AND DELIVER EFFICIENCIES AND INNOVATION. Best practice commissioning practices and processes, aligned with HMG bureaucracy review recommendations are implemented and result in strong, fair, efficient and well managed competitions.
Output number:		2	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
2.1 / 2.1.1 % participation in relevant BRRIN Working Group sessions 2.1.2 # representations in wider sector groups, networks and forums, including topic-specific conferences 2.1.3 % of relevant BRRIN recommendations addressed (20 out of 32 in total)	1) 90% / 2) Baseline / 3) Baseline	1) 91% / 2) 7 / 3) 70%
2.2 Evidence of improved or innovative commissioning practices demonstrated, as a result of active learning and engagement with FCDO, other funders and wider sector	Baseline	3 x one-pager examples
2.3 % of awards 1) commissioned and 2) delivered to agreed timelines [Agreed timelines should refer to the most recently approved timeline signed off by the FCDO team]	1) 100% projects commissioned on time / 2) 100% outputs delivered on time	1) 100% / 2) 85.7%

Briefly describe the output’s activities and provide supporting narrative for the score

This output scores an A due to RCC demonstrating strong collaboration, adherence to best practices, alignment with the HMG bureaucracy review recommendations and continuous improvement, resulting in in strong, fair, efficient, and well-managed competitions and research delivery.

Output 2.1
RCC is actively engaged with 4 relevant Bureaucracy Review Reform and Implementation Network (BRRIN) sub-groups working on the following themes: Assurance; Applications and Assessments; and Digital and Impact Reporting. In this reporting period the RCC has participated in 91% of the meetings under those sub-groups.

The RCC team also reviewed all recommendations set out in the Independent Review of Research Bureaucracy: final report and has been working towards addressing 20 relevant recommendations out of 32 in total. Of these, the RCC has addressed 70% of recommendations to date. In February 2025, the BRRIN Steering Group noted the RCC’s implementation of recommendations and streamlined, best-practice approaches, in particular:
- The adoption of a 2-stage due diligence processes
- A triage process ahead of peer review
- Flexibility (transfer of funds between budget headings without sign-off or no-cost extensions)
- Standardisation across application forms (based on best practice)
- The considered use of 2-stage commissioning
- The implementation of a Grant Management System

In addition, the RCC has actively engaged with 7 topic-specific conferences, workshops and forums of relevance to RCC and supported by FCDO. This has included conferences and workshops on equitable partnerships, evidence-informed policymaking and research on research. This includes workshop sessions relating to BRRIN working groups, specifically focused on impact, applications and assessments.

Output 2.2
Across the wider sector, the RCC team held numerous meetings and engaged across multiple fora to establish strategic connections, to learn and share learning. This includes UK funders Wellcome Trust, NIHR, UKRI and AHRC, as well as academics across the Global South, the UK, consortium members, institutes and bodies engaged on research on research and international organisations. Many of these have been targeted conversations on research uptake, open-access policy development, equitable partnerships and research agenda-setting. In its continuing efforts to understand prevailing and emerging practices across the larger funding landscape, the RCC is scoping over 40 funders globally across 38 processes and templates.

Key examples of practical application of this learning in this reporting period are:

  1. EIPM: In April 2025, the RCC launched two calls for expressions of interest for its largest programme to date, focusing on evidence use in policymaking in Sub-Saharan Africa and South Asia. The first call aims to study evidence use in practice, while the second seeks to evaluate interventions to influence evidence use. The programme's design included an extensive scoping period with a systematic review, consultations, and a pathfinding paper to identify research priorities. Influenced by Professor Tickell’s Independent Review of Research Bureaucracy, the commissioning process features a two-stage approach to reduce applicant burden and increase efficiency. The RCC emphasises equity, diversity, and inclusion, engaging Southern researchers and extending submission timelines. Applications will be evaluated based partly on team diversity, contextual expertise, local stakeholder engagement, and equitable partnerships.

  1. The RCC Impact Fund: This is a new RCC initiative to enhance the societal impact of FCDO's research investments by providing additional financing for promising projects. The fund's design was informed by benchmarking research and learning from six existing impact funds from across the sector. The pilot phase features specific submission windows, diverse eligible activities, engagement and communication plans, and collaboration with RED team leads and downstream partners.

  1. The Equity Action Plan (EAP): RCC developed this plan to implement its equity, diversity, and inclusion (EDI) and Southern Engagement strategies. Drawing on best practices from over ten UK and global research funders, plus the 'EquiPar Tool', the EAP covers community building, research commissioning, and legal/financial management. Key recommendations include fostering and budgeting for research partnerships and sustaining these relationships. The EAP consolidates such measures, with several already in place—such as diversified communications, time allocation for partnership development, equity-focused grant scoring, diverse review panels, and flexible delivery schedules. Additionally, RCC has adjusted awarding processes and due diligence to better support smaller or diverse organisations, including offering multiple contract types and allowing advance payments when justified.
Output 2.3
For this reporting period, 8 projects (100%) were successfully commissioned over the reporting period and 7 completed and delivered outputs to agreed timelines. Going forward, the RCC will improve the tracking of the project status throughout the project lifecycle, to better understand lead-times across different stages of the commissioning process, including the timeline from the initial request to awarding, and the awarding process itself. This will allow identify any bottlenecks and drive further improvements.

Describe any changes to this output during the past year, and any planned changes as a result of this review

This is the first reporting year in which logframe has been fully developed and data has been collected in a systematic way.

Progress on recommendations from the previous AR

N/A

Recommendations for the year ahead

See amalgamated set of recommendations in table on pages 4-5

Output Title	LOCALLY-LED RESEARCH AND EQUITABLE PARTNERSHIPS. Awardees function as equitable partnerships with enhanced opportunities for Southern-based institutions.
Output number:		3	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
3.1 % of projects where the research team includes a researcher based in the Global South or a LMIC	Baseline	72%
3.2 3.2.1 # of awarded grants led by organisations in the Global South 3.2.2 # of applications submitted by organisations in the Global South	1) Baseline / 2) Baseline	1) 3 / 2) 95
3.3 # of organisations in the Global South who are actively engaged with RCC processes (including contributing/consulting on ToRs, peer reviews, uptake) and/or strategic development of RCC structures	Baseline	8

Briefly describe the output’s activities and provide supporting narrative for the score

This output scores an A+ as expectations moderately exceeded results for outputs 3.1. and 3.2 even though formal targets are yet to be agreed. The programme demonstrates the high level of active participation in research delivery, particularly around the submission rate of applications and active engagement of researchers from Global South in research delivery.

Output 3.1 and 3.2
72% of RCC projects commissioned so far have a research team that includes at least one LMIC or Global South researcher, reflecting the broad global RCC focus. Three of the awarded grants have been led by organisations based in the Global South. Upon the launch of both EIPM and Impact Fund 95 out of a total 183 applications received by the RCC to date have been from Global South institutions; this is just over half of all applications. This is a very positive indicator that global south representation will continue to improve across the RCC for the coming reporting period.

Dedicated outreach activities were conducted to engage Global South and LMIC institutions, including in-person events in Cape Town and Nairobi for the 'Evidence-Informed Policymaking' programme. Additionally, the pilot phase of the Impact Fund encouraged lead partners to share this opportunity with downstream partners in the Global South for direct applications.

Output 3.3
RCC has engaged 8 Global South organisations which contributed to RCC processes and/or strategic development. This includes many of the organisations in the RCC consortium, such as the American University in Beirut, the American University of Cairo, Birzeit University, and the BRAC Institutes of Governance and Public Health. The engagement covers a broad range of activities, including consultation in key RCC strategies (EDI and Southern Engagement), participation in advisory groups (EIPM), and contributions as peer reviewers.

Describe any changes to this output during the past year, and any planned changes as a result of this review

This is the first reporting year in which logframe has been fully developed and data has been collected in a systematic way.

Progress on recommendations from the previous AR

Recommendation	Progress	Status
Design and implement a proportionate strategy that mainstreams diversity and inclusion throughout the portfolio	RCC created an Equity, Diversity and Inclusion Strategy and a Southern Engagement strategy. The Equity Action Plan outlines RCC's specific action areas.	Completed

Output Title	EFFECTIVE IMPACT AND OPEN ACCESS FUNDS. Impact Fund pilot launched and iterated based on feedback and review of effectiveness.
Output number:		4	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
4.1 Impact Fund pilot launched and iterated based on feedback and review of effectiveness	Pilot Impact Fund launched	Met
4.2 # of impact fund grants awarded	0	0
4.3 # of open access grants awarded	0	0

Briefly describe the output’s activities and provide supporting narrative for the score

This output scores an A upon successful launch of the Impact Fund, initially as a pilot phase. RCC will work to establish an Open Access fund when FCDO’s updated Open Access Policy is finalised. RCC and FCDO will co-ordinate to ensure full alignment in guides and approaches to develop a common GRTD standard for open data and research publishing.

Output 4.1
The RCC launched the pilot phase of the Impact Fund in April 2025, designed to enhance the societal impact of FCDO's research investments. This milestone was achieved after a prolonged delay due to RCC’s capacity issues. Work accelerated significantly when a new RCC Managing Director joined in November 2024.

The fund's design was informed by benchmarking research from six existing impact funds, identifying key themes such as fixed deadlines, bundling impact strategies, active collaboration, and early engagement. The pilot phase includes specific submission windows, diverse eligible activities, engagement and communication plans, and collaboration with RED team leads and downstream partners. Although no impact fund grants have been awarded yet, the RCC has received positive interest and engagement, with multiple Q&A sessions to clarify the process and the review of applications is currently in progress. The pilot phase will be evaluated later in the year to incorporate learnings and improve subsequent funding rounds.

Describe any changes to this output during the past year, and any planned changes as a result of this review

This is the first reporting year in which logframe has been fully developed and data has been collected in a systematic way.

Progress on recommendations from the previous AR

Recommendation	Progress	Status
Develop and agree on delivery of the Open Access and Impact Fund	RCC reviewed existing initiatives and developed pilot phase of Impact Fund- first call went live in May 2025. Open Access Fund awaiting FCDO approval to proceed	Completed

Output Title	RCC CONSORTIUM RESPONDS EFFECTIVELY AND FLEXIBLY TO FCDO DEMAND. The RCC establishes strategically aligned partnerships and strong communication with the consortium, research partners and wider research network to deliver responsive and high-quality research
Output number:		5	Output Score:	A
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
5.1 / 5.1.1 % of timely initial responses to research requests 5.1.2 Examples of responsiveness and agility to changing needs and priorities	1) 100% / 2) Baseline	1) 100% / 2) 7
5.2 # of senior academics and deep (10+ years) subject matter experts contributing to RCC commissions	Baseline [last review had 72]	75
5.3 RCC annual survey demonstrates regular and high-quality engagement with FCDO commissioning teams and researchers	0	0
5.4 Examples of strategic relationships established within the consortium and wider research commissioning community which contribute to improving the RCC’s efficiency and effectiveness	Baseline	6

Briefly describe the output’s activities and provide supporting narrative for the score

This output scores an A for the strong performance and responsiveness demonstrated throughout the year, particularly in terms of delivering 100% timely responses to initial FCDO requests. The consortium has shown great agility in adapting to changing needs and priorities, positioning the RCC as a reliable and high-quality research partner.

Output 5.1
The examples of RCC’s responsiveness and agility to meet emerging priorities and changing needs are presented are summarised in the table below:

Example	Details
Climate and Nature Roundtable to inform Africa approach	Mobilised a team of experts from the consortium and beyond and operational leads from the RCC to meet project specific goals. In just over a month of project kick off, the Roundtable had been actualised via the RCC. Successful delivery of roundtable at short notice.
Supporting Pastoralism and Agriculture in Recurrent and Protracted Crises (SPARC); and Fragility and Agriculture Resilience Evidence (FARE)	Developed accelerated and light touch commissioning process bespoke to project constraints. RCC also conducted an online FAQ webinar to address some questions potential applicants may have had prior to proposal submission. Call for proposals awarded within 1 month to meet project needs.
Water Risk in Uruguay	Developed tailored safeguards, policies and schedules to accommodate research needs for making advance payments. This was possible by close working relationship with the research team (weekly meeting schedule). Project revised to accommodate advance payment structure, to allow it to continue. Advance payment structure approach can be applied to other projects where suitable.
Countering influence	Developed process and documentation for direct procurement requests (including ToR and sole source memo). Within 1-week RCC was able to respond to FCDO’s direct procurement request with details of what would be needed for sign-off and get the process underway. Clear procedures for direct procurement in place allowed to move through the pre-award process quickly.
New Frontiers: The Cross-Border Conflict Evidence, Policy, and Trends (XCEPT)	Discussed a wide range of options for a stronger agenda-setting focus. Followed up engagements within short time frames, offered quick access to operational and academic expertise for un-costed consultation. XCEPT to progress to project via RCC conditional on FCDO budget sign off. Delays from the initial engagement linked to Spending Review outcomes.
Centre of Expertise for Science in Emergencies (SECE)	With minimum information about the needs and parameters of the project, developed plans in preparation for a kick-off. Running this kind of commission is a new area of work for the RCC. Maintained open channels of communication, followed up regularly after initial engagements.

Output 5.2
Senior academics and subject matter experts have significantly contributed to RCC commissions by ensuring quality assurance and peer review, providing technical and advisory roles, and engaging in strategic relationships with key stakeholders. They have actively participated in events and workshops, supported commissioning processes, and played a crucial role in developing and implementing the RCC’s Equity Action Plan. Their mentorship and capacity-building efforts have enhanced the capabilities of research teams, particularly those from the Global South, ensuring the quality, relevance, and impact of RCC-funded research while promoting equitable research practices.

Output 5.3
The Annual FCDO User and Grant Holder surveys will be designed and launched in the upcoming reporting period, to collect systematic data and measure progress and process improvements in RCC priority areas.

Output 5.4
The consortium had been an underutilised tool during the first two years of the RCC. The RCC Managing Director has conducted a comprehensive consortium review, which has led to the identification of key areas for improvement and stratification of the consortium to ensure purpose-driven communications and best utilisation of the organisations within the consortium. During the reporting period, the RCC has actively engaged within the consortium and wider research commissioning community, contributing to improved RCC’s efficiency and effectiveness through collaboration, sharing best practices, and leveraging sector-wide expertise as per examples provided in the table below.

Organisation	Collaboration Details
British Academy	Collaboration on EIPM through joint events, presentations, and staff engagements. Shared learning on commissioning practices and coordinated reporting to maximise research impact.
UK Research and Innovation (UKRI)	Ongoing consultations focused on equitable partnerships, including sharing the RCC’s Equity Action Plan and discussing potential areas for collaboration.
Institute of Development Studies and Southern Voice	Partnership on equitable research partnerships, including participation in workshops and ongoing dialogue. Valuable insights for the RCC’s Equity Action Plan and expanded network for future collaborative initiatives.
International Network for Advancing Science and Policy (INASP)	Discussions on shaping the RCC’s strategic approach to its Open Access Fund. Plans to integrate INASP’s evidence into the fund’s design and explore collaborative contributions.
Pew Charitable Trusts / Impact Funders Forum	Engagement through panel contributions, webinars, and individual meetings focused on evidence use in policymaking. Building networks with funders invested in EIPM and aligning research agendas.
World Health Organisation (WHO)	Collaboration on enhancing evidence use in policymaking, including joint events and learning sharing activities. Representation of the RCC on WHO working groups to align respective programmes of work.

Describe any changes to this output during the past year, and any planned changes as a result of this review

This is the first reporting year in which logframe has been fully developed and data has been collected in a systematic way.

Progress on recommendations from the previous AR

Recommendation	Progress	Status
Design and implement a partnership-level agreement for RCC and FCDO	RCC developed draft PLA in December 2024, and following feedback converted this into a Project Overview Document (POD).	Completed
Standardise RCC Terms of Reference template with core clauses included	Created Project Overview Document (POD) in place of standardised ToR	Completed
Improve calendar of engagement with FCDO’s research teams and communicate successes effectively	RCC has implemented an improved communications framework with FCDO, shared May 2025, together with clear reporting structure.	Completed
Agree and deliver a vision for the role of the consortium	Consortium review conducted December 2024-March 2025, and subsequently agreed to move forward with a targeted consortium approach.	Completed

Output Title	RESEARCH COMMUNICATION AND DIGITAL PLATFORM. GRTD research priorities, opportunities, outputs and research impacts are effectively communicated, widely disseminated and more accessible through a digital GRTD platform.
Output number:		6	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
6.1 GRTD platform progress - RCC	1) Launch of platform / 2) Train up to 3 FCDO staff to help upload FCDO content directly to the GRTD website, including news and outputs / 3) Approach to publishing outputs on GRTD agreed	1) Met / 2) Met / 3) Met
6.2 FCDO produces regular and up to date content to communicate on GRTD latest activities and results	Development of an FCDO-internal process and pipeline to ensure regular communication	Met
6.3 Positive user experience with the GMS (4 -‘Good’ or 5 - ‘Excellent’)	Baseline	87

Briefly describe the output’s activities and provide supporting narrative for the score

This output scores an A due to meeting expected milestones related to the successful launch of the GRTD website and establishment of regular communication processes. In addition, high positive user feedback demonstrates a strong start for a newly rolled out GMS.

Output 6.1
The RCC successfully developed and launched the GRTD website in January 2025, following a weaker performance in the early months of this reporting period, before joint working on this became more efficient and effective. The beta site features seven primary pages, including sections for funding opportunities, research outputs, news, and contact information. The website aims to embed the RCC within the GRTD brand, facilitating the dissemination of research findings and funding opportunities. Initial feedback has been positive, with plans to further enhance the site by prioritising content updates and improving user experience. The RCC is working closely with FCDO to ensure the effective running of the website, including training FCDO staff on content management and developing a comprehensive communication strategy to maximise the impact of the GRTD platform as soon as a dedicated GRTD Programme Funded role is appointed.

Output 6.2
A milestone for this output was set to develop an internal FCDO process and pipeline to ensure regular communication, with future ambitions to include more proactive engagement indicators. FCDO has committed to maintaining a steady flow of content, including links to GRTD platforms, impact stories, and research outputs. A communications specialist programme funded role was proposed to lead the design of a comprehensive communication plan, including audience mapping and engagement strategies. However, budget limitations and uncertainties around funding allocations have constrained the pace of content expansion. Technical and editorial bottlenecks during the initial phase of the website have also slowed publication. The necessary training has now been provided and plans for establishing a staged site agreed, to ensure FCDO can publish content more effectively. Additionally, while internal feedback has been positive, structured engagement cycles and clearer alignment with strategic GRTD objectives are still being developed to ensure consistent and credible communication.

Output 6.3
The GMS is integrated into the broader GRTD website to support the RCC’s role as the commissioning arm of GRTD, to streamline the end-to-end process of managing FCDO-funded research. Its objective is to enable faster application processes, easier re-application for returning researchers, and more efficient oversight of deliverables. The GMS was rolled out for the first time - and feedback gathered from users - within the EIPM commissioning process. In total, 352 user surveys were submitted with feedback asking for experience of the new GMS system and application process. The results included 87% of users rating their experience as good (4/5) or excellent (5/5). Illustrations of several positive comments are shown in the box below. Some users did report occasional technical issues, suggested bigger text boxes and some context papers were inaccessible in low-income countries due to not being open access. Overall, the feedback provided valuable insights that will help guide future enhancements and the RCC will resolve technical glitches and revisit application process for future calls, including pre-populating FAQs and extending feedback survey to include external reviewers The GMS will continue to evolve based on user input and operational needs.

GMS User Survey questions being asked:

On a scale of 1 to 5, how would you rate your user experience of the RCC grant management system? (very poor, poor, average, good, excellent)

How easy was it to navigate the application process? This could include the clarity of the call documents, the grant management system user guide, and the application form (very difficult, difficult, neutral, easy, very easy)
Positive feedback points highlighted:

- Ability of saving on every page and low data usage.
- Considered one of the best online submission portals.
- User-friendly compared to other similar platforms.
- Seamless experience.

Describe any changes to this output during the past year, and any planned changes as a result of this review

This is the first reporting year in which logframe has been fully developed and data has been collected in a systematic way.

Progress on recommendations from the previous AR

Recommendation	Progress	Status
Ensure adequate capacity and oversight of the new digital platform	GRTD MVP (minimum viable product) website launched January 2025, content management system training held with FCDO in April 2025 and options presented for further development and oversight.	Completed
Develop a GRTD Communication Plan	A GRTD process to maintain MVP communication has been agreed between FCDO and RCC to maintain a regular pipeline of communication pieces. More detailed communication plan will be developed once a GRTD programme funded strategic comms lead is in place.	Completed

## D: VALUE FOR MONEY

Key cost drivers and performance

The total spend for the RCC for the financial year April 2024 to March 2025 amounted to £1,823,857. Of this, £1,394,223 represented spend for RCC coordination and management, the RCC technical hub, spend on the digital platform as well as the wider expert pool, travel, subsistence and other direct and indirect costs. A total of £429,633 was directly commissioned research spend with £169,370 on non-ODA, and £260,263 on ODA research. Finally, in addition to the core and research costs above, an additional £750,414 was spent on the basis of ‘external’ business cases commissioned through the RCC (i.e. not accounted for by the business case for the RCC itself).

RCC Spend Breakdown

Of the RCC core budget, the largest portion of this was allocated to 3ie project staff, whose roles include the Commissioning Centre Director, Programme Director, Senior Programme Manager, and other technical experts in evaluation, engagement, finance, and communications at a combined cost of £760,110. The University of Birmingham (UoB) contributed staff costs amounting to £146,175 covering academic directors, a project manager, and a research fellow.
Additional direct costs were incurred through project activities and platform development. The discovery process for the digital platform, undertaken by CABI, in addition to platform development costs added another £69,952. Other project activities, including travel, editorial production, dissemination, and event costs, amounted to £39,833. A total spend of £16,891 was made in the expert pool, which draws on the wider consortium partners. Indirect costs, referred to as NPAC (Non-Project Attributable Costs), totalled £341,787 for 3ie and £19,472 for 3ie and UoB respectively.

Core Costs
RCC Staff	£760,110
UoB	£146,175
Digital Platform Discovery	£6,181
Digital Platform Development	£63,771
Travel, editorial production, dissemination, and event costs	£39,833
Expert Pool	£16,891
3IE NPAC	£341,787
UoB NPAC	£19,473
Core Total	£1,394,221
Research (ODA and non ODA)	£429,633
Full Total	£1,823,854
External Costs
External Business Cases	£750,414

VfM Performance

Economy
RCC benchmarks costs against industry standards to ensure competitive pricing and conducts regular audits to eliminate unnecessary expenditures. Performance is evaluated by tracking spending on commissioning/management as a proportion of research awards, benchmarking key costs, and monitoring annual disbursement against the budget to keep the unit costs of inputs as low as possible whilst maintaining the necessary quality and sustainability. For this, going forward the RCC will track the proportion of central management costs recovered through external business cases to understand the RCC’s progress towards a sustainable costing model.

Efficiency
Standardised templates and an automated Grants Management System streamline application, reviewing and reporting processes, while random spot checks maintain compliance and drive improvements. Efficiency is assessed through award timelines, granting process duration, and savings derived from strategic relationships.

Effectiveness
Projects are tracked for on-time delivery and alignment with FCDO priorities, with research findings actively disseminated via workshops and publications. Effectiveness is measured by evaluating project presentations and citations to determine research uptake.

Equity
RCC partners with Global South organisations and uses flexible payment models to promote inclusivity and fair resource distribution. Equity is monitored by analysing project and grant participation rates among Global South or LMIC researchers and organisations. The Equity Action Plan will allow the RCC to adopt a systematic approach to increasing equity within its portfolio.

Cost-Effectiveness
An RCC VfM framework and scoring in proposal assessments ensure funding supports cost-effective projects, with direct commissioning focusing on high-impact investments that minimise overheads. Cost-effectiveness is balanced using both quantitative indicators and qualitative evidence to demonstrate overall value delivery.

VfM performance compared to the original VfM proposition in the business case

The RCC has demonstrated strong responsive access to expertise, effectively mobilising sector experts for various initiatives to respond to FCDO priorities, reflecting high value for money in this area. The introduction of Grant Management System and the development of the VfM framework reflect strong efforts to enhance efficiency and financial management. However, challenges in communication and specific engagements on individual FCDO projects indicate areas for improvement. Addressing these challenges and continuing to refine processes and strategies will further enhance the RCC’s value for money. It is also acknowledged that the RCC operating cost remains high in relation to the RCC’s overall portfolio value. This is partly due to demand at lower budget levels than anticipated and partly an intentional programmatic decision to limit the research pipeline to allow RCC to fully develop its processes and deliver required improvements, before further scale-up.

In addition, in line with the last year’s recommendations, the RCC developed a Triangle Model as a strategic framework designed to enhance the effectiveness and impact of the RCC. The model leverages three core components: strategic support and agenda-setting, academic leadership and quality assurance, and efficient commissioning processes. The Triangle Model concept is designed to deliver multifaceted benefits to FCDO. It will help ensure that research agendas are strategically aligned and informed by expert input, enhancing the relevance and impact of the research. High standards of academic rigour through structured reviews and quality assurance processes, will ensure methodological robustness. By leveraging best practices, the model will focus on efficient commissioning processes, enabling quick responses to FCDO’s needs and delivering high-quality research at pace. It also supports equitable partnerships, ensuring diverse and representative voices in research teams. Furthermore, the model enhances research uptake and dissemination, ensuring outputs are widely shared, accessible, and utilised by policymakers and practitioners. Overall, the RCC Triangle Model has potential to strengthen collaboration, foster innovative research, and position the RCC as a central link for FCDO’s research commissioning efforts, if combined with enhanced cost effectiveness.

Visualisation of the Triangle Model

To better define the VfM proposition of the Triangle Model, the RCC has started developing a 'sliding scale' approach. This approach aims to identify key variables that impact VfM benefits, ranging from simple grant delivery to complex partnerships. Further refinement of this approach will continue in the coming year.

Visualisation of the ‘sliding scale’ model

Assessment of whether the programme continues to represent value for money

Given the slow delivery pace of the programme in Year 1, the core elements of the RCC operational framework were only finalised towards the end of Year 2. This includes value for money framework and indicators which will allow to undertake a more rigorous VfM assessment in the coming year.
Based on the expected outputs and milestones the RCC has demonstrated strong performance across the following key delivery areas:

- High quality final outputs published and presentations delivered at academic forums.
- Strong representation and engagement in sector groups and networks to drive innovation and best practice
- Significant involvement of Global South researchers and institutions in shaping RCC commissions and delivering research
- Launch of the Impact Fund pilot and positive user experience with the Grant Management System.

The RCC has embedded VfM principles across its operations to drive economy, efficiency, effectiveness, equity, and cost-effectiveness by adopting:

- Use of benchmarked rate cards for staff and consultants.
- Standardised budget templates and financial reporting tools.
- Inclusion of Global South partners in research commissioning and peer review.
- A comprehensive VfM framework and checklist for systematic tracking and assessing VfM
Based on the conceptual framework, the programme has strong potential to deliver value for money if the triangle model and sustainable costing structure are fully developed, so the RCC can establish a competitive edge to secure a sustainable demand from FCDO in the long-term. Scenario modelling shows the RCC increasing cost-efficiency over time, if the demand for commissioning increases. More precise calculation and analysis will be conducted once baseline data and VfM targets are fully established and bespoke tracking process for cost recovery is fully implemented by the RCC. As programme matures and more research is fully completed, FCDO will be able to objectively assess whether the RCC can deliver research efficiently and in a cost-effective way. The introduction of Grant Management System and the development of the VfM framework reflect strong commitment by the RCC to drive VfM.

Progress on recommendations from the previous AR

Recommendation	Progress	Status
Expand the triangle model to set and deliver research commissioning and management vision and objectives	RCC have developed approach for building on best practice and lessons learned, and shared slide deck with FCDO in May 2025 on how to incorporate this work into the Delivery Models work.	Completed
Formalised value for money assessment on core RCC staff and downstream partners	Completed document summarising approaches for assessing VfM of downstream partners, shared with FCDO May 2025.	Completed

E: RISK

Overview of risk management

RCC’s approach to risk management involves regular monitoring and proactive mitigation strategies. The RCC risk register currently tracks 41 live programme-level risks. Of these, 8 are classified as major and 1 severe. These mainly relate to fiscal uncertainty, which can reduce FCDO research pipeline, and increased pressure to demonstrate the VfM of the RCC model. Ultimately, these risks can have negative impact on achieving the intended outcomes and impacts by the programme. In addition, new risks relate to the implications of use of AI tools and GDPR data compliance for research quality and integrity. In response to those risks, initial language on AI will be included in downstream agreements and robust metrics will be implemented to drive decision-making on VfM. Given the challenges yet to be overcome, the programme’s overall risk rating remains Major.

Quarterly risk reviews are conducted, and a new Delivery Chain Risk Mapping tool has been piloted to enhance visibility and accountability across the RCC delivery chain. All grantees are required to submit project-specific risk registers, ensuring early engagement with potential risks. Risk reporting is integrated into the GMS for continuous oversight and adaptive management throughout the project lifecycle.

Data Protection Impact Assessments (DPIA)
Two DPIAs were completed: one for the GRTD website and another for the GMS portal, in collaboration with 3ie and SmartSimple, the platform provider. The assessments categorised personal data into two streams: data collected directly via the GRTD website (e.g. mailing list subscriptions, contact forms) and data processed through the GMS. The Office of the Data Protection Officer assessed that the processing activity can go ahead as the level of compliance is acceptable and risk responses, measures and the level of residual risk are acceptable.

Review of the risk appetite across FCDO risk categories

Risk Category	Risk Appetite	Residual Risk Level	Summary
Policy and Programme Delivery	Receptive	Minor to Moderate	The RCC has maintained a moderate risk appetite for operational delivery, focusing on efficient and high-quality research commissioning. Residual risks have been managed through robust quality assurance processes, regular monitoring, and adaptive project management.
Financial and Fiduciary	Cautious	Major	The RCC has a low-risk appetite for financial management risk, prioritising transparency and accountability. Residual risks have been driven by uncertainties in the financial model and delays in budget approvals, mitigated through detailed financial tracking and regular reviews.
Reputational	Cautious	Moderate	The RCC has a low-risk appetite for reputational risks, aiming to build trust and credibility. Residual risks have been influenced by the changing aid landscape and the need to demonstrate value for money, addressed through proactive stakeholder engagement and communication.
Public Service Delivery & Operations	Cautious	Minor	The RCC has a low-risk appetite for compliance risks, ensuring adherence to policies and regulations. Residual risks have been managed through comprehensive due diligence processes and regular compliance checks.
Safeguarding	Cautious	Minor	The RCC has a low-risk appetite for safeguarding risks, prioritising the safety and well-being of all stakeholders. Residual risks have been mitigated through updated safeguarding policies and training.
Strategy and Context	Receptive	Moderate to Major	The RCC has a receptive risk appetite for strategic and contextual risks, focusing on long-term impact and sustainability. Residual risks have been driven by uncertainties in the pipeline and strategic direction, mitigated through regular strategic reviews and adaptive planning.
People	Cautious	Moderate	The RCC relies on strong technical support and business continuity to ensure effective management of and oversight of grants. Roles assigned to the RCC have been carefully reviewed resulting in increased programme management capacity to ensure effective delivery. However, building a new brand and effective delivery model at times of fiscal austerity will require building motivation and sense of identity to keep high morale and reduce risk of staff turnover.

Trends in risk exposure and response

The main trends in risk exposure and response over the last year for the RCC have been driven by several factors:

- Increased Financial and Fiduciary Risks: There has been a notable focus on financial management, with risks related to economic sustainability of the RCC. This trend is driven by external pressures, such as aid budget reductions and shifts in donor priorities, to strengthen value for money strategies and costing model to enhance RCC’s financial resilience.
- Operational and Capacity Challenges: The RCC has faced challenges related to recruitment delays, staff turnover, and capacity to meet FCDO demand in the first part of the reporting period. These have been addressed through ongoing recruitment efforts, restructuring, and flexible delivery models to manage workload and expectations, under a dedicated leadership of a new RCC Managing Director
- Reputational and Compliance Concerns: There is a heightened awareness of reputational risks, particularly concerning conflicts of interest, ethical research conduct, and engagement with sanctioned groups. This has led to the development of comprehensive policies and regular reviews to ensure transparency and compliance.
- Strategic and Contextual Risks: The RCC has been adapting to strategic shifts, such as potential changes in FCDO priorities and geopolitical uncertainties. This has involved strengthening policy engagement and maintaining flexibility in programme delivery to align with evolving strategic directions.
- Technological and Data Management Risks: With the increasing reliance on digital platforms and AI, there are emerging risks related to cybersecurity and data integrity. The RCC has responded by implementing stringent cybersecurity measures and developing guidelines for ethical AI use.

Overall, the RCC's risk response has been proactive, with a focus on enhancing financial management, ensuring compliance, and maintaining flexibility to adapt to changing external conditions. These efforts are supported by regular communication with stakeholders, including FCDO, and continuous monitoring of the risk landscape.

Progress on recommendations from the previous AR

Recommendation	Progress	Status
Implement a clear risk escalation process and conduct a review of the risk register and risk management process	Review of risk register and risk management process completed, with agreed reporting structure and escalation process shared in May 2025.	Completed

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues

The RCC has continued to strengthen its programme management systems and processes during Year 2, supporting the delivery of a growing and increasingly complex research portfolio. The RCC’s management approach is underpinned by clear governance, robust financial management, and a commitment to continuous improvement.

Governance and Oversight:
The RCC Steering Group, with updated Terms of Reference, provides strategic oversight and direction. Regular engagement with FCDO SROs and technical leads ensures alignment with FCDO priorities and enables rapid decision-making. The RCC has also established new engagement structures with consortium partners, including targeted working groups and regular portfolio reviews.

Operational Delivery:
The RCC has implemented standardised project management tools, including Project Overview Documents, SEEPs (Stakeholder Engagement and Evidence Uptake Plans), and a Master Tracker for all live and pipeline projects. The launch of the SmartSimple Grant Management System (GMS) has streamlined project administration, with 87% positive user feedback and improved efficiency in grant processing, reporting, and risk management.

Consortium Management:
A review of consortium engagement led to targeted reforms, including the expansion of Global South membership and clearer roles and responsibilities. The RCC has prioritised equitable partnership practices, with 72% of projects including LMIC/Global South researcher(s) and three grants led by Global South institutions.

Financial Management:
Ongoing reviews of resources and consolidation of roles have been undertaken to improve financial management and cost-effectiveness. A standardised budget proposal template has also been introduced to ensure costs are applied consistently and in line with the RCC agreement across all projects. Moving forward, the RCC will update its financial coding and reporting systems to improve tracking of spend against budgets and better alignment with FCDO requirements. Structured budget templates and cost policies have been rolled out to FCDO teams and downstream partners, and benchmarking of staff and consultant rates has been introduced to ensure value for money.

The total spend on RCC Management and Technical Expertise for FY24/25 was £1,400,000. This was an increase of about £73,000 (considering £150,000 underspend on the previous year) on the original £1,173,000 allocation. In 25/26, this allocation is forecast to increase by £652,183 to £1,650,000 when compared to the original proforma budget. This figure includes a 14% reduction of costs from the initial forecasts for FY 25/26.£115,000 of expected costs are forecast to be recovered through external Business Cases commissions. An additional £61,000 is linked to pending external business cases. If the pipeline is realised, then this would mean a potential total of £176,000 could be recovered in 25/26 representing a 10% recovery rate. It is anticipated that the recovery of management costs will be on the upward trajectory, towards a fully sustainable model in the future.

RCC	Original allocation 24/25	RCC spend in 24/25	Forecast 25/26
Cost Category	£	£	£
RCC Management (including website and GMS)	623,000	1,050,000	1,180,000
Technical Experts	550,000	450,000	470,000
Research funded from the core RCC Business Case	3,500,000	500,000	1,650,000
Research funded from external Business Cases	0	750,000	1,200,000

This significant increase reflects the addition of new roles and the expansion of existing ones to enhance the RCC's capacity, greater investment into GRTD website, management system, dissemination activities and significant increase in research commissions of which the EIPM has been most significant. The new increased RCC capacity allowed to accelerate progress and implementing of improvements in FY24/25. The new roles include: a full time RCC Managing Director, 3 x Senior Research Specialists, Programme Manager, HR Manager, Finance Manager and Compliance and Contracts Manager. At the same time some leadership costs reduced whilst communication roles have been consolidated to drive savings.

Assets
During the reporting period 24/25 the RCC has procured 8 laptops of a combined value £12,300 for staff working more than 50% FTE on the programme. The record has been maintained up to date through the RCC Asset Register.

Delivery Chain Risk and Issue Management:
Programme-level and project-level risks are tracked through a live risk register, with quarterly reviews and escalation protocols in place. The new Delivery Chain Risk Mapping tool has been piloted to strengthen risk management across the consortium and delivery partners In total £3,940,000 has been agreed to be distributed across more than 35 downstream partners, of which 25 are universities and institutes (this includes funding from both RCC and external business cases).

Responsiveness and Agility:
The RCC has demonstrated agility in responding to FCDO pipeline requests, with 100% of requests responded to within five working days. Fast-tracked commissioning, sole-sourcing, and process improvements have enabled the RCC to adapt to changing needs and funding environments.

IATI Compliance:
The programme has maintained compliance with FCDO’s IATI reporting requirements, supporting transparency and accountability by publishing data quarterly. Moving forward, the programme will continue to monitor data quality and efficiency, further integrating IATI reporting into routine management systems such as GMS to uphold transparency in development cooperation and strengthen internal processes for data capture and verification.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring
Throughout the review period, the RCC conducted monitoring activities, including gathering feedback from FCDO teams, consortium partners, grant holders, and applicants. Feedback was systematically collected through surveys at key milestones, regular meetings, and consultations. FCDO’s RCC team provided input via monthly operations and finance meetings, quarterly risk sessions, and annual away days, where strategic discussions and reviews of RCC progress took place. Grant holders submitted project-specific risk registers and SEEPs, ensuring early engagement and continuous monitoring. Applicants were surveyed post-application to capture their experience and suggestions for improvement. Insights from these feedback mechanisms informed programming decisions, leading to process refinements, enhanced communication strategies, and adaptive project management. Actions from RCC away days included the establishment of improved governance structures, strategic planning for the RCC model, and the development of a comprehensive engagement framework to strengthen relationships with FCDO and consortium partners. These activities ensured that the RCC remained responsive, adaptive, and aligned with its strategic objectives, whilst a comprehensive stakeholder engagement mechanism helps maintain effective communication and collaboration with key stakeholders.

Evidence
Reflecting a commitment to - and evidence on the value of - engaging researchers based in the Global South, the programme has successfully grown the number of applications from Global South institutions (95) and their participation in evidence generation. (72% of projects). including at least one LMIC or Global South researcher and 95 applications This enriches the evidence base with diverse perspectives and contextual expertise, enhancing the quality and relevance of the research outputs.

Learning
The RCC's learning mechanism involves continuous feedback collection from key stakeholders, including FCDO RED teams, applicants, grant recipients, and consortium members. Strategic sector engagement and internal reviews help refine processes and policies. Tools like the Master Tracker and Project Overview Document consolidate project data, while the Lessons Learned Tracker ensures systematic capture and addressing of learnings, leading to continuous improvement and enhanced impact.

Progress on recommendations from the previous AR

Recommendation	Progress	Status
Build a monitoring framework and establish a comprehensive approach to collecting and responding to feedback from stakeholders	Monitoring framework: Logframe and accompanying monitoring framework approved by FCDO. / Approach to stakeholder feedback: RCC has developed separate approaches for feedback from FCDO, applicants and grant recipients.	Completed

Date of last narrative financial report	June 2025	Date of last audited annual statement	31 December 2024

Annex A – Progress against annual review recommendations 24/25

Annual Review Recommendations 2024/25	Status (May 2025)	Update
Design and implement a proportionate strategy that mainstreams diversity and inclusion throughout the portfolio / It is a cross-cutting priority to ensure diversity of opportunity, access to, and delivery by a diverse range of partner institutions and individuals, complementing the Southern Engagement Strategy. The RCC will report disaggregated output achievements by age, sex, disability, geography, and other relevant characteristics where it is possible to do so. The RCC will make impactful changes and adaptations to processes, management, and delivery to ensure inclusion at all levels, facilitating the delivery of a diverse portfolio of projects and partners, and achievement of stronger outcomes. This work can build on FCDO’s more recent gender and disability portfolio reviews.	Completed	RCC developed Equity, Diversity and Inclusion (EDI) Strategy, and Southern Engagement strategy. In order to consider specific actions for the RCC, the Equity Action Plan (EAP) has been developed to identify areas of action across the RCC model.
Design and implement a partnership-level agreement / The RCC should develop a robust and deliverable partnership-level agreement (PLA). This could cover types of support (both commissioning and technical support); indicative response times, delivery timescales, and regularity of updates to communicate progress. Communication routes, respective expectations, and roles (for the RCC and for FCDO teams), and points of contact should also be set out, including for any engagement, escalation, or queries outside of the PLA. FCDO will share robust examples of SLA/PLAs.	Completed	RCC developed draft PLA in December 2024, and following feedback converted this into a Project Overview Document (POD).
Develop and agree on delivery of the Open Access and Impact Fund / This is a core deliverable outlined in the statement of need and budgeted for within the business case. The RCC team should set out and agree with FCDO a delivery plan for the Open Access and Impact Fund that meets the statement of need (including any updated requirements).	Complete	RCC reviewed existing initiatives and developed pilot phase of Impact Fund- first call went live in May 2025. Open Access Fund awaiting FCDO approval to proceed.
Improve calendar of engagement with FCDO’s research teams and communicate successes effectively / To more effectively assess and set expectations, meet demand, and ensure clarity of delivery and roles and responsibilities across the RCC team and FCDO research teams, a calendar of engagements and activities (e.g. in-days, away days, and updates) should be developed by the FCDO and the RCC team and delivered (also related to Output 5). Communications from the RCC should focus on sharing success stories (where sensitivities allow) or progress, such as contracts being signed.	Completed	RCC has implemented an improved communications framework with FCDO, shared May 2025, together with clear reporting structure.
Expand the triangle model to set and deliver research commissioning and management vision and objectives / The RCC should build on best practices and lessons learned from across the sector, to construct processes and templates that reduce bureaucracy and address FCDO needs and priorities, and assurance requirements. This will require close collaboration and engagement with the reducing research bureaucracy agenda as well as other expert commissioning and research management practitioners, and strong engagement with FCDO teams, to share and align approaches and agree expectations, where possible. A key indicator of success for this objective will be negotiating a balance between reducing research bureaucracy and meeting FCDO assurance requirements, which have proven challenging in the inception year.	Completed	RCC have developed approach for building on best practice and lessons learned, and shared slide deck with FCDO in May 2025 on how to incorporate this work into the Delivery Models work.
Build a monitoring framework and establish a comprehensive approach to collecting and responding to feedback from all stakeholders / In line with the existing requirement, a monitoring framework that collates results and measures success at both programme and projects level, including feedback from FCDO, applicants and grant holders. An RCC Workplan should be used alongside log frame to monitor and assess progress. Payments to downstream partners need to be clearly linked to performance standards and expected deliverables across the delivery chain, as a key mitigating measure against poor performance. Additionally, the RCC should develop a systematic process and mechanism for gathering and implementing actions based on feedback at different stages of the commissioning and research management process (from both FCDO and researchers). The RCC should undertake similar approaches toward feedback from the consortium. These approaches should be both proportionate and strategic in order not to unduly burden stakeholders or create additional bureaucracy.	Completed	This was split into two activities in the 2024/5 RCC workplan. / Monitoring framework: Logframe and accompanying monitoring framework approved by FCDO. / Approach to stakeholder feedback: RCC has developed separate approaches for feedback from FCDO, applicants and grant recipients.
Agree and deliver a vision for the role of the consortium / The RCC consortium members and the academic directors should collectively agree core benefits and a role for the consortium; that enables influence and contribution to the delivery of RCC objectives. A more purposeful, targeted, and objectives-driven engagement strategy should be developed, to support multifaced delivery that benefits and is enhanced by collaboration with the consortium and wider sector. As part of this strategy, the RCC will develop the partnership principles that set standards for its collaboration with FCDO and downstream partners.	Completed	Consortium review conducted December 2024-March 2025, and subsequently agreed to move forward with a targeted consortium approach.
Develop an RCC roster of experts / The RCC will develop a roster of experts in key areas of focus, beyond the consortium, to improve rapid access to diverse, trusted, and high-quality expertise. This had been recommended as an action to take forward by the RCC during the RCC Away Days in November 2023.	Not initiated	Agreed with FCDO to remove from workplan in February 2025.
Ensure adequate capacity and oversight of the new digital platform / The RCC is expected to launch an MVP website, under a new FCDO R&D brand, by end of 2024. The RCC needs to promptly address any capacity gaps to ensure the website is designed, built, and tested on time. Any issues, slippages, and additional resourcing needs within the workplan to be promptly escalated to FCDO.	Completed	Beta website launched January 2025, content management system training held with FCDO in April 2025 and options presented for further development and oversight.
Develop a GRTD Communication Plan / A GRTD process for collating and publishing impact stories and results from the FCDO full R&D portfolio needs to be fully developed and incorporated into a broader GRTD communication plan.	Completed	A GRTD process to maintain MVP communication has been agreed between FCDO and RCC to maintain a regular pipeline of communication pieces. More detailed communication plan will be developed once a GRTD programme funded strategic comms lead is in place.
Formalised value for money assessment on core RCC staff and downstream partners / FCDO notes that the RCC does not apply pre-agreed rates for the core RCC staff across all projects, which has potential to reduce overall programme VfM. This will need to be addressed in collaboration with FCDO given the goal of rapid and agile research commissioning and the need to deploy resources in an efficient and timely manner. Additionally, the RCC should continue to build a systematic approach to assessing VfM on budgets supplied by partners.	Completed	Completed document summarising approaches for assessing VfM of downstream partners, shared with FCDO May 2025. Approach agreed with FCDO for staff rates.
Design and implement value for money metrics Value for money metrics to measure efficiency and effectiveness will be developed by the RCC within the next quarter. A range of indicators (with a focus on progress against the outcomes) will be established, to ensure the RCC delivers the expected outcomes.	Completed	VfM Framework and metrics developed with FCDO Economist in June 2025
Shifting FCDO input to strategic direction and oversight / Recognising that too much reliance on FCDO input can create additional management and stifle innovative approaches to delivery, the FCDO will step back from support to operational delivery in year two, focusing instead on setting strategic direction, whilst ensuring the required programme assurance is in place to ensure robust risk management, progress against workplan and delivery of targets within the log frame. To achieve this, a new FCDO/RCC meeting schedule will be developed to ensure more effective operational and strategic oversight.	In progress	Some improvements made to reporting structures, but shifting aid landscape and questions on financial model preventing further progress.
Implement a clear risk escalation process and conduct a review of the risk register and risk management process / The RCC should develop a clear escalation process to report and manage issues to allow the FCDO being notified as soon and effectively as possible. Project risk rating and issues will need to be clearly incorporated within the RCC project.	Completed	Review of risk register and risk management process completed, with agreed reporting structure and escalation process shared in May 2025.
Standardise RCC Terms of Reference template with core clauses included / In the absence of sperate agreements signed between the FCDO research teams and the RCC, a RCC Terms of Reference template, including standardised clauses, such us payment by results, budget, and process for virements, communication and reporting arrangements etc. In addition, there will be one RCC Partners Level Agreement (PLA) to monitor RCC’s overall performance against KPIs (e.g. quality, responsiveness, timely delivery etc.).	Completed	Created Project Overview Document (POD) in place of standardised ToR