Programme Title	Human Rights and Peacebuilding Programme (HARP)
Directorate/ Post	Africa/ Addis Ababa	Contact name	Oliver Russell
Original programme budget	£41,000,000	Country or region targeted	Ethiopia
Cost extension value (if applicable)	NA	Original BC approver (Minister, DG, HoM, Director, Dep. Director)	Minister
New increased or reduced programme budget (if applicable)	N/A	Original programme start and end dates	01 Jan 2021 – 31 March 2027
Latest AR programme score	B	New programme end date (if applicable)	31 December 2027
		Programme ID	301191

A brief summary of the programme and its purpose, as approved in the Business Case - noting any caveats from Minister/approver at CN or BC approval stages. / Describe what the programme has achieved so far and what lessons have been learned. / Programme summary / The Human Rights and Peacebuilding Programme (HARP) was set up in 2021, to contribute to a reduction of violent conflict and help enable the conditions for peaceful political transition in Ethiopia by addressing three of the main dimensions of Ethiopia’s instability: political tensions, inter-communal violence, and human rights violations. / HARP has four programme components and associated outcomes: / Reduce violence and support peace processes: sustained peace and conflict resolution processes make progress towards the non-violent management or resolution of armed conflicts / Promote women peace and security (WPS): increase in representation of women and girls in conflict-affected communities/regions of Ethiopia participating in and influencing peace process and recovery initiatives / Improve accountability for human rights and support transitional justice processes: Increased domestic and international capacity to address and reduce human rights abuses and violations / Strengthen conflict related policy and programming: conflict analysis, research and conflict sensitivity advice/support leads to improved engagement and understanding of conflict and conflict sensitivity by HMG and national and international actors / To date, HARP key achievements include: / Supporting the demobilisation of combatants to progress the implementation of the Pretoria Agreement in Tigray (45,000 combatants up to July) / Facilitating dialogue initiatives in Somali and Oromia regions. Including supporting mediation of talks between the Government and Oromo Liberation Army (OLA) / Helping survivors of sexual and gender based violence (SGBV) and conflict related sexual violence (CRSV) rebuild their lives in Tigray, Afar and Somali region. Including by creating the framework for victim’s emergency reparations agreed by the Somali Regional Government and supporting 18 women’ groups in Tigray and Afar to shape local recovery from conflict. / Empowering women and women-led organisations to advance the WPS agenda in Ethiopia, advocating for the WPS National Action Plan, influencing national policy and support women to be lead grassroots peacebuilding. / Strengthening the Ethiopian Human Rights Commission (EHRC), especially their monitoring and investigations capacity and establishing UNOHCHR-led early warning networks in human rights hotspots across the country / Establishing the Peace Research Facility (PRF) which has produced and disseminated more than 17 reports, 22 briefing/responsive pieces and 4 research covering key peace, security and human rights developments across Ethiopia. / Launching the Ethiopian Women Researchers’ Network (EWNET), a national platform to enhance the visibility, participation, and leadership of women in research and policymaking. / HARP’s 2024 and 2025 Annual Review identified several lessons: / Shrinking civic space is limiting civil society’s ability to monitor human rights and advocate effectively. Alternative delivery approaches may be needed. / Given the complexity of the operating context in Ethiopia for conflict and human rights related work, a programme like HARP needs to continue to be flexible and adaptive. / Barriers to women’s participation in peace and recovery processes remain significant, with key milestones unmet. / Conflict sensitivity and real-time analysis have proven valuable in informing UK engagement and should be further leveraged.
Has the programme been amended previously? If so - provide a brief overview of dates of changes and purpose of changes. / What is the objective or purpose of making this change? What are the drivers of that change (eg. context change, under-performance of programme or partner). / How will the programme deviate from the original business case? How significant is the change (be clear if this is a material change which requires re-approval)? Where there is a material change, describe that change and the overall impact you expect it to have. / Describe the change(s) to the programme outcome(s), including any adjustments required to the theory of change and VfM assumptions. / Is there any new evidence from ongoing monitoring, evaluation or learning work which supports/justifies making the change? / In proposing a cost extension, are there any trade-offs or choices that you have considered including If the programme was not extended, what might be done with the funds instead? What is the rationale for the choice between these options? / Are there other activities within your portfolio that would need to be cut back or curtailed as a result of extending this programme / Programme amendments and adaptations / HARP was specifically designed to be scalable and to adapt to the conflict context and stability risks in Ethiopia. HARP was previously extended in 2024 to respond to the Cessation of Hostilities Agreement in Tigray, and evolving conflict dynamics. The programme budget was increased by £36.5 million (41m in total). 16m of this budget increase was to support Disarmament, Demobilisation and Reintegration (DDR) in Northern Ethiopia, with the rest supporting conflict and dialogue processes in Oromia, the rise of conflict in Amhara and parts of Somali region and critical challenges in the human rights context. / HARP is seeking a no-cost time extension from 31 March 2027 to 31 December 2027 to mitigate risks of conflict and instability around the 2026 national elections. Elections are likely to start in summer 2026, but could be staggered for up to 12 months. Extending the end-date for the programme will help accommodate the varied timeframes, and potential slow down in delivery during voting periods. / Funding for the elections is likely to cost 2.7m - during 2025 and 2026. We have reallocated funding away from Transitional Justice (which is currently stalled) and by deciding not to fund DDR beyond the completion of phase one (due October 2025), to prioritize election-related activities, which offer a more strategic path to advancing our CBP objectives by exerting influence on national elections planning and the environment in which they take place to mitigate against elections-related conflict risks. / The change is considered non-material as it reallocates budgets within the programme. Work on elections falls under HARP Objective 1: “Reduce violence and support peace processes: sustained peace and conflict resolution processes” / The Programme outcomes are unchanged, but Outcomes 1 and 4 will be strengthened as detailed in the table below. / Outcome Description Programme changes which strengthen this outcome How it will be strengthened / 1 Reduce violence and support peace processes: Sustained peace and conflict resolution processes make progress towards the non-violent management or resolution of armed conflicts New activities within the programme will contribute to: / 1. Strengthening the resilience and capacity of the National Electoral Board of Ethiopia (NEBE) to independently, peacefully and transparently manage a broadly inclusive elections process; / 2. Support civil society coalitions to provide voter education, encourage voter registration and observe the process; / 3. Support platforms for inter-political party dialogue and coordination. Countering systemic exclusion, supporting political participation of marginalised groups, and ensuring civic actors have a voice in shaping political settlements through these activities will reduce the risk of elections-related violence and prevent elections stoking wider conflict or undermining existing national and regional peace efforts. / 4 Strengthen conflict related policy and programming: Conflict analysis, research and conflict sensitivity advice and support leads to improved engagement and understanding of conflict and conflict sensitivity by HMG and national and international actors. Conflict and political economy analysis produced by existing HARP partners will be extended to cover elections-related work. Actions by the UK and the broader international community will be informed by an increased understanding of the ways in which election-related activities might exacerbate existing conflicts or potentially ignite new violence. / Evidence and programme learning / This case for this adjustment is supported by recent HMG analysis and recent electoral history in Ethiopia. The May 2024 JACS update drew out the potential links between elections and conflict. The disagreement in 2020 over the one-year postponement of national elections was a proximate cause to the outbreak of the two year war in Tigray and northern Ethiopia. / The proposed set of interventions are grounded in recent evidence from UK funded programmes in Ethiopia. A review of previous election programming concluded that the programme had contributed to NEBE’s emerging institutional resilience and ability to run near-nationwide elections in 2021 in a politically restricted and conflict-affected environment. / Secondly, evidence from past UK-funded CSO programmes show that well-coordinated CSO coalitions can effectively raise awareness, monitor progress, and strengthen government–citizen interaction; supporting CSO coalitions to work on elections could make an important contribution to publicly accepted and peaceful elections in 2026. / Finally, ISF-funded support to opposition political party dialogue has proven effective in building operational capacity, encouraging participation in national processes (e.g. national dialogue), and fostering issue-based engagement. Contributing to intra-party initiatives will be important for the genuine participation of opposition parties in 2026 elections. / Value for Money / As set out in the HARP Business Case, HARP’s overall goal for delivering Value for Money (VFM) is to make the best use of HMG resources to enable quality, evidence-based interventions that make as great a contribution as possible towards reducing levels of violent conflict and opening space for peaceful political transition in Ethiopia. The proposed changes strengthen the overall VFM by increasing the economy, effectiveness and equity of the programme. On economy, HARP will be better positioned to deliver results which reduce levels of violent conflict by adapting the programme to respond to the immediate political context and reallocate resources to address the risk of conflict around the elections. On effectiveness, the integration of election support under outcomes 1 and 4 is expected to strengthen peacebuilding and conflict prevention by countering systemic exclusion, supporting political participation of marginalised groups, and ensuring civic actors have a voice in shaping political settlements. On equity, the proposed change focuses on inclusive electoral processes, supporting civic education, voter engagement, and participation of marginalised groups, especially women and People with Disabilities.
Describe how the change(s) to the programme will be implemented. / Will changes be required to the existing management arrangements as a result of the amendments to the Business Case? / Budget and Implementation / The indicative budget breakdown for election-related activities is given below. / Total / Description Mechanism FY25/26 FY26/27 FY27/28 / Funding to CSO coalitions Accountable Grants 600,000 300,000 900,000 / Targeted funding to NEBE through UNDP MoU SEEDS2 1,200,000 300,000 1,500,000 / Political Parties Accountable Grant 200,000 100,000 300,000 / Sub Total (elections component) 2,000,000 700,000 0 2,700,000 / The contracting modalities for the new projects will include an MoU with UNDP, which administers the only pool fund currently available to channel HMG support to NEBE. Additionally, Accountable Grants will be established with CSO coalitions and to support inter-political party platforms to be more inclusive of local actors. / The HARP programme is managed under the oversight of a Senior Responsible Owner (SRO), who provides technical guidance, and a Programme Responsible Owner (PRO), who ensures effective implementation and coordination aligned with the Theory of Change. A Deputy Programme Manager supports overall programme oversight, while a CBS and UKB programme funded conflict Advisor contribute thematic expertise. Two Programme Officers handle day-to-day programme operations. / As part of this programme extension, we will add 1.5 FTE equivalent governance advisers to HARP from current PolGovComms team, who will join the Advisory Team, enhancing PRO oversight and providing local expertise on elections and civil society.
For cost extensions, set out the pre/post amendment finance profile over the life of the programme including: / original budget / total amount already spent / amount of cost extension / revised total(s) / Confirm that any cost extension is financially affordable within the Post/Directorate allocation, i.e. where will the Post/Directorate find the funding for any cost extension, and whether the proposed cost extension will take the programme beyond this SR period? (See Section 5 of the PrOF Guide to Programme Approvals for further guidance. / Budget
Impact / Impact of cost/time extensions on VfM: / ☒ Positive impact – Business Case delivery ambition is being increased at the same time as the time extension. / ☐ No impact – no/negligible change to Business Case delivery ambition. / ☐ Negative impact – decrease in Business Case delivery ambition.
Describe any new key risks arising as a result of this change. How will they be mitigated? / Risk / The overall programme risk level will remain classified as Major, with a receptive risk appetite. However, the inclusion of elections support within the programme introduces a new set of risks. These new risks are outlined below. / Strategy & Context / Conflict and Security (Major): Ongoing violence in Amhara and Oromia, and the risk of renewed conflict in Tigray or the region, could disrupt and undermine elections or prevent them from happening in some areas. / Mitigation (Major): The programme supports NEBE in conflict-sensitive electoral planning, including preparedness for operating in conflict affected areas and the potential use of staggered elections. This is complemented by diplomatic engagement with relevant actors to promote inclusive decision-making and coordination around security and access. While these measures aim to reduce disruption, the overall context remains high-risk due to ongoing conflict and the potential for renewed violence in key regions. / Electoral Legitimacy and Trust Risk (Major): If NEBE decisions on staggered elections and political party registration are not transparent, inclusive, lawful, consistent, and well-communicated, this could create perceptions of political bias, and mistrust and fuel instability. / Mitigation (Major): Higher level diplomatic engagement and closer monitoring of NEBE to ensure careful handling of decisions on staggered elections and political party registrations both through UNDP (as part of the SEEDS2 Project Management Board) and as co-Chairs of the EWG; helping reduce tensions and zero sum thinking by fostering civic education and constructive engagement through the civil society support and political party platforms components of the programme. Nonetheless, the political environment remains volatile, and the risk of electoral disputes escalating into conflict remains. / Civic Space Constraint Risk (Severe): Potential changes in law and policy restricting CSO funding and activities may present a strategic risk to HARP’s ability to contribute to inclusive elections and conflict reduction. These constraints may limit civic and political actors' ability to engage in electoral processes, reducing opportunities for broad-based participation and weakening the programme’s strategic relevance in addressing election-related drivers of conflict. / Mitigation (Major): The UK will reassess its support to the elections to ensure continued alignment with strategic objectives on inclusive elections and conflict reduction, considering the impact of legal and policy changes on civic and political engagement. HARP will monitor constraints on donor-funded work with CSOs and political parties, given their role in mitigating exclusionary electoral processes. The UK will coordinate with UNDP and other partners to track political developments and respond to emerging risks, while continuing advocacy with NEBE and the Government of Ethiopia to preserve space for electoral engagement. Through its leadership in donor coordination, the UK will align messaging to maintain the strategic relevance of its support. / Policy & Programme Delivery: / Changes in CSO law (Severe): If potential changes in law and policy restrict CSO funding and activities, they may block HARP from funding core elements of its election activities —facilitating inter-party dialogue and supporting civic and voter education and election observation through CSOs. This would weaken the programme’s ability to deliver on its objective to reduce the risk of the next elections driving instability in Ethiopia by If changes in law and policy restrict CSO funding and activities, HARP may be unable to support core components of its elections work—such as facilitating inter-party dialogue, civic and voter education, and election observation—delivered through CSOs. This would significantly weaken the programme’s ability to deliver on its objective of reducing the risk of elections contributing to instability in Ethiopia by preventing it from investing in activities that help mitigate tensions around the electoral process. / Mitigation (Major): The UK will closely monitor developments around proposed CSO law changes, particularly their impact on HARP’s ability to fund civic and political engagement. If restrictions do happen, the UK will reassess its support to NEBE, focusing on impacts to transparency, inclusion, and conflict sensitivity. Where feasible, delivery will be adapted with UNDP and NEBE to support NEBE functions still viable under the restrictions—such as public outreach, complaints and dispute resolution, and inclusive legal reform. Given the EU and Germany’s significant investments, through another programme, in the upcoming elections, the UK will coordinate with them to leverage joint financial and diplomatic efforts to work around restrictions and preserve critical partnerships, particularly with CECOE and the EJPPC, essential for inclusive and peaceful elections. / Programme Delivery Delays Due to National Elections (Moderate): The preparation and roll out of national elections, potentially staggered over a twelve month period, will likely distract key programme counterparts and stakeholders especially government ones and disrupt programme implementation including by creating operational restrictions (e.g. sensitivities around activities on peace process support and possible security related travel restrictions). Overall, this could result in slowed delivery across multiple programme areas. / Mitigation (Minor): A programme no-cost time extension to 31 December 2027 will help accommodate potential slow down in delivery during voting periods, especially if elections are staggered for up to 12 months. Additional mitigations will include close monitoring of implementing partners to ensure continued delivery; prioritisation of critical deliverables ahead of the election period to minimize disruption and adjusted implementation timelines to accommodate election-related constraints. Contingency plans will be made to include the option to bring forward next year’s payments for components where spending is feasible. Timely escalation of issues to ensure PDEL can reallocate any unspent funds to other programmes as appropriate.
Describe the new/additional results that you would expect to see from these changes. Outline at what level changes to the results will be seen, e.g. what is expected at outcome or output level? / Review the Theory of Change for the Business Case and outline whether the approach taken is still valid based on the evidence for the BC addendum and whether any updates are needed. / Outline any additional monitoring and evaluation activity that will be needed in the programme as a result of the changes proposed. / Results & Monitoring and Evaluation / The Theory of Change remains valid but requires minor updates to reflect the integration of election-related activities and revised assumptions. This integration is expected to deliver additional results at the output level and enhance results under existing outcomes and overall impact. At impact level this will include contributing to broad stakeholder acceptance of the electoral process, reducing the risk of violent contestation around the elections and mitigating risks of greater national instability. / Indicative results per planned elements of electoral support are: / NEBE will be better placed to increase the predictability of the electoral calendar, and conduct early training of voter registration staff, conflict-sensitive planning and risk-monitoring around decisions on staggering for the 2026 elections. / Selected CSO coalitions will be better equipped to contribute to transparent and inclusive elections through voter education, election observation, advocacy and protecting civic space. / Support to the facilitation of inter-party dialogue contributes to participating parties’ improved internal party governance, increases the likelihood of more peaceful and issues-based campaigning by them, and their engagement in resolving electoral disputes through dialogue, and greater diversity among candidates. / The logical framework will be updated to reflect the context of conflict and stability risks around elections and ensure robust measurement of results of new interventions. / Suppliers will report quarterly on spending and progress against milestones. The programme team will review and assure data quality, while BE Addis will engage in oversight of multi-donor programmes. The governance advisors will also use donor coordination groups, including the EWG co-chaired by the UK, to monitor risks. BE Addis will lead annual reviews and a Programme Completion Review in 2027 (or later), documenting lessons to inform future programming and potential programme extensions. Additional monitoring will include means of escalation to ensure that if strategic or delivery risks materialise, senior decision-makers—including the Policy Board, Delivery Committee, and SLT—are engaged to guide programme adjustments and election support decisions.
[note] “Conflict sensitivity needs to be applied across all UK activities and engagements in Ethiopia including UK finance for basic services through Government systems, support for elections, peacebuilding, humanitarian aid and our diplomatic engagements with the Government. Any of these have the potential to exacerbate tensions and fuel divisions leading to violence.” Ethiopia JACS, May 2024, paragraph 34

REVISED August 2025