## Annual Review
Title: Human Rights and Peacebuilding Programme (HARP)
Programme Value £ (full life): £41 Million		Review date: November 2025
Programme Code : 301191	AMP start date: 21/01/2022	AMP end date: 31/12/2027

Summary of Programme Performance
Year	2022/23	2023/24	2024/25	2025/26	2026/27	2027/28
Overall Output Score	A	A	B	A
Risk Rating	Major	Major	Major	Major

DevTracker Link to Business Case:	Business Case; Business Case Addendum
DevTracker Link to results framework:	Log-Frame

Note – a list of acronyms and alphabetisations can be found at Annex 1

A. SUMMARY AND OVERVIEW
Description of programme
The Human Rights and Peacebuilding Programme (HARP) was set up in October 2021. It aims to reduce violence, protect civilians, and facilitate an inclusive transition out of conflict by addressing three key dimensions of Ethiopia’s instability: (1) political drivers, including competition for regional and national power during the transition; (2) inter-communal tensions, rooted in territorial disputes, competition for natural resources, and inequalities; and (3) the human rights crisis, characterized by widespread violations of international human rights law.
The HARP Business Case was approved initially in November 2021 with a budget of £4.5m until March 2024 and was extended till 31 March 2027 with an increase in budget of 36.6m, bringing the total to £41m. The programme has been further extended till 31 December 2027 to add projects to mitigate risks of conflict and instability around the 2026 Ethiopian National Election.
HARP takes a flexible and responsive approach to programming in a complex political context. The business case has four main objectives.
I. Reduce violence and support peace processes - support structures and processes to facilitate and implement peace agreements and sustainably resolve violent conflicts between communities, amongst regions and nationally. Currently, there are three projects under this objective.
- National Demobilisation and Reintegration (UNDP) £16M: Facilitates the demobilisation and reintegration of ex-combatants in Northern Ethiopia, laying the groundwork for long-term peacebuilding.
- Peace by Piece (CR - Conciliation Resources) £4.5M: Advances inclusive peace in Somali, Afar, and Oromia through research and dialogue, in partnership with local actors.
- Mediation and Dialogue (HD- Centre for Humanitarian Dialogue) £987K: Promotes peace agreements in Oromia through inclusive dialogue processes, ensuring representation of diverse stakeholders, including women.
II. Improve accountability for human rights and support transitional justice processes: - provide financial and technical support for monitoring and investigation of human rights abuses, strengthen national institutions, and contribute to a credible transitional justice process. The following programme component delivered under this objective
- Human Rights Monitoring (UN OHCHR) £1.8M: Conducts joint investigations with EHRC (Ethiopian Human Rights Commission) to address violations, report gaps, and reinforce monitoring capacity in hotspot regions.
- Strengthening EHRC £3.5M: i) through DIHR (Danish Institute for Human Rights): Enhances EHRC’s capacity to promote and protect human rights in collaboration with state and non-state actors ii) through CIR (Centre for Information Resilience): Builds a network for open-source investigations, covering gender and minority rights, and addressing technology-facilitated gender-based violence.
- Centre for Information Resilience (CIR) £1M: aims to contribute to a sustainable and joined up network of open-source stakeholders across the Ethiopian Human Rights Commission (EHRC) and civil society representatives operating in the human rights reporting space, that can independently and more safely lead digital investigations, including coverage of gender and minority rights, and enhance awareness and response efforts addressing technology facilitated gender based violence (TFGBV) within the Ethiopian online information environment.
III. Promote women peace and security (WPS) - increase women’s participation, leadership and representation in political dialogue, conflict resolution and response to violence and conflict, especially its impact on women and girls, including survivors of sexual and gender-based violence (SGBV). This objective is delivered through three components.
- CARE 4M: Builds women’s leadership and agency in Tigray and Afar to enable meaningful participation in recovery and peace processes
- ELiDA 1M - Empathy for life integrated for Development Association consortium Enhances women’s participation and leadership in peacebuilding across Amhara, Tigray, and Oromia.
- ACCORD £850K: Strengthens localisation and resilience of the WPS agenda by empowering local peace leaders and improving institutional capacity for sustainable, inclusive peace.
IV. Strengthen conflict related policy and programming - provide evidence and expertise to guide diplomatic and programmatic activity, as well as to strengthen conflict sensitivity practices. This objective is delivered through two partners
- Peace Research Facility (through RVI -Rift Valley Institute) £2.2M: Provides conflict analysis and supports peacebuilding through trend analysis, knowledge sharing, and conflict-sensitive programming
- Conflict Sensitivity Hub (Mercy Corps) £600K: Builds capacity of HDP (Humanitarian Development and Peace) actors to recognise and mitigate conflict risks and adapt programming for peacebuilding
Annual Review Team: This Annual Review covers the fourth year of the programme, running from January to December 2025. The review was conducted between 3 and 14 November through a desk-based assessment of key documents, field visits, and consultations with all eleven partners in Addis Ababa, Mekelle, Adigrat, and Jijiga. The process was led by a Conflict Adviser from FCDO Yangon, supported by the HARP team comprising two conflict advisers and two programme management staff.

Conflict Context in Ethiopia 2025
The operating and conflict context in Ethiopia has been difficult during 2025. While violence has fluctuated, some local deals have been made and peace agreements in Tigray and Somali region have held, there has been little progress towards peace, and the trajectory is concerning. The peace agreement in Tigray has been unravelling due to poor implementation, lack of trust between the parties and divisions within Tigray. Widespread insurgency in Amhara has persisted with no prospect of meaningful dialogue. Conflict in Oromia has continued despite a deal one OLA faction at the end of 2024. Politics in Somali region has become more contested, with a faction within the Ogaden National Liberation Front (ONLF) questioning the basis of the 2018 peace agreement. Therefore, three years since the conflict in Northern Ethiopia and ahead of elections in mid-2026 the context remains violent, divided and fragile – providing both a rationale for and challenge to HARP.
Summary supporting narrative for the overall score in this review
HARP achieved an overall output score of ‘’A’’, with most of the outputs meeting or surpassing expectations. These achievements are particularly notable given Ethiopia’s fragile stability, shrinking civic space, and heightened sensitivity around human rights work. They demonstrate the programme’s ability to deliver impact in an exceptionally challenging operational environment.
At the impact level, the indicators showed mixed progress. Ethiopia’s Freedom in the World score has improved compared to the baseline, although it has declined relative to last year. The second indicator—conflict‑related violence data—has not yet been released, and thus the impact cannot be fully assessed at this point.
The HARP programme has made notable progress toward its expected outcomes, but full achievement remains difficult to confirm due to the absence of a systematic tracking system for outcome-level evidence. Progress is evident in initiatives promoting non-violent conflict resolution at local level, gender inclusion, and human rights advocacy, with EHRC resolving over 1,100 complaints and OHCHR influencing national and international fora. However, without consistent monitoring and data collection, it is challenging to determine whether these achievements translate into sustained systemic change.
At the output level, during the reporting period, 69,167 combatants (23% women) were successfully demobilised and returned to civilian life, marking a substantial contribution to stabilisation efforts. The programme supported seven regional and national dialogues and facilitated community-level engagements in Oromia, Afar, and Somali regions, convening local stakeholders to advance peace initiatives and tackle key drivers of conflict.
Additionally, the programme strengthened women’s leadership by supporting over 42 formal, informal, and cross-regional women-led platforms and networks, enhancing coordination, advocacy, and decision-making. The Office of the High Commissioner for Human Rights (OHCHR) published more than 1,000 reports on human rights, including those addressing gender-based violence (GBV) and conflict-related sexual violence (CRSV), reinforcing both international and national monitoring systems.
The Peace Research Facility (PRF) expanded its reach and partnerships, driving demand for tailored conflict analysis to inform conflict-sensitive programming. Similarly, the Conflict Sensitivity Hub, launched this year via Mercy Corps, initiated audits and accompaniment with 23 engagements across development and peacebuilding organisations. Engagement from FCDO and other programmes on conflict analysis continues to grow, underscoring the Hub’s strategic relevance.
Overall, the programme has delivered significant progress and remains firmly on track.
	Output	Score	Weighting %
1	National and regional peace, reconciliation and conflict resolution processes are more effective, coordinated, inclusive (of the main political actors, conflict parties and local community) and accountable.	A	35%
2	Women, girls and WLOs, (Women’s Lead Organisations) and their communities, have increased capacity for, and participation, in mediation, peacebuilding and recovery processes	A	25%
3	National human rights monitoring and early warning systems are strengthened, international monitoring increased	A+	25%
4	Increased exposure of HMG, international and national actors to quality conflict research and analysis, and conflict sensitivity advice/support, provided in response to demand	A	15%

Major lessons and recommendations for the year ahead
This year’s review has highlighted several critical lessons for the programme.
First, supporting peace and dialogue processes requires a holistic, integrated approach that brings together multiple actors and sectors. Implementing partners consistently emphasize that addressing urgent humanitarian and emergency needs is critical to creating the conditions for dialogue and negotiation. These needs must be considered and addressed as part of the dialogue and negotiation process—not treated as a separate, sequential step. This applies across sectors, including work on Women, Peace and Security (WPS) and dialogue initiatives, without reference to geographical preferences. Without integrating these immediate needs, efforts to convene stakeholders risk being undermined.
Second, the programme must maintain flexibility in its design, resource allocation and delivery, while ensuring strong strategic linkages between local-level initiatives and national-level processes. This dual focus is vital for coherence and impact, enabling interventions to respond effectively to evolving political dynamics and emerging opportunities for peace. Strengthening these linkages will also help avoid fragmentation and ensure that local actions contribute meaningfully to broader national objectives.
Finally, process matters as much as outcome. Capturing lessons and recognising progress in the process itself is essential, as these achievements often lay the foundation for sustainable results.
Building on these lessons, recommendations for next year are as follows. (Note: a list of action points for the team on the following recommendations can be found at Annex 2)
- Strengthening Strategic Linkages Across the FCDO Portfolio: HARP’s work extends beyond its goal of stability and influence, with strong linkages across the wider FCDO portfolio. To maximise impact, HARP should adopt a strategic approach that looks beyond its current outcomes and articulates how its activities contribute to broader objectives of FCDO Addis. A practical starting point would be to build on existing cross-portfolio linkages and areas of engagement, such as conflict sensitivity, issues related to IDP returns, human rights, and humanitarian service delivery. This should be structured as a proactive and regular process, rather than ad hoc coordination, and could ultimately embedded across different goals considering developing a multi-year country business plan.
- Strategic Coherence for Local and National Peacebuilding: Component One focuses on reducing local-level violence and fostering dialogue among diverse groups, while preparing for current and potential national processes. Given the localised nature of the conflict, sustaining dialogues that deliver tangible reductions in tension is critical. A single process is unlikely to resolve Ethiopia’s complex, multi-layered conflict; however, there is a risk that efforts become fragmented and overly localised. To mitigate this, HARP should ensure strategic coherence across partners, guided by a clear vision of how all actions contribute to national objectives. Developing a strategic linkage framework is a practical first step to enable coordination and coherence. Additionally, HARP should maintain flexibility in resource allocation, adapting to context and ensuring timely support for high-level discussions when opportunities arise.
- Framing Election Support Through a Violence Reduction Lens: Under HARP’s Theory of Change, interventions are intended to contribute to reducing violence. In Ethiopia’s current sensitive context, election support carries significant risks—elections could deepen divisions and trigger violence rather than foster unity. There is also a reputational risk for the UK in being seen to enable or associate with a sensitive political process.
HARP should acknowledge these risks transparently and update its assumptions accordingly. All election-related activities must be framed with violence prevention as the core objective, moving beyond generic support such as promoting inclusivity, voter education, or party dialogues. Every intervention should be designed to prevent and mitigate election-related violence This framing will also strengthen the programme’s strategic coherence across all components by ensuring that every engagement collectively contributes to creating an enabling environment for a peaceful and less violent electoral process.
- Developing a Cross-Office Human Rights Approach and Diversifying Support:
  In response to requests from human rights organisations, including UN agencies and local civil society organisations, for stronger international and FCDO advocacy; Ethiopia’s shrinking civic space; and the cross-cutting nature of human rights work; HARP should adopt a structured cross-office human rights approach. This will maximise influence, ensure coherence, and unify advocacy across BE Addis and the wider international community. In addition, continued support for human rights institutions and their effective functioning is more critical than ever in the current context of Ethiopia. In the context of a shrinking civic space and increasing challenge to work on human rights, the programme should explore to diversify its support beyond institutions to include civil society organisations (CSOs). This would also help the programme’s resilience to be more flexible and adaptable in a fast-changing context. A practical starting point would be to review current CSO support and identify opportunities to expand within the existing resource as a pilot for future programming.
- Developing a Cross-Office Human Rights Approach and Diversifying Support: Human rights considerations cut across nearly all areas of UK engagement in Ethiopia—political advocacy, service delivery, protection, livelihoods, and economic rights. To better integrate and elevate this work, which is also an FCDO priority, HARP should consider adopting a cross‑office human rights approach. Establishing a shared framework would ensure that human rights value are embedded consistently across all BE Addis programmes, rather than remaining confined to the HARP component. This would strengthen coherence, reinforce a unified UK position, and help ensure that human rights are prioritised as a core element of every programme and engagement. At programme level, continued support for human rights institutions and their effective functioning is more critical than ever in the context of a shrinking civic space. The programme should explore to diversify its support beyond institutions to include civil society organisations (CSOs). This would also help the programme’s resilience to be more flexible and adaptable in a fast-changing context. This does not have to mean that the component needs to be expanded with more partnerships, but to review existing CSO support and identify opportunities to expand within the existing resource as a pilot for future programming.
- Strategic Coherence of WPS: The WPS portfolio has gained momentum and delivered notable successes. Building on these achievements, for the remaining programme year, it is important to consolidate efforts and define a clear strategic focus. Without this, impact will be difficult to demonstrate, and there is a risk of spreading too thinly. This means that in the coming year, the programme should focus on building upon the foundational work already achieved—such as capacity building and awareness training—by investing in strengthening and advancing these areas for strategic-level impact, rather than expanding the same foundational work. A practical first step would be to map current partner activities against areas of greatest impact and influence, aligned with the five strategic objectives of the UK National Action Plan (NAP). This will help identify where the programme can achieve the most significant results and define a clear strategic outcome for the rest of the programme year.
- Focus to increase Uptake of the Conflict Sensitivity Component: Prioritise increasing the uptake and practical application of the conflict sensitivity component by establishing a process to monitor how resources and research findings are used, and what impact they achieve. This includes tracing how conflict sensitivity guidance has influenced decisions and practices, identifying gaps, and refining approaches to maximise adoption and effectiveness. Embedding conflict sensitivity as a core operational standard—rather than an optional reference—will strengthen HARP’s strategic relevance and ensure lasting impact.
- Review Log frame: For the remaining years, this review recommends
  - Systematically track progress against outcomes by establishing clear methods for data collection, identifying reliable sources, and ensuring consistency across indicators.
  - Revise Output one and its indicators to reflect the inclusion of election-related activities.
- Work with partners to review and adjust targets for the final year, increasing them where feasible to keep ambitions high and targets meaningful.
- HARP team ways of working: To enhance coherence across components and the overall portfolio, the team should consider adopting alternative ways of working to improve coordination. Currently, each component is organised under a thematic area—such as Women, Peace and Security (WPS) and Human Rights—and led by an advisor, with a single advisor assigned to a cross-component coordination role. An alternative approach would be for thematic leads to assume coordination responsibilities within their respective themes across HARP components, rather than appointing a separate coordinator for all components. This would also strengthen alignment with the wider BE Addis team, as these themes extend beyond HARP. In addition, with only two programme management staff overseeing 14 partners (of which only two operate under MoUs), capacity is significantly stretched. HARP should explore options to leverage the annually recruited interns via the bidding process to help ease programme management pressures.
- Develop a Comprehensive Framework for Evaluating Programme Outcomes and Lasting Impact: Establish a robust approach for evaluating programme outcomes over the remaining years, demonstrating how the programme has contributed to influencing or strengthening conflict and peace-related policies and practices. This should include evidence of improvements, an assessment of sustainability (achieving lasting change), and an evaluation of overall effectiveness.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Although there are challenges in the political context, fragile peace processes, ongoing conflict and increasing threats to civic space, the Theory of Change (ToC) as stated in the Business Case remains valid.
A business case extension up to March 2027 and budget increase of £36.5m was confirmed in January 2024. It was approved on the basis that HARP is central to the delivery of the UK’s priority to support Ethiopia’s transition away from conflict, including implementation of the Pretoria Agreement (through a £16m UK contribution to DDR) and upholds our commitments as a Women Peace and Security (WPS) focal country.
A no-cost business case extension up to December 2027 was confirmed in August 2025. It was approved to enable the programme to broaden the scope of component 1 to mitigate risks of conflict and instability around the 2026 national elections through: i) support to the National Electoral Board of Ethiopia (NEBE) to deliver elections in the most challenging and conflict affected areas, ii) implementing an early warning system through NEBE and partners and iii) bringing political parties together to reduce electoral tensions to ensure a broad franchise and manage disputes.
The Theory of Change is illustrated in the diagram below. Following the 2024 business case extension there were non-material changes on Outcomes 2 (Women, Peace and Security) and 3 (Human Rights), resulting from the incorporation of new elements within components. These changes are reflected in the updated diagram and in Annex III (Log Frame) approved in July 2025. The update was developed together with partners and finalised by the programme team and agreed by the SRO. As the changes were non-material, they were approved by the Development Director per PRoF rules in July 2025.

At Impact level, the programme aims to contribute to a reduction in the levels of violent conflict and increased space for peaceful political transition. This can be achieved if HARP invests:
- resources into inclusive peacebuilding initiatives, including women, girls and other marginalise groups in dialogue platforms that have shown evidence of success
- in strengthening gender-sensitive systems, services and capacities for supporting victims of, and investigating, Human Rights abuses and violation
- in a conflict research facility that provides evidence to guide and shape our diplomatic and programmatic activities (and those of the wider community).
Several assumptions underpin this ToC, including 1) There is political will, at least at the local level, to resolve conflict; 2) Local level peacebuilding interventions can make a meaningful difference to local dynamics, even if national politics remain unchanged 3) There is sufficient access to conflict-affected areas to enable services to survivors of Human Rights abuses and violations 4) Conflict actors have constituencies to which they are responsive 5) Human Rights CSOs are able to operate freely and accountability mechanisms will be sufficiently unbiased and non-politicised to make progress.
Programme-funded post: The programme-funded post has been effective in improving the delivery of the Theory of Change (ToC) through providing dedicated technical expertise. The specialized technical expertise enabled the translation of strategic objectives into practical interventions in conflict resolution processes, human rights, gender sensitivity and women peace and security; ensuring alignment between activities, outputs, and intended outcomes. The technical leadership, quality assurance, and evidence-based guidance improved programme implementation
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page
The programme is partially on track to contribute to its intended outcomes and impact. At the output level, delivery remains strong, but outcome-level progress is mixed. Outcomes 2, 3, and 4 are broadly on track, demonstrating strong progress in women’s participation, human rights advocacy, and conflict analysis support. Outcome 1 is off track against its milestone, although there is evidence of meaningful progress toward intended results. The programme is structured around four outcomes with eight indicators. However, systematic tracking of evidence to assess achievement at the outcome level has not yet been established. Consequently, this assessment should not be regarded as a definitive judgement on whether these outcomes have been fully met, as the evidence is drawn from varied sources. It should therefore be read as an evaluation of progress against the outcomes, using the available evidence to illustrate movement towards achieving them, rather than determining that the outcomes have been conclusively met.
IPE Peace Index Score
Year	Score	Rank (Out of 163)
2024	2.84	144
2025	2.68	138

Source: Institute for Peace and Economics (IPE) Peace Index
Conflict Related Violence Events by Region
Region	2024	2025
Tigray	105	106
Amhara	1,626	2618
Oromia	1000	1214
Somali	20	30
Afar	12	26

Source: ACLED data as of January 2026
The first indicator is the Freedom in the World score. Ethiopia’s score for 2025 is 18/100, showing improvement compared to the baseline in the logframe (8/100). However, the score declined from 20 in 2024 to 18 in 2025, signalling a setback in political rights and freedoms. This deterioration is linked to worsening security conditions, increased government crackdowns, and limited progress on democratic reforms, despite some gains from the baseline.
The second indicator is the Institute for Peace and Economics (IPE) Peace Index. Ethiopia’s 2025 score is 2.68 (rank 138/163), compared to 2.84 (rank 144/163) in 2024 and the baseline. This reflects a modest reduction in conflict intensity and militarisation, suggesting slight improvement in peace conditions. However, Ethiopia remains among the least peaceful countries globally, highlighting persistent challenges in achieving sustainable peace and stability.
The third indicator measures the number of conflict-related violence events by region (Tigray, Amhara, Oromia, Somali, Afar). Compared to 2023, the data shows that conflict-related violence events in Ethiopia increased in 2024. Specifically, Tigray recorded 1 additional event, Amhara saw a significant rise with 992 more events, Oromia experienced an increase of 214 events, Somali registered 10 more events, and Afar reported an increase of 14 events.
Outcome 1 did not meet its milestone of six fully resolved disputes through targeted non-violent processes. Nonetheless, progress is evident through preventive dialogue and trust-building efforts. The Moyale Memorandum of Understanding between Somali and Oromo communities helped avert violence, and HD facilitated two rounds of dialogue with women leaders in Wollega, creating inclusive spaces for engagement. HD also maintained its mandate with conflict parties in Amhara, positioning itself for future mediation. Persistent challenges include deep-rooted mistrust, weak security frameworks, and limited political commitment, which continue to impede full resolution.
Outcome 2 is on track, with strong progress across indicators. Women now actively lead mediation and governance roles, moving beyond supportive positions. Advocacy efforts have influenced discourse on gender-responsive peace processes, and EMAP-led initiatives have challenged harmful norms, securing tangible gains such as women’s inclusion in Orthodox Church leadership and expanded education rights for Muslim girls. While Indicator 2.1 fell short of its numeric target due to data gaps in Oromia and Somali, qualitative evidence demonstrates significant progress toward inclusive leadership.
Outcome 3 shows strong progress in strengthening human rights capacity. EHRC resolved 1,153 of 1,380 complaints, demonstrating improved institutional capacity. OHCHR met its milestone by raising eight priority human rights concerns at national and international fora, resulting in concrete follow-up actions, including releases of arbitrarily detained civilians and directives to improve access to justice. These efforts have contributed to accountability and early-warning systems.
Outcome 4 is broadly on track, with evidence that RVI’s research informed FCDO engagements and policy discussions. Two conflict sensitivity assessments were completed, and the CS Hub began institutional accompaniment, though defining and measuring “conflict sensitivity” remains a challenge. Strengthening evidence collection and aligning milestones with indicators will be critical to demonstrate impact.

Impact	Indicators	Milestone(s) for this review	Progress
Reduced levels of violent conflict and increased space for human rights protection and inclusive political dialogue contributing to sustainable peace	Impact Indicator 1. Freedom in the World 2025 score	Impact milestones are not set because impact indicators reflect long-term, system-level changes beyond the programme’s direct control in a complex peacebuilding context	Score is 18/100. Improved from baseline but declined from 2024 (20 -18), signalling setbacks in rights and freedoms due to worsening security and limited democratic reforms.
	Impact Indicator 2. Institute for Peace and Economics (IPE) Peace Index score		Score improved to 2.68 (rank 138/163) from 2.84 (144/163) in 2024, indicating modest improvement, but Ethiopia remains among the least peaceful globally
	Impact Indicator 3. Number of conflict-related violence events in Ethiopia reduced, by region (Tigray, Amhara, Oromia, Somali, Afar)		ACLED data indicates that conflict-related violence events in Ethiopia increased in 2024. Specifically, Tigray recorded 1 additional event, Amhara saw a significant rise with 992 more events, Oromia experienced an increase of 214 events, Somali registered 10 more events, and Afar reported an increase of 14 events.
Outcomes	Indicator(s)	Milestone(s) for this review by 2026	Progress
Outcome 1: Sustained peace and conflict resolution processes make progress towards the non-violent management or resolution of armed conflicts	Indicator 1.1 Increase in number of disputes resolved through targeted non-violent resolution processes in Somali, Oromia, Tigray and Afar regions	At least 6 instances of conflicts resolution/dialogue processes progressing (to cover minimum three regions formal and informal processes)	Did not meet expectation / 2 instances of dialogue in progress

Outcome 2: Increase in representation of women and girls in conflict-affected communities/regions of Ethiopia participating in and influencing peace process and recovery initiatives. (more inclusive leadership, stronger community platforms, and gender-responsive institutional reforms)	Indicator 2.1 % increase in women holding leadership roles in local peace committees, recovery task forces, or community governance structures in targeted community of Tigray, Afar, Oromia and Somali	10% increase in women holding leadership roles in local peace communities/regions, recovery task forces, or community governance structures since January 2024	Did not meet expectation / 41% in Afar and Tigray (no data in Oromia and Somali)
	Indicator 2.2 # of advocacy actions led by women’s rights groups, women-led organizations, and informal women’s groups that result in verifiable changes in peace policies or practices, such as the inclusion of gender provisions in peace agreements, adoption of gender quotas, and implementation of National Action Plan (NAP) on Women, Peace, and Security by 2027. (national and disaggregated by implementation in priority conflict affected regions: Tigray, Afar, Amhara, Oromia, and Somali regions)	3 advocacy efforts in implementation regions result in documented influence on peace-related policies or practices	Met Expectation / 4 advocacy efforts in progress
	Indicator 2.3 # of sustained initiatives led or co-led by men and boys champions challenging traditional norms and promoting women’s leadership in peace and security resulting in change in community attitudes and inclusions.	At least 3 instances of male champions who led and co-led sustained initiatives (e.g. dialogue, campaign, training and community forums) that challenges harmful traditional norms and promote women leadership	Met expectation / 8 initiatives were implemented with 3 specific examples of change

Outcome 3: Increased domestic and international capacity to address and reduce human rights abuses and violations	Indicator 3.1: Increased implementation of EHRC’s recommendations based on its monitoring and investigation in selected regions	By the end of 2025, increase the number of EHRC individual and group complaints received and resolved by 409 compared to 2024 levels	Met Expectation / 1380 complaints received, and 1153 cases resolved
	Indicator 3.2: Increased number of human rights advocacy actions by UNOHCHR taken up in national and international fora	8	Met Expectation / 8 major issues are taken up

Outcome 4: Conflict analysis, Research and conflict sensitivity advice/support leads to improved engagement and understanding of conflict and conflict sensitivity by HMG and national and international actors	Indicator 4.1 Number of instances HMG teams use the findings and recommendations of analysis and research to inform programming and diplomacy (measured through feedback, and programme design reviews)	At least 3 instances	Met Expectation / (Royal College of defence studies round table, RVI facilitated roundtable on Ethiopia security and governance and briefing to Omar Daair FCDO Director to east, centre and southern Africa)
	Indicator 4.2 Number of FCDO programmes supported to be more conflict sensitive through training and internal/external evaluations.	At least 2 instances of FCDO programme being conflict sensitive.	Did Not Meet Expectations / 2 conflict sensitivity assessment has been implemented but not accessed.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.
HARP remains the primary vehicle for delivering the BE Addis Country Business Goal on stability and influence. Its strategic importance is underscored by the approval of a no-cost extension, enabling targeted support to mitigate violence during the election period. The programme has demonstrated its ability to convene multi-layered dialogues across diverse conflict contexts, reinforcing its role in fostering inclusive peacebuilding. Evidence shows progress towards key outcomes, particularly in advancing the UK National Action Plan on Women, Peace and Security (WPS), as Ethiopia is a WPS focus country. Considering global reductions in funding for human rights and a shrinking civic space in Ethiopia, HARP’s contribution remains critical to sustaining momentum to improve accountability for human rights at different levels. The programme also offers significant opportunities to drive impact across FCDO portfolios, notably through RVI and the Conflict Sensitivity Hub, which strengthens conflict-related policy and programming across the FCDO portfolio. However, measuring progress against Indicator 4.2 has been challenging due to the absence of a systematic tracking mechanism to verify whether cross-embassy programmes supported are conflict-sensitive. Despite this limitation, RVI’s early work demonstrates potential to embed conflict sensitivity principles across programming. Given these achievements and the evolving risks, it is essential that HARP continues to operate and scale its efforts to safeguard stability and influence in Ethiopia.
In a world of declining Official Development Assistance, HARP remains relevant by delivering impact through approaches that go beyond traditional aid and align with three of the four global shifts. It strengthens national systems such as the Ethiopian Human Rights Commission while linking sub-national peacebuilding efforts to national frameworks, ensuring coherence and sustainability. It leverages internal and partner expertise to design and implement interventions, reducing reliance on grants and adding value beyond funding. Localisation is central to its approach, with increased engagement of grassroots organisations and women-led initiatives through consortium models, ensuring legitimacy, cost-effectiveness, and resilience. These shifts position HARP as a forward-looking programme that responds effectively to the realities of a lower ODA world.
## C. DETAILED OUTPUT SCORING
Output 1	National and regional peace, reconciliation and conflict resolution processes are more effective, coordinated, inclusive (of the main political actors, conflict parties and local community) and accountable
Output number:	1	Output Score:	A
Impact weighting (%):	35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) January 2026	Progress
1.1 Instances of regional and national dialogue and peace processes (national, Tigray, Oromia, Somali) meaningfully including key stakeholders (opposition, non-state actors and marginalised groups)	At least 8 instances of inclusive dialogue processes since April 2025	Moderately did not meet - B / Total of 7 instances
1.2 Number of ex-combatants reintegrated into the community as civilians (at least 25% women; child combatants TBC; people with disabilities TBC)	January 2026 / 50000	Met expectations with exceptions - A / Total 65,173(19% female and 64% People with disabilities) – for Tigray and Afar) No data on child combatants due to sensitivities.
1.3 % of strategic objectives in the Somali Truth and Reconciliation Commission (TRC)’s Matrix that have been implemented	End of 2025, at least 40% of the strategic objectives outlined in the Somali TRC Matrix are implemented, with documented evidence of actions taken, stakeholder engagement, and initial outcomes reported in at least two priority thematic areas (e.g., justice, reconciliation, or institutional reform).	Met expectations with exceptions - A / 75% completed by December 2025 against a 40% target. Actions under Truth-Seeking and Victim Support were carried out, with stakeholder engagement and initial outcomes reported. While documentation is still pending, the milestone is broad and progress is clear

The output is rated “A” as progress is evident across all components. Of the three output indicators, two met expectations, while one moderately fell short of expectations. Although Indicator 1.2 exceeded its quantitative targets, the gender-specific target was not met. For Indicator 1.3, while the planned percentage of implementation was achieved, the substantive requirement to define thematic areas was not fulfilled.
Output indicator 1.1 CR has initiated four structured dialogue initiatives in 2025. Two of these were dialogue initiatives focused on bringing together elites and local communities on either side of the Afar–Tigray border. The other two dialogues focused on intra-mediation efforts within the ONLF, engaging an international expert to work with each of the two main ONLF factions, and supporting the new leadership to align with national dynamics and emerging challenges. Under this indicator, HD achieved its milestone of conducting three multi-round dialogue processes focused on Oromia. In partnership with I4C, three intra-Oromo elite dialogues were held to promote critical engagement, collective reflection on historical experiences, current political dynamics, and prospects, and to identify action points for future peacebuilding and consensus. Through collaboration with Adoye, HD supported the Oromo Women Peace and Development Network (WPDNO) by engaging 20 leaders from all zones of Oromia to share lessons from conflict and strengthen leadership for peacebuilding. Additionally, WPDNO facilitated two dialogue rounds with 20 women from four Wollega zones, creating a new space for women from conflict-affected areas to exchange experiences, challenges, and strategies for navigating conflict.
Output indicator 1.2 During the reporting period, a total of 69,167 individuals were demobilised from Tigray and Afar with women accounting for 23% and people with disabilities 51% of those demobilised. The overall demobilisation target has been met; however, female participation remains significantly below expectations. Delivery of this output has been constrained by political challenges, particularly the level of political will and the pace of implementation of the COHA agreement. It also remains unclear how gender considerations were integrated throughout the DDR process, highlighting a gap in the application of gender-sensitive approaches.
Output Indicator 1.3 By October 2025, 57% of the TRC’s strategic objectives had been achieved, with progress varying across objectives related to truth-seeking, victim support, reconciliation, institutional reform, and operations. The TRC presented its interim progress report to the Regional Parliament, highlighting significant advancement towards establishing and operationalising a mechanism for truth-seeking and reconciliation. Key achievements also included: a) collecting over 50,000 witness statements (59% male and 40.6% female), which demonstrates strong community engagement. Some victim statements also include the experiences of the individual’s family members making the total individual victim statements 69,000; b) identifying 165 suspected mass grave sites linked to past atrocities. Notable findings include a newly discovered mass grave in Degahmedow and evidence of severe atrocities at Goljano, underscoring the gravity of historical violations.
Changes to this output during the past year, and planned changes as a result of this review
There have been no significant changes to this output over the past year, and the targets appear to have been set at a realistic level. Given the budget constraints facing FCDO Ethiopia and following progress in delivering the planned first phase of DDR in Tigray with the overall £16 million contribution, no further funding has been committed for DDR in subsequent years. Consequently, there is some headroom within the business case to allocate budget to reducing risks of election-related violence, and the addition of an elections-related sub-programme has been approved.
In the forthcoming programme year, HARP should amend the logframe for this output, revising Indicator 1.2, and updating it to capture and measure the new election-related activities.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
Progress on recommendations from the previous Annual Review includes the following:
- First, HARP is expected to adopt Adam Smith International’s recommendations to ensure the sustainability of DDR processes; progress on this remains to be updated.
- Second, UNDP was advised to strengthen its data collection and reporting systems to include comprehensive, disaggregated data on all targeted demographic groups, such as child ex-combatants and persons with disabilities. While improvements have been made in gender-disaggregated reporting, disability data is still absent.
- Third, CR was tasked with accelerating the completion of the TRC’s planned activities in underperforming areas, such as supporting victims of violence and ensuring restorative justice, by providing additional technical assistance to the Commission. This recommendation is ongoing and partially achieved, with notable progress in the TRC’s implementation of its strategic objectives, including improved coordination with the federal transitional justice process.
- Finally, enhancing coordination between programmes (CR, HD, and UNDP) remains a priority, as partners are working towards similar goals; better collaboration could significantly improve efficiency and impact. This recommendation is also ongoing, alongside a broader call for greater coherence across all programme components.

Lessons learned
Given Ethiopia’s interconnected conflicts and persistent emerging tensions, deliberate and coordinated efforts are essential to identify and act on opportunities for peacebuilding. This requires leveraging existing relationships and institutional credibility while adopting a strategic approach that recognises linkages between different processes and remains adaptable to evolving dynamics. A key lesson is the need for stronger coordination mechanisms and a clear articulation of how national, regional and local layers of dialogue and peacebuilding interact, to prevent duplication and maximise impact. This principle must also guide budget planning, ensuring that resource allocation is context-sensitive and aligned with strategic priorities.
Recommendation for next year
Building on the earlier suggestion for the HARP team to improve coordination under Component One, it’s important to strengthen links between activities and ensure coherence across partners. For instance, HD and CR could collaborate by sharing lessons learned, harmonizing approaches where relevant, and jointly developing standards for monitoring and reporting. This would help maintain consistency across regions and amplify impact without requiring identical workplans.
A comprehensive review of this output will be required next year, given the programme’s recent adjustments under this component, including the ending of DDR activities and the integration of election support. This review should encompass a revision of the output title, as its current focus on conflict resolution processes no longer fully reflects the expanded scope. Any changes must align with the agreed approach and the framework within which the election support will operate.
Output 2	Strengthened capacity of women, girls and institutions to engage in and promote gender- responsive peace and recovery efforts
Output number:	2	Output Score:	A
Impact weighting (%):	25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 % of women and girls trained reporting increased confidence and knowledge to actively engage in peacebuilding and recovery processes (disaggregated by priority conflict-affected regions: Tigray, Afar, Amhara, Oromia, and Somali regions)	60% of women and girls trained report improved knowledge and confidence to engage meaningfully in peace processes. / Source: ACCORD, CARE, ELIDA, HD, CR	Moderately Exceeded expectation- A+ / Total 80% in Afar and Tigray, Total 91% in Oromia, Tigray, Amhara)
2.2 # of formal, informal, and cross-regional women-led platforms or networks that are supported through funding/technical assistance and are actively participating in advocacy and decision making. (national and disaggregated by priority conflict affected regions: Tigray, Afar, Amhara, Oromia, and Somali regions HD)	40 women-led platforms and sub-platforms are technically assisted to strengthen their organizational capacity, coordination, and engagement in advocacy and decision-making. / Source: M&E, pre and post survey (CARE, ELIDA, ACCORD, CR)	Met Expectation - A / Total of 41
2.3 # of public communication products (e.g., podcasts, dialogues, research, online forums) produced and shared on digital platforms that amplify diverse women’s voices and perspectives in conflict analysis, peacebuilding and recovery efforts.	12 public communications / products produced / Source: ELiDA, CIR, RVI	Met Expectation- A / Total of 14 Public communications products produced
2.4 # of advocacy events led by men and boys champions promoting women’s role in peace and security in implementation regions (Tigray, Afar)	At least 5 events across / targeted communities, reaching a minimum, of 1000 people	Moderately did not meet expectation- B / Total of 4 events

The output is rated “A+” as progress is evident across all components. Of the four output indicators, three met or exceeded their targets, while one moderately fell short of expectations.
Output Indicator 2.1 Under this output, both CARE and ELiDA delivered a series of training sessions in Afar, Tigray, Amhara and Oromia. According to CARE’s mid-term evaluation (September 2025), nearly 8 in 10 women in WLiE groups (around 520 women) across Afar and Tigray reported increased confidence and knowledge to engage in peacebuilding and recovery processes. Confidence levels were similar in both regions (81% in Afar and 79% in Tigray). This progress is largely attributed to WLiE group’s activities, which provide strong peer-learning and solidarity networks as well as safe spaces for women to share experiences, learn, and take collective action. In addition, ELiDA implemented a two-stage capacity-building programme designed to strengthen the leadership and advocacy skills of women’s organisations engaged in peace and security initiatives. Training sessions were held in Tigray, Amhara, and Oromia, reaching 90 participants (77 women and 3 people with disabilities) from women-led and women-focused CSOs. Of these, 78 completed both pre- and post-training assessments, with 91% (71 participants) demonstrating improved knowledge based on the evaluation questions. CR reported that it has reached out to 70% of women estimated to have been subjected to SGBV across the seven target zones of the SRS, based on modelling. Similarly, HD achieved its milestone of ensuring 30% women’s participation in capacity-building and dialogue activities. In addition, HD’s downstream partner WLO reported improved knowledge among women to engage in peace processes, including members of the Chafee Oromia Women Caucus and the Oromia Women Peace and Development Network.
Output 2.2 Through ELiDA, the project supported the establishment of four women-led peace platforms. These include two formal regional and two informal coordination mechanisms created through Regional Peace Forums. All four platforms are now actively engaged in advocacy and engaging in decision-making across three priority conflict-affected regions. Similarly, CARE supported thirty women-led platforms, with 26 action plans implemented within the first month of support. CR supported four women-led platforms: three in the Somali region and one cross-regional platform for Moyale cross-border peace initiatives, engaging over 100 women members. HD met its milestone by backing two women-led platforms——through technical and financial assistance to promote inclusive dialogue and advance the Women, Peace and Security (WPS) agenda. ACCORD continued to strengthen the Ethiopian Women Peace Builders (EWPB) network with comprehensive support, enhancing its organisational capacity, advocacy, and resource mobilisation. These efforts have enabled EWPB to coordinate activities, engage local authorities, and participate meaningfully in dialogue platforms, contributing to grassroots peacebuilding and amplifying women’s voices. Future support will focus on sustainability, expanding regional representation, and deepening engagement in national WPS frameworks.
Output 2.3 Under this output, CIR published three research papers on TFGBV (Technology Facilitated Gender Based Violence) and one recommendation paper. RVI produced seven podcasts through the Ethiopian Women Researchers’ Network (EWNET), six of which were shared on YouTube, attracting 1,941 views, and amplified via social media. These podcasts explored the role of women researchers and their contributions to national issues. ELiDA organised five advocacy events, including a virtual Peace Conference, an online dialogue on eliminating sexual violence in conflict, and a televised panel on Tigray Broadcasting Service, promoting Ethiopia’s National Action Plan on Women, Peace and Security (WPS). Social media campaigns marked International Women’s Day and highlighted WPS themes. TIMRAN also aired a 40-minute televised panel on WPS via Amhara Media Corporation, reaching a wide regional audience. Collectively, these initiatives amplified women’s voices in peacebuilding, conflict analysis, and recovery efforts. Collectively, these initiatives represent and amplify women’s voices in peacebuilding, conflict analysis, and recovery efforts.
Output 2.4 During this review period, CARE completed a 12-week training programme on Engaging Men through Accountable Practices (EMAP) for 257 men across 14 WLiE men’s groups. The training focused on shifting social norms towards more gender-equitable attitudes and promoting women’s participation and leadership. Following the training, EMAP gender champions organised four advocacy events and implemented eight initiatives across project locations. Examples of these initiatives include advocacy for women’s engagement in leadership roles within the Orthodox Church, campaigns supporting Muslim women’s access to education and the prevention of early marriage.
Changes to this output during the past year, and planned changes as a result of this review
All output indicators under this output were updated in July 2025.and were approved by the Development Director. The challenge with the current indicators is that they primarily measure quantitative data—numbers or percentages. When all partners contribute collectively, it becomes relatively easy to meet targets, yet this approach only reflects the volume of activities rather than their quality. Although it is not ideal to continually change indicators, the team should consider reviewing how to capture the quality of activities, as well as ensuring that appropriate targets are set for all indicators.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
Progress on recommendations from the previous AR includes i) CARE prioritising institutional capacity support for local WLOs in Tigray and initiating activities in Afar before the end of the financial year, which is ongoing with evident progress ii) BE Addis to revise the log frame to include clear, measurable indicators with baselines and realistic targets which has been completed on July 2025 iii) HD to strengthened the internal operational capacity of the Oromia Women Peacebuilders Network – this is completed as reflected in Indicator 2.2 and iv) the newly funded programme role is fostering stronger collaboration between CARE, CR and HD to ensure a more holistic approach to achieving programme goals which is on going
Lessons Learned
Key lessons under this output include the need to link WPS initiatives with economic empowerment, livelihood support and leadership opportunities, supported by formal governance structures to build confidence and influence. It is also critical to recognise that cultural and structural barriers persist, as male leaders often hesitate to challenge traditional norms, leaving women to lead counter-advocacy efforts. Finally, inclusive and participatory approaches—such as language accessibility, mentorship, and stakeholder engagement—are essential for strengthening advocacy skills, fostering peacebuilding, and ensuring sustainable impact.
Recommendations for the year ahead
It is essential to maintain clear collaboration and complementary ways of working across programme components. The team should explore opportunities to consolidate efforts, strengthen areas showing the most progress, and redirect where similar activities are being implemented by the same organisations in the same locations. This approach will allow the component to go deeper rather than spreading too thinly, while aligning closely with strategic WPS objectives.
The current output indicators effectively capture quantitative achievements but fail to reflect the quality of those results. The team should review and adjust the indicators to better measure qualitative aspects. When setting targets, it is important to clarify which organisation contributes to each indicator. If all organisations within a component contribute to a single indicator, targets should be more ambitious; otherwise, responsibilities and milestones should be clearly separated. Additionally, some milestones require greater clarity—for example, Output Indicator 2.1 sets a 60% increase, yet data sources come from multiple partners with different participant bases. This creates ambiguity when partners operate in the same areas, making it difficult to accurately assess improvements.
Output 3	National human rights monitoring and early warning systems are strengthened, international monitoring increased, and atrocity prevention increased.
Output number:	3	Output Score:	A+
Impact weighting (%):	25%	Weighting revised since last AR?	NO

Indicator(s)	Milestone(s) for this review	Progress
3.1 Increased implementation of EHRC’s recommendations based on its monitoring and investigation in selected regions	110 EHRC public events/reports/media coverage	Moderately exceeded expectation- A+ / 72 events, 8 reports, 105 media coverage = Total 185
3.2 Increased number of reports and updates produced (confidential and public) on Human Rights including on GBV/CRSV by OHCHR.	360	Substantially exceeded expectation- A++ / 1,067 reports
3.3 Number of reports and updates (confidential or public) produced by the early warning network (EWN).	160 notes	Substantially exceeded expectation- A++ / Total 1,626,152 reports, 796 advocacy engagements and 293 actions by duty-bearers and stakeholders in response to concerns raised by/from EWNs/alert.
3.4 Number of EHRC investigation based on increased OSINT capabilities as a result of training delivered or capable of training peers as a result of Training of Trainers (ToT) programme delivered.	6 EHRC Investigators advance to silver certification, and continue to develop advanced OSINT skills and capability of delivering trainings	Met expectation - A / Six Investigators advance to silver certification.

The output is rated “A+” as progress is evident across all components. Of the four output indicators, three exceeded their targets while one met expectations. Although Indicator 3.1 1.2 surpassed its quantitative target, this was largely driven by 105 media reports out of a total of 185, which account for the majority of milestone target. Based on the latest update received from OHCHR the number of reports produced for the period January- December 2025 is as 1067 exceeding the milestone set for the review period. For 3.3, overall performance justifies the “A+” rating.
Output 3.1 - Between the end of 2024 and 31 July 2025, EHRC organised 72 events on key human rights issues, all reported on its website, and published 8 reports. There were 105 media coverages on both the events and reports published, all adds up to 185 events/reports/media coverage, exceeding the target. A few notable examples of reports include: i) On 13 June 2025, EHRC, in collaboration with the Ministry of Justice, held a consultation meeting in Bishoftu on Ethiopia’s 4th and 5th draft state reports concerning the implementation of the International Covenant on Economic, Social and Cultural Rights (ICESCR) ii) On 03 April 2025, EHRC organised a follow-up consultation in Bishoftu to review progress on implementing recommendations from its March 2024 report on the treatment and rights of women and children victims of violence within the criminal justice system.
Output 3.2 Between October 2024 and September 2025, OHCHR produced over 1,000 reports, updates and analytical products covering human rights situations across Tigray, Amhara, Oromia, Afar, Somali, Benishangul-Gumuz, Gambella, Sidama and Addis Ababa. These outputs included incident reports, periodic situation updates and confidential briefings addressing violations such as arbitrary detention, extrajudicial killings, conflict-related sexual violence and attacks on civilians. In addition, OHCHR conducted 384 field missions (including detention and trial monitoring) and 155 remote monitoring sessions, verifying 936 violations affecting 36,356 individuals, including 7,644 women and children, of which 24,445 were linked to displacement. Evidence-based advocacy led to the release of 692 arbitrarily detained persons, the establishment of 12 GBV-specialised benches in Tigray and Oromia, and improved detention conditions in Afar, Tigray and Amhara. In collaboration with UNFPA, ICRC and IMC, OHCHR facilitated referrals for 3,240 survivors and at-risk individuals to medical, legal and psychosocial services, reinforcing survivor-centred protection pathways.
Output 3.3 Between October 2024 and September 2025 the EWNs generated 1,183 alerts and produced 809 analytical reports, including human rights violation reports, flash reports and early-warning notes: exceeding the target. These outputs informed 524 advocacy actions and resulted in 195 concrete measures by duty-bearers and partners, such as the release of 692 detainees, 65 court appearances, and 327 survivors (including 291 women and girls and 36 men and boys) receiving comprehensive services—medical care, psychosocial support, legal aid and protection—through referrals coordinated with IMC, UNFPA, ICRC and local One Stop Centres. EWN alerts also contributed to early-stage accountability and peacebuilding processes, including the prosecution of a militia member in Oromia sentenced to 15 years’ imprisonment for unlawful killing, and in Tigray, supported OHCHR’s engagement with the Public Dialogue and Consultation Council, strengthening reconciliation and confidence-building efforts
Output 3.4 CIR successfully delivered the EHRC Training of Trainers (ToT) cohort as scheduled, conducting two five-day in-person sessions in June and late September till early October 2025. Six EHRC investigators completed the programme, gaining advanced skills in investigative methodologies and human rights standards. Participants progressed to Silver certification and continue to develop advanced OSINT capabilities, strengthening their ability to deliver high-quality training. According to feedback from participants, this has significantly enhanced EHRC’s institutional capacity to conduct robust investigations and cascade knowledge through internal training, contributing to more effective human rights monitoring and accountability.
Changes to this output during the past year, and planned changes as a result of this review
As part of the HARP logframe update, Outputs 3.3 and 3.4 were added to strengthen monitoring of EWN activities and CIR’s capacity-building work. In light of the changing context, including shrinking civic space and a slight strategic shift under EHRC’s new leadership, publishing reports could face greater challenges, which may affect indicators measuring public statements in the future. The HARP team may have to therefore consider reviewing Output 3.1 to ensure it accurately reflects results in the current context.
Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
Recommendations from the previous AR includes the following: i) OHCHR was advised to improve data collection and monitoring in hard-to-reach and conflict-affected areas. This recommendation is ongoing with OHCHR highlighting the challenge due to active conflict in some areas. ii) DIHR/EHRC was recommended to monitor the implementation of EHRC recommendations and systematically track the number of statements and reports published. This is ongoing, with DIHR providing updates on the status of recommendations and their implementation.
Lessons Learned
One of the main challenges in delivering this output is the conflict context, where security risks and restricted access are compounded by a shrinking civic space. To sustain operations and gather reliable information, it is essential to maintain field offices, nurture relationships with local networks, and ensure their functionality—this remains the only viable way to keep activities running.
The second key lesson is the need for collective diplomacy. This involves two critical actions: (1) advocating to the diplomatic community through timely briefings on the situation, and (2) leveraging their influence to apply pressure on relevant parties. These lessons highlight the importance of adaptive strategies that combine operational resilience with diplomatic engagement to safeguard programme delivery and amplify impact in highly constrained environments
Recommendations for year ahead
Partners have raised concerns about the shrinking civic space, which poses significant challenges for sustaining human rights work. While this output has received an “A+” rating for two consecutive years, reflecting strong progress in monitoring and reporting, it does not fully capture the restrictive context or the need to support civic space. It is recommended that the HARP team diversify its human rights programming to consider initiatives that strengthen civic space and expand civil society engagement where feasible.
Additionally, output indicators that rely on public statements should be reviewed with partners to determine their continued relevance or replaced with alternative indicators that better reflect ongoing efforts. Milestones should also be set to remain ambitious yet achievable given the current environment.

Output 4	Increased knowledge and demand of HMG, international and national actors on independent conflict research and analysis, and conflict sensitivity advice/support.
Output number:	4	Output Score:	A
Impact weighting (%):	15%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review – January 2026	Progress
4.1 Demand for conflict analysis from FCDO and external partners as expressed by number of attendees at all types of briefings (disaggregated where possible)	On average, 15 participants both from the FCDO and partners attended the roundtable debrief at the FCDO	Met expectation- A / 10. Analysis and equivalent debrief with the FCDO with an average of 15 attendees.
4.2 Number of downloads / Online interactions with publicly available research.	8500 views/downloads and 6000 regular visitors	Substantially exceeded expectation- A+ / 17,000 including downloads and visits / (note: no breakdown on views vs download)
4.3 Number of technical support and training delivered by the CS hub and RVI to FCDO to HDP actors.	15 engagements (CS audit, Champions programme and help desk)	Met expectation- A / 15
4.4 # of capacity building sessions, workshops or cross- actor dialogues on conflict sensitivity convened by the CS Hub (including participation from FCDO, CSOs and implementing partners)	13 engagements workshop, issue specific briefing, conflict assessment briefings and outreach dialogues)	Substantially did not met expectation-C / 5 engagements

The output is rated “A” as progress is evident across all components. Of the four output indicators, two exceeded their targets, one met its target, and one fell substantively short of expectations. Taken collectively, the overall rating remains “A”.
Indicator 4.1 RVI consistently delivered monthly conflict analysis bulletins and in-person briefings to the FCDO and its partners, with 10 sessions held between January and October, each attracting around 15 engaged participants. In addition to these outputs, RVI also organised expert presentations, including a well-attended session on boundary conflicts in Ethiopia and a peer-to-peer experience sharing event on conflict sensitivity for HARP partners. Three public events were held, covering urban spaces, online research challenges, and Ethiopia’s political economy. Due to the sensitive nature of the analysis and the restrictive civic space, wider dissemination was limited, and the monthly bulletin was rebranded as the monthly conflict analysis. RVI’s podcasts received 1,941 views and download growth for publications is expected to increase in the third quarter. Overall, RVI’s outputs were well-received and contributed valuable insights to FCDO programming.
Indicator 4.2 Under this indicator, RVI reports a combined figure of more than17,000 for total downloads and online visits to publicly available research. However, the data does not disaggregate downloads from visits, making it difficult to assess user engagement patterns or determine the relative impact of each activity. Greater granularity is needed to evaluate performance accurately and inform future strategies.
Indicator 4.3 - Under this output, the Hub and RVI conducted fifteen engagements across technical support, institutional assessments, accompaniment, and specialised training. This included peer-learning sessions on conflict-sensitive research, reviews of FCDO-funded programmes with practical recommendations, and targeted training for partners. The Hub completed three support assessments, initiated HDP organization accompaniment process, and began additional programme-level assessments, demonstrating the adaptability of its framework.
Indicator 4.4: The milestone for this output was not met. Against a target of 13 engagements, the Hub delivered 5 engagements by October 2025. These included the first Conflict Sensitivity Awareness Workshop, two cross-hub peer learning exchanges, and outreach contributions through external platforms. Several factors slowed progress. Recruitment delays for MEL and research roles affected the Hub’s ability to roll out planned activities at the intended pace. The delayed formalisation process with the Ministry of Peace also limited progress on convening work that required government engagement. In addition, the hub noted that some convening functions were not fully resourced, which constrained the number and frequency of learning events and dialogues. Despite this, the Hub established a foundation for future delivery. It developed and piloted its core frameworks, strengthened staff capacity, expanded outreach to a wide range of HDP actors, and generated early demand for further engagement. These preparatory steps position the Hub to scale its convening role in the next period.
Changes to this output during the past year, and planned changes as a result of this review
There were no major changes to outputs 4.1 and 4.2 during the past year. However, two new indicators 4.2 and 4.3 were added following the launch of the Conflict Sensitivity Hub. These indicators were added to better capture technical support, training delivery, and engagement activities under the Hub’s purpose. Based on this review, no structural changes to the outputs are planned, but refinement of indicator definitions and disaggregation is recommended.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead
Recommendations from the previous Annual Review includes the following: i) RVI to strengthen the link between analysis and conflict sensitivity – RVI has taken steps to improve methodological rigour and policy relevance, making outputs more actionable for programme teams and initiating integration of conflict sensitivity into analytical work ii) BE Addis to ensure smooth and timely delivery of the Conflict Sensitivity Hub – completed. Despite not meeting all quantitative milestones, Mercy Corps successfully launched the Hub, which has already generated strong demand from local CSOs iii) BE Addis to establish clear milestones and baselines for all indicators – completed. Updated indicators and baselines have been applied in this year’s AR, providing a clearer framework for monitoring progress and ensuring consistency and iv) RVI to invest in analytics tools to track disaggregated data and improve measurement of online engagement – completed. However, disaggregated data and online metrics remain unavailable, limiting the ability to assess reach and engagement effectively.
Lessons Learned
First lesson is on risk management - partners are experiencing heightened risks in an environment where civic space is shrinking, and control is tightening. The key lesson in mitigating these risks is to anticipate potential challenges and prepare accordingly. This means thinking ahead about what could happen and developing proactive plans to address unseen risks before they materialise. Second lesson on this output is around the approach of conflict sensitivity. From the experience of the Mercy Corps Conflict sensitivity hub, Conflict sensitivity is not a one-off project but an ongoing process and thus to embed it meaningfully within an organisation or programme, the accompaniment approach—which includes coaching and continuous support—is the most effective method.
Recommendations for year ahead
At this stage of the programme, with the Conflict Sensitivity Hub operational and research facility gaining momentum, the team should prioritise strengthening uptake and capturing evidence of how the facility is being used and what changes it has influenced, contributing to Outcome Indicator 4.1 and clarifying how to trace this outcome.
Additionally, the programme needs to review target setting against outcome/output indicators. For example: milestone for Outcome Indicator 4.2 “at least one instance of an FCDO programme being conflict sensitive” is difficult to measure and should be rephrased. Similarly, Indicator 4.3 lists 15 engagements, but these vary significantly in resource requirements and impact; disaggregating the indicator or defining specific milestones for each implementing partner would improve accuracy. Finally, while Indicator 4.2 now reports total downloads/views, the lack of a breakdown between downloads and visits limits its usefulness; this should be discussed with the partner and revised if disaggregated data cannot be provided.
## D: VALUE FOR MONEY
Key cost drivers and performance
During the past year of implementation, there have been minimal changes in the cost drivers for the major inputs required to run the programme effectively. Taking the average across all components the largest share of funds continues to be allocated to activity costs (48%) and programme staff costs (38%). Given the nature of the programme, a significant portion of the available funds is directed toward expertise fees, which explains the relatively balanced allocation between these two categories.
The drivers were agreed with the programme delivery team over a robust scrutiny and negotiation in the initial proposal and consecutive cost extensions to achieve best value for money including expert daily rates are benchmarked’. NPAC costs are less than or equal to 12% of the overall project cost in line with best-practice and expenses are in line with global polices and FCDO marker rates.
The decision to add a programme-funded advisory role was aimed to improve the efficiency and effectiveness of delivery, further reinforcing value-for-money considerations given the programme now includes 14 partners. Having a dedicated advisory resource has proven essential, adding significant value through technical expertise on human rights and peacebuilding, strengthening linkages, and enhancing lesson learning via relationships with key stakeholders. This role has been particularly critical in ensuring coherent programme implementation and alignment with FCDO policy and priorities.
A Value for Money (VfM) matrix was developed and shared with implementing partners as a comprehensive tool to capture VfM metrics and strategies for activities, aligned with the 4E’s framework (economy, efficiency, effectiveness, equity). Its purpose is to gather tangible examples rather than generic responses or justifications for factors affecting programme effectiveness (e.g., weak link between outputs and outcomes) or efficiency (e.g., economic reforms, conflict).
The programme demonstrates strong alignment with the FCDO’s 4E framework—Economy, Efficiency, Effectiveness, and Equity—through cost-conscious delivery, strategic resource use, and inclusive approaches that maximise impact across all components. The following provides an overview of the VfM achievements, categorised by the 4Es:
Economy
The programme has consistently prioritised cost-effectiveness without compromising quality. Partners have adopted innovative strategies to reduce costs; HD saved approximately USD 10,000 by using internal Geneva-based experts for dialogue facilitation instead of hiring external consultants at USD 500–700 per day. CIR negotiated competitive venue rates and leveraged local knowledge to secure cost-effective training spaces, reducing catering and accommodation costs around £13,000 while maintaining quality. ELiDA adopted hybrid and virtual modalities for conferences, reaching 200+ participants online and 1 million via social media at a fraction of traditional event costs. ECSH avoided high overhead costs by leveraging Mercy Corps’ existing infrastructure and hybrid staffing models, ensuring economies of scale. These measures demonstrate prudent financial management, ensuring resources are directed toward programme delivery rather than overheads. By capitalising on internal expertise and competitive procurement, the programme has achieved substantial savings while maintaining high-quality standards.
Efficiency
Efficiency is evident in exceeding output targets within existing budgets. Partners have optimised processes and leveraged synergies: HD established two new dialogue platforms in Oromia and expanded elite-level engagement without additional funding, using existing networks and relationships. ELiDA implemented a phased delivery model (Mapping, Training, Mentorship, Network Establishment), ensuring resources were targeted for maximum impact and avoiding duplication. CIR streamlined grant processes and hired a local liaison to improve oversight and reduce delays, enabling efficient delivery of human rights capacity-building activities. ESCH adopted hybrid training delivery and milestone-based consultant payments, ensuring timely outputs and reducing waste. These strategies reflect strong operational efficiency, converting limited resources into high-value outputs. The ability to exceed targets without increasing budgets demonstrates effective planning and resource allocation.
Effectiveness
Outputs are translating into measurable outcomes that align with programme objectives: CARE reported a threefold increase in women’s participation in decision-making spaces and 92 women assuming leadership roles. HD advanced peacebuilding through multi-level dialogues and exploratory engagement in Oromia and Amhara, contributing to conflict resolution efforts. CIR improved EHRC’s investigative capacity, with trained staff applying OSINT techniques to enhance human rights reporting and case verification. ECSH achieved significant knowledge gains in conflict sensitivity training, with participant understanding increasing from 27% to 91%, and evidence of policy uptake by local CSOs. These achievements demonstrate that programme outputs are effectively contributing to higher-level outcomes and impact. Evidence of behavioural change, policy uptake, and leadership roles among women confirms that the programme is delivering on its strategic objectives.
Equity
Equity principles are embedded across all components to ensure inclusion of marginalised groups: ELiDA deliberately targeted women, youth, persons with disabilities, and ethnic minorities through mapping studies and sub-granting mechanisms. HD ensured 30% women’s participation in dialogue platforms and supported grassroots women’s networks in Oromia. CIR integrated gender equity into all activities, including TFGBV research and toolkit development, ensuring broad impact across vulnerable communities. ECSH prioritised local actors in capacity building (90% national organisations) and maintained gender balance in staffing and participation. These efforts ensure that benefits are distributed fairly and reach those most affected by conflict and marginalisation.
While gender balance and inclusion are embedded across the programme—either as a dedicated activity or through minimum participation targets—the level of women’s leadership remains very limited at the project lead level particularly on Component One. All those providing update, analysis and direction of project are men. It is rare to see women in positions where they lead or manage projects directly unless it is WPS-focused project. This is a gap that the programme should address proactively to ensure that gender equality extends beyond participation to meaningfully steer the project and have a meaningful role at leadership level.
Assessment of whether the Programme continues to represent value for money.
While there are clear areas for improvement, the evidence strongly indicates that the programme is on track to delivering VfM. It demonstrates cost-effective delivery, measurable progress toward intended outcomes, and a commitment to inclusive participation across all activities. Moreover, this programme is the only one contributing to Goal 1 (Stability) of the Country Business Plan reaffirming strong VfM and supporting its continuation. Continued focus on strengthening VfM reporting, enhancing equity in project leadership roles, and improving outcome-level tracking will further consolidate these gains and ensure maximum impact by the end of the programme cycle.
E: RISK
Overview of risk management
HARP’s risk rating is ‘Major’, reflecting its operation in an unstable and fragile environment. The FCDO programme team and partners apply the FCDO risk matrix to identify and mitigate risks, working with a diverse range of international and national partners to balance higher- and lower-risk interventions. A total of 15 risks have been identified across the seven FCDO risk categories, all within the approved risk appetite.
FCDO manages risks through formal and informal mechanisms, including:
- Quarterly reviews of the HARP risk register
- Ad hoc reviews as required
- Enhanced due diligence assessments
- Regular programme dialogue with partners
- Review of quarterly reports
- Delivery chain risk mapping
- Audit
- Beneficiary feedback and reporting mechanisms
- Annual review
Key risks identified as ‘major’ over this year include:
Strategy & Context and Reputational risks present the most critical challenges to programme delivery. Five of six Strategy & Context risks are rated Major, driven by volatile political dynamics, election dynamics with potential tensions, divisions in Tigray risking armed group remobilisation, and civil society funding restrictions—threatening access, timelines, and inclusive governance. Reputational risks, also Major, focus on UK credibility in sensitive contexts, with potential damage from demobilisation without agreement, early DDR withdrawal, and association with bodies facing human rights concerns. Together, these risks underscore a fragile operating environment requiring flexible programming, rigorous political analysis, proactive diplomacy, and transparent communication. Mitigation includes regular conflict analysis, flexible delivery, close coordination with partners, election tension management, human rights adherence, and ongoing engagement with donors to reinforce UK’s commitment to inclusive governance.
Policy & Programme risks comprise two Major-rated risks. The first is budget reprioritisation, which could delay activities and limit achievement of programme outcomes by directly affecting resource allocation and timelines. The second is difficulty in demonstrating results for peacebuilding, given the long-term nature of interventions and the tension between programme duration and measurable progress—posing risks to accountability and donor confidence. These risks call for flexible budgeting, realistic target-setting, and strong monitoring and evaluation frameworks. FCDO will mitigate by setting achievable targets, applying appropriate M&E tools, and conducting regular reviews and external appraisals to ensure results are documented and communicated effectively.
Financial and Fiduciary Risk Comprises one Major and one Moderate rated risks. The programme faces financial and fiduciary risks primarily linked to implementing partners and operational delays. There is a significant risk that partners, including downstream actors, could be implicated in aid diversion, fraud, or corruption, exacerbated by a complex and fast-changing political context, leadership changes, active conflict, and weak oversight mechanisms. To mitigate this, the programme maintains clear communication of expectations and procedures, encourages open reporting of incidents, and ensures timely investigations. VfM indicators are monitored and reported regularly, complemented by annual FCDO audits, spot checks on asset registers, and six-monthly reviews of audit recommendations. Additionally, an underspend risk exists due to delayed budget confirmation and anticipated disruptions during national elections, which may slow implementation. Mitigation measures include close monitoring of partners, prioritizing critical deliverables ahead of the election period, adjusting timelines to accommodate constraints, and activating contingency plans such as advancing next year’s payments where feasible. Issues are escalated promptly to enable reallocation of unspent funds, ensuring programme continuity and financial accountability.
There is an ongoing business-managed programme fraud case that was formally investigated by FCDO’s Investigation Department in London. The programme team is currently following up with the partner to progress towards closure, as the partner has taken responsibility for managing the case. The handling of this case demonstrates the partner’s robust escalation and response mechanisms in addressing complex fraud incidents.
Safeguarding Risk Comprises One Major rated risk. The programme faces safeguarding risks primarily linked to implementing partners’ limited capacity to apply robust safeguarding measures. There is a significant risk that programme activities delivered by partners could unintentionally increase safeguarding vulnerabilities, particularly in contexts with weak systems and limited oversight. To mitigate this, the programme conducts full Due Diligence Assessments (DDA) of all implementing partners to confirm safeguarding policies and mechanisms are in place. Open and regular communication is maintained with partners to ensure beneficiary feedback channels function effectively, and any incidents are promptly reported to the FCDO team, escalated as necessary, and managed in line with FCDO protocols. Safeguarding checks are embedded within the programme’s Monitoring and Evaluation (M&E) framework to reinforce compliance. Residual risk remains Moderate because of the difficult context, but proactive engagement and continuous monitoring aim to minimize exposure and uphold beneficiary protection standards.
During the past year of implementation 3 new and 5 refresher DDAs were conducted, for the new DDAs, only ACCORD had major findings assessed and their suggested recommendation were:
1. for the partner to establish formal system for monitoring downstream partners including due diligence, risk management and reporting mechanism
2. Revise their safeguarding policy to address gaps identified
ACCORD has established formal monitoring systems for the consortium members AWPSI and NEWA, they have conducted due diligence, updated Delivery Chain Risk Mapping and have established quarterly reporting timeframe. They have also revised their safeguarding policy to include guidelines for communicating SEAH and have assigned a focal person for SEAH. Additionally, ACCORD has added clauses that suggest all staff should be trained on SEAH incident response.
The refreshed DDAs had no Major findings assessed with most risks being moderate. To ensure action plans are being implemented, the programme team have been doing housekeeping, checking the progress on agreed actions.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Delivery
During the review period, the performance of HARP of the eleven implementing partners across the four programme components has varied significantly, with some demonstrating exceptional delivery against agreed commitments while others (ACCORD, ELIDA and Mercy Corps) have struggled to meet expectations. High-performing partners have shown strong operational capacity, timely implementation, and proactive risk management, often adapting quickly to contextual challenges and maintaining transparent communication with the HARP team. Conversely, underperforming partners have faced persistent issues such as delays in activity rollout, weak financial and reporting compliance,
The 11 implementing partners of HARP across the four programme components are proofing their standard performance through meeting contractual obligation such as outputs, outcomes, delivery of quality and relevance of activities delivered were showing. The team revised and finalized the programme logframe to better capture partner contributions across four core long-term outcomes and intermediate outputs. This revision included fifteen output indicators, which strengthened the measurement. The report provides recommendations for refining targets and improving indicator prioritization to reduce this complexity.
In terms of compliance and reporting, partners operating under FCDO grant agreements were required to submit quarterly reports, while UN agencies followed the pooled fund arrangement reporting biannually. All partners used a standardized reporting template for both narrative and financial submissions, which included updates on agreed KPIs, safeguarding, fraud, and aid diversion cases, including nil responses. Out of the 11 implementing partners, two of the implementing partners faced a challenge in meeting requirement of quarterly report deadlines in the inception phase. But with continuous support provided from the programme team they can submit timely and accurate quarterly reports.
All implementing partners updated their Delivery Chain Mapping (DCM) and Delivery Chain Risk Mapping (DCRM). The DCM identifies all downstream partners involved in delivering project activities, while the DCRM enables the programme team to capture and manage risks, particularly those related to fraud and aid diversion. Despite operational challenges, the programme demonstrated strong compliance with FCDO PRoF rules and procedures, with partners largely adhering to reporting and risk management frameworks.
To foster a better collaboration between implementing partners and encourage cross project understanding, the HARP team also organises an annual coordination meeting gathering all implementing partners including second tier consortium partners. The last coordination meeting held a session on conflict sensitivity run by RVI. The coordination meetings have helped implementing partners in finding areas of collaboration which in turn increases coherence to achieve the overall HARP objectives.
Overall, strengthened coordination mechanisms, ongoing monitoring, and continuous refinement of programme implementation have contributed to improved effectiveness and impact.
Commercial
During the Annual Review period, the programme had twelve active contracts (ten accountable grants and two MOUs). In December 2025, two additional agreements—one accountable grant and one MOU—were introduced to support election-focused programming, bringing the total to fourteen. Four contract amendments were also completed for ELiDA, CR, RVI, and OHCHR to enable project scale-up and provide additional funding.
All new agreements and amendments were managed in line with the Programme Operating Framework (PRoF). The programme management team ensured each proposal and amendment underwent a rigorous review process, including budget and narrative scrutiny to confirm best VfM. Furthermore, all documentation was reviewed by the Strategic Delivery Unit (SDU) for quality assurance, adding an extra layer of compliance and ensuring adherence to FCDO standards on governance, risk management, and VfM. The programme team also secured all necessary approvals before development director sign offs.
Financials & audit
During the reporting period, implementing partners’ financial reports were generally clear and reliable. In the initial months of newly launched projects, some partners experienced delays in meeting deadlines. The programme team addressed these challenges through regular monthly catch-up meetings and by clarifying FCDO expectations on financial standards. Continuous feedback was provided to partners, including one-to-one discussions with the embedded finance professional focused on grant management, which helped strengthen compliance and improve timeliness. For partners whose last audit was conducted over a year ago, audits have been completed recently or are currently in progress. Some partners have commissioned independent audits that clearly segregate FCDO project funding within their financial statements, ensuring transparency and compliance. Others have opted to include FCDO project funding within their annual audited accounts, accompanied by a certified statement from an independent and appropriately qualified auditor confirming the accuracy of the allocation.

Summary of programme budget vs spending report as of Jan 2025.
Component	Project Title	Contract value under HARP	Year to date spending	% Utilisation
301191-101	Peace by piece	£4,509,828	£2,347,538.54	52.05%
301191-102	Empowerment of EHRC	£3,501,111	£3,105,300.00	100%
301191-103	Women leadership in peace recovery	4,020,663	£2,766,195.00	68%
301191-401	Independent Monitoring and Evaluation	£131.33	£131.33	100%
301191-402	Leveraging the peace process	£1,800,000	£1,200,000.00	66.67%
301191-403	National Demobilization and Reintegration	£16,000,000	£16,000,000.00	100%
301191-404	Supporting Dialogue to End conflict in Oromia	£987,494	£434,221.00	43.97%
301191-405	Ethiopian Peace Research Facility	£2,263,660	£1,034,401.31	45.70%
301191-406	Ethiopian Conflict Sensitivity Hub	£600,594	£312,304.47	52%
301191-407	Technical Assistance to the National demobilization and reintegration	£99,677.17	£99,677.17	100%
301191-408	Building localization and resilience for WPS	£850,000	£268,149.13	31%
301191-409	Women count for peace	£1,019,752	£565,598.00	55.46%
301191-410	TA for provision of peacebuilding and capacity support	£473 453.5	£120,161.00	25%
301191-411	Strengthening the capacity of EHCR and monitoring	£1,011,708.17	£490,709.29	48.50%
301191 -412	Strengthening Ethiopia Election for Democratic Sustainability	£1,500,000	£1,200,000	80%
301191-413	Inclusive interparty Dialogue	£300,000	£115,880	38%
301191-414	Support and strengthen NEBE system	£900,000		0%
Total		£39,364,619	£30,060,266.24	76%

Spending in the first quarter of the fiscal year was slow, primarily due to the late confirmation and release of the budget. This resulted in funds being disbursed to implementing partners only in the final month of the first quarter, which delayed activities and negatively affected expenditure. Consequently, this had a knock-on effect on the overall utilisation rate for the fiscal year.

G: MONITORING, EVIDENCE AND LEARNING
Monitoring and Evaluation
At the programme level, HARP continues to rely on its logframe as the primary tool for monitoring and evaluating impact. The logframe remains essential for structuring M&E processes; however, challenges persist in ensuring alignment with evolving context and challenges, addressing data quality issues, and effectively communicating outcomes. While the logframe provides a structured approach, its format can limit the ability to capture nuanced achievements and comprehensive impacts, which are often process-driven in nature. To strengthen monitoring, the HARP team conducts quarterly field visits with partners. During the review period, monitoring visits were carried out in implementation areas, including Jijiga, Mekelle and Adigrat.
Most partners employ traditional or participatory MEL approaches, while some have adopted innovative methods. For example, HD applies an adaptive MEL approach that combines the strengths of the logframe with an expanded evidence base, offering a realistic framework for assessing the value of peacebuilding efforts. CARE implements a systematic and participatory MEAL (Monitoring, Evaluation Accountability and Learning) approach, incorporating tools such as key informant interviews and significant change stories to capture outcomes throughout the activity cycle. Similarly, UNOHCHR utilises its Performance Monitoring System (PMS), an internet-based platform aligned with results-based management principles for planning, monitoring, and reporting. CR has adopted Outcome Harvesting, an approach that blends outcome mapping—focusing on behavioural change—with utilisation-focused evaluation to ensure findings are practical and actionable. Overall, these diverse approaches demonstrate a commitment to robust monitoring and evaluation, enabling the programme to adapt and respond effectively to complex operating environments.
Evidence
The HARP programme log frame, with its defined quantitative targets, combined with publicly available partner data and statements, provides a solid evidence base for assessing progress against the programme’s monitoring and evaluation framework. The logframe enables systematic tracking of key metrics, offering quantitative insights into intervention frequency, geographic coverage, and some level of measurable improvements in awareness across target regions. In addition to quantitative evidence, partners’ quarterly reports, public statements, and findings from monitoring visits and discussions with partners provide qualitative insights. These complement the numerical data by capturing context-specific changes, stakeholder perceptions, and nuanced shifts in programme impact across all components. Together, these sources present a comprehensive picture of progress and effectiveness.
Learning
The programme’s current results framework does not fully capture the depth and breadth of learning generated during implementation. This review period surfaced critical lessons that hold significant value for FCDO and the wider conflict and peacebuilding community. Key insights include reflection on thinking around multi-approach dialogue strategies, the importance of adopting a holistic WPS approach that integrates livelihood support and emergency response, and the necessity of cross-sector collaboration to achieve sustainable peace outcomes. Further lessons emphasise the role of local partnerships and trust-building, as well as the challenge of maintaining credibility while managing risks—particularly balancing rigorous research standards with relationship-building to mitigate risks without compromising core values. Another important takeaway is the need to frame conflict sensitivity as a continuous process rather than a fixed outcome.
Looking ahead, the HARP team should prioritise the systematic capture and documentation of lessons learned to inform future programming and shape the next generation of conflict and peacebuilding initiatives in Ethiopia. This process could begin by leveraging existing coordination platforms, creating structured opportunities for knowledge sharing, and establishing mechanisms for recording and disseminating lessons learned. Doing so will ensure that valuable insights are not only retained but actively used to strengthen programme design and delivery.
Date of last narrative financial report	CR	October 2025	Date of last audited annual statement	October 2025
	DIHR	October 2025		July 2025
	CARE	October 2025		January 2024
	OHCHR	October 2025		March 2025
	UNDP-DDR	January 2026		December 2020
	CHD	October 2025		August 2024
	RVI	October 2025		December
	MC	October 2025		2024June 2025
	ACCORD	October 2025		August 2025
	ELiDA	October 2025		March 2025
	CIR	December 2025		November 2025
	ASI	April 2025

Annex I – List of Key Acronyms
Acronym	Full Form
ACLED	Armed Conflict Location & Event Data Project
AR	Annual review
ACDD	Advocacy Center for Democracy and Development
ACCORD	the African Centre for Constructive Resolution of Dispute
AWPSI	Africa Women Peace and Security Institute
BE	British Embassy
CR	Conciliation Resources
CRSV	Conflict Related Sexual Violence
CSO	Civil Society Organization
CETI	Climate Economy Trade and Investment Team
DIHR	Danish Institute for Human Rights
ELiDA	Empathy for life integrated for Development Association
EHRC	Ethiopian Human Right Commission
ENDF	Ethiopia National Défense Force
EMAP	Engaging Men in Accountable Practices
EWNET	Ethiopian Women’s Network for Education and Training
IRCE	Inter-Religious Council of Ethiopia
FCDO	Foreign, Commonwealth and Development Office
NHRI	National Human Rights Institutions
GBV	Gender Based Violence
HARP	Human Rights and Peacebuilding program
HMG	His Majesty’s Government
HR	Human Rights
HD	Centre for Humanitarian Dialogue
HDP	Humanitarian, Development, and Peacebuilding
JACS	Joint Assessment of Conflict and Stability
K4P	Knowledge for Peace
M&E	Monitoring and Evaluation
MoU	Memorandum of Understanding
NEBE	National Election Board of Ethiopia
NEWA	Network of Ethiopian Women’s Associations
NRC	National Rehabilitation Committee
NDRP	National Demobilisation and Reintegration Programme
NHRI	National Human Rights Institutions
NRTD	National Recommendation Tracking Database
OHCHR	Office of High Commission for Human Rights
OSCs	One Stop Centres:
ONLF	Ogaden National Liberation Front
PRF	Peace Research Facility
PSEA	Protection from Sexual Exploitation and Abuse
RVI	Rift Valley Institute
RGA-P	Rapid Gender Analysis on Power and Participation
SGBV	Survivors of Gender Based Violence
SIRAD	Somali Institute for Research and Development
SRVN	Somali Regional Victims Network
ToC	Theory of Change
TRC	Truth and Reconciliation Commission
TPLF	Tigray People’s Liberation Front
UK	United Kingdom
USRI	Umbrella for Somali Region Intellectuals
UPR	Universal Periodic Review
UNDP	United Nations Development Programme
UN OHCHR	Office of the United Nations High Commissioner for Human Rights
VFM	Value for Money
WPS	Women Peace and Security
WPDNO	Oromo Women Peace and Development Network
WAT	Women’s Association of Tigray
WLiE	Women Leading in Emergencies
WLOs	Women-Led Organizations

Annex II – Action points for Recommendations

No.	Recommendations & Suggested Actions	Owner (in Bold)	Deadline
1	Strengthening Strategic Linkages Across the FCDO Portfolio / to identify existing cross-portfolio linkages (conflict sensitivity, IDP returns, human rights, humanitarian delivery) and develop a strategic linkage plan showing how HARP activities contribute to broader FCDO Addis objectives / Establish a regular coordination mechanism (monthly/quarterly) to proactively engage instead of ad hoc engagement. / To incorporate HARP outcome across FCDO portfolio (to the extent possible) in the upcoming multi-year country business plan process	PRO + CAs	June 2026
2	Strategic Coherence for Local and National Peacebuilding / Develop some sort of Strategic Linkage Framework/narrative/ the approach to align local dialogues with national peace objectives. / Explore idea on how to maintain flexible resource allocation for emerging high-level dialogue opportunities including existing budget allocation and plans to maintain flexibility	PRO + CAs + Programme management team on resource allocation discussion	June 2026
3	Framing Election Support Through a Violence Reduction Lens / Develop clear document on risks attached to supporting election and update HARP ToC assumptions accordingly. / Designing election support component and ensure that all activities are designed to prevent and mitigate election-related violence / Develop plans to link up with other components on HARP and identify ways to monitor risks and its impact across components	SRO, PRO + Governance Advisors and CAs	January 2026
4	Developing a Cross-Office Human Rights Approach and Diversifying Support: / Start a process to discuss a structured cross-office human rights approach and what it could look like and develop a cross-office human rights approach / Identify existing support for CSOs and discuss with partners on ways to maximise support (eg. CIR)	Conflict Advisor (HR Lead)	June 2026 (end of Q1) / March 2026 (end of this FY)
5	Strategic Coherence of WPS / Mapping current partner activities against areas of greatest impact and influence, aligned with the five strategic objectives of the UK National Action Plan (NAP This will help identify / Define priority areas for impact and focus resources on advancing strategic-level outcomes for the remaining years	Conflict Advisor (WPS Lead)	June 2026 (End of Q1)
6	Increase Uptake of Conflict Sensitivity Component / Start a discussion on how to track and better understand the application of products and support from conflict sensitivity (CS) resources and develop an ongoing approach to i) maximise uptake ii) establish a systematic method to monitor uptake and iii) systematic way to track ‘uptake’ and integrate into outcome level log frame	Conflict Advisor (PRF Lead) + PRO and CAs
7	Review Log frame / Establish systematic tracking methods for outcome progress and data consistency / Update Assumption on ToC, outcome and output 1 and indicators to include election-related activities. / Reset milestones, increasing ambition where feasible.	PRO + CAs + HARP team	June 2026
8	HARP Team Ways of Working / Discuss on shifting to theme-based coordination (WPS, Human Rights) led by thematic advisors across components. / Explore additional programme management support to address capacity gaps (currently 2 staff for 14 partners).	PRO + HARP team	June 2026

Annex III – HARP Log frame