## Annual Review Template

Title: Building a Resilient Health System to End Preventable Maternal, New-born and Child Deaths in Ethiopia
Programme Value £ (full life): £100m		Review date: 28/05/2025
Programme Code: 301196	AMP start date: / 01/04/2023	AMP end date: 31/03/2028

Summary of Programme Performance
Year	23/24	24/25
Overall Output Score	A	B
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003183.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004503.xlsx

# Abbreviations and Acronyms

ACP ANC AR Gates CPR CAR DLIs DHS DHIS2 EFY EPD-E EPSS FCDO FP FRA Gavi GF HMIS HPF HPN HSDIP HSTP IDP ICF KPI MMR MOH OPD P4R PDEL PPA PRO PFM RHB RMNCAH SBA SDG-PF SRH SRO TA TAMU TPMA TWG VfM WB WHO UNICEF UNOPS YL	Annual Comprehensive Plan Antenatal Care Annual Review The Gates Foundation Contraceptive Prevalence Rate Contraceptive Acceptance Rate Disbursement Linked Indicators Demographic and Health Survey District Health Information System Ethiopian Fiscal Year End Preventable Maternal, New-born and Child Deaths in Ethiopia Ethiopian Pharmaceutical Supplies Services Foreign, Commonwealth, and Development Office Family Planning Fiduciary Risk Assessment Global Alliance for Vaccines and Immunization Global Fund Health Management Information System Health Pooled Fund Health, Population and Nutrition Health Sector Development and Investment Plan Health Sector Transformation Plan Internally Displaced People International Climate Finance Key Performance Indicators Maternal Mortality Ratio Ministry of Health Outpatient Department Payment for Result Programme Delivery Excellence Lead Partnership Principles Agreement Programme Responsible Owner Public Financial Management Regional Health Bureau Reproductive, Maternal, Neonatal, Child and Adolescents Health Skilled Birth Attendance Sustainable Development Goal Performance Fund Sexual Reproductive Health Senior Responsible Owner Technical Assistance Technical Assistance Management Unit Third Party Monitoring Agent Technical Working Group Value for Money World Bank World Health Organization United Nations International Children's Emergency Fund United Nations Office for Project Services Young Lives

A. SUMMARY AND OVERVIEW

Description of programme
The "Building a Resilient Health System to End Preventable Maternal, Newborn and Child Deaths in Ethiopia (EPD-E)" programme seeks to strengthen Ethiopia's health system resilience, focusing on reproductive, maternal, newborn, and child health (RMNCH) and to promote universal health coverage (UHC). The £100m, 5-year programme is aligned to Ethiopia’s national health plan and intends to reduce maternal mortality rate (MMR) from 401 to 279, under-five mortality from 59 to 44 per 1000 live births and increase the Universal Health Coverage index from 65.5 to 68, and the Health Security Index (HSI) from 0.63 to 0.78.

The EPD-E programme is an integral part of British Embassy’s country business plan, contributing to the third goal: invest in human capital, building a healthier and better-educated society, ending preventable deaths, improving outcomes for women and girls and building resilience to shocks. EPD-E is helping establish an equitable, high-quality healthcare system that effectively reduces preventable deaths among mothers and
young children while enhancing the capacity to respond to public health threats.

The EPD-E programme combines financing for service delivery through government channels and technical assistance to build the long-term capacity of the health system. The service delivery support, delivered through the SDG Performance Fund (SDG-PF), focuses on enhancing health system delivery, particularly in RMNCH services, disease surveillance, and response. The programme is one of the interventions led by British Embassy
Ethiopia, to address global disease threats. The SDG-PF is a pooled funding mechanism managed by the Federal Ministry of Health (MoH). Other donors include the WB, FCDO, GAVI, Spain, Italian Cooperation, UNICEF UNFPA, WHO and the Gates Foundation.

EPD-E also includes two technical assistance (TA) components. The first is designed to improve the effectiveness of RMNCH service delivery investments and to build the long -term capacity of the health system to improve care quality, equity and public health financial management. UNOPS delivers this component at both federal and sub-national levels, supported by FCDO through EPD-E, the Italian Development Cooperation, and the Gates Foundation. This component addresses challenges such as high staff turnover and retention of qualified workers, focusing on health systems strengthening, grant management, resource mobilisation, and skill transfer. A second TA component is implemented by the Young Lives Project, which provides longitudinal study data to enhance the evidence base informing our policy and subsequent programming choices. Young Lives provides data on the interactions between education, health/nutrition and work/family lives for young people in Ethiopia. Insights from the study will inform EPD-E data gaps, and assist the GoE in evidence-led policy making.

The TA components are new to this reporting year of the programme and not yet fully reflected in the key outputs of the logframe.

Summary supporting narrative for the overall score in this review

Each of the 4 outputs of this programme has scored a B, resulting in an overall score of B for this annual review. Key successes over the review period include strong demand and uptake of critical Reproductive, Maternal, Newborn, and Child Health (RMNCH) interventions, particularly in antenatal care and immunisation coverage. The programme has facilitated significant improvements in the quality of child health services, with high rates of immunisation and vitamin A supplementation reported in several regions. Efforts to address regional and socioeconomic inequalities have resulted in some progress, though disparities in service coverage between pastoralist and non-pastoralist regions, and between high- and low-performing districts, remain pronounced. The programme has also contributed to improved health facility sanitation and epidemic response, though performance on medical waste management and epidemic control fell short of targets.

Persistent challenges include data reliability issues, particularly due to the lack of accurate census data and population denominator problems, which affect the confidence in reported coverage rates. Conflict and insecurity in several regions have continued to restrict access and strain resources, limiting the reach and impact of interventions. Supply chain inconsistencies, especially for contraceptives and essential equipment, have also affected service delivery in some areas.

This annual review was conducted by a PRO/ Health Adviser, Deputy Programme Manager, Social Development Adviser, Head of Finance, and Policy Adviser at the British Embassy. It included visits to Afar and the Jimma Zone in Oromia.

Major lessons and recommendations for the year ahead
The 2024/5 context was challenging. Healthcare delivery and access to healthcare was severely affected in conflict-affected regions such as Amhara, Tigray, Afar, Oromia, and Benishangul-Gumuz. This was compounded by US aid cuts, which among others led to the dismissal of thousands of healthcare workers at the woreda and facility level, with impacts on vaccination campaigns and routine service provision. This underlined the need to redouble collective efforts towards ensuing health financing sustainability. Moreover, an IMF/ World Bank programme was agreed in late 2024, with seemingly mixed immediate impact on the social sectors, including health. The programme’s theory of change should be revisited by September 2025 (see recommendation #1 below), given the significant changes in external context and issues with the results framework.

FCDO has conducted an FRA in 2024, covering six pillars, with 31 findings. Top FCDO SDG-PF priorities include budget reliability, transparency of internal controls, predictability and control in budget execution, as well accounting, reporting and procurement. Following the FRA findings, the MOH has implemented several mitigation measures. These include launching the Channel Two Finance Administration for the Health Sector directive number 979/2024, an MoU signed between the Ministry and RHB heads, and the establishment of an audit oversight committee with the support of FCDO-funded TA. The efforts are aimed at addressing continuous underspend and bringing more predictability and control in budget execution.

Issues remain such as the absence of good budgetary monitoring; disjoined budgeting controls that cause delays in disbursement; control risks due to the excessive use of advances; the proliferation of different accounting system in the MoH and RHBs causing continued miscoding of data, posting duplication and unreconciled accounts. As an illustration, the most recent financial report used for this review indicates weak budget utilisation (7% utilised and 31% committed from the approved budget). It demonstrates that initiatives such as the Channel 2 directive or the MOU signed between MoH and RHBs are yet to deliver concrete improvements. The FCDO should continue working with development partners and the MoH through the SDG-PF to enhance budget utilisation via early approval of Annual Comprehensive Plan (ACP), follow the implementation and impact of the financial directive and MoU, settle the proliferation of different accounting systems, and thoroughly scrutinise the procurement plan and its implementation, as this makes up for more than 75% of the ACP value. FCDO will need to clearly set out the financial management conditions which would enable disbursement to the SDG-PF.

Regional health disparities persist, notably in pastoralist and, as above, conflict-affected areas. FCDO is currently co-chair of the SDG-PF. FCDO should use their influence to ensure the pooled fund continues to address these inequities, with targeted interventions within the wider pooled fund. On data, visits have illustrated ongoing challenges around availability, quality, accuracy and utilisation. These challenges are also reflected in the reliability of the official MOH data used in this annual review. Efforts should be concentrated on ensuring that a robust M&E strategy and results framework is in place. Insights generated by the Young Lives Project, supported by the TA component of this programme, should be fully reflected. Moreover, lessons should be integrated from the forthcoming SDG- PF Impact Assessment, which is evaluating how the SDG-PF financing mechanism has contributed to Ethiopia’s health sector between 2015 and 2023.

Recommendation	Timeframe
#1 Revise the Business Case theory of change: Given ongoing challenges such as extended conflict in large parts of the country, and recent ones, including significant withdrawal of donor support, and the IMF/World Bank Programme agreed in 2024, revise the ToC for the programme. (FCDO)	September 2025
#2 FCDO Programme management: FCDO improves programme management and monitoring, including through putting an M&E strategy in place, as a matter of priority. FCDO to ensure clear roles and responsibilities in the strategy and delivery of the programme. (FCDO)	September 2025
#3 Logframe and alignment with DLIs: Evolve the current logframe, paying close attention to results attribution (setting out clearly what results UK financing is achieving through the financing), as well as data availability and quality. Assess whether to better align logframe to the DLIs applied by the WB P4R programme and other partners. (FCDO)	September 2025
#4 SDG – PF financial management: Work with development partners and the MoH through the SDG-PF to enhance budget utilisation via: early approval of the ACP; following the implementation and impact of initiatives such as the financial directive and MoU; settling the proliferation of different accounting systems; and thoroughly scrutinising the procurement plan and its implementation. Set out outstanding financial management conditions for the FCDO to make its next payment into the SDG- PF within the next quarter. As per recommendation #3, assess whether to link disbursement with the DLIs. (FCDO)	September 2025
#5 Strategic use of SDG- PF chairpersonship role: Given the FCDO also chairs the SDG- PF for the upcoming year, develop a strategic plan for how to use this position effectively to better deliver the EPD-E programme. (FCDO)	August 2025
#6 Technical Assistance – relevance and monitoring: FCDO and UNOPS to set out a strategy for how the TA element delivered by UNOPS can most effectively support the delivery of programme outcomes and impact. FCDO to include indicators to accurately measure the performance of the TA element in the next iteration of the EPD-E logframe. (FCDO, UNOPS)	September 2025
#7 Value for Money (VfM) indicators: Assess how to incorporate VfM indicators in the results framework. (FCDO)	September 2025

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Building Health System Resilience to End Preventable Deaths in Ethiopia (EPD-E) programme's Theory of Change builds upon the Sustaining and Accelerating Primary Health Care in Ethiopia (SAPHE) initiative. It is harmonised with Ethiopia’s Health Sector Transformational Plan 2 (HSTP2) (2020-25) and the WHO’s Theory of Change for Africa. Initially based on HSTP, the Theory of Change now aligns with the Health Sector Development and Investment Plan (HSDIP), the successor to HSTP2.

The intended impact of the programme is to reduce maternal, new-born, and child mortality by strengthening the resilience of the health system. Progress towards this impact is measured through three key outcomes. Firstly, the programme aims to increase Universal Health Coverage, as assessed by the UHC score. Secondly, it seeks to enhance Health Security, measured by the Health Security Index. Thirdly, the programme is working to increase domestic financing for health.

To achieve these outcomes, the programme delivers a series of outputs. It focuses on improving the uptake of the highest impact package of RMNCH interventions, which directly contributes to both increased Universal Health Coverage and Health Security. The programme also works to reduce regional and socioeconomic inequalities in essential RMNCH service coverage, and to improve the quality of maternal and new-born health services, both of which are closely linked to the first two outcomes. Additionally, the programme enhances disease surveillance and response, further supporting progress towards Universal Health Coverage and Health Security. Finally, by improving RMNCH programme planning, budgeting, and financial management, the programme contributes to increased domestic financing for health.

There were no changes to the outcome or impact indicators from the original business case.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The EPD-E programme remains partially on track to contribute to its intended outcomes and impact, with all four outputs scoring a B in this review period as per above. According to MOH data, there has been tangible progress in several key areas, notably in the uptake of high-impact RMNCH interventions, improvements in the quality of child health services, and the strengthening of health facility sanitation and disease surveillance. These achievements are reflected in increased antenatal care coverage, high rates of immunisation and vitamin A supplementation, and improved access to basic sanitation in health facilities. The programme’s technical assistance components have also begun to strengthen the MOH’s capacity for planning, monitoring, and delivery.

However, persistent challenges continue to affect the programme’s ability to fully achieve its outcomes. Data reliability remains a significant concern, particularly due to the lack of accurate census data, which undermine confidence in reported coverage rates and make it difficult to measure progress precisely. Regional and socioeconomic inequalities in service coverage persist, especially in pastoralist and conflict-affected areas, where access to essential health services remains limited. Ongoing conflict and insecurity in several regions have strained resources, damaged infrastructure, and restricted the ability to monitor and deliver services. Supply chain inconsistencies, particularly for contraceptives and essential equipment, have also impacted service delivery.

To address these challenges and ensure continued progress towards the expected outcomes and impact, several actions are planned for the year ahead. The programme will prioritise improving data quality and availability, including revising indicators and considering alternative data sources to triangulate MoH data. Efforts will continue to target support to conflict-affected and underserved regions, with a focus on reducing regional and socioeconomic disparities in health service coverage. The programme will also strengthen its monitoring and evaluation strategy, including through a renewed logframe. Financial management will be enhanced by setting out clear conditions for future disbursements and improving budgetary monitoring and controls. Finally, the programme will work to better integrate climate adaptation and crisis response, including the addition of relevant indicators to the logframe and closer collaboration with FCDO’s humanitarian programme.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme demonstrates an effective approach towards addressing crucial health needs, aligned behind Ethiopian priorities. There is evidence of progress in key areas, such as demand and uptake of critical RMNCH interventions and improvements in the quality of child health services, which indicate the program's effectiveness. The two modalities - implementation of services through targeted financial aid to the GoE and technical assistance support through TAMU and Young Lives, are in line with the Lusaka Agenda, which promotes coordinated actions for achieving equity in health outcomes. Considering the decision to reduce UK ODA spend to 0.3 of GNI from 2028, it is possible that the EPD-E might need to alter focus in future years.

## C. DETAILED OUTPUT SCORING

Output Title	Improved uptake of the highest impact package of RMNCH interventions
Output number:		1	Output Score:	B
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Contraceptive Prevalence Rate (CPR)	43%	N/A / *Census not completed
1.2 Deliveries attended by Skilled Birth Provider (Percentage)	76%	74%
1.3 Proportion of pregnant women who received antenatal care (ANC) - 8 contacts or more (Percentage)	25%	27%
1.4 Proportion of children participating in Growth Monitoring and Promotion (GMP) for 0-24 months (%)	70%	66%

Briefly describe the output’s activities and provide supporting narrative for the score.

32% of the FCDO’s SDG-PF contribution under EPD-E is allocated to family planning activities. The output focuses on enhancing the uptake of critical Reproductive, Maternal, Newborn, and Child Health (RMNCH) interventions.

Indicators 1.2 and 1.3 met expectations. Indicator 1.4 did not meet expectations. Data for indicator 1.1 was not available, due to the census not being completed. However, proxy indicators (declining birth rates, reduction in maternal mortality) and anecdotal evidence from monitoring speaks to good availability and strong demand for contraception and therefore a likely increasing contraceptive prevalence rate, despite supply challenges, particularly in conflict affected areas. The lack of available data for 1.1 and the partially met 1.4 indicator therefore means output 1 scores a B.
- Indicator 1.1: The core indicators the MoH uses to measure and track the performance of family planning program through the routine health management information system (HMIS) includes the contraceptive acceptance rate (CAR), contraceptive method mix, and immediate postpartum contraceptive acceptance rate. CAR, representing the proportion of non-pregnant women aged 15-49 accepting modern contraceptives, has risen over the years. In 2016 EFY, over 16.4 million women (75%) received modern contraceptives. In 2016 EFY, the most used contraceptive method was injectable (52%), followed by implants (28.7%) and Oral Contraceptive pills (15.9%). From the total contraceptive acceptors in the fiscal year, 31% received long term contraceptive methods, while 69% received short term contraceptives. This is consistent with trends from preceding years.
- Indicator 1.2: Over the past six years, the proportion of women who delivered at health facilities assisted by skilled health professionals has consistently increased from 62% in 2011 Ethiopian Fiscal Year (EFY) to 75% in 2015 EFY. It stood at 74% in 2016 EFY (this review period). Given the positive long term-trend, and achievement of results close to the milestone, this indicator scores an A. There is a high disparity in performance among regions, ranging from the lowest performance in Afar (37%) to the highest in Harari and Addis Ababa regions with a performance more than 100%.
  [note] The Ethiopian Fiscal Year (EFY) runs from 8 July to 7 July of the following year.
- Indicator 1.3: more than 1 million pregnant women received at least eight ANC contacts during their pregnancy period. This is 27% of the total expected pregnant women in the year. Performance varied among regions, ranging from 2% in Tigray to 73% in Addis Ababa.
- Indicator 1.4: In 2016 EFY, more than 3.7 million (66%) of children under 2 years of age have received growth monitoring and promotion service. Regional analysis reveals significant disparities in service coverage. The Afar, Somali, and Gambella regions reported the lowest achievement rates at 6%, 4%, and 7% respectively. In contrast, several regions surpassed the national average, with Tigray leading at 86%, followed by Oromia (77%), South Ethiopia (66%), Sidama (72%), and Harari (67%).
Monitoring visits have shown great demand for family planning services, as reported by health professionals across various health centres, posts, and facilities. The most in-demand contraceptive is the medium-term contraceptive, which provides effective birth control for several months. However, the supply of medium-term contraceptives the reviewers observed was inconsistent, especially in Oromia, due to very strong demand and inability of the pharmaceutical delivery system to shift stock between facilities. Authorities reported that there were establishments with excess medium-term contraceptives but no mechanisms to re-deliver the stock where needed. Additionally, many health facilities face critical shortages in complementary areas, including a lack of running water in labour wards, inadequate lighting, absence of ultrasound and premature birth support equipment, and no refrigeration for oxytocin used to manage postpartum haemorrhage (PPH).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicator 1.4 was added - “Proportion of children participating in Growth Monitoring and Promotion (GMP) for 0-24 months" since last year’s AR to measure a critical metric of child health and development, emphasising early intervention.

The indicator for 1.1 will be revised, considering ongoing issues with census data for CPR. CPR is fundamentally an outcome indicator, typically used in evaluations to assess the progress achieved among those reached by the programme, either at critical milestones or upon project completion. To monitor programmes on a routine basis, output indicators are best suited. Secondly, as EPD-E’s major investment is in procurement of RMNCAH commodities it is essential to select output indicators that are useful for monitoring commodity delivery/availability, provide valuable information on service uptake and client choice such as the contraceptive acceptance rate (CAR), which reflect the number of new users and indicates service uptake, and /or the contraceptive method mix , which shows the distribution of methods chosen and can inform procurement needs.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Following recommendations from the previous AR, efforts were made to provide differentiated support to conflict-affected regions, particularly Tigray, from the SDG-PF. While the conflict in Tigray has greatly subsided, ongoing conflicts in Amhara, Oromia, Benishangul, and Gambella have continued to strain resources, damaged existing infrastructure and systems, and restricted our ability to access and monitor in these regions. Although a portion of the SDG-PF was allocated to these conflict-affected regions, the demand for support far exceeds the available interventions. The UK will continue to advocate for enhanced support for conflict-affected regions through the SDG- PF.

Recommendation	Timeframe
#8 Revise indicators for output 1, particularly 1.1, and work with partners to ensure access to reliable data sources that can be used to triangulate MoH data (FCDO).	September 2025
#9 Work through complimentary mechanisms to drive performance: Work with donors and MoH through other complimentary mechanisms (JCC, CCM) to improve performance across output 1 areas (FCDO, MOH).	November 2025

Output Title	Improved quality of child health services including nutrition services
Output number:		2	Output Score:	B
Impact weighting (%):		35%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Children 12-23 months immunised with Pentavalent 3 vaccine	70%	100%
2.2 Vit A supplementation (two dose)	30%	90%
[note] Ministry of Health - Annual Performance Report of 2016 EFY – among eligible infants
[note] Ministry of Health - Annual Performance Report of 2016 EFY

Briefly describe the output’s activities and provide supporting narrative for the score.

Improving the quality of child health services, including nutrition services, focuses on essential childhood immunisation to reduce the risk of preventable diseases (e.g. measles, polio, rota) and vitamin A supplements to maintain strong immune systems and reduce the incidences of diarrhoea and measles in children.

Through the SDG-PF, the UK supports childhood immunisation through facilitating nationwide catch-up vaccination for zero dose and under-immunised children and improving the immunisation supply chain management system. The latter includes the forecasting of need, procurement of vaccines and cold chain equipment, and the coordination of distribution and storage in collaboration with Ethiopian Pharmaceutical Supplies Service. This output scores a B, though, due to low confidence in data reliability, mainly due major population denominator issues stemming from the lack of accurate census data, as discussed below.
- Indicator 2.1: measures the number of eligible infants receiving combined vaccine to protect against diphtheria, tetanus, whooping cough, hepatitis B and haemophilus influenza type B. Some regions exceeded this target, including Oromia (117%), Central Ethiopia (110%), Harari (117%) and Addis Ababa (169%), while Tigray (66%), Benishangul Gumz (81%), and Dire Dawa (83%) fell below 90% coverage. According to the MoH’s annual report (EFY 2016), this overestimation is primarily due to population denominator issues. These issues involve challenges in accurately estimating the total number of children who should receive immunisation. Thie is due to inaccurate census data, high internal migration rates due to conflict, and variations in data collection methods. Such inaccuracies led to underestimating the target population, thereby affecting reported coverage rates, hence the immunisation coverage appearing artificially high. The programme has identified an estimated 3,987,986 zero-dose (ZD) children between 2019-2023 and numerous under-vaccinated children. To address this, catch up vaccination programs were conducted, especially in low performing, conflict/emergency affected areas. As a result, more than 584,000 zero-dose children were vaccinated during the EFY 2016.
- Indicator 2.2: According to MoH reports, during the EFY 2016, over 13 million children aged 6-59 months received two doses of vitamin A supplementation, achieving a coverage rate of 90%. This number is again subject to the same population denominator issues as indicator 2.1. The Somali region reported the lowest coverage at 20%, followed by Dire Dawa (24%) and Benishangul-Gumuz (30%). In contrast, several regions show high performance rates, with Sidama achieving 98.6%, while Afar and Addis Ababa reached 100% coverage, Oromia and Amhara regions also performed well, both attaining 86% coverage.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

As above, population denominator issues mean it is challenging to judge progress for this output. Recommendation 9 below will ensure the FCDO programme team considers alternative indicators.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Although policy frameworks for immunisation exist, significant policy challenges persist. The most pressing issues centre on equity, financing, and logistics. As support from the GHIs and bilateral development partners might be on a downward trajectory, it becomes increasingly important to advocate for greater domestic budget allocation for immunisation. Another key policy priority is to ensure that zero-dose and under-immunised children—particularly those living in remote, conflict-affected, and marginalised communities—are not left behind. Addressing weaknesses in the supply chain and cold chain systems is also critical, as this will help prevent stockouts and wastage, ensuring that vaccines remain available and effective.
Beyond these immediate concerns, strengthening the foundations for effective delivery is essential. Key to this are community engagement and human resources development, ensuring immunisation services are managed and delivered efficiently across the country.

Recommendation	Timeframe
#10 Consider alternative indicators and data sources for output 2, given ongoing challenges with population denominator issues (FCDO).	September 2025
#11 Immunisation policy: Work with MOH to strengthen their strategy for increased domestic immunisation financing, improved supply chain systems, and equitable access for zero-dose and under-immunised children (FCDO, MOH).	November 2025.

Output Title	Decreased regional and socioeconomic inequalities in essential RMNCH service coverage
Output number:		3	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Ratio of deliveries assisted by Skilled Birth Attendants (SBAs) between pastoralist and non-pastoralist regions	0.68	0.56
3.2 Ratio of pentavalent 3 coverage between the lowest quantile and highest quantile	0.64	0.77
3.3 Ratio of Outpatient Department (OPD) attendance Between Pastoralist and Non pastoralist regions	0.83	0.31

Briefly describe the output’s activities and provide supporting narrative for the score.

A key aim of the programme is to address geographic inequalities, especially concerning service coverage in pastoralist compared to non-pastoralist regions.

The output has scored a B - while there has been progress in addressing regional and socioeconomic inequalities in RMNCH service coverage, significant disparities remain. The ratios for skilled birth attendance, vaccine coverage, and OPD attendance highlight ongoing challenges in ensuring equitable access to essential healthcare services. Non-pastoralist regions and higher-performing districts continue to have better healthcare outcomes compared to their counterparts. This suggests that while activities have had a positive impact, further efforts are needed to achieve more balanced healthcare service coverage across all regions.
- Indicator 3.1: The ratio of deliveries assisted by Skilled Birth Attendants between pastoralist and non-pastoralist regions represents the comparative level of access to skilled birth assistance in these two types of regions. A ratio of approximately 0.56 indicates that a lower proportion of deliveries attended by SBAs compared to their non-pastoralist counterparts. This ratio highlights the disparity in maternal healthcare services between the two regions, suggesting that women in non-pastoralist regions are significantly less likely to receive professional assistance during childbirth than those in pastoralist regions.
- Indicator 3.2: The ratio of pentavalent 3 coverage between the lowest quantile (Q1) and the highest quantile (Q3) is approximately 0.77. This ratio indicates that the coverage rate in the lowest quantile is about 77% of the coverage rate in the highest quantile. This ratio highlights the disparities in vaccine coverage between different regions.
  [note] Ministry of Health - Annual Performance Report of 2016 EFY
- Indicator 3.3: The ratio of OPD (Outpatient Department) attendance between non-pastoralist and pastoralist regions, which is approximately 0.31, represents the comparative level of healthcare utilisation in these two types of regions. Specifically, this ratio indicates that indicating that the OPD attendance rate in pastoralist regions is only about 31% of that in non-pastoralist regions. This significant difference suggests that people in non-pastoralist regions are less likely to seek and access outpatient healthcare services than those in pastoralist regions. For example, Somali (0.29) and Afar (0.56) exhibit notably low OPD Attendance per Capita, well below both their targets and the national average.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

In line with recommendations #2 and #3, the FCDO team will review the appropriateness of the output indicators.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

The MoH is working to enhance healthcare delivery in pastoralist regions and lower-performing districts. Activities include increasing investments in healthcare infrastructure, expanding training programmes for healthcare providers, and implementing targeted outreach initiatives to raise awareness and encourage utilisation of healthcare services. While this some of this is beyond the scope of the programme, FCDO will continue to work with the SDP-PF and MoH to ensure the effectiveness of interventions aimed at reducing regional inequalities.

Output Title	Response for climate change and enhanced disease surveillance and response
Output number:		4	Output Score:	B
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Proportion of health care facilities having basic health care sanitation facilities	68%	77%
4.2 Proportion of health facilities (health centres and hospitals) with basic medical waste management system	78%	67%
4.3 Proportion of epidemics controlled within the standard of mortality	95%	67%
[note] Ministry of Health - Annual Performance Report of 2016 EFY
[note] Ministry of Health - Annual Performance Report of 2016 EFY

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 4 scores a B, with mixed performance across activities aimed at improving health care facilities and enhancing disease response capabilities in the context of climate change is mixed.
- Indicator 4.1: measures the proportion of health care facilities equipped with basic health care sanitation facilities. At 77%, most health care facilities have successfully met the required sanitation standards.
- Indicator 4.2: assesses the proportion of health facilities, including health centres and hospitals, with a basic medical waste management system decreased. The milestone for this indicator is 72%, yet progress dropped to 67%. Effective waste management is crucial for preventing the spread of disease, particularly in the face of climate-related health challenges.
- Indicator 4.3: In EFY 2016, the cholera outbreak in Ethiopia resulted in 38,616 reported cases and 501 deaths, case fatality rate (CFR) of approximately 1.3%. There were an estimated 5,643,331 malaria cases resulting in approximately 96 deaths, with a CFR for malaria approximately 0.017%. In 2016, Ethiopia reported 52,861 measles cases and 394 deaths – with a CFR of approximately 0.745%. The WHO recommends a target CFR of less than 1% for cholera, less than 1% in well-nourished populations with access to healthcare for measles and less than 0.1% for malaria.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

The programme output statement refers to climate change, but none of the indicators relate to ICF key performance indicators or how beneficiaries are being supported to adapt to the effects of climate. FCDO should work on including an ICF indicator into the logframe going forward.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

To address challenges this output is trying to address more effectively, FCDO is planning to enhance collaboration between the EPD-E programme and their humanitarian programme Ethiopia Crises to Resilience (EC2R). EPD-E focuses on building resilient health systems, improving infrastructure, and ensuring sustainable health services, while the humanitarian EC2R programme provides immediate relief and support during crises. These programmes can complement each other by ensuring that while immediate needs are met, there is also a long-term strategy in place to strengthen health systems and improve epidemic response capabilities.

This collaborative approach aims to leverage resources and expertise from both programmes to enhance surveillance, improve health care access, and ultimately control epidemics more effectively.

Recommendation	Timeframe
#12 ICF Indicator: Include an ICF indicator into the logframe (FCDO).	September 2025
#13 Nexus working: FCDO to set out and implement a strategy for effective EPD-E – EC2R working (FCDO).	August 2025

Additional Output – Technical Assistance
The two TA components are new to this reporting year of the programme, and not yet fully reflected in the key outputs of the logframe (see Recommendation 6). They are not included in the scoring of this Annual Review.
UNOPS implements the Technical Assistance Management Unit (TAMU), a multi-donor initiative designed with the Ministry of Health to ensure capacity building and TA support is well targeted according to areas of highest need. This is done under a project called ‘Strengthening the Capacity of the Ministry of Health for the Realisation of Health Sector Transformation Plan (HSTP II) in Selected Areas’. FCDO has been part of the steering committee since project inception and began funding in August 2024. A detailed results plan was agreed between FCDO, UNOPS and MoH. The Results or Outcome level indicators of the results plan are:
1. HSTP II selected priorities achieved through effective planning, implementation and monitoring system
2. An integrated Technical Assistance Management Unit (TAMU), which coordinates the implementation of the selected activities is established.
TAMU aims to strengthen MoH’s capacity, through management and coordination of TA, to deliver the Health Sector Development and Investment Plan (HSDIP). All expected outputs were achieved under this component during the reporting year for which FCDO contributed funds to two project quarters Oct-Dec 2024 and Jan-Mar 2025. In particular:
1. Of the 31 onboarded TAs, 97% completed their annual work plans aligned with MOH objectives.
2. The project team introduced a planning tool to the Minister's Office and initiated a monitoring system for TAs. Quarterly performance reviews provided feedback on deliverables.
3. The TAMU automated dashboard was launched to track contributions towards HSDIP objectives. TA management guidelines and SOPs are being developed.
4. A stakeholder workshop and 31 knowledge-sharing activities were conducted on various topics, including gender inclusion and data analysis.
5. A draft centralised TA database is underway, positively received by key stakeholders. A simplified annual work plan was also created at the Minister’s request.

TAMU is an innovative solution to a widespread issue of TA being too supply driven rather than demand or priority led. The coordination and strategic placement of TA can be challenging, and this integrated approach is a way to achieve greater coordination, government ownership, and effectiveness of our investments. Discussions with MoH have indicated they are satisfied with the progress made against this component. Going forward we will continue to address three areas for potential improvement, which are how to ensure high quality performance management of individuals recruited to TA roles as part of TAMU; finalisation of the TA database to ensure data is complete and Agencies are inputting into one system; and continuing to push the ambition on MoH ownership of the unit.

The Young Lives Project have been commissioned under this programme to deliver Health and Wellbeing in Times of Crises in Ethiopia, Proposal for Young Lives Qualitative Longitudinal Research (‘Qual 6’) in 2024. Insights from the study will inform EPD-E data gaps, and assist the GoE in evidence-led policy making. This work began on 30 October 2024. In accordance with the expected outputs of this component, by the time of this review, the Young Lives Project had produced three Factsheets and presented on their most recent findings. These Factsheets gave insights into the previous year’s findings of the Young Lives Project and focused on:
[note] Young Lives is a University of Oxford longitudinal study of poverty and inequality following the lives of 12,000 children in Ethiopia, India, Peru and Vietnam since 2002.
- Education and learning
- Health and Nutrition
- Work and Family Life

The subsequent presentation of this research gave valuable insights for both the EPD-E programme and British Embassy’s wider portfolio. Findings considered equity and regional disparities, mental health due to recurrent crises the interconnectivity of conflict and nutrition, the link between food security and mental health, and the regional prevalence of malnutrition. The project will now focus on interpreting new data sets to identify emerging patterns.

## D: VALUE FOR MONEY

Key cost drivers and performance
The programme’s VfM is determined by the ‘5E’s, namely i) economy measured by the cost of commodities/drugs compared to the international price and capacity building/ skill development of primary health care workers; ii) efficiency - whether the output is delivered as per the budget; iii) effectiveness - whether the planned outcomes are being achieved as per the budget and specified time; iv) equity - whether health outcome disparities seen geographically are reducing and the gap between the lowest performing regions and the national average is narrowing; and v) cost effectiveness.
VfM performance compared to the original VfM proposition in the business case
The insights below are based on data from the EFY 2017 second quarter interim financial and physical financial reports related to the SDG-PF.
- Economy: The cost drivers are prices of commodities/drugs compared to the international price, the cost of skill development of primary health care providers, and the cost of TA provision compared to similar programmes. Currently, it is too early to assess whether cost drivers are economical due to the financial and physical reports covering only two quarters. 82% of the SDG-PF’s 2017 EFY budget has been allocated to procurement. For this annual review, we could not get adequate data on local procurement and cost per units of RMNCH commodities, cost of skill development of primary health care providers. We will work with the MoH to include international comparisons of the cost per unit of the main cost drivers following this review.
- Efficiency: the cost drivers are cost per ante-natal care attendance, cost per immunisation, cost per facility-based delivery and cost per other outputs specified in the log frame. For the next AR we will work with the MoH to include an indicator that will help us assess whether programme is efficient.
- Effectiveness: The indicators are Maternal Mortality Rate (MMR) from 401 to 279, Under five mortalities reduced from 59 to 44 per 1000 live births, UHC (Universal Health Coverage) index increased from 65.5 to 68, Health security index (HSI) increases 0.68 to 0.78. It is too early to obtain a high-level result of the programme. The output results are indicative of a high likelihood of reaching the outcome level results.
- Equity: This programme has a primary gender marker, as it is explicitly focused on saving the lives and improving the health of women and children in Ethiopia. The vast majority of EPD-E funding is focused on gender. The programme also aims to reduce the gap between the average for each of the lower performing regions and the national average. In the second quarter of 2024/25, a total amount of USD 54.4 Million was transferred to regional agencies. From the total allocated, 42% of the budget was allocated to two emerging regions and three newly established regions. These are positive steps towards greater health equity in Ethiopia.
The original VfM proposition emphasised the importance of our Technical Assistance (TA) at both national and sub-national levels. The aim was to complement service delivery financing through enhancing decision-making, delivery, and public financial management capabilities. This approach is designed to improve the VfM of service delivery investments through more effective prioritisation and targeting, ultimately leading to enhanced health system efficiency and effectiveness. To fully assess how the TA is complementing FA, FCDO should undergo a thorough review of the TA’s strategy and performance (see Recommendation 6).

Assessment of whether the programme continues to represent value for money
The output scores in Section C demonstrate that the current state of progress is partially aligned with milestones set in the programme logframe. In the next year, the 5Es of VfM delivery of the programme will be further enhanced by extensive monitoring at different levels of the health sector alongside development partners and the MoH. This will help us understand the main cost drivers. To determine whether the programme fund is utilised economically, efficiently, effectively, equitably and cost effectively, the programme team should continuously follow up on FRA recommendations, audit response plan of action, and incorporate VfM indicators in the logframe. The programme is expected to reach women and children, as well as communities that are severely affected by conflict, those with low health facilities coverage, and thus increase the availability and accessibility of health facilities through a long-term development response. This will lead to a reduction in geographic health disparities.

E: RISK

Overview of risk management
The overall risk rating for the EPD-E programme is moderate. The programme risk register was updated in discussion with TA partners (UNOPS and YL) and the Ministry of Health. The risks are identified against portfolio risk categories and monitored on quarterly basis. There is a quarter risk discussion with implementing partners on their respective risk registers ahead of the quarterly internal risk register update. Risk appetite for different categories of risk are within the Embassy’s risk appetite during this annual review. Risks can be escalated to the Human Capital team risk register and then to the Embassy’s portfolio wide risk register.
The Partnership Principles Assessment (PPA) was revised in December 2024. The assessment revealed a mixed level of commitment by the Government of Ethiopia (GoE) towards poverty reduction and the Sustainable Development Goals (SDGs). There was a noted decline in the commitment of the GoE to respecting human rights and fulfilling internal obligations, highlighted by issues such as arbitrary arrests, torture, restricted space for real opposition parties, and deprivation of property ownership due to corridor development in Addis Ababa and other regions, as well as ongoing conflicts in the Oromia and Amhara regions. Moreover, the PPA indicated a mixed level of commitment to strengthening financial management and accountability, and towards reducing the risk of funds being misused due to weak administration or corruption. In terms of strengthening domestic accountability, the GoE's commitment was judged to be limited in ensuring accountability, with shrinking political and civic space.
Delivery
The most recent SDG-PF report (EFY 2017 Second Quarter) highlights potential risks in completing procurement activities for medical supplies and equipment, with only 7% of the budget utilised. Delays in funding disbursement in accordance with their commitment, as well as unexpected USAID and wider ODA cuts, have also been identified as potential delivery risks. To address these and other delivery risk, the AR team led discussion with EPSS officials during the AR mission. The MoH is assessing the impact of USAID cuts and is aiming to develop a strategy for mitigating the funding gap.

At the technical assistance level, UNOPS has developed a resource mobilisation plan and is engaging donors. There is quarter monitoring of programme delivery risks carried out by the service providers - UNOPS and Young Lives. Both suppliers hold quarterly risk discussion with the FCDO programme team.

Strategy & Context
The continued conflicts in Amhara region, and parts of Oromia, are constraining access to basic health services, slowing down the implementation of some of the programme's pillars, including by damaging health facilities. As part of the mitigation measures, FCDO liaises with GoE, WB, and other contributing DPs to monitor changes in the political and security context. The team is also working closely with other teams across the embassy, engages in regular SDG-PF meetings, and in biannual joint missions and quarterly discussions with other DP.
Financial and Fiduciary
Financial and fiduciary risks are managed by scrutiny of the quarterly Interim Financial Reports (IFRs) from the Ministry of Health (MoH), including annual audit reports submitted to SDG-PF with the attendance of all contributing DPs including FCDO. Moreover, the programme team is engaged in following up on the progress of FRA recommendations. The SDG-PF members review all fiduciary risk categories: financial management, procurement, and audit. In addition, the MoH has established an audit oversighted committee to carry out a dedicated periodic financial management, review internal and external audit findings, and follow up on mitigation measures.
FCDO has conducted an FRA in 2024, covering six pillars. The pillars are budget reliability, transparency and public finance, management and asset and liabilities, policy -based fiscal strategy and budgeting, predictability and control in budget execution, financial reporting, and external audit. There are around 31 findings under the six pillars. Top FCDO priorities around the SDG-PF are budget reliability, transparency of internal controls, predictability and control in budget execution, as well accounting, reporting and procurement. Following FRA findings, the MOH has implemented several mitigation measures. These include launching the Channel Two Finance Administration for the Health Sector directive number 979/2024, an MoU signed between the Ministry and RHB heads, and the establishment of an audit oversight committee established with the support of FCDO-funded TA. The efforts are aimed at addressing continuous underspending, and bringing more predictability and control in budget execution.
Issues remain such as the absence of good budgetary monitoring; disjoined budgeting controls that cause delays in disbursement; control risks due to the excessive use of advances; the proliferation of different accounting system in the MoH and RHBs causing continued miscoding of data, posting duplication and unreconciled accounts. Manual financial reporting at the woreda level caused delayed timely submission of financial and activity report to signatory DPs within 45 days of the end of each quarter of the Ethiopian Fiscal Year (in November, February, May and August). Moreover, there is weak predictability in the receipt of resources. The second quarter report of indicates weak budget utilisation (7% utilised and 31% committed from the approved budget). It demonstrates that initiatives such as the Channel 2 directive or the MOU signed between MoH and RHBs are yet to deliver concrete improvements. In terms of next steps, the FCDO and other donors should continue working with the MoH through the SDG-PF to enhance budget utilisation via early approval of Annual Comprehensive Plan (ACP), follow the implementation and impact of the financial directive and MoU, settle the proliferation of different account systems and thoroughly follow the procurement plan and its implementation – as this makes up for more than 75% of the ACP value.
Safeguarding:
Gender-based violence is a potential risk identified in the DDAs for both TA partners. During the reporting period UNOPS undertook awareness-raising trainings in addressing sexual harassment, sexual exploitation, and abuse (SEAH). Additionally, the UNOPS Ethiopia office has ensured that all technical assistants complete mandatory training on the prevention of sexual exploitation and abuse (PSEA). Our second TA partner, the Young Lives Project (YLP) is not currently a member of the Misconduct Disclosure Scheme and is adhered to both its internal whistleblowing policy and that of the University of Oxford.
As additional mitigation measures, DDA recommendation follow-up and quarterly risk discussions including delivery chain risk mapping, were held regularly with both with UNOPS and Young lives Project partners, to monitor potential risks related SEAH.

Issues Management:
Issue logs consisting of the following fields were added to programme risk register, to feed into the team level risk register, which then will feed to portfolio Risk Register: – An Issue Description – Issue rating (see previous slide) – Impact on delivery – Actions – Owner – Escalation (Yes/ No) – When resolution is expected.
Annual Statement of Progress (financial aid programmes only)

Current level of fiduciary risk and direction of travel since last ASP	Fiduciary risk: Moderate / Improving this FY
Specific assessment of corruption risk and direction of travel since last ASP	Corruption risk: Moderate / Improving this FY
Is a full FRA update required?	No, since independent FRA was conducted in Dec 2024

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Financial Performance
By January 2025, SDG-PF partners had disbursed USD 61 million. This is 48% of the original commitment for EFY 2017 – the SDG-PF secured USD 128.7 million in new commitments, plus a carryover of USD 21.2 million, bringing the total to USD 149.8 million (about ETB 16.8 billion). Including unspent funds from the previous year, the total budget for EFY 2017 was ETB 22.4 billion.

Funds were allocated according to the MoH’s ACP. In the first quarter, 36% of the budget went to Reproductive, Maternal, Newborn, and Child Health (RMNCH). In the second quarter, 16% was allocated to RMNCAYH-N, Health Extension, Primary Health Care, and disease prevention. Financial performance is monitored through quarterly reports and annual audits, though the 2025 audit was delayed. The cash balance nearly doubled from Q1 to Q2 (from ETB 2.6 billion to ETB 4.2 billion), indicating improved donor disbursement. About ETB 8.9 billion was spent on essential medical supplies and infrastructure, showing good progress compared to last year.

Through the technical assistance (TA) component of the EPD-E Programme, the UNOPS TAMU project demonstrated strong performance in strengthening the Ministry of Health’s capacity to implement the Health Sector Transformation Plan (HSTP-II) across selected focus areas. For the reporting period, FCDO disbursed a total of £1.4 million in TA funding, alongside financing from Italy and the Gates Foundation. According to the TAMU project’s financial progress report, expenditures reached 45% of the total budget, which is in line with expectations. This increase is attributed to the successful recruitment and onboarding of 32 TAs, as well as the implementation of related activities. This positive trend in expenditure is expected to continue into 2025.

Key achievements during the reporting period include the identification, onboarding, and management of seconded and project staff at Ministry of Health and its affiliated agencies; the development of a results framework; the establishment of a planning, monitoring, and reporting system; and the creation of an automated dashboard. This dashboard enables real-time tracking of technical assistance inputs and progress against the nine strategic objectives outlined in the Health Sector Development and Investment Programme (HSDIP).

Summary of budget utilization of EPD-E programme
During the implementation of EPD-E programme, FCDO signed three agreements during FCDO FY 23/24 and 24/25. The first agreement signed was the MoU between FCDO and MoF in May 2023. and the other two agreements were signed under the TA component. The MoU was signed between UNOPS and FCDO in August 2024, while an accountable grant was signed between FCDO and Young Lives in November 2024. As per the ODA-approved budget of 24/25, £23m was disbursed to the MoH, as the disbursement triggers under the JFA were met. £1.4million was disbursed to UNOPS in two tranches while £144K was disbursed for Young Lives in FY24/25. As per the narrative report of YLP, Q1 and Q2 deliverables were met, which includes survey design, fieldwork, data cleaning, data gathering report, and initial research analysis.

The table below shows the programme budget and spending from FCDO FY 23-26.

The overall financial performance showed relative improvement in public financial management compared to the last annual review period.

Date of last narrative financial report	April 2025	Date of last audited annual statement	June 5, 2025 / (Received from MoH)

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
- Programme management of the EPD-E programme includes reviewing quarterly performance and financial reports produced by MoH, the annual audit report, and fiduciary assessments. This AR was conducted through field visits to sample selected regions (Oromia and Afar). The SDG-PF is managed by the MoH using the GoE procedures via the Joint Financial Agreement signed by all development partners on the commitment to adhere to one plan, one budget, and one report. The JFA jointly agreed terms and procedures for SDG-PF management that provide oversight and regular monitoring and evaluation of plans, finance, and procurement. This includes reviewing and clearing the MoH’s ACP, quarterly performance reports, annual external audit reports, audit follow-up action plans and procurement plans. In addition, the programme team has conducted a follow up of the Fiduciary Risk Assessment to assesses implementation and fed into the latest Annual Statement of Progress.
- The MoH submitted four quarterly narrative and financial reports in the review period. These reports were initially reviewed by each DPs and later reviewed jointly by all donors including FCDO, at a SDG-PF meeting. Consolidated feedback was then communicated to the MoH through the SDG-PF chair. In addition to the periodic reports, such as the agreed JFA framework, Joint Review Mission (JRM) monitoring missions were conducted. The last Annual Review meeting was conducted in October 2024 in Arba Minch.
- Quarterly reports are submitted from UNOPS, and the final research product is expected from Young Lives Project in FY25-26. For UNOPS, monitoring meetings with DPs take place every quarter to review progress, discuss outstanding issues and pass joint decisions to improve the performance of the Technical Assistance Management Unit (TAMU).
- The SDG-PF, the highest governance body for the FA element of the programme, also provides strategic oversight and enables decision-making. It is attended by MoH and DPs. The Joint Core Coordinating Committee (JCCC), the technical arm of the Joint Consultive Forum (JCF), held its most recent meeting in May. Moreover, there are other forums that the team use to evaluate the programme including the Joint JCF, ARM and Joint review Missions. SDG-PF decisions made during the review period include approval of the EFY 2017 (24/25) annual comprehensive plan, audit report and recommendation follow up, financial and activity report for the third quarter of the previous Ethiopia fiscal year – these are all requirements for FCDO FA disbursement.
- This annual review has benefited from field visits made to Oromia and Afar regions, gathering beneficiaries’ feedback. During the field visits, the team discussed with programme beneficiaries, the regional and zonal health bureaus.

Evidence and learning
Establishing new evidence and integrating lessons from best practice are core principles of the programme. Periodic reports and evidence produced by the MoH continue to have reliability issues - there were no good alternatives to verify evidence from the MoH. The programme evidence and learning were hindered by FCDO staff turnover, particularly in the PRO role. In addition, the team is planning to disseminate findings from the Young Lives longitudinal research and the UNOPS Dashboard to a wider audience for lesson learning.