## Annual Review Template

Title: Building a Resilient Health System to End Preventable Maternal, Newborn and Child Deaths in Ethiopia
Programme Value £ (full life): £100m		Review date: 28/05/2026
Programme Code : 301196	AMP start date: 25/5/2023	AMP end date: 31/03/2028

Summary of Programme Performance
Year	23/24	24/25	25/26
Overall Output Score	A	B	A
Overall programme risk rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003183.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/S30119621.xlsx

Abbreviations

AMP	Aid Management Platform
ANC	Antenatal Care
AR	Annual Review
BC	Business Case
DP	Development partners
EFY	Ethiopia Fiscal Year
EPD-E	End Preventable Maternal, Newborn and Child Deaths in Ethiopia
EPHI	Ethiopian Public Health Institute
EPSS	Ethiopia Pharmaceutical Supplies Services
FA	Financial Aid
FGM/C Female Genital Mutilation/ Cutting
FP	Family Planning
GAVI	Global Financing Facility
HSDIP	Health Sector Development Investment Plan
JFA	Joint Financial Agreement
MDTF	World Bank Multi Donor Trust Fund
MMR	Maternal Mortality Ration
MoH	Ministry of Health
MoU	Memorandum of Understanding
PforR	Programme for Result
RHB	Regional Health Bureau
RMNCH	Reproductive, Maternal, Neonatal and Child Health
SDG-PF	Sustainable Development Goal Performance Fund
SRH	Sexual Reproductive health
TAMU	Technical Assistance Management Unit
TA	Technical Assistance
ToC	Theory of Change
UHC	Universal Health Coverage
VfM	Value for Money

## A. SUMMARY AND OVERVIEW

Description of programme
The Building a Resilient Health System to End Preventable Deaths in Ethiopia (EPD-E) programme is the UK flagship health investment in Ethiopia. It aims to support the Government of Ethiopia to reduce preventable maternal, newborn and child deaths while strengthening the country’s longer-term progress towards Universal Health Coverage (UHC). In July 2022, the UK approved the programme with a total budget of £100m. The programme is delivered primarily through financial aid (FA) to the Sustainable Development Goals Performance Fund (SDG-PF), complemented by targeted technical assistance (TA) to strengthen planning, budgeting, monitoring and institutional capacity within the Ministry of Health (MoH) and the Regional Health Bureaus (RHB) through Technical Assistance Management Unit (TAMU). EPD-E funding also supports the Young Lives project, a long running longitudinal study of young people’s wellbeing and the determinants of health, which contributes to evidence informed policy making.
Changes to the operating environment
The internal operating environment for EPD-E during the review period has been challenging. Changes in FCDO strategic directions and reductions in UK official development assistance (ODA) budget are resulting in a portfolio review by the Human Capital Team. The UK’s work on human capital in Ethiopia is likely to have an increased focus supporting key reforms and catalytic investments that strengthen systems and domestic capacity.

At national level, the Government of Ethiopia (GoE) has continued to prioritise Universal Health Coverage (UHC) throughout the review period, maintaining a strong policy focus on primary healthcare and health financing. This has been reflected in the consolidation of UHC as a core pillar of health sector reform; the development and implementation of new compacts, including an RMNCH and UHC compact; and ongoing efforts to mobilise domestic resources despite fiscal constraints. Key reforms have included continued expansion of Community-Based Health Insurance (CBHI), now covers a substantial proportion of households (the SDG-PF impact study reports expansion to 87% of woredas), alongside measures to strengthen strategic purchasing and reduce out-of-pocket expenditure. In parallel, the GoE has advanced health workforce reforms through expanded training, professional regulation, and task shifting approaches, while sustaining investments in community-based service delivery through the Health Extension Programme and broader primary health care unit strengthening.

During the review period, the Ministry of Health also prioritised a set of practical actions to sustain service delivery and address gaps. This included scaling up routine immunisation through outreach and catch‑up campaigns; expanding community-based service delivery through the Health Extension Programme; progressing implementation of the National Health Equity Strategy with greater focus on low-performing regions; and introducing targeted interventions to improve sexual and reproductive health outcomes, including adolescent-friendly services and community engagement to address social norms. These actions were supported by partners, including through SDG-PF financing and technical assistance.

These efforts have taken place in a challenging context characterised by severe fiscal pressure, high inflation, debt distress, and constrained public spending, which have limited the pace and scale of health sector investments. Moreover, conflict and displacement across several regions have disrupted service delivery, damaged health infrastructure, and placed additional strain on human resources, particularly in conflict￼affected and hard￼to￼reach areas. At the same time, disease outbreaks and climate￼related shocks have underscored underlying system vulnerabilities. During the review period, a disease outbreak highlighted both the increasing importance of preparedness, surveillance, and early warning systems, and the progress made in strengthening public health emergency management, including rapid detection, coordination through emergency operations centres and deployment of response teams.

Ethiopia saw its first outbreaks of Mpox and Marburg Viral Disease (MVD) during this period. MVD cases identified in the Jinka region in November 2025 were contained within three months through swift national action. In total 14 confirmed cases were reported across the southern region and in January, Ethiopia officially declared its MVD outbreak over. The UK supported Ministry of Health during the Marburg outbreak by providing equipment, funding via the SDG-PF, and technical assistance to MoH and its designated partners. Ethiopia’s leadership, coordination and ability to contain the outbreak demonstrated the value of sustained investment in health system strengthening and preparedness from partners, including the UK government.

Internationally, the review period has been characterised by heightened geopolitical instability, including conflict in the Middle East, alongside reductions in global ODA and shifting donor priorities, which have collectively reduced the predictability of financing for humanitarian and development programmes. Stakeholders consulted during the AR noted that these pressures have reinforced the importance of sustainable financing, including a focus on increasing domestic resource mobilisation (DRM) and reducing reliance on external financing. In this context, in line with FCDO Ministerial direction on shifts in our development approach, there has been a renewed emphasis on GoE-led, system strengthening approaches that prioritise efficiency, equity, and resilience, rather than fragmented or short-term programme support.
TA Partner performance
The TA component of EPD‑E is delivered by UNOPS under the TAMU project, aiming to enhance the MoH’s planning, budgeting and management capabilities, alongside the Young Lives Project, which contributes evidence to inform policy‑making. Through TAMU, capacity within the Ministry of Health has been strengthened through the recruitment and deployment of 32 technical advisers and project staff embedded within the MoH, Regional Health Bureaus, and affiliated agencies, including EPSS. Monitoring data indicates that TA inputs have contributed to nine national health priorities, including RMNCH, the National Immunisation Programme Performance Situation Analysis (2021–2025), and development of the forthcoming National Immunisation Strategy (2026–2030). TA has also supported the development of HSDIP II, Marburg Virus Disease case management guidelines, national RMNCH policy and programme assessments, participation in audit and risk committees, and initiatives to support local pharmaceutical manufacturing. In parallel, TAMU has established a central planning, monitoring, and reporting database and an automated dashboard to track TA inputs and progress against HSDIP I strategic objectives, with responsibility increasingly transitioning to the MoH.

The long-established Young Lives Project has completed the latest stage of their longitudinal research, with ensuing policy briefs, and ten policy relevant studies across FGM/C, early child marriage, maternal and child health, SRH, disability, mental health, education, and migration. The programme-supported research was presented at the Ethiopian Studies international conference.

FCDO management of the programme
Governance and programme management arrangements for EPD-E have improved during the review period, responding to the previous AR recommendation to strengthen monitoring and clarify roles and responsibilities. A M&E structure is now in place and functioning, with regular monitoring. Further consolidation of governance improvements will depend on effective implementation of forthcoming plans around team and programme transition. During the review period, EPD‑E operated within a phase of transition with workforce changes and portfolio reprioritisation. The Programme Responsible Owner (PRO) was appointed during this AR cycle. The team navigated the departure of the CBS health advisor alongside wider portfolio reprioritisation in the team. A senior health adviser was appointed at the time of writing, who will provide dedicated technical leadership and strengthen oversight of the programme.

Summary supporting narrative for the overall score in this review

The programme achieved an overall output score of A during this AR period, reflecting performance that met expectations. Performance was strongest in the TA component output (5), where support to the MoH and RHBs contributed to improvements in planning, coordination and institutional functioning. The TAMU programme also made important progress in establishing a consolidated database of TA provided to the MoH, capturing inputs not only from EPD-E but also from a wide range of external partners. This work is now being transitioned to full MoH ownership, which is an important step towards improving oversight, coordination and alignment of sector support. National surveillance and response capacity continued to strengthen during the period (output 4); these gains are likely largely the result of broader GoE and other partner engagement in health security. Progress in this area reflects strong national leadership and coordinated donor engagement, underpinned by sustained investment in health systems and preparedness. Within this broader effort, EPD‑E has contributed through both flexible financing and support to institutional capacity, planning, and system readiness.

The AR was conducted by the EPD‑E team, with support from a health adviser from headquarters. Including a desk‑based review of key programme documents, data including EDHS 2026 results and administrative data, GoE strategies and implementing partner documents, as well as interviews and consultations. This included engagement with the FCDO EPD‑E team and BE advisers, the MoH, implementing partners (Young Lives and TAMU), development partners (WHO, UKHSA, Gavi, UNICEF), and a field visit to Somali Region (Jijiga), involving the Regional Health Bureau, a hospital, health centre and a health post. This AR was completed shortly after the release of initial EDHS findings, a nationally representative household survey conducted every four years using stratification by region and urban/rural residence; more comprehensive EDHS results are still awaited. Findings were triangulated with other data sources, including administrative data provided by the MoH, recognising ongoing challenges related to population denominators derived from outdated census figures, which affect the reliability and interpretation of coverage indicators. For example, routine administrative immunisation coverage estimates were consistently higher than those from household survey‑based estimates, highlighting ongoing uncertainties around population denominators and the need for cautious interpretation of administrative data.

Progress of output indicators was mixed in areas related to equity, service utilisation and infection prevention care (IPC) facilities. Indicators on antenatal care and growth monitoring and promotion for children showed limited or inconsistent improvement across regions, and indicators of WASH and waste management are lagging. A range of factors are likely to be contributing to these disparities, including longstanding system challenges and the distinct needs of pastoralist and semi-pastoralist communities. These pressures have been further intensified by ongoing conflict, displacement and wider fiscal constraints. Many of these issues are complex, vary by region and are not easily resolved within a short period.

Outcome and impact indicators present a mixed but broadly positive trajectory in Ethiopia over the past two decades, with recent gains proving harder to sustain and unevenly distributed. Maternal mortality has continued its long‑term decline, falling from 267 per 100,000 live births in the mini‑EDHS 2019 to 141 per 100,000 live births in the EDHS 2025 (95% CI: 88–195). While this represents substantial progress, estimates should be interpreted with caution given the small number of maternal deaths captured and differences in reference periods across surveys. By contrast, trends in child survival indicators have been less favourable in the most recent period. Neonatal mortality has remained largely unchanged (26 per 1,000 live births in the mini‑EDHS 2019 compared with 25 per 1,000 live births in the EDHS 2025, measured over the five years preceding the survey), falling short of the HSTP‑II national target of 21 neonatal deaths per 1,000 live births by 2025. Over the same period, infant and under‑five mortality have increased modestly (from 34 to 39 per 1,000 live births, and from 47 to 51 per 1,000 live births, respectively). These short‑term patterns contrast with the longer‑term trajectory of sustained improvement, particularly in under‑five mortality, which declined from 166 per 1,000 live births in 2000 to 51 per 1,000 live births in 2025. However, national‑level trends mask pronounced regional and socio‑demographic inequalities, with evidence that aggregate gains have been driven disproportionately by higher‑performing regions and population groups. Taken together, the data point to a slowing of progress and some erosion of earlier gains in recent years, highlighting increasing system pressures and the growing complexity of sustaining improvements and extending equitable coverage to underserved populations.

Relative to the SDG targets for 2030, Ethiopia has made substantial progress but remains some distance from key SDG thresholds, including reducing maternal mortality to fewer than 70 deaths per 100,000 live births (SDG 3.1) and neonatal mortality to 12 deaths per 1,000 live births (SDG 3.2). Outcome‑level indicators of health system performance show a similar pattern. According to the HSDIP I situational analysis, the Universal Health Coverage (UHC) service coverage index increased from 34% in 2015 to 38% in 2019, before declining to 33% in 2023, reflecting systemic constraints and the growing burden of non‑communicable diseases. As Ethiopia moves toward the final stretch of the SDG period, achieving the pace of reduction required to meet health‑related SDG targets is likely to depend less on broad national gains and more on addressing persistent regional and sociodemographic inequalities. Progress toward both national and global targets will therefore require accelerating improvements in lagging regions and underserved populations, where outcomes remain poorest and marginal gains are increasingly difficult to secure.

Against this backdrop, the overall score reflects both the difficulty of addressing structural inequities and the programme’s strategic decision to work through government systems and national financing mechanisms. Several of the programme’s most important contributions, including strengthened government ownership and better alignment of partner support, are not fully captured by the current service focused output indicators, yet remain critical to long-term progress, capacity building and sustainability.

According to national sector analyses, including the HSDIP I situational analysis, Ethiopia’s improvements in health outcomes over the past two decades have been driven primarily by sustained investments in primary health care and the large-scale expansion of community-based service delivery. Central to these gains has been the Health Extension Programme, alongside the expansion of the PHC network and strengthened community engagement mechanisms such as the Women Development Army, which together improved access to preventive and promotive services, particularly for RMNCH. The analysis also highlights the role of targeted expansion of lifesaving interventions, integration of disease specific programmes within PHC platforms, and improved use of routine and survey data for planning and monitoring. At the same time, the document emphasises that while these drivers explain historical progress, they are no longer sufficient to sustain the same pace of improvement, as quality, equity, and system readiness have become increasingly important determinants of outcomes.

Discussions with MoH advisers on the forthcoming Health Sector Development and Implementation Plan (HSDIP) II point to a clear set of emerging strategic priorities for GoE in the coming years. These include addressing inequities through more targeted, data driven approaches; strengthening integrated primary health care, which is critical for immunisation delivery given that most immunisation services are provided at this level; advancing health financing reforms, including increased DRM, expanded local manufacturing, and a more government owned financing system; addressing health workforce shortages, including issues related to competency, motivation, and incentives; and accelerating digital health and data systems, with a particular focus on digitising PHC in line with the new Digital Ethiopia 2030 strategy.

Across outputs, performance was mixed. Output 1 (RMNCH service uptake) showed broadly stable performance with some indicators marginally missing milestones and GMP underperformance. Output 2 (child health and nutrition) largely met expectations, combining strong Vitamin A performance with more modest gains in immunisation completion. Output 3 (equity) remained off track, with persistent and in some cases widening disparities. Output 4 (disease surveillance and response) continued to show solid system-level performance, including effective outbreak response. Output 5 (technical assistance and evidence) delivered important system-strengthening gains, improving coordination, planning and the use of evidence across the sector.
Output Summary Table

Output	Output title	Score
1	Improved uptake of the highest impact package of RMNCH interventions	A
2	Improved quality of child health services including nutrition services	A
3	Decreased regional and socioeconomic inequalities in essential RMNCH service coverage	B
4	Enhanced disease surveillance and response	A
5	Technical assistance and evidence generation (TAMU and Young Lives)	A+

Major lessons and recommendations for the year ahead

Equity and sub-national disparities: Improvements in national indicators have been driven disproportionately by gains in higher‑performing regions. Addressing disparities is important to ensure equitable access to essential services. GoE stakeholders have emphasised that using the SDG‑PF to address equity gaps is a priority, including through more targeted budget allocations focused on low‑performing regions.
Recommendation: Develop and articulate a more explicit health equity approach, including through the EPD-E programme, clarifying how SDG‑PF funding contributes to reducing sub‑national disparities. This could be supported by analysis of the regional distribution of SDG‑PF‑financed commodities, if data is made available. Consider reviewing equity indicators to better capture progress, for example through outputs related to engagement with the next national health equity strategy, improved targeting of resources, or strengthened equity‑focused planning.

Population denominators and data reliability: Ongoing challenges with population denominators continue to affect the reliability and interpretation of coverage indicators. Emerging plans to integrate digital identification with health service delivery offer potential to enhance the quality and reliability of health data.
Recommendation: Improved population estimates should be recognised as a critical system-level enabler that sits largely outside EPD-E’s direct control. A focused political economy analysis could help identify feasible pathways for addressing denominator challenges over time. These data challenges were repeatedly raised in discussions with other donors, indicating an opportunity for coordinated approach to help reinforce alignment and momentum behind government‑led solutions.

Capturing system alignment and modern development principles: The programme’s added value lies in its strong alignment with government systems via the SDG‑PF. However, current outputs and indicators largely reflect a traditional service‑delivery framing and do not adequately capture these system‑level contributions.
Recommendation: Consider adding an indicator that captures system alignment, government stewardship (for example, use of government planning and financing systems), to better capture the programme’s strategic intent and contribution to sustainable health systems strengthening.

Health financing: The original EPD-E Business Case included explicit commitments to support stronger health financing and value for money, including influencing increased domestic financing for health, strengthening planning and financial management at national and regional levels, and prioritising cost-effective, high-impact RMNCH interventions. During the review period, the health financing agenda became increasingly central to Ethiopia’s reform trajectory, reflected in GoE’s renewed focus on UHC, compact commitments and emerging HSDIP II priorities, among others. It is also increasingly relevant to the wider World Bank/IMF-supported macroeconomic reform agenda, including DPO3/4, where health financing-related reforms create an important opportunity for the UK to align health, human capital and macro-fiscal engagement.
Recommendation: Develop a clear UK health financing approach and embed in the UK One HMG Health Strategy for Ethiopia, setting out where and how the UK can add value through policy dialogue, technical assistance, wider influencing and programme levers including EPD-E. Based on discussions with partners and emerging GoE priorities, this should include consideration of targeted support to Community Based Health Insurance (CBHI) reform, domestic resource mobilisation for health, strategic purchasing, and regional-level planning and financial management. The strategy should also clarify how UK engagement on health financing links to wider decisions, including the recommended transition of FA to the World Bank and the UK’s wider objectives on human capital and macro-fiscal.

Conflict sensitivity and adaptability: Conflict remains a defining feature of the Ethiopian context, yet conflict sensitivity and adaptive mechanisms are not consistently articulated or systematically applied across EPD-E components. This creates risks to delivery, equity and sustainability, particularly in conflict‑affected regions.
Recommendation: Strengthen conflict sensitivity and adaptive management across the programme (as intended in the original business case) and clearer alignment with humanitarian planning.

Health–humanitarian collaboration: Inequalities in access and health outcomes are increasingly shaped by conflict and displacement, yet collaboration between development‑focused health programming and humanitarian planning remains limited.
Recommendation: Enhance engagement with humanitarian counterparts to complement approaches in conflict‑affected and hard‑to‑reach areas.
Retaining technical breadth on key determinants: Key determinants of health outcomes in Ethiopia, including WASH and nutrition, remain critical, yet technical capacity in these areas has reduced within the wider team.
Recommendation: Ensure continued access to specialised expertise on WASH and nutrition, for example through Centres of Expertise, to maintain (where possible) multisectoral approach to health outcomes.

FA component, P4R and transition to the World Bank: During the AR period, a structured analysis which looked at a potential transition of the FA element of the programme to a WB–hosted P4R instrument was undertaken and identified potential benefits – as well as drawbacks. Potential benefits include the use of the Bank’s independent monitoring and evaluation, PFM risk management and synergies with the Bank’s wider work. Potential drawbacks include the need to manage limitations of the MDTFs operations in conflict-affected regions in Ethiopia, partner management and unintended consequences. In addition, given ongoing discussions regarding the wider portfolio, a decision to transition will need to be made as part of these wider discussions and decisions.
Recommendation: Consider the option to transition the FCDO financial support to the SDG-PF to a WB–hosted MDTF within wider portfolio discussions bearing in mind that any decision would need to be implemented in a way that protects UK visibility and influence in SDG-PF governance, formalises good practice and proactively manages risks and outline specific measures to manage the limitations of the MDTF’s operations in conflict affected regions.

Portfolio review: The wider human capital portfolio is being reviewed, considering budget and priority changes. By the end of the FY25/26, there will be one human capital business case for the UK’s health and education work. Moreover, the programme has shown clear strengths in combining FA with TA through TAMU and Young Lives. Evolving FCDO priorities and funding envelopes means the FCDO team needs to reflect on whether the current mix and modalities continue to represent the most effective and strategic approach.
Recommendation: The FCDO team should consider whether there are synergies to be exploited across the human capital work, through merged contracts, for example for M&E or TA. Furthermore, reassess the balance between FA and TA to confirm it remains suited to strategic priorities.

10. Malnutrition as a Key Health Sector, Public Sector and Human Capital Challenge: Malnutrition remains a pervasive and deeply rooted public health challenge in Ethiopia, shaped by interrelated social, economic, and environmental factors.
Recommendation: Define the UK’s and EPD’s contributions towards addressing malnutrition, clarifying alignment with humanitarian and multisectoral responses.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change for EPD‑E was initially based on Ethiopia’s Health Sector Transformation Plan (HSTP) and has since been updated to align with the Health Sector Development and Investment Plan (HSDIP I). The programme’s intended impact is to reduce maternal, newborn, and child mortality. This impact is through three core outcome pathways: increased Universal Health Coverage (measured by the UHC service coverage index), strengthened health security (measured by the Health Security Index), and increased domestic financing for health.

Overall, the ToC logic remains valid and consistent with the programme team’s implementation experience. Evidence from delivery to date supports the central assumption that sustained improvements in service coverage, system resilience, and health financing are necessary to achieve mortality reductions. Implementation experience has, however, reinforced the importance of system enablers, for example TA at national and regional levels, to translate financial inputs into sustained institutional and service delivery improvements. Output‑level interventions - particularly those focused on RMNCH and child health (including immunisation and nutrition), technical assistance at national and regional levels, and infection prevention and control - are expected to contribute to outcomes such as improvements in the UHC service coverage index and health security by increasing the availability, quality and continuity of essential services, strengthening institutional capacity, and improving preparedness and response functions. However, the extent to which these output‑level gains translate into sustained outcome‑level improvements is constrained by ongoing conflict, fiscal pressures, and uneven regional performance, which continue to limit coverage, equity and system functionality in parts of the country. The emphasis on strengthening core system functions and capabilities is consistent with FCDO’s approach to health systems strengthening, which prioritises resilient, well‑governed systems as the foundation for progress towards universal health coverage and improved health security.[1]
[1] Health systems strengthening for global health security and universal health coverage - GOV.UK

Since programme inception, the most significant changes have occurred at the output level, rather than at outcome or impact level, and do not represent a material departure from the programme design approved in the Business Case. Key changes to the logframe include:
- Introduction of a new Output on Technical Assistance (Output 5): A new output has been added to make explicit the role of TA in strengthening MoH and RHB planning, budgeting and management capabilities. This includes indicators on the development and uptake of planning and reporting tools, transition planning for TA and the production of research and policy outputs.
- Rebalancing of output weightings: Output weightings have been revised to place greater emphasis on equity and systems strengthening, alongside service delivery. This includes a relative increase in weighting for the inequalities output and the introduction of a dedicated weighting for TA.
- Refinements to output indicators and targets: Output‑level indicators have been expanded or refined where appropriate (for example, the addition of Growth Monitoring and Promotion under Output 1), and targets have been revised to reflect more realistic targets based on the team’s implementation experience.
- Clarification of output focus areas: While earlier versions of the log-frame explicitly referenced climate change, the current log-frame narrows the focus to disease surveillance and response

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Overall, the programme remains broadly on track to contribute to its intended outcomes and impact, with output targets largely on track (with the notable exception of childhood immunisation), albeit with uneven progress across regions. As outlined elsewhere in this report, national‑level health outcomes continue to show long‑term improvement, but recent gains have slowed and become more uneven, reflecting a combination of system pressures, conflict‑related disruption, resource constraints, and persistent regional and socioeconomic inequalities. While the programme’s core logic remains valid, the extent to which delivered outputs translate into sustained and equitable outcomes is shaped by a range of interrelated contextual and system‑level factors. Over the past year, delivery has been further challenged by national economic pressures, reductions in ODA, and ongoing conflict. Looking ahead, political uncertainty surrounding national elections, potential fuel and supply‑chain disruptions linked to regional instability and Middle East–related crises, and the prospect of further funding pressures may affect the pace of progress. At the same time, there are important opportunities for the EPD‑E programme, including strengthened leadership within the team. More broadly within Ethiopia, the increased international attention associated with COP32 being hosted in Addis Ababa presents opportunities to strengthen continued policy engagement.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Despite ongoing contextual challenges, the programme continues to represent good value for money by delivering through government systems and supporting sustainable health system strengthening. Delivery against agreed outputs indicators provides reassurance on implementation. In a context of evolving conflict, the programme’s focus on sustaining core government systems remains relevant to mitigating service disruption and maintaining delivery of essential primary health care. Through this systems‑based approach, the programme supports government‑led efforts to address maternal and child mortality by strengthening service access and contributing towards progress on SDG 3. Based on delivery performance, alignment, and value‑for‑money considerations, there is sufficient evidence to justify continuation of the programme.

## C. DETAILED OUTPUT SCORING

Output Title	Improved uptake of the highest impact package of RMNCH interventions
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	Down

Indicator(s)	Milestone(s) for this review	Progress
1.1 Modern Contraceptive Prevalence Rate	35%	34.5% married women, 33.9% unmarried (EDHS)
1.2 Deliveries attended by Skilled Birth Provider (Percentage)	65%	64.1% (EDHS)
1.3 Proportion of pregnant women who received antenatal care 8 contacts or more (Percentage)	30%	47% (administrative data) / 37% HSDIP I Situational Analysis / ANC 8+ Data not released from EDHS yet - 53% of women received ANC4+ (EDHS 24-25)
1.4 Proportion of children participating in Growth Monitoring and Promotion (GMP) for 0-24 months (%)	75%	60% (HSDIP situation analysis)

Briefly describe the output’s activities and provide supporting narrative for the score.
For the Ethiopian financial year 2018 (8 July 2025 to 7 July 2026), the Ministry of Health allocated 31% of the national health programme budget to RMNCH. As per the most recent quarter report, RMNCH counts 46% of the SDG-PF budget. According to SDG-PF financial monitoring reports, 29% of SDG-PF expenditures were directed towards RMNCH, including activities related to adolescent health. According to the Health Sector Development and Investment Plan I (HSDI I) situation analysis (2005–2025), changes in RMNCH outcomes in Ethiopia were attributed investments in primary health care expansion, the health extension programme, and selected facility- based interventions.

Progress against last year’s indicators has been difficult to assess, primarily because this year’s review draws on the recently released EDHS 2024–25 data, whereas last year’s AR relied largely on administrative sources. For example, the modern contraceptive prevalence rate was not reported in the previous AR, and although administrative data suggest a significant increase in ANC8+ coverage compared with last year, this trend is not corroborated by the EDHS findings. GMP performance has also remained broadly unchanged, with persistent and notable regional disparities.

Overall, Output 1 is assessed as having met expectations, while recognising mixed performance across the underlying indicators and continued challenges in data comparability. Two indicators narrowly missed their annual milestones: modern contraceptive prevalence was 34.5% among married women against a 35% milestone, and skilled birth attendance was 64.1% against a 65% milestone. These variances are small and do not, in themselves, suggest material underperformance. ANC8+ appears to have met or exceeded the milestone using available administrative and HSDIP I sources, although the EDHS 2024–25 ANC8+ figure has not yet been released and comparisons across data sources should be treated cautiously. Growth Monitoring and Promotion materially underperformed, at 60% against a 75% milestone, and this remains the clearest area of underperformance under the output. On balance, the output is assessed as meeting expectations overall, given that most indicators are either close to or above milestone, while the narrative and recommendations recognise the significant underperformance on GMP, persistent regional disparities and the need to review indicator suitability in the next results framework update.
Indicator 1.1 Modern Contraceptive Prevalence Rate
Results from the 2024–25 EDHS show that 34.5% of married women and 33.9% of unmarried women were using a modern method of contraception. In comparison, the mini‑EDHS 2019 reported 40.5% of married women using a modern method. Among married women, modern contraceptive use was 44% in urban areas and 30% in rural areas. Among unmarried women, use was 42% in urban areas and 26% in rural areas; further disaggregation for unmarried women was not available. Unmet need for contraception declined from 22% to 15% between EDHS 2016 and EDHS 2024-25.

Regional variation was substantial for married women. The lowest levels of modern contraceptive use were observed in Somali (1.6%) and Afar (8.8%). The highest levels were found in Sidama (55.7%) and South-West Ethiopia (54.2%). Use of modern contraceptives among married women varied by education level, ranging from 21.4% among those with no formal education to 49.8% among those with secondary education. Variation was also observed across wealth quintiles, with 16.2% use among women in the lowest quintile and 46.6% in the highest.

The HSDI I situational analysis noted continued uptake of short acting family planning methods and identified low coverage of postpartum family planning, indicating missed opportunities during postnatal contacts. Mid-year administrative data for EFY 2018 showed an increase in overall family planning coverage from 24% to 29%. Short acting methods, including injectables, accounted for the majority of use (68%). The data also reported an improvement in postpartum family planning coverage (26%) and a reduction in teenage pregnancy from 13% (EFY 2017) to 11%.

Stakeholders consulted during the AR period highlighted several factors affecting family planning uptake, including persistence negative social norms and the influence of religious beliefs, limited male engagement, early marriage in some communities, and limited provision of reproductive health education within the school system. The Ministry of Health reported several initiatives to address these challenges. These included trials of self-administration of long-acting depo, human-centred design approaches to better address barriers and developing guidelines around these, identifying married adolescents for tailored counselling and scaling up adolescent friendly services, ministerial collaboration on early marriage and work with the Ministry of Education on a roadmap to address teenage pregnancy with educational material and teacher training. Additional efforts included expanding postpartum family planning services by scaling up IUCD training and task shifting to enable provision at health posts. Some of these initiatives are being supported through FCDO Women’s Integrated Sexual Health 2 programme (WISH2) in regions such as Tigray, Afar and Amhara.
Indicator 1.2: Deliveries Attended by a Skilled Birth Provider
Progress on this indicator is reported using results from the EDHS 2024–25, which reflect births occurring in the two years prior to the survey. The indicator is defined as the proportion of births delivered with the assistance of skilled providers, including doctors, nurses, midwives, health officers and health extension workers. Results from the 2024–25 EDHS show that 64.1% of births in the previous two years were attended by a skilled provider. In comparison, the mini‑EDHS 2019 reported that 49.8% of births in the previous five years were delivered by a skilled provider. Differences in recall periods between the two surveys should be noted, although this is unlikely to substantially affect interpretation of the upward trend. Over the longer term, the percentage of women with a live birth in the two years preceding the survey whose delivery was assisted by a skilled provider has increased from 12% in 2011 to 64% in 2024–25. Further analysis of the disparity in deliveries attended by a skilled birth provider can be found in the output 3 section.

Mid-year administrative data for EFY 2018 reported that in the last six months, skilled birth coverage was 83%. Regional variation showed that Afar had the lowest coverage (34%), while Addis Ababa and Harari reported 100% coverage. At facility level, the administrative data indicate that 70% of skilled deliveries were conducted in health centres, 26% in hospitals and 4% in clinics and health posts. As these are administrative coverage figures, they may differ from survey-based estimates such as the EDHS, which use reported births rather than expected births as the denominator.

Stakeholders consulted during the AR period identified several interventions they viewed as contributing to progress in this area. These included the expansion of PHC and the health extension programme, as well as the establishment of maternity waiting homes, which provide accommodation for expectant mothers close to health facilities. Many of these facilities are located in remote areas and have been developed with regional authorities to ensure culturally appropriate design and community mobilisation to support the women.
Indicator 1.3 Proportion of pregnant women who received antenatal care 8 contacts or more (Percentage)
The preliminary EDHS 2024–25 data released to date do not include the indicator for ANC8+. However, EDHS does report the proportion of women attending ANC4+, with 53% of women had four or more ANC visits during their most recent pregnancy resulting in a live birth (75.0% in urban areas and 43.8% in rural areas). Regional variation was substantial, with the lowest coverage reported in Somali (12.0%) and the highest in Addis Ababa (94.8%). Differences by education level showed 35.5% coverage among women with no formal education compared with 90.9% among those with more than secondary education. By wealth quintile, the lowest quintile recorded 25% coverage and the highest 82%.

The recent HSDIP I situational analysis notes that completion of ANC8+ visits remains challenging, despite improvements in administrative reporting. The analysis reports ANC8-contact coverage increasing from a baseline of 15% to approximately 37%, surpassing the HSDIP I target of 30%, while also noting that early ANC initiation before 12 weeks remains low at around 33%. The lowest uptake was observed in pastoralist and remote regions. The report attributes the limited uptake to factors such as population mobility, uneven distribution of health facilities, transport barriers and shortages of skilled health workers, as well as sociocultural factors affecting service use. Conflict and climate related shocks have also disrupted service delivery in some regions. Measures introduced to help address these challenges include mobile and outreach services, region specific equity plans and humanitarian health responses.

Midyear administrative data for EFY 2018 reported that 47% of pregnant women received ANC8+ services, an increase from 37% the previous year. Regional disparity showed that Gambella, Tigray, Benishangul-Gumuz, Afar and Harar had the lowest coverage, while Addis Ababa and Sidama recorded the highest. The denominator for this administrative indicator is the expected number of pregnancies derived from population projections rather than actual recorded pregnancies. This administrative figure is therefore useful for tracking trends within the HMIS system, but comparisons with survey-based estimates should be made cautiously, as the two systems use different denominators, data sources and recall periods.

Consultation with stakeholders indicated that early engagement was viewed as critical, with ANC1 highlighted as an important entry point for supporting accurate gestational age assessment and encouraging continued ANC attendance. They noted several barriers to early initiation, including a high proportion of unplanned pregnancies, cultural norms that discourage announcing pregnancy before three months, and earlier health messaging advising women to attend ANC after the first trimester. Stakeholders reported working with communities to change longstanding messages that discouraged early ANC attendance and noted that the availability of ultrasound services at health posts had supported ANC attendance. They also emphasised that achieving ANC8+ is particularly challenging for pastoralist communities, where long travel distances and associated costs make repeated facility visits difficult.
Indicator 1.4 Proportion of children participating in Growth Monitoring and Promotion (GMP) for 0-24 months (%)
This indicator reflects service utilisation, capturing the proportion of children aged 0–24 months who were brought for routine GMP services. According to HSDIP I, GMP services reached approximately 60% of children nationally, and health posts conducted 78.6% of child growth monitoring activities. The year plan target set out in the SDG-PF admin report is 70% and actual performance achieved in six months is 63% (90% of the plan).

Mid‑year administrative data for EFY 2018 reported a performance gap for GMP compared with the national target, with coverage also falling below the baseline from the previous year. Regional variation was significant. The highest proportions of children participating in GMP were recorded in Amhara (77%) and Oromia (76%), while the lowest were in Somali (8%) and Gambella (8%). These differences point to disparities in service access, availability, and utilisation across regions.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Recommendations from last year’s AR included revising the indicator and ensuring access to reliable data sources. The indicator wording has been updated to modern contraceptive methods and with the availability of EDHS further data is available to triangulate. The other recommendation was to work with donors and MoH through other complimentary mechanisms (JCCC, CCM) to improve performance across output 1 areas, which has been implemented throughout the review period.

One consideration emerging from this year’s lessons is whether the emphasis placed on ANC8+ as a core indicator remains appropriate. Stakeholders highlighted the national prioritisation of ANC1 and ANC4, and it may be more appropriate for the logframe to reflect this focus - particularly if ANC8+ data is not to be released through the EDHS.

The continued and pronounced regional inequities present a substantial challenge: national level improvements appear to be driven largely by higher performing regions, which obscures limited progress in other areas. Although substantial work is underway nationally - such as through the National Health Equity Plan - to address these disparities, the EPD-E programme team should consider how best to use programme levers to advocate for and support action on regional and socioeconomic inequalities. Strengthening this focus will be an important learning aim for the coming year.
Recommendation 11: Consider revising the relevant output indicator from ANC8 to ANC4 or ANC1, to improve alignment with GoE priorities, data availability and pathways of change.

Output Title	Improved quality of child health services including nutrition services
Output number:		2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	Down

Indicator(s)	Milestone(s) for this review	Progress
2.1 Children 12-23 months immunized with Pentavalent 3 vaccine	41%	39.8%
2.2 Vit A supplementation (two dose)	37%	86%

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is focused on improving the quality of child health services, including nutrition services, essential childhood immunisation to reduce the risk of preventable diseases (e.g. measles, polio, rota) and vitamin A supplements to maintain strong immune systems and reduce the incidences of diarrhoea and measles in children. According to MOH and Agencies Level Health Program Budget for the Year 2018 EFY, 7% was allocated to immunisation, 7% to child health and another 7% to nutrition. Of these funds, 29% came from SDG-PF for newborn and child health, 15% from SDG-PF for immunisation and 17% from SDG-PF from nutrition. From EDHS 2024-25 data and AHEAD immunisation analysis (with UNICEF), it appears childhood vaccination trends improved slightly compared to 2019 but stagnated in the recent years. In the context of milestones for this review, the progress for children receiving pentavalent 3 vaccine moderately did not meet expectations and according to administrative data the vit A supplementation progress significantly exceeds the milestone.
Give an overview of what the output has achieved, and whether it is on track or off track to hit end-of-programme targets. Make sure you highlight any significant challenges, issues or underperformance.

Indicator 2.1 Children 12-23 months immunized with Pentavalent 3 vaccine: According to the EDHS 2024–25, 39.8% of children aged 12–23 months received the third dose of the Pentavalent vaccine, with most data drawn from vaccination cards. There is a notable drop‑off across the immunisation schedule: while 70.6% of children received the first dose, only 39.8% completed all three. Coverage was similar across gender (41.0% for males and 38.3% for females) but showed substantial disparities by residence, with uptake at 58.8% in urban areas compared with 32.1% in rural areas. Birth order was also associated with completion rates: first‑born children had much higher coverage (49.1%) than those sixth or later in birth order (25.6%). Regional disparities were pronounced, ranging from 18.9% in Somali to 88.2% in Addis Ababa.

Socioeconomic factors mirrored these inequalities. Children whose mothers had education beyond secondary level had much higher completion rates (70.5%) compared with those whose mothers had no formal education (26.6%). A similar pattern emerged across wealth quintiles, with coverage at 65.9% in the highest quintile but only 15.8% in the lowest. Overall, the indicator highlights both low completion of the full Pentavalent schedule and significant inequities across geography, education, and economic status.

Ethiopia’s routine immunisation denominators in DHIS2 are based on population projections from the 2007 national census. Consequently, these denominators do not adequately reflect subsequent administrative boundary changes, demographic shifts, or population movements. In addition, the projected population figures are lower than UN World Population estimates, contributing to distortions in coverage calculations. For example, mid‑year administrative data for EFY 2018 report coverage of the third dose of the pentavalent vaccine at 113 percent, indicating likely denominator underestimation.

Despite these limitations, stakeholders noted that DHIS2 data remain useful for monitoring relative trends in immunisation performance over time, particularly as national investments in data quality improvement continue. A recent UNICEF–Ministry of Health report, which applied alternative population denominators, found that immunisation coverage has improved modestly since 2019 but has plateaued in recent years. The analysis also highlighted substantial geographic inequities, underscoring the need for targeted, subnational strategies rather than uniform national approaches.[2]
[2] Actionable Health Analytics for Decision-Making. National and subnational immunisation Data Quality Revied and Coverage Estimation, 2018-2024

According to the HSDIP situational analysis, routine immunisation services are available in approximately 75 percent of health facilities nationwide and are supplemented by outreach, mobile delivery strategies, and periodic supplementary immunisation activities. Through the Big Catch‑Up initiative, Ethiopia reported a 57 percent reduction in the number of zero‑dose children, vaccinating more than 2.2 million previously unvaccinated children by November 2025. However, the report highlights several persistent challenges, including cold chain reliability, human resource constraints, data quality gaps, and continued reliance on external financing. In addition, field visits to health centres and health posts in the Somali region observed generally strong practices, including accurate vaccine data collection, functional cold chain facilities with regular temperature monitoring, availability of sharps disposal bins, and the use of immunisation monitoring charts.

Consultations with MoH stakeholders indicated that a national immunisation strategy is currently in draft, with a renewed focus on strengthening routine immunisation within PHC. Discussions with global health initiatives highlighted that equity—now a core principle of the Gavi strategy -is expected to be operationalised through more tailored, sub‑national grant design. Partners pointed to complementary initiatives, including the Gates‑funded Project HOPE woreda‑level surveys to better identify zero‑dose children and recurrent outbreak areas, and the ZIP project, initially launched in Tigray and subsequently expanded to Oromia and Amhara, which has demonstrated the value of flexible approaches to service delivery and supply chain strengthening in conflict settings. Gavi reflections also underscored persistent challenges, including aligning partners around consistent population data, ensuring data are programmatically useful (for example, using BCG as a proxy denominator for first contact), and managing coordination within Ethiopia’s “one plan, one budget, one report” framework amid an increasingly complex landscape of compacts. Overall, stakeholders emphasised the need for partners to support Ethiopia’s level of ambition by translating strategic direction into practical, operational approaches that strengthen MoH oversight and decision‑making.

Vit A supplementation (two dose): Vitamin A supplementation data were obtained from mid‑year administrative reports for EFY 2018 and therefore represent a six‑month reporting period. Coverage estimates are based on projected target populations derived from routine administrative denominators. According to these data, 86% of eligible children received two doses of vitamin A during the reporting period. This is an increase from 57% in the same period the year before. According to SDG‑PF reports, vitamin A capsule availability was monitored monthly, with inter‑regional redistribution used to mitigate localized supply gaps. Field visits to a health centre and a health post in the Somali region observed adequate supplies of vitamin A, along with routine facility‑level monitoring.

While Vitamin A supplementation coverage is a widely used measure and provides a useful snapshot of service reach, it offers only a limited view of the broader quality and comprehensiveness of nutrition services. A more informative indicator would be the proportion of children screened for malnutrition at key clinical contact points would better reflect the integration and routine delivery of essential nutrition assessment within the health system. Mid‑year administrative reports for EFY 2018 shows 79% of under 5-year-olds were screened for malnutrition, compared to 76% in the same time period a year earlier.

In addition to service‑delivery metrics, outcome‑oriented indicators, such as the proportion of children achieving Minimum Dietary Diversity (MDD) and Minimum Meal Frequency (MMF) provide a stronger indication of actual improvements in feeding practices and nutritional status, thereby offering a more meaningful assessment of programme quality and impact. For example, data from the EDHS 2024–25 report show that only 16% of children aged 6–23 months are fed with a minimum dietary diversity, highlighting the substantial gap that persists in child feeding practices.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

While the previous Annual Review recommended revisiting a number of indicators, including those related to immunisation in this output and equity in output 3, these were not actioned during this review period due to ongoing data constraints and the timing of the EDHS 2024–25 release. With updated data now available and limitations more clearly identified, revising indicators and strengthening the results framework will be prioritised in the next review cycle.

The output on improved quality of child health and nutrition services is currently measured using Pentavalent 3 coverage and two‑dose vitamin A supplementation. While important and often used as proxies for service performance, these indicators primarily capture service coverage rather than quality, creating partial misalignment between the output description and how performance is assessed.
Recommendation 12: Either revise the output description to explicitly reflect coverage outcomes or introduce a complementary quality‑focused indicator (for example, related to timeliness or protocol adherence) to strengthen coherence between the output and indicators.

Output Title	Decreased regional and socioeconomic inequalities in essential RMNCH service coverage
Output number:		3	Output Score:	B
Impact weighting (%):		20	Weighting revised since last AR?	Up

Indicator(s)	Milestone(s) for this review	Progress
3.1 Ratio of deliveries assisted by Skilled Birth Attendants between pastoralist and non-pastoralist regions	0.6	0.51
3.2 Ratio of pentavalent 3 coverage between the highest quantile and lowest quantile	0.78	0.24
3.3 Ratio of OPD attendance Between Pastoralist and Non pastoralist regions	0.9	0.21

Briefly describe the output’s activities and provide supporting narrative for the score.
A key aim of the programme is to address geographic inequalities, especially concerning service coverage in pastoralist compared to non-pastoralist regions. Persistent inequities in access to essential health services align with the structural constraints outlined in the National Health Equity Strategic Plan 2020–2025. The Plan identifies inadequate health financing and high out of pocket expenditures as primary determinants of unequal service utilisation, further compounded by weaknesses in health planning, limited healthcare worker capacity, and incomplete last-mile drug distribution in developing regions. These system inefficiencies intersect with sociocultural norms that reduce health-seeking behaviour, collectively reinforcing disparities in coverage, quality, and outcomes across population groups. Therefore, this output scores a B.
Give an overview of what the output has achieved, and whether it is on track or off track to hit end-of-programme targets.
3.1 Ratio of deliveries assisted by Skilled Birth Attendants between pastoralist and non-pastoralist regions: The current ratio of skilled birth attendance between pastoralist (Afar and Somali) and non-pastoralist regions is 0.51, compared with 0.56 last year. Skilled birth attendance in pastoralist regions remains at roughly half the level seen in non-pastoralist regions. This indicates a worsening inequality and suggests the output is off track to narrow regional disparities by end-of-programme.

However, this ratio has important limitations. Both Afar and Somali include urban and agrarian areas, and pastoralist populations also reside in other regions. As a result, the “pastoralist vs non-pastoralist” comparison oversimplifies population realities and may not accurately reflect inequity in mobile and semimobile populations. Stakeholders in the Ministry noted that this ratio provides limited operational value, and the equalities team is exploring woreda (district) level analyses to generate a more meaningful picture of inequity.

More detailed descriptive statistics provide a clearer understanding of progress. The region with the lowest skilled birth attendance in mini-EDHS 2019 (Somali at 26%) has improved to 35% in EDHS 2024–25. Addis Ababa, the highest performing region, increased from 95.7% to 98.2% over the same period. Despite these improvements, substantial inequalities persist: Urban: 91.5% vs. Rural: 52.5%; Regional lowest: Afar 35%, Somali 37%; Regional highest: Addis Ababa 98.2%, Dire Dawa 83%; By education: 44.2% (no education) vs. 97.2% (secondary+); By wealth: 30.6% (lowest quintile) vs. 96.1% (highest quintile).

Ratio of pentavalent 3 coverage between the highest quantile and lowest quantile: EDHS 2024–25 data show pentavalent 3 coverage of 15.8% in the lowest wealth quintile and 65.9% in the highest, resulting in an absolute disparity of over 50 percentage points. In mini‑EDHS 2019, coverage was 46.2% among the lowest quintile and 80.6% among the highest. This suggests a widening wealth‑related inequality; however, the magnitude of the change raises questions about data comparability between survey rounds, given differences in sample size, survey timing, and methodology. Despite this caveat, the direction of inequality is consistent across multiple datasets.

The National Health Equity Survey reports a concentration index of 0.12 for all base vaccines, indicating that overall vaccination coverage remains disproportionately concentrated among the wealthiest households. This aligns with the trend seen in the pentavalent data and highlights persistent systemic barriers.

3.3 Ratio of OPD attendance Between Pastoralist and Non pastoralist regions: Mid‑year EFY 2018 administrative data indicate that OPD attendance per capita was 0.6 in Afar and 0.4 in Somali over the six‑month reporting period. When compared with the non‑pastoralist regions, this translates to a ratio of 0.21, signalling markedly lower utilisation of outpatient services in areas commonly categorised as pastoralist. However, the usefulness of this ratio is constrained by several structural limitations. Afar and Somali cannot be treated as pure proxies for pastoralist populations, as both include substantial agrarian and urban communities, while pastoralist groups are also present in other regions that are classified as non‑pastoralist within this metric. In addition, administrative data do not capture seasonal mobility patterns or the way population movement shapes fluctuating service use.

Despite these caveats, the overall trend is consistent with regions with large pastoralist populations continue to demonstrate significantly lower OPD attendance compared with the rest of the country. This indicates that the indicator remains off track, with limited progress in addressing the unique access barriers faced by mobile and hard‑to‑reach communities.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
The main lesson from this year’s review is that Output 3 needs to move from describing inequity to more clearly influencing how programme resources, data and policy engagement are used to address it. The current indicators highlight important disparities but have limitations: Afar and Somali are imperfect proxies for pastoralist populations; wealth-quintile ratios are sensitive to survey comparability; and OPD attendance based on administrative data does not capture seasonal mobility or unmet need. At the same time, the evidence is consistent: inequities remain pronounced across geography, wealth, education and residence, and lower-performing regions and populations continue to lag behind national averages. This suggests that the programme should retain a strong equity focus, but make it more operational through better subnational analysis, more explicit resource targeting, and clearer links to SDG-PF planning, monitoring and review processes.
Recommendation 13: FCDO should work with MoH and SDG-PF partners to develop a clearer, evidence-based equity approach for the next review period, focused on low-performing regions and woredas. This should include EPD-E reviewing the current equity indicators, which have limited operational value; using EDHS, DHIS2 and regional data to identify priority underserved populations; assessing whether SDG-PF-financed resources and commodities are reaching these areas; and agreeing targeted actions through existing sector mechanisms.

Output Title	Enhanced disease surveillance and response / (change from: Response for climate change and enhanced disease surveillance and response)
Output number:		4	Output Score:	A
Impact weighting (%):		10%	Weighting revised since last AR?	Down

Indicator(s)	Milestone(s) for this review	Progress
4.1 Proportion of health facilities having basic sanitation / facilities (%)	54%	40% (Admin data EFY 2018), / 65.5% (SDG-PF Q2 report) / 77% (HSDIP-I situation analysis)
4.2 Proportion of health care facilities having basic health / care waste management (%)	73%	74% (EFY 2017)
4.3 Percentage of outbreaks controlled without excess mortality above national standards	95%	88.6% (2017, Woreda Based Plan via MoH)

Briefly describe the output’s activities and provide supporting narrative for the score.

During the reporting period, activities under this output focused on strengthening core public‑health protection functions at the facility level, improving WASH and waste‑management systems, and supporting outbreak detection and response capacity. Overall progress shows continued improvements in surveillance readiness, though performance across indicators remains uneven, with persistent gaps in low‑capacity and conflict‑affected regions. The overall score is A.
Give an overview of what the output has achieved, and whether it is on track or off track to hit end-of-programme targets.

4.1 Proportion of health facilities having basic sanitation facilities (%): Basic sanitation in health facilities reached 40% according to EFY 2018 mid‑year administrative data. However, performance varied widely, with extremely low coverage in Tigray (2%) and Somali (3%) compared to higher levels in Dire Dawa (65%). Estimates from other data sources were higher, for example the SDG-PF Q2 report reports 65.5% of health facilities had basic sanitation and the HSDIP 1 situation analysis reported 77%.

Facility visits showed similarly mixed conditions: A health centre had running water, soap, sanitiser, personal protective equipment, and functioning sterilisation capacity, whereas the visited Somali health post lacked running water and relied on stored rainwater. While basic infection‑prevention commodities were present, the absence of consistent water supply highlights ongoing challenges. Overall, progress is modest but off track to reach universal basic standards.

4.2 Proportion of health care facilities having basic healthcare waste management (%): Basic healthcare waste management performed better, with EFY 2018 data indicating 74% of facilities meeting minimum waste‑management requirements. Field observations confirmed the presence of sharps bins, segregation of clinical and non‑clinical waste, and access to an incinerator at the Somali health centre. In contrast, the health post relied on cardboard sharps boxes that were transferred via ambulance for disposal, and placenta pits were used in the absence of an incinerator. These findings demonstrate that while most facilities meet minimum standards, significant infrastructure gaps persist at the primary‑care and community levels, particularly in remote settings.

4.2 Percentage of outbreaks controlled without excess mortality above national standards: For outbreak control, MOH estimates indicate that 88.5% of outbreaks in EFY 2017 were contained without excess mortality above national standards. A notable event since the last AR was the containment of the Marburg Virus Disease outbreak in EFY 2018. Fourteen cases and nine deaths were confirmed in the regions of Southern Ethiopia, and a total of 886 contacts were traced and monitored. The Ethiopian authorities responded swiftly, reporting through relevant outbreak mechanism, declaring the outbreak and standing-up MoH-led pillars to coordinate the response. The fast containment and response in this outbreak demonstrated how over a decade of sustained investment in health system strengthening and preparedness backed by the UK and other partners, supported the Ethiopian health system respond and lead the coordination of this outbreak.

During the response the UK provided support through a wide array of mechanisms. It included EPD-E, through which the UK provided additional £500k to support the Ministry of Health in providing resilience to ongoing health services, whilst technical assistance through TAMU coordinated the development of its first MVD Case management guidelines. The bilateral humanitarian programme Ethiopia from Crisis to Resilience (EC2R) programme provided PPE, ICU equipment, and MVD diagnostic tests to support the Ministry of Health scale up its response.

The Ethiopian Health System’s ability to coordinate, respond and contain the Marburg outbreak stands out as evidence of strengthened national public health capacity backed by sustained different complimentary investments across the health system beyond thsi programme.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Climate change is a significant determinant of health outcomes in Ethiopia and a priority for FCDO, with growing national attention ahead of COP 30 in Addis Ababa.
Recommendation 14:
Consider an indicator for climate resilience under Output 4 of the EPD‑E programme, focused on strengthening climate‑resilient health system planning and service delivery.

Output Title	EPDE TA Supported which enhances planning budgeting and management capabilities (CT completing)
Output number:		5	Output Score:	A+
Impact weighting (%):		10%	Weighting revised since last AR?	New output

Indicator(s)	Milestone(s) for this review	Progress
5.1.1. Number of new planning, monitoring and reporting tools put in place to strengthen MOH institutional capacity	2	1 dashboard and another under development (TAMU)
5.1.2. Number of MOH units applying the TA planning and reporting tools in their planning and reporting cycles.	15	15 (TAMU)
5.2 / Number of TAs with agreed MOH transition plans in place	32	32 (TAMU)
5.3 TAMU transition plan Developed	1	Awaiting MoH approval (TAMU)
5.4 Number of longitudinal research Analytical Summary Reports and Policy Briefs produced	2	2 (Young Lives)

Briefly describe the output’s activities and provide supporting narrative for the score.
This output supports technical assistance, institutional capacity and evidence generation through two complementary components: the Technical Assistance Management Unit (TAMU), delivered by UNOPS and embedded in the Ministry of Health, and the Young Lives Qualitative Longitudinal Research programme, delivered by the University of Oxford and its Ethiopia partners. Together, these components strengthen government systems, improve the coordination and use of technical assistance, and generate policy-relevant evidence on the health and wellbeing of young people during overlapping crises.

TAMU has exceeded expectations during the review period. TA inputs have supported priority areas including immunisation strategy development, HSDIP II, Marburg Virus Disease guidelines, RMNCH policy and programme assessment, measles vaccination campaigns, emergency preparedness, audit and risk management, CBHI adaptation in pastoralist settings, and local pharmaceutical capacity. In addition to supporting the directly onboarded TAMU TAs, TAMU has begun to provide MoH with much stronger sector-wide visibility of technical assistance, including through a national TA distribution assessment covering federal and regional institutions and a centralised dashboard/database capturing more than 5,000 TA profiles across MoH, agencies and regions. TAMU has also supported knowledge-sharing and capacity-building across MoH and regions, with 30 knowledge-sharing activities reaching 933 participants between July 2024 and June 2025, although women represented only around a quarter of participants, suggesting continued scope to strengthen gender balance in capacity-building activities.

Young Lives has also exceeded expectations against agreed outputs. The Qual 6 programme completed fieldwork with 494 respondents, exceeding the original target of 460, and completed the analytical summary report alongside a literature review on health services, health expenditure and health outcomes in Ethiopia. The research provides evidence across eight themes: FGM/C and early and child marriage; maternal and child health; sexual and reproductive health; disabilities; mental health; education; work and underemployment; and migration. These findings are directly relevant to EPD-E’s focus on RMNCH, equity, health systems resilience, conflict sensitivity and the wider determinants of health. Young Lives evidence has been actively disseminated and used for policy engagement, including through an Embassy-hosted presentation, the January 2026 high-level dissemination event with over 130 policymakers, researchers and practitioners, and follow-up interest in applying the findings to Embassy priorities such as migration, mental health, SRH, education and wider human capital policy

Overall, this output is on track and assessed as moderately exceeding expectations. All milestones have been met or exceeded. It has delivered important system-level contributions including stronger government stewardship of technical assistance, better visibility of TA deployment and deliverables, improved evidence for policy-making, and stronger alignment with national systems and priorities.
Give an overview of what the output has achieved, and whether it is on track or off track to hit end-of-programme targets.
The output is on track to meet its end-of-programme intent, although some areas require close management over the coming year. TAMU has established a functioning system for overseeing current TA including coordination, planning tools, workplans, quarterly performance reviews, a centralised TA database and a performance dashboard. This represents a shift towards institutionalising a more strategic, demand-led and government-owned approach to technical assistance through systems. Wider Ministry-wide uptake remains incomplete: out of 326 TAs deployed to the Ministry by various development partners, only 121 had submitted EFY 2018 individual workplans. This suggests TAMU has built credible systems and demonstrated proof of concept, but further senior leadership and partner alignment are needed to extend these tools beyond the TAMU-supported cohort.

Young Lives has also delivered impact. A second phase, Qual 6.2, has been agreed for January-December 2026, with FCDO Ethiopia and Irish Aid support to produce five research papers and five policy briefs, accompanied by high-level policy engagement and dissemination.

The main challenges are around institutionalisation and use. For TAMU, the key risk is whether the systems developed under the project can be sustained and mainstreamed beyond the directly supported cohort, given delayed approval of the TA Management Guideline and SOPs, incomplete uptake of TA planning tools across the wider TA ecosystem, data gaps for partner-hired TAs, delayed supervisor feedback, and transition issues relating to governance, staffing, systems, assets and financing. For Young Lives, the main challenge is not delivery, as Phase One deliverables were completed, but ensuring that the evidence is translated into policy dialogue and programme learning across health, education, gender, migration, mental health and wider human capital priorities.
Describe major changes in the past year and their implications for the programme.
Following this review, the FCDO team should focus on setting clear milestone targets for the next AR around the approval and operationalisation of the TA Management Guideline and SOPs; the implementation of a realistic TAMU transition plan and the broader adoption of TA planning and reporting tools beyond TAMU-supported TAs; and on the use of Young Lives evidence in relevant policy and programme fora.

Recommendation: FCDO should engage with UNOPS, as well as MoH and IPHC-E senior leadership to ensure smooth transition and continuity of TAMU, and work with donors to ensure alignment behind the MoH vision of better TA management and oversight.
## D: VALUE FOR MONEY

Cost drivers and VfM performance compared to the original VfM proposition in the business case

The programme’s VfM is determined by the ‘5E’s, namely i) economy measured by the cost of commodities/drugs compared to the international price and capacity building/ skill development of primary health care workers; ii) efficiency - whether the output is delivered as per the budget; iii) effectiveness - whether the planned outcomes are being achieved as per the budget and specified time; iv) equity - whether health outcome disparities seen geographically are reducing and the gap between the lowest performing regions and the national average is narrowing; and v) cost effectiveness. The insights below are based on data from the EFY 2018 second quarter financial and on wider reports related to the SDG-PF.

Economy: The programme demonstrates strong economy through effective control of key cost drivers, including the pricing of commodities and medicines benchmarked against international reference prices; the costs of skills development for primary health care providers; and the cost of technical assistance (TA) provision compared with similar programmes.

Approximately 90% of the SDG-PF EFY 2018/19 budget was allocated to procurement. All procurement was undertaken through open and competitive bidding, in line with Ethiopia’s Federal Public Procurement and Property Authority and Ministry of Finance procurement rules, as stipulated in the Joint Financing Agreement (JFA). The Ethiopian Pharmaceutical Supply Agency (EPSA)—the mandated national health-sector procurement agency—remained responsible for the procurement and distribution of health commodities to public health facilities. Procurement plans and implementation were further subject to review and clearance through SDG-PF donor group and Joint Core Coordinating Committee (JCCC) monthly meetings, providing additional assurance. These arrangements ensured that medical equipment and supplies were procured at the right quality and price, thereby maintaining good value for money.

In relation to TA and grants, an MoU amendment of £20,000 was signed with UNOPS to allow TAMU to continue programme implementation. An Accountable Grant amendment of £200,000 was signed with the University of Oxford on a non‑competitive basis, justified by the counterparty’s partnership with the Young Lives Project, which has over 25 years of demonstrable expertise in longitudinal research in maternal and child health, nutrition, sexual and reproductive health, mental health, and disability in Ethiopia. The direct award represented value for money through proven capability, strong contextual knowledge, and timely delivery.

The programme also invested in cost‑effective capacity building and skills development at primary health care level, including training on ultrasound, nutrition screening, Women’s Development Alliance (WDA), training of trainers (ToT) on emergency preparedness and response to climate‑related public health hazards, point‑of‑care early infant diagnosis (EID) testing and reporting, breast cancer, weaving and sewing, and other professional skills, strengthening frontline service delivery at relatively low unit cost.

1. Efficiency: The programme achieved all planned milestones for FY 2025/26, including targets on cost of immunisation and cost per facility‑based delivery across the four programme indicators set out in the logframe, Annual Comprehensive Plan (ACP), and procurement plans. Despite procurement delays, medicines, medical supplies, and equipment worth ETB 17.8 billion were distributed to health institutions during the six-month reporting period, demonstrating strong throughput and operational efficiency.

For the financing arrangement (FA) components, MCV1 and MCV2, pentavalent vaccination, and full immunisation achieved 100% coverage as per admin data, in line with FY 2025/26 targets. The cost per facility‑based delivery, managed through EPSA supply systems, remains efficient, contributing to a national essential medicines availability average of 82.1%.

During the six‑month reporting period, medicines, medical supplies, and equipment valued at ETB 17.8 billion were distributed to health institutions, demonstrating strong throughput and operational efficiency in the national supply chain.

Under the TA component, the Young Lives Project efficiently delivered Qualitative Round 6 longitudinal research, policy briefs, and ten policy‑relevant studies. These outputs supported improved complementarities across health sector and generating efficiency gains across the programme.

Effectiveness: Effectiveness is assessed by the extent to which RMNCH programme activities and outputs contribute to intended outcomes. During the review period, the programme contributed to improved RMNCH outcomes, reflected in national data: maternal mortality reduced to 169 per 100,000 live births (from 402 per 100,000 in EDHS 2016); under‑five mortality reduced to 51 per 1,000 live births; infant mortality to 39 per 1,000; and neonatal mortality to 25 per 1,000, compared with EDHS 2016 figures of 69, 48, and 29 respectively.

As the programme is in its third year of implementation, output‑level results are contributing to the higher‑level outcome of “reduced maternal, newborn and child mortality through a more resilient health system.” Evidence from EDHS data and SDG‑PF administrative reports confirms that the programme is delivering against its intended outcomes within the review period.

Quarterly performance reports from TAMU further confirm that the TA component delivered high effectiveness, driven by comprehensive institutional strengthening and operational efficiency improvements across federal, regional, and agency levels. The systems‑focused strategic support strengthened institutional capacity to implement the nine strategic objectives of the Health Sector Development and Investment Plan (HSDIP), particularly in supply chain systems. While these results reflect cumulative programme efforts rather than only the current review period, they have made a substantial contribution towards annual targets and overall programme outcomes.

Equity: The programme carries a primary gender marker, with an explicit focus on improving the health and survival of women and children in Ethiopia. A significant proportion of EPD‑E funding directly targets gender‑related outcomes.

The programme also prioritises regional equity, aiming to narrow gaps between lower‑performing regions and the national average. In Q2 FY 2025/26, approximately ETB 1.35 billion (60% of the quarterly budget) was allocated to underserved regions, including Afar, Amhara, Tigray, and three newly established regions.

This targeting responds to persistent regional disparities highlighted by EDHS data, including wide gaps in modern contraceptive use, ANC 1 and ANC 4 coverage, iron supplementation, and skilled birth attendance. While these disparities remain—particularly in Somali and Afar regions—the allocation demonstrates a deliberate and positive step toward reducing inequity in RMNCH outcomes.
Assessment of Continuing Value for Money
Overall, the programme continues to represent good value for money. Output performance during the reporting period shows progress broadly in line with programme expectations and delivery milestones. By targeting RMNCAH and system strengthening, the programme is generating measurable improvements in maternal and child health outcomes nationwide. Although regional inequities persist, current achievements indicate positive trajectories and reinforce the programme’s strategic contribution to health system improvement in Ethiopia.

E: RISK

Overview of risk management

The overall risk rating for the EPD‑E programme remains Moderate. The programme maintains a comprehensive and actively managed risk register on AMP, which is updated monthly and reviewed quarterly by the Programme Team and Programme Responsible Owner (PRO) to ensure effective monitoring and mitigation. The risk register was reviewed with Technical Assistance (TA) partners (UNOPS and Young Lives Project) to ensure shared understanding of key delivery risks. Quarterly risk discussions are held with the Senior Responsible Owner (SRO) to review emerging risks and agree mitigation actions. Where appropriate, risks are escalated to the Human Capital Development (HCD) team risk register and subsequently to the Embassy Delivery Committee. The programme’s risk appetite is aligned with the Embassy-wide risk appetite. The programme’s risk appetite is assessed as Receptive for Strategy and External Context, Policy and Programme Delivery, Safeguarding, Financial and Fiduciary Risk. The appetite is Cautious for People, Public Service Delivery and Operations and Reputation. Overall, the programme’s risk profile and appetite remain consistent with office‑level expectations.
Key Risk Areas and Mitigation

Programme Delivery
The SDG‑PF EFY 2018/19 Quarter 2 report identified risks related to delayed implementation of procurement activities for medicines, medical supplies, and equipment, with ETB 3.9 billion (13%) recorded as actual expenditure against the allocation. Contributing factors included delays in fund disbursement by some development partners, rising pharmaceutical input prices, limited domestic manufacturing capacity, foreign exchange shortages, delivery delays, security challenges, disease outbreaks, and natural and man‑made emergencies disrupting service delivery. Inefficiencies in regional fund utilisation also resulted in accumulated unspent balances.

To mitigate these risks, the MoH implemented measures including reducing procurement lead times, strengthening follow‑up and decision‑making processes, and enhancing coordination through monthly JCCC and SDG‑PF donor meetings, which provide close oversight and support implementation acceleration. Moreover, the MoH has implemented the channel two Financial Administrative Directive 979/2024 and MoU signed between the Minister and Regional Health Bureau.

At TA level, UNOPS and the Young Lives Project undertook regular risk monitoring and maintained updated risk registers through January 2026. Quarterly risk review meetings were held with the FCDO programme team, with key risks feeding into the HCD team risk register. UNOPS has also developed a resource mobilisation plan and is actively engaging donors to mitigate funding risks.
Strategy and External Context
Ongoing conflict in Amhara region and parts of Oromia continues to restrict access to basic health services, delay implementation of programme components, and damage health infrastructure. Especially in the latter half of the review period, these issues were amplified by exacerbated by the Gulf war and uncertainty of upcoming elections. To manage this, FCDO works closely with the MoH, World Bank, and other development partners to track political and security developments and identify adaptive actions. The programme team maintains close coordination across Embassy teams and participates in regular SDG‑PF meetings, biannual joint missions, and quarterly development partner discussions.
Financial and Fiduciary
The two main financial and fiduciary risks identified are recurring outstanding and unsettled advances, and procurement delays. Financial and fiduciary risks are closely managed through quarterly financial and audit report reviews, annual audits, and regular JFA group meetings. Monthly review meetings involving all contributing donors are used to assess financial performance, identify emerging issues, and agree corrective actions. The programme team also follows up on Financial Risk Assessment (FRA) and audit recommendations, including those from previous years.

The MoH has strengthened oversight by establishing an Audit Oversight Committee, supported by FCDO‑funded TA, to review internal and external audit findings and monitor implementation of mitigation measures. Following FRA recommendations on aged advances and underspending, the MoH introduced the Channel Two Finance Administration for the Health Sector Directive (No. 979/2024), signed an MoU with Regional Health Bureau (RHB) heads, and strengthened budget execution controls.

Next steps include continued joint engagement by FCDO and donors through the SDG‑PF to improve budget utilisation, ensure timely approval of the Annual Comprehensive Plan (ACP), monitor implementation of the financial directive and MoU, and closely track procurement planning and execution, which accounts for over 90% of ACP value.
Safeguarding
In line with FCDO zero‑tolerance policies on SEAH and Counter‑Fraud and Anti‑Corruption (CAD), both compliance requirements were incorporated into the Joint Financing Agreement (JFA) and are being reinforced in the revised agreement. The FCDO team routinely reviews quarterly performance reports to identify any safeguarding concerns and ensure robust monitoring and reporting.

Gender‑based violence was identified as a potential risk in the Delivery Due Diligence Assessments (DDAs) for both TA partners. UNOPS provided mandatory SEAH awareness and training to staff. The Young Lives Project, while not currently a member of the Misconduct Disclosure Scheme, complies with its internal whistleblowing policy and that of the University of Oxford. Additional mitigation actions include regular DDA follow‑up, quarterly risk discussions, and delivery‑chain risk mapping with both TA partners.
People
People risks have increased due to high staff turnover within the programme, with key posts such as Social Development Advisor and most recently the Bilateral Health Advisor currently vacant. This combined with the recent ODA reductions is impacting staff morale. To mitigate this risk, the team will prioritize Learning and Development, including cross-office skill development, and will continue to promote diversity, inclusion and respect. In addition, a G6 Health Advisor has been recruited to provide essential technical support to the team.
Partnership Principles
The Partnership Principles Assessment (PPA) for January–December 2025 indicates a mixed level of Government of Ethiopia (GoE) commitment to poverty reduction and the SDGs. Challenges remain regarding human rights, civic space, and governance, including ongoing conflict and constraints on domestic accountability. Financial management and accountability continue to present risks, although improvements in public financial management were noted during the year. In response, FCDO has introduced portfolio‑level mitigation measures, including human rights and peacebuilding programming, conflict and instability monitoring, third‑party monitoring, and strengthened safeguarding arrangements.
Issues Management

An issues log has been integrated into the programme risk register and feeds into the team‑level and portfolio issue registers. This approach ensures systematic tracking, timely escalation, and resolution of delivery‑critical issues.
Annual Statement of Progress (financial aid programmes only)

Current level of fiduciary risk and direction of travel since last ASP	Moderate Improving
Specific assessment of corruption risk and direction of travel since last ASP	Major worsening
Is a full FRA update required?	No

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Financial Performance
During EFY 2018/19, the SDG‑PF secured ETB 17.8 billion (USD 131.7 million) in new budget allocations, in addition to ETB 11.39 billion in carried‑forward funds, bringing the total available budget to ETB 29.28 billion. During the reporting period, SDG‑PF partners disbursed USD 38.8 million against a total commitment of USD 131.7 million.

In line with the EFY 2018 Annual Comprehensive Plan (ACP), the UK transferred £13.36 million to the Ministry of Health (MoH), with disbursement linked to the fulfilment of agreed triggers in the MoU. Overall resource allocation under the ACP remained strongly aligned with national health priorities, with approximately 46% allocated to RMNCH‑N, 14% to health insurance, 12% to primary health care, and the remainder supporting health system strengthening, disease control, and digital health investments.

FCDO’s financial assistance and disbursements to SDG‑PF are governed by the MoU with MoH and are implemented in accordance with the approved ACP. Financial performance is monitored through quarterly financial reports and annual external audits. While the 2025 audit experienced delays, interim controls and reporting mechanisms continued to provide assurance on the use of funds.

Technical Assistance Financial Performance
Through the Technical Assistance (TA) component of the EPD‑E Programme, the UNOPS‑implemented TAMU project demonstrated strong financial and programme management performance in strengthening MoH’s capacity to implement the Health Sector Development and Investment Plan (HSDIP) across nine strategic priority areas.

During the reporting period, FCDO disbursed £10,000 in TA funding, alongside contributions from Italy and the Gates Foundation. According to the TAMU financial progress report, from a total project budget of USD 5,806,737, expenditure as of January 2026 reached USD 4,257,215, with USD 1,550,493 committed through to end‑October, resulting in 100% budget utilisation.

Under the research TA component, FCDO disbursed £210,284 to the Young Lives Project to support phase 2 of the Qualitative Round 6 research and the Hawassa International Research Conference. The project successfully delivered the conference and produced the planned Qual 6 research outputs, in line with the approved budget and grant agreement.

Summary of EPD‑E Budget Utilisation and Programme Management
Since programme inception, three agreements have governed the implementation of the EPD‑E Programme an MoU between FCDO and MoH, signed in May 2023 and amended in the last two consecutive years. An MoU between FCDO and UNOPS for the TA component, signed in August 2024 and amended three times, most recently amended in January 2026. An Accountable Grant Agreement with the Young Lives Project, signed in November 2024 and second amended in December 2025.

The overall financial performance showed relative improvement in public financial management compared to the last annual review period.
Q performance and financial reports ending Dec 2025	March 2025
Date of last audited annual statement ending 7 July 2024	Not yet released
TAMU quarter report ending Dec 2025	Feb 2026

G: MONITORING, EVIDENCE AND LEARNING

A comprehensive joint monitoring and performance management system is in place for the EPD‑E programme through the SDG‑PF framework. Monitoring arrangements include Joint Review Missions (JRMs), Annual Review Meetings (ARMs), Mid‑Term Reviews (MTRs), and systematic review of quarterly performance and financial reports produced by the Ministry of Health (MoH). These are complemented by annual external audits and fiduciary risk assessments.

Performance oversight is strengthened through monthly SDG￼PF donor group meetings, which review programme progress, fiduciary performance, procurement implementation, and safeguarding risks. These meetings formally review and clear MoH quarterly reports, audit findings and follow￼up actions, and procurement plans, providing regular assurance and corrective action where required. The team also engage in regular independent M&E through field visits. During the review period, the team undertook monitoring visits to Somali region.

For this Annual Review, quantitative data were drawn from MoH administrative reports, SDG‑PF quarterly performance reports, and the Ethiopia Demographic and Health Survey (EDHS) 2024/25 RMNCAH indicators. Qualitative evidence was collected through field visits to Somali Regional State, purposively selected due to its pastoralist context and persistent service delivery challenges.

The review team conducted key informant interviews and focus group discussions with Regional Health Bureau leadership and technical staff, focusing on programme implementation, supply chain functionality (including the regional EPSS hub), quality and equity of RMNCH‑N services, financial management, gender inclusion, and safeguarding in the Somali region.
Governance and Reporting
The SDG‑PF operates under a Joint Financial Agreement (JFA) signed by all development partners, committing to one plan, one budget, and one report, and using Government of Ethiopia systems. The JFA provides a clear framework for monitoring and evaluation, including clearance of the Annual Comprehensive Plan (ACP), quarterly reports, audit reports and follow‑up actions, and procurement plans.

Strategic oversight is provided by the Joint Consultative Forum (JCF), chaired by the Minister of Health, with representation from government, development partners, NGOs, and professional associations. The Joint Core Coordinating Committee (JCCC) acts as the technical arm of the JCF and met during the reporting period to review progress and approve key programme decisions, including ACP approval and audit follow‑up—preconditions for FCDO disbursement.

During the review period, the MoH submitted four quarterly narrative and financial reports, which were reviewed individually by development partners and jointly through SDG‑PF meetings. Consolidated feedback was formally communicated to MoH through the SDG‑PF Chair. Joint Review Missions were also conducted in line with the agreed monitoring framework.
Monitoring of Technical Assistance
TA partners UNOPS (TAMU) and Young Lives Project submitted quarterly performance reports throughout the period. TAMU successfully completed recruitment of 32 technical advisors and project staff across MoH, regional bureaus, and affiliated agencies (including EPSS), establishment of a planning, monitoring, and reporting system, supported by a central database; and development of an automated dashboard enabling real‑time tracking of TA inputs and progress against the nine HSDIP strategic objectives. The transition of TAMU to the Institute of Primary Health Care (IPHC) was initiated, alongside completion of a technical Mid‑Term Review, confirming progress against planned deliverables. The Young Lives Project finalised Qualitative Round 6 (Qual 6) research outputs and delivered an international research conference in Hawassa.

UNOPS performance is also monitored through quarterly Board Meetings and Technical Working Group meetings, which review progress, address implementation challenges, and agree corrective actions.
Evidence and Learning
Generating robust evidence and embedding learning are core principles of the programme. While data reliability has historically been a challenge, the quality of MoH reporting has improved due to consistent partner feedback and capacity‑building embedded within the TA component. The key evidence outputs include: a finalised TA management dashboard and centralised database covering 5,507 TA profiles, enabling evidence‑based decision‑making and resource allocation; and completion of six waves of qualitative longitudinal research (Qual 6) under the Young Lives Project, providing complementary data to administrative sources. National outcome data from EDHS 2024/25 demonstrate sustained improvements across RMNCH indicators, reflecting the cumulative impact of long‑term SDG‑PF and FCDO support.
Learning and Adaptive Management
Learning from the TA component demonstrates that systems strengthening, clear TA governance, and harmonised planning and monitoring tools significantly improve institutional performance. During the review period, TAMU and Young Lives produced high‑quality knowledge products and learning materials, shared with MoH, FCDO, and other stakeholders.

These tools and products are now being actively used by MoH and have attracted interest from other development partners as a common platform for managing technical assistance, supporting sustainability, coordination, and adaptive programme management.