## Annual Review Template

Title: Climate and Ocean Adaptation and Sustainable Transition (COAST) Programme
Programme Value £ 154m		Review date: 20 July 2025
Programme Code : 301203	AMP start date: 20 July 2023	AMP end date: 31 March 2030

Summary of Programme Performance
Year	2023/24	2024/25
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003167.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005171.xlsx

 A. SUMMARY AND OVERVIEW [1-1 ½ pages]

Description of programme [1-2 paragraphs]
The £154 million Climate & Ocean Adaptation Sustainable Transition (COAST) programme aims to improve the adaptive capacities, climate resilience and prosperity of vulnerable coastal communities, and drive a more sustainable and inclusive management of their marine and coastal resources. To deliver this, COAST is focused on core themes: (i) protecting, restoring, and sustainably managing coastal habitats (e.g., mangroves, seagrass, corals), (ii) improving small scale fisheries’ sustainability, productivity, and resilience, (iii) catalysing more sustainable, less intensive aquaculture, and (iv) supporting inclusive coastal planning and management.
 COAST will be delivered in up to 6 priority countries across two delivery phases. Phase 1 will include Indonesia, the Philippines, Vietnam, and Mozambique. Phase 2 may include the expansion to an additional two countries depending on the outcome of a further scoping process and future Government spending reviews.  The programme adopts a multi-component structure. As set out in the business case, COAST’s design aims to achieve its outcomes through: (i) adopting an evidence-based approach, (ii) taking an integrated approach across COAST’s themes and avoiding siloed delivery, and (iii) targeting robust results at scale.
This multi-component approach allows COAST to build early evidence within thematic areas with mixed underpinning evidence of successful approaches (e.g. small-scale fisheries, sustainable aquaculture) and to advance policy development in key areas (e.g. blue carbon policy) to maximise opportunities for COAST funded projects at the community level to attract further investment to scale. Alongside this, COAST will adapt its delivery in response to programme-generated lessons and evidence, with mechanisms in-built to support this. COAST’s four components are outlined below:
- Component A (up to £101.1m) – Component A’s delivery partner was procured through a competitive process and won by DAI Global. The contract was signed in November 2024, with mobilisation kicking off in December 2024. Component A, now named the COAST Facility, is focussed within COAST’s priority countries (Indonesia, the Philippines, Vietnam, Mozambique and with an optional additional two countries) and will provide technical assistance and capacity building to support regulatory strengthening and grants for local level projects across COAST’s themes to build a pipeline for investment that allow COAST support to achieve scale. The COAST Facility also includes a responsive element for UK Embassies and High Commissions (collectively referred to as posts) to request support for strategic projects in their host countries aligned to COAST’s aim and themes.
- Component B (up to £44.5m) – Component B is delivered through WorldFish’s Asia-Africa Blue-Tech Superhighway (AABS) project. Recognising that there is mixed overall evidence for successful interventions under the small-scale fisheries and sustainable aquaculture themes, Component B’s role is to test and scale technologies, tools and approaches that aim to improve small scale fisheries and aquacultures climate resilience, productivity, inclusivity, and sustainability. AABS operates in several countries in Africa and Asia within and outside of COAST’s priority countries (including Kenya, Tanzania, Mozambique, Nigeria, and Bangladesh) to support wider evidence generation and learning. The AABS projects has four work packages,
  - Digital information systems for effective management of small-scale fisheries - in Kenya, Tanzania, Mozambique.
  - Integrated multi-trophic aquaculture (IMTA)- in Bangladesh, Nigeria & Kenya.
  - Innovative, climate smart food processing and storage technologies to reduce food loss and waste - in Kenya, Tanzania & Mozambique.
  - Incentives for coastal and marine conservation and fisheries management - Bangladesh, Tanzania & Mozambique.
- Component C (up to £4m) – Component C is delivered through the World Economic Forum’s (WEF’s) Blue Carbon Action Partnership (BCAP) project (April 2023- March 2026). BCAP convenes national governments and other in-country stakeholders in Vietnam, the Philippines and Indonesia to support national planning and policy making processes to support ‘blue carbon’ (i.e. mangroves, seagrasses, saltmarshes) habitat protection, sustainable management, and restoration. BCAP processes will help to develop national blue carbon roadmaps owned by national governments that outline countries’ blue carbon habitat priorities, providing greater clarity on standards and approaches to be used to ensure robustness of approaches, and opportunities for mobilising finance and investment (e.g. through the voluntary carbon market and private sector). BCAP convenes global partners to support the integrity of finance, science and standards for blue carbon to be connected to these national processes. There is potential to scale projects identified for investment through the national roadmap development process via Component A as part of COAST’s integrated delivery model.
- Component D (up to £4.4m) – Component D is COAST’s independent monitoring, evaluation and learning (MEL) component delivered by Itad following a competitive selection process. Itad will provide programme level results reporting and monitoring support, undertake evaluations of COAST’s performance, and establish and facilitate COAST’s lessons capturing and learning approach. Itad will also support COAST’s cross-component engagement through organising partner coordination forums, and COAST’s engagement with other HMG programmes and external stakeholders.

Summary supporting narrative for the overall score in this review [1-2 paragraphs]
This Annual Review covers COAST’s second year of delivery. In Year 1, performance was measured against logframe Output 7 only, which covered the mobilisation of Components B, C and D. Year 2 has been assessed against logframe Output’s 1-7, which covered delivery of the AABS and BCAP Projects (Outputs 1-6) and the mobilisation of the COAST Facility (Output 7). Across Outputs 1-6, Worldfish and WEF have successfully mobilised the AABS and BCAP projects in Year 2 respectively, mobilising new country teams, engaging and influencing a diverse set of stakeholders, including national and local government, community groups and private sector, and developing policies and generating evidence, delivering 14 separate interventions under the COAST programme. Under Output 7, FCDO successfully procured and mobilised Component A of the COAST Programme. Which despite some early delays due to the UK General Election in June 2024, is on track to deliver in Year 3.
Delivery in Year 2 however has not been without challenges and delays. Political transitions in the Philippines, Mozambique and Indonesia during Year 2 delayed project delivery, finalising financial roadmaps and influencing national policy in Indonesia and the Philippines (Outcomes 2 & 4, Outputs 4 & 6). Moreover, the deliberately staggered mobilisation of projects under COAST resulted in discrepancies between logframes, workplans, individual project targets and COAST programme milestones, meaning project logframes and the overall COAST logframe were often misaligned, creating discrepancies in expected milestones and achievements (Output 2). It also meant the COAST approach to gender equality, disability and social inclusion (GEDSI) was introduced late in Year 2, creating further discrepancies between expectations around GEDSI ambition and partner delivery for Year 2 (Outcome Indicator 1b).
Early issues however are inevitable when mobilising a complex multicomponent, multicounty programme, and many of these challenges have been or are being addressed. The next logframe review is already planned to take place in August 2025. This will be an opportunity to address many of the recommendations outlined below. Overall, therefore, the programme has scored an A at annual review, broadly meeting expectations in Year 2. COAST’s Year 2 output performance is summarised below with more detail in Section C:

Output	Summary Narrative
1.Coastal stakeholders are actively engaged in projects supporting the sustainable use, protection, management and restoration of marine environments​;	AABS and BCAP have mobilised 14 interventions collectively (e.g. NBCAP establishment, freezer pilot programmes, training workshops), establishing partnerships with key stakeholders, and with beneficiaries reporting meaningful participation in COAST interventions.	A
2. Stakeholders’ skills and capacity to sustainably use, protect, restore and manage the marine environment;	Training was not set out in the AABS milestones for this year, however AABS have delivered freezers and training to 136 participants. Skills and knowledge gained has improved although sample numbers were small.	A+
3. Evidence-based recommendations, guidance or tools are provided for project planning/adaptation, policies, plans and governance frameworks;	Together, AABS and BCAP delivered 23 reports based on the information, knowledge and recommendations generated by the projects, more than was initially planned. All outputs involved the consultation of key stakeholders; however ‘meaningful participation’ should be improved.	A
4. Appropriate and strengthened governance structures are in place;	COAST is working across a large number of governance structures. However, evidence is lacking for how COAST has strengthened these governance structures and no new plans, policies or regulatory frameworks under AABS and BCAP were approved by host Governments.	B
5. Networks, partnerships and peer-peer learning are established, supporting knowledge exchange and financial flows;	COAST has delivered a number of peer-peer learning exchanges, particularly for knowledge sharing between countries through national fisher fora. Several partnerships and taskforces have also been established to provide ongoing technical guidance to the governance groups established. Improvements needed on engaging and measuring marginalised groups participation in these events.	A
6. Financial roadmaps and pipelines of viable projects are established;	Only the BCAP project reported against this output. WEF has made considerable progress towards developing financial roadmaps but did not achieve final Government approval. Significant progress has been made towards engaging with financial institutions and potential funders.	B
7. Effective mobilization of COAST (Component A);	Despite an initial 2–3-month delay in signing the contract due to the UK General Election, Component A was successfully mobilized in Year 2 and is on track to deliver in Year 3.	A

Major lessons and recommendations for the year ahead

A summary of the year 1 annual review recommendations and actions taken in year 2 is contained in Annex A. For year 3, major lessons and recommendations include:

Lesson & Recommendation 1: The staggered mobilisation of COAST components B, C and D led to misalignment between project workplans and logframes, and the overall COAST programme logframe. In Year 3, Itad will undertake a logframe refresh in consultation with partners to ensure all project workplans and logframes accurately feed into the COAST logframe and to improve the consistency of partner target setting and reporting. Working with Itad, FCDO to ensure all partners understand reporting expectations and to hold partners accountable for improving the consistency in target setting and meeting targets.
Lesson & Recommendation 2: COAST underachieved against its GEDSI ambition in Year 2. In part this was because the COAST GEDSI Ambition Statement was not introduced until halfway through Year 2, however this was also due to a lack of partner understanding around COAST GEDSI expectations. Itad will work with partners to ensure clarity around GEDSI indicators, and partners will undertake reviews of their own M&E systems and project workplans to ensure alignment. FCDO will implement quarterly monitoring of GEDSI performance to strengthen programme wide accountability.
Lesson & Recommendation 3: Partners experienced challenges reporting against logframe and VfM indicators, which were not finalised until late in Year 2. Moreover, binary success/failure logframe targets did not always capture the breadth and nuance of delivery, particularly policy development and stakeholder engagement. Itad will work with delivery partners in Year 3 to finalise indicator reference sheets and to clarify definitions (e.g. Direct Beneficiaries, ICF KPIs) to strengthen evidence collection and reporting. Itad will also revise and refine output indicators to ensure progress made towards policy development and stakeholder influencing is captured, e.g using tiered milestone systems to measure policy development – e.g. initiation, draft, consultation, finalisation.
Lesson & Recommendation 4: Stakeholder engagement was a strength of the COAST programme in Year 2. However partners lacked suitable systems to track or verify the participation of marginalised groups. To address this, Itad and partners should refine metrics for participation that are contextually appropriate and develop and apply consistent methods for tracking the participation of marginalised groups, including disaggregated data collection and participant self-identification where appropriate.
Lesson & Recommendation 5: Political transitions in Indonesia, the Philippines and Mozambique caused delays and impacted COAST delivery in Year 2. FCDO to work with partners to ensure political economy analysis and risk mitigation strategies are in place for identifying and managing political risk and build flexibility into delivery. FCDO to encourage partners to engage closely with Post and BPF Regional Coordinators to help delivery in the face of contextual challenges. Partners to share lessons learned from delivery and capitalise on the fact that DAI now have an in-country presence in all COAST priority countries.
Lesson & Recommendation 6: The COAST Year 1 annual review recommended that FCDO prioritise securing host government approvals for Component A to operate in each COAST priority country during the Mobilisation phase (see annex B). In year 2, FCDO and DAI prioritised working collaboratively with host governments and other national stakeholders in the co-design and approval of COAST Facility Country Plans and Workplans. Following the completion of the co-design process in June 2025, FCDO will seek formal government approval of Country Plans and agree ongoing coordination mechanisms to ensure Host Governments remain engaged in COAST delivery. We will continue engaging closely with host Government and other national and sub-national stakeholders in the ongoing delivery of the Coast Facility in year 3.
Lesson & Recommendation 7. Partners were not being proactive in providing updated forecasts to FCDO which in some cases left little time to take corrective action on unspent budgets. FCDO to ensure that partners submit monthly updated forecasts. FCDO to hold quarterly meetings with partners to lock down each quarter forecast to minimise large variances between forecast vs actuals.
Lesson & Recommendation 8: Lack of engagement between COAST delivery partners and Posts led to slower engagement with government institutions and a less robust understanding of in-country landscapes, demonstrated by WorldFish’s delayed mobilisation in Mozambique. Continued lack of engagement could result in missed synergies and a lack of bilateral support for the programme. FCDO to work with partners to ensure regular post engagement is embedded in their delivery approach.
Lesson & Recommendation 9: COAST is a complex multicomponent programme, operating in a new area for FCDO (i.e coastal resilience, small scale fisheries and sustainable aquaculture), and with a relatively underdeveloped international evidence base. The original business case set out the key contextual, delivery, evidential and financial assumptions, which informed the design of the programme’s theory of change and subsequent theory of delivery. Now that all components are fully mobilised, FCDO should test the programmes underlying assumptions to ensure they still hold, and the programme ToC and ToD remain relevant as we move into Year 3 of delivery.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES [1-2 pages]

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case. [1/2 page]

COAST’s Theory of Chance (ToC) recognises a set of key challenges hindering coastal communities’ and nature’s effective climate adaptation and sustainable coastal management. These include:
- The loss and degradation of coastal habitats, their biodiversity and associated ecosystem services (e.g. supporting local fish stocks and biodiversity through providing nursery areas, coastal protection, etc.) due to a combination of unsustainable or over-use of resources, poor governance and planning, and other drivers.
- Weak governance and management rights for coastal habitats and ecosystems alongside marginalisation of coastal communities from decision making, particularly women.
- Reliance on precarious, unsustainable and/or harmful livelihood practices by coastal communities (e.g. small-scale fishing or practices leading to habitat destruction).
- A lack of accessible finance for coastal communities and projects.
- Exacerbation of these of challenges and drivers due to climate change’s impacts in coastal areas (e.g. more frequent and/or intense storms, sea level rise, ocean acidification).
Collectively these challenges impact developing country coastal communities’ livelihoods (small scale fisheries, aquaculture farmers, etc.), food security and nutrition, and vulnerability and exposure to coastal hazards and the impacts of climate change.
In response to these challenges and based on available evidence, the ToC focuses on the following themes:
1. Protecting, restoring, and sustainably managing coastal habitats (e.g., mangroves, seagrass, corals).
2. Improving small scale fisheries’ sustainability, productivity, and resilience.
3. Catalysing more sustainable, less intensive aquaculture.
4. Supporting inclusive coastal planning and management.
The structure of COAST’s ToC is complex and multi-tiered. An original ToC developed during the business case was updated post-business case approval in March 2023. Between January and mid-April 2024, a further update to COAST’s ToC was undertaken by Itad as part of their mobilisation phase and the production of COAST’s MEL strategy. This process involved significant consultation and workshops with FCDO, WorldFish and WEF with additional reviews by Itad’s expert advisory panel. A gender equality and social inclusion (GESI) review was conducted to ensure GESI is fully embedded into COAST’s approach. This supported COAST’s efforts to respond to ICAI’s findings and recommendations for the Blue Planet Fund programme portfolio. The most up to date COAST ToC, approved by the COAST SRO in mid-April 2024, is presented in Annex B.
In year 2, FCDO, with Itad’s support, updated the COAST logframe to meet the ToC ambition. In April 2024, the COAST logframe was shared with partners to map component-level logframe indicators to the overall programme level indicators. In September 2024, Partners finalised their milestones for each COAST logframe output and intermediate outcomes, before a final updated logframe was approved by FCDO in November 2024 (including new Outputs 1-6 in this review, plus Output 7 from the original logframe).
The ToC and logframe will now be reviewed and updated on an annual basis following the annual review to embed lessons from COAST’s delivery, results achieved, and emerging evidence from within and beyond COAST. The next review will take place in July 2025 and will include COAST Facility contributions in the reviewed Year 3 logframe, which has been in mobilisation phase from December 2024 to June 2025 (see Output 7).
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead? [1/2 page]
At this early stage in the programme cycle, COAST aimed to contribute to the intermediate outcome; Improved enabling environment leads to the adoption and implementation of sustainable, socially inclusive and adaptive management practices and technologies from local to national level.
Overall, progress across the intermediate outcome during Year 2 was varied. The COAST programme included 14 distinct interventions targeted at supporting the adoption of technologies and approaches for national governments and coastal communities to sustainably use, protect, manage and restore marine environments. 12 of these interventions were implemented by Worldfish under AABS (in Bangladesh, Nigeria, Kenya, Tanzania and Mozambique), and 2 are with the WEF under BCAP (in Indonesia and Philippines). At the end of Year 2, 60% (8) of these interventions were considered on-track (compared to a target of 80%), with a further 20% (3) experiencing minor delays but with corrective plans in place, and only 20% (3) facing significant delays (Intermediate Outcome Indicator 1a). Whilst moderately not meeting expectations, challenges during the first year of implementation are not uncommon and FCDO has been working closely with Worldfish and WEF to understand the issues, learn from Year 2 implementation and adapt for Year 3 (see lessons learned and recommendations).
For the 12 projects under the AABS project specifically, Year 2 saw Worldfish began implementation across AABS four work packages. Where Worldfish had pre-established interventions, for example, work package 1, delivery across Year 2 was largely on track. However, when establishing new work packages, Worldfish initially experienced delays mobilising the projects (e.g Work packages 3 and 4). In part this was due to contextual challenges, for example government shutdown pre-elections and then post-election violence in January 2025 paused implementation in Mozambique. However, challenges around mobilising AABS teams in numerous countries and coordinating delivery across all work packages concurrently delayed progress. Moreover, whilst Worldfish has been engaging with 25 different government plans, policies, processes that benefit coastal nature and communities across all countries, none reached the “approved” stage in Year 2, which relies on final national Government approval. Despite these delays, the initial implementation, the relationships built across national stakeholders and progress across all work packages means FCDO are confident Worldfish and AABS is on track to contributing to the expected outcomes and impact in Year 3.
Under the BCAP project, year 2 saw the WEF successfully establish the National BCAP (NBCAP) governance structures in Philippines and Indonesia, convening national government and completing the stakeholder engagement to develop national blue carbon roadmaps in each country respectively (Intermediate Outcome Indicator 3). The completion of these roads maps is crucial for supporting national planning and policy for ‘blue carbon’ habitat protection, sustainable management, and restoration projects, and linking national priorities with investors interested in Blue Carbon. Changes in government and the lead ministry for domestic blue carbon markets in Indonesia and the Philippines respectively however delayed the final agreement and approval of National Blue Carbon Road Maps in each country which was due to take place in Year 2 (Outcome Indicator 2). This in turn impacted the opportunity to leverage blue finance in each country over the reporting period (Intermediate Indicator 4). Despite these delays however, progress of BCAP project has been strong, with Roadmaps expected to be publish Quarter 2 (Q2) of Year 3, with efforts now focusing on mobilising investment in blue carbon ecosystems through them.
On GEDSI, COAST performance was more disappointing (intermediate outcome indicator 1b). COAST’s GEDSI responsiveness is an important component of delivering against COAST Outcome 3; increasing effective and equitable representation and participation of stakeholders in coastal resource management. To help deliver this, in September 2024 Itad developed the COAST GEDSI Ambition Approach, which outlined expectations of partners to deliver GEDSI in project activities. Overall, COAST is designed and commits to being a GEDSI responsive programme with a focus on empowerment by building assets, capabilities and opportunities for women and marginalised groups. It aspires to be GEDSI transformative wherever possible. While partners have subsequently started to implement changes to their programming to align with the new ambition statement, only a small proportion of interventions met COAST’s intended level of ambition during the reporting period.
This was in large part due to the introduction of the ambition statement halfway through implementation. For example, under AABS many downstream partners work plans were established prior to the GEDSI guidance from Itad being available. Since then however, AABS in particular has developed specific strategic GEDSI guidance to ensure all teams and partners understand and apply GEDSI principles; Capacity Strengthening and reviews to embed GEDSI considerations across planning, resourcing, implementation, and monitoring and improved monitoring and learning to better capture GEDSI outcomes and ensure mechanisms are in place to promote transformative participation of marginalized groups. With these changes, we anticipate in Year 3 COAST will see a much-improved score with clearer actions and priorities to achieve GEDSI-sensitive scores in Components A, B and C. Annex C highlights the activities undertaken on GEDSI under COAST in Year 2.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
Creating improved enabling environments at local and national levels, which lead to the adoption and implementation of sustainable, socially inclusive and adaptive management practices and technologies takes time to cultivate and deliver. At this relatively early stage in the programme, despite some challenging political contexts in Mozambique, Indonesia and Philippines, AABS and BCAP projects have mobilised important interventions for longer term policy and institutional capacity building work, e.g the BCAP national plans, that are essential to delivering results in future. Based on this, and the programmes achievements across outputs 1-7, we asses the programme should continue into Year 3 of implementation.
Whilst early issues are inevitable when mobilising a complex multicomponent, multicounty programme. There were several initial design assumptions that have been challenged over the year. For example, that political contexts remain conducive to COAST programme delivery, that COAST themes remain priorities amongst public sector policy makers, and that the staggered mobilisation of the programme creates opportunities for learning between components, rather than challenges in coordination. Whilst these design assumptions have ultimately held across the year, they have at times proven challenging and suggest FCDO should more closely monitor the programmes underlying assumptions to ensure they still hold, and the programme ToC and ToD remain relevant as we move into Year 3 of delivery. Principally whether:
Finally, the COAST programme remains an important component of the FCDO’s climate and nature portfolio, and the only FCDO programme supporting Coastal resilience and adaptation. It is part of HMG’s wider marine environment portfolio under the Blue Planet Fund and has become important parts of the UK’s bilateral relationship on marine issues with Mozambique, Indonesia, Philippines and Indonesia, supporting the governments broader policy agenda on food security, growth and development. In the context of the wider portfolio and given the reviews overall score, we recommend the COAST programme should continue into Year 3 of implementation.

## C. DETAILED OUTPUT SCORING

Output Title	Coastal stakeholders, specifically the most vulnerable, are actively engaged in projects supporting the sustainable use, protection, management and restoration of marine environments
Output number:		1	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	no

No	Description	Milestone	Progress
1.1	Number of projects that are a) new b) live/ongoing c) completed d) planned to scale	1.1a) 12 / 1.1b) 2	Expectations Met: achieved a. 14; b. 0 / All 12 AABS projects are underway. Both NCAP projects (2) started in Indonesia and the Philippines.
1.2	Number of people participating in projects that support the sustainable use, protection, management or restoration of the marine environment (ICF KPI1)	15	Expectations Exceeded: achieved 181 / AABS engaged with 136 direct beneficiaries. BCAP engaged with 45 direct beneficiaries.
1.3	% of participants reporting meaningful engagement and participation in COAST projects	80%	Expectations Exceeded: 92% 12 respondents reported meaningful participation in the AABS project.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this Output Scored an A. This output measures how coastal stakeholders, specifically the most vulnerable, are actively engaged in projects through the AABS (Component B) and BCAP (Component C) projects.
Indicator 1.1: Expectations Met: All 12 of the planned AABS projects mobilised across Kenya, Tanzania, Mozambique, Bangladesh and Nigeria. AABS transitioned from scoping and baselining assessments to active implementation and identifying scalable innovations across all work packages. AABS completed Integrated Multi-Trophic Aquaculture (IMTA) scoping and baseline studies in Kenya, Nigeria and Bangladesh; installed PAY-AS-YOU-GO (PAYGO) solar freezer pilots in Kenya; and undertook participatory Theory of Change workshops in multiple countries. Digital fisheries dashboards were launched in Kenya, Zanzibar, and Mozambique, and postharvest loss reduction assessments were finalised.
The WEF established two National BCAP projects in Indonesia and the Philippines. In Indonesia BCAP supported the establishment of the NBCAP Secretariat and alignment with the new Coordinating Ministry of Food Affairs, helping to navigate the political transition while advancing technical planning. Indonesia’s blue carbon action plan moved into full development, with stakeholder workshops and a draft set for release in early FY3 at the UN Ocean Conference. In the Philippines, the NBCAP Secretariat became fully operational, hosting a national launch and a series of private sector and policy engagements, positing the NBCAP as a central actor in the country’s emerging blue carbon governance landscape. The Philippines roadmap development process is well underway, with a consultation draft ready for June.
1.2 Expectations Exceeded: Despite not originally setting a target for Year 2, WorldFish reported reaching 136 direct beneficiaries in Kenya through the installation of freezers and related training on their use to reduce fish loss and waste. The absence of a target stemmed from misaligned timelines between WorldFish project delivery and the COAST MEL component mobilisation, with uncertainty around who qualified as a direct beneficiary under the indicator. The BCAP project also exceeded original target of 15 direct beneficiaries, reaching 45 beneficiaries, however again downstream partners expressed uncertainty over measuring ‘participation’ and more work is needed to better define and more robustly measure the total number of people participating under output indicator 1.2 (see lessons and recommendations below).
1.3 Expectations Exceeded: This indicator measures the % of participants reporting meaningful engagement and participation activities linked to output indicator 1.2. Worldfish surveyed 13 beneficiaries of PAYGO freezer pilots, 12 of whom reported that there had been “meaningful participation” in the AABS project. Whilst positive, this is less than 10% of the 136 individuals targeted via the AABS food loss and waste workstream, suggesting Worldfish need to improve surveying. BCAP did not meet its milestone target as project delays linked to government changes in Indonesia and the Philippines meant participant engagement surveys could not be conducted within Year 2 and been scheduled for Year 3.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
In 2024, FCDO, with support from Itad, refreshed the COAST logframe to better align with the programme’s Theory of Change. A key milestone in this process was partners finalising their specific milestones for each logframe output and intermediate outcome by September 2024, ensuring stronger alignment and accountability across the programme. The updated logframe, incorporating Outputs 1-6 and Output 7, was approved in November 2024. Going forward, the logframe and ToC will be reviewed annually to reflect learning and emerging evidence. The next programme logframe review is scheduled for July 2025.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
- Output 1 Lesson 1: Beneficiary definitions require greater clarity: the narrow interpretation of “direct beneficiary” under ICF KPIs limited the ability to reflect the full scope of the programme’s engagement. For example, WorldFish reported over 5,000 indirect beneficiaries, yet only those under Work Package 3 qualified as direct beneficiaries. This excluded key actors such as Beach Management Unit (BMU) members and government officials who received training and participated in co-design processes critical to long-term outcomes.
- Output 1 Recommendation 1: Itad to clarify and align definitions and ensure all partners have a shared understanding of definitions in line with relevant ICF definitions. Consider expanding definitions to ensure that Year 3 reporting fairly captures partner activities.
- Output 1 Lesson 2: Logframe and Workplan Misalignment in Year 2. The deliberately staggered mobilisation of projects under COAST resulted in discrepancies between logframes, workplans, and indicator reference sheets which caused confusion in target setting and reporting. The timeline of Itad’s mobilisation meant that when MEL guidance was distributed affected the accuracy of year 2 targets, particularly for Output Indicator 1.2.
- Output 1 Recommendation 2: Update and synchronise programme wide reporting framework, including logframes, workplans and indicators. Ensure all partners are happy with the detail contained in the indicator reference sheets to improve consistency in target setting and reporting.
- Output 1 Lesson 3: Data Collection Systems need strengthening and refining: the National Blue Carbon Action Partnerships had not yet implemented a systematic tracking of disaggregated participation data, and the AABS project faced challenges in capturing meaningful engagement metrics. These gaps limited the ability to report comprehensively on participation and impact.
- Output 1 Recommendation 3: Strengthen data collection systems and support all partners to implement robust, disaggregated data collection tools for tracking participation.
- Output 1 Lesson 4: National Government changes can disrupt delivery: Government changes in BCAP countries and Mozambique delayed implementation and survey activities, resulting in missed milestones for participant engagement, e.g. Output Indicator 1.3. This highlights the need for political risk mitigation.
- Output 1 Recommendation 4: Work with partners to develop and ensure risk mitigation strategies in place for managing political risk, particularly in countries that risk undergoing political transitions.

## C. DETAILED OUTPUT SCORING

Output Title	Stakeholders’ skills and capacity to sustainably use, protect, restore and manage the marine environment and support the development of inclusive, gender sensitive, resilient and sustainable coastal economies is increased
Output number:		2	Output Score:	A+
Impact weighting (%):		15	Weighting revised since last AR?	no

No	Description	Milestone	Progress
2.1	Number of individuals trained	0	Expectations Exceeded: Achieved 136 / AABS installed 12 freezers in Kenya and trained a total of 136 community members on freezer operation and PAYGO systems.
2.2	% of individuals trained reporting increased knowledge/capacity	0%	Expectations Exceeded: Achieved 92% / 12 recipients of freezer training reported that training was relevant and constructive.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this Output scored an A+ as all output indicators exceeded expectations. This output measures stakeholders’ skills and capacity to sustainably use, protect, restore and manage the marine environment and support the development of inclusive, gender sensitive, resilient and sustainable coastal economies is increased. This output only reflects AABS activities in Year 2 because the Blue Carbon Action Partnership project was not delivering training over the reporting period.
2.1 Expectations Exceeded: This output indicator measures the number of individuals trained through COAST programme activities. WorldFish exceeded expectations in Year 2 through piloting a PAYGO partnership with Kuza Freezer to address critical cold chain gaps. 12 freezers were installed across two sites in Kenya, resulting in training for a total of 136 community members. Training focused on empowering local fisher groups with sustainable cold storage, training and a revolving fund model to ensure long-term ownership and scalability. Training was delivered on freezer use, operational training, basic maintenance, and the PAYGO system. Follow up training emphasised fish quality control, hygiene, sustainable pond management and fishing practices. During the milestone setting phase for Year 2 Worldfish initially did not believe they would be able to undertake this training this early in delivery. However, they successfully conducted two training sessions that contributed to this indicator, delivering results earlier than anticipated.
2.2. Expectations Exceeded: AABS follow up surveys resulted in 13 responses from the recipients of freezer training, and 12 of these respondents reported that the training provided them with new knowledge. Participants appreciated the solar freezers’ effectiveness in preserving fish and reported increased knowledge in post-harvest handling, value addition, and financial management. Key takeaways from the training included increased freezer operation confidence, increased record-keeping, saving practices, and increased business skills such maximising fish yield. The training also introduced techniques that helped to boost income, such as frying fish before sale, and strengthened women’s leadership in fisheries and mariculture.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Logframe refreshed during Year 2 and expected again in July 2025 (Year 3) (see explanation above under Output 1)

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
- Output 2 Lesson 1: Delivery can exceed expectations. WorldFish delivered training earlier than anticipated through the PAYGO solar freezer pilot in Kenya, demonstrating that with strong partnerships and adaptive planning, results can be achieved ahead of schedule.
- Output 2 Recommendation 1: Leverage early success for scaling. Use the successful PAYGO freezer pilot as a model for scaling similar interventions.
- Output 2 Lesson 2: Relevant training drives impact. Follow-up surveys revealed that participants found the training highly relevant, particularly in areas such as postharvest handling, value addition, and financial management. This underscores the importance of tailoring training content to local needs and livelihoods. Training not only improved technical skills but also enhanced business and leadership skills, especially amongst women, highlighting the broader social and economic value of well-designed capacity building interventions.
- Output 2 Lesson 3: Timing misalignment. Output 2.3, which measures the application of new skills after three months, could not be reported on due to insufficient time since training. This highlights the need to align training schedules with MEL timelines to enable output tracking.
- Output 2 Recommendation 3: Align Itad MEL reviews in line with project delivery in year to allow for accurate target setting and reporting. Coordinate with BCAP teams to ensure their training activities are captured in future reporting cycles.

## C. DETAILED OUTPUT SCORING

Output Title	Evidence-based recommendations, guidance or tools provided for project planning / adaptation, policies, plans and governance frameworks from local to national level
Output number:		3	Output Score:	A
Impact weighting (%):		14	Weighting revised since last AR?	no

No	Description	Milestone	Progress
3.1	Number of outputs (policy briefs, frameworks, recommendations, guidelines, tools) developed or strengthened with evidence	Planned 21	Expectations exceeded: achieved 23; AABS produced 17 reports developed the Peskas data tools. BCAP published the corporate playbook for investing in Mangroves.
3.2	% of outputs (3.1) that are developed through an inclusive process	Planned 90%	Expectations exceeded: achieved 95%; All AABS outputs involved consultation of key stakeholders. BCAP’s playbook was developed through a consultative process, however the level of consultation is not currently classified as ‘meaningful’.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this Output scored an A. This output assesses the COAST programme’s contribution to generating evidence-based recommendations, guidance, or tools that support project planning, adaptation, and the development of policies, plans, and governance frameworks from local to national levels.
Output 3.1 Expectations Exceeded: This indicator measures the number of outputs -such as policy briefs, frameworks, recommendations, guidelines, tools – developed or strengthened by the COAST programme. In year 2 the AABS project produced 17 reports, including recommendations for improvements to coastal resource management based on Fish Loss Assessments carried out by WorldFish, and the Peskas data tools that have been developed as outputs of the work completed by AABS. The Digital Coasts workstream strengthened national data systems in Kenya and Zanzibarb supporting the development of fisheries dashboards, vessel tracking, and digital catch monitoring tools. It has enabled more informed policy and management decisions through co-design workshops with government agencies, aligning digital systems with national priorities. In April 2025 the WEF published their Corporate Playbook for investing in Mangroves which provides concrete guidance to corporates on how to invest in mangrove ecosystems in a high-quality way. Case studies from the Philippines and Indonesia included in the Playbook illustrate how the private sector can help implement national blue carbon roadmap priorities development by the NBCAPs. The BCAP project have a further four outputs developed this year that are currently still in draft but are expected to be completed in the coming months.
Output 3.2 Expectations Exceeded: This indicator measures the percentage of outputs were developed through an inclusive process. 100% of the outputs that Worldfish finalised in year 2 involved consultation of key stakeholders. For example, Worldfish facilitated eight ToC workshops across Kenya, Tanzania, Nigeria and Bangladesh engaging government, fishers, NGOs, researchers, and private sector actors; convened Fishers’ Forums in Kenya and Zanzibar, bringing together fishers, NGOs, and government agencies; and in Kenya, Tanzania and Mozambique WorldFish consulted local fishers, processors and BMUs during assessments of solar dryers, cold chains and processing technologies resulting in community feedback informing the design and deployment of PAYGO solar freezers. In Kenya and Tanzania, Worldfish conducted Gender-Responsive consultations to understand gendered roles in fish loss and waste, to identify barriers to women and youth participation to inform inclusive technology and policy design. The WEF developed their Playbook through a consultative process with 25 stakeholders from the projects corporate engagement group, the Mangroves Working Group, and engagement with private sector and civil society partners through the NBCAPs. However, WEF did not meet their target for this indicator due to the level of participation not currently classified meeting the classification of “meaningful” participation within the COAST indicator reference, suggesting more work is needed.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]

Logframe refreshed during Year 2 and expected again in July 2025 (Year 3) (see explanation above under Output 1)

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]

- Output 3 Lesson 1: Evidence generation was strong but was often based on existing knowledge. AABS produced a high volume of outputs, many of which collated existing data and stakeholder insights.
- Output 3 Recommendations 1: As COAST moves into Year 3 and continues delivery the programme should produce more original, context-specific evidence that can inform policy and practice.
- Output 3 Lesson 2: Evidence sharing is key for delivering impact. Not all reports and tools developed by WorldFish are currently accessible online and several are still under review. Delays in publication and restrictions on products shared could limit the influence of AABS outputs.
- Output 3 Recommendations 2: Establish clear timelines and sharing mechanisms for programme outputs, ensuring that programme stakeholders can find and access evidence and lessons in real time.
- Output 3 Lesson 3: Definitions may need to be reconsidered. All WorldFish outputs were developed through inclusive processes, yet BCAP fell short of its participation target due to restrictive definitions of “meaningful participation” in the COAST indicator reference sheets. This highlights the needs for the parameters of ‘participation’ to be contextually appropriate, especially for private sector engagement.
- Output 3 Recommendations 3: Revisit the indicator reference sheets during the next logframe review process and review participation definitions to make sure they are appropriately defined and reflect the nature of the workstreams, especially for BCAPs corporate engagement.
- Output 3 Lesson 4: Stakeholder engagement is central to design and uptake. Consultative processes such as Theory of Change workshops, Fishers’ Forums, and gender-responsive assessments, were instrumental in shaping tools and recommendations that reflect local realities and priorities.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Appropriate and strengthened governance structures in place
Output number:		4	Output Score:	B
Impact weighting (%):		14	Weighting revised since last AR?	no

No	Description	Milestone	Progress
4.1	Number of governance structures established or strengthened	Planned 10	Expectations exceeded: Achieved 90 / ABBS is working with a number of stakeholders including governance institutions and local management organisations. BCAP established its global BCAP and two national BCAPs in Indonesia and the Philippines.
4.2	Number of plans or regulatory frameworks proposed	Planned 2	Expectations not met: achieved 0; / AABS have not submitted any plans, policies or regulatory frameworks for approval. The Indonesian NBCAP Roadmap was not finalised in Y2, a consultative draft was finalised in June 2025 to be submitted for approval in September 2025.
4.3	% of planning or framework development processes that included consultation with marginalised groups	Planned 100%	Expectations not met: achieved 0%; / AABS did not submit any plans, policies or frameworks to be assessed for participatory processes. Both BCAP roadmaps are still in development and so processes are still underway.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output scored an A, as whilst indicator 4.1 hugely exceeded expectations, indicators 4.2 and 4.3 did not meet expectations. This output measures the number of appropriate governance structures strengthened or put in place as a result of the COAST programme.
4.1. Expectations Exceeded: This output indicator measures the number of governance structures established or strengthened in Year 2 through the programme. WorldFish significantly exceeded expectations in Year 2 by successfully establishing or strengthening 87 governance structures through the AABS programme despite a Year 2 target of 0. To achieve this WorldFish collaborated with a range of stakeholders, including local and national coastal management institutions such as BMUs. The target for this indicator was set to 0 due to the misalignment of the AABS’s project delivery planning and Itad’s development of the logframe Indicators.
In year 2 the BCAP project made significant progress in establishing governance structures at both global and national levels. At the global level, BCAP established its Global Secretariat and launched two key governance and coordination platforms: the Mangroves Working Group and the Finance Expert Engagement Group. These bodies play a central role in guiding international investment strategies and aligning policy across BCAP countries. In Indonesia, Konservasi Indonesia was appointed as the NBCAP Secretariat, and thematic working groups were formed to facilitate stakeholder engagement and ensure alignment on national blue carbon priorities. Similarly, in the Philippines, the Zoological Society of London (ZSL) was established as the NBCAP Secretariat and convened working groups to support the development of the national Blue Carbon Action Roadmap. Additionally, the Philippines NBCAP was invited by the Department of Environment and Natural Resources (DENR) to contribute to the Ocean Environment Task Force, further embedding its work within national governance frameworks.
4.2. Expectations Not Met: This output indicator measures the number of plans or regulatory frameworks proposed in Year 2. Worldfish have been working across 25 policy products, however no plans, policies or regulatory frameworks were finalised during the reporting period and therefore Worldfish missed their year 2 target. These policy products are expected to inform planning and regulatory frameworks in year 3. The WEF was expected to finalise and launch the Blue Carbon Action Plan for its Indonesia NBCAP, however due to a change in the federal government administration in October 2024 the timeline was adjusted resulting in this target being delated. A consultation draft of the roadmap is now scheduled for release at the UN Ocean Conference in June 2025, which falls just outside the period of this annual review and submitted for approval in September 2025.
4.3 Expectations Not Met: This output indicator measures the percentage of planning or framework development processes that included consultation with marginalised groups. This output indicator is linked to the progress reported in 4.2 and because no plans, policies or frameworks have been submitted yet, they were not able to be assessed for participatory processes.
Describe any changes to this output during the past year, and any planned changes as a result of this review. [1 paragraph]
Logframe refreshed during Year 2 and expected again in July 2025 (Year 3) (see explanation above under Output 1)
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
- Output 4 Lesson 1: Governance engagement may be broader than initially captured. Under Output Indicator 4.1 most AABS activities involved engaging governance bodies in consultations, surveys, and project design rather than formal institutional strengthening. Currently the focus is narrower on formal structures and frameworks. There is currently limited evidence on how these engagements translate into strengthened governance capacity.
- Output 4 Recommendations 1: Itad should engage with WorldFish to clarify definitions for governance structures and ensure that AABS’s participatory and systems-based approach is appropriately recognized and captured in reporting.
- Output 4 Lesson 2: Misalignment between project targets and indicator definitions. The Year 2 target for Indicator 4.1 was set at 0 due to a lack of alignment between WorldFish delivery planning and the later development of Indicator Reference Sheets by Itad.
- Output 4 Recommendation 2: Align Itad MEL reviews in line with project delivery in year 3 to allow for accurate target setting and reporting.
- Output 4 Lesson 3: National contexts have affected policy and framework development. Both WorldFish and BCAP experienced delays in submitting formal plans or frameworks due to external factors such as government changes. As a result, Indicators 4.2 and 4.3 could not be met or assessed.
- Output 4 Recommendation 3: Work with delivery partners to mitigate risks that arise as a result of changing regional contexts.
- Output 4 Lesson 4: inclusive participation results are dependent on overall project progress. Because no frameworks were submitted in Year 2, Indicator 4.3 could not be measured.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Networks, partnerships and peer-peer learning processes supporting knowledge exchange and financial flows that strengthen the blue economy
Output number:		5	Output Score:	A
Impact weighting (%):		14	Weighting revised since last AR?	no

No	Description	Milestone	Progress
5.1	Number of networks, partnerships and peer-peer learning processes established or strengthened	Planned 4	Expectations exceeded: Achieved 23 / AABS conducted peer-peer knowledge exchanges between target countries and regions through national fisher fora. / BCAP established 4 networks and 4 peer-peer learning events across Indonesia and the Philippines, as well as establishing 7 partnerships to provide technical advice to NBCAPs.
5.2	% of networks, partnerships and peer-peer learning processes where stakeholders report objectives being met	Planned 75%	Expectations met: Achieved 100% (for established networks) / AABS: 100% of AABS networks, partnerships and processes reported objectives being met. / BCAP: The majority of BCAP networks and learning groups were established recently and it is too early to assess if they have met their objectives.
5.3	% of networks, partnerships and peer-peer learning processes which include participation of marginalised groups	Planned 50%	Expectations not met: Achieved 17% - In all events convened by AABS there was participation of stakeholders and marginalised groups. BCAP has not been able to provide sufficient evidence of marginalised group participation in taskforces.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output scored an A. This output measures the number of networks, partnerships and peer-to-peer learning processes established through the COAST programme that facilitate knowledge exchange and mobilize financial flows to strengthen developing countries blue economies.
5.1 Expectations exceeded: This output indicator measures the number of networks, partnerships and peer-to-peer learning processes established or strengthened. WorldFish exceeded its target, largely due to the AABS project’s facilitation of peer-to-peer knowledge exchanges both across countries and between regions. At the country level, AABS supported a delegation from Kenya to Bangladesh to learn about IMTA systems, including site visits to hatcheries and research institutions. This exchange directly informed Kenya’s IMTA implementation strategy. Similarly, a Zanzibar to Kenya exchange enabled stakeholders to observe digital fisheries monitoring systems in action, fostering alignment on data governance. AABS also convened a multi-country delegation from Kenya, Mozambique, and Tanzania for a digital fisheries knowledge exchange in Timor-Leste. This event provided learning on the Peskas system and its application in small-scale fisheries management. Regionally, in the Western Indian Ocean, AABS co-hosted the first bilateral meeting between Kenyan and Zanzibar governments on fisheries data sharing.
The WEF also exceeded its Year 2 target. At the global level BCAP strengthened two key engagement platforms: the Mangroves Working group, which grew to 21 member organisations, and the Finance Expert Engagement Group, which convened financial institutions and NGOs to co-develop a finance framework for high-quality blue carbon investment. These platforms enabled cross-sectoral collaboration and informed the development of project outputs such as the Corporate Playbook for Investing in Mangroves. Nationally, BCAP supported the operationalisation of NBCAP secretariats in Indonesia and the Philippines, each of which established multi-stakeholder technical working groups and steering committees. At COP29, Indonesia and the Philippines NBCAPs participated in their first formal exchange, accompanied by a cross-sectoral workshop with government, private sector, civil society, and community leaders.
5.2 Expectations met: This output indicator measures the percentage of established networks, partnerships and peer-to-peer learning processes where stakeholder report objectives being met. WorldFish met its Year 2 target, reporting that in a 100% of cases, stakeholders indicated that objectives had been achieved. Upon review, there was insufficient evidence provided from each of the exchanges to provide individual scoring on whether participants felt that objectives were being met. To improve this AABS have now implemented a Kobo form to be deployed across projects which will improve reporting in the future. The WEF did not contribute to the indicator because the majority of the BCAP networks established in 2ear 2 were established too recently to assess whether participants felt they had met their objectives. Assessments will be conducted in year 3 to monitor progress.
5.3 Expectations Not Met: this output indicator measures the percentage of networks, partnerships and peer-to-peer learning processes which include participation of marginalised groups. WorldFish had not originally set a target for this indicator, however, wherever WorldFish convened networks or learning events they consistently facilitated the participation of stakeholders and marginalised groups. A notable example is the Timor-Leste project visit, conducted as part of South-South collaboration efforts. This visit focused on digital transformations for small-scale fisheries monitoring and included active participation from local fishers and government officials. The event aimed to amplify local voices and share lessons on inclusive data systems. Meanwhile, BCAP were not able to provide evidence of sufficient marginalised groups participating in taskforces. Stakeholders included government officials, NGOs, research institutions, and women representatives were included. However, no evidence was submitted demonstrating the inclusion of youth, elders and coastal community members. Looking ahead, further focus group discussions are planned, and the NBCAPs are enhancing their systems for tracking and documenting participation.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Logframe refreshed during Year 2 and expected again in July 2025 (Year 3) (see explanation above under Output 1)
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

- Output 5 Lesson 1: COAST delivered strongly on network building and peer learning in Year 2. Both WorldFish and the WEF exceeded expectations in establishing and strengthening networks and peer-to-peer learning processes.
- Output 5 Recommendation 1: Further strengthen monitoring of learning outcomes. Implement standardized post-event feedback tools (e.g. Kobo forms) across all learning events to assess whether participants feel objectives were met and to capture qualitative insights.
- Output 5 Lesson 2: Partners provided insufficient evidence on output achievement. Although WorldFish reported that objectives were met in all cases, there was limited supporting evidence to verify this. Similarly, BCAP’s networks were too new to assess outcomes, highlighting a gap in monitoring and feedback mechanisms.
- Output 5 Recommendation 2: Itad should work with partners to improve and strengthen evidence submission.
- Output 5 Lesson 3: Participation of the marginalized groups could be documented more strongly. Both partners demonstrated inclusive practices, yet neither had a suitable system in place to track or verify the participation of marginalized groups. WorldFish did not set a target for this indicator despite consistently facilitating inclusive engagement.
- Output 5 Recommendation 3: Improve data collection on inclusion. Itad and partners need to work together to develop and apply consistent methods for tracking participation of marginalized groups, including disaggregated data collection and participant self-identification where appropriate.
- Output 5 Lesson: There was a lack of understanding of indicators and confusion around target setting. WorldFish did not set a target for 5.3.
- Output 5 Recommendation: Itad to work with partners on indicator review and target setting.
## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	Financial roadmaps and pipelines of viable projects are established
Output number:		6	Output Score:	B
Impact weighting (%):		14	Weighting revised since last AR?

No	Description	Milestone	Progress
6.1	Financial roadmaps developed or strengthened (public/private)	BCAP Indonesia roadmap finalised	Expectations not met: the Indonesia Roadmap was not finalised.
6.2	Number of climate finance providers engaged	15 climate finance providers engaged	Expectations met: 14 climate finance providers were engaged.

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, this output scored a C. This output measures the number of financial roadmaps and pipelines of viable projects that are established through the COAST programme. In Year 2, only the BCAP project reported against this output.
6.1. Expectations Not Met: The WEF originally intended to complete development on their Indonesia Blue Carbon Action Plan in Year 2, however due to a change in Indonesia’s federal government in October 2024, this process was delayed. Despite this, the roadmap was developed through a robust and collaborative process with the Indonesian government, marked by strong national-level engagement. The NBCAP Secretariat was successfully mobilised and operational, and although outside the reporting period, a consultative draft of the Indonesia Blue Carbon Action Plan was shared with stakeholders in June 2025 for feedback. Whilst not meeting the milestone, substantial and meaningful work was undertaken.
6.2. Expectations Met: This output indicator measures the number of climate finance providers engaged. In Year 2 the WEF only missed their target by 7% and demonstrated strong engagement with fourteen climate finance providers. 47% of these providers have continuous and strategic support, particularly in the Mangroves working group and in the development of the ‘Corporate Playbook for Investing in Mangroves’.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Logframe refreshed during Year 2 and expected again in July 2025 (Year 3) (see explanation above under Output 1)
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
- Output 6 Lesson 1: The binary nature of the indicator 6.1 (e.g finalised vs not finalsied) does not measure the progress made by the project in developing the roadmaps, such as stakeholder engagement, institutional setup, and draft development. This oversimplification risks undervaluing substantial groundwork and collaborative achievements that are critical to long-term success.
- Output 6 Recommendation 1: Revise and refine the output indicator to help capture the extent of delivery, for example, redesigning indicators to include qualitative milestones (e.g. stakeholder engagement, draft development, institutional set up) alongside quantitative targets. Potentially introduce tiered milestone system for roadmap development – e.g. initiation, draft, consultation, finalisation.
- Output 6 Lesson 2: Political transitions can affect project timelines even when technical and stakeholder progress is strong. The change in Indonesia’s federal administration in October 2024 delayed the finalization of the Blue Carbon Action Plan.
- Output 6 Recommendation 2: Build flexibility into planning and risk mitigation measured in response to political or institutional changes. Maintain momentum through consultations, workshops, and other engagement even when formal outputs are delayed.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]
Output Title	Effective mobilisation of COAST
Output number:		7	Output Score:	A
Impact weighting (%):		14	Weighting revised since last AR?

No.	Description	Milestone(s) for this review	Progress
7.1	Number of agreements signed with COAST tier-1 delivery partners;	Contract signed for Component A supplier and all agreements in place for COAST's 4 tier-1 partners covering 100% of COAST's budget.	Expectations met: Contract signed for Component A supplier in November 2024 and all agreements therefore in place for COAST's 4 tier-1 partners covering 100% of COAST's budget.
7.2	Recruitment completed for COAST tier-1 delivery partners' core teams	Complete for Component A	Expectations met: Recruitment complete for Component A Programme Management Unit (core), Country Teams and Consortium Partners (tier 1) (Milestone deliverables 3, 17 and 15).
7.3	COAST programme and component level strategies in place	Component A Mobilisation Phase successfully finalised (including / strategies, workplans, results frameworks, etc.)	Expectations met: All 18 Component A Mobilisation Milestones successfully delivered to schedule, including programme and country strategies, workplans and the results framework.
7.4	Number of countries where components have begun to deliver projects	Planned - Total:4 new countries / Component A: 4 / Component B: 0 / Component C: 1 / Component D: NA / (NB Component C's new country overlaps with Component A)	Expectations moderately not met: / Component A: 0 / Component B: 0 / Component C: 0 / Component D: NA / See explanation below.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 7 measured the effective mobilisation of COAST during Year 2 of programme implementation. Unlike the previous year which measured the effective mobilisation of COAST Components B, C and D, in Year 2 only COAST Component A remained to be mobilised over the reporting period.
Procurement for Component A’s commercial supplier adopted a two-stage process. This approach was informed based on extensive early market engagement undertaken by FCDO in year 1 (see Year 1 AR). The first stage was launched on 24th January 2024, and successful bidders from Stage 1 were invited to submit full proposals at stage 2 on 26th March 2024. In Year 2, Procurement was on track and expected to be completed with the selected delivery partner starting before the end of September 2025.
Unfortunately, the UK General Election in June 2025 delayed final Ministerial approval of the Component A contract until October 2024, with the final Contract signed with the winning supplier, DAI Global, in November 2024 (Output Indicator 7.1). This delay, outside of the scope of the COAST programme, pushed back Component A mobilisation timelines by approximately 2-3 months and Component A has not therefore managed to deliver live projects in its 4 priority countries within the reporting period (Output indicator 7.4).
Despite this, DAI global has made good progress in mobilisiing COAST component A (Output Indicators 7.2 & 7.3). Under the original Terms of Reference and Contract, Mobilization of Component A was divided into 19 deliverables, with submission deadlines to FCDO between December 2024 and June 2025. Amongst them, these included specific deliverables on:
- Introductory meetings with FCDO Posts, Component B, C and D suppliers
- Mobilisation Phase Plan & Core Team Recruitment
- Risk Management Strategy & Due Diligence Approach
- Project Screening process and evaluation criteria
- Communications and Stakeholder engagement strategy
- A gender equality and social inclusion (GESI) strategy
- Learning, Sustainability and Exit strategies
- Recruitment of other staff to support core team
- Component A Logframe, Theory of Change and MEAL approach
- Establishment of Country offices and full recruitment of country teams
- Country Strategies for each Phase 1 Priority Country
Overall, this output scored an ‘A’, with three indicators (7.1, 7.2 and 7.3) meeting expectations and one indicator (7.4) moderately not meeting milestone targets for this review due to the initial 2–3-month delay in signing the contract. That said on current timelines, COAST Component A is expected to have live projects in 3 priority countries by July 2025 and the final priority country in September 2025. We are confident there, despite the initial delay in signing the contract and mobilising due to the 2024 General Election, Component A is on track to deliver.
Describe any changes to this output during the past year, and any planned changes as a result of this review.
Logframe refreshed during Year 2 and expected again in July 2025 (Year 3) (see explanation above under Output 1), which will include Component A activities and results in the overall COAST logframe.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead [1-2 paragraphs]
A full list of COAST Year 1 (23/24) Annual Review Lessons, recommendations and actions taken since the last review are included in Annex 1. This related to Output 7 are included below, included actions taken and follow up recommendations:
Year 1 Recommendation #1: The SRO and FCDO COAST team should ensure all programme-level delivery, engagement and monitoring strategies including the COAST ToC, COAST theory of delivery and programme-level logframe, are updated to reflect Component A's onboarding and strengthen COAST’s strategic delivery. Lead(s): COAST SRO. Deadline: Throughout year 2.
Action Taken: Since the contract for Component A was signed in November 2024, DAI Global have been in a mobilisation phase for the remaining reporting period (Dec 24 – April 25), developing key project delivery, engagement and monitoring strategies. With the completion of Component A’s mobilisation phase in June 2025, FCDO and Itad will undertake a review and update of overall COAST programme-level delivery, engagement and monitoring strategies including the COAST ToC, COAST theory of delivery and programme-level logframe. Next steps: We recommend maintaining this recommendation for Year 3. Lead(s): COAST SRO. Deadline: Q2 Year 3.
Year 1 Recommendation #5: FCDO and the appointed Component A supplier must prioritise securing host government approvals for Component A to operate in each COAST priority country during the Mobilisation phase given the anticipated complexities and long timeframes. FCDO seniors and advisers both at post and in central teams should be asked to engage counterparts to help this process. Lead(s): COAST SRO and Component A delivery partner. Deadline: Throughout year 2.
Action Taken: During ICAI’s Rapid Review of the Blue Planet Fund in 2023 they recommended that “Defra and FCDO should ensure that governments and other national stakeholders in the countries where the Fund operates are empowered to shape programmes by creating formal channels for them to communicate their priorities and needs.
In response, working collaboratively with host governments and other national stakeholders in the launch, co-design and approval of COAST Component A has been at the forefront of FCDO and DAI’s approach to mobilisation in the 4 priority countries (Dec 24 to Apr 24). FCDO, DAI and host Government have delivered high-level and official-level launch events in Indonesia, Mozambique and Philippines and have prioritised co-designing COAST Country Strategies with relevant government stakeholders which support overarching Blue Planet Fund Country Plans and build buy-in and ownership with partner governments. An emphasis on co-designing COAST activities has ensured that COAST delivers against host government marine priorities, alongside UK priorities set out the Blue Planet Country Plans and the COAST Business Case.
This process has at times proved challenging, in part because the programmes, relationships and coordination mechanisms are relatively new. However, through utilising the FCDO’s diplomatic network overseas at post, including Ministerial visits, and the appointment of Blue Planet Fund Regional Coordinators to coordinate programme delivery, these challenges have been addressed and overcome. Following the completion of the co-design process in June 2025, FCDO and DAI will seek formal government approval of COAST Country Plans and agree ongoing coordination mechanisms to ensure Host Governments remain engaged in COAST delivery. We are also exploring the appointment of COAST Advisors in selected countries to improve oversight of partners and engagement of Government and other national stakeholders.
Next steps: We recommend maintaining this recommendation for Year 3 until Government approval secured and Governance arrangements agreed with Host Governments agreed. Lead(s): COAST SRO. Deadline: Q2 Year 3.
## D: VALUE FOR MONEY (1 page)

The COAST approach to Value for Money (VfM) was developed as part of the COAST Programme Monitoring, Evaluation and Learning (MEL) Strategy, finalized in June 2024. The COAST VfM approach aims to integrate VfM elements into COAST MEL workstreams, and not to track VfM as an isolated reporting line. To this end, Itad developed VfM indicators, to be periodically reported against by DAI, Worldfish and WEF. For COAST Evaluations, VfM-related questions and sub questions are included in the evaluation matrix and all planned COAST evaluations.
COAST performance across the VfM 5 Es during year 2 is as follows:
Economy: Being a good steward of programme resources, buying the right inputs, of the appropriate quality, at the right time, right price, and leveraging networks.
In year 2, COAST delivery partners demonstrated strong performance on economy, with clear evidence of cost-conscious decision-making and competitive procurement. The largest cost drivers across Components B (AABS) and C (BCAP) continued to be personnel costs but with an increased share of budget dedicated to delivery. AABS reported cost savings exceeding £80,000 across multiple COAST countries, primarily through contract negotiations with suppliers and cost comparisons across competitors. Additional savings were achieved through the review of large-scale supplier contracts. BCAP also identified two specific cost-saving measures that resulted in a reduction of approximately £129,000. Both AABS and BCAP consistently applied competitive procurement practices, including the use of benchmarked consultancy fee rates and output-based payment mechanisms to ensure value from technical assistance and advisory inputs.
 Efficiency: COAST produces the intended mix, quality and quantity of deliverables aligned with the needs of partner countries and other beneficiaries, working adaptively and within the available resources.
Efficiency in year 2 was mixed across COAST components, with strong performance in some areas and challenges in others. AABS achieved a high fund utilisation rate of 99% (£7.46m spent against a £7.5m budget), demonstrating sound financial execution. The NBCAPs reported a relatively low budget execution rate of 70% (£1.04m out of a forecast £1.43m), falling short of the <5–10% variance benchmark. This underspend was largely attributed to contextual delays—including political transitions in Indonesia and internal changes in the Philippines—as well as staff turnover. Two national blue carbon frameworks were supported in Indonesia and the Philippines, with broadly similar costs of £274k and £328k respectively, although trend data will be required to better assess efficiency in future years and these investments are expected to leverage greater private investment.
Importantly, the implementation of the COAST VfM monitoring system in Year 2 enabled partners to begin reporting against standardised VfM indicators, though as with other areas of the review (logframe and GEDSI indicators) further work is needed to ensure full alignment with the MEL framework and consistency in reporting.
 Effectiveness: COAST activities demonstrate impact for partners, countries and beneficiaries in line with COAST’s aim and objectives.
Both BCAP and AABS engaged extensively with coastal communities through consultations, technical assistance, and workshops, with AABS alone reaching over 5,500 indirect participants. However, more systematic tracking and reporting will be needed in future rounds to better evidence the effectiveness of interventions in terms of environmental and community-level impacts. AABS also provided several examples of adaptive management, including revisions to mobilisation plans in Mozambique to mitigate delays, and updates to databases and analytical tools to enhance flexibility and responsiveness to local contexts. These adaptations reflect a proactive approach to risk management and improved contextual relevance of delivery. BCAP did not formally report on effectiveness against VfM indicators in this round; however, the component made important progress through the consolidation and activation of the Indonesia and Philippines NBCAPs and meaningful momentum toward the establishment of the Viet Nam NBCAP. Furthermore, progress was made regarding the production and dissemination of influential knowledge products and convening platforms designed to unlock finance and advance high-quality blue carbon action for the benefit of coastal community livelihoods, well-being, equity, and inclusion. Notably, the High-Quality Blue Carbon Practitioners Guide and the Corporate Playbook for Investing in Mangroves are now in use by governments and private investors, supporting replication of high-quality blue carbon approaches.
Equity: COAST contributes to reducing constraints, improving opportunities and influence in climate change and coastal matters for women, other marginalised groups, and future generations.
Equity considerations were actively integrated across COAST components in Year 2, though with some variation in depth and reporting completeness. AABS reported £141,000 in expenditure on gender equality, disability, and social inclusion (GEDSI)-related activities, reflecting a targeted effort to address the needs of marginalised groups. On localisation, Tanzania stood out with 21.4% of AABS's budget allocated to downstream partners in low- and middle-income countries (LMICs), compared to 9.8% in Kenya, 4.7% in Nigeria, and 4.3% in Bangladesh. BCAP reported lower but notable budget allocations to LMIC-based partners, with 5% of its expenditure directed to organisations in Indonesia (£50,446) and 8% in the Philippines (£72,383). While comprehensive disaggregated data on the cost of reaching women and marginalised groups remains limited, there have been some promising developments: BCAP contributed to sectoral thought leadership through a scientific paper on gender in blue carbon initiatives, authored with regional experts. Additionally, NBCAPs have committed to implementing disaggregated GEDSI data tracking starting in FY3, which will improve equity assessments going forward.
Cost-effectiveness: COAST creates more value than it consumes and/or meets expectations commensurate with the resources invested in the programme.
While neither AABS nor BCAP have reported on cost effectiveness metrics this round, Year 2 cost-effectiveness developments can be inferred but should be fully reported as soon as possible. Current examples include:
- COAST is increasingly working on leveraging private and philanthropic finance, through BCAP’s Financial Institutions Workstream which directs investment into high-quality blue carbon ecosystem restoration and conservation and their communities. This workstream will be developed further in Year 3.
- Investment strategies have been aligned with national priorities in the Philippines and Indonesia, laying the groundwork for future finance mobilisation. For example, the National Blue Carbon Roadmap developed under COAST in the Philippines is now serving as the technical and strategic basis for the forthcoming Blue Carbon Executive Order, a national policy directive funded by the Agence Française de Développement (AFD) and the Asian Development Bank (ADB).
Conclusion
Year 2 has seen COAST transition from planning to implementation, with improved efficiency, stronger delivery partnerships, and a focus on inclusive, sustainable outcomes. COASTs progress in year 2 aligns with its strategy and partners have begun reporting against VfM KPIs which, overall, demonstrate good VfM. To strengthen VfM in the next round, FCDO recommend: 1) better alignment of partner reporting with Itad’s framework to ensure consistent, reliable metrics 2) Improving equity tracking through disaggregated GEDSI data, 3) Reducing outreach unit costs through scaling or revised delivery models and, 4) Initiating formal reporting on cost-effectiveness.

E: RISK

Overview of risk management
The overall risk rating of the programme continues to be moderate. The programme has operated within risk appetite for each risk category throughout year 2. The COAST team has held quarterly risk meetings throughout year with all partners to help identify key risks under each project and provide assurance to FCDO that key risks across the components are being proactively managed. This process improved partners understanding of FCDO expectations and strengthened their risk monitoring and registers. It has also helped in ensuring that partner registers inform the main FCDO COAST programme risk register, as the FCDO team are better informed of the risk across the programme. The COAST project risk register holds all identified risks and has mitigation measures in place and a named risk owner. These are monitored and discussed within the team every 2 months.
 Key risks that were monitored and mitigated by FCDO during year 2 are presented in Table 1.
 Table 1: Year 2 Key COAST Risks
Risk Description	Gross Risk	Mitigations	Residual Risk
Priority countries identified for engagement prove to be unsuitable for programme delivery, leading to ineffective use of spend. This could be as a result of challenging political economy contexts, or marine and social contexts thwarting proposed interventions.	Moderate	An analysis of countries' marine contexts and NDCs was undertaken as part of business case development, capturing some of the specific challenges within countries (and ambitions to address them). Delivery partners will conduct scoping exercises as part of initial stages of projects, and where appropriate will proactively engage with governments to ensure compatibility and join-up on objectives. COAST Country Plans help in country stakeholders to buy into the COAST programme. We are engaging with the government of all priority countries to understand their priorities and ensure stakeholder buy in.	Moderate
GEDSI Interventions under COAST are not effective and our programme fails to meaningfully reach and/or benefit marginalised groups.	Moderate	Partner workplans each year are reviewed to ensure they are proactively targeting women, girls and other groups. Partners will report on inclusion results to drive a proactive focus during delivery. MEL component and independent monitoring will help track progress and provide further support where needed. COAST logframe now approved and requires dis-aggregation of results by different groups. Component A project selection criteria will consider the impact on women and girls and other groups to ensure that opportunities to drive transformation are not missed. The COAST team and ITAD recently undertook a GESI workshop to articulate COAST's GESI ambitions.	moderate
COAST programme activities gain adverse media attention questioning FCDO investment within priority countries, or HMG's use of ODA funding, leading to reputational damage for HMG, FCDO and the COAST programme.	Moderate	We have engaged with posts, host governments and other stakeholders (private sector and communities) to ensure that the programme understands and supports local priorities, improving legitimacy, effectiveness and buy-in, and minimizing the risk of unwanted local media attention. For the UK domestic audience, FCDO should develop reactive media lines and flag to comms lead potential risks, particularly around stories which question "shrimp farming	moderate
During the programme delivery, financial mismanagement by partners and downstream partners increase the chance of fraud, corruption and aid diversion, reducing the impact of the project.	Major	FCDO undertakes extensive due diligence on partners, including a counter aid diversion guidance and statement within all agreements. FCDO staff undertake fraud, bribery and corruption training regularly to ensure processes are known and followed. PROF guides also include delivery chain mapping to give the FCDO programme manager oversight of where funds are being spent down the chain. These activities reduce the risk that funds are spent on intended purposes as well as equipping staff with the knowledge and processes to escalate concerns early to avoid high impact risks being realised. We have quarterly meetings with partners to discuss risks which include fraud. Regular reporting of activities undertaken will be required as part of governance and monitoring framework. We will ensure that all partners carry out due diligence reports before they have signed any agreements with them and this will be discussed at regular risk meetings with partners. Partners will also be required to hold regular meetings with sub grantees to discuss these risks and will report any issues to FCDO immediately	Moderate
During COAST delivery, inadequate partner due diligence/ controls enables sexual exploitation to occur, causing harm to victims (staff & beneficiaries), potential suspension of activities and/or reputational damage to FCDO.	Moderate	FCDO undertakes due diligence on all partners, including a specific assessment of safeguarding policies, processes, training and other measures in place. All agreements include safeguarding clauses. Partners will use FCDO reporting procedures and agree to report any incidents to FCDO as soon as they arise. / The COAST team will ensure each partner under the programme has a strategy in place for tackling SEAH and promoting GEDSI under the COAST programme and push partners to demonstrate that they have put in place sufficient measures to mitigate the likelihood of the risk, and that these have been cascaded down the delivery chain. / Throughout implementation, FCDO reviews and discusses partner risk registers on a quarterly basis to ensure safeguarding risks are monitored and safeguarding controls are in place. Partners will also be required to hold regular risk meetings with sub grantees to ensure they follow all FCDO policy and procedures on SEAH. All partners are required to report any incidents to FCDO immediately. / Finally, safeguarding risks will be flagged to FCDO posts and BPF regional coordinators in the countries COAST operates, and we will look for opportunities to test whether controls are in place on the ground through monitoring.	Moderate
COAST does not sufficiently address ICAI’s findings and recommendations following their rapid review of the BPF.	Major	A high-level action plan has been produced and agreed between Defra and FCDO which includes actions for programmes to address ICAI’s recommendations. FCDO is proactively working to embed these actions into COAST’s delivery. FCDO and Defra meet monthly to track progress on addressing ICAI actions which the COAST SRO attends and reports on COAST’s progress.	Moderate
Poor coordination between Blue Planet Fund programmes in country results in incoherence and creates reputational and delivery risks	Major	FCDO have led the development of BPF portfolio country plans in all four COAST priority countries during COAST’s year 1. These present the host governments’ priorities and outline how each BPF programme prioritised for that country, including COAST, will contribute to delivering them helping to reduce overlap between countries. FCDO and Defra hold quarterly oversight meetings for the BFP to support portfolio coordination. The FCDO Coast team works closely with BPF Regional Coordinators in Southeast Asia and East Africa to ensure close alignment with FCDO posts, host governments and other BPF programmes.	Moderate

 Risk appetite trends:
Strategy and Context: Appetite = Receptive. COAST delivers in a relatively new area for HMG’s ODA programming, the marine environment sector. The success of COAST continues to depend on its ability to engage in this new sector, build relationships and navigate political economies, deliver high quality interventions based on evidence and learning, and drive a strong MEL approach that supports continuous programme improvement. COAST’s year 2 has delivered in line with COAST’s strategy set out in the business case. Elections in COAST’s priority countries have occurred in this period. However, it is unlikely this will result in a significant de-prioritisation of marine environment or blue economic issues that will impact COAST.
Policy & Programme Delivery: Appetite = Cautious. COAST is designed to build upon available evidence and ensure this is applied during delivery. Delivery partners have been selected on their ability to deliver the Components and the engagement requirements underpinning it. COAST’s MEL strategy is now in place and Itad are regularly engaging with and supporting other COAST partners to support its implementation, ensuring COAST will capture evidence and lessons to support delivery choices. No change is proposed for this risk appetite.
Safeguarding: Appetite = Minimal. COAST partners have undergone due diligence checks to ensure they have appropriate policies and procedures in place to avoid, minimise and mitigate safeguarding risks during delivery. Any new tier-1 partners will also undergo due diligence checks in advance of any agreements being signed. All live COAST tier-1 partners have appropriate policies and procedures in place to ensure safeguarding risks are minimised throughout their delivery chains. Year 2 has focussed on delivery of AABS and BCAP projects and procurement of a supplier for Component A, DAI Global. Since the contract was signed in November 2024, DAI have been concentrating on mobilising the COAST Facility, which is due to begin full implementation in July 2025. The potential for safeguarding incidents may increase as direct engagement with local communities and other stakeholders increases through year 3. This risk appetite will be monitored carefully throughout year 3.
Financial & Fiduciary: Appetite = Cautious. WorldFish, WEF, ITAD and DAI have undergone due diligence processes to ensure they have appropriate policies and procedures in place to avoid, minimise and mitigate financial and fiduciary risks during delivery. Any new tier-1 partners will also undergo due diligence checks in advance of any agreements being signed. All live COAST tier-1 partners have appropriate policies and procedures in place to ensure financial risks are minimised throughout their delivery chains.
FCDO staff overseeing COAST have completed mandatory fiduciary risk training in year 2. WorldFish, WEF and Itad have produced delivery chain risk maps to monitor funds and fiduciary risks. DAI will also send a delivery chain spreadsheet once they move into implantation phase. FCDO and all delivery partners regularly discussed fiduciary risks during year 2. There is potential for fiduciary risks to grow in year 3 onwards as COAST’s downstream delivery chain becomes larger and more complex, particularly through Component A. FCDO and delivery partners will continue to closely monitor fiduciary risks and ensure policies and procedures are followed. No change is proposed for this risk appetite.
 Reputational: Appetite = Cautious. COAST is still a relatively new programme in a new sector for HMG and has been designed using the best available evidence. Sufficient time has been allocated for COAST to deliver interventions with support from a strong MEL approach to ensure delivery is robustly assessed. This will help the programme team to identify and scale successful activities and stop those performing poorly. COAST has been well received by ICAI in their review of the Blue Planet Fund. No change is proposed for this risk appetite.
People: Appetite = Cautious. COAST is being delivered in a phased approach to streamline programme management, allowing ECED to manage capacity and budgets. Experienced delivery partners and their staff have and will be engaged for each COAST component to reduce programme management burdens and risks. No change is proposed for this risk appetite.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE [1 - 1 ½ pages]

Summarise the performance of partners and FCDO, notably on commercial and financial issues. [max 1 page]
Throughout year 2, WorldFish, WEF and Itad have performed well when it comes to commercial and financial management of their respective projects. They all produced good quality Year 2 workplans and were responsive to engaging with FCDO to ensure these met requirements.
All partners have provided regular progress updates throughout the year through monthly and quarterly meetings with FCDO. Regular topics included general progress updates, recruitment, risks, finance and progress against KPIs. These have helped to build a strong relationship with FCDO. Quarterly progress reports have been good quality and have proactively addressed comments and responded to clarifications from FCDO in a timely manner.
DAI was selected as the supplier for Component A and their contract started in November 2024 with a 7-month mobilisations phase which has gone well and will conclude in June 2025. Throughout the mobilisation phase FCDO has met with DAI on a weekly basis, producing high quality documents in line with their mobilisation phase deliverables (see Output 7).
Component A - DAI Global
 As stated above, DAI were awarded the contract as supplier for Component A in November 2024. Procurement for Component A’s delivery partner involved extensive early market engagement to inform FCDO’s procurement strategy. Two online events were held to present Component A and its ToRs with a detailed survey on the ToRs released to the market between these events. A two-stage procurement process was adopted based on the feedback received, involving: Stage 1, a fully open call for organisations to submit bids to demonstrate their experience to deliver Component A, and Stage 2 , the top bids from Stage 1 invited to submit detailed bids outlining how they would deliver the requirements of the Component A ToR. During year 1, Stage 1 was completed, and Stage 2 was undertaken during June 2024 and DAI was the successful bidder. There was a delay in getting the contract signed due to the general election in the UK in July 2024 and it was not until late November that the contract was signed.
The ToR for Component A includes performance based KPIs that will apply to a percentage of the supplier’s fees. These will become effective after Component A’s mobilisation phase has completed in June 2025. Component A’s mobilisation phase will use a milestone-based payment method.
They began a 7-mobilisation phase which included a set of 20 milestone deliverables. Their initial budget for the mobilisation phase was £350,00 but this was increased to £739,838 due to DAI confirming that they would be able to deliver 18 milestones by the end of 24/25 financial year. Milestone 19 and 20 will be delivered in April and June respectively. DAI has provided regular progress updates during the mobilisation phase through weekly meetings with FCDO. Regular topics included general progress updates, Progress against KPIs, recruitment, risks, and finance. These have helped to build a strong relationship with FCDO. They have proactively addressed comments and responded to clarifications from FCDO in a timely manner. DAI have provided a work-plan for their implementation phase, and it is expected that they will be able to deliver against this work-plan and budget.
Component B - WorldFish
During the early part of the financial year, there was some issues around spend against original forecasts particularly in quarters 1 and 2. However, FCDO implemented regular dialogue with Worldfish to strengthen their forecasting performance which resulted in improvements in forecasting in quarters 3 and 4. WorldFish provided regular progress updates during year 2 through monthly/quarterly meetings with FCDO. Regular topics included general progress updates, recruitment, risks, and finance. These have helped to build a strong relationship with FCDO. Quarterly reports have been good quality and have proactively addressed comments and responded to clarifications from FCDO in a timely manner. The expenditure for year 2 of AABS was GBP £7,458,901, a spend rate of 99.5% (year 2 budget GBP 7,500,000).
Component C – The World Economic Forum
The WEF had an initial budget of £1,241,731 for year 2. The actual spent was £1,036,072 which is represents an underspend of £205,660. The main areas for this underspend were in personnel and NBCAP costs and these were due to
- Personnel: The WEF previously budgeted using median salaries which were higher than those on BCAP teams; these have adjusted to a lower rate for Y3 to more accurately match forecast with actuals.
- NBCAPs: Staffing transitions resulted in underspend on salary
WEF have had issues on forecasting accuracy which has also contributed to the underspend, and we had regular meetings with them to try and resolve the problem. As a result of these meetings, it was agreed that for year 3, they would request that the NBCAPs provide monthly forecasts that incorporate actuals from previous months to help minimize the gap between forecasted and actual results; and to highlight any major factors that may impact future spend. WEF also provided regular progress updates during year 2 through bi-weekly/quarterly meetings with FCDO. Regular topics included general progress updates, recruitment, risks, and finance. These have helped to build a strong relationship with FCDO. Quarterly reports have been good, and they have proactively addressed comments and responded to clarifications from FCDO in a timely manner.
Component D - ITAD
The workplan budget for FY 24/25 was set at £665,157, while the actual spend amounted to £554,646.07 (excluding VAT), resulting in a 20% underspend. This variance has been closely monitored throughout the year, primarily due to three key factors impacting the MEL workplan:
- Alignment with Component A: Activities were adjusted to better align with Component A.
- Evaluation Planning: The decision was made to initiate the Evaluation Inception and Evaluation Steering Group in the next fiscal year.
- Reduced International Travel: International travel was deemed unnecessary.
The majority of the underspend was attributed to input-based fees. For year 3 (FY 25/26), robust work planning and utilisation forecasting systems have been implemented, along with regular communication with FCDO to mitigate future underspend risks. ITAD also provided regular progress updates during year 2 through bi-weekly/quarterly meetings with FCDO. Regular topics included general progress updates, Progress against KPIs, recruitment, risks, and finance. These have helped to build a strong relationship with FCDO. Quarterly reports have been good, and they have proactively addressed comments and responded to clarifications from FCDO in a timely manner. A clear workplan and deliverables have been set out for year 3 and FCDO is confident delivery and spend rates will be as planned. The ToR for Component D includes performance based KPIs that will apply to a percentage of Itad’s fees should they not deliver against the agreed KPIs.
Recommendations for next Year
FCDO to ensure that partners submit monthly updated forecasts. FCDO to hold quarterly meetings with partners to lock down each quarter forecast to minimise large variances between forecast vs actuals.
G: MONITORING, EVIDENCE AND LEARNING
Monitoring of the COAST programme during year 2 was undertaken by FCDO and itad. FCDO monitored implementation of the programme through weekly, fortnightly, monthly and quarterly progress discussions, where implementation was monitored against agreed workplans and milestones. For BCAP and AABS projects, FCDO met with the WEF and Worldfish on a fortnightly and monthly basis respectively, with formal quarterly review meetings for both partners. During the mobilisation of the COAST Facility, FCDO met with DAI on a weekly basis to monitor progress against agreed mobilisation deliverables.
FCDO also undertook a 3 week visit to Mozambique, Kenya, Tanzania in March 2025 to monitor implementation of the AABS project. The objective of the visit was to assess the progress and impact of the project in communities, support coordination efforts in Mozambique between WorldFish and DAI, and engage with government and local stakeholders to build support for the COAST programme. Lessons learnt included the need for a) greater coordination between AABS work packages in induvial countries, b) the need for more streamlined project leadership and management of the AABS from Worldfish, and c) the need for deeper integration of GESI considerations in AABS delivery. Actions and lessons were discussed and agreed with Worldfish following the visit and will be implemented over Year 3.
Logframe and Monitoring
Itad supported FCDO’s programme’s monitoring by conducting workshops with each partner to review indicator reference sheets (IRS) and reporting templates. These sessions clarified reporting expectations and allowed for iterative improvements to the templates based on partner feedback. Throughout the development and implementation of the monitoring framework, Itad maintained regular engagement with both programme implementers and FCDO. This included co-developing indicators and tools, incorporating feedback, and preparing partners for the first round of reporting under a new logframe. As this is the first reporting cycle, quarterly reporting was deferred, with Q1 results expected in Q2 of Year 3.
Whilst Itad’s collaborative approach has helped ensure that partners were better prepared for the reporting period and that the tools used were practical and understood. Based on findings from the annual review process, there is still some way to go to ensure that progress is being monitored effectively across the programme. For example, partner tracking of disaggregated participation data and capturing meaningful engagement of marginalised groups was not effective. Moreover, the binary nature of some output indicators does not reflect the extent of the progress made towards policy development and stakeholder influencing in COAST countries, such as stakeholder engagement, institutional setup, and draft policy development. This is an overarching challenge of aligning multi projects into a single monitoring framework and FCDO will need to work with all partners to revise and refine the programme logframe following this review.
To do so, itad lead reflection sessions with FCDO and partners are planned for August 2025, alongside the annual review of the Theory of Change, logframe, and indicators to ensure alignment with programme goals. This will be an opportunity to address many of the recommendations outlined in this review. The COAST programme evaluation is currently in its inception phase (January–June 2025), which was slightly delayed due to procurement delays to Component A. The evaluation will move into a formative process evaluation phase in Q3 and Q4 of Year 3.
Evidence
In the first year of the MEL Strategy, evidence generation has been limited, with efforts focused on designing and implementing the monitoring system. This included developing indicator methods, reference sheets, and initiating the evaluation inception phase. These foundational activities are expected to support more robust evidence collection in the coming years, with quarterly monitoring and the first evaluation phase scheduled for Year 3. While the programme aims to align with the ‘Leave No One Behind’ agenda by disaggregating data by geography, income, sex, age, and disability, implementation has been inconsistent. AABS and BCAP have struggled to meet these expectations, largely because the requirement for disaggregated data was not clearly communicated at the outset of Year 2. However, efforts are now underway to ensure downstream partners are aware of these expectations, with the aim of improving data quality in future reporting cycles.
Learning
COAST has followed a six-monthly learning cycle outlined in the MEL Strategy (figure below). Over the past year, Itad have delivered evidence reviews on poverty alleviation and strategic partnerships, held component-level learning sessions on GEDSI, and introduced new processes to support adaptive programming. Key learning events included Partner Coordination Forum’s in October 2024 and March 2025, which brought together all partners under the COAST programme to discuss key issues/themes, share learning and build collective understating of each partner workstream.
An annual learning synthesis is being prepared for delivery by the end of July 2025. Key lessons from the past year will be detailed in the upcoming learning synthesis. To strengthen learning going forward, Component partners are being asked to develop annual learning plans. Below summarises the COAST annual learning cycle.

For the coming year, Itad will focus on two key learning questions: (1) How to develop and implement a robust exit strategy, and (2) How to scale effectively within the COAST programme. These questions will be explored through structured learning discussions, evidence reviews, and facilitated sessions, with the aim of generating actionable insights to inform programme delivery in Year 3.

Date of last narrative financial report	WorldFish – 15 May 2025 / ITAD – 28 May 2025 / WEF – 1 July 2025	Date of last audited annual statement	WorldFish is not due until after the annual review.

Annex A: COAST Year 1 (23/24) Annual Review Lessons and recommendations Tracker
Lesson:	Recommendation:	Action/Update:
Early delivery is validating COAST’s overarching ToC and multi-component approach and strategy. Year 2 will be a further test with the onboarding and mobilisation of Component A’s delivery partner. Based on year 1’s experience, strong oversight and high engagement from FCDO SRO and the COAST team, with additional engagement from posts in COAST priority countries, will be needed to ensure the new delivery partner successfully mobilises, enhances COAST’s strategic delivery and that live COAST’s Components continue to deliver successfully. This engagement should be organised around ensuring COAST’s overall strategic delivery plans and MEL strategy are updated to account for Component A.	The SRO and FCDO COAST team should ensure all programme-level delivery, engagement and monitoring strategies including the COAST ToC, COAST theory of delivery and programme-level logframe, are updated to reflect Component A's onboarding and strengthen COAST’s strategic delivery. Lead(s): COAST SRO. Deadline: Throughout year 2.	Since the contract for Component A was signed in November 2024, DAI Global were in a mobilisation phase for the remaining reporting period (Dec 24 – April 25), developing key project delivery, engagement and monitoring strategies. With the completion of Component A’s mobilisation phase in June 2025, FCDO and Itad will undertake a review of overall programme-level delivery, engagement and monitoring strategies including the COAST ToC, COAST theory of delivery and programme-level logframe. Next steps: We recommend maintaining this recommendation for Year 3. Lead(s): COAST SRO. Deadline: Q2 Year 3.
COAST’s first Partner Coordination Forum (PCF) was a valuable tool for building COAST delivery partners’ relationships and trust, build knowledge of COAST’s different components, and enhance delivery partners’ collective understanding of COAST’s strategy and their role within it. Having the Component D Independent MEL delivery partner support FCDO to organise the PCF reduced the burden on FCDO. The clear message given by FCDO on the importance of collaboration has been proactively adopted by WorldFish, WEF and Itad, who have all continued to work closely since the PCF, holding regular calls and seeking and identifying collaboration opportunities. With Component A’s delivery partner coming onboard in year 2, it will be crucial to build on this experience to ensure collaboration across all COAST components in year 2.	A) COAST’s first PCF during year 2 (likely September/October 2024) should be timed to occur shortly after COAST’s Component A delivery partner has started. Its agenda should support relationship building across all COAST partners and help the refinement of COAST’s overarching strategy with all delivery partners now live. / B) The second PCF in late year 2 (likely February 2025) should aim to align with key moments in Component A’s mobilisation phase to finalise Component A’s delivery strategy to ensure all COAST delivery partners understand Component A plans and can input to strengthen collaboration. / C) FCDO should continue to monitor and support all COAST partners’ collaboration throughout year 2 through updates provided in regular reports and through performance KPIs within Component A Lead(s): COAST SRO (A, B, C), FCDO component leads (C), and Itad (A, B). Deadline: Throughout year 2.	The COAST Partner Coordination Forums were important tools for bringing together all COAST partners for a week of engagement and workshops. Itad lead the delivery of PCF’s in Year 3, which were valuable opportunities to build strategic coherence and collaboration between FCDO and partners. Recommendations 2. A and B were delivered in Year 2. Due o delays in mobilising Component A (see Output 7), collaboration between components proved challenging as WEF and WF were operating in different countries (e.g SEA vs East Africa). However now the COAST facility is mobilising, Year 3 will be important for ensuring collaboration between components. FCDO should continue to ensure 2.C is delivered in Year 3. / Next steps: We recommend maintaining 2.C for Year 3. Lead(s): COAST SRO. Deadline: Q2 Year 3.
Delays to WorldFish’s start date, staff recruitment and overall mobilisation due to delays in securing in country approvals resulted in underspend and slower than anticipated progress in some workstreams in year 1. This risk is anticipated to reduce in year 2 as all key recruitments have now been finalised and in-country approvals obtained. However, WorldFish have developed an ambitious year 2 delivery plan that aims to catch up on year 1’s delays. Whilst it is a justified and credible plan, there remains a risk of delivery and spend optimism bias and will require close monitoring, including to support delivery adaptation where needed, to achieve the targeted ambition and results in year 2.	FCDO and WorldFish should retain close oversight of Component B’s progress and spend rates during year 2 and take action to address areas of slower progress than planned. After 5 months of delivery, if WorldFish’s spend is forecast to be >10% below what was planned and not due to cost savings, FCDO and WorldFish shall develop a revised workplan for year 2’s Q3 and Q4 to improve delivery confidence. Lead(s): COAST SRO, FCDO WorldFish Lead, WorldFish Component B lead. Deadline: September 2024.	In year 2 there was a risk that WF would have a significant underspend based on Q1 spend. FCDO agreed that if they fell under 10% of their Q2 forecast then FCDO would ask them for a revised workplan with a view to reduce the budget. AS WF hit 99% spend in Q2, FCDO closely monitored their spend for Q3 which was fine so there was no need to review the workplan. WF managed to successfully hit 99% spend for the financial year and spend approx £7.4m. No further action required.
Securing host government approvals or buy in for workstreams under Components B and C have taken time. However, proactive efforts by WorldFish and WEF in these processes have helped establish good relationships with host governments that will benefit delivery. FCDO scoping visits to Indonesia, the Philippines, Vietnam, and Mozambique before and during year 1 revealed that Component A is likely to require a higher level of approval in some of these countries, likely Vietnam and Indonesia.	FCDO and the appointed Component A supplier must prioritise securing host government approvals for Component A to operate in each COAST priority country during the Mobilisation phase given the anticipated complexities and long timeframes. FCDO seniors and advisers both at post and in central teams should be asked to engage counterparts to help this process. Lead(s): COAST SRO and Component A delivery partner. Deadline: Throughout year 2.	Working collaboratively with host governments in the launch, co-design and approval of COAST Component A has been at the forefront of FCDO and DAI’s approach to mobilisation (Dec 24 to Apr 24). FCDO, DAI and host Government have delivered high-level and official-level launch events in Indonesia, Mozambique and Philippines and have prioritised co-designing COAST Country Strategies with relevant government stakeholders to build buy-in and ownership with partner governments, and to ensure COAST delivers against host government marine priorities. Following the completion of the co-design process in June 2025, FCDO and DAI will seek formal government approval of COAST Country Plans. Next steps: We recommend maintaining this recommendation for Year 3 until Government approval secured. Lead(s): COAST SRO. Deadline: Q2 Year 3.
There has been significant interest and early buy in from the Indonesian and Philippines governments into Component C’s BCAP project. COAST plans to deliver BCAP in all four COAST priority countries, requiring expansion to Vietnam and Mozambique where host government interest in blue carbon policy support from the UK has also been identified by posts and WEF. To align with COAST’s strategy, scoping and mobilising in both countries should begin in year 2. The FCDO-WEF accountable grant agreement is up to £4m and is valid until 31st March 2026 and may require a cost extension to fully deliver this ambition of delivery in all four countries.	FCDO should consider a cost extension to the accountable grant agreement with WEF for BCAP to accommodate BCAP’s full delivery in all four COAST priority countries. Any additional budget for BCAP should come from within COAST’s overall total budget of £154m through balancing across other COAST components. A decision should be taken by the end of October 2024 to give WEF greater certainty for year 3 planning. Lead(s): COAST SRO and FCDO BCAP lead. Deadline: Before the end October 2024.	A cost extension is under discussion and will be agreed early in Year 3. No further action required.
Lesson: As a new programme in a relatively new area of ODA spend for HMG with fewer previous programme examples and experiences to draw from, COAST will need to use in house and partner expertise to model annual planned results milestones for each logframe KPI given. Experience from delivery partners will be crucial to this to ensure planned milestones are achievable but ambitious and reflect the ToC and scale that COAST seeks to achieve. Itad’s role as COAST’s independent MEL lead and expertise will be important to support FCDO and COAST partners with advice in this process.	A) WorldFish, WEF and Itad shall propose ambitious but achievable annual milestones for all relevant logframe KPIs for FCDO to agree before the end of September 2024. / B) Within 4 weeks of contract award, FCDO and the Component A supplier, with Itad’s support, shall agree milestones for COAST year 2 for Component A, and; / C) shall agree ambitious but achievable annual milestones for all relevant logframe KPIs for all programme years before the end of Component A’s mobilisation phase. / Lead(s): COAST SRO and FCDO COAST component leads (A, B, C); WorldFish (A); WEF (A); Itad (A, B, C); Component A supplier (B, C). Deadline: 30th September (A); Dependent on Component A contract award (B, C).	Actions under this recommendation are set out in Section C - Output 7 and Section G, monitoring and evaluation. Recommendations 6, A, B and C have been met in Year 2 and no further action required. New recommendations for M&E have been made for Year 3, see Section A.

Annex B – COAST Theory of Change approved April 2024

Annex C – COAST Year 2 GEDSI Activities
Asia-Africa BlueTech Superhighway, WorldFish
The Asia-Africa BlueTech Superhighway (AABS) embedded Gender Equality, Disability, and Social Inclusion (GEDSI) across all programme components, ensuring that inclusive practices were not only a cross-cutting theme but a core operational principle. AABS began the year with a GEDSI planning and self-assessment session in Penang, followed by a regional training workshop in Nairobi that brought together 18 participants from seven countries to strengthen capacity in gender-responsive approaches. The programme also supported graduate students conducting gender-focused research in Kenya and Tanzania, contributing to a stronger evidence base for inclusive aquatic food systems. South-South knowledge exchanges further promoted inclusivity by involving women researchers and practitioners in peer learning and regional collaboration. Across all countries, AABS ensured GEDSI principles were integrated into digital monitoring systems, training sessions, and policy development—laying the groundwork for more inclusive, resilient, and equitable aquatic food systems.
Country Updates:
- In Bangladesh, AABS piloted Integrated Multi-Trophic Aquaculture (IMTA) systems designed to improve employment, nutrition, and income for poor coastal women. These community-led pilots in the Maheshkali channel were informed by gender-disaggregated socioeconomic surveys that identified key barriers such as limited training, financial constraints, and socio-cultural norms. Under its coastal conservation workstream, AABS assessed alternative livelihood programmes for fishers during seasonal bans and developed policy recommendations emphasizing gender-inclusive approaches and targeted subsidies for marginalized groups.
- In Kenya, a job opportunity study identified specific roles for women in IMTA systems and highlighted barriers such as cultural norms and limited access to capital. A gender-responsive assessment under the Fish Loss and Waste work package revealed that women processors faced up to three times higher postharvest losses than men, largely due to exclusion from decision-making and limited access to preservation technologies. Youth engagement was also prioritized through participatory research and consultations to inform future interventions.
- In Tanzania, stakeholders at a national Theory of Change workshop prioritized women and youth participation in postharvest decision-making. AABS supported women seaweed farmers with training and improved drying infrastructure, particularly in Mafia Island and Kilwa, where climate-smart technologies were introduced to reduce losses during the rainy season. The programme also monitored gleaning fisheries, small-scale, shore-based harvesting activities typically carried out by women, helping to elevate their visibility in coastal food systems and inform equitable policy design.
- In Mozambique, AABS supported women-led seaweed farming through solar drying technology and microfinance access, addressing infrastructure gaps that disproportionately affect women. Field assessments also documented women’s central role in fish processing and marketing, while case studies on community-led conservation (e.g., octopus closures and oyster farming) highlighted women’s active participation.
- In Nigeria, an employment study revealed significant gender and age disparities in aquaculture recruitment. AABS responded by conducting focus group discussions with women and youth, using their insights to inform the design of inclusive IMTA demonstration sites.
Blue Carbon Action Partnership, WEF
In Year 2, BCAP strengthened its commitment to gender equality, disability, and social inclusion (GEDSI) across global and national initiatives. Key achievements included the launch of the High-Quality Blue Carbon Practitioners Guide, which integrates GEDSI principles into project design, and a forthcoming scientific paper highlighting the importance of gender in blue carbon success. In Indonesia and the Philippines, national partnerships ensured inclusive stakeholder engagement, with planned GEDSI reviews of draft blue carbon roadmaps to guide equitable implementation. These efforts are helping ensure that blue carbon investments benefit coastal communities, especially women and marginalized groups.