## Logframe (last updated Sept 25)
SCALE Logframe [last updated Sept 2025] - additional updates needed if no-cost extension is approved later in 2025, which will change outer year milestones 4 and 5
PROJECT TITLE
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
Faster global progress to get millions more disadvantaged children, especially marginalised girls, enrolled into school and achieving foundational learning. | Proportion of TA and innovative partnerships countries that are on target (scoring 'average' or 'faster progress') to meet or exceed national benchmarks for SDG4 indicators: (a) out of school rate and (b) number of children meeting reading minimum proficiency levels by end of primary (disaggregated by sex, disability status and income group where available) | Planned | n/a | To populate once research partner is on board. | To populate once research partner is on board. | Research partner and EDT to set benchmarks for first two innovative partnerships. EDT to set benchmarks for TA assignments in their annual report. | To populate once baselines are set | To populate once baselines are set | 2028
|  | Achieved |  | n/a | n/a
Source
UIS / GEMR SDG4 annual country scorecards for SDG indicators 4.1.1 and 4.1.4 disaggregat by sex, disability status and income group where available, research partner evaluation framework and EDT annual reports.
Long term outcome | Outcome Indicator 1 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date) | Assumptions
Reformed education systems delivering sustainable outcomes at-scale which improve teaching and learning for disadvantaged children, especially girls. | Proportion of SCALE countries where an innovative partnership is a) established on the pathway to scale, as evidenced by a rating of 2 or above on the "scaling progress metric" and b) where they are scored a rating of 2 and above and likely to reach higher or severely disadvanataged children. | Planned | 0 | n/a | n/a | n/a | a) 20% | a) 40% b) 20% | 2028 | Time delay in intermidate outcomes to the longer term outcome, with only a few innovative partnerships funded getting to this stage by the end of the programme. Third-party evaluator is in place to help measure and collect change stories.
|  | Achieved |  | n/a | n/a
Source
Grading will be informed by progress recorded using the Multidimensional framework for assessing progress to scale (designed by our third party evaluator). Final grading will be agreed during a SCALE MEL workshop (scaling change story workshop) conducted with FCDO posts, research partner and IPs, facilitated by SCALE MEL team during country scaling roadmap development and review.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Intermediate outcome 1 | Outcome Indicator 1 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date) | Assumptions
Technical assistance (TA) is applied to strengthen education systems and drive cost – effective expenditure | Percentage of TA projects that record a contribution to improving equitable learning outcomes at scale, of moderate or major significance in a verified change story (cumulative). | Planned | 0 | n/a | 20% | 60% | 80% | 80% | 2028 | TA will run for the life of the project, but impact will occour outside of the programme lifetime. PIRs will be recuited in early 2024 and in place for the lifetime of the programme. Third-party evaluator is in place to help measure and collect change stories and validate grading.
|  | Achieved |  | n/a | Milestone achieved. One third-party assessed change story for a completed TA assignment, which has been validated as being of ‘moderate significance’.
Source
Assignment package signed off by EDT & FCDO defining the technical area / ‘system’ and success criteria for 'moderate' and 'major' change story co-produced by EDT and FCDO Education Adviser, and scored against third party evaluator rubric. Number and proportion of projects are reported on through MEL framework. Change stories or assignment completion forms for each assignment are submitting to third party evaluator for grading.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
Intermediate outcome 2 | Outcome Indicator 2.1 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date) | Assumptions
Scale up of cost-effective education interventions initiated and finances secured from domestic and/or strategic partner resources. | Proportion of country scaling roadmaps with annual progress rated green or green-amber. | Planned | 0 | n/a | n/a | First two innovative partnership scaling roadmaps designed. | 50% | 75% | 2028 | Time lag in commitments from donors, due to innovative partnerships taking 2-3 years to be implemented. That not all innovative partnerships will be successful, have strategic partner buy-in or be taken to scale. We influence FCDO's main development partners to fund scale up, alongside governments.
|  | Achieved |  | n/a | n/a
Source
Annual progress updates from research partner and third party evaluater for live innovative partnerships
| Outcome Indicator 2.2 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
| # of innovative partnerships where there is evidence of adequate finances mobilised from partner government and/or strategic partners to support scale-up (cumulative) | Planned | 0 | n/a | n/a | n/a | 2 | 4 | 2028
|  | Achieved |  | n/a | n/a
Source
Evidence from partners e.g. WB Project Appraisal Documents (PAD) committment. Third party evalutation. Scaling roadmaps.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date) | Assumptions
Technical assistance is used | Package of TA support from in-house and external experts designed, mobilised, and available to the FCDO network. | Planned | Centrally managed TA not available | Design: • TA scoping exercise completed to understand demand across FCDO network • Job Specs developed for PIRs • Agreements with technical scopes of work agreed with external partners • Process for responding, prioritising and allocating TA support requests under Centre of Expertise Mobilisation: • Recruitment/onboarding of core PIRs (up to 4) • Workplan for inception phase agreed with external partners and core team available. Available: • Responsive TA package of support launched for the FCDO network | Further design and adaptation: • TA strategy and approach (inc PIR recuitment and approach to demand) revised and adapted according to lessons learned from Year 1, including on GEDSI. • New agreements signed for further TA support on other areas of demand. • GEDSI TA mainstreaming actions set out in the SCALE GEDSI Strategy on track. • Development of TA menu of options and TA offer under the Centre of Expertise for Education. | • Updated PIR staffing and recruitment plan, with action underway to recuit vacant positions to ensure adequate expertise, including on GEDSI. • GEDSI TA mainstreaming actions set out in the SCALE GEDSI Strategy on track. • Plan for offering a deep/longterm TA offer alongside the Centre of Expertise. | n/a | n/a | 2025 | TA offer will be iterated continously once live and additional agreements added until the end of Y2. We can recruit PIR's, there are advisers availble and interested in the roles and there is enough budget to cover the permenant increase in headcount within FCDO. Sufficient demand and opportunities for SCALE​ Co-ordination structures within the Centre of Expertise are effective at managing TA offers across FCDO​ Internal and external TA providers help to identify and build demand for TA. TA providers and PIRs are chosen with a skillset to respond to the needs of FCDO advisers and staff.
|  | Achieved |  | Design: Achieved: • Internal TA scoping exercise completed in May 2023. • Job specifications for the first four PIRs developed. • TA agreement in place with Education Development Trust (EDT). • Interim process for triaging and prioritising TA in design, to be finalised by end May 24. Mobilisation:Achieved; • Three PIRs recruited in September-November 2023. Two started in January 24 and third will start in July 2024. • Inception workplan agreed with EDT. Availble: Partly achieved. • Initial TA package to be launched across FCDO network by end March 24 and trialled during the programme inception phase. Full TA package will be launched in summer 2024. | Milestone achieved: - TA strategy was revised following onboarding of the G6 PIR in line with lessons learnt from previous year, including to prioritise pilots and ensure delivery despite PIR recruitment challenges outside the programme’s control. - GEDSI strategy was developed, finalised, and rolled out to benefit SCALE and FCDO’s broader centrally managed education programmes. Refreshed scoping documents include a GEDSI section to ensure mainstreaming from the start. - New downstream partner agreements with Teaching at the Right Level (TaRL) Africa and Pratham International mobilised through EDT to enable SCALE to respond to significant demand on this approach (TaRL already in place, Pratham International by end of March) - The TA menu of options has been developed and will be used in our proactive communications of the SCALE TA offer in year 3 - SCALE is advertised through the Centre of Expertise and accessible to the full FCDO network through this route.
Source
Surveys to advisers, approval of job sepcs, approval of external TA provider proposals, TA strategy and approach documented, workplans, live TA offer on the Centre of Expertise which can be linked.
| Output Indicator 1.2 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
| # of opportunities identified and/or requested for TA (cumulative) | Planned | Centrally managed TA not available | • 3 TA drop in sessions held for the network to build demand • Strategic mapping of multilateral and global fund pipeline developed to identify opporuntities for engagement. • 4 (c. 20% of advisers) opportunities, disaggregated by requested vs identfied | • 12 TA assignments identified and/or requested (cumulative) | • 20 TA assignments identified and/or requested (cumulative) | • 25 of TA assignments identified and/or requested (cumulative) | TBC whether TA will be required in the final year | 2028
|  | Achieved |  | Milestone achieved. • First TA and pilot drop-in held in Sept 2023 and two planned for March 2024 • Initial multilateral mapping in progress. • Five TA opportunities identified | Milestone achieved: - 13 assignments have been identified and/or requested
Source
Meeting minutes/presentations from TA drop ins, strategic mapping document, TA tracker
| Output Indicator 1.3 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
| # of TA projects a) actioned and b) completed (cumulatative) | Planned | Centrally managed TA not available | • 4 TA Terms of Reference (ToRs) agreed and initiated • 0 TA projects completed. | • a) 9 actioned and b) 5 completed • 50% assignment demonstrate a logical chain to impacts for children experiencing significant, high or severe forms of discrimination and marginalisation. •50% assignment GEDSI sensitive or transformative | • a) 20 actioned and b) 13 completed • 70% assignments demonstrate a logical chain to impacts for children experiencing significant, high or severe forms of discrimination and marginalisation. • 50% assignments GEDSI sensitive or transformative | • a) 25 actioned and b) 25 completed • 70% assignments demonstrate a logical chain to impacts for children experiencing significant, high or severe forms of discrimination and marginalisation. •70% assignments GEDSI sensitive or transformative | TBC whether TA will continue into final year. | 2028
|  | Achieved |  | Milestone partly achieved: • Three ToRs currently in development, on track by end April. | Milestone achieved: -12 actioned - 5 expected to be complete by end of March 2025. At time of writing, one complete (A04), but A01, A02, A03 and A06 are complete/wrapping up. - More than 50% of assignments are demonstrating a logical chain to children experiencing high or severe forms of discrimination and marginalisation - More than 50% of assignments are GEDSI sensitive or transformative
Source
TA tracker. ToRs agreed by FCDO. Final reports for projects submitted.
| Output Indicator 1.4 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
| Proportion of TA assignments that meet FCDO's quality criteria | Planned | Centrally managed TA not available |  |  | 80% | 85% | 90% | 2028
|  | Achieved |  | n/a - metric introduced Sept 2025 | n/a - metric introduced Sept 2026 |  | n/a - metric introduced Sept 2028 | n/a - metric introduced Sept 2029
FCDO quality critiera signed off with EDT after each quarter
IMPACT WEIGHTING (%) | Output Indicator 1.5 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
35% | Proportion of (a) users and (b) providers that rate TA as satisfactory or better. | Planned | Centrally managed TA not available | n/a - TA service only just operationalised. | 75% | 80% | 85% | 90% | 2028
|  | Achieved |  | N/A until next Annual Review | Milestone achieved: - 100% - 1 assignment (A04) has gone through the full assignment cycle. 6 out of 6 respondents to the satisfaction survey for A04 rated the TA to be satisfactory or better.
Source
Central survey issued by TA provider or FCDO to users and providers
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 - 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date) | Assumptions
Test-learn-adapt innovative partnerships are complete | # of innovative partnerships a) identified, b) scoped and c) selected (cumulative) | Planned | No pilots identified or selected. | • Test-learn-adapt pilot scoping and selection process agreed by GED SLT • 4 potential test-learn-adapt pilots identified, concept notes drafted and presented to challenge board • 2 test-learn-adapt Accelerator Pilots selected/agreed by SRO and HoD | • a) 6 potential test-learn-adapt pilots identified • b) 6 test-learn-adapt pilots scoped, concept notes drafted and presented to challenge board.. • c) 4 test-learn-adapt Pilots selected/agreed by SRO and HoD • 2 selected pilots expected to reach children experiencing at least significant level of discrimination/marginalisation • 4 selected pilots expected to be at least GEDSI sensitive | • a) 4 potential test-learn-adapt innovative partnerships pilots identified. (cumulative) • b) 8 3 test-learn adapt innovative partnerships pilots scoped, concept notes drafted and presented to advisory group (cumulative) • c) 3 test-learn-adapt innovative partnerships pilots selected/agreed by SRO and HoD (cumulative) •2 selected innovative partnerships pilots expected to reach children experiencing at least significant level of discrimination/marginalisation and 1 experiencing severe level (cumulative) • 3 selected innovative partnerships pilots expected to be GEDSI sensitive and 1 GEDSI transformative.(cumulative) | • a) 5 potential accelerator test-learn-adapt innovative partnerships pilots identified. (cumulative) • b) 5 test-learn adapt innovative partnerships pilots scoped, concept notes drafted and presented to advisory group (cumulative) • c) 5 accelerator test-learn-adapt pilots innovative partnerships selected/agreed by SRO and HoD (cumulative) •3 selected innovative partnerships pilots expected to reach children experiencing at least significant level of discrimination/marginalisation and 1 experiencing severe level (cumulative) • 5 selected innovative partnerships pilots expected to be GEDSI sensitive and 1 GEDSI transformative. (cumulative) | Need to update if no-cost extension | 2027 | We can identify enough high potential innovative partnerships, despite changing global architeture for education.​ Commitment to dual-lock agreement between HQ and posts.​ The majority of pilots are sussessful, but that some may make less progress and/or won't be taken to scale. MEL of the pilots is robust and the results influence the direction and implementation of scaling. Innovative partnerships are 2-3 years long. Innovative partnerships selected won't have reported on teaching and learning in the first year due to being early in implementation.
|  | Achieved |  | Milestone partly achieved: • Scoping and selection process for pilots developed and agreed by GED SLT on 6 July 2023. • Six potential test-learn-adapt pilots identified; four concept notes drafted and two in development; two concept notes presented to Challenge Group in November 2023. • Following feedback from the Challenge Group, work is underway to further develop the concept notes. | Milestone partially met: - So far there have been 6 pilots identified. Further design is underway in 2 other countries to identify pilot opportunities. - 4 test-learn-adapt pilots have been scoped and concept notes presented to the challenge group. - 1 pilot has been selected and agreed by SRO and 2 pilots expected to be agreed between March and April. - All 3 selected/proposed pilots are expected to reach children experiencing at least significant levels of discrimination/marginalisation - All selected pilots are expected to be GEDSI sensitive. 1 of the pilots could be GEDSI transformative based on the pilot geography and aims to reach out-of-school children.
Source
Minutes from SCALE Challange Board. Approval emails from HoD.
| Output Indicator 2.2 |  | Baseline | Milestone 1 - 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
| # of innovative partnerships designed and ready for implementation | Planned | No innovative partnerships in design | • 2 test-learn-adapt pilots proposal (workplan, budget) with research study design agreed between FCDO and implementing partners/ relevant partner governments • 1 test-learn-adapt pilot mobilised including due diligence assesemnts (DDAs) completed , dual-lock PM set up between GED and Post, agreements signed | • 2 test-learn-adapt pilot proposals (workplan, budget) with high level research study design developed between FCDO and implementing partners/ relevant partner governments • 2: new test-learn-adapt pilots underway including due diligence assesemnts completed , dual-lock PM set up between GED and Post, agreements signed. • Quality GEDSI analysis undertaken and clear GEDSI objectives set (targeted or mainstreamed) for all pilots | • 2 test-learn-adapt proposals (workplan, budget) with high level research study design developed between FCDO and implementing partners/ relevant partner governments • 2 new test-learn-adapt innovative partnerships underway including due diligence assesemnts completed , dual-lock PM set up between GED and Post, agreements signed •Quality GEDSI analysis undertaken and clear GEDSI objectives set (targeted or mainstreamed) for all innovative partnerships | • 3 test-learn adapt proposals (workplan, budget) with research study developed between FCDO and implementing partners/ relevant partner governments • 3 new test-learn-adapt innovative partnerships underway including due diligence assesemnts completed , dual-lock PM set up between GED and Post, agreements signed •Quality GEDSI analysis undertaken and clear GEDSI objectives set (targeted or mainstreamed) for all innovative partnerships | Need to update following no-cost extension | 2027
|  | Achieved |  | Milestone not achieved: • No progress as test-learn-adapt pilots have not been selected (as outlined above). | Milestone partially met: - Partially met/on track: 1 pilot proposal (including workplan, budget) and high-level design is awaiting signature. 1 proposal document still underway – aiming for completion by end of April. - Partially met/off-track: 1 due diligence completed. Dual lock agreement and implementation is awaiting agreement signature. 1 pilot is aiming for due diligence to be completed end of April and for implementation to begin May/June. - Partially met/on-track: GEDSI analysis will be completed shortly for first 2 pilots.
Source
Pilot workplans, budgets, DDA reports, signed dual-lock agreement, signed accountable grants/contracts, GEDSI analysis
| Output Indicator 2.3 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
| # of test-learn-adapt innovative partnerships completed and scaling roadmaps produced with recommendations for scaling (cumulative) | Planned | No pilots completed | n/a | 2 pilots that are on-track to meet agreed annual workplan deliverables | 2 innovative partnerships on track to meet agreed annual targets | 5 innovative partnerships on track to meet agreed annual targets. | 5 innovative partnerships completed. Need to update if no cost extension | 2028
|  | Achieved |  | n/a | Milestone partially met: - 2 pilots expected to start shortly. Both have draft workplans set out which will be agreed and monitored monthly.
Source
Pilot completion report and scaling roadmaps completed which include recommendations for scaling.
| Output Indicator 2.4 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
| a) The design of a innovative partnership includes test-learn-adapt methods and b) active innovative partnerships are adapting based on learnings (cumulatative) | Planned | No implementation of pilots | a) 2 pilots designed with MEL plans/processes that will use real-time data to improve performance | a) 2 pilots designed with MEL plans/processes that will use real-time data to improve performance | a) 2 innovative partnerships designed with MEL plans/processes that will use real-time data to improve performance b) 2 innovative partnerships actively practicing test-learn-adapt piloting (cumulative). (inc whether pilots are adapting based on data related to results for marginalised children where relevant/targeted) | b) 5 innovative partnerships actively practicing test-learn-adapt piloting - (inc whether pilots are adapting based on data related to results for marginalised children where relevant/targeted) | b) 5 innovative partnerships actively practicing test-learn-adapt piloting (of those live in the final year) - (inc whether pilots are adapting based on data related to results for marginalised children where relevant/targeted) | 2028
|  | Achieved |  | Milestone not achieved: • No progress as test-learn-adapt pilots have not been selected. | Milestone partially met: Research partner IPA in place and MEL plan for 2 pilots in design. Both pilot concept notes/proposals include clear learning questions and MEL approaches.
Source
Reliant on IPA Tracking research, MEL and TA activities documented through pilot research and evaluation workplans, meeting notes from 'pause and reflection sessions', use of MEL data generated during implementation, pilot costing and reporting documentation.
| Output Indicator 2.5 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
| # of innovative partnerships generating disaggregated cost data to inform cost-effectiveness or cost-optimization analysis | Planned | No baselines set. | To populate once pilots are selected and baselines are set | Research partner to include methodology/approach to collecting this data (inc further disaggregation when relevant and possible to demonstrate factors of marginalisation). | All innovative partnerships include cost data collection and analysis in their research plans | Cost data collected in 1-2 innovative partnerships and used to inform ongoing pilot implementation or adaptation discussions | Cost data collected in ongoing pilots and used to inform ongoing pilot implementation or adaptation discussions | 2028
|  | Achieved |  | n/a | Milestone achieved: Research partner IPA identified and accountable grant in place. Approach to measure cost-effectiveness set out in evaluation framework and workshopped during their February inception workshop to ensure coherence with complementary work, e.g. via the WWH-GE and D4FL.
Source
Research protocols and instruments with costing modules or data collection strategies; Meeting notes and minutes from pause-and-reflect sessions, scaling and influencing plans that reference costing
IMPACT WEIGHTING (%) | Output Indicator 2.6 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
50% 60% | Proportion of test-learn-adapt innovative partnerships which are effective in improving teaching and/or learning | Planned | No pilots in implementation. | n/a | Research partner to include methodology/approach to collecting this data (inc further disaggregation when relevant and possible to demonstrate factors of margionalisation). | Evaluation framework finalised; Research and Learning Designs for first two innovative partnerships include plans for measuring teaching and/or learning outcomes. | Learning and teaching data collected in 1-2 innovative partnerships to inform ongoing pilot implementation or adaptation discussions | Learning and teaching data collected in ongoing innovative partnerships to inform ongoing pilot implementation or adaptation discussions | 2028
|  | Achieved |  | n/a | Milestone achieved: Common metrics to measure pilot effectiveness on teaching and learning set out in research partner evaluation framework. During inception the team workshopped this approach to coordinate with efforts across other FCDO programmes, notably D4FL and the WWH-GE. The evaluation framework also includes GEDSI metrics in line with the SCALE strategy.
Source
Data and learnings (from endline assessments and interim learning cycles) included in pilot reporting which show a positive increase in teaching and/or learning levels.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date) | Assumptions
Strategic partners commit to action to finance longer term scaling and support the learning at scale pathway. | # of strategic partners engaged and actively contributing to SCALE and the learning at scale pathway (cumulatative) | Planned | No strategic partners engaged on SCALE. | • 8 strategic partners engaged on SCALE through introductory meetings • Strategic partnership strategy developed (in collaboration with other FCDO programme teams) outlining more detailed approach to partnering and influencing objectives for each strategic partner (for future milestone targets) | • 5 partners engaged and commited to collaborating on SCALE in country through pilots and/or TA. • Joint WB-FCDO SCALE partnership approach agreed and implementation underway • 2 pilots include stakeholder partnership approach/plan in their scaling roadmaps | - 2 strategic partners providing in kind collaboration on TA leverageing multilateral/Strategic Partner funding (cumulative) - 2 strategic partners actively participating in Innovative partnerships (cumulative) | - 10 strategic partners providing in kind collaboration on TA (cumulative) - 4 instances of SCALE TA leverageing multilateral/Strategic Partner funding (cumulative) - 5 strategic partners actively participating in Innovative partnerships (cumulative) | - 15 strategic partners providing in kind collaboration on TA (cumulative) - 6 Instances of SCALE TA leverageing multilateral/SP funding (cumulative) - 5 strategic partners actively participating in Innovative partnerships (cumulative) | 2028 | UK objectives align with those of other funders.​ Funding availability and will from partnerships​, despite declining ODA Staff time and political capital to build partnerships​ Partnerships to include a mix of government, donors and private philanthropists. Assumes all innovative partnerships have strategic partnerships Events can be either FCDO or partner led. Innovative partnerships will need at least a year before showing credible financial buy-in from partnerships.
|  | Achieved |  | Milestone partly achieved: • Six strategic partners engaged: Gates Foundation, World Bank, USAID, BHP Foundation, Pousaz Foundation, Royal Norwegian Embassy in Malawi. Meetings scheduled for March 2024 with GPE, Aga Khan Foundation following introductory discussions at BE2 Evidence in Education event in January 2024. • Strategic Partnership Strategy outline has been drafted, to be completed by May 2024. | Milestone partially met: - Met: We have engaged many partners who are interested and aligned with the SCALE approach. We have prioritised in-country relationships linked to pilots and TA. Partners engaged/committed to collaborating include: GPE, UNICEF, GIZ, Gates - Partially met: Joint WB: Central SCALE engagement with Africa Regional Practice managers, and ongoing engagement through the Foundation Learning Compact. At a country level we have engaged with the WB to ensure alignment and collaboration. It has not been possible to pursue a specific WB partnership pilot with current staff resourcing in the reporting period. - On track: partnership plan and scaling roadmap underway for 1 pilot and will be finalised by June in partnership with IPA. For pilot 2 this will be developed as part of design during their inception, from May onwards.
Source
Meeting minutes. Strategic partnership strategy. Scaling roadmap plans. TA and pilot trackers.
| Output Indicator 3.2 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
| # of evidence events on scaling for strategic partners to influence the global evidence base on scaling. | Source | n/a | 1 event | 2 events | 2 events (global) | 2 events (global) 1 per each live innovative partnership | 2 events (global) 1 per each live innovative partnership | 2028
|  | Achieved |  | Milestone achieved: • FCDO-Gates Foundation co-convened an evidence event on Scaling Foundational Learning Interventions, attended by implementing partners, researchers, and some Development Partners in September 2023. • Internal FCDO evidence workshop on scaling held with academics in September 2023. | Milestone achieved: - SCALE presented at the TaRL Africa conference in Nairobi, on a panel focused on funders’ approach to scaling. - There will be a presentation on scale at CIES conference 2025 in March, as part of a funders and implementers panel discussing the challenges to scaling.
Source
FCDO Events tracker, Research partner event tracker
IMPACT WEIGHTING (%) | Output Indicator 3.3 |  | Baseline | Milestone 1 - Mar 24 | Milestone 2 - Mar 25 | Milestone 3 - Mar 26 | Milestone 4 - Mar 27 | Milestone 5 - Mar 28 | Target (date)
15% | # of knowledge/learning products produced to influence the global evidence base on scaling | Planned | Low # knowledge products exist on scaling from other organisations. | Research and evalutation partners develop a MEL/research framework for evaluating and adapting pilot interventions. | Research partner in place and inception workplan produced with milestones for research products included. | Research outputs planned for inititial innovative partnerships Portolio level workstream designed and first outputs in progress. | 1 output per each ongoing innovative partnership 1 from portfolio-wide workstream | 1 output per each ongoing innovative partnership, and 2 from portfolio-wide workstream | 2028
|  | Achieved |  | Milestone partly achieved: • MEL supplier contract signed in February 2024. MEL framework for the programme will be finalised during their inception by end April 2024. • Concept note for research component drafted and scoping for partners undertaken. | IMilestone achieved: PA agreement signed on 22nd November, inception workshop conducted in February 2025 and plan for knowledge products produced in conjunction with other FCDO funded research/global public goods.
Source
Research publications, MEL reports, synthesis reports written by third-party evaluator and/or research component partners. A robust QA process must have been followed.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) |  |  |  | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## Data sources
Number | Indicator name | Definitions | Annual or cumulative | Source | Frequency of collection
Impact Indicator 1 | Proportion of TA and pilot countries that are on target (scoring 'average' or 'faster progress') to meet or exceed national benchmarks for SDG4 indicators: (a) out of school rate and (b) number of children meeting reading minimum proficiency levels by end of primary (disaggregat by sex, disability status and income group where available) | This indicator uses SDG4 scorecard progress reports for 4.1.1.b.r (reading by end primary) and 4.1.4.b (out of school rate, primary). To count as being on target to meet or exceed national benchmarks, a country must be rated as making 'fast' or 'average' progress, as indicated in the 'national benchmarks' dashboard at https://geo.uis.unesco.org/sdg-4-scorecard. | Annual | UIS/GEMR SDG4 scorecard. https://geo.uis.unesco.org/sdg-benchmarks , research partner evaluation framework and EDT annual reports | Annual
Long term outcome 1 | Proportion of SCALE innovative partnership countries where a pilot intervention is a) established on the pathway to scale, as evidenced by a rating of 2 or above on the "scaling progress metric" and b) where they are scored a rating of 2 and above and likely to reach higher or severely disadvanataged children. | A multidimensional set of scales for assessing the progress of pilots along the FCDO pathway to scaling learning outcomes, taking into account intervention characteristics, the national adoption contexts and support from strategic partnerships. The full matrix for grading can be found in the summative evaluation plan. | Annual | Grading will be informed by progress recorded using the Multidimensional framework for assessing progress to scale. Final grading will be agreed during a SCALE MEL workshop (scaling change story workshop) conducted with FCDO posts and IPs, facilitated by SCALE MEL team during country scaling roadmap development and review. | Annual
Intermediate outcome 1 | Percentage of TA projects that record a contribution to improving equitable learning outcomes at scale, of moderate or major significance in a verified change story (cumulative). | Emerging - Education system leaders and/or their development partners show positive engagement in processes contributing to improving equitable learning outcomes at scale due to a SCALE TA project. Moderate - Education system leaders and/or their development partners commit to take actions contributing to improving equitable learning outcomes at scale as a result of a SCALE TA project. Major - Education system leaders and/or their development partners invest financial/ human or political resources in reforms contributing to improving equitable learning outcomes at scale as a result of a SCALE TA project. | Annual | Third party evaluator change story tracker | Quarterly
Intermediate outcome 2.1 | Proportion of country scaling roadmaps with annual progress rated green or green-amber. | Research partner to set metrics | Annual | Scaling roadmaps | Annual
Intermidate outcome 2.2 | # of innovative partnerships where there is evidence of adequate finances mobilised from partner government and/or strategic partners to support scale-up | Adequate finances mobilised: Financial committments in partner government or stratergic partners plans match scaling roadmap targets. | Cumulative | Scaling roadmaps and other written commitments evidenced | Annual
Output 1.1 | Package of technical assistance support from in-house and external experts designed, mobilised, and available to the FCDO network |  | Annual | A series of approvals documenting progress | Quarterly
Output 1.2 | # of opportunities identified and/or requested for TA (cumulatative) |  | Cumulative | TA tracker - hosted by EDT | Quarterly
Output 1.3 | # of TA projects a) actioned and b) completed (cumulatative) |  | Cumulative | TA tracker - hosted by EDT | Quarterly
Output Indicator 1.4 | Proportion of TA assignments that meet FCDOs quality criteria |  | Annual | FCDO quality critiera | Annual
Output Indicator 1.5 | Proportion of (a) users and (b) providers that rate TA as satisfactory or better. | The satisfaction survey contains nine questions. All question responses are provided against a six point Likert scale of: 1 – Very dissatisfied, 2 – Dissatisfied, 3 – Neither satisfied nor dissatisfied, 4 – Satisfied, 5 - Very satisfied, N/A - Not applicable | Annual | Survey results - collected by EDT | Quarterly
Output 2.1 | # of innovative partnerships a) identified, b) scoped and c) selected. |  | Annual | Pilot tracker - hosted by FCDO | Annual
Output 2.2 | # of innovative partnerships designed and ready for implementation |  | Annual | PM and commercial deliverables | Annual
Output 2.3 | a) The design of a pilot includes test-learn-adapt methods and b) active pilots are adapting based on learnings. | Quality of implementation of 'test-learn-adapt' methods measurement: to design | Cumulative/live pilots | Quality of implementation measure - research partner reports on this | Annual
Output 2.4 | # of innovative partnerships completed and roadmap produced with recommendations for scaling | Roadmap for scaling: Document produced with pilot completion report, which includes recommendations and timelines for completition for scaling | Cumulative | Pilot completion reports and scaling roadmaps. | Annual
Output 2.5 | Number of innovative partnerships generating disaggregated cost data to inform cost-effectiveness or cost-optimization analysis | Research partner evalution framework | Cumulative | Research protocols and instruments with costing modules or data collection strategies; Meeting notes and minutes from pause-and-reflect sessions, scaling and influencing plans that reference costing | Annual
Output 2.7 | Proportion of innovative partnerships which are effective in improving teaching and/or learning. | Pilots which are effective: Data and/or learnings which show positive increases in teaching and/or learning levels (definition not yet defined). | Annual | Data and learnings (from endline assessments and interim learning cycles) included in pilot reporting which show a positive increase in teaching and/or learning levels.
Output 3.1 | # of strategic partners engaged and actively contributing to SCALE and the learning at scale pathway (cumulatative) |  | Annual | Scaling roadmaps EDT annual reports | Annual
Output 3.2 | # Evidence events on scaling for strategic partners to influence the global evidence base | Events which FCDO has either presented at or hosted. | Annual | Events tracker (FCDO and research partner) | Annual
Output 3.3 | # Knowledge/learning products produced to influence the global evidence base on scaling |  | Annual | Knowledge products tracker (Research partner) | Annual

## VfM indicators
VFM indicators
Area | Number | Indicator | Precise definition | Rationale | Data necessary | Who is responsible? | When?
Economy | 1.1 | Component 1 spend and cost | Component spend will be on-budget spend including allocation of SCALE team time. We will also make estimates of off-budget costs such as partner time and costs, user costs and averted costs, to calculate total component cost. | Necessary to collect to calculate higher order metrics | Completion of data collection templates by FCDO and partners including: quarterly financial data, estimates of staff time for each component (including non-SCALE staff such as posts), assessment of partner costs, user costs and averted costs | SCALE MEL team to calculate following collection of completed cost capture templates | October each year (Q3-Q2)
| 1.2 | Component 2 spend and cost
| 1.3 | Component 3 spend and cost
| 1.4 | % PM spend | Total spend on SCALE PM (cost category 1) / Total SCALE (on-budget) spend | Internal PM was cited in the BC as a VfM measure
| 1.5 | Average consultant fee | Average international consultant fee Average national consultant fee | Needs to be compared to impact to understand VfM but interesting to track variations in fee rates and potentially identify any excessive spend.
Efficiency | 2.1 | Cost per completed TA assignment | Total cost will be estimated as the sum of three components: - direct on-budget costs (TA only) - other on-budget costs (e.g. management contributions) - estimates of off-budget costs | Key efficiency metric Also allows a comparison between in-house and external TA unit costs |  |  | Report on completed TA assignments October each year
| 2.2 | Cost per pilot | Total cost will be estimated as the sum of three components: - direct on-budget costs - other on-budget costs (e.g. TA contributions) - estimates of off-budget costs For uncompleted pilots, we will consider forecast costs and actual vs forecast for the period under review. | Key efficiency metric. Allows a comparison between costs of different types of pilot (location, intervention type, stage of scaling) |  |  | October each year (reporting on Q3-Q2 costs and costs to date)
| 2.3 | Speed to start | Time from identification of potential pilot to project start. We will also consider the average time (months) from the Business Case approval date to pilot start. | Since SCALE is a relatively short programme compared to the scaling progress, speed to start is essential if pilots are to make significant progress. | Date of pilot identification Date of pilot start | FCDO (pilot scaling outcomes database) | October each year (reporting on all pilots started that year)
| 2.4 | Speed to failure | For any pilots that are judged unsuccessful, how long did it take to recognise this and cease funding? Start time: start of pilot End time: cessation of funding Qualitative assessment will also consider the decision making and bureaucratic processes involved. | Aborting unsuccessful pilots in a timely fashion reduces lost investments. This is part of the strategy as laid out in the Business Case | Pilot start and end dates |  | October each year (reporting on all pilots ended that year)
Effectiveness | 3.1 | TA impact rating | Each TA will be assessed as having Emerging, Moderate, Major impact. We will consider individual ratings, by journey to scale groupings, and the average across the portfolio. | This will be our main assessment of TA effectiveness. | Judgement to be made against a simple rubric; proposed in inception report | SCALE MEL team based on data provided by SCALE (validated by Posts). | Report on completed TA assignments October each year
| 3.2 | Pilot Scaling Progress rating | Based on Scalability Assessments, a scaling progress rating (0-45) will be assigned to each pilot. We will consider individual ratings and the average across the portfolio. | Scaling progress is the main objective of SCALE. | Judgement to be made against a simple rubric, based on Scalability Assessments. | SCALE MEL team based on data provided by SCALE (validated by Posts). | Report on completed pilots October each year
| 3.3 | Pilot potential impact on learning | Estimates of the long-term number of additional learners reaching minimum proficiency levels reasonably attributable to SCALE pilots | Combining with the probability of success (scalability rating), this is the key measure of pilot effectiveness | Estimate of long-term number of additional learners | Researcher partners or implementing partner
| 3.4 | Amount of funds leveraged from other donors/governments towards SCALE objectives | Estimates for individual pilots (and TAs?) and overall | This is another key measure of the success of SCALE, both directly and as a proxy for the relevance and sustainability of interventions. | Actual or expected funds leveraged | FCDO SCALE Team, Posts, IPs
Equity | 4.1 | Equity inputs: % TA in high-need contexts | Numerator: number of TA interventions in countries with high levels of equitable learning needs (defined as primary completion rate below 50%) Denominator: total number of TA interventions | Measures extent TA targets countries/contexts with high needs | Number of TA assignments total; TA assignments in high-need contexts | SCALE MEL Team | October each year
| 4.2 | Equity inputs: % pilots in high-need contexts | Numerator: number of pilot interventions in countries with high levels of equitable learning needs (defined as primary completion rate below 50%) Denominator: total number of pilot interventions | Measures extent pilots targets countries/contexts with high needs | Number of Pilots; number of pilots in high need context
| 4.3 | Equity inputs: % TA with main focus on GEDSI issues (disaggregated by dimension of focus) | Numerator: number of TA interventions with main focus on GEDSI issues (and clear description of what aspects of equity are being addressed) Denominator: total number of TA interventions | Measures extent TA with explicit GEDSI focus | Number of TA assignments total; TA assignments with GEDSI focus
| 4.4 | Equity inputs: % pilots with main focus on GEDSI issues (disaggregated by dimension of focus) | Numerator: number of pilot interventions with main focus on GEDSI issues (and clear description of what aspects of equity are being addressed) Denominator: total number of pilot interventions | Measures extent pilots with explicit GEDSI focus | Number of pilot assignments total; pilot assignments with GEDSI focus
| 4.5 | Equity inputs: % TA that include focus on GEDSI issues (disaggregated by dimension of focus) | Numerator: number of TA interventions with significant focus on GEDSI issues (and clear description of what aspects of equity are being addressed) Denominator: total number of TA interventions | Measures extent TA with GEDSI factor | Number of TA assignments total; TA assignments with GEDSI as factor
| 4.6 | Equity inputs: % pilots that include focus on GEDSI issues (disaggregated by dimension of focus) | Numerator: number of pilot interventions with significant focus on GEDSI issues (and clear description of what aspects of equity are being addressed) Denominator: total number of pilot interventions | Measures extent pilot with GEDSI factor | Number of pilot assignments total; pilot assignments with GEDSI as factor
| 4.7 | Equity outputs: % of TA interventions that delivered on equity dimensions (disaggregated by dimension of focus) | Numerator: number of TA interventions that are considered to have delivered on equity dimensions set out in ToR Denominator: total number of TA interventions with equity dimension in ToR | Evaluates the effectiveness of TA interventions in achieving the equity dimensions | Number of TA assignments; Number TA with dimension of equity
| 4.8 | Equity outputs: % of pilot interventions that delivered on equity dimensions (disaggregated by dimension of focus) | Numerator: number of pilot interventions that are considered to have delivered on equity dimensions set out in ToR Denominator: total number of pilot interventions with equity dimension in ToR | Measures the success of pilot interventions in meeting the equity dimensions | Number of pilot assignments; Number pilot with dimension of equity
| 4.9 | Equity outcomes: % of TA interventions with transformative impact on equity (disaggregated by dimension of focus) | Numerator: number of TA interventions that are considered to have had a transformative impact on equity Denominator: total number of TA interventions with equity dimension in ToR | Assesses the proportion of TA that have achieved a transformative impact on equity, indicating deep and lasting change | Number of TA assignments; Number TA with transformative outcome
| 4.10 | Equity outcomes: % of pilot interventions with transformative impact on equity (disaggregated by dimension of focus) | Numerator: number of pilot interventions that are considered to have had a transformative impact on equity Denominator: total number of pilot interventions with equity dimension in ToR | Assesses the proportion of pilots with transformative impact on equity, indicating deep and lasting change | Number of pilots assignments; Number pilots with transformative outcome
Cost-Effectiveness | 5.1 | Cost per successful TA intervention | Numerator: Component 1 costs as defined above Denominator: # TA projects that record a change to an education system of Moderate or Major significance in a verified Change Story. Note we will also look at individual TA cost-effectiveness considering their impact rating, journey to scale position, equity rating, and cost. | Measures the financial resources invested relative to the significant outcomes achieved in the education system | SCALE Intermediate outcome indicator 1 | SCALE MEL team | October each year
| 5.2 | Cost per successful pilot | Numerator: Component 2 costs as defined above Denominator: # pilot countries that adopt pilot interventions at national or sub-national level of Moderate or Major significance in a verified Change Story Note we will also look at individual TA cost-effectiveness considering their scalability rating, potential impact on learning, equity rating, and cost. | Measures the financial resources invested relative to the significant outcomes achieved in the pilot | SCALE Outcome indicator 1
| 5.3 | Leverage ROI | Numerator: Amount of funds leveraged from other donors/governments towards SCALE objectives Denominator: SCALE investment (on-budget costs) Note, this will need to include some assessment of attribution To be calculated for individual pilots and overall | Measures the effectiveness of SCALE investments in attracting additional funds from other donors or governments | Actual or expected funds leveraged; overall SCALE costs (on-budget)
| 5.4 | Impact on learning ROI | Numerator: Estimation of the potential impact of SCALE-funded pilots in terms of additional children meeting minimum learning proficiency Denominator: SCALE investment (on-budget costs) Note, this will need to include some assessment of attribution To be calculated for individual pilots and overall | provides measure of educational impact relative to financial resources spend | Estimate of long-term number of additional learners; overall SCALE costs (on-budget)
| 5.5 | Overall success to be measured qualitatively, e.g. how successful has the programme been at achieving its objectives across the portfolio of investment, relative to the amount of money spent, including assessment of opportunity cost |  | Provides more holistic assessment of the broader context, challenges and qualitative outcomes | Qualitative data collected through monitoring of TA and pilots