Title: Scaling Access and Learning in Education (SCALE)
Programme Value £ (full life): Up to £68m		Review date: 30/03/2026
Programme Code: 301211	AMP start date: 30/03/2023	AMP end date: 31/03/2028

# Summary of Programme Performance
Year	2024	2025	2026
Overall Output Score	B	B	A
Overall programme risk / rating	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Results Framework

A. SUMMARY AND OVERVIEW

# Description of programme
The Scaling Access and Learning in Education (SCALE) programme (up to £68m, 20232028) aims to improve the effectiveness of education financing in low and lower‑middle‑income countries. The programme recognises that UK Official Development Assistance (ODA) is a fraction of education financing. It is therefore working with partner governments, multilaterals, and philanthropy to support, embed, and sustainably scale up evidenced-based foundational learning education reforms.

SCALE is delivered through three components:
Demand-led technical assistance (TA) to support partner governments and other major education stakeholders to adapt evidence-based interventions to new contexts. This is delivered in-house by FCDO Programme Insourced Roles (PIRs) and externally by our implementing partner Education Development Trust (EDT) and downstream partners.

Innovative Partnerships (IPs) to scale up sustainably successful education initiatives into national systems. These are delivered by country specific implementing partners alongside our external research partner Innovations for Poverty Action (IPA).

Partnerships for scaling with donors, multilaterals, and other major stakeholders. Built through FCDO influencing, these support sustainable scale up of promising interventions.

A third-party evaluator, Alinea International, supports all three components, running formative and summative evaluations to support programme learning and adaptation.

The reduction in UK ODA, announced by the Prime Minister in March 2025, led to changes to programme logframe targets to enable realistic delivery whilst maintaining appropriate ambition. At the time of writing the review, the programme team is awaiting the outcome of the current Spending Review which will determine the future scope of the programme and may require additional logframe changes.

# About changes to UK ODA
With conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s ODA. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.

The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts. These will build on those already underway as the government implements its modernised approach to development, establishing long-term partnerships based on mutual interests and respect, with an emphasis on expertise rather than grants, and on local rather than international interventions wherever possible.

ODA allocations and the impact on programmes are being considered, including through impact assessments. We will take a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.

We remain committed to spending 0.7% of GNI on ODA when fiscal circumstances allow.

# Summary supporting narrative for the overall score in this review
As above, the reporting period has been shaped by a highly constrained operating environment, marked by continued uncertainty on the future of the UK’s ODA budget and significant workforce pressures. This has required the team to deliver ambitious objectives with reduced capacity and limited ability to forward plan with confidence.

Despite this, SCALE has met its objectives, scoring an A overall for this Annual Review. Substantial progress has been made on delivering a high-quality, effective, demanddriven model of TA support with lots of learning to inform the UK’s new Communities of Expertise (CoE) delivery model. SCALE’s flexible programme design has enabled adaptation, responding to the changing internal and external operating context.

Highlights this year include successful implementation in fragile and conflict affected states (FCAS); launching the first IPs in Malawi and Nigeria; and onboarding our research partner, IPA.

# Major lessons and recommendations for the year ahead
12. The year has generated important lessons and recommendations. These are set out in the table below and further explored under the relevant outputs.

Output #	Lesson	Recommendation
Cross - programme	Programme flexibility enables delivery amid uncertainty: Despite capacity constraints and uncertainty around timelines and budgets, SCALE has continued to deliver strongly. The programme’s adaptable, design, enabled by Accountable Grants and a dedicated core team, has allowed	Take stock to recalibrate ambition and delivery post Spending Review / Following the outcome of the Spending Review and FCDO restructure, the SCALE team should undertake a structured internal stocktake to reassess budgets, delivery timelines, and levels of ambition across TA, IPs and the dual

	activities to be reprioritised and adjusted to sustain delivery and momentum. In-person engagement with and between implementing partners has proved highly valuable (where feasible), significantly improving alignment, shared understanding, and collaborative decision making.	lock process. This should consider the use of a no-cost extension (proposed in last year’s Annual Review and staffing strategy), to ensure the programme remains realistic, focused and deliverable. This should be followed by an inperson convening of external partners / (where feasible) for specific discussions on TA and IPs to agree any necessary adjustments and changes to ways of working needed. / (May)
1	Investing in strong systems creates demand and delivers high-quality technical assistance Taking time to build robust systems, tools, processes and quality assurance has paid off. SCALE now has strong demand for TA from the overseas network, high-quality delivery, and a credible pipeline of investments. We have learned how to shape effective work plans, identify the right expertise, and manage quality from design to delivery. These insights will inform the Community of Expertise for Education (CoEE) and other CoEs.	Embed SCALE learning across the CoE model The SCALE programme team should continue to actively share SCALE’s proven tools, processes and delivery lessons to influence successful design and operations of the CoEE and wider CoE model. This should be done through sharing templates, monitoring tools, short case studies, and delivery insights, ensuring these assets directly inform future TA design, scoping and quality assurance. (August)
1	A clear gender equality, disability, and social inclusion (GEDSI) strategy drives meaningful mainstreaming Having a dedicated GEDSI strategy with clear targets has been effective in embedding equity and inclusion across TA assignments. Refinement of this approach has helped strengthen inclusion of GEDSI in system strengthening. SCALE has been able to design a strategy which is flexible enough to meaningfully deploy across our diverse geographic portfolio.	Refresh GEDSI targets to maximise impact across the remaining pipeline SCALE should review and refine its GEDSI targets in response to the Spending Review and programme Annual Review outcomes to ensure they remain realistic, intentional and deliverable across the remaining TA pipeline. The SCALE team should support other FCDO teams to adapt and adopt the GEDSI strategy to underpin successful delivery of FCDO’s Women and Girls priority through the CoEE and broader CoE offer. (June)
1	SCALE can deliver high-quality TA in FCAS contexts: Experience in Sudan, Palestine, and Lebanon shows that SCALE can effectively deliver education system	Build a usable evidence base on FCAS delivery: SCALE partners, / supported by the FCDO programme team, should prioritise the documentation of concise case

	strengthening TA in FCAS settings. Targeted engagement with / Advisers at Post and structured demand scoping have generated strong demand and high-quality delivery - an approach that will be increasingly important as FCDO looks to increase its use of expertise-led TA and to work effectively at a systems level in these contexts.	studies which capture successful approaches and lessons alongside the existing impact stories from FCAS contexts. These products should be practical, and delivery focused and used to inform CoEE programming, education system strengthening, and (where applicable) broader FCDO TA / efforts in FCAS. (June)
2	Establishing effective multistakeholder collaboration IPs involve multiple stakeholders from different organisations / (Ministry of Education officials from / central, district, school level; donors; implementing partners; researchers) working together to support bold education reforms. It takes time to align organisational incentives and ensure effective collaboration and coordination. This should be prioritised in the early stages of IPs. To date, funding uncertainty has meant focusing on short-term delivery. The stability that will be provided by the multiyear spending settlement gives an opportunity to re-set.	Prioritise time to develop effective collaboration within each IP Now the Spending Review outcomes are finalised, SCALE will ensure time for additional teambuilding, alignment, and role clarification for Malawi and Nigeria. / Malawi: To be integrated in Phase 2 / implementation plan. (April) / Nigeria: To be integrated into implementation plan review at the end of inception period (April). / For future IPs, dedicated onboarding time should be prioritised through inperson meetings and structured onboarding to the one team approach. This will establish shared understanding of tools, responsibilities, and ways of working. / (Ongoing)
2	Adapting evidence-based interventions for scale-up requires continuous learning through implementation Embedding evidence based interventions within government systems often requires implementers to adapt away from the original evidence based model, as set out in the Smart Buys. These adaptations are needed to align with government priorities, existing curricula, and operational constraints. While necessary for scale and sustainability, they raise questions about how effectiveness can be maintained as interventions evolve. The value of the SCALE model lies in its focus on continuous testing and learning during implementation. Through test-learn-adapt cycles, real time data feedback, and close collaboration between research and implementing partners’ Monitoring Evaluation and Learning (MEL). teams, SCALE builds ongoing evidence on implementation while supporting sustainable system change.	Align partners around the evidence informed path to scale To manage the risks of necessary adaptations to evidence-based interventions within government systems, SCALE’s learning tools need to be more fully integrated into partners’ implementation and scaling plans. Test-learn-adapt (TLA) cycles, research activities, and the scaling roadmap should actively shape how interventions evolve. / Future IPs Set clear expectations at scoping stage for how TLA cycles will guide adaptation and support the path to scale, ensuring all partners have a shared understanding of the evidence informed learning process and their / role within it. (Ongoing) / Ongoing IPs (Malawi and Nigeria) Use Phase 2 activities and scaling roadmap design to agree shared expectations on how research plans, TLA cycles, and the scaling roadmap are integrated into implementation. This will ensure common understanding of the learning approach and joint ownership of adaptation. (May)
3	Shifting ODA context requires more strategic partnership selection / The ODA landscape has changed significantly since programme design, including reductions across bilateral donors and the closure of USAID as a potential partner in many contexts. While SCALE continues to prioritise leveraging domestic and multilateral funding, the programme is also exploring additional partnership models, including philanthropic actors, to support scaling ambitions.	Reassess partnership criteria to reflect the changing funding / landscape / As part of the recommended internal programme review, the SCALE team should undertake a review of the current partnership criteria within the IP design. This will ensure they remain fit for the current ODA context. This should include reassessing the weighting of criteria related to credibility and funding for scaling so that pipeline planning and partnership selection are explicitly informed by shifts in the donor and financing landscape. (July)

# B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

## Theory of change
SCALE aims to contribute to the impact of “faster global progress to get disadvantaged children, especially marginalised girls, enrolled into school and achieving foundational learning”. SCALE’s investments use the strongest available evidence of what works from the Smart Buys and other credible sources and adapts this to local contexts. The overall programme theory of change still stands, however changes to some assumptions have been made this year in response to changes in the UK and global ODA context and the lower than anticipated number of FCDO PIRs. The update theory of change is as follows:

The reduction in UK ODA and pause on signing new partner agreements between March and August 2025 necessitated revisions to logframe targets to ensure realistic objectives while retaining ambition. The programme paused planned IPs and pivoted its delivery approach to expand the standalone TA offer. Once the agreement pause was lifted, SCALE rapidly mobilised IPs in Malawi and Nigeria.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
SCALE is making good progress towards its intermediate and longer-term outcomes and impact indicators at this stage. A No-Cost Extension may be considered over the next 12 months as the new FCDO operating model and priorities are implemented.

Over the past year, Alinea completed the second round of the Formative Evaluation, focusing on implementation of the GEDSI Strategy. The evaluation highlights strong TA delivery, high demand from Posts, and successful expansion of TA into FCAS. It confirms that TA and IP activities are relevant to country needs, well researched, context appropriate, and aligned with national reform priorities. The evaluation also found that SCALE has helped influence strategic thinking among country-level partners on marginalisation, GEDSI, foundational learning, and scaling approaches.

## Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
17. SCALE’s focus on systems strengthening and improving the cost effectiveness of domestic education expenditure aligns strongly with FCDO’s development priorities and strategic shifts to work differently in line with the new operating model and more constrained ODA. By leveraging UK expertise and working closely with national governments and partners, SCALE helps to build resilient, locally owned education systems that deliver sustainable learning outcomes, reduce long-term aid dependency, and unlock economic growth. SCALE’s model empowers local partners to ensure solutions are contextually relevant. The programme is on track against output and outcome indicators, and its value for money case remains strong. Stakeholder interviews consistently highlighted the high value delivered by the SCALE team, Advisers at Post, and implementing partners, as well as the importance of SCALE’s flexible and adaptive approach. As FCDO moves further towards a new model of deploying UK-led expertise in a demand-driven approach, SCALE is well positioned to serve as a central delivery mechanism for the CoEE.

# C. DETAILED OUTPUT SCORING

Output Title	Technical assistance is used
Output number:		1	Output Score:	A+
Impact weighting (%):		35	Weighting revised since last AR?	Yes – increased by 10%

Indicator(s)	Milestone(s) for this review	Progress
Output 1:1 Package of TA support from in-house and external experts designed, mobilised, and available to the FCDO network.	a) Updated PIR staffing and recruitment plan, with action underway to recruit vacant positions to ensure adequate expertise, including on GEDSI. b) GEDSI TA mainstreaming actions set out in the SCALE GEDSI Strategy on track. / c) Plan for offering a deep/long term TA offer alongside the Centre of Expertise.	Milestone met / Recruitment plan in place. / 78% (7 out of 9) of TA assignment rated as accommodating or transformative GEDSI categories, against a target of 50% / Clear offer set out alongside Community of / Expertise
Output 1:2: # of opportunities identified and/or requested for TA (cumulative)	20 TA assignments identified and/or requested (cumulative)	Milestone exceeded / 26
Output 1.3. # of TA projects / a) actioned and b) completed (cumulative)	20 actioned and b) 13 completed / 70% assignments demonstrate a logical chain to impacts for children experiencing significant, high or severe forms of discrimination and marginalisation. / 50% assignments GEDSI sensitive or transformative	Milestone exceeded / a) 24 actioned and b) expect 15 to be completed by end March deadline b) 80% assignments demonstrate a logical chain to impacts for children experiencing significant, high or severe forms of discrimination and marginalisation. / c) 78% assignments GEDSI / sensitive or transformative
Output 1.4. Proportion of TA assignments that meet FCDO's quality criteria	80%	Milestone exceeded 92% met quality / expectations
Output 1.5. Proportion of (a) users and (b) providers that rate TA as satisfactory or better.	80%	Milestone exceeded 100% of users and 88% of providers reported overall satisfaction

Briefly describe the output’s activities and provide supporting narrative for the score:
This output measures in-house and external TA that responds to requests from the FCDO network with two main offers. First, through standalone TA based on evidence from the Smart Buys, and second, TA to scope IP opportunities for funding through Output 2. The programme has met or exceeded all indicators.

Output 1.1. has been met with significant progress on GEDSI, and proactive lesson sharing to support and influence the development of the new FCDO CoE model. SCALE continues to be the main delivery mechanism for the existing CoEE. On PIR resourcing, a recruitment plan is in place but has not yet been fully implemented due to current workforce controls. Output 1.2 has been exceeded following extensive efforts to build a strong TA pipeline through information events for FCDO advisers and provision of support to help them to develop requests alongside in line with the programme model. .

EDT and PIRs have delivered strongly against TA requests, with ten standalone assignments completed or underway and a further seven in inception or scoping[1] (see examples in Annex A). EDT has also scoped eight IPs[2]. Selection is guided by robust criteria, including strength of evidence, political will, and opportunities for locally led, sustainable impact. One TA request did not meet these criteria and was not taken forward. TA delivery in FCAS has increased and represents a notable success. Change stories continue to track contributions to equitable learning outcomes, with 80% rated as having moderate or major significance (Output 1.3). Output 1.4, which assesses TA quality, has been exceeded, with 92% of the criteria agreed for each deliverable in scoping assignments met. Review interviews confirmed high consultant quality overall,
[1] DRC, Myanmar, Syria, Uganda x2, Sudan follow-on, multilateral education architecture study
[2] Malawi, Nigeria, Nepal, Uganda, Zambia, Ghana, Mozambique, Somalia

though some assignments initially required changes to find the right expertise. EDT has strengthened processes this year, including consultant swaps and more structured monthly check-ins-. Output 1.5 has also been exceeded with the majority of respondents rating TA positively at the end of assignment feedback collection. Consultations with FCDO Education Advisers at Post also reinforced the high quality of TA delivered across several contexts.

Substantial progress has been made on the GEDSI Strategy. GEDSI ratings are now agreed jointly by FCDO and partners for each assignment. The new GEDSI rating process requires more evidence to help ensure our ambition is matched with results that are robust. The formative evaluation found the strategy has contributed to mainstreaming GEDSI within SCALE, with change stories from three of the first five TA assignments demonstrating influence on education leaders and development partners to increase GEDSI attention in reform processes. The evaluation also highlighted areas to strengthen, including addressing gaps that may constrain future demand for targeted GEDSI support and improving consistency in applications of GEDSI ratings.

Describe any changes to this output during the past year, and any planned changes as a result of this review:
Output 1.4 was added to the logframe this year to provide a measure of TA quality to sit alongside the measures of number of assignments identified and completed. The SCALE programme has adapted given staffing constraints and has increased the prioritisation of stand-alone TA over IP delivery during this first phase.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead:

## Lessons learned
Investing in strong systems creates demand and delivers high-quality technical assistance Taking time to build robust systems, tools, processes and quality assurance has paid off. SCALE now has strong demand for TA from the overseas network, highquality delivery, and a credible pipeline of investments. We have learned how to shape effective work plans, identify the right expertise, and manage quality from design to delivery. These insights will inform the CoEE and other CoEs.

A clear GEDSI strategy drives meaningful mainstreaming Having a dedicated GEDSI strategy with clear targets has been effective in embedding equity and inclusion across TA assignments. Refinement of this approach has helped strengthen inclusion of GEDSI in system strengthening. SCALE has been able to design a strategy which is flexible enough to meaningfully deploy across our diverse geographic portfolio.

SCALE can deliver high-quality TA in FCAS contexts: Experience in Sudan, Palestine, and Lebanon shows that SCALE can effectively deliver education system strengthening TA in FCAS settings. Targeted engagement with Advisers at Post and structured demand scoping have generated strong demand and high-quality delivery - an approach that will be increasingly important as FCDO looks to increase its use of expertise-led TA and to work effectively at a systems level in these contexts.

Education capacity at Post is critical to effective TA delivery Strong education capacity at Post, supported by HQ PIR roles, has been central to effective TA design and delivery. Capacity gaps have limited reach of TA to countries without Education Advisers, as anticipated in the business case. Leveraging Regional Advisers has proved successful. Education expertise and capacity at Post will remain a critical factor for effective TA delivery through SCALE and the CoEE.

Strengthening political economy analysis has improved TA and Partnership Design This year highlighted the need to strengthen Political Economy Analysis (PEA) within both standalone TA and IP scoping. The programme has responded by bringing in specialist technical expertise through EDT to strengthen politically informed design and delivery.

## Recommendations
Embed SCALE learning across the CoE model The SCALE programme team should continue to actively share SCALE’s proven tools, processes and delivery lessons to influence successful design and operations of the CoEE and wider CoE model. This should be done through sharing templates, monitoring tools, short case studies, and delivery insights, ensuring these assets directly inform future TA design, scoping and quality assurance. (August)

Refresh GEDSI targets to maximise impact across the remaining pipeline SCALE should review and refine its GEDSI targets in response to the Spending Review and programme Annual Review outcomes to ensure they remain realistic, intentional and deliverable across the remaining TA pipeline. The SCALE team should support other FCDO teams to adapt and adopt the GEDSI strategy to underpin successful delivery of FCDO’s Women and Girls priority through the CoEE and broader CoE offer. (June)

Build a usable evidence base on FCAS delivery: SCALE partners, supported by the FCDO programme team, should prioritise the documentation of concise case studies which capture successful approaches and lessons alongside the existing impact stories from FCAS contexts. These products should be practical, and delivery focused and used to inform CoEE programming, education system strengthening, and (where applicable) broader FCDO TA efforts in FCAS. (June)

## Last year’s recommendations and progress against these
Work with EDT to develop a pipeline of TA assignments to sit alongside the existing pilot pipeline, creating demand for this SCALE offer through staggered proactive communications to the entire FCDO network, including using the CoEE to promote the SCALE offer (EDT and FCDO - ongoing).	This has been achieved. SCALE now has a strong pipeline of varied TA assignments which will absorb the majority of budget remaining for TA. This has been achieved through proactive communications to the Education Cadre and PIRs supporting the development of TA requests. Decision taken to only proactively communicate with Posts with an Education Adviser until additional PIRs can be on-boarded.
Agree new ways of working with EDT in the medium term which empower them to take the lead on delivery of stand-alone TA and enable FCDO to draw on	This has been achieved, with EDT taking a stronger role on day-to-day delivery of standalone TA specifically. EDT collaboration with FCDO advisers at Post has remained essential, as has ongoing PIR oversight of assignment
additional external expertise to support delivery ahead of recruitment of additional PIRs / (EDT and FCDO by end April).	selection, design, and delivery. There was some learning through the year that this lighter touch model works less well for IP scoping which requires significant input from PIRs. We have been able to draw on additional technical GEDSI and PEA resource through EDT’s consultant network to help fill short-term gaps. A recruitment plan has been developed for additional PIRs.

Output Title	Test-learn-adapt IPs are complete
Output number:			2	Output Score:		A
Impact weighting (%):			50	Weighting revised since last AR?		Yes – decreased by 10%
Indicator(s)		Milestone(s) for this review			Progress
Output 2.1 Number of IPs / identified, / scoped, / selected (cumulative)		4 potential test-learnadapt IPs identified. / 3 test-learn adapt IPs scoped, concept notes drafted and presented to advisory group (cumulative) c) 3 TLA IPs selected/agreed by SRO and HoD. / 2 selected IPs expected to reach children experiencing at least significant level of discrimination or marginalisation and 1 experiencing severe level. / 3 selected IPs expected to be GEDSI sensitive and 1 GEDSI transformative. (cumulative)			Milestone met / Malawi, Nigeria, Somalia, Nepal. / Malawi, Nigeria, Somalia. / Malawi, Nigeria, Somalia. / 2 selected IPs expected to reach children experiencing at least significant level of discrimination/marginalisation (Malawi and Nigeria) and 1 experiencing severe level / (Somalia) / 3 selected IPs expected to be GEDSI sensitive and 1 GEDSI transformative (Malawi and Nigeria as sensitive; Somalia as transformative).
Output 2.2 Number of IPs designed and ready for implementation.		2 TLA proposals / (workplan, budget) with high level research study design developed between FCDO and implementing partners/ / relevant partner governments. / 2 new TLA IPs underway / including due diligence assessment (DDA) completed, dual lock set up			Milestone partially met / Malawi proposal agreed (workplan, budget) with high-level research study developed. Nigeria: Concept Note approved, with draft workplan and budget for long-term IP, full proposal with research design expected before end of March. / Malawi - DDA completed, dual lock set up and agreement signed.
		between GED and Post, agreements signed. / c) Quality GEDSI analysis undertaken; clear GEDSI objectives set (targeted or mainstreamed) for all IPs.			Nigeria - DDA underway expected by end of February, decision to sign dual lock once budgets clear. c) GEDSI analysis undertaken for Malawi and Nigeria to guide implementation and design activities.
Output 2.3 Number of testlearn-adapt IPs completed, and scaling roadmaps produced with recommendations for scaling. (Cumulative)		2 IPs on track to meet agreed annual targets			Milestone Met / Malawi - Scaling roadmap developed in Jan 2026. Sets out targets for implementation and milestones for scaling. Nigeria - scaling roadmap in progress, on track to meet current workplan. Key milestones, e.g. baseline scalability assessment, completed and multiyear workplan expected by end of March.
Output 2.4 a) The design of an IP includes testlearn-adapt (TLA) methods and b) active IPs are adapting based on learnings (cumulative)		2 IPs designed with MEL plans/processes that will use real-time data to improve performance. / 2 IPs actively practicing test-learn-adapt piloting (cumulative). This includes whether IPs are adapting based on data related to results for marginalised children where relevant/targeted.			Milestone Met / Malawi: MEL plan in place, real time data being used to improve performance. Nigeria: MEL plan in progress and the objectives set out in the approved concept note and proposal (by March). / Malawi implemented an initial mini learning cycle alongside the master training before full rollout. Nigeria: TLA approach being used as part of bridging phase. Practise classes planned from March using TLA approach.
Output 2.5 Number of IPs generating disaggregated cost data to inform costeffectiveness or cost-optimization analysis		All IPs include cost data collection and analysis in their research plans			Milestone Met / Met where research plans have been finalised (e.g. Malawi) and the plans are in place (e.g. outlined in the concept note) for how this will be done in Nigeria.
Output 2.6 / Proportion of TLA IPs effective in improving teaching and/or learning.		Evaluation framework finalised; Research and Learning Designs for first two IPs include plans for measuring teaching and/or learning outcomes.			Milestone Met: / Evaluation framework finalised and being applied to Malawi and Nigeria IPs. Learning plans for Malawi in place. Draft plans for Nigeria by March.

Briefly describe the output’s activities and provide supporting narrative for the score
31.Output 2 is focused on progress of SCALE’s IPs where we support partner governments to adapt and scale evidenced-based interventions through a TLA approach. Support from the UK is provided via technical expertise and research partners. Scaling roadmaps are a new tool used to ensure reforms are embedded in national systems with an action plan to securing sustainable funding and achieve scale. This means implementation plans also include actions focused targeted towards scaling and influencing, not just delivery.

Delivery under Output 2 has met milestone targets. The mobilisation of new IPs in Malawi and Nigeria was slower than planned and the partnership with Somalia had to be withdrawn due to delayed final Spending Review decisions. SCALE continued to scope IP opportunities in Nepal, Zambia and Ghana (under Output 1) for later progression.

The Malawi IP approach is adapting Teaching at the Right Level (TARL) (Smart Buy[3]) evidence to the Government of Malawi’s remediation reform for foundational literacy and numeracy.
[3] Teaching at the Right Level is a “Great Buy” in the latest Smart Buys ‘2023 Cost-effective approaches to improve global learning’

  1. Partners VVOB and TARL Africa are implementing partners, along with IPA as SCALE’s research lead, and the Ministry of Education, Science and Technology.

  1. Early progress An internal concept note was endorsed by the advisory group, SRO, and HoD in November 2024. Delays to final funding decisions meant inception did not start until October 2025 and implementation in January 2026. Government and partners held a two-week design workshop to agree the model and develop context specific teaching and learning materials. Partners then trained 914 teachers and 30 master trainers across 80 schools. IPA carried out the first learning cycle to provide real-time feedback on this training.

  1. Pathway to scale Malawi’s 2027 Global Partnership for Education (GPE) programme, coordinated by the World Bank, has been identified as the main financing route for national scale-up. Following FCDO engagement, the TARL informed model has been incorporated into the GPE programme document, positioning it for scale if cost effective. A baseline scalability assessment showed strong performance across most scaling indicators with government delivery capacity in resource-constrained classrooms identified as a priority. A Scaling Roadmap Workshop brought together government, FCDO, and partners to prioritise actions for scale.

  1. HQ monitoring In January, SCALE HQ visited Malawi to attend the Roadmap Workshop and observe early assessments schools. School visits provided insights into how the model is being applied, particularly in Standards 1-2 where there is less global evidence. Teachers understand TARL concepts and are enthusiastic about the grouping and play-based activities. The programme is drawing effectively on TARL expertise from Zambia, where similar reforms have scaled nationally.

The Nigeria IP is supporting government to update and adapt the Accelerated Basic Education Programme (ABEP) by integrating TARL methods.

  1. Partners TARL Africa and Education Development Trust are implementing partners, alongside IPA, working in partnership with Government agencies including the Nigerian Education Research and Development Council, and state bodies in Katsina and Zamfara.

  1. Early progress An internal concept note was endorsed by SCALE’s advisory group, SRO and HoD in May 2025. SCALE then completed a comprehensive design phase (including political economy, situational and security analyses) across states, confirming strong political interest and providing input to the baseline scalability assessment. Federal and state-level design workshops helped shape the initial model and established strong early ownership. A Technical Working Group (TWG) is now in place to guide governance and align state design with federal curriculum reforms. The team have embedded a dedicated GEDSI approach reflecting the high levels of disadvantage faced by learners in the Northern states. The programme mobilised this work through a bridging phase during the ODA pause, allowing technical work and government engagement to continue.

  1. Pathway to SCALE Workshops took place in late 2025 and early 2026, including the ABEP TWG cocreation workshop and the Federal Design and Roadmap Review Workshop. These identified curriculum, teacher preparation, and Islamiyya, Quranic and Tsangaya Education (IQTE) specific delivery bottlenecks and translated them into a sequenced reform roadmap, to guide implementation of the IP.

  1. HQ monitoring Whilst implementation has not yet started, SCALE HQ has utilised country-level engagement through the country-based Education Adviser under the dual lock to monitor progress, support partner collaboration, and government engagement.

Across both Malawi and Nigeria IPs, the central SCALE team have worked closely with Post to set the foundations for the dual lock approach, identifying a lead Adviser and Programme Manager. These have been integral during the reporting period in strengthening engagement in-person with partners, enabling access to the right government stakeholders and ensuring technical coherence of the approach.

## Describe any changes to this output during the past year, and any planned changes as a result of this review
Nigeria and Malawi’s implementation timeline shifted due to delays to Spending Review decisions. Malawi was able to begin its inception phase in October 2025 and implementation in January 2026. For Nigeria, FCDO was able to use the existing EDT agreement and work through an extended bridging phase to begin activities. Progress against indicator 2.2 has been affected by delays to signing multi-year agreements.

The programme revised logframe targets in 2025 to reflect a pivot toward fewer but deeper IPs. Once Spending Review allocations are confirmed, we will revisit the logframe.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

## Lessons Learned
38.Establishing effective multi-stakeholder collaboration IPs involve multiple stakeholders from different organisations (Ministry of Education officials from central, district, school level; donors; implementing partners; researchers) working together to support bold education reforms. It takes time to align organisational incentives and ensure effective collaboration and coordination. This should be prioritised in the early stages of IPs. To date, funding uncertainty has meant focusing on short-term delivery. The stability that will be provided by the multi-year spending settlement gives an opportunity to re-set.

Adapting evidence-based interventions for scale-up requires continuous learning through implementation Embedding evidence-based interventions within government systems often requires implementers to adapt away from the original evidence-based model, as set out in the Smart Buys. These adaptations are needed to align with government priorities, existing curricula, and operational constraints. While necessary for scale and sustainability, they raise questions about how effectiveness can be maintained as interventions evolve. The value of the SCALE model lies in its focus on continuous testing and learning during implementation. Through test-learn-adapt cycles, real-time data feedback, and close collaboration between research and implementing partners’ Monitoring Evaluation and Learning (MEL). teams, SCALE builds ongoing evidence on implementation while supporting sustainable system change.

Education Advisers in-country are a pivotal part of the SCALE IP model Providing deep contextual expertise and leading diplomatic engagement with national governments. Their strategic influence is evident in Malawi, where the Education Adviser’s experience working with the World Bank helped secure inclusion of the SCALE IP in the GPE programme document.

## Recommendations
1. Prioritise time to develop effective collaboration for each IP Now the Spending Review outcomes are finalised, SCALE will ensure time for additional teambuilding, alignment, and role clarification for Malawi and Nigeria.
  1. Malawi: To be integrated in next implementation plan for Phase 2 (April)
  2. Nigeria: To be integrated into implementation plan review at the end of inception period. (April)
  3. For future IPs, dedicated onboarding time should be prioritised through in-person meetings and structured onboarding to the one team approach. This will establish shared understanding of tools, responsibilities, and ways of working. (Ongoing)

1. Align partners around the evidence informed path to scale To manage the risks of necessary adaptations to evidence-based interventions within government systems, SCALE’s learning tools need to be more fully integrated into partners’ implementation and scaling plans. TLA cycles, research activities, and the scaling roadmap should actively shape how interventions evolve.
  1. Future IPs: Set clear expectations at scoping stage for how TLA cycles will guide adaptation and support the path to scale, ensuring all partners have a shared understanding of the evidence informed learning process and their role within it.
(Ongoing) ii. Ongoing IPs (Malawi and Nigeria): Use Phase 2 activities and scaling roadmap design to agree shared expectations on how research plans, TLA cycles, and the scaling roadmap are integrated into implementation. This will ensure common understanding of the learning approach and joint ownership of adaptation. (May)

Last year’s recommendations and progress against these
Recognising the time required to identify, mobilise, and start implementing the pilots, we will re-evaluate the current Business Case timelines and overall pilot ambition. This may include recommending a no-cost / extension to extend the lifetime of the programme and/or adjusting targets for the number of pilots per year (SRO, PRO, June 2025).	Spending Review outcome pending.
The ambition for the pilots needs to align with staffing. SCALE team to develop a staffing options paper for the HoD (SCALE team, June 2025). The team will take stock every six months (PIRs and PRO September 2025).	Staffing options submitted.
Update ToRs for the SCALE Challenge Group based on learning from early pilots to improve efficiency of advice and decision-making for pilots (SRO, April 2025).	Completed
Formalise pilot governance arrangements during pilot inception phase, focusing on MoE ownership, and clear ways of working between SCALE partners (SCALE Team, end of pilot inception periods).	Governance formalised in Malawi and Nigeria. Roles agreed with Post and HQ.

Output Title	Strategic partners commit to action to finance longer term scaling and support the learning at scale pathway
Output number:		3	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Output 3.1 Number of strategic partners / engaged and / actively contributing to SCALE and the / learning at scale pathway / (cumulative)	2 Strategic partners providing in-kind collaboration on TA leveraging multilateral/strategic partner funding / (cumulative) / 2 Strategic partners actively participating in / IPs (Cumulative)	Milestone Exceeded / TA: Non-formal education in Lebanon in partnership with UNICEF and UNRWA. Early childhood education in partnership with UNICEF in Nepal and Ghana. Harmonization of non-formal education programming in Sudan in partnership with GPE, UNESCO, ECW, WFP, UNHCR, ILO, UNICEF and Save the / Children. TA to strengthen gender equity content of GPE funding in Mozambique. In Sierra Leone, working with the World Bank to build on their school subsidy pilot.
		IPs: The IP in Malawi is working closely with development partners: World Bank, / GPE, Prevail, Save the Children, UNICEF. In Nigeria, government partners, including the Universal Basic / Education Commission (UBEC), and / National Commission for Almajeri / Education and Out-of-school Children’s Education have actively participated in state and federal design workshops. In Nepal IP preparations are underway in partnership with UNICEF.
Output 3.2 Number of evidence events on scaling for strategic partners to influence the global evidence base on scaling.	2 events (global)	Milestone Exceeded / SCALE presented at the Research Coordination Group for What Works Hub for Global Education (WWHGE) in February 2026 on scaling frameworks and integration with research and learning. / SCALE Nigeria presented at a WWHGE symposium in the margins of the Education and Development conference (UKFEIT 2025) discussing strategies and policies for addressing Nigeria’s out-ofschool children. / There will be a SCALE panel at the / Comparative International Education Society Conference in March 2026.
Output 3.3 Number of knowledge and learning products produced to influence the global evidence base on scaling	Research outputs / planned for initial IPs / Portfolio level workstream designed and first outputs in progress.	Milestone Met: / Research plan in place, with intended outputs for Malawi IP and Nigeria research plan under development. Portfolio level workstream designed. / Two rapid evidence reviews were completed and presented to teams working on school management in / Zambia and school violence in Uganda.

Briefly describe the output’s activities and provide supporting narrative for the score:
This component has made significant progress, through an increased focus on in-country partnerships alongside TA and IPs, and the establishment of country and global research agendas led by the SCALE research partners.

Strategic Partnerships (3.1) exceeded expectations across both TA and IPs. Organisations including UNICEF, GPE, and the World Bank provided in kind collaboration with TA, helping shape design and implementation of the TA, in Lebanon, Nepal, Sudan, Mozambique and Sierra Leone. This helped to ensure alignment and coordination with national priorities and multilateral processes. In parallel, partners actively participated in the inception and scoping phases of IPs in Malawi, Nigeria and Nepal, contributing to scaling roadmaps, research plans and coordinated ecosystem engagement. These contributions significantly advanced the goals of the SCALE partnership component.

Evidence sharing (3.2) surpassed targets as outlined above. Knowledge production (3.3.) met expectations, with a clear research plan for Malawi and ongoing development of a learning agenda for Nigeria IPs. A portfolio level evidence workstream is now in place, and rapid reviews on school management in Zambia and school violence in Uganda were delivered. Two additional deep dive reviews on equity in TARL and structured pedagogy and TARL in conflict settings are underway, expanding the global evidence base on scaling foundational learning.

## Describe any changes to this output during the past year, and any planned changes as a result of this review
46. As a result of findings from the SCALE formative evaluation, last year’s annual review recommendations, and against the backdrop of ODA reductions across bilateral donors, the team decided to focus efforts on deepening strategic partnerships in country (rather than at a global level) to support the IPs. In the log frame, we combined indicators 3.1 and 3.4 to avoid duplication and emphasise the depth and type of engagement with partners for TA and IPs.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead

## Lessons learned
47. Shifting ODA context requires more strategic partnership selection The ODA landscape has changed significantly since programme design, including reductions across bilateral donors and the closure of USAID as a potential partner in many contexts. While SCALE continues to prioritise leveraging domestic and multilateral funding, the programme is also exploring additional partnership models, including philanthropic actors, to support scaling ambitions.

## Recommendations for year ahead
48. Reassess partnership criteria to reflect the changing funding landscape As part of the recommended internal programme review, the SCALE team should undertake a review of the current partnership criteria within the IP design. This will ensure they remain fit for the current ODA context. This should include reassessing the weighting of criteria related to credibility and funding for scaling so that pipeline planning and partnership selection are explicitly informed by shifts in the donor and financing landscape. (July)

Last year’s recommendations and progress against these:
Focus on strong partnership approaches at the country level through our scaling and partnerships plans (which should include a focus on advocacy and communications), testing operationalisation of this approach	SCALE strengthened its country-level partnerships, progressing from introductory engagement toward more structured and strategic collaboration, particularly in Malawi and Nigeria. This has supported early scaling roadmap dialogues that are
through the first two pilots and use of plan templates to be created by the SCALE research partner (FCDO and IPA, ongoing 2025).	beginning to build political and financial commitment for IPs.
Build on the success of the Mozambique TA to GPE, working with central GED team and relevant Posts to identify further opportunities to influence multi-donor funds through SCALE TA (including GPE and ECW) (FCDO, Sept 2025).	TA increasingly focused on influencing multilateral and donor investments, building on the success of Mozambique’s GPE support, through work in Ghana on ECE scaling under the new GPE programme and in Lebanon through technical support to UNICEF on TARL implementation.
Review the Output 3 indicators and milestones in light of learning from previous years to ensure that ambition is realistic, resources are used where they are likely to have greatest impact, and to agree where and how best to focus efforts during the next reporting period (FCDO August 2025).	Output 3 indicators were reviewed and refined in line with learning from previous years as outlined above.

# D. VALUE FOR MONEY
Key cost drivers and performance SCALE continues to deliver good value for money despite challenges. Strong economy, efficiency, and effectiveness are evident through its in-house model, targeted TA, and independently verified results. The VfM framework enables ongoing assessment, with Alinea preparing the latest independent report to guide the programme’s approach.

Economy Progress on assessing cost effectiveness at scale depends on full implementation of the IPs, but the programme has already laid strong foundations for this as delivery accelerates through improved cost data collection led by IPA and Alinea.Key cost drivers currently are PIR costs measured against consultant rates, scoping and mobilisation costs. Spend to date reflects the early stage of delivery and the time required to identify, scope, and design IPs in complex and evolving contexts. PIR labour remains more cost effective than external TA on a daily rate basis, and continue to add value through institutional knowledge, political engagement, and coordination for FCDO and partners.

Efficiency The TA function has maintained momentum despite the pause on new agreements. Key VfM metrics for efficiency currently are delivery of the TA assignments and meeting targets on quality criteria and satisfaction ratings.Of 26 identified assignments, 24 were actioned and 15 are expected to complete this period.
Performance is strong (92% criteria met; 100% satisfaction). Staffing gaps mean PIRs spent more time on programme management than planned. This will be adjusted over the next year.

Effectiveness Completed TA assignments are independently verified by our Alinea through change stories to assess assignment impact. Of the ten completed assignments, eight were rated as delivering moderate or major significance. This is an important result given the short duration of most TA inputs relative to the pace at which meaningful change typically occurs. SCALE’s highest value component is the IPs and overall VfM will hinge on governments scaling these partnerships. It is too early to assess this, but IPA will track cost effectiveness as implementation advances.

Equity SCALE’s GEDSI Strategy sets clear aims to reach marginalised groups. Early progress is positive: 78% of TA assignments are GEDSI sensitive or transformative, and 80% have credible pathways to impact. IPs in Malawi and Nigeria target significantly disadvantaged children and are expected to deliver at least GEDSI sensitive outcomes.

# E: RISK

Overview of risk management The SCALE programme’s overall risk rating is
Moderate and remains within FCDO’s risk appetite. Risks are actively managed through close coordination with partners, regular follow-up on due diligence actions, and monthly discussions with each partner. The SRO is accountable for ensuring effective management of risks to programme objectives, while the PRO leads the active risk management process with support from Programme Managers, including through dual lock agreements

People Across both delivery and MEL, people‑related risks include capacity constraints within FCDO and partners. The programme originally planned to recruit up to ten PIRs but currently operates with three, which has led to IP delays. The team manages risk closely and has been working with partners to ensure support.

Financial and fiduciary As a demand‑led programme operating in a constrained ODA environment, SCALE faces risks related to forecasting accuracy. SCALE has had an underspend this financial year. These challenges have affected partner planning leading to a shift in timelines and workplan.

Safeguarding While no safeguarding incidents have been reported, both delivery and MEL activities operate in contexts involving children, vulnerable groups and downstream partners. In line with best practice and FCDO feedback, safeguarding risks are explicitly recognised. Mitigation measures include adherence to safeguarding policies, partner due diligence, safeguarding training and clear reporting and escalation pathways. In higher‑risk contexts, safeguarding risk assessments are embedded within assignment scoping and inception activities. The team will also conduct spot checks with in-country visits and has started doing this.

Operating in FCAS Contexts Delivery and MEL activities in FCAS settings face risks related to security, access constraints, political instability, and disruption to timelines. These risks are managed through FCDO travel guidance, Post and UN security briefings, assignment‑level risk assessments, and flexible delivery and data collection approaches. This includes remote methods where appropriate. Where risks cannot be adequately mitigated, activities are postponed.

Policy and Programme Delivery The complexity of SCALE, involving multiple partners delivering overlapping activities, creates risks around clarity of roles, co-ordination, and delivery pace, particularly as the first IPs was mobilised. Bringing partners together and establishing effective ways of working requires time, especially in early phases. These
risks are mitigated through agreed ways‑of‑working documents, clear delivery planning, and early escalation of emerging issues.

Dual Lock Insufficient programme management capacity at Post within the dual lock model could undermine SCALE delivery leading to delays. Capability of staff assigned to dual lock roles may further limit effective decision making and compromise programme quality. The SCALE Programme Manager will continue to engage with Post ensuring the required programme management resource is in place to allow the dual lock to fulfil what is expected on the SCALE programme.

# F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

SCALE overall Programme management arrangements remain clear and proportionate to a complex, demand-led portfolio. Accountability is well defined through the SRO and PRO roles, with day to day coordination led by the Programme Manager. These arrangements are strengthened by structured monthly management meetings with delivery partners and the dual lock process with Posts, which supports shared ownership and country level decision making. Over the financial year, the team has prioritised adaptive work planning to respond to external and operational pressures. Pending the outcome of the Spending Review, this may include recommending a no-cost extension to extend the lifetime of the programme

EDT has maintained strong performance management of TA and demonstrated an adaptive approach that ensured high quality delivery despite ongoing uncertainty. They successfully expanded delivery into FCAS contexts and introduced regular monthly check ins that produced key tools such as assignment and pipeline trackers now used across SCALE. EDT has worked closely with Programme Managers to address forecasting and budgeting challenges. In December 2025, the Accountable Grant Agreement was amended to provide a necessary budget uplift, enabling continued delivery in response to rising demand and supporting bridging assignments for the Malawi and Nigeria IPs.

Alinea recorded a small underspend this financial year, mainly due to delays to the IPs and the resulting decision to defer the Formative Evaluation to next year. Financial forecasts were closely monitored through monthly programme management meetings, with changes escalated promptly. Progress on the contract amendment is temporarily on hold pending confirmation of FCDO Spending Review allocations, allowing all required adjustments to be consolidated into a single amendment. Throughout this process, Alinea and FCDO have worked closely, with Alinea providing timely engagement and responses.

IPA participates in regular programme management and technical check ins with FCDO and coordinates closely with other SCALE partners. Delivery has adapted to changes in the number, timing, and sequencing of IPs and increased emphasis on crosscutting portfolio work where timelines shifted. These adjustments required reprofiling workplans, staffing, and budgets. Forecast spend for the year was lower than anticipated due to IP delays. IPA worked closely with the Programme Manager to strengthen monthly forecasting and mitigate emerging financial risks.

VVOB/TARL Africa Strong working relationships with FCDO were established quickly, supported by regular and open communication. The team remained responsive to FCDO requirements, providing timely updates to budgets and absorbed further spend this financial year than originally anticipated. Attendance at monthly programme management meetings ensured clear oversight, with up to date information shared on delivery progress, forecasts, and emerging issues, enabling prompt discussion and decision making.

Dual Lock Having dedicated, high-quality programme management staff in Post is essential to delivering the dual lock and the overall SCALE operating model. The FCDO Overseas Network Review may reduce programme management and advisory capacity available in Posts. Any reduction in capacity would limit their ability to engage fully in the dual lock, so this risk will need close monitoring once the review outcomes are confirmed.

Commercial engagement The Programme Manager has maintained regular, monthly engagement with the FCDO Commercial Department. This engagement supports the effective management of contract amendments as they arise and enables the programme to seek timely advice on commercial best practice. All proposed changes to existing agreements are managed through the Commercial function, ensuring appropriate oversight, compliance with FCDO commercial policies, and alignment with agreed contractual procedures.

Financial performance There was a £2.8m underspend this financial year, largely due to delays in the IPs and Somalia being withdrawn as a delivery option. Somalia being withdrawn as a delivery option. Forecasting remained challenging due to these delays and the programme’s demand-led nature. As the IPs move from mobilisation into implementation, expenditure is expected to rise next year. To strengthen financial oversight, the Programme Manager convenes monthly meetings with each delivery partner, ensuring early mitigation of financial risks. PIRs also closely monitor the TA pipeline to support partners in planning expenditure throughout the year.

# G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation Alinea is the external evaluator, assessing programme effectiveness and sustainability across all outputs, and working closely with IPA and implementing partners. For TA, Alinea validated ten change stories, confirming significance ratings. Evaluation of the IPs has focused on establishing a baseline for Malawi. FCDO, Alinea, and IPA agreed to streamline the process to reduce country level burden and align scalability assessments. Alinea will outline the revised process for FCDO ahead of the Nigeria Scaling Roadmap workshops.

For this annual review, two FCDO Education Advisers led an independent review of documentation and held consultations with programme partners and FCDO Advisers.

Evidence As SCALE’s research partner, IPA has supported scoping of IPs in Zambia, Nepal, Uganda, and Somalia. They have prioritised four deep dive evidence reviews to inform the design of future IPs covering the following topics: school management; equity in TARL and structured pedagogy interventions; TARL in conflict and crisis settings; and school violence. This includes building strategic partnerships with the Centre for Global Development and London School of Hygiene and Tropical Medicine. IPA also scoped a new learning product on school attendance as an input to intervention effectiveness. Phase 1 of the Malawi partnership will test cost efficient methods for measuring attendance and explore attendance profiles

Learning A GEDSI focused formative evaluation was completed in January 2025, generating programme wide recommendations and informing a learning workshop. This was the second such evaluation. Five of eight recommendations from the previous round are complete. The remaining three (linked to communications and Strategic Partnerships) were deprioritised due to capacity constraints. The recent evaluation resulted in six new FCDO recommendations: two for the programme overall and four for implementing the GEDSI Strategy (see Annex B). These have been integrated into the Annual Review.

Date of last narrative financial report	January 2026	Date of last audited annual statement	February 2026

Annex A:

Country	TA Case studies – low-cost expertise, major systems-level impact
Sudan	GPE, ECW, and ECHO, wanted to invest more than $100m on nonformal education in Sudan but lacked evidence on learner needs and the most effective models and approaches of response. A rapidly deployed SCALE team of local and international expertise requested by Post researched and created ‘learner profiles’ to capture the diverse needs of children and built sector consensus around an evidence-based approach. This has substantially increased the ability of the donor response to meet the needs of children impacted by conflict. The final report can be accessed here.
Ethiopia	Rapid mobilisation of SCALE embedded TA enabled Post to respond to the Minister of Education’s request for support to the National Education Taskforce, working to prioritise system reforms and use of domestic resources based on the latest data and evidence. Recommendations have scope to reach over 750,000 teachers, significantly strengthening the education system.
Mozambique	Post and the Government of Mozambique requested rapid gender and inclusion support through the country’s first ever education sector GEDSI analysis. The findings of this have been mainstreamed through Mozambique’s national education plan (where previously these critical equity considerations were absent) and has influenced the design of up to $178m of Global Partnership for Education investment. If these are implemented, the result will be a strengthened and more equitable education system, on a path to better understand and meet the needs of all learners.
Central Asia	Five Embassies in Central Asia jointly requested technical assistance to scope and design a new UK regional education investment. SCALE’s support has enabled the UK to better meet its diplomatic objectives in the region through investing in education systems, despite having no education expertise at Post.

Annex B:
Recommendations from Alinea Formative Evaluation
  1. Review of SCALE’s ambition and approach to TA and IPs following the Spending Review.
  2. Review approach to tracking strategic partnerships at the country level.
  3. Formalise requirement for GEDSI expertise into implementing partner requirements to support capacity building and build in-house expertise in partners at country level.
  4. Build internal GEDSI awareness and confidence across SCALE countries and across the wider education portfolio.
  5. Review GEDSI targets following the outcome of the Spending Review
  6. Establish process to strengthen QA of marginalisation ratings and GEDSI outcomes in Technical Assistance.