## Annual Review Template

Title: Women’s Integrated Sexual Health - Dividend
Programme Value £ (full life): £200,000,000		Review date: 03/07/2025
Programme Code: 301213	AMP start date: 03/04/2025	AMP end date: 31/03/2029

Summary of Programme Performance
Year	2025	2026	2027	2028	2029
Overall Output Score	A
Risk Rating	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0004445.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0006588.xlsx

Glossary

CanWaCH	Canadian Partnership for Women and Children’s Health
CIFF	Children’s Investment Fund Foundation
CSE	Comprehensive Sexual Education
CYP	Couple Years Protection
DALY	Disability Adjusted Life Years
DHS	Demographic Health Survey
GBV	Gender Based Violence
IAWG	Inter-Agency Working Group on Reproductive Health in Crises
ICF	International Climate Fune
IPPF	International Planned Parenthood Federation
IP	Implementing Partner
mCPR	Modern Contraceptive Prevalence Rate
MISP	Minimum Initial Service Package
MSI	MSI Reproductive Choices
ONS	Office for National Statistics
OPM	Oxford Policy Management
PLWD	Person living with disability
SBCC	Social Behaviour Change Communication
SRHR	Sexual and Reproductive Health and Rights
SRH	Sexual and Reproductive Health
STI	Sexually Transmitted Infections
UNFPA	United Nations Population Fund
UIP	Unintended Pregnancy

## A. SUMMARY AND OVERVIEW

Description of programme
Women’s Integrated Sexual Health (WISH) - Dividend (WISH-D) is the FCDO’s flagship sexual and reproductive health and rights programme in Sub-Saharan Africa. WISH-D supports women and adolescents, with a specific focus on the poor and most marginalised and those living in humanitarian contexts, to have greater voice, choice and control over their sexual and reproductive health and rights (SRHR).

The programme builds on a predecessor programme (WISH) to support targeted countries in Sub-Saharan Africa to be more ambitious on improving comprehensive SRHR for women and girls. WISH-D maintains the focus on equities but has a greater focus on system strengthening. There are three main components to the programme:

- WISH2 (MSI and IPPF): service delivery and technical assistance with and through government partners to increase access to SRHR and strengthen national capacity, ownership and domestic financing in 13 countries in SSA. Delivery led by two consortiums made up of local and international partners.
- WISH Policy and Systems (Palladium and ONS): demand-led, flexible technical assistance programme on SRHR and Demographic Transition for countries that exited service delivery support under previous WISH programme (excluding DRC which is part of both WISH2 and P&S)
- WISH Learns (OPM, Guttmacher and IAWG): Third party monitoring and verification, learning and course correction and evaluation of two other components above; evidence generation for advocacy on comprehensive SRHR and SRHR in emergencies.
As a flagship programme, WISH-D stands out for its explicit focus on equity. Prior to this reporting period WISH mobilised 75 million dollars in additional funding for SRHR in West Africa (Nigeria, Niger, DRC, Senegal, Mali and Burkina Faso) from the Children’s Investment Fund Foundation. Over the annual review period, Gates and Hewlett Foundation have committed further funds and this shared funding platform has evolved into the ‘Challenge Fund’ providing potential for further philanthropic funding.

Summary supporting narrative for the overall score in this review

This annual review was completed in July 2025 and covers the period 1st April 2024 to 31st March 2025. This review covers the procurement of all of the Implementing Partners of the programme and the subsequent inception phases. Over the period reviewed, none of the Implementing Partners have begun to deliver against the output indicators (the logframe is not due to be finalised until June 2025). The programme has therefore been scored against procurement timelines and inception phase deliverables needed to achieve those outputs. On this basis, WISH-D is scored as an A. Although procurement across two out of three components did not meet expectations, the subsequent inception phases worked at an accelerated pace which helped the programme to course correct. Deliverables against the ToRs have been assessed as having met expectations. Despite a reduction in time, the partners have remained committed to achieving the headline results of the programme.

Table 1: Output Scores
	Output Description	Score
1.	Information, attitude and social norms (SBCC)	A
2.	Sustainable and inclusive access to integrated SRH services	B
3.	SRH policy environment	A
4.	Increased evidence and learning to increase access to SRHR	A
5.	Human development policy environment	B

Procurement timelines: The procurements for the various components under WISH-Dividend took longer than planned (see Table 2). A procurement after action review was conducted internally to establish what lessons can be learnt from this process (more detail given in section F).

Table 2: Procurement timeline
Programme Component	Partner	Agreement start date	Implementation start date
Policy and Systems	Office for National Statistics	10/07/2024	01/01/2025
WISH2	International Planned Parenthood Federation	06/09/2024	12/03/2025, / Sudan & Madagascar 15/4/2025
	MSI Reproductive Choices	23/09/2024	14/03/2025
WISH Learns	Guttmacher Institute (Global Goods)	01/10/2024	01/10/2024
	Oxford Policy Management (E&L)	07/10/2024	12/06/2025
Policy and Systems	Palladium	06/01/2025	Expected 06/07/2025

Inception phase deliverables: Whilst there were delays during procurement, the work through the inception phase has since kept pace. Notably, WISH2 partners and OPM agreed to an accelerated inception phase with inception deliverables prioritised to allow a faster move to implementation by February-March 2025.

Having said this, multiple iterations of deliverables from WISH2 Implementing Partners were required to reach agreement on priority areas of engagement at country level. This reflects a shift in the delivery model of WISH-D from the previous WISH programme. Greater emphasis is being placed on working through these plans with FCDO Posts to assure alignment with FCDO country strategies and strong country ownership. Where Implementing Partners had not done this sufficiently, further consultation and refinement was requested before deliverables were approved. The imperative to work with Posts will continue and it’s anticipated this will require ongoing oversight from the FCDO team to instil.

Operating context: The operating context of the programme has shifted significantly over the Annual Review period. The worsening humanitarian situation and escalation of conflict and fragility in Sudan, DRC, South Sudan, Ethiopia, Chad, Niger, Burundi and Somalia and the large-scale defunding of SRHR has put back gains made on universal access to SRHR by decades. The majority of WISH-D's support to service delivery is now in a humanitarian context.

Whilst the programme was still in inception phase, WISH2’s operating model (with Implementing Partners working through membership associations, public sector health facilities and locally embedded NGOs) enabled some early demonstration of the potential of the model to quickly pivot and deliver in these challenging contexts. In DRC, for example, WISH2 partners were able to quickly pivot plans so that they would be able scale up their emergency-sensitive services, such as the provision of services tailored to GBV survivors (psychosocial support and medical care e.g. emergency contraception, STI treatment), and the provision of minimum packages of SRH services in line with Minimum Initial Service Package in response to huge need in the wake of the outbreak of conflict in Eastern DRC.

Major lessons and recommendations for the year ahead:

A full list of all the recommendations in this AR have been annexed (Annex A). The main recommendations are as follows:

Develop nested ToC for WISH-D in humanitarian contexts: The rapidly deteriorating humanitarian situation in the majority of WISH2 countries necessitates greater consideration of the WISH-D theory of change in these contexts. A nested ToC should be completed within first six months of the next reporting year to inform mobilisation and delivery. OPM should lead this process, with IPs and FCDO engagement.

Identify alternative data sources to DHS to measure impact: OPM will need to investigate whether alternative data sources are available for current impact indicators, or whether new indicators and corresponding data sources are required. The situation should be reviewed in September 2025 and a decision taken by FCDO on whether to revise these indicators or continue to wait for further information.

Prioritise engagement with Chad and Mauritania to secure Ipas registration and accelerate mobilisation: Ensure country visits by regional lead and support MSI visits to secure registration and accelerate mobilisation in Chad and Mauritania, within first six months of the next reporting year. In addition, FCDO should finalise the DDA of MSI no later than July 2025, including agreeing recommendations which clarify mechanisms for coordination and expectations between MSI and Ipas. This should ensure adequate support and collaboration across WISH2 to enable successful mobilisation of WISH2 in Chad and Mauritania.

Establish a means for coordination and collaboration across the different components of the programme: Delivery against outputs is split across different Implementing Partners and contracts, each contracted at different times. There is a significant risk of the components working in silos. SRO and OPM to establish mechanism for coordination across the programme within the first six months of the next reporting year.
A specific focus should be given to cementing the cross-programme offer to IPs and the FCDO on rollback.

Continue to focus on building country oversight and ownership of the programme: The programme has made significant efforts as a regional programme to work closely with Posts and integrate design with country plans. All WISH-D countries (with the exception of Kenya) have signed dual lock agreements with the programme. Delays to signing off deliverables were in large part due to lack of consultation with posts, especially on geographies and policy and engagement priorities. WISH team to ensure the programme creates mechanisms for regular engagement with and feedback from Posts on IP engagement, within first quarter of next reporting year.

Ensure the WISH Policies and Systems (P&S) Component builds in adequate flex in its delivery model; in reviewing inception phase deliverables from Palladium (remaining submissions due 5th July), FCDO to ensure design is flexible and adaptive in order to be able to meaningfully engage with the reform agenda and be strategic, opportunistic and responsive to the needs of Posts.

Integrate evidence generated by the WISH-D Global Goods component into the delivery of WISH-D. OPM, Guttmacher and FCDO to agree a proposal to capture the work of the Global Goods component, including relevant reporting into the WISH-D logframe and the engagement required to support this, by December 2025.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The intended impact of WISH-Dividend is to advance universal access to SRHR in Sub-Saharan Africa, unlocking the potential of women and girls and supporting inclusive, transformative policies that enable countries to harness demographic shifts for human development.

The original ToC was first presented in the WISH-Dividend business case. During an accelerated inception phase (November 2024 - April 2025) the WISH2 and WISH Policy and Systems (P&S) implementing partners (IPs), with FCDO, reviewed the original ToC and made adjustments to ensure it accurately reflects WISH-Dividend’s planned interventions and intended impact. This work was led by OPM.

For the purposes of this AR we are referring to outputs 1-5, however in the earlier TOC we referred to the outputs as A-E. Also note the order of the outputs will be standardized (currently 4 (D) and 5 (E) are out of sync with the logframe.). For this AR output 4 is the Evidence and Learning output and output 5 is the Human Development Policy Environment output. This will be amended in the finalised ToC so the ToC and logframe align.

Changes to the ToC:

Humanitarian: As outlined above, the operating context for the programme has shifted significantly with the majority of countries facing greater fragility and conflict. OPM are prioritising the development of a nested ToC in humanitarian contexts, working with the Implementing Partners. This is a priority for the following year.

Demography: The original ToC presented ‘inclusive demographic transition’ as a key rationale for investing in SRHR. However, the review highlighted that this term is not appropriate in some African countries, due to negative connotations associated with ‘demographic transition’. Additionally, it did not accurately reflect the focus of Policy and Systems components, which is more aligned with demographic data utilisation. Output 5 and the related areas and pathways of the ToC were updated to reflect this shift in emphasis.

Impact level indicators: While the programme impact statement has not been revised materially, changes may be required to the impact indicators. The planned data source for these was the Demographic and Health Surveys (DHS). Formerly funded by USAID, the DHS program has been suspended indefinitely. The E&L partner OPM will need to stay engaged with discussions on the future of the DHS, which may differ country by country. In the absence of the DHS, OPM, working closely with Guttmacher, will need to investigate whether alternative data sources are available for the current indicators, or whether new indicators and corresponding data sources are required. The situation should be reviewed in September 2025 and a decision taken whether to revise these indicators or continue to wait for further information.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Table 3: Review of Outcome and Impact Indicators
Type	Indicators	Milestones for 24-25	Progress
Impact; Drive progress on universal SRHR to unlock the full potential and power of women and girls and enable African countries to accelerate an inclusive demographic transition	% change in mCPR / Proportion of women aged 15-49 years who make their own informed decisions regarding sexual and reproductive health and rights.	Finalise in inception phase; mCPR by country or mCPR specific to <20 year olds or mCPR in lowest wealth quintile	Target mCPRs finalised (see more info below)
Outcome 1: Women and adolescents, including the poor and most marginalised have greater voice, choice and control over their sexual and reproductive health and rights	Estimated maternal deaths averted; estimated unsafe abortions averted, estimated unintended pregnancies averted, estimated DALYs averted, estimated cost per maternal death and DALY averted.	Finalise in inception phase	Forecasted results finalised (see more info below)
Outcome 2: Improved enabling environment for SRHR, gender equality and human development policy.	Number of examples of national SRHR policy/guidance improvements/reforms; Number of examples where human capital/gender equality policy/plans used demographic data/forecasts following WISH-D influence/support.	Finalise in inception phase	In progress (see more info below)

The forecasted results are lower than originally anticipated in the business case because headline results at outcome level were estimated based on historical cost data for WISH 1 and estimates for the full £200m spend. Underlying assumptions of the estimates included continuing to deliver in high results, low cost-per-Couple Year Protection (CYP) countries like Nigeria (accounting for a huge 23.6% of WISH historical CYPs using only 13.1% of total expenditure, and the lowest unit cost of £3.48).

As design progressed, FCDO identified 12 priority countries (assessed as the poorest with the highest SRHR need) to be supported in WISH-Dividend. This halved the number of countries supported in WISH. In addition, higher shares of the budget were directed towards priority countries that had the highest unit costs, such as South Sudan. Ahead of procurement, fresh modelling using these parameters estimated that our lower budget and higher unit cost footprint would deliver 11.3m CYPs. This figure was used as a floor for the procurement terms of reference and was surpassed by the bids received. With £161m of the £200m budget committed, the current results forecast is as follows:

Table 4: Results

Indicators	BC Estimated Results	Current forecast results
Couple Years of Protection	20.9m	11,800,001
Unintended Pregnancies averted	9.5m	5,376,124
Unsafe Abortions Averted	3.4m	1,634,671
Maternal Deaths Averted	30,600	11,883
Disability Adjusted Life Years averted (DALYs)	18.9m	10,356,319
[note] Couple Years Protection is the estimated protection provided by family planning (FP) methods during a one-year period, based upon the volume of contraception provided to clients during that period
[note] One DALY represents the loss of the equivalent of one year of full health.

Whilst these forecasted results are lower than BC results, as outlined above, they represent a significant shift in the programme’s design (from WISH to WISH-D) to focus on equities and meeting unmet need amongst the harder to reach e.g. in humanitarian contexts.

To ensure this focus on equities is sustained, the programme will continue to operate a payment by results model for four key performance indicators on Couple Years Protection, youth, poverty and sustainability.

The key risk in not meeting these targets is the uncertainty around budget allocations for future years and the potential need to revise programme design over the course of the year ahead of the move to 0.3%. Donor cuts are likely to also impact on the viability of some downstream partners.

A mid-term evaluation of the programme is planned for March 2028. The draft evaluation framework, including the approach and evaluation questions have been developed. EQUALS engaged to review and quality assure.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

This annual review has reviewed the inception phase of the programme. Based on this phase, there is early demonstration that the IPs are positioning their work to be well placed to meet the growing challenges facing SRHR in Sub-Saharan Africa, particularly in fragile and conflict affected states. The pivot to system strengthening and focus on support in humanitarian countries is well aligned to the emerging priorities of the FCDO. The Policy and Systems offer of flexible technical assistance will fit well within the emerging new operating model for FCDO and WISH Learns is establishing a strong basis on which to ensure learning is relevant to both the programme and the wider SRHR community, adding value to efforts to counter rollback. On this basis, the programme should continue.
## C. DETAILED OUTPUT SCORING

Output Title	Information, attitudes and social norms: Individuals have increased knowledge, capacity and community support to make informed SRHR decisions and recognise and advocate for their SRH rights.
Output number:		1	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
1.1 - % Proportion of clients accessing services through a WISH-Dividend partner who believe those around them (i.e. family, friends, wider community) support their decision to take family planning	N/A
1.2 - % of WISH clients reporting referral to a WISH consortium partner as a result of WISH supported messages/activities.	N/A
1.3 - % reduction in regressive social gender norms held by target reference groups (parents, community leaders, service providers) within intervention areas	N/A
1.4 - % change in an individual behaviour change driver, among targeted individuals in norms intervention (to be proposed by implementing partner in inception phase, depending on intervention design)	N/A

Results against the above indicators will be delivered through WISH2 (IPPF and MSI).

Over the review period, none of the implementing partners began delivery against the output indicators. In lieu of inception phase milestones, the programme has been assessed against the procurement timeline and delivery of the inception phase deliverables as outlined in the ToRs.

Deliverable(s) for this review	Progress
Commercial: Procurement timeline as set out in Business Case:
Procurement timeline, including April 2024 objective for signature for WISH2 contracts	Substantially not met: / Contracts with MSI and IPPF signed September 2024. / Mobilisation from October 2024, / Implementation phase started March 2025.
Inception Phase: Activities set out in the WISH2 TORs within 6 months of mobilisation (priority activities for this output in bold)
Make all administrative, logistical and management arrangements to facilitate the launch and delivery of the programme in the implementation phase.	Met: / WISH2: Inception phase completed March 2025 / Team and country leads recruited in 12/13 countries, and subs contracted. / Inception phase workshops in Nairobi (IPPF) and Dakar and Kinshasa (MSI). / Registration in all countries with exception of Chad and Mauritania. Awaiting final administrative sign – off in Mali. / Technical oversight group on social norms established (December 2024)
Develop, in agreement with FCDO and the E&L Supplier, a comprehensive results framework and methodology for measuring results including for Key Performance Indicators (KPIs), drawing on learning from WISH.	Met: / KPIs and Performance Indicator Reference Sheets on track. / Development of WISH2 results framework broadly on track despite some technical and definition challenges with some indicators. These are expected to be resolved in line with agreed timelines. / Initial discussions with P&S component held.
Establish relationships with relevant partners / including government, FCDO official(s) at post and development partners and ensure all key programme governance mechanisms are fully in place.	Moderately not met: / Dual lock agreements signed for WISH2 with WISH2 posts. Governance mechanisms for the consortiums in place. / Country steering committees established and first meetings taken place in 4/13 (2 in WACA, 2 in ESA) countries.
Contribute to the design of, and make provision for, ongoing engagement with WISH Evidence and Learning.	Moderately exceeded: / MoUs agreed between OPM and IPPF/MSI, E&L workshop attended, with active participation and contributions from all consortiums. WISH2 teams have been responsive and open to regular exchange on the Logframe and MEL agenda.
Production of Inception Phase deliverables.	Met: All deliverables submitted. Country level sustainability frameworks and safe abortion ecosystems frameworks are due by month 12 and expected by August (month 10).

Briefly describe the output’s activities and provide supporting narrative for the score.

Despite early delays to procurement at the start of the year, all Implementing Partners are now contracted, and most inception phase activities have progressed as planned. On this basis this output has been considered to meet expectations.

It is particularly important that work against this output is politically and socially astute. The inception phase was a critical time to proactively lay the foundations of networks and relationships that would enable a smooth transition to implementation. Given the sensitivity of the issues the partners intend to work on, securing the early buy-in of champions within government and their understanding of the proposed work under this output is essential e.g. to assure timely validation of SBCC tools (which is required in most WISH2 contexts) to avoid delays during implementation.
In some cases, WISH2 Implementing Partners have been able to use the buy-in and recognition of the first WISH programme to secure early engagement and support. They have conducted political economy analyses and country needs assessments to inform the country workplans and build the WISH2 consortium’s structures, governance mechanisms and partnerships. The needs assessments provided important learning about the social-cultural context and key actors that enable the social and cultural beliefs that prevent (or enable) women’s access to SRHR, and/or influence SRHR programming. Post reported that they appreciated being part of the feedback process and the opportunity to shape the programme in their host countries.

Having said this, more work will be needed over the course of the programme to ensure WISH-D partners use their political and social networks sensitively to assure impact. Two rounds of feedback were required from FCDO on the workplans, country needs assessment and risk registers to ensure the programme was responding to the nuance of each country context and feedback from one FCDO focal point was that they (post) had had to facilitate stronger government engagement from the IP to mitigate foreseen risks of sensitivities and lack of national support. The focus on setting up the programme with the lead Ministry (of Health) may have also meant less engagement with other Ministries relevant to this output (e.g. Ministry of Women/Family, Education and communication) and a recommendation has been made below to respond to this. Finally, as WISH2 leads are often the service delivery leads, there is a risk that they dedicate more time to output 2 set up, and work on social norms change under output 1 is deprioritised. This may be a particular risk for Chad and Mauritania in the first months of implementation as Ipas are new to these countries.
The inception phase was also dedicated to building cross-consortium understanding of Social Behaviour Change Communication (SBCC) and disability inclusion. For example, WISH2 Eastern and Southern Africa (ESA) lead (John Hopkins University) launched the WISH2 Learning Platform for SBCC, introducing four self-paced online courses. This is available to all WISH2 partners across ESA, as well as Ministry of Health representatives from project countries.

It is particularly important that these trainings ensure that SBCC and social norms messaging reinforce positive messaging about the role of women in society and do not stigmatise the choices women make about if, when and how many children to have. WISH-D works through local organisations as they are best placed to understand local contexts and situate messaging appropriately. However, with this there is a risk that in some settings SBCC can shift from the intended messaging and reinforce harmful social norms to coerce certain behaviours. The sub leads within both WISH2 consortia need to be alive to this risk and manage it appropriately. Specific recommendations on this below.

The technical oversight group on social norms was set up by the FCDO in December 2024, to support the exchange of ideas and approaches and FCDO oversight on technical issues relating to social norms/SBCC. This is one mechanism through which FCDO can monitor the content of SBCC. Discussions to date have enabled teams to share learning generated from WISH1 and how this will be applied to WISH2. According to feedback from consortium members, the two meetings that have taken place to date have felt inclusive and created a space for easy exchange/discussion. This will be a critical forum through which to continue to support and guide the use of SBCC.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made. The logframe milestones and indicators are still being finalised and the agreed version will be used for future annual reviews.

To note however that shifts in the Niger context may affect programme activities; a decree from the Ministry of Education at the end of 2024 instructed the immediate removal of CSE from school curricula between certain grades. This may mean some WISH2 activities will have to adapt.

 Lessons learned this year and recommendations for the year ahead.

1. FCDO to find a solution by September 2025, to ensure French or English only speaking participants can contribute to technical oversight group discussions that are relevant to them. Currently made up of English-only speakers meaning to date it’s been difficult to invite in individuals who are French speaking only.
2. Review of approaches to monitor SBCC content to ensure adherence to carefully developed messaging - this includes: 1) FCDO to organise a dedicated discussion on this at next technical oversight meeting in Q1 2) FCDO and OPM to actively monitor this issue during country visits, and consider as theme for in-depth assessment, and 3) RAES, MSI and JHU to establish a plan by October 2025 on how they will monitor SBCC messaging, particularly at the community level, to ensure consistency with intended content. This should include an approach to follow up, should inconsistencies by identified. This risk should be included in risk register and WISH2 quarterly reports, from Q1.
3. By August 2025, WISH2 country leads to have demonstrated their wider engagement (alongside relevant WISH2 partners) of relevant output1 national stakeholders with WISH2, including senior members of government of national Ministries (e.g. Ministry of women, ministry of education). MSI and IPPF to report on this under country feedback at FCDO quarterly meetings, from Q2.

Output Title	Sustainable, inclusive access to integrated SRHR services / Access to quality, voluntary FP and other SRH services, eliminating barriers for young and marginalised women, the poorest and those with disabilities including in fragile and conflict affected areas.
Output number:		2	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 - KPI: Number of couple years' of protection (CYPs) (disaggregated by public sector support and private sector)	N/A
2.2 - Estimated number of annualised family planning clients served	N/A
2.3 -Number of family planning client visits	N/A
2.4 - KPI: % family planning client visits for those under the age of 20	N/A
2.5 - KPI: % of family planning client visits from those in severe multidimensional poverty.	N/A
2.6 - % of family planning client visits from those living with a disability	N/A
2.7 - % of DMPA-SC self injection as a proportion of total DMPA (self injection + provider assisted)	N/A
2.8 - % sites reaching Method Information Index Plus score > X (disaggregated by private and public sector support)	N/A
2.9 - % of sites that provide >1 LAPM (Long Acting or Permanent Methods) OR Number of LAPM services provided to clients	N/A
2.10 - Integration: % of WISH clients receiving additional services to their family planning.	N/A
2.11 - Cost per CYP generated (exclusive of non-service delivery costs)	N/A

WISH2 is the only component contributing to this output and implementation is through MSI and IPAS for West and Central Africa (covering Chad, DRC, Mali, Mauritania, Niger and Senegal) and IPPF for Eastern and Southern Africa (covering Burundi, Ethiopia (Tigray/Afar/Amhara only), Madagascar, Somalia, South Sudan, Sudan and Zambia).
[note] Zambia is funded through a bilateral buy-in from FCDO Zambia rather than APEX funds.

Over the review period, none of the implementing partners began delivery against the output indicators. In lieu of inception phase milestones, the programme have been assessed against the procurement timeline and delivery of the inception phase deliverables as outlined in the ToRs.

Deliverable(s) for this review	Progress
Commercial: Procurement timeline as set out in Business Case:
WISH2 implementation phase starting in April 2024.	Substantially not met: / Contracts with MSI and IPPF signed September 2024, / Mobilisation from October 2024, / Implementation phase started March 2025.
Inception phase: Activities set out in WISH2 contracts within 6 months of mobilisation (priority activities for this output in bold):
Make all administrative, logistical and management arrangements to facilitate the launch and delivery of the programme in the implementation phase, including securing insurance for medical negligence.	Met: / Inception phase completed March 2025 / Team and country leads recruited in 12/13 countries, and subs contracted. / Inception phase workshops in Nairobi (IPPF) and Dakar and Kinshasa (MSI) / Ipas registration not yet completed in Chad and Mauritania delaying implementation. This is not within control of suppliers.
Develop, in agreement with FCDO and the E&L Supplier, a comprehensive results framework and methodology for measuring results including for Key Performance Indicators (KPIs), drawing on learning from WISH.	Met: / KPIs and Performance Indicator Reference Sheets on track. / Development of WISH2 results framework broadly on track despite some technical and definition challenges with some indicators. These are expected to be resolved in line with agreed timelines.
Establish relationships with relevant partners / including government, FCDO official(s) at post and development partners and ensure all key programme governance mechanisms are fully in place.	Moderately not met: / Dual lock agreements signed. / Governance mechanisms for the consortiums in place. / Country steering committees established. First meetings taken place in 4/13 (2 in WACA, 2 in ESA) countries. / 3 Technical oversight groups established by FCDO advisers.
Contribute to the design of, and make provision for, ongoing engagement with WISH Evidence and Learning.	Moderately exceeded: / Ways of working agreed between OPM and IPPF/MSI, / E&L workshop attended and active engagement with E&L programme.
Production of Inception Phase deliverables.	Met: / All deliverables submitted. Country level sustainability frameworks and safe abortion ecosystems frameworks are due by month 12 and expected by August (month 10).

Briefly describe the output’s activities and provide supporting narrative for the score.

This output, judged against procurement timelines and inception phase deliverables had mixed achievement. WISH2 began implementation as planned within six months of mobilisation in all countries except for Chad and Mauritania which are delayed by registrations in country of Ipas. The impact of delays on Output 2 is more severe than Output 1 (highlighted above in bold; delayed registration in Chad and Mauritania and delayed convening of country steering committees), as this has delayed the move to mobilisation for clinical work so on this basis this work against this output has moderately not met expectations.

As outlined above, the operating context for WISH2 shifted significantly over this reporting period, with implications for the design of some parts of this output.

In Sudan, geographical selection took significant negotiation because of efforts to ensure activities included worst affected locations whilst balancing risks. In Madagascar, due to donor cuts, the programme shifted to focus on systems strengthening and policy engagement with limited service-delivery support focussed on engagement at sub-national level with health management teams.

As with output 1, the inception phase provided an important opportunity to map existing work and identify opportunities for greater alignment with FCDO’s bilateral programming and other Centrally Managed Programmes, other donor programming and government priorities. In South Sudan, the programme has not yet achieved adequate alignment with the approach used in the Health Sector Transformation Programme which is co-funded by FCDO and this issue has been made more urgent by loss of the USAID Momentum programme. In DRC, the WISH2 partners have demonstrated their ability to pivot to respond to the Eastern DRC crisis. For example, in response to the shift in needs, Ipas has scaled up their emergency-sensitive services, such as the provision of services tailored to GBV survivors (psychosocial support and medical care like emergency contraception, STI treatment), and the provision of minimum packages of SRH services in line with Minimum Initial Service Package. They are also working closely with UNFPA to support referrals for services that UNFPA cannot offer (e.g. abortions) enabling a more comprehensive offer of care.

An output 2 technical oversight group was established by FCDO with service delivery partners which focussed on clinical due diligence to ensure that IPs were monitoring and managing risks associated with supporting service delivery in both public and private sectors. MSI was slow to deploy appropriate clinical expertise for WISH programme oversight in the inception phase, but this has since been improved. The pharmaceutical licensing, procurement, storage and good distribution practice pillar of the clinical due-diligence framework was delayed by lack of a policy owner and technical expertise in FCDO for the relevant rule under the Programme Operating Framework (PrOF). FCDO is now contracting externally quality assurance of implementing partners and oversight of their delivery chains.

In Chad and Mauritania, the main implementing partner is Ipas. There have been significant delays in registering the NGO within those countries (both countries still awaiting registration at the end of the inception phase). This, alongside a lack of country footprint and experience of public service support to facilities, has delayed the start of service delivery support. FCDO has been working closely with MSI to strengthen the oversight they provide to their sub-grantee Ipas.

Describe any changes to this output during the past year and any planned changes as a result of this review.

No changes have been made. The log-frame milestones and indicators are still being finalised and the agreed version will be used for future annual reviews.

Lessons learned this year and recommendations for the year ahead

1. FCDO and MSI to agree by September 2025 performance objectives for their role as consortia leads, on Chad and Mauritania for the next six months.
2. FCDO Regional Lead, working with Post in Juba, to agree action plan by September 2025 with IPPF on how WISH2 will harmonise with HSTP approach and revise workplan and geographical locations as required.
3. IPs to identify options to improve safeguarding reporting in health facilities and suggest action plan by October 2025.
4. FCDO Regional Lead and MSI team to prioritise visits to Chad and Mauritania to support the programme starting implementation and identify key risks and mitigations by October 2025 that need to be put in place.

Output Title	SRHR policy and systems environment / Improved policies and legal framework to support gender equality, effective government financing, commodity security and SRHR service capacity.
Output number:		3	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?

Indicator(s)	Milestone(s) for this review	Progress
3.1 - KPI: % of countries with ≥6 milestones on the pathway to national ownership over the last 3 quarters (rolling quarter average). Target: 75%	N/A	This indicator has been revised for clarity as part of work on the KPI framework: / 75% of countries with ≥ 2 milestones on the pathway to national ownership per quarter
3.2 - A safe abortion ecosystem milestone indicator (to be defined during inception phase)	N/A
3.3 - A tackling rollback SRH Rights milestone indicator (to be defined during inception phase)	N/A
3.4 - Number of accountability platforms/client feedback systems established/strengthened; eg enabling civil society/clients to have the ability to meaningfully participate in the design, provision, and evaluation of SRHR provision/policy.	N/A
3.5 - Mean % annual budget execution on (an agreed) FP budget line OR Number of countries that had an increase FP budget allocation since last annual budget	N/A

WISH2 (MSI, IPPF) and WISH P&S components (Palladium) contribute to this output.

In lieu of milestones, we are assessing success for output 3 against the procurement timeline and delivery of WISH2 contract ToR deliverables (see progress set out in table under output 2), the WISH Policy and System contract ToR deliverables (up to 5 April) and the ONS MoU.

Deliverable(s) for this review:	Progress
Commercial: Procurement timeline as set out in Business Case:
WISH P&S component implementation expected to start in April 2024.	Substantially not met: / Delayed contract with Palladium signed December 2024, / Mobilisation January 2025, / Inception phase started February 2025 / ONS MoU signed July 2024.
Palladium: Inception phase activities expected by end March 2025 as set out in contract
Make all administrative, logistical and management arrangements to facilitate the launch and delivery of the programme in the implementation phase, according to the approved programme design and approach.	Met: / Teams and country leads appointed, subs contracted. / First inception phase workshop (Feb)
Establish relationships with relevant partners including government, FCDO official(s) at post and development partners and ensure all key programme governance mechanisms are fully in place	Met: / Dual lock agreements secured in all countries in the Policies and Systems component except Kenya. / Attendance at E&L workshop. / Too early to assess engagement with Post.
Contribute to the design of, and make provision for, ongoing engagement with WISH Evidence and Learning.	Met: / A Ways of Working Compact agreed between OPM and Palladium. / E&L workshop attended and active engagement with E&L programme. Discussions on ToC have progressed and a plan set out.
Production of Inception Phase deliverables: / Exit and Transition Plan, Risk Register, Due Diligence and Finalised ToC	Met: / Palladium Team established including downstream partners with regular meetings in place. The first two Milestones have been delivered: Exit and Transition Plan for Month 1 and Risk Register and Due Diligence for Month 2.
ONS: activities expected by end March 2025 as set out in MoU
ONS Inception Phase deliverables include the submission of the first quarterly report; the second quarterly report and an overall inception report, Scope of Work documents for each country once scoped, and concept notes for new activities proposed during this period.	Moderately exceeded: / Quarterly Reporting to FCDO agreed timeframes [including Inception Reporting.] Scoping Work conducted and fed back to FCDO with Concept Notes prepared and submitted. / Attended inception phase workshops of WISH Learns and P&S. / Established and held the First Data Panel Review meeting in March 2025 with proposals prepared in a timely manner.

Briefly describe the output’s activities and provide supporting narrative for the score.

Despite significant delays to procurement of the lead WISH P&S supplier (Palladium) at the start of the year, all Implementing Partners are now contracted, and inception phase activities have progressed as planned. On this basis this output has been considered to meet expectations.

Palladium are still in their inception phase. Country Leads have established relationships with Posts and host governments. As outlined above with WISH2, ensuring that these country leads develop a close working relationship with Post will be critical to the success of this component. FCDO DRC noted that it is ‘extremely helpful’ to have a demography expert to work with under Palladium. Impressing upon Palladium the need to build strong relationships and work closely with posts will be a priority over the coming year (more on this under output 5).

The challenges of rollback across the continent have grown during the reporting period. Across the programme, WISH-D has been designed to work to protect rights and within each component there are number of subs with significant expertise on rollback and reproductive rights.

There are, therefore, considerable opportunities (for example through thematic technical oversight groups and communities of practice, learning events or annual programme reflection workshops) for implementing partners to learn from each other within and between components on issues such as countering rollback and policy influencing to ensure that these approaches permeate activities in all outputs. However, due to the way in which the programme is contracted out to different leads there is a real risk of silos and potential for the programme to fail to realise the ways in which it can be more than the sum of its parts. There are multiple areas in which greater coordination would ensure the programme could deliver more, but rollback is at the forefront of these. A key priority for the next reporting year to establish clear ways to coordinate and collaborate across components and to define the collective offer of these subs to the programme and to the FCDO (see recommendation).

It has also become increasingly difficult to advance global consensus on SRHR through multilateral for a within the reporting period. However, regional initiatives are increasingly demonstrating that they have more traction. WISH-D is well positioned to work through these regional initiatives through its expert health diplomacy at post and the programme’s civil society networks and champions within government. For example, within the reporting period, a key success has been the UK’s support to the African-led Ouagadougou Partnership, a long-standing, regionally-led partnership that aims to improve access to family planning in Francophone Africa.
In October 2024, the UK hosted the Partnership’s annual donors meeting. This enabled exchange on progress (and challenges) in the region, learning from regional and international experts, and stronger understanding of current investments. Our leadership demonstrated UK support for African-led partnership, and improving access to SRHR. We continue to actively participate in partnership activities (including monthly donors' meetings) to maximise UK support, including through WISH-D.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made. The log-frame milestones and indicators are still being finalised and the agreed version will be used for future annual reviews.

Lessons learned this year and recommendations for the year ahead

1. FCDO to engage with OPM to agree by December 2025 how capacity can be built through learning between partners with specific expertise e.g. Ipas and Engender Health to support implementing partners on WISH2 on approaches to identifying and countering rollback and other areas which need strengthening.
2. FCDO to convene first technical oversight group on rollback by the end of July 2025. Through this refine and develop what is being proposed, and how this can complement the offer being developed through WISH Policies & Systems. Rollback to be priority theme at learning event planned for the second half of 2025
3. WISH2 country teams to review government engagement to ensure all relevant ministries/authorities are engaged and aware of relevant WISH2 activities that fall under their portfolios (e.g. Ministries of Youth, Education, Family/Women, and Communication)
4. FCDO to strengthen the level of engagement between Palladium and Posts through establishing regular meetings with Post leads to monitor engagement and securing Payment linked KPI on post engagement, by the end of Palladium’s inception phase.

Output Title	Evidence and Learning: / Evidence-based innovations and practice shared globally to increase women’s choice and access to SRH services and rights.
Output number:		4	Output Score:	A
Impact weighting (%):		15%	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
4.1 - Number of new evidence/knowledge products generated by WISH-Dividend shared with relevant stakeholders	None set	N/A
4.2 - Number of different dissemination formats utilised in sharing evidence/knowledge products and findings (e.g. data dashboards, word documents, Twitter bites etc)	None set	N/A
4.3 - Number of views or downloads of generated evidence/knowledge products	None set	N/A
4.4 - Number of examples where WISH evidence and learning findings influenced WISH-Dividend programme activity design.	None set	N/A
4.5 - % of recommendations overdue in WISH2 tracker at end of last quarter (agreed written recommendations from Annual Reviews, field visits, TPM reports and quarterly/thematic meetings).	None set	N/A
4.6 - Number of instances evidence/data/recommendations/ methods/ approaches from WISH-Dividend work is cited/referenced/replicated in other research/evaluation work within the SRHR sector	None set	N/A
4.7 - Average annual partner/Evidence and Learning team Engagement Score for WISH-Dividend	None set	N/A

The WISH Learns, Evidence & Learning (E&L) component is the main contributor to this output. Work is ongoing to consider how to capture the work produced by the other WISH Learns component: Global Goods, under this output. WISH2 and WISH P&S partners will contribute to this output in future.

In lieu of milestones, we are assessing success for output 4 against the procurement timeline and delivery of contract ToR deliverables for OPM and Guttmacher.

Deliverable(s) for this review	Progress
Procurement timeline.	Met: / E&L: Contracted in line with expected timelines. / Global Goods: Accountable Grant (AG) arrangement signed within expected timelines.
Make all administrative, logistical and management arrangements to facilitate the launch and delivery of the programme in the implementation phase.	Met: / E&L: Achieved. Inception broadly progressed as planned and timetable for transition to implementation expected to be met. / Global Goods: Achieved. Moved direct to delivery and no formal inception phase under the AG.
Develop, in agreement with FCDO and the E&L Supplier, a comprehensive results framework and methodology for measuring results including for Key Performance Indicators (KPIs), drawing on learning from WISH.	Met: / E&L: Development of WISH2 results framework broadly on track despite some technical and definition challenges with some indicators. These are on track to be resolved in line with agreed timelines. Initial discussions with P&S component held. / Global Goods: Unclear how Global Goods is to be included in programme results framework. To be resolved for next version of the logframe due July 2025.
Establish relationships with relevant partners including government, FCDO official(s) at post and development partners and ensure all key programme governance mechanisms are fully in place.	Moderately exceeded: / E&L: Achieved. Strong relationships built with programme stakeholders. Programme wide face-to-face workshop held February 2025. / Global Goods: Attended February programme workshop but integrating Global Goods component into the rest of the programme requires further work.
Production of Inception Phase deliverables.	Met: / E&L: Submitted on time with minor delays in some deliverables, and to required standards after revision. / Global Goods: Progressed actions against their internal workplan components.

Briefly describe the output’s activities and provide supporting narrative for the score.

During the review period, the E&L component was in its setup phase. Intended activities broadly progressed as planned. A contract was awarded to a consortium led by Oxford Policy Management (OPM) to lead the component, and the first three months of the inception phase were completed. A three-day MEL workshop in Oxford brought together E&L consortium members, WISH-D lead IPs, and the FCDO team.

The E&L component comprises three main workstreams: programme assurance and accountability, evidence generation, and learning & evidence use. Typical for MEL contracts, the scope is broad and the number of activities and deliverables is substantial, covering all WISH-D components and lead partners to a greater or lesser degree. This creates multiple dependencies which led to some delays in inception deliverables, driven in part by FCDO review timelines and OPM's consultative and inclusive approach with IPs. However, these minor delays did not materially impact the E&L component or programme more generally. However, because delivery against outputs is split across different Implementing Partners and contracts, each contracted at different times, there is a risk of siloed working. OPM is the only partner with a mandate to work across the entirety of WISH-D and so help coordination and collaboration across the components, but this in not their role and alternative mechanisms need to be established to prevent siloed working. (See related recommendation below)

Beyond these deliverables, strong progress was made building partnerships and a supportive MEL culture across WISH-D stakeholders. WISH2 partners and the E&L partner spoke highly about the relationships and trust built between them, spurred on by the Oxford workshop held in February 2025. Unlike the previous WISH programme, the E&L partner was on board early in WISH-D enabling collaboration and technical assistance on a set of deliverables, and an integrated approach. Further learning from WISH MEL has been adopted, perhaps most significantly, the approach to learning. WISH-D is set up as an adaptive programme and intends to use research undertaken by the E&L partner and IPs to improve the delivery and performance of the programme. The main vehicle for this is the 'learning agendas'. Three learning agendas were scoped at Oxford workshop: disability inclusion; countering SRH rights roll-back, and delivery in humanitarian settings. Work to develop research studies on measuring reach of SRH services to people living in poverty and people living with disabilities advanced through the period. WISH2 partners also noted that the WISH verification model has evolved for WISH2.

 For FCDO (and partners), while assurance and accountability remain important objectives, verification in WISH-D is also a tool for learning and improvement.

The volume of inception work placed pressure on the relatively small E&L partner and FCDO teams, and whilst partners are positive about MEL activities to date and future plans, they noted that these are resource intensive. For example, multiple MEL forums (e.g. Community of Practice, Evaluation Reference Group, bi-weekly OPM/WISH-D partner MEL catch-ups, Research Secretariat) add to the workload. OPM should seek efficiencies in its engagements with IPs. FCDO can also help efficiency, by for example making clear when a decision or conclusion has been reached and when an issue remains open for discussion and getting directly involved in discussions when relying on OPM as go-between is inefficient (see recommendation 2 below).

During the review period, an accountable grant arrangement was signed with the Guttmacher Institute to lead the Global Goods component. The Guttmacher Institute works with the Inter Agency Working Group on Reproductive Health in Crisis (IAWG) on this component. The Global Goods component comprises the production of research and analysis, as well as advocacy and communications to advance SRHR policy.

During the review period, the Guttmacher Institute initiated work on its research, ‘Abortion Worldwide’ and ‘Adding It Up’, preparing for the publication of key papers in 2025. Guttmacher began its regional and country-level policy activities, leading workshops on the Global Gag Rule and the changing international sexual and reproductive health rights (SRHR) landscape at several international convenings. Additionally, Guttmacher’s Research, Policy, and Communications teams leveraged data from their analyses at multiple events at the UN Commission for the Status on Women. IAWG transitioned to its new host organisation, the Canadian Partnership for Women and Children’s Health (CanWaCH), executing a MOU between CanWaCH and IAWG’s leadership. IAWG activities, including on the SRH Task Team and the Global Evaluation were put on pause during the reporting year as IAWG assessed the immediate impacts of the US policy announcements and subsequent funding cuts on members, partners and the humanitarian sector overall. Going forward, IAWG has identified four areas of focus in direct response to these new operational realities: advocacy, thought leadership, documenting the impact, and supportive tools and resources.

Representatives from the Global Goods component have engaged with other WISH-D programme actors, including the Guttmacher Institute participating in the Oxford MEL workshop convened by the E&L partner. IAWG have also met with MSI and IPPF under WISH2, to discuss ways in which they might collaborate to support WISH2 countries experiencing humanitarian crises. Work is ongoing between OPM and Guttmacher, supported by FCDO, to understand how to integrate evidence generated by the WISH-D Global Goods component into the delivery of WISH-D.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made. The logframe milestones and indicators are still being finalised and the agreed version will be used for future annual reviews. The output wording and indicators in the table above were based on the business case and predecessor programme WISH and are being revised to reflect a more developed understanding of this component. This will better reflect WISH-D’s planned extensive use of evidence and learning to adapt delivery of the programme. These changes will be in the revised logframe planned for July 2025. This includes work to incorporate performance data from Guttmacher into the results framework to better capture the performance and effectiveness of the Global Goods component.

Lessons learned this year and recommendations for the year ahead

WISH-D built on learning from WISH MEL. Nonetheless, some challenges arose during the period.
1. Delivery against outputs is split across different Implementing Partners and contracts, each contracted at different times. There is a significant risk of the components working in silos. SRO and OPM to establish mechanism for coordination across the programme within the first six months of the next reporting year.
2. OPM to provide an assessment on engagement with IPs through the MEL forums, when they have all been initiated, with recommendations to improve efficiencies as required, by December 2025.
3. OPM, Guttmacher and FCDO to agree a proposal to capture the work of the Global Goods component, including relevant reporting into the WISH-D logframe and the engagement required to support this, by December 2025.

Output Title	Demographic transition: / Policy environment (national, regional & international) Countries better able to apply demographic data/forecasts to respond to future population needs and achieve accelerated demographic transition through more effective investment in human capital and empowerment of women and girls.
Output number:		5	Output Score:	B
Impact weighting (%):		10%	Weighting revised since last AR?	NA

Indicator(s)	Milestone(s) for this review	Progress
5.1 - DT demand: number of country governments or regional institutions requesting demographic data analysis/forecast support as a result of WISH-D support	N/A
5.2 - DT evidence use: number of examples where governments have used DT data/evidence for decision-making as a result of WISH-D support	N/A
5.3 - DT policy change: number of new policies/guidelines developed for 5+year change citing data/evidence generated as a result of WISH-D support	N/A

The WISH P&S component (ONS, Palladium) contributes to this output. In lieu of milestones, we are assessing success for output 5 against the delivery of the WISH-D P&S contract ToR deliverables (up to 5 April).

Deliverable(s) for this review	Progress
Commercial: Procurement timeline as set out in Business Case:
Procurement timeline	Substantially not met: / Delayed contract with Palladium signed December 2024.
Inception Phase: Activities set out in Palladium contracts/ToRs due by end of March 2025:
Make all administrative, logistical and management arrangements to facilitate the / launch and delivery of the programme in the / implementation phase.	Met: / All Country Leads recruited. / Inception workshop held.
Develop, in agreement with FCDO and the E&L Supplier, a comprehensive results framework and methodology for measuring results including for Key Performance Indicators (KPIs), drawing on learning from WISH.	To early to assess this as Palladium’s deadline for its results framework is the end of the inception phase.
Establish relationships with relevant partners / including government, FCDO official(s) at post / and development partners and ensure all key / programme governance mechanisms are fully in place.	Met: / Dual lock agreements secured in all P&S countries (with the exception of Kenya). / Attendance at E&L workshop. / Too early to assess engagement with Post / ONS and Palladium ways of working agreement not yet finalised.
Contribute to the design of, and make provision for, ongoing engagement with WISH Evidence and Learning.	Met: / A Ways of Working Compact agreed between OPM and Palladium. / E&L workshop attended and active engagement with E&L programme. Discussions on ToC have progressed and a plan set out.
Production of Inception Phase deliverables.	Met: / All deliverables on track. Exit plan, risk register, DDAs and ToC submitted. Further deliverables due May-July 2025.
ONS Inception Phase deliverables include the submission of the first quarterly report; the second quarterly report and an overall inception report, Scope of Work documents for each country once scoped, and any concept notes for new activities proposed during this period.	Moderately exceeded: / ONS has submitted Quarterly Reporting to FCDO agreed timeframes [including Inception Reporting] Scoping Work conducted and fed back to FCDO with Concept Notes prepared and submitted. The First Data Panel Review meeting was also held in March 2025 with proposals prepared in a timely manner.

Briefly describe the output’s activities and provide supporting narrative for the score.

The WISH Policies & Systems (P&S) component delivers this output on demographic transition. The key implementing partners are (1) a consortium led by Palladium and (2) the Office for National Statistics (ONS). They will provide flexible technical assistance on demographic transition and SRHR in seven countries in Sub Saharan Africa (Nigeria, DRC, Tanzania, Kenya, Uganda, Malawi and Mozambique). The programme will support governments by providing technical assistance to help improve their capacity to generate, use, and apply demographic data and evidence for effective policy and planning so that they can better plan and respond to future population needs.

The Palladium Consortium began work on their inception phase in late January 2025. Therefore, this annual review only covers the initial two months of early mobilisation. Dual lock agreements were signed with all P&S countries, except Kenya. These agreements are a new way of working for the FCDO, but have proven particularly useful for WISH-D, to ensure robust conversations on the proposed regional programming in country. Whilst the process to secure these agreements can be time consuming, they are of real value in agreeing expectations and establishing ways of working. This was particularly the case with WISH P&S where the component is a new part of the programme (less so for WISH2 where the programme is building on established ways of working from WISH1).

Suspension of donor funding to large parts of the health sector in WISH P&S countries soon after contracting meant that this component has had to rapidly review and adapt the scope of their work. This encompassed a rapid analysis of the impact of donor cuts and ongoing conversations as the implications become clear of where and how to best engage to support system strengthening as a part of a reform agenda. In particular, the suspension of the Demographic and Health Survey (DHS) programme means that there is likely to be gaps in the demographic data in WISH P&S countries. This will make it more difficult to achieve output 5.2 on promoting demographic transition evidence use, with less timely data available. However, this also presents opportunities to look at new innovations and ways to support the development of smaller, and less costly, data sets that can still meet similar needs.

Crucial to the future success of this component will be the extent to which the design enables agility so that Palladium and team are well placed to provide flexible technical assistance. There is no doubt this programme is operating in a period of rapid change. It will be crucial that this component is able to rapidly flex and pivot, working closely with FCDO posts to ensure alignment, political acuity and strategic thinking. Concerns were raised about budget allocation, where early planning has suggested full budget allocations over each year, which will hinder the potential for the programme to be responsive to new opportunities. Palladium will need to borrow from frameworks that deliver flexible and adaptive programming to ensure there is enough space in plans to meet the brief. Specific recommendations are included for the remainder of the inception phase to address these concerns.

During ONS inception phase (July - December 2024), ONS carried out scoping in the WISH-D P&S countries, and other WISH-D countries where ONS has an existing footprint. Experts from relevant business areas of ONS (the international development team, population statistics, data science campus, methodology and quality directorate) along with colleagues from FCDO country offices, were involved in scoping out population data needs and identifying where WISH-D funded ONS interventions could add most value. Scoping was undertaken remotely, or by using visits which were already planned, either for early WISH-D funded activity, or other ONS ODA funded activities. Specific scoping visits were undertaken in Nigeria, DRC and Somalia.

Recognising the risk that ONS could be quite detached from the rest of WISH-D, ONS have established a Data Review Panel, which will meet quarterly, drawing leads from across the programme to review ONS proposals and to identify ways in which these could better link up with other activities the programme is delivering or engaged in. This Review Panel has met once so far and supported proposals for specific workstreams on population projections in Tanzania, vital statistics and administrative data in Nigeria, and vital statistics in Uganda.

Both Palladium and ONS have engaged and contributed to cross WISH-D meetings on evaluation and learning, value for money, sustainability and theory of change reviews. This engagement should contribute to delivery of output 5 over the lifetime of the programme.

Wilton Park Roundtable on Demography in Sub-Saharan Africa

In addition, the FCDO WISH-Demography sub-team successfully bid for a Wilton Park high-level roundtable titled: “Towards Demographic Dividends in Africa: action and investments”. The event will be held in July 2025 and will bring together senior Government officials from WISH P&S countries, academic experts, representatives from international organisations, FCDO and the World Bank. The objectives include developing a shared understanding of key demographic trends, drivers of demographic transition, and their implications for SSA’s future growth, security, climate and human development and will set in motion key areas of work under the WISH P&S component of the programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes have been made to the definition of this output. The logframe milestones and indicators are still being finalised and the agreed version will be used for future annual reviews.

There have been a few key changes to the activities and delivery of this output:

1. Contract amendment for Palladium: this is currently underway in collaboration with FCDO Commercial Advisor with a VfM focus, revised KPIs; travel and budget lines; recruitment of a new Malawi lead and other amendments as we move from Inception into Implementation phases.
2. Budgetary uplift for ONS: The original budget estimates were based upon maximising the synergies between the ONS other main project "High Quality Statistics that Improve Lives Globally" and WISH-D. The costing model used in the inception phase is no longer sustainable, especially in the current financing climate and an uplift from £0.9m to £1.15m in 25/26 was proposed and agreed.
Lessons learned this year and recommendations for the year ahead

1. Palladium country leads to share products – such as the political economy analyses and workplans - with FCDO staff at post, giving them ideally two weeks (at a minimum one week) to review. From the start of this reporting year, all products submitted to HQ should have incorporated FCDO post recommendations.
2. As part of work to finalise the KPI framework inception deliverable, Palladium and FCDO to agree a new payment-linked KPI which assesses whether Palladium is engaging effectively with FCDO Posts, and to agree a method for measuring this. This should be reflected in the finalised KPI framework due by end of June 2025.
3. Palladium to keep an agreed portion of their budget uncommitted for emerging opportunities or to respond to unforeseen events (e.g. budget changes, or a new window of opportunity with a government) and as a drawn down facility for posts. This will be reflected in the finalised workplan by July 2025, and each subsequent year.
4. Palladium country leads to update their Political Economy Analyses every six months so that the team is aware of changes to the global and local context. This will ensure that workplans – which will respond to changes in the PEAs - are relevant and identify activities with the greatest impact.
## D: VALUE FOR MONEY

Key cost drivers and performance
WISH2 is the largest component by budget allocation, at £136m in total. This includes a £4m buy-in from FCDO Zambia in addition to APEX’s budget, all of which is managed within the WISH-D business case allocation. Within this, MSI’s largest cost area as per their proposal is staff costs, which are 39% of their budget. For IPPF, the largest cost area is frontline activities at 35% of their budget; staff costs are second at 33%. This difference will be in part due to IPPF’s larger budget overall and their more conflict-affected and therefore more costly delivery areas.

In year 1, payments have largely been on a milestone basis on approval of inception deliverables. A small amount of implementation was undertaken in March 2025, but it is too soon to assess performance or compare across countries

Table 5: Programme budget and expenditure by component
		Committed	Spend to end March 25	Remaining commitments
Design spend	Design costs	£14,400	£ -	£ 14,400
WISH2	MSI	£60,875,000	£ 4,789,031	£ 56,085,969
	IPPF (including £4m Zambia buy-in)	£75,125,000	£ 11,457,994	£ 63,667,006
Policy & Systems	Palladium	£9,999,079	£ 205,417	£ 9,793,662
	ONS	£5,450,000	£ 342,675	£ 5,107,325
WISH Learns (Evidence and Learning and Global Goods)	OPM	£4,445,000	£ 307,605	£ 4,137,395
	Guttmacher Institute	£2,412,425	£ 269,106	£ 2,143,319
Programme-funded posts	Programme funded posts	£2,498,190	£ 248,190	£ 2,250,000
	Wilton Park	£91,934		£ 91,934

	Total Allocated	£160,911,028	£ 17,620,018	£ 143,291,010
	Unallocated	£39,088,972
	Business case total	£200,000,000

The Policy and Systems contract, which accounts for 9.6% of the total budget, was only signed in December 2024, is still in inception phase, and accounts for only 3.1% of spend so far.

VfM performance compared to the original VfM proposition in the business case

The core, quantifiable VFM proposition within the business case (BC) was centred on service delivery outcomes (e.g. CYPs generated, DALYs averted). The BC cost-effectiveness analysis developed estimates using actuals from the first WISH programme – adjusting them to reflect the expected reduced spend on service delivery in WISH-D (due to increased work on health systems and SRHR policy) and the greater impact on equities due to the increased focus on the poorest. Focusing on providing SRHR access to the poorest groups can avert catastrophic out-of-pocket expenditure for those who need SRHR services, and provides an element of financial risk protection, which is a core criterion of the Disease Control Priorities 3 (DCP3) objective in this area.
[note] Disease Control Priorities 3 (DCP3) provides a review of evidence on cost-effective interventions to address the burden of disease in low- and middle-income countries (LMICs). More information is available here

However, as described in Section B, the estimates from the business case are now unaligned with the current programme’s projected spend and country portfolio because fewer countries were chosen during design phase, and budget allocations were prioritised for the most fragile countries and those with the greatest SRHR need. The country prioritisation exercise was informed by varying projected impact estimates (driven by the variance in country unit costs) throughout and VFM considerations were central in the strategic discussions that ended with the selection of the 12 priority countries. The costs are higher to deliver SRH services in these contexts.

Work during the inception period to develop a VFM framework was coordinated by the Evidence and Learning partner and supported by FCDO Economist, in collaboration with relevant IPs. OPM worked with IPs to agree VFM indicators (and unit cost calculation methodologies), VFM case study questions, and a VFM report template; which all WISH-D partners can report on. Despite the lack of a programme logframe, a zero draft VFM Framework was produced in March and is expected to be finalised by June 2025.

WISH-D's VFM framework is underpinned by FCDO’s VFM approach and assessment of the 5E’s (Economy, Efficiency, Effectiveness and Equity) and will utilise VFM Indicators, case studies and deep-dive learning questions for greater exploration of VFM. Policy and Systems is not yet included in this framework this work had not yet begun within the reporting period. The framework will track the indicators below, looking at VFM across countries, beneficiary classifications and outputs:

- Economy: cost for each channel of service delivery - i.e. cost of operating an outreach team and cost of operating a static public site.
- Efficiency: cost per SRH service delivered or CYP generated; Unit costs by country; rural/urban; high-impact client groups (i.e. Poorest, Youth, PLWD); and number of persons reached with community engagement and mass media campaigns.
- Effectiveness: cost per unintended pregnancy averted, cost per maternal death averted, Percentage of WISH clients who reported that WISH supported SBC activities contributed to their decision to seek services. Number of Nation/Sub-National SRHR policy/guidance improvements/reforms e.g increase in FP budget allocation, policy/guidance approval etc following WISH-D influence/support.
- Equity: percentage of services provided to youth, people with disabilities and the poorest.
- Cost-Effectiveness: The VFM Framework proposes that the programme will define research questions and make use of detailed case studies (by output) and guided evidence generation and learning agenda to assess the extent to which the programme outputs are meeting the overall impact statement in a cost-effective way.
This 5Es approach will be applied to all of the programme outputs. For example, under the SBCC output, we will assess the economy of community engagement and media campaigns, the efficiency of these campaigns in reaching the population and their ultimate effectiveness in leading the population to seek SRHR services - with discrete case studies highlighting VFM insights. Case studies and the learning agendas will be particularly important for assessing the progress and VFM of the programme’s work on SRHR policy, domestic financing, health systems strengthening and demographic transition, where the timelines for measuring success (Policy changes for SRHR and Demographic transition and increased domestic government SRHR allocations in WISH-supported countries) are more elongated than service delivery outcomes and the attribution of WISH more difficult to define.

Positive progress has been made on refining the calculation of cost per CYP – the intention is for this to be presented in multiple ways: a) as a unit cost of total programme expenditure; b) as a unit cost of service delivery expenditure, including a proportion of central and management costs; and c) as a unit cost of country-level service delivery expenditure. Although complex, this will give granular detail about the comparability of costs in different contexts and mark a significant improvement on identifying core service delivery unit costs compared to the original WISH programme.

Assessment of whether the programme continues to represent value for money

It is too early to draw on data to assess the value for money of the programme, as the programme’s logframe was not yet developed with this review’s reporting period and therefore there are no output indicators to measure progress against. However, WISH-D remains aligned to the FCDO’s development priorities under humanitarian (lift vulnerable people out of crisis and build state and community resilience to shocks through stronger, more locally-led humanitarian systems) and human capital (harness health and education opportunities and build human capital to drive growth).

Delays in procurement have led to a condensed inception period (which could carry the increased risk of sub-optimal planning but no evidence of this currently exists and we will continue to monitor this through routine reporting. The implementation period has also been condensed due to the extended procurement – but there is currently no expectation of lower overall results linked to this.

WISH-D implementing partner contracts were offered to the organisations of the winning tenders after an open and competitive commercial process, that included extensive early market engagement to attract many bidders. However, the number of final bidders was low and there may be lessons to be learned on FCDO reflections on the entirety of the tender process. The procurement and programme teams have undertaken a review of the entire procurement process for any lessons that can improve future procurements.

Overall, despite delays in the start of the inception phase, the signed IP contracts met the tender proposal’s central VFM proposition at the expected cost, and the contracts indicate that the programme is on track to meet the central VFM proposition.

E: RISK

Overview of risk management
WISH-D is a complex programme delivering across a diverse geographic portfolio which includes fragile and conflict affected states (FCAS). The overall risk rating for this programme is major. Risk appetites as per category are as follows:

Strategy & Context	Policy & Programme Delivery	Public Service & Operations	Financial & Fiduciary	People	Reputational	Safeguarding
Receptive	Receptive	Cautious	Receptive	Cautious	Minimal	Cautious

The Financial and Fiduciary appetite was revised in December 2024 period following a prompt from APEX risk lead, noting the additional challenges of fraud prevention in FCAS.

The WISH Team have been actively managing risks and proposing mitigations through a range of internal and external mechanisms including regular team Risk discussions around the Delivery Plan, identifying new and emerging risks through external and internal reporting.

The programme is not eligible for ICF. Climate risks considered throughout programme design were mainly around the impact of travel for outreach, monitoring/transport of commodities on the environment, and the impact of climate change on health systems and supply chains.

The programme addresses gender and disability issues by strengthening health systems to scale-up sustainable, inclusive access to integrated SRHR services, with a Leave No One Behind and rights-based approach reaching the poorest, young women, displaced women and people with disabilities (PWD).

Since the programme began, two severe risks have emerged regarding Policy & Programme Delivery and Strategy & Context:
- The UK ODA budget cuts; scaling back on planned activities with impact on the results, continuity and effectiveness of existing and planned initiatives. Any cut will necessitate reprioritisation and/or reduced scope of interventions.
- Other donor cuts and increasing traction of rollback policies: restricted space in which to deliver SRHR due to legislation, the politicisation of women’s rights and increasingly regressive social norms; increasing fragility of health sector limiting opportunities for public sector strengthening e.g. UNFPA has estimated USAID funded between 20-60% of reproductive health commodities in many WISH-D countries.
  [note] For example. US funding previously accounted for 29% of all SRHR supplies in Zambia (UNFPA 2025).

Recommendation: FCDO and IPs should continue to closely monitor the impact of the above risks on the commodity supply chains, and ensure WISH-D’s technical assistance offer is deployed effectively to support the mobilisation of domestic financing to fill the gap, where possible.

Due diligence in WISH-D
Only one partner (Guttmacher) required a full due diligence assessment (DDA), as commercial partners (OPM, Palladium, MSI, IPPF) are covered by other assurance processes. ONS, as a government agency, are exempt from the DDA process.

Nevertheless, repeating the approach taken in WISH, because of the level of perceived risk when working with vulnerable women, the WISH2 partners were both subjected to enhanced DDA processes during the reporting period – with a focus on downstream delivery, clinical quality assurance and safeguarding. As FCDO’s SRHR Policy team was conducting a Central Assurance Assessment of IPPF at the same time, the FCDO WISH team fed in concerns and focus areas to the DDA lead. MSI’s DDA was jointly conducted by the PRO and the Social Development Adviser. Neither of these enhanced processes are satisfactorily concluded yet. The clinical due diligence is discussed above under Section C - Output 2.

MSI’s due diligence has highlighted concerns about the different levels of oversight MSI have for Ipas-led countries (Chad and Mauritania) and recommendations are being built to ensure MSI take accountability for ensuring Ipas has access to the support needed to deliver effectively (whether from MSI or Ipas own teams).

IPPF’s Central Assurance Assessment led to the creation of a high-level action plan on safeguarding, and work is ongoing to refine this and ensure it draws out specific actions that relate to WISH2.

As WISH2 pivots to focus on system strengthening and supporting provision in public sector health facilities, IPs will have less control over the outcome of a concern that is raised. Managing these downstream risks will be considered within the DDAs and be a part of work to strengthen the delivery of SRHR within public sector health facilities.

Recommendation: PRO ensures enhanced DDAs of WISH2 partners including clinical governance assessments are finalised ASAP, and no later than end of July 2025.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

WISH-D has six main implementing partners. They are considered in turn below. As outlined above, most of the reporting period was dominated by procurement processes. The WISH-D team engaged with Commercial Department to undertake a lessons-learned review which is underway. Recommendation: The procurement and programme team should finalise the review and share any lessons that can assist in improving future procurements.

Despite extensive early market engagement, the WISH2 tender did not receive an increased number of viable bids. A key instruction in the tender was that the primary bidder (i.e. the “prime”) for one WISH2 Lot could not sub-contract to the other (known as a “sub”). This was intended to break up dominance of large players. However, the result of this was both lead Primes (MSI and IPPF) therefore have had to sub-contract newer, less established partners in some countries (Zambia, Madagascar, Chad, Mauritania) where they could not sub-contract the other Prime. The positive of this is that WISH-D may build the market for SRHR expertise through these downstream partners in these contexts, but it has caused challenges in the inception period (e.g. delayed registration of Ipas in Chad and Mauritania)

WISH-D was allocated £28.5m in 24/25, and this was reviewed throughout the year. After initial delays in the WISH2 contracts being signed, the team returned £5m in July. Following the agreement of WISH2 contracts in the autumn, partners were asked to reforecast, which reduced the programme forecast to £22.5m. At the start of February, the planned move from inception to implementation was delayed while workplans were revised in response to FCDO feedback and spend was revised down further to £19.3m. In March, a final check on forecasts was made, resulting in an end of year forecast of £17.7m.

Whilst this represents significant underspend, this is in large part due to procurement delays which both delayed the inception phase and onboarding of IPs and pushed the completion of the inception phase into the last quarter of the annual year. The FCDO team prioritised taking additional time to refine deliverables to get the foundations of the programme right over meeting spending forecasts for the year. Due to proactive communication with the FCDO finance teams, the funding was able to be reallocated to support other programmes and humanitarian crises. Similar issues are not anticipated in future now the programme is in implementation.

Mobilisation payments of £2.5m were made to IPPF and MSI to support cashflow in the first six months of the programme. Finance Business Partner agreement was sought to ensure this was compliant with PrOF and HMT rules.

This spend of £17.7m enabled full mobilisation across WISH-D, including recruitment of the programme teams within MSI and IPPF; recruitment of country teams and set-up of country offices for WISH 2; inception phase activities (including equipment purchases) regionally and in country for WISH 2, WISH P&S and WISH Learns; recruitment and set up of Policy and Systems team within Palladium and of country leads across P&S countries. The programme is now set-up to deliver an ambitious set of results and learning.

Recommendation: PRO to meet monthly with WISH2 partners on finance to ensure close monitoring and clear understanding of FCDO expectations during the implementation period.

MSI Reproductive Choices – commercial contract
MSI have acted as a responsive partner, providing reporting on time and responding well to FCDO requests. Delivery to date has been largely in line with terms and conditions, with two minor issues being approved retrospectively (one procurement not advertised on Contracts Finder despite being over the threshold, and one change in key personnel). This is likely due to unfamiliarity with the terms and conditions and not a cause for concern.

Inception deliverables were received on time and content was adapted in response to FCDO feedback. Financial reporting is detailed and the team will work to improve proactive reporting of underspends, which were considerable this FY and to an extent avoidable. Delivery chain maps, asset registers and risk registers are regularly updated and contain a good level of detail. KPI framework has been agreed.

International Planned Parenthood Foundation – commercial contract
IPPF are a collaborative and responsive partner, providing reporting on time and responding well to FCDO requests. Delivery to date has been in line with terms and conditions. Inception deliverables were received on time and content was adapted in response to FCDO feedback. Financial reporting is detailed with accurate forecasting. Delivery chain maps, asset registers and risk registers are regularly updated and contain a good level of detail. KPI framework has been agreed.

Palladium – commercial contract
Palladium’s contract was signed in December 2024. They are collaborative and responsive, providing deliverables on time and responding well to FCDO requests and feedback. Delivery to date has been in line with terms and conditions. Inception deliverables were received on time (or extensions agreed) and content was adapted in response to FCDO feedback. Financial reporting is detailed with accurate forecasting. Delivery chain maps, asset registers and risk registers have been provided and contain a good level of detail. KPI framework is under negotiation.

Office for National Statistics – Memorandum of Understanding
ONS have engaged well across the board. They have a strong relationship at Post and with partner governments which has enabled them to develop strong concept notes. A Data Review Board has been established to facilitate coherence with other partners. Reporting is on time and a good level of detail. Forecasting is accurate.

Oxford Policy Management – commercial contract
OPM have a unique role in the programme as their work relies on others’ inputs. Deliverables have been delayed many times over the inception period due to the staggered onboarding of Implementing Partners. Having said this, they have agreed a ways of working memorandum with key partners and formalised the ways of working over the reporting year. Delivery chain maps and risk registers are regularly updated and contain a good level of detail. Financial reporting is accurate. WISH-D scored them 73% on the latest Strategic Relationship Management scorecard, with the following comment: “content with performance so far. There are aspects of performance which remain untested at this early stage of the programme. Appreciate the strong team leadership, as well as flexibility exhibited throughout the inception phase. Positive performance in relationship management across the programme demonstrated in convening and organising their inception workshop.”

Guttmacher Institute – Accountable grant arrangement
Guttmacher Institute are a new partner for FCDO but have responded positively to FCDO requests for reporting and engagement. Guttmacher is the lead partner on the Global Goods component of WISH-D and work with the Inter Agency Working Group on Reproductive Health in Crisis (IAWG) under the accountable grant to submit joint narrative reporting on their activities. We have agreed that financial reporting is submitted slightly later than other partners at 45 days after the quarter ends, but forecasts are generally accurate. Risks are discussed at quarterly meetings and the project has a delivery chain risk mapping document that is subject to review throughout the life of the grant.

Programme funded roles (PFRs)
WISH-Dividend currently funds three PFRs at Grade 7 (Economist; Social Development Adviser; Demographic Transition Adviser). There is scope in the business case for additional roles and in the reporting period an updated VFM statement was submitted to the Centre for Delivery outlining planned future recruitment of a G7 MEL and VFM adviser, and a Governance Adviser. Recruitment for an SEO Demographic Transition adviser to lead on the Wilton Park even is underway. In the first year, PFRs accounted for 1.4% of total spend, if all roles are filled this will be within 2% of the programme’s forecasted spend. Performance of programme funded roles is assessed and managed through the FCDO’s existing staff performance management systems.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
The WISH-D MEL contract is described under Output 4. With WISH-D in its inception phase during the reporting period, no monitoring visits were undertaken in the review period. The E&L partner has scheduled its first routine country visits for autumn 2025. Three visits are scheduled for the 2025/26 reporting year. Substantial work, facilitated by the E&L partner, was undertaken on the WISH-D logframe. Changes will be reflected in a revised logframe that will be in place in July 2025. A mid-term process evaluation is planned for completion in March 2028.

This annual review was completed by the WISH-D programme team, reflecting that the programme was in its inception phase. Team members obtained feedback from lead IPs and Posts on progress to date, and achievements and challenges.

Evidence and learning
As outlined under Output 4, WISH-D has a continuous and integrated learning component. Key cross-programme research themes are organised into ‘learning agendas’, defined as a set of questions, planned activities, and products relating to a specific theme. The 3 learning agendas for Y1 (disability inclusion, delivery in humanitarian settings, and countering SRHR rollback) were prioritized in consultation with FCDO. In parallel, we also moved ahead with two of the 3 research studies that were prioritized in our ToRs. The two operations research studies initiated during inception are linked to inclusion by answering the following: How can WISH-D cost-effectively measure, using routine data, the uptake of services by people living in severe multi-dimensional poverty and by people living with a disability? The research will help WISH-D implementers monitor inclusion of these groups and potentially offer an approach that could be adopted by other service providers in the sector. Both studies will complete their main phase in the next reporting period. Additionally in this period, the programme established an approach to disaggregating data by clients’ displacement status.
The two key sources for beneficiary feedback – IP client exit interviews and the E&L partner mid-term evaluation – were not implemented in the reporting period.

No changes to the evidence base underpinning the programme and ToC arose in the reporting period. Changes in the programme operating environment are described in Section B. Work is ongoing to better understand how to integrate evidence generated by the WISH-D Global Goods component into the delivery of WISH-D.

	Date of last narrative financial report		Date of last audited annual statement
MSI	30/04/2025	MSI	15/07/2024 Annual Report & Financial Statements 2023 - MSI Reproductive Choices
IPPF	30/04/2025	IPPF	14/09/2024 - IPPF in 2023: Financial Statements | IPPF
Palladium	08/05/2025	Palladium	Not yet received.
ONS	07/04/2025	ONS	Not yet received.
OPM	15/04/2025	OPM	Not yet received.
Guttmacher	14/05/2025	Guttmacher	Not yet received.