## Annual Review – AfCFTA FY24/25

Title: African Continental Free Trade Area (AfCFTA) Support Programme
Programme Value £ (full life): up to £35,120,000		Review date: April 2026 / (covering results Jul-24 to Jun-25)
Programme Code: 301220	AMP start date: September 2021	AMP end date: September 2026

Summary of Programme Performance
Year	2022	2022	2023	2024	2025	2026
Overall Output Score	A	A	B	A	A
Risk Rating	Major	Major	Moderate	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/90000778.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0004601.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The African Continental Free Trade Area (AfCFTA) Support Programme is an FCDO‑funded programme that aims to facilitate the negotiation and implementation of the AfCFTA, with the objective of increasing intra‑African trade. Launched in 2021, the programme provides support on trade policy and trade facilitation, delivered through ODI Global (ODI) and TradeMark Africa (TMA) respectively. The programme operates across three geographic levels: at continental level through support to the AfCFTA Secretariat; at regional level within West Africa, with a particular focus on countries along the Lagos-Abidjan corridor (Ghana, Nigeria, Benin, Togo and Côte d’Ivoire); and at national level through engagement with individual State Parties.

This Annual Review considers results reported during the period from July 2024 to June 2025. This period captures the fourth year of the five‑year programme, placing it in its penultimate year and at a critical stage for assessing progress, results, and readiness for transition and close‑out. During this period, the FCDO’s spend for the AfCFTA Support Programme was £3.54 million. There was some delay between the end of the period under review and this review being completed due to the timelines associated with results reporting as well as short-term resourcing constraints in the team. In line with FCDO’s Programme Operating Framework, results from the subsequent, final year (2025/26) will be captured in a forthcoming Programme Completion Review (PCR).

Summary supporting narrative for the overall score in this review

The programme scored an A (outputs met expectations). In line with the programme’s results framework, scoring in this review is based upon quantity (i.e. whether volume of outputs was achieved) and quality (using the agreed quality assessment framework for the programme).

	Output	Assessment	Score
1	ODI - Continental AfCFTA negotiations and implementation supported through high quality research, capacity building and evidence dissemination	Met expectation / Two output indicators were met; one indicator was partially met	A
2	ODI - Country AfCFTA negotiations and implementation supported through high quality research, capacity building and evidence dissemination	Met expectation / All three output indicators were met	A
3	TMA - Continental AfCFTA negotiations and implementation on trade facilitation is supported through harmonising policies and standards, operationalising policies, installing digital solutions, and capacity building.	Moderately did not meet expectation / One output indicator met expectations, one moderately did not meet expectations; and the third output indicator was no longer required.	B
4	TMA - Country and Regional Economic Community (REC) AfCFTA implementation on trade facilitation is supported through harmonising policies and standards, operationalising policies, installing digital solutions, and capacity building.	Met expectation / Four output indicators were met, one indicator not applicable in this reporting period	A

As recommended in the previous Annual Review, Output 5 (‘Implementing partners deliver effectively, adapt to changing context and work in partnership to support AfCFTA negotiations and implementation’) has been removed for this review. An assessment of partner performance (ODI and TMA), including responsiveness and quality of reporting, is provided in Section F (Programme Management: Delivery, Commercial & Financial Performance).

Major lessons and recommendations for the year ahead

The key recommendations for the year ahead are as follows:

Strengthen the link between analysis and implementation (by the end of the programme cycle): During the final year of the programme (FY25/26) upcoming activities should integrate implementation planning alongside analytical work, including early consideration of design options, costing, adoption pathways and institutional responsibilities. Embedding a clearer “what happens next” approach will help accelerate uptake, support sustainability and maximise the long‑term value of analytical outputs.

Align ambition with realistic sequencing, timelines and risk management (within the final year’s planning period): The final year’s programme planning should place greater emphasis on realistic sequencing, built‑in contingency time and explicit management of dependencies. Where delivery relies on partners or complex systems, plans should allow flexibility and prioritise the most critical activities for completion by programme end, helping to protect overall results.

Combine technical delivery with political buy‑in and institutional ownership (throughout the final year): The final year of the programme’s implementation should provide balanced technical support with sustained investment in political engagement, change management and institutional strengthening. More emphasis should be placed on monitoring how capacity is utilised in practice, not just delivered. This will help to better understand and strengthen longer‑term outcomes.

Strengthen learning, synthesis and outcome‑level reflection (by the end of the programme cycle): During the programme’s final year it should prioritise synthesis and structured reflection on learning generated across the programme life, that will support sustain impact beyond the programme’s life. Key evidence and lessons should be consolidated and packaged for continental, regional, and national stakeholders to support continued impact beyond programme closure. The programme should also undertake a review of its contribution to outcomes using the outcomes‑mapping framework designed and piloted in FY24/25, to enable a more thorough, programme‑wide outcomes analysis during the final year (FY25/26).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change (ToC) for programme implementation is set out below. This builds on the high-level ToC developed within the Business Case and refines the pathways to impact for the programmatic support at the national, corridor, regional and continental levels. The ToC remains valid, and we do not recommend any amendment or re-prioritisation at the output or intermediate outcome levels at this stage.

FCDO has worked with implementing partners to ensure each programme workstream has a clear pathway towards achieving outcomes. These efforts were accompanied by rigorous prioritisation to ensure that workstreams were targeted towards delivering maximum impact.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The operational and political context in which the programme operates remains complex, involving multiple stakeholders and institutions at continental, regional and national levels. As negotiations on the core aspects of the AfCFTA near finalisation, emphasis has shifted increasingly towards implementation. Now in its fourth year, the programme is beginning to show more clearly where outputs are translating into specific outcomes. Given its focus on influencing institutions to effect change, the team has continued to apply an outcomes-mapping approach to assess where outcomes have been achieved and the extent to which these can be directly or indirectly attributed to programme activities and outputs.

During the year under review, FCDO worked with an independent consultant, through the Africa Directorate’s Third-Party Monitoring programme, to design a bespoke framework for embedding this methodology. The framework established a hierarchy of outcomes from early to intermediate to instrumental, set progress markers, and defined categories for assessing attribution: direct attributable change, distinct contribution to change, and indirect contribution within the wider context. Working with implementing partners, stories of change were developed using a bespoke template to analyse specific examples of programme impact. Initial case studies showed direct attributable contributions, and distinct contributions to change, in the negotiation of the AfCFTA Protocol on Investment, Nigeria’s participation in the AfCFTA Guided Trade Initiative, and trade facilitation improvements at the Ghana–Côte d’Ivoire border. The text box below highlights one of these Stories of Change, focusing on Nigeria’s participation in the AfCFTA Guided Trade Initiative.
Story of Change Highlight: Nigeria’s Participation in the AfCFTA Guided Trade Initiative: Nigeria’s participation in the AfCFTA Guided Trade Initiative (GTI) reflects a progression from political commitment to practical engagement, led by the Government of Nigeria. ODI’s work supported this process by helping to inform discussions on how GTI participation could be operationalised. Early analysis and engagement with the National Action Committee contributed to a shared understanding across ministries of the potential benefits of the GTI and the technical steps required, helping to address initial scepticism and coordination challenges. ODI’s research products, infographics and convening activities fed into technical exchanges with key ministries and the AfCFTA Secretariat, supporting assessments of Nigeria’s readiness to trade under the GTI. Targeted technical support to the Ministry of Finance helped inform coordination across Finance and Customs and sustain momentum through a complex process. Collectively, these contributions supported Nigeria’s timely gazetting of its GTI participation and the launch of its first GTI shipments, illustrating how evidence and technical inputs can complement government-led AfCFTA implementation.

The shift to implementation calls for an increasing focus on trade facilitation, customs cooperation, border efficiency, removal of non-tariff barriers, domestication of the protocols of the Agreement, and alignment of regulatory and legal frameworks at the country and regional levels. The programme is adapting accordingly, with a targeted focus on digital systems, corridor efficiencies, gap analyses, implementation frameworks (through National Implementation Committees (NICs)) and capacity building. Early indicators from the outputs delivered this year are already showing direct and specific contributions to institutional capacity and policy change. The guide to NICs is being embedded in the AfCFTA institutional structure, gap analyses are providing actionable recommendations which have been accepted by countries, clear plans are in place for the development and roll-out of the digitisation of certificates of origin at a continental level, and agreements have been signed between countries to improve border management along the Abidjan-Lagos corridor. Using the established methodology, further work will be undertaken in the final year of the programme to fully assess contribution to outcomes across the full programme life.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

The AfCFTA remains a key political priority for the African continent, with 54 countries having signed the Agreement and 49 having ratified it. As the focus on AfCFTA now transitions from negotiations to implementation, the demands on the Secretariat, Regional Economic Communities and Member States are arguably increasing in order to unlock the benefits in terms of trade volumes/values and sustainable economic growth. The needs of these institutions and partners are directly aligned with the programme in terms of its delivery ambitions, technical expertise and target outcomes. Meanwhile support to the AfCFTA initiative and African trade remains clearly aligned with UK priorities, including those established through the UK’s Africa Approach and renewed approach to development partnerships. This Annual Review finds that the programme is performing well against its output targets, even as it shifts its focus more heavily towards supporting implementation and is starting to help build replicable models for effective delivery. As we transition into the final year of the programme, there is a significant opportunity to embed progress to date into tangible and measurable impact. This includes ensuring that key deliverables such as best practice guides, gap analysis methodologies and research findings can be replicated, scaled and utilised across the continent, as well as embedding lessons into future delivery and partnerships. On this basis, it is recommended that the programme continues.

## C. DETAILED OUTPUT SCORING

This section assesses performance against output milestones during the period July 2024 – June 2025 [1]. It covers four outputs, assessing delivery against agreed annual milestones. In line with the results framework, the outputs are scored on quantity and quality (using the agreed quality assessment framework for the programme). Outputs 1 and 2 relate to trade policy interventions (implemented by ODI Global), while 3 and 4 relate to trade facilitation interventions (implemented by TMA). Outputs 1 and 3 cover continental level interventions, while 2 and 4 cover country and regional level delivery.
[1] The reporting year follows a cycle ending in June and aligns with the independent review commissioned for TMA. The completion of the review was delayed to allow sufficient time for results reporting and for Co‑Water’s independent assessment to be finalised. Programme results for the subsequent assessment period (July 2025-June 2026) will be captured in the final Programme Completion Review (PCR).

Output Title	Continental AfCFTA negotiations and implementation supported through high quality research, capacity building and evidence dissemination
Output number:		1	Output Score:	A – met expectations
Impact weighting (%):		20 %	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 - Number of high-quality policy/research studies, documents and tools completed and disseminated which inform AfCFTA negotiations and implementation	8 studies/ briefs	A – met expectations / 8 reports/briefs completed: / Gap Analysis on Implementation of Investment Protocol (Economic Community of Central African States (ECCAS) and The Gambia) / Investment Protection Brief / Sustainable Development Brief / Guide on National Implementation Committees / AfCFTA Digital Trade Business Plan / Action Plan for AGII / Research Study on Textile Value Chains / Research Study on Geopolitics and the African Automotive Sector / Activities not completed: / Gap Analysis on Implementation of Digital Trade Protocol (ECCAS) Report and Brief
1.2 - Number of effective outreach, training and advocacy events which identify relevant opportunities for effective AfCFTA negotiations and implementation, brings them to the attention of stakeholders, and builds their capacity to respond to them	6 policy discussions/ trainings/ / outreach events	A – met expectations / 7 policy discussions/ training/ outreach events: / National Gap Analysis Awareness Creation Workshop, Ghana / REC Gap Analysis Awareness Creation Workshop, Cameroon / Side Event at AfDB Annual Meetings for dissemination of REC Gap Analysis Report / 3x NIC Support Workshops supporting Mozambique, Tanzania and Cameroon / Extra: NIC capacity building support for The Gambia, Sierra Leone and AfCFTA Secretariat / Digital Trade Masterclass on Implementation of the protocol at AfCFTA Digital Trade Forum, Zambia / Activities not completed: / Digital Trade Gap Analysis Capacity Building Research & subsequent Workshop / Support to the NIC focal point meeting
1.3 - Effective ongoing support provided to the AfCFTA Secretariat and UNECA ATPC on AfCFTA negotiations and implementation	4 Technical Advisors embedded	A – met expectations / 3 Technical Advisors in place: 1x Senior Investment Expert and 2x NIC Technical Advisors / Activities not completed: / 1 Senior NIC Technical Expert recruitment was not finalised

Briefly describe the output’s activities and provide supporting narrative for the score.

The agreed FCDO-ODI workplan for the year focused on three thematic areas – investment, digital trade, and national implementation – building directly on achievements from the previous year. Across these thematic areas, ODI delivery comprised of the following activity types: embedded experts, technical assistance, research & analysis, convening and capacity building.

Output Indicator 1.1:

A total of eight policy research studies and tools were successfully completed, including gap analysis reports for the Economic Community of Central African States (ECCAS) and The Gambia, both of which directly support AfCFTA Protocol on Investment (PoI) implementation by identifying concrete policy and regulatory reforms. The ECCAS report provided a region‑wide assessment of investment regulatory gaps, while The Gambia report identified priority legal and institutional reforms to align national frameworks with AfCFTA commitments. The research instigated active engagement from the relevant stakeholders in The Gambia, Cameroon and the Democratic Republic of Congo. The investment gap analysis methodology is now being rolled out to other countries.

There were delays in finalising the gap analysis on implementation of the Digital Trade Protocol in ECCAS and the accompanying brief, due to leadership transitions within the ECCAS Secretariat, resulting in reduced engagement during the second half of the year. Completion of this research was therefore deferred to the next year.

ODI worked with the Secretariat to produce a guide to best practice in the formation and functionality of National Implementation Committees (NICs), a key structure to achieve effective and coordinated implementation. The guide was presented to the AfCFTA focal points meeting in April, (whilst outside the reporting year) and has subsequently progressed through the formal process including being reviewed at a plenary in September 2025 before being sent to the Senior Trade Officials for consideration by all State Parties prior to submission to the Council of Ministers.

Two substantive research studies were completed following consultation with the Secretariat and a wide range of experts. These focussed on (a) the potential for regional value chains in the textiles and garments sector and (b) the impact of the evolving geopolitical landscape on the AfCFTA, with a deep dive focus on the African automotive sector. The research strengthened understanding of how global trends - such as rising economic nationalism, protectionist policies, and strategic competition between Western economies and China - are shaping Africa’s trade and industrialisation prospects under the AfCFTA and informed related policy discussions.

Output Indicator 1.2:

A total of seven policy discussions and outreach events were delivered during the reporting period, spanning continental, regional, and national levels. These included national‑level and REC‑level awareness‑creation workshops relating to gap analyses undertaken in Ghana and Cameroon, as well as an event at the AfDB Annual Meetings to further disseminate findings from the REC gap analysis. Support to NICs included three NIC support workshops for Mozambique, Tanzania, and Cameroon, alongside targeted NIC capacity‑building support for The Gambia, Sierra Leone, and the AfCFTA Secretariat. A digital trade masterclass on implementation of the Digital Trade Protocol was delivered at the inaugural AfCFTA Digital Trade Forum in Lusaka, Zambia. Certain planned activities not completed during the period included the ECCAS digital trade gap analysis capacity‑building research and workshop (given the gap analysis was postponed), as well as support to the NIC focal points meeting, which was rescheduled by the Secretariat to after the financial year.

Output Indicator 1.3:

This indicator assessed the impact of three embedded technical advisers within the AfCFTA Secretariat: one Senior Investment Expert and two NIC Advisors. While the original plan envisaged four experts, including a Senior NIC Advisor, this position was not filled, as the Secretariat was unable to complete the recruitment process before the end of the financial year. Despite this constraint, the advisory team delivered against core portfolio objectives. The Senior Investment Expert led critical workstreams supporting implementation of the Protocol on Investment (PoI). This included development of the Annex on the Rules and Procedures for the Prevention, Management and Resolution of Investment Disputes under the PoI; coordination of thematic policy briefs to strengthen continental awareness and capacity‑building; and enhanced private sector engagement and investment promotion efforts, including coordination of a PoI‑related gap analysis. The two NIC Advisors worked directly with the AfCFTA Secretariat to support the formation and coordination of National Implementation Committees, including providing Member States with the NIC formation guide, with best practices already being adopted by Rwanda, Tanzania and Uganda. Over the reporting period, they facilitated institutional meetings overseeing AfCFTA implementation and strengthened coordination across national and regional levels. They also provided research and analytical inputs on the status of NIC establishment across State Parties and Regional Economic Communities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In the absence of a Senior NIC Advisor, the two NIC Advisors absorbed additional responsibilities throughout the year, ensuring that agreed deliverables were met within original timeframes. This demonstrated that the existing level of embedded advisory support was sufficient to deliver the required outputs.

Progress on recommendations from the previous Annual Review (if completed), lessons learned this year and recommendations for the year ahead.

Progress, lessons and recommendations:
There has been a noticeable improvement in how the output workplan is structured and presented compared to the previous year. Building on this progress, greater emphasis could be placed on clearly articulating the specific activities to be delivered and how these are expected to contribute to intended outcomes and future use. Strengthening this results focus would support transparency, implementation planning, and more effective tracking of progress and impact.
ODI’s gap analyses were well received by Member State Parties and demonstrated clear relevance to AfCFTA implementation. To maximise their potential impact, synthesising key findings into more accessible and user‑focused formats would support wider uptake and application across a broader range of countries in the next year of the programme. This would help share clearer methodology, strengthen policy alignment, inform reform efforts, and enhance the contribution of the analyses to AfCFTA across multiple countries.

Output Title	Country AfCFTA negotiations and implementation supported through high quality research, capacity building and evidence dissemination
Output number:		2	Output Score:	A
Impact weighting (%):		20 %	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Number of high-quality policy/research studies, documents and tools completed and disseminated which inform AfCFTA negotiations and implementation (cumulative)	5 studies/ tools	A - met expectations / 5 studies / tools / Ghana Investment: Implications of the Investment Protocol Research Report / Ghana Women & Youth: Implementing the AfCFTA Women and Youth Protocol Research Report / Digital Trade Strategy for Nigeria within AfCFTA Research Report / Outsourcing and Digital Trade within AfCFTA for Nigeria / Digital Trade and AfCFTA for Nigeria
2.2 Number of effective and relevant outreach, training and advocacy events which identify relevant opportunities for effective AfCFTA negotiations and implementation, brings them to the attention of stakeholders, and builds their capacity to respond to them	7 policy discussions / trainings / outreach events	A - met expectations / 7 policy discussions / trainings / outreach events / Ghana Investment: Capacity Building on Investment Protocol / Ghana: Digital Trade Stakeholder Information Workshops / Ghana: Capacity Building on Digital Trade Protocol for Women & Youth Workshop / Nigeria: Launch of Presidential Committee on Digital Trade Workshop / Nigeria: Stakeholder Engagement to Set Up the Presidential Committee Workshop / Nigeria: Meeting of State Commissioners of Trade/Investment Workshop / Nigeria: Training to Implement AfCFTA Digital Trade Policies Workshop
2.3 Number of requests for research support from UK Missions supported which inform AfCFTA negotiations and implementation in-country – Rapid Research Window (RRW) Reports	4 reports	A - met expectations / 4 RRW reports: Cameroon, Côte d’Ivoire, Djibouti and Mozambique

Briefly describe the output’s activities and provide supporting narrative for the score.

This output covers country-level deliverables relating to AfCFTA implementation, with a continued focus this year on partnerships with Ghana and Nigeria.

Output Indicator 2.1:

Investment Protocol Alignment, Ghana: This research provided a systematic assessment of gaps in national policy, regulation, and institutional coordination. The work translated AfCFTA commitments into policy and regulatory recommendations aimed at strengthening transparency, improving institutional coherence, and enhancing the investor-friendliness. Feedback from senior government officials rated the work positively, with requests for continued engagement.

Women and Youth Protocol Implementation, Ghana: This study assessed structural and regulatory barriers faced by women and youth-led enterprises in Ghana, including access to digital trade services and investment. The research delivered an implementation roadmap and targeted policy recommendations to support inclusive trade participation. The findings were positively received by government and stakeholders at validation, with recommendations formally accepted and reportedly being used to inform policy design.

Digital Trade Strategy under AfCFTA, Nigeria: Given the interlinked nature of digital trade, outsourcing, and inclusion, three originally distinct studies were consolidated into a single, comprehensive national digital trade strategy for Nigeria aligned with the AfCFTA Digital Trade Protocol. The report addressed strategic alignment, barriers within Nigeria’s digital economy, and priority policy interventions to scale digital trade – particularly in business process outsourcing (BPO), e‑commerce, and women and youth participation. An implementation framework and roadmap were developed and accepted by government. The Nigerian Minister publicly stated that the research is informing policy design, particularly in priority areas such as payments systems and digital identity, demonstrating policy traction.

Across these outputs, the work bridged technical AfCFTA provisions with national policy realities, delivering practical recommendations that were validated, accepted, and in several cases actively used by governments. Positive stakeholder feedback and requests for further engagement suggest a positive contribution to advancing AfCFTA implementation.

Output Indicator 2.2:

All planned milestones were delivered, including capacity‑building workshops and policy engagements across Ghana and Nigeria. These activities strengthened the ability of government and stakeholder participants to understand, engage with, and operationalise key AfCFTA Protocols, including Investment, Women and Youth, and Digital Trade. Participant feedback scores consistently exceeded the minimum target of 7, with scores ranging between 7.8 and 8.4 out of 10. In Ghana, capacity‑building workshops on the Investment Protocol, Women and Youth Protocol, and Digital Trade Protocol enhanced stakeholder understanding of AfCFTA obligations and national implementation requirements. In Nigeria, a series of engagements were delivered supporting the launch and operationalisation of the Presidential Committee on Digital Trade. These activities achieved strong satisfaction scores (average 8.2 out of 10). The activities also generated broader visibility through national media coverage, reinforcing outreach and advocacy objectives.
Output Indicator 2.3:
Indicator 2.3 covers the delivery of Rapid Research Window (RRW) reports commissioned by FCDO country offices. The indicator was fully met, although delivery took place close to agreed deadlines, highlighting the need for improved planning.
The RRWs delivered analysis across priority AfCFTA areas, including digital trade, investment policy alignment and national implementation arrangements, tailored to each country’s needs in Cameroon, Côte d’Ivoire, Djibouti and Mozambique. Cameroon sought evidence on the opportunities and regulatory challenges of digital trade under the AfCFTA Digital Trade Protocol; Côte d’Ivoire requested analysis of its investment regulatory framework, with a focus on strengthening its Aftercare Unit to improve foreign direct investment retention; Djibouti focused on aligning domestic investment laws and its Free Zone regime with the AfCFTA Protocol on Investment; and Mozambique sought practical options to establish an AfCFTA National Coordination Committee to facilitate the coordination, monitoring and implementation of the AfCFTA. In Mozambique, the analysis directly supported follow‑on engagement related to the National Implementation Committee.
Across all cases, the RRWs translated AfCFTA provisions into practical, country‑specific insights and institutional regulatory recommendations. Delivery experience confirmed the continued effectiveness of RRWs as a demand‑led tool, while also highlighting the importance of early scoping and prioritisation to manage risks associated with compressed timelines. That said, delays in post‑delivery feedback, most notably from Mozambique, limited full assessment of outcome‑level impact, indicating a need for stronger follow‑up mechanisms in future cycles.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes.

Progress on recommendations from the previous Annual Review (if completed), lessons learned this year and recommendations for the year ahead.

Progress, lessons and recommendations:
Firstly, feedback on the investment and digital trade workshops delivered in Ghana and Nigeria was positive, indicating strong relevance and engagement. To further enhance impact, the implementing partner is encouraged to ensure that future workshops are targeted at the most appropriate stakeholders and institutions, with a clear focus on how the research and learning can be institutionalised and translated into implementation. This would support broader uptake and sustained influence beyond the immediate workshop participants.
Secondly, RRW reports were successfully delivered during the reporting period. To support more effective assessment and verification, and to better manage seasonal delivery pressures, any future RRW activities would benefit from earlier initiation and the inclusion of additional contingency time within implementation and reporting timelines.

Output Title	Continental AfCFTA negotiations and implementations on trade facilitation are supported through harmonising policies and standards, operationalising policies, installing digital solutions, and capacity building.
Output number:		3	Output Score:	B
Impact weighting (%):		30%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of policies, frameworks, and instruments developed and approved	Development of AfCFTA digital platform for electronic Certificate of Origin (e-CO): / Validated Business Process Architecture for the e-CO. / Project Implementation Plan with timelines developed. / Selection criteria for pilot countries developed.	A - met expectations / Project implementation plan with delivery timelines developed. [A] / Development of selection criteria for pilot countries. [A] / Actions not completed: / Validation of business architecture process for the e-CO system (following Technical Working Group recommendations were still pending and adoption by the AfCFTA Secretariat’s Inter-Ministerial Steering Committee). [B]
3.2 Number of high-quality training and capacity building activities delivered	Enhancing customs-customs cooperation and collaboration amongst selected State Parties through officer exchange. / National Trade Facilitation Committees (NTFCs) including Abidjan-Lagos Member States trained on AfCFTA Information-Sharing Platform.	B – moderately did not meet expectations / NTFCs including Abidjan-Lagos Corridor Member States trained on AfCFTA Information Sharing Platforms. [A+] / Actions not completed: / Facilitation of an exchange between 2x senior officers and 2x junior officers for selected State Parties, ensuring appropriate country selection for delivery of effective capacity building and information sharing. [C]
3.3 Effective ongoing support provided to the AfCFTA Secretariat on AfCFTA negotiations and implementation	Development of AfCFTA digital platform for electronic certificates of rules of origin (e-CO system): / One Business Analyst/Business Process Architecture Consultant procured to support with the implementation of the e-CO System.	N/A – milestone was amended / Action no longer required: / Consultant to support the implementation of the e-CO system was no longer required by the AfCFTA Secretariat within this FY year as decision taken to improve service in house of institution.

Briefly describe the output’s activities and provide supporting narrative for the score.

Output 3 focused on advancing AfCFTA trade facilitation through a combination of digital systems, targeted technical assistance and capacity building at continental and country level. The core activity was support to the AfCFTA Secretariat to operationalise the electronic Certificate of Origin (e-CO) system, a priority trade facilitation instrument under the AfCFTA Agreement.

Output Indicator 3.1:

Under this indicator, TMA made contributed to advancing AfCFTA trade facilitation through technical support to the development and piloting of the e-CO system. Validation of the Business Process Architecture (BPA) system requirements for the e‑CO system is a critical foundation for the development. However, finalising the BPA was slower than anticipated, as the Technical Working Group appointed to manage delivery requested significant revisions to ensure alignment with the World Customs Organization (WCO) framework. A revised draft BPA was presented in January 2025, however, Secretariat‑level validation had not been completed by the end of FY 2024/25 and therefore delivery here only partially met expectations within the timeframe. The development of stakeholder criteria for piloting was completed as planned, supporting structured engagement with Member States. However, while the technical components advanced, the overall system development and readiness for piloting changed as the AfCFTA Secretariat arranged to draw this process in-house.

Output Indicator 3.2:

Under this indicator, training and engagement activities for National Trade Facilitation Committees (NTFCs), Regional Trade Facilitation Committees (RTFCs), and AfCFTA Secretariat staff exceeded expectations. Training workshops on the Information-Sharing Platform strengthened coordination, reinforced trade facilitation frameworks, and improved operational understanding of AfCFTA commitments among Member States. Collaboration with the ECOWAS Commission’s Trade Directorate supported the identification of institutional capacity gaps, leading to the development of a comprehensive capacity‑building and implementation plan. However, planned peer‑to‑peer exchanges between AfCFTA Member States were not delivered during the reporting period, reflecting coordination challenges between the AfCFTA Secretariat and Member States. Despite this, NTFC members nevertheless reported that TMA support accelerated key processes and improved coordination across structures that had previously been characterised by fragmented approaches. At the same time, frequent turnover of NTFC members, delays in recruitment and execution, and persistent funding constraints continue to affect continuity.

Output Indicator 3.3:

Under this indicator, TMA planned to engage technical expertise to support implementation of the AfCFTA digital platform for the electronic Certificate of Origin. Linked to indicator 3.1, the impact of the BPA delays had knock‑on effects on downstream activities, including the recruitment of an external consultant, planned validation missions with RECs and shortlisted pilot countries scheduled for March 2025. The challenges reflected broader programme considerations such as timing, system complexity, and cross‑institutional coordination, rather than limitations in individual technical expertise. However, AfCFTA Secretariat experts demonstrated growing internal capacity by advancing the BPA development in‑house, reducing reliance on external consultants and reinforcing institutional ownership of the process.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following the decision at the previous Annual Review to remove Output 5, the weightings of the remaining outputs have been adjusted to align with revised delivery requirements. Output 3’s weighting has increased from 20% to 30% to reflect the scale and complexity of the activities involved, particularly its focus on systems‑related delivery and implementation.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Progress, lessons and recommendations

A key lesson under Indicator 3.1 is the importance of aligning ambition with realistic delivery timelines when supporting complex, multi‑country digital platforms. While early validation and system architecture design are necessary, they are insufficient on their own. Future programmes should ensure stronger sequencing from design to build and pilot phases, supported by clearer delivery ownership and robust risk management. Greater attention to dependencies - particularly Member State readiness, governance arrangements and resourcing - would improve the prospects for timely implementation.

There were no substantive changes to the output’s objectives, indicators or targets during the review period. However, delivery increasingly focused on operationalising digital trade facilitation tools, particularly the e‑CO system, in response to AfCFTA Secretariat priorities and implementation readiness. This involved refining the scope of technical assistance to ensure access to specialised, sustained expertise. As a result, planned adjustments included setting more granular milestone targets for the e‑CO pilot phase and strengthening the link between digital tool deployment and national‑level capacity building. These changes are intended to support effective uptake by State Parties and maintain momentum towards full implementation.

Overall, TMA delivered effectively in a technically complex area with ambitious targets. While some activities required more time and flexibility than initially anticipated, delivery demonstrated strong commitment and adaptability in response to evolving circumstances. Looking ahead, greater foresight in planning - particularly where delivery depends on other partners - alongside built‑in contingency time and realistic target‑setting, will support smoother delivery and maximise results for similar indicators in future programmes.

Output Title	Country and REC AfCFTA implementation on trade facilitation is supported through harmonising policies and standards, operationalising policies, installing digital solutions, and capacity building
Output number:	4	Output Score:	A
Impact weighting (%):	30%	Weighting revised since last AR?	Yes

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of high-quality technical designs and surveys	Border assessment of the Noe-Elubo, Seme-Krake and Sanvee-Kondje/Hilacondji completed	A – met expectations / Institutional Coordination of Border Management (ICBM) assessment of the Noe-Elubo and Seme-Krake borders completed and key identified interventions prioritised.
4.2 Number of policies, frameworks, and instruments developed, and approved	Institutional Coordination of Border Management ICBM Framework review	A – met expectations / Draft ECOWAS Institutional Border Frameworks development for review and adoption by Member States [A] / ICBM assessment of the Noe-Elubo and Seme Krake borders completed [A] / Bilateral Agreement between Ghana and Côte d’Ivoire signed [A] / Sustainable supply of renewable energy at the Akanu-Noepe Joint Border Post (JBP) [A] / Supply of clean water for the border facility, fire station and clinic at Akanu-Noepe JBP [A] / Refurbishment, supply and installation of sanitary facilities at the Akanu-Noepe JBP [A] / Refurbishment / supply of canopies for pedestrian walkway at the Akanu-Noepe JBP [A] / Actions partially/not complete / JBP Procedures and Operational Manuals at Noe-Elubo border developed in French and English languages for Member States [B] / Establishment and operationalisation of the Joint Border Management Committee for at least two borders (Noe-Elubo and Seme-Krake borders) [B] / National Trade Facilitation Strategies and Roadmaps for Côte d’Ivoire, Ghana, Togo and Benin, developed and implemented [B]
4.3 Number of IT systems and digital solutions harmonised and operational, and enabling hard infrastructure developed and operational	Customs to customs information exchange for Ghana, Côte d’Ivoire, Kenya, Togo, Begin, Nigeria, Burkina Faso, Mali and EAC.	A - met expectations / Interconnectivity on SIGMAT (the system for the management of goods in transit) enhanced for Côte D’Ivoire, Togo, Benin, Nigeria, Burkina Faso and Mali [A] / Development of bilingual training document [A]. / Enhancement of internet connectivity for border officials at the Elubo border. [A] / Provision of IT equipment and tools at the Elubo border: screens, laptops, desktops, and peripherals; network switches and routers, cabling and installation supplies and security screening devices. [A]
4.4 Number of high-quality training and capacity building activities delivered	Strengthening trade facilitation structures and frameworks	A+ - moderately exceeded expectations / ECOWAS’ Regional Trade Facilitation Committee’s (RTFC) institutional capacity identified and strengthened [A+]

Briefly describe the output’s activities and provide supporting narrative for the score.

Output Indicator 4.1:

Under this indicator, TMA successfully delivered core analytical inputs to support border modernisation. Institutional and coordination assessments were completed for the Noe-Elubo and Seme-Krake borders, with priority interventions clearly identified. This provided strong evidence for subsequent investments and decision‑making and met expectations in terms of analytical quality and usefulness. There were no major shortfalls reported under this indicator. However, the work was focused on assessment and prioritisation rather than progressing into implementation‑ready designs in all cases.

Output Indicator 4.2:

Significant progress was made under this indicator, particularly in establishing institutional frameworks and operational mechanisms. TMA supported the development of draft ECOWAS Institutional Border Frameworks, Joint Border Post (JBP) procedures and operational manuals, and bilateral cooperation mechanisms. The establishment and operationalisation of Joint Border Management Committees for Noe-Elubo and Seme-Krake borders represented an important achievement in strengthening cross‑border governance.

On the infrastructure and services side, tangible outputs were delivered including renewable energy supply to Akanu-Noepe JBP, water provision and sanitary facilities, refurbishment of JBP facilities, and pedestrian canopies. In addition, national and regional trade facilitation strategies and roadmaps were developed and implemented across Côte d’Ivoire, Ghana, Togo and Benin. However, not all outputs reached full adoption or sustainability. The ECOWAS Institutional Border Frameworks and some JBP manuals were drafted and piloted but not formally adopted by all Member States, falling short of expectations. Sustainability risks were also noted for the renewable energy intervention at Akanu-Noepe, indicating gaps in long‑term operation and maintenance planning.

Output Indicator 4.3:

TMA made strong contributions to digital and operational interoperability at border posts. Internet connectivity on SIGMAT was enhanced across multiple countries, improving data exchange and customs cooperation. The development of bilingual training materials supported usability across linguistic contexts, and border officials’ connectivity at Noe-Elubo was improved. Additionally, the provision of IT equipment and infrastructure at the Elubo border strengthened day‑to‑day operational capacity. Despite these achievements, progress was uneven, with SIGMAT connectivity improvements largely delivered at a “mostly met” level. This reflects challenges related to differing national systems, infrastructure readiness, and institutional capacity across participating countries.

Output Indicator 4.4:

Under this indicator, TMA successfully strengthened institutional capacity through trade facilitation structures. ECOWAS’ Regional Trade Facilitation Committee (RTFC) had its institutional capacity assessed and reinforced, supporting a more coordinated regional approach to trade facilitation governance. While capacity was identified and strengthened, the evidence points more strongly to institutional reinforcement than to large‑scale individual capacity‑building activities.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following the decision at the previous Annual Review to remove Output 5, the weightings of the remaining outputs have been adjusted to align with revised delivery requirements. Output 4’s weighting has increased from 20% to 30% to reflect the scale and complexity of the activities involved, notably its emphasis on systems‑related delivery.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
Progress, lessons and recommendations

Under indicator 4.1, early technical assessments are highly effective in aligning stakeholders around priorities, but future programmes could benefit from clearer pathways linking assessments to funded implementation. Where feasible, pairing diagnostics with early‑stage design or costing exercises would help maintain momentum and reduce delays between analysis and delivery.

For indicator 4.2 the experience highlights the importance of early and sustained political buy‑in for formal adoption of regional frameworks. Future programmes should invest more heavily in Member State consensus‑building and adoption processes, alongside technical drafting. For infrastructure and service delivery, sustainability planning, including ownership, maintenance financing, and institutional responsibility, needs to be embedded earlier to ensure long‑term impact beyond programme closure.

Covered in indicator 4.3 digital harmonisation requires not only technical upgrades but also sustained coordination across customs administrations. Future interventions would benefit from phased roll‑outs, stronger national IT focal points, and clearer contingency planning for infrastructure and connectivity constraints. Investment in change management and user support is as important as the technology itself.

For indicator 4.4 strengthening regional institutions is a necessary foundation, but future programmes could complement this with more systematic tracking of individual‑level training outcomes and behavioural change. Embedding monitoring of capacity utilisation, not just capacity delivery, would improve understanding of longer‑term impacts.

D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition and previous Annual Review
Under ODI delivery, operating costs (staff, research and implementation, M&E and non-project costs) accounted for 47.1% of total programme spend, consistent with the programme’s technical assistance model and emphasis on high-quality analytical and policy engagement. Consultant costs remained within benchmarks (£660 senior / £473 mid / £225 junior average daily rates), demonstrating sustained cost discipline. Travel costs increased to 5.25% of spend, reflecting a shift from design to implementation, with increased in-person convening, capacity-building and stakeholder engagement; this remains proportionate and aligned with the AfCFTA Secretariat-centred delivery model. Communications and policy engagement costs (including translation and interpretation) represented 7.48% of spend, consistent with the programme’s continental and national influencing objectives.

Under TMA delivery, operating costs (staff, research and implementation, M&E and non-project costs) accounted for 36% of total programme spend, with core cost drivers continuing to be national and continental level activities, including significant investment in trade facilitation infrastructure and systems (customs interconnectivity and border post infrastructure). TMA benchmarked daily technical assistance rates against its internal consultancy fee rate guide (£870 senior principal / £609 senior / £391 associate), evidencing cost control.

Economy: Compared to FY23/24, the programme continues to demonstrate good economy. ODI maintained stable fee rates and proportionate travel costs while scaling delivery, and management costs have remained lower as a share of total spend due to improved planning and clearer activity costing. TMA continues to apply competitive procurement and regional benchmarking, with restricted tendering used only where market constraints apply. While these processes ensure fair pricing and good economy, they can be time intensive and contribute to delivery delays, with potential efficiency implications.

Efficiency: Efficiency has improved relative to issues identified in the previous Annual Review. The introduction of a RAG rating system by both ODI and TMA has strengthened delivery oversight, timeliness and reporting. ODI reports 88.6% of activities delivered on time, with only 8.6% delayed by more than three months, indicating improved planning and delivery discipline. TMA reports 70% of activities delivered by end‑June 2025. While procurement timelines and political processes continue to affect delivery schedules, closer monitoring and risk escalation have mitigated impacts on VfM.

Effectiveness: Effectiveness continues to reflect the complex and long-term nature of AfCFTA outcomes. ODI’s focus on fewer, more targeted interventions has improved alignment with policy priorities, and the introduction of outcome mapping and “stories of change” should strengthen evidence of contribution over time. For TMA, while several intermediate outcomes remain partially on track, continued investment in capacity building, border operations and stakeholder cocreation supports credible longer‑term delivery pathways, with some residual risks around infrastructure utilisation. Overall, outcome delivery is more constrained by contextual and institutional factors than by programme design or cost‑effectiveness. Continued focus on timely delivery and outcome evidence will be critical in the next programme year.

Equity: Equity is more systematically embedded than in FY23/24. ODI reports 44.5% of papers authored or co‑authored by women and continued action to improve gender representation across events and outputs. TMA continues to integrate inclusive trade and environmental considerations across its portfolio.

Assessment of whether the programme continues to represent value for money

FY24/25 is the first full year of applying the revised VfM framework. ODI reported directly against the framework, while TMA reported through its independent assessor, Co‑Water, as part of its third‑party monitoring arrangements. TMA should extract VfM‑relevant data from this process into quarterly financial and narrative reporting to strengthen ongoing VfM monitoring.

ODI’s Non‑Project Attributable Costs rate remains high relative to other ODA partners; FCDO continues engagement with ODI to address this. Overall, compared to FY23/24, VfM has improved, with clearer cost drivers, stronger delivery discipline and more robust evidence across economy and efficiency. While effectiveness remains dependent on longer‑term outcomes in a challenging context, partner performance in planning, oversight and VfM monitoring has strengthened. The programme therefore continues to represent acceptable value for money, with sustained focus required on early planning, investment utilisation and outcome evidence.

E: RISK

Overview of risk management
The overall risk rating for the programme is ‘Major’ which is within FCDO’s Africa Programmes and Expertise Department’s risk appetite. Risks are formally reviewed by the FCDO programme management team at least quarterly, any risks exceeding appetite are escalated and mitigated. Implementing partners manage project level risks through established processes, reporting updates quarterly and flagging changes. Monthly meetings between FCDO and partners support ongoing monitoring of emerging risks and agreed actions. Clear escalation and incident-reporting procedures help ensure compliance and effective delivery.

Strategy and Context Risks
The programme operates across diverse institutions and politically complex environments, resulting in a risk of delays due to actions outside the programme’s direct control. These delays may impede activity sequencing and slow progress toward outcomes. Mitigation focuses on maintaining flexibility, an adaptive management approach and working with a broad coalition of reform minded partners.

Financial and Fiduciary Risks
Budgetary fluctuations and delayed confirmation of annual allocations presented a risk of rushed work planning and difficulties maintaining a clear set of programme activities across the portfolio. Mitigation actions included biannual strategic reviews to refine priorities and protect essential delivery. Fiduciary safeguards which ensure robust financial governance include a strict zero tolerance approach to fraud, whistleblower mechanisms and internal audit arrangements.

Policy and Programme Delivery Risks
Differences in priorities and the speed of decision-making among implementing partners, governments, and stakeholders introduce risks to activity selection and programme coherence. Mitigations include strengthened governance structures, detailed joint work planning and quarterly performance reporting reinforce monitoring and help maintain value for money.

People and Capacity Risks
Delivery risks arise from limited staffing capacity within programme teams and implementing partners, potentially affecting oversight, pace, and quality. The programme mitigates these risks through ongoing monitoring of recruitment and retention, establishing well-understood reporting expectations, and embedding clear and consistent programme management processes with delivery partners.

Safeguarding and Environmental Risks
The programme recognises that safeguarding risks related to unintended harm to vulnerable groups or the environment may materialise if gender, climate, and inclusion considerations are not sufficiently embedded. Mitigating actions include mandatory “do no harm” assessments, mainstreaming safeguarding and environmental processes across all activities. Implementing partners maintain robust safeguarding and inclusion policies.

Reputational Risks
Reputational risks may arise if implementing partners fail to communicate effectively with stakeholders or if negative reporting affects their institutional standing. Mitigation measures include governance arrangements with feedback loops, regular partner engagement, and ongoing monitoring to ensure the benefits of FCDO supported activities are presented positively and aligned with FCDO standards to safeguard the programme’s credibility.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

FCDO’s original budget for the AfCFTA programme in FY24/25 was set at £4.8m. Expenditure for this period was £3.54m, split between ODI (£1.49m), TMA (£1.99m) and the cost of the programme funded finance specialist seconded to TMA (see below).
Overall, the AfCFTA programme management and financial controls supported delivery during the review period. Financial performance of implementing partners was characterised by slower spending in the first half of the year, with improved expenditure in the second half as delivery accelerated. Variances were primarily driven by delays rather than weak financial controls. Some planned activities could not be completed in this period, resulting in a lower spend figure, these activities were carried forward and completed in the following year.
Despite constraints, both ODI and TMA demonstrated effective adaptive management, prioritising high impact and higher value activities. Financial reporting from both partners was comprehensive and transparent, with clear explanations provided for variances, including those linked to re‑profiling, reduced event costs or changes in delivery sequencing. FCDO received unqualified audited financial statements for both ODI and TMA in this reporting year.
The FCDO team updated the Due Diligence Assessments (DDAs) of ODI (Aug 25) and TMA (Jan 2026). These DDAs took a risk-based approach and identified a few areas of risk, where improvements in policies or process could be made. An action plan was agreed with each partner, making recommendations and suggesting corrective action that should be taken.
From a commercial perspective, delivery arrangements remain appropriate and complementary. ODI’s flexible, expert-led delivery model and TMA’s systems-focused approach together provide coverage across policy, institutional and operational dimensions of AfCFTA implementation. Both partners demonstrated prudent commercial management, including proportionate use of consultants and adjustments to deliver value for money. Procurement was specifically assessed within the DDAs for both partners. While TMA’s thorough processes can add to procurement timelines, no material commercial risks were identified.
FCDO recruited a programme funded financial business partner implanted into TMA to provide strategic finance leadership. The role is funded from this programme, but improvements generated by this post support all the FCDO-funded programmes across the TMA portfolio.
During the year, the secondee significantly strengthened TMA’s programme and corporate financial management by identifying weaknesses in forecasting and budget management - then designing and implementing an improvement process which focused on clearer ownership of financial information and more disciplined financial management practices. The secondee updated key financial policies and worked with the Programme Board to establish finance dashboards, strengthening senior oversight and decision‑making. In recognition of the scale and importance of these reforms, the secondment has been extended for a further year to ensure that improvements are fully embedded and sustainable.
Implementing partners largely complied with visibility and attribution requirements, ensuring that outputs and communications appropriately recognise UK Aid funding in line with agreed standards. Checks are undertaken, and on a few occasions the FCDO team has had to remind partners to include references to UK support. FCDO will continue to reinforce expectations under the UK Aid visibility guidance.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation: The AfCFTA Support Programme has employed a mix of monitoring approaches to track progress across workstreams and ensure alignment with expected outcomes. Monitoring by the programme team has centred on ongoing engagement with programme partners, including interviews, field visits to border posts, and reviews of quarterly and annual reporting. These interactions have enabled the programme team to identify delivery challenges early, adapt to political‑economy constraints, and refine workplans, particularly in relation to trade facilitation on the Lagos-Abidjan Corridor. The introduction of outcome mapping and “Stories of Change” has strengthened the programme’s ability to evidence behavioural and institutional change, helping teams trace contributions to developments such as the Digital Trade and Investment Protocols, adoption of SIGMAT at Lagos-Abidjan borders, and country‑level progress through NICs. This approach is helping generate clearer evidence of outcomes in response to earlier recommendations.

Communications: Previous recommendations highlighted the need for a more structured communications approach. While outreach and lesson sharing improved, it remains sporadic. To the extent that capacity and funding are available for this, a coordinated plan covering ODI Global, TMA and FCDO would help disseminate research, demonstrate implementation results, and amplify lessons across continental, regional and national partners. Opportunities to share outputs - including those related to NICs, trade protocols and border post improvements - should be prioritised in the next financial year to inform key influencers and decision makers.

Annual Review process: This Annual Review, completed by the FCDO programme team, drew on interviews across the Secretariat, RECs, governments and border agencies, in addition to site visits which offered insights into operational practices and highlighted remaining infrastructure and capacity gaps. Independent assessments, including TMA’s internal monitoring reviews, informed the analysis of milestone delivery and implementation challenges. These inputs provided a clearer picture of programme strengths, such as strong partner relationships and effective capacity building, and areas requiring further attention, including sustainability of border investments and institutional coherence. It was not possible to draw on FCDO’s wider third‑party monitoring framework during this period due to retendering, limiting opportunities for additional independent verification.

Evidence: No major changes in evidence quality were identified, though research uptake remains an important focus as the programme seeks to strengthen the link between analytical outputs and policy or implementation decisions. Evidence from Stories of Change is helping clarify how programme interventions contribute to measurable outcomes, including increases in customs revenues and accelerated progress on key protocols.

Learning: Continued investment in strengthening monitoring and evaluation - particularly drawing on existing monitoring, evaluating and learning (MEL) processes and wider use of outcome mapping - would enhance programme learning. As mentioned above, additional MEL capacity within TMA and ODI would help embed this approach, ensure consistent data collection, and deepen understanding of the long‑term effects and sustainability of programme interventions.

Date of last narrative financial report	ODI - February 2026 / TMA - February 2026	Date of last audited annual statement	ODI - 31 March 2025 / TMA - 30 June 2025