## Annual Review Template

Title: Building Peace and Stability in Iraq (BPSI)
Programme Value £ (full life): £25m		Review date: 22 Aug 2025
Programme Code: 301223	AMP start date: 22/07/2022	AMP end date: 31/03/2027

Summary of Programme Performance
Year	July 2022 – March 2023	June 2023 – March 2024	April 2024 – March 2025
Overall Output Score	A	A	A+
Risk Rating	Major	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0001021.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0005143.xlsx

A. SUMMARY AND OVERVIEW

Programme summary:
The original business case summarises the programme as follows:

Protracted displacement of Iraqis affected by the Daesh conflict is rendering the population vulnerable to extremist narratives. This is compounded by the slow (stalled) return and reintegration process, weak security and justice system, and discrimination against those accused of Da’esh affiliation. The programme will:
1. Address barriers to return, reintegration and reconciliation of Iraqis still displaced including perceived Da’esh-affiliated families.
2. Support access to justice for local communities and reintegration of juveniles in disenfranchised areas.
3. Maximise donor influence and Government commitment to reconstruction and reconciliation.
4. Evaluate impact and generate evidence to inform engagement, targeted advocacy and enhance institutional memory.

Since business case sign off the programme has continued to evolve based on the needs and context within Iraq. In its current form, BPSI seeks to support those who remain internally displaced within Iraq and those returning from Northeast Syria by tackling barriers to return through interventions on peacebuilding and social cohesion, livelihoods, legal support and small-scale infrastructure rehabilitation, coupled with policy, advocacy and capacity building at local and national levels.

The programme is funded via the International Organization for Migration and International Rescue Committee, who manage a consortium of five local NGOs. The programme also funds the Durable Solutions Advisor to the UN Resident Coordinator in Iraq, who influences and convenes on the UN’s approach to Durable Solutions in Iraq, as well as inputting into the UN’s global Durable Solutions initiative. In FY 24-25, given the fall of the Assad regime and the Government of Iraq’s subsequent expedited repatriations of Iraqis from Northeast Syria, the programme has expanded its focus on these returnees – a UK national security priority. The programme provided support via cash grants to those leaving Al Amal Rehabilitation Centre in Iraq and also providing direct support to Al Amal following the US review of federal foreign assistance (the latter funded exclusively via ISF funding).
[note] Upon return from Al Hol or Al Roj camps in Northeast Syria, Iraqis are initially repatriated to Al Amal rehabilitation centre in Nineweh where they receive rehabilitation support and services, before departing to areas of return.

During the reporting period, the programme received a significant uplift in funding from the Integrated Security Fund budget (£3.3m). This contribution allowed BPSI to expand its work into a third community in Anbar, deliver additional infrastructure projects in Diyala, provide cash assistance to those leaving Al Amal, and increase programme targets for livelihoods, policy and community dialogues, as well as supporting critical camp management, legal, protection and mental health activities in Al Amal.

BPSI collaborated with the Iraq Integrated Security Fund team to deliver £3.3m of ISF spend via IOM during the reporting period. This allowed IOM to significantly increase their targets and add additional outputs to the results framework. These results will be reported on separately through the ISF annual review, but it is important to acknowledge the impact this funding had on the programme’s overall success:
- £1.5m to deliver activities, including expansion into an additional community in Anbar, an additional four Quick Impact Infrastructure projects and adding an additional 110 participants to the livelihoods activities, as well as increased targets for cash assistance to those leaving Al Amal, and policy and community dialogues focusing challenges to reintegration.
- £1.8m to respond to needs in Al Amal Rehabilitation Centre. ISF funding enabled IOM to deliver critical camp management, legal, protection and mental health activities in Al Amal, including delivery of Mental Health and Psychosocial Support (MHPSS) to 232 individuals, procurement and distribution of critical equipment such as hygiene items to 681 new arrivals, and a disability inclusion and protection assessment.
Broadening the scope of IOM’s work has embedded the UK’s programming footprint in conflict-affected areas of high return, aligning strongly with UK security and development objectives. The Ministry of Migration and Displacement thanked the Ambassador for the funding to Al Amal in a meeting in June 2025, and the UK has maintained a leadership position on this file in part due to the increased funding we provided. This demonstrates the collaboration, flexibility and agility of BPSI, the British Embassy, and its partners, to deliver in a rapidly changing context.

Context:
Over the period summarised in this annual review, Iraq has continued to experience relative stability, although challenges raised in the last annual review continue - protracted humanitarian and development needs, a complex political environment, and a volatile security situation, including regionally. As of December 2024, data from the International Organization for Migration’s (IOM) Displacement Tracking Matrix (DTM) indicates that approximately 1.03 million individuals remain internally displaced across Iraq, this includes 104,617 people living in 20 internally displaced persons (IDP) camps.
[note] UNHCR and IOM Update on Internal Displacement in Iraq – 30 June 2025

Rates of return from IDP camps have remained slow since mid-2024. IDPs and those reintegrating into areas of return still face multiple barriers to return, including community acceptance and stigmatisation, access to services, housing and civil documentation, livelihoods, access to basic infrastructure and security concerns.

The programme has operated against the following key contextual developments during the reporting period:

- Government approach to IDPs: In January 2024, the Council of Ministers announced that it would close all remaining IDP camps by 30 July 2024. Following advocacy against this, the remaining IDP camps were not closed in July 2024 and camps remain open in Erbil, Dahouk and East Mosul at the time of writing. Since August 2024, the Government has focussed on convening various committees to look at recommendations to support camp closures and an end to displacement.
- Expedited returns from Syria: Following the fall of the Assad regime in December 2024, the GoI has expedited returns of Iraqis from Al Hol and Al Roj camps in Northeast Syria (NES) to Al Amal Rehabilitation Centre in Nineweh, Iraq. Expedited returns, whilst welcomed by the international community, have put pressure on infrastructure and services in Al Amal rehabilitation centre and those leaving Al Amal will face similar challenges to IDPs in areas of return, albeit with some added complexities and challenges.
- US funding: In January 2025, the US government announced it would conduct a review of Federal Foreign Assistance. Following this, several US-funded projects in Iraq were terminated or paused.

Over the course of the reporting period, BPSI has pivoted activities to provide greater support to Al Amal and those returning from NES, as well as directly supporting activities affected by the US Federal Foreign Assistance review. We will continue to focus partially on areas of high return from NES in FY25/26.

Key achievements:
Over the reporting period the following key results were achieved:
- 19,532 individuals targeted by ‎awareness raising campaigns ‎on peacebuilding and conflict ‎management
- 68 households returning from Al Amal received cash support to reintegrate into areas of return
- BPSI supported the rehabilitation of a water treatment plant and the expansion of electricity infrastructure in Salah-Al-Din, benefitting at least 2,000 people
- 2,445 people attended legal awareness raising sessions
- 7,469 people received legal counselling and 2,143 people were supported to receive civil documentation
- 367 people completed job skills employability training
- 65 people received business development training and a cash grant to establish a business or expand an existing business

Summary supporting narrative for the overall score in this review
The programme has scored an A+. This reflects consistently strong performance across the programme – with all outputs scoring an A or A+, whilst partners effectively adapted to changes in the context. Activities continue to be aligned with data and evidence on the key barriers to return and reintegration, and efforts to embed community ownership, local government engagement and capacity building, policy work and advocacy at the national level demonstrate BPSI’s ambitions to both deliver tangible change for beneficiaries individually and drive systemic, sustained, nationally-owned change. Any under-achievements against outputs were minor and mostly caused by prioritising more complex interventions for the most vulnerable, in line with BPSI’s objectives to reach the most marginalised.

Major lessons and recommendations for the year ahead

Whilst the main lessons are captured throughout the annual review, some overarching or key lessons and recommendations are captured here:

The programme has adapted well to the changing context and should continue to retain flexibility to adapt to the latest developments in the context and needs of those displaced Iraqis. FCDO should also work with partners to consider how best to design BPSI for 26/27 to achieve maximum impact in light of the transition to 0.3% ODA and to align with FCDO Iraq network priorities. The programme should consider longer-term planning horizons.
- The presence of the SRO and PRO in Baghdad should be maintained because it has allowed for: greater synergies in programming across the British Embassy, notably with Integrated Security Fund (ISF) and Counter Terrorism (CT) teams; better monitoring of BPSI partners and activities, and more frequent engagement with BPSI partners; better engagement with the full range of stakeholders relevant to displacement-related issues in Iraq, including government, UN, NGOs, and donors; better UK understanding of and ability to influence on displacement and durable solutions agendas in Iraq. This should be built upon, including through regular field visits and engagement with programme partners based in Erbil. BPSI staff should also consider how the programme creates greater synergies with the UK’s economic programming, and whether these interventions can help support greater budget availability for interventions that would remove barriers to return.
- The theory of change contained in the original business case has not been fully adopted in the realities of implementation. The theory of change should undergo a full refresh to remove activities not progressed and to reflect the importance of national level engagement and advocacy, as well as the change in context.
- Delivery locations were disparate across IOM and IRC projects during the reporting period. To ensure greater efficiencies, BPSI partners should consolidate, and where possible align, delivery locations and increase individual targets in those locations. IOM and IRC should also continue the strong collaboration and livelihoods referrals implemented during the reporting period.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

This Theory of Change as originally set out in the Business Case is summarised in the programme logic and the diagram below:

Programme logic
à
Grassroots work in communities enables FCDO to 1) address the barriers to return and reintegration of people returning from Daesh-induced displacement, 2) Capacity change leads to a reduction in the potential for local conflict, 3) Behaviour change results in improved motivation and capacity to support the return and reintegration of the displaced, 4) Security threats and lack of political will are no longer barriers to return, 4) The displaced are rehabilitated and returned to their areas of origin.
à
Grassroots action gives FCDO credibility when working with Government and international agencies: FCDO is acting as well as talking.
à
Grassroots action gives a valuable evidence base for influencing. The perspective of the most-affected people is brought into the national debate.
à
Combining the knowledge acquired through grass-roots action with information from other programmes and research, the FCDO is in a strong position to influence the policies of the Government and international organisations.

Fig. 1: Original Theory of Change for the Building Peace and Stability in Iraq Programme.

The Theory of Change (ToC) and programme logic focus on delivering at the local level, however, BPSI is now increasingly coupling direct interventions, capacity building and advocacy at the local level with engagement with national actors. Actions and delivery at the local level continue to give FCDO credibility with the Government of Iraq and donors, as well as providing an evidence base and knowledge on what works in reintegration, but must be coupled with national level engagement.

As noted in the previous annual review, the original programme assumptions remain mostly relevant, however, two assumptions underpinning the ToC have changed or are less certain. The assumption around the effectiveness of political advocacy is partially borne out in practice. The FCDO maintains a good relationship with key government counterparts on a range of displacement issues in Iraq. Our voice is heard and well respected among Government and UN counterparts. However, it is increasingly important to coordinate advocacy with the international community to maximise the impact of or combined influence.

The original assumption over the level of funding available to the programme (£25m) has not been realised and this has necessitated a reduction in programme ambition, for example justice sector reform activities have not been implemented, and partial co-funding of the programme from Integrated Security Fund (ISF) budgets. Given the transition to 0.3 announced in February 2025 and the general landscape of reduced donor funding in Iraq, it will be important for FCDO to work with partners to ensure the programme can remain as impactful as possible for FY 25/26 onwards – leveraging programme evidence, networks, advocacy and policy work will be critical to ensure this.

Further risks flagged in the business case cover lack of government will to reconstruct and deliver services in war-affected areas and FCDO funding being too small and thinly spread to make a difference. On the former, whilst there are government funds set up to tackle this, challenges remain and reconstruction efforts continue to be needed. FCDO advocacy, diplomacy and economic support could be further leveraged on these areas. On the latter point, FCDO remains alive to this risk and continues to mitigate this through national engagement and advocacy to build on our localised interventions, whilst also seeking to consolidate support in priority geographic areas in FY 25/26.

Whilst there were no formal changes to BPSI’s theory of change over the reporting period, a rapid internal review of the TOC was conducted in December 2024, in preparation for FY 25/26 delivery. This review resulted in a discussion with partners to agree which parts of the TOC should receive emphasis in upcoming proposals. It was agreed that:
- IRC and the consortium would focus further on justice system reform and legal support given the link to civil documentation
- That both IOM and IRC would continue to focus on livelihoods
- That activities relating to access to services would be strengthened (particularly infrastructure and social services)
- That all partners would assess and implement the best way to build political will and technical capacity at local and central government lesson to increase the programme’s sustainability, and linked to this, advocacy will be strengthened in FY25/26
- That environmental sustainability relating to infrastructure rehabilitation is emphasised, and that climate-sensitive interventions can be mainstreamed into the project
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Over the reporting period, the IRC consortium significantly exceeded all three outcome indicators, demonstrating that the programme continues to translate activities to outputs and outcomes in terms of reducing community conflict, empowering individuals to exercise their rights and improving government capability for systems strengthening and service delivery. This flows from strong performance against the vast majority of outputs across the IRC-led consortium.

Similarly, IOM exceeded all outcome and impact indicators, most of them significantly, demonstrating success in the programme interventions’ ability to support living conditions and safety in targeted communities, engagement in community planning, access to services, improved income, awareness of durable solutions approaches and policy/capacity building efforts to support social cohesion. As with IRC, this flows from strong performance at the output level. Interestingly, rates of satisfaction with community-based planning processes varied across gender and age, with men and those aged over 41 less satisfied than women and younger people. This may reflect IOM’s targeted approach to encourage female and youth participation, which could be perceived as deviating from social and cultural norms in some communities.

Delivery against outcome indicators is summarised in the table below:

Outcome number	Outcome description	Target	Achieved
International Rescue Committee
Outcome indicator 1	% of individuals reporting that the number of conflicts in their community has reduced	55%	87%
Outcome indicator 2	‎% of individuals who report experiencing an improvement ‎in their ability to exercise their rights as a result of the ‎assistance	75%	85%
Outcome indicator 3	% of Government Officials and Duty Bearers Reporting Improved Capability in Strengthening System and Procedures for Service Delivery.	75%	95%
International Organization for Migration
Overall objective	Percentage of stakeholders (direct beneficiaries, community representatives, and local authorities) reporting that the project's outcomes have contributed to improving living conditions / Percentage of surveyed project beneficiaries reporting a sense of safety and absence of fear of violence within their communities	60% / 60%	93% / 76%
Outcome indicator 1	Percentage of stakeholders (community representatives, local authorities, and others) satisfied with level of engagement, contributions in the development of community-based plans (disaggregated by sex, and age) / # of displaced people who are supported to access safe, voluntary, and dignified solutions	70% / 725	80% (74% M, 100% F, (18-30) 100%, (31-40) 100%, (41-50) 64%, (51 and above) 71%) / 979
Outcome indicator 2	Percentage of the supported community members reporting increased access to basic services (disaggregated by sex, age, demographic status, and presence of disabilities) / Percentage of beneficiaries who received individual livelihood assistance reported having maintained the increased income 3 months after the service delivery (disaggregated by sex, age, status displacement status and type of training) / (SRF Indicator) % of migrants, displaced persons and other community members who access quality essential services	60% / 60% / 60%	97% / (97% M, 97% F, (18-30) 95%, (31-40) 97%, (41-50) 97%, (51 and above) 100%), (95% Anbar, 100% Diyala, 95% Salah al-Din) / 65% / (69% M, 63% F, (18-25) 83%, (26-30) 71%, (31-35) 53%, (36- 40) 75%, (41-45) 54%, (46 and above) 66%), (62% Returnees, 50% IDPs, 92% host community) / 92%
Outcome indicator 3	Percentage of stakeholders who participated in capacity building activities reporting improved awareness of durable solutions / # of policy or capacity building processes for transition, recovery or development promoting social cohesion and prosperity that included participation of migrants, displaced persons and their communities in line with a whole of society approach to policy development.	70% / 4	100% / 6 processes

Although the Durable Solutions Advisor (DSA) role does not deliver against specific outputs or outcomes, this role has been pivotal to the Durable Solutions and displacement mechanisms in Iraq – playing a critical role in government discussions on ending internal displacement, convening the UN response to Northeast Syria returns and driving UN/government engagement on displacement at the highest levels. This role has also provided invaluable influence for the British Embassy in this space and access to information required to effectively conduct development diplomacy with key interlocuters.

The programme also largely delivered effectively against budget in FY24/25, with both IOM and IRC reporting full spend, and underspend only reported against the DSA role budget.

The last annual review noted engagement between partners and with FCDO and partners could be improved. This has occurred over the course of the reporting period, with both the SRO and PRO roles in FCDO moving to Baghdad, enabling greater engagement and coordination with both BPSI partners and wider stakeholders on the displacement file, including government, donor and UN counterparts, as well as the wider NGO system. Engagement between IOM and IRC, and with the DSA, has also improved this year, with livelihoods referrals instituted between IOM and IRC, regular meetings between the partners, and both parties working together on both lessons learned following the reporting period and forward planning for activities in FY25/26. IRC’s wrap up workshop for BPSI in March 2024 also engaged IOM and the DSA, with both parties and the FCDO speaking at this event.

As noted in the last annual review, there are high levels of ambition within the ToC model which may not be possible to measure or achieve, specifically around reducing or removing Daesh affiliation perceptions, but the intended impact of the displaced being rehabilitated and returning to Daesh affected areas is demonstrably happening, both through the work of the BPSI programme and domestic and international actors more widely. The overachievement of IRC’s outcome on reduced community conflict also demonstrates that peacebuilding and conflict resolution interventions are having the desired effect.

There continues to be inadequate budget for TPM under the programme, however, this has been mitigated by FCDO staff being in country and able to visit BPSI partners, as well as increased in person engagement with BPSI partners. Further, IOM conducted an evaluation of activities delivered during the reporting period, and FCDO approved a reallocation of underspend in IRC’s budget to procure a mid-term evaluation which covered this reporting period. Results of both evaluations have been embedded throughout this review, as appropriate.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

BPSI has consistently performed effectively against budget both this year and last, with partners performing effectively and collaborating well both between themselves and with FCDO, whilst retaining flexibility to adapt to changing priorities and the changing context.

Given the ongoing context of remaining post-conflict displacement in Iraq, and the Government of Iraq’s recent prioritisation of NES returns, this programme remains highly relevant to the Iraqi context and critical to UK development, security, CT and human rights priorities. FCDO’s funding of BPSI, and particularly the DSA role and our increased focus on the high-profile issue of returns from Northeast Syria, alongside our diplomatic diplomacy efforts in country, places us in a leading role amongst donors on displacement issues in Iraq. The programme is reflected in FCDO country business plans as a continuing priority for British Embassy Baghdad and should continue, whilst continuously taking into account learning and recommendations, and adapting to the context as required alongside other relevant programming (such as CT and ISF).

## C. DETAILED OUTPUT SCORING

NB: Outputs achieved under previous phases of BPSI, for which no targets were set in this review period, have been excluded from this annual review and the weighting (10%) evenly redistributed across other outputs. The outputs previously achieved under the IRC component include:
- 1.1.1: # of individuals consulted to identify common local priorities and needs
- 1.1.2: # of community members trained on organising community data collection exercises
- 1.2.1 # of individuals who participate in community dialogues
- 1.2.2: % of individuals who report being satisfied with the community dialogues
Output Title	IOM: Displaced communities and key stakeholders have increased engagement in the reassessment of priority areas of intervention to enable sustainable, inclusive, and peaceful returns and progress towards durable solutions.
Output number:		1.1	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes – IOM not reviewed in the last AR

Indicator(s)	Milestone(s) for this review	Progress
1.1.1: # of communities re-assessed based on established criteria and selected for intervention	Phase II planned: 2	Phase II achieved: 2
1.1.2: # of inclusive and conflict-sensitive community consultations conducted	Phase II planned: 2	Phase II achieved: 4
1.1.3: # of community-based plans re-drafted	Phase II planned: 2	Phase II achieved: 2
1.1.4: # of consultation meetings conducted with authorities	Phase II planned: 2	Phase II achieved: 2
1.1.5: # of community feedback sessions conducted	Phase II planned: 2	Phase II achieved: 3

Briefly describe the output’s activities and provide supporting narrative for the score.
Building on Phase I of BPSI, members (including returnees and existing residents) of two identified communities (Al Askara in Diyala and Yankaja in Salah-Al-Din) were engaged to validate community needs and prioritise interventions. Community meetings in all locations led to updated community action plans and prioritised interventions (infrastructure rehabilitation delivered under output 2.1). Community engagement was followed by local government consultations and site visits to assess the feasibility of infrastructure projects identified by the community. Final infrastructure project selection was validated with local community representatives. This community-based planning approach allowed IOM to effectively engage with local communities and ensure the selected interventions were both deliverable and needs-based.

Activities under this output, such as the community feedback sessions, also give an opportunity for communities to voice their opinions in a safe and facilitated space. Although representation in these sessions was broadly even across men and women in Diyala and Salah-Al-Din, IOM record low female participation in Anbar. Although this location is not covered under this annual review, this highlights the importance of continued and contextually-specific efforts to ensure women’s inclusion in community planning processes.

This output achieved all its indicator targets, and indicator 1.1.2 overachieved, by conducting separate male and female consultations, allowing space for community members to provide feedback comfortably. Output 1.1.5 also overachieved as two feedback sessions were conducted in Al Askara, and there were split-gender sessions.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output during the reporting period and no changes will be made as a result of this review. However, we will continue to discuss with IOM the importance of a representative sample of community members being involved in both planning and feedback discussions.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from the last AR.

For the next reporting period, it is recommended that IOM and IRC collaborate to ensure greater synergies in their work and better value for money (IOM output 1.2, IRC output 1.1 and IRC output 1.2). This recommendation applies to activities including community dialogue, community action plans, and community-based data collection. This will ensure there is no duplication of activities across the IOM/IRC portfolios and should drive complementarity, as well as reducing the risk of “consultation fatigue” amongst communities. This collaboration will be supported by the FCDO’s instruction to IRC and IOM to further align the locations in which they both work.

IOM and IRC should also continue efforts to ensure any community consultations, dialogues or feedback sessions remain representative of the community as far as possible, ensuring effective inclusion of women, youth, marginalised groups, returnees and IDPs as appropriate to the local context – this should also help ensure that interventions remain inclusive and conflict sensitive.

Output Title	IRC: People have innovative reconciliation activities and adequate opportunities to implement small-scale community-based initiatives for living in a peaceful and just society: (Reconciliation and Social Cohesion)
Output number:		1.3	Output Score:	A++
Impact weighting (%):		21%	Weighting revised since last AR?	Yes – up from 20%

Indicator(s)	Milestone(s) for this review	Progress
1.3.1 # of individuals who receive training on peacebuilding and conflict management skills	Phase II planned: 75	Phase II achieved: 30 (activity was started in Q4 of Phase I, with 45 individuals trained, making net achievement 75)
1.3.2: # of community-driven initiatives implemented for social cohesion with focus on women and youth	Phase II planned: 15	Phase II achieved: 27
1.3.3: # of government officials engaged in the implementation of small-scale social cohesion projects	Phase II planned: 15	Phase II achieved: 94
1.3.4: # of positive narratives collected and prepared for sharing	Phase II planned: 15	Phase II achieved: 35
1.3.5: # of individuals targeted by ‎awareness raising campaigns ‎on peacebuilding and conflict ‎management	Phase II planned: 12,000	Phase II achieved: 19,532
1.3.6: % of individuals who are satisfied with the social cohesion activities	Phase II planned: 75%	Phase II achieved: 87%
1.3.7: % of individuals believe that relationships between and among different groups have improved	Phase II planned: 55%	Phase II achieved: 84%
1.3.8: % of individuals including vulnerable and youth at risk who state that their capacity to ‎identify hate speech and violent extremism has increased	No targets set for Phase II: target achieved in Phase I

Briefly describe the output’s activities and provide supporting narrative for the score.

Progress under this outcome was delivered by Al Tahreer Association for Development (TAD) and Peace and Freedom Organisation (PFO), who implemented reconciliation and community cohesion activities across five governorates. Activities focused on building peaceful communities through:
- Dialogue sessions in areas of high return, to address intra-community tensions.
- Investing in youth leadership on peacebuilding and conflict resolution.
- Incorporating climate into community discussions, given the increasing role environmental degradation and resource scarcity will play in community tensions.
All indicators except one overachieved this year. Indicator 1.3.1 target was 75 individuals, with 30 individuals being trained this year. However, 45 individuals were trained in the last quarter of year 1 of the programme, leading to a net achievement.

A large portion of this output was focused on the establishment of Peace Committees. These committees are an ethnically and religiously diverse set of community members who are trained on stakeholder mapping, engagement and dispute resolution (indicator 1.3.1). Subsequent indicators (e.g.1.3.2) were developed in coordination with the Peace committees to ensure they were embedded within local structures and relevant to the local context. BPSI (through indicator 1.3.3) was able to secure buy-in across a wide spectrum of government institutions including mayors, education directorates and police departments. IRC worked alongside government to deliver campaigns relating to these initiatives, ensuring they were aligned to their priorities. IRC noted that early coordination with government stakeholders was key to the high levels of engagement (overachievement against targets) cited above and efforts were also able to be increased on this indicator due to exchange rate gains.

The output also overachieved on sharing positive narratives and raising awareness of peacebuilding. This overachievement was partly due to exchange rate gains meaning Implementing Partners could increase targets, and partly because of the effective use of social media. Topics related to social cohesion had the biggest impact – these campaigns directly reduce the likelihood of local conflict by encouraging social cohesion and prepare communities to accept returnees.
BPSI provides excellent synergies by further mitigating the push factors into radicalisation and recidivism by decreasing social and economic marginalisation and conflict. BE Baghdad’s CT programming focused on returnees from North-East Syria is designed to increase resilience and preparedness for return to Iraq and onward re-integration. BPSI also consolidates the impact of the Counter-Daesh Communications Cell’s strategic communications In Iraq, which sensitises audiences to rehabilitation and reintegration, and promotes shared social identities and the citizen-state relationship in Governorates that BPSI delivers activities in. This reduces the CT risk by increasing individual protective factors against sources of radicalisation in North-East Syria and communities of return. BE Baghdad have linked appropriate implementing partners up, to amplify impact across similar outputs.

Overall, IRC report high levels of satisfaction with the social cohesion activities, noting that participants particularly valued the participatory approach, relevance of topics, and opportunities for cross-community interaction. Significant overachievement against expectations was also seen for indicator 1.3.7, indicating the impact of social cohesion activities on improving relationships between different groups in the communities targeted. Whilst this year’s achievement represents a slight decline from year 1 (88%) it still reflects the positive sentiment towards activities delivered and perceptions of social cohesion in the communities targeted.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes were made to this output during the reporting period. In Phase III of BPSI, there will be greater emphasis on Peace Committees and ensuring their structures are fully embedded and functioning within communities. Peace Committees will also be complemented by Natural Resource Management Committees – allowing for further integration of climate-sensitive activities and greater understanding and prioritisation of climate concerns at the local level.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from previous AR:
Indicators 1.3.2 and 1.3.3 were both moved from Phase I to Phase II – staff shortages in TAD and PFO last year meant they could not be completed within the original planned timeframe. Both these indicators have now been achieved (and exceeded) within this reporting period. The recommendation of IRC as consortium lead conducting regular meetings with partners to track progress has been actioned, and this output has not suffered any issues since.

Recommendations for next year:
A mid-term evaluation conducted by IRC (through a third-party) suggested stronger follow up on Community Action Plans and ensuring Peace Committees’ capacity for conflict resolution was improved. As the donor landscape shrinks in Iraq and, localisation and sustainability of interventions becomes a key priority investing in structures like Peace Committees foster community cohesion as the rate of returns to communities continues (as a result of accelerated returns of Iraqis from Northeast Syria, and the eventual – although undefined – closure of IDP camps). Moving forward, BPSI should continue to focus on building the capacity of peace committees to conduct consistent, community-driven and contextually-appropriate community-level peacebuilding activities, raising their own or local government funds to do so, and to continue engaging effectively with local community structures.

Evidence and feedback from partners show that BPSI communities are increasingly concerned about climate impacts in their communities. Partners should integrate climate-sensitivity further into BPSI and consider the impacts of this, as well as how climate sensitivity can continue to be integrated into BPSI in future years, given the links between climate impacts and internal displacement/livelihoods.

Output Title	IOM: Registered and prioritized IDPs and returnees from NES, transiting via J1, receive material assistance and tribal engagement support for safe and dignified return and reintegration.
Output number:		1.2	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes – IOM not reviewed in last AR

Indicator(s)	Milestone(s) for this review	Progress
1.2.1: # of households receiving tailored grants packages	Phase II planned: 70	Phase II achieved: 68

Briefly describe the output’s activities and provide supporting narrative for the score.

This output aims to ensure smooth, dignified and sustainable departures for those leaving Al Amal rehabilitation camp (formerly known as J1). In February 2025, in response to US funding pauses in Al Amal camp. FCDO provided an extra £100,000 to IOM to deliver multi-purpose cash assistance departure grants to a further 70 households leaving Al Amal to ensure their return is dignified and sustainable. Priority was given to female headed households (65% of grants), and most of these households returned or relocated to Anbar (particularly Al-Qaim).

A follow-up survey of recipients showed that 99% could find the items they needed to purchase in local markets, although high prices and transport costs remained a constraint to the purchasing power of the grant, and 70% of recipients said the grant was insufficient due to its value and market inflation. Most used the grant within one month, and 83% of recipients said the grant helped them avoid negative financial coping mechanisms such as borrowing, child labour or skipping meals. Whilst Focus Group Discussions showed these grants made recipients feel more secure (93%), recipients stated that once the money ran out, financial challenges re-emerged.

The IOM evaluation found that, despite the challenges cited above, the grants provided to those leaving Al Amal were a “critical enabler of reintegration” – respondents cited the grant as “essential” in facilitating their return and “addressing their most pressing needs”. The evaluation outlines that these grants were used to cover a range of pressing needs, including food, basic non-food items and housing (rent and shelter repairs). Some also noted having used the grant for electricity reconnections, school enrolment, clean water, medical needs and civil documentation – reflecting the ongoing importance of these needs and further underlining the case for BPSI’s continued work on infrastructure rehabilitation and legal assistance.
[note] Final Evaluation Report, Building Peace and Stability in Iraq (BPSI), Salah Al-Din, Anbar, and Diyala in Iraq, Progressive Resolutions of Displacement Situations, May 2025, written by ARFADA for Development and Consultations p26

The evaluation also confirms that cash is an appropriate response in this context, with 99% of recipients stating that cash was the most suitable form of assistance for their needs, giving them greater autonomy to direct the support towards their specific needs. The evaluation also emphasised the criticality of the timing of these grants, with many surveyed receiving these after returning home or during financial stress.
[note] Final Evaluation Report, Building Peace and Stability in Iraq (BPSI), Salah Al-Din, Anbar, and Diyala in Iraq, Progressive Resolutions of Displacement Situations, May 2025, written by ARFADA for Development and Consultations p43

The results of the evaluation also demonstrate the impact of these grants on reducing negative coping mechanisms – with 83% of respondents saying the grant helped them avoid this. 88% of women reported a reduction in coping strategies compared to 68% of men. As this demonstrates, the grants were more impactful among women than men – whilst women noted the grant helped them avoid strategies like borrowing, selling assets or withdrawing children from school, men emphasised the short-term relief of the grant and noted resumption of borrowing, cutting household spending and accepting exploitative labour conditions once grants were depleted.
[note] Ibid. p64

The IOM evaluation notes these grants and the infrastructure rehabilitation to be the most effective interventions assessed, noting that “reintegration monitoring and assessments confirmed that the [grant] remained one of the top three priorities raised by conflict-affected families.” The grants not only provided short-term financial relief but improved both recipients’ confidence in remaining in areas of return (93%) and their perceived community social acceptance (69% - 84% for men and 63% for women). Although overall social cohesion effects were limited and the evaluations notes instances where host community members expressed jealousy over the grants.
[note] Ibid. p75
[note] Ibid. p83-84

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Output 1.2.1 was added in Autumn 2024, as part of an expansion of BPSI activities using ISF funding, and increased in February 2025, as IOM approached FCDO with an assessment of critical gaps following the US review of Federal Foreign Assistance. The targets were agreed by the SRO through the proposal process.

In the coming reporting period, IOM plan to continue more targeted assistance to those leaving Al Amal, providing departure/reinstallation grants, rental assistance and supporting family visitation and reunification.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations relating to this output last reporting year – this is a new output.

Given beneficiary feedback suggests the grants offer only short-term relief, the next reporting period, it is recommended IOM to monitor recipients and explore whether they are eligible for further assistance. This assistance may be through BPSI (e.g. referring them to IRC for legal assistance, or providing livelihood support and training), or through linking beneficiaries to government-delivered services/referral systems, where available. This responds to findings in the IOM evaluation that “the Grant’s limited scalability and lack of linkage to broader recovery frameworks sharply constrained its long-term impact.”
[note] Ibid. p119

The results of this output should also be used as evidence to continue advocacy with the Government of Iraq to ensure returnees are fully supported over the longer-term through proper provision of public services, timely compensation payments, support with livelihoods opportunities and admission into government social protection systems. The sustainability of this support relies on the swift and effective transition of beneficiaries to government support systems.

Output Title	IOM: IDPs, returnees, and host communities prioritized needs have increased access to basic services through quick impact projects (QIPs)
Output number:		2.1	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes – IOM not reviewed in last AR

Indicator(s)	Milestone(s) for this review	Progress
2.1.1 # of QIPs implemented (disaggregated by sector, and governorate)	Phase II planned: 2	Phase II achieved: 2 (both in Salah-Al-Din, one water, one electricity)

Briefly describe the output’s activities and provide supporting narrative for the score.
Infrastructure (and therefore public service provision) in areas of high return has often been left in a state of disrepair since the conflict with Daesh destroyed many villages. Reconstruction efforts have often been directed to more populous, urban areas. Thus, BPSI has supported the rehabilitation of such infrastructure to increase access to basic services such as water and electricity.

Projects are selected through the community prioritisation exercise (output 1.1) and infrastructure assessments. IOM also coordinates with local government before finalising project selection and during the infrastructure rehabilitation process. IOM have significantly expanded the coverage of the electricity infrastructure in Yankaja, that was partially repaired in the previous reporting period. There are now 800 direct and 170 indirect beneficiaries of the expanded network.

IOM also rehabilitated the local water treatment plant in the same village (Yankaja), which has improved both the quantity and quality of drinking water in the community. This has directly benefitted 1700 beneficiaries and indirectly benefitted 300 residents.

During a site visit to Yankaja in Salah-Al-Din in October 2024, a Department of Electricity employee reflected on the challenges he faced in such a diverse community: if he erects an electricity pole in one part of the village where a certain ethnicity is more prevalent, he will be accused by other ethnicities in the village of prejudice. This example highlights the suspicion residents may have towards local authorities, who have not been allocated enough funds by the Government to provide services to the entire village. Therefore, IOM ensure residents are consulted and at the forefront of decision making, through Output 1.1 (community assessments and action plans, which lead to infrastructure projects being prioritised).

Infrastructure rehabilitation work was underpinned by regular engagement with local authorities, communities and national utility bodies, complemented by community feedback sessions and visibility on the activities being conducted. By the time of writing, IOM had finalised the documentation for the infrastructure, and the sites had been handed over to local authorities for future maintenance.

The IOM evaluation found that the suitability of the infrastructure provided varied. Whilst over 90% of respondents in Yankaja suitable, the overall poor condition of the wider local infrastructure system meant te sustainability of the infrastructure rehabilitation was limited because of spare part shortages and ineffective cost-recovery. However, some of these issues can be mitigated through effective maintenance and personnel. Thus, whilst BPSI’s interventions are a net positive to the community, their effectiveness will be limited unless surrounding critical infrastructure (which is outside the scope of BPSI) is allocated sufficient human and financial resource to upgrade and maintain it.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No changes to this output this reporting period.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No recommendations in previous AR.

- IOM and FCDO have discussed how to improve the climate-friendliness of the infrastructure, for example by including solar panels on water treatment plant roofs. This will be looked at in the next phase.
- IOM also suggested they may look to match Government investment into infrastructure rehabilitation, to increase the scope of activities undertaken (designed, implemented, maintained) by GoI. Recommendations from the evaluation also underline the importance of user cost recovery. It is recommended that IOM discuss these options with GoI in conjunction with FCDO in Phase III of BPSI, to further improve the sustainability of the infrastructure.
- The lack of local government funding to prioritise basic infrastructure rehabilitation remains a constraint to the sustainable return and reintegration of those displaced, whilst also negatively impacting host communities and returnees. International funding for these efforts is not a sustainable solution. Both partners and FCDO should advocate for the government to increase its funding for basic infrastructure in areas of high return and FCDO should consider how it can utilise its economic programming and diplomatic networks, i.e. relationships with relevant water and electricity ministries, to advocate for greater government prioritisation of these projects.
- When working on infrastructure, IOM should continue to engage regularly with local authorities throughout and continue to ensure they have the financial and technical capacity to take over infrastructure at the end of the year.
- IOM and FCDO to discuss the issues raised around quality of supplies via infrastructure provided cited in the evaluation.
Output Title	IRC: Individuals affected by conflict and displacement receive legal assistance to remove barriers to durable solutions. (Legal assistance and access to justice services)
Output number:		2.1	Output Score:	A
Impact weighting (%):		17%	Weighting revised since last AR?	Yes – down from 20%

Indicator(s)	Milestone(s) for this review	Progress
2.1.1 # of individuals who attend legal awareness raising sessions	Phase II planned: 1750	Phase II achieved: 2445
2.1.2: # of individuals who received legal assistance or counselling	Phase II planned: 7600	Phase II achieved: 7469
2.1.3: # of individuals who successfully secure civil documentation	Phase II planned: 2600	Phase II achieved: 2143
2.1.4: # of monitored decisions made by justice institutions that are protective of the rights of women, men, girls and boys	Phase II planned: 10	Phase II achieved: 9
2.1.5: % of surveyed individuals reporting improved access to government services and institutions	Phase II planned: 75%	Phase II achieved: 80%
2.1.6: # of individuals who received emergency cash for protection issues	Phase II planned: 22	Phase II achieved: 22

Briefly describe the output’s activities and provide supporting narrative for the score.

Note: for the indicators listed below, some of the beneficiaries may have received more than one service from the legal partners and therefore may be represented more than once in the overall numbers. For example, an individual who received legal assistance or counselling may also then have later successfully secured civil documentation with support from partners and would then be represented under targets for both indicators 2.1.2 and 2.1.3.

This output made significant strides in ensuring individuals have the necessary legal awareness and support to sustainably return to their area of origin/return. Legal Clinics Network (LCN) and Justice Centre (JC) provided legal awareness raising sessions across all five BPSI governorates on civil documentation, family law, and housing, land and property rights. Indicators around legal counselling and support in securing civil documentation slightly underachieved, which was a result of technical disruptions (including the Iraqi Census necessitating a pause in civil documentation registrations; the suspension of electronic appointments with the Civil Documents Directorate, and unpredictable fee changes), and disruption during the period of the US Federal Foreign Assistance review. The indicator was also impacted due to the partners prioritizing complex returnee cases as well as the high demand for Unified ID cards. However, the cumulative two-year target for indicator 2.1.3 was exceeded. Implementing partners also prioritised complex legal cases affecting the most vulnerable, embedding BPSI’s commitment to Gender Equality, Disability and Social Inclusion (GEDSI), however this prioritisation did lead to a slight underachievement against this target as these were cases that were more difficult to conclude.
The exchange rate gains in 2024 again enabled the over-achievement of BPSI indicators (in this case indicator 2.1.1). While not a formal indicator, IRC also used its digital platform “Signpost”, to reach an extra 323,000 people with legal information – showing the effectiveness of utilising digital tools (as also noted above with indicator 1.3.5).

The Implementing Partners also monitored and influenced nine legal decisions that improved protection for marginalised groups. This included faster civil documentation processing (from a one-month to four-day wait time), and a decision which encourages courts to take flexible approaches to marital and parental status (e.g. accepting unregistered marriages). These legal decisions show the progress BPSI’s Implementing Partners have made to dismantling structural barriers to justice. This is further compounded by 80% of surveyed individuals reporting improved access to government services as a result of this output – an overachievement of 5%.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

In March 2025, FCDO provided IRC with £22,128 to urgently address critical needs in Kirkuk and Anbar that arose in the wake of the US Federal Foreign Assistance review. Activities fell under output 2.1, and allowed IRC to directly serve 234 legal cases (65% more than IRC targeted) (213 securing civil documentation, and 21 legal cases addressed). The funding also allowed IRC to collaborate with the Ministry of Interior local authorities in Kirkuk, to expedite the printing and delivery of civil documentation. This work – specifically IRC’s contributions to improving administrative systems and supporting conflict-affected populations - was also recognised by the Judge of the compensation Department in Kirkuk, showcasing the impact and influence IRC has. The funding also enabled IRC to deliver emergency protection cash assistance to a total of 22 individuals (12 in Kirkuk, 10 in Anbar).

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the last AR: “IRC has agreed to update the activities for the next year of the project to ensure that the missed targets will be met within the next year of the programme.” Targets were set for the reporting period at the start of the year. Indicator 2.1.5 was reassessed and overachieved against the target.

Recommendations for FY25/26:
- Targets should be reassessed this year to ensure that a) they remain feasible in light of upcoming Federal elections, b) they reflect the reality of the timescales needed to address the most complex legal cases experienced by the most vulnerable.
- IRC should continue to couple direct legal support with advocacy and capacity building support to address structural issues that affect access to justice – i.e. work on the implementation of the legal aid law and advocacy to support localised justice decisions being applied more broadly.

Output Title	IRC: People have adequate access to livelihood opportunities for improving their living conditions
Output number:		2.2	Output Score:	A+
Impact weighting (%):		11%	Weighting revised since last AR?	Yes – down from 20%

Indicator(s)	Milestone(s) for this review	Progress
2.2.1 % of surveyed individuals whose monthly personal income ‎increased from baseline to endline	Phase II planned: 50%	Phase II achieved: 77%
2.2.2: % of individuals in employability training who improve at least 20% in pre- and post-testing	Phase II planned: 80%	Phase II achieved: 100%
2.2.3: # of individuals completing job skills employability training	Phase II planned: 300	Phase II achieved: 367

Briefly describe the output’s activities and provide supporting narrative for the score.

This output focuses on improving economic resilience and opportunities for individuals, through targeted capacity building sessions that equip individuals with practical skills and market knowledge to enhance employment and self-employment opportunities, with a particular focus on youth.

Key activities included job counselling (including CV writing and interview support), financial health support, networking events with employers and stakeholders. An effective referral mechanism was also initiated whereby IRC referred 86 individuals (54 females, 22 males) in Anbar, Diyala and Salah-Al-Din to IOM, who provided business start-up or expansion grants and further livelihoods training. 27 individuals were also supported with linkages to private and public sector organisations that led to them securing employment.

The number of people receiving capacity building (indicator 2.2.3) was overachieved due to exchange rate gains meaning partners could increase targets, coupled with increased demand and strong community engagement. This was matched with strong demand from communities. Both returnees (221), IDPs (63) and host community residents (83) benefited from this capacity building and partners achieved a relatively even split between male and female participants (186 women and 181 men).

The IRC-facilitated networking sessions challenged negative misconceptions employers had of hiring returnees. IRC found that most employers prefer to hire people they know. IRC supported some in hiring returnees by providing funding for a few days of wages to incentivise a trial period. Up to 70% then continued beyond a year with this approach.

The success of this training is demonstrated by a 100% increase in knowledge among surveyed participants. Participants have engaged with a variety of sectors since completing the training (indicator 2.2.1) and 77% have reported an increase in income (indicator 2.2.3). The overachievement of this indicator is partly due to the successful referral of individuals to IOM’s livelihoods scheme which bolstered opportunities to improve income.

Type of business	Percentage
Retail & Sales	48%
Skilled Trades & Handcrafts	16%
Education & Tutoring	16%
Public Sector	6%
Delivery & General Services	7%
Beauty & Personal Services	7%

Figure table detailing the types of businesses recipients of employment training engaged with.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

No major changes were made, and no major changes are planned as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No recommendations were made in the previous annual review.

Recommendations from this annual review:
- Livelihoods are consistently cited as one of the top barriers to durable solutions for both host communities, IDPs and returnees. In the most recent IRC protection monitoring needs assessment it was cited as the top need across all three groups, amongst 86% of IDPs, 85% of returnees and 92% of host community members. Whilst BPSI has supported small-scale livelihood activities, the programme should consider expanding its scope to focus on embedding economic opportunities within the community – including integrating livelihood opportunities with local economic recovery strategies. This recommendation can be delivered by both IRC, its consortium partners, and IOM (with the addition of a new activity which focuses on small business expansion – detailed below).
  [note] IRC protection needs overview: Monitoring and Trends October 2024 – March 2025 p7
- Whilst it was too early in this reporting period to follow up on retention rates in employment, FCDO and IRC have discussed IRC’s intention to follow up with beneficiaries in Phase III to understand how sustainable these employment opportunities have been.
- IRC to consider whether to expand the networking delivered under this output, given demand from beneficiaries.
- The IRC evaluation found that “the Livelihood component showed mixed but generally positive results. While all participants (100%) reported knowledge improvements, employment outcomes varied significantly. . . Job Counselling proved more effective in quality outcomes, with 33% reporting stable and sufficient jobs compared to 11% from Financial Health Encouragement, though the latter group experienced slightly higher income growth rates.” IRC, IOM and FCDO should discuss findings from both the IRC and IOM evaluations and consider whether livelihoods activities could or should be modified to improve impact in terms of employment outcomes and sustained income.

Output Title	IOM: IDPs, returnees, and host communities have increased income generation capacity through individual livelihoods assistance (ILA) to support sustainable reintegration.
Output number:		2.2	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes – IOM was not reviewed in the last AR

Indicator(s)	Milestone(s) for this review	Progress
2.2.1 # of individuals provided with individual livelihood assistance (disaggregated by sex, age, type of assistance, and demographic status)	Phase II planned: 65	Phase II achieved: 65

Briefly describe the output’s activities and provide supporting narrative for the score.

IOM delivered Individual Livelihoods Assistance to returnees, IDPs and host community residents. Notably, 30% of the initial cohort for Phase II and 49% of all beneficiaries across the reporting period were referred to IOM by IRC. This demonstrates the effective coordination between BPSI implementing partners, increasing the likelihood of beneficiaries achieving positive outcomes, as they had received complementary support from both organisations.

The majority of recipients were female (65%), and returnees (85%). This high proportion of female recipients reflects IOM’s embedded gender sensitivity approach to livelihoods interventions: for example, IOM ensured flexible hours for registration and activities related to livelihoods training. IOM’s teams are also gender sensitive/balanced, and activities were designed to align with existing social norms around gender. Recipients received and completed business development training activities, including writing a business plan that was then assessed by IOM, with all 175 business plans meeting IOM standards for viability and sustainability. Recipients received a cash grant to support them in setting up or expanding their small business. IOM continued to balance setting up and expanding existing businesses, to ensure income generation opportunities were distributed across the population. 141 beneficiaries were supported to establish new businesses, with 34 expanding existing micro businesses. Interestingly the gender breakdown was more even between those expanding businesses (53% female, 47% male), compared to those starting new businesses (74% female, 26% male).

In October 2024, BE Baghdad conducted a field visit to Yankaja, Salah-Al-Din, where HMA Steve Hitchen engaged with recipients of the livelihoods assistance. They reported feeling grateful to IOM for the support provided, and showed HMA around their small businesses, outlining the challenges and opportunities they had faced. IOM Iraq generated social media posts from this visit, which received strong engagement.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to the output during the past year, and no planned changes for the next year. However, for the next year of the programme, BPSI is expanding its livelihoods support via IOM to include funding for their Enterprise Development Facility, which supports micro-, small- and medium-sized enterprises (MSMEs) and job creation within these businesses. An additional indicator will be added to capture this work.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from the previous AR.

For the next reporting period, FCDO and IOM have agreed to continue this output and add another related activity – the Enterprise Development Fund (EDF). This livelihoods approach seeks to bolster local value chains by boosting job creation and increasing employability outcomes for Small and Medium Sized Enterprises. The EDF approach should be aligned with existing livelihood activities from both IOM and IRC.

It is also recommended that IOM ensure proportionate market assessments are conducted when determining the scope of livelihoods grants. IOM’s own evaluation points out that many recipients of grants struggle with intense competition or lack of access to the value chain. Prior assessments and careful tailoring of grants may therefore increase the likelihood of sustainable positive impact of the grants.

IOM has achieved excellent representation of female beneficiaries in livelihoods interventions through a gender-sensitive approach. Both IOM and IRC should continue to ensure livelihoods interventions are gender-sensitive and continue to reach a significant proportion of female beneficiaries, given the high levels of female-headed HH among returnee and IDP households.

Output Title	IOM: Technical capacity support for civil society and international organizations on durable solutions
Output number:		3.1	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes – IOM not reviewed in the last AR

Indicator(s)	Milestone(s) for this review	Progress
3.1 # of training workshops conducted on durable solutions for civil society organizations and international actors in Iraq	Phase II planned: 2	Phase II achieved: 2

Briefly describe the output’s activities and provide supporting narrative for the score.
Training workshops have been conducted with both civil society and governmental actors in Iraq – covering theory, standards and challenges relating to the practical application of durable solutions. These trainings also provided networking opportunities for participants.

Workshops were delivered in Diyala and Kirkuk. In Kirkuk, IOM organised training for the Joint Coordination Forum (JCF) on durable solutions principles, humanitarian standards and policy frameworks. This was attended by government and civil society. IOM then hosted a Durable Solutions retreat, which reviewed durable solutions plans and addressed gaps, as well as exploring how best to enhance local government leadership and community agency. This workshop helped develop a cohesive vision for durable solutions planning and identified Diyala as a priority area for 2025.

Subsequently, in Diyala, training was delivered in close collaboration with the Diyala Joint Coordination Forum, to equip members of the Forum, and local authorities, with an understanding of durable solutions frameworks and how to apply these within the local context. A second workshop in Diyala then brought authorities together from across the area to identify challenges and agree a set of recommendations for how to plan for reintegration within high-priority districts in the Governorate.

IOM reported that a key challenge in making progress on this file was the lack of resource (both human resource and financial resource allocated from the Federal government) at the Governorate level to solve displacement issues. It was also difficult for Governorates to advocate for increased funding from federal budgets. This is a persistent issue programme teams have heard across various Governorates. However, IOM report having “facilitated follow-up meetings with higher-level authorities, resulting in tangible commitments such as confirmed funding for infrastructure upgrades and the formation of issue-specific committees”.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from the previous AR.
FCDO recommends a continued emphasis on strengthening civil society. As funding becomes more scarce, civil society organisations will be crucial to holding the Government of Iraq to account through advocacy and supporting the transition from INGO or UN-delivered services to Government-delivered services.
IOM should continue to support linkages between local authorities and higher-level authorities to help facilitate the realisation of tangible action to address barriers to return at the local level.

Output Title	IRC: Iraqi civil society organizations and affected individuals have the means, tools, and opportunities to advocate for improved and equitable services
Output number:		3.1	Output Score:	A+
Impact weighting (%):		13%	Weighting revised since last AR?	Yes – increased from 5%

Indicator(s)	Milestone(s) for this review	Progress
3.1.1 # of government officials who received technical support including system strengthening	Phase II planned: 230	Phase II achieved: 355 (250 men; 105 women)
3.1.2: % of individuals who are satisfied with equity in applying the existing laws and regulations	Phase II planned: 75%	Phase II achieved: 82%
3.1.3: # of trainings and support provided for marginalised groups, with emphasis on girls and women, to lead advocacy campaigns	Phase II planned: 4	Phase II achieved: 4 / (96 people; over 60% women)
3.1.4: # of policy papers produced to influential actors	Phase II planned: 1	Phase II achieved: 3
3.1.5: # of evidence-based advocacy campaigns supported/started with the government to amend/implement policies	Phase II planned: 4	Phase II achieved: 6

Briefly describe the output’s activities and provide supporting narrative for the score.
This output focuses on systems strengthening, by supporting marginalised groups, training local authorities, and directly delivering advocacy campaigns relating to Durable Solutions and equitable service provision.

Indicator 3.1.1 overachieved in terms of the number of government officials it trained on issues such as mainstreaming rights-based approaches to public services and protection principles. This was, in part, due to IRC internal and some government funding contributing to this initiative. Whilst trainings in the field and support to the Child Welfare Committee were fully FCDO-funded, the Iraqi High Committee on Human Rights (IHCHR) was funded by IHCHR with BPSI technical support. IRC also funded trainings with the National Department for Iraqi Women and the Ministry of Migration and Displacement, whilst the access to information law workshops were jointly funded through BPSI and with IRC internal funding.

The effectiveness of the capacity building is demonstrated in the results of indicator 3.1.2’s survey, where 82% of respondents were satisfied with the application of laws and regulations; surpassing the target of 75%.

To complement the capacity building of government officials, Baghdad Women’s Association (BWA), Peace and Freedom Organisation (PFO), and Justice Centre (JC) delivered training sessions to empower marginalised groups to advocate better on local issues including women’s rights, youth engagement and anti-discrimination efforts.

Members of the consortium also over-achieved on indicator 3.1.4, partially due to exchange rate gains and partially due to some work starting in the last reporting period. This produced influential policy papers on specific return and reintegration issues in Kirkuk and Anbar; the impact of climate change on employment opportunities for IDP women, and a paper recommending ways to strengthen social cohesion in conflict-affected areas. FCDO attended the launch of the climate and gender paper written by BWA. The launch conference was well attended, with a high proportion of women in the audience. There were members of the Environment and Planning Ministries present, as well as the PM’s Advisor on Civil Society.

Finally, the implementing partners delivered four evidence-based advocacy campaigns, representing a commitment to policy reform. They included a national dialogue on the Legal Aid Law, advocacy around the enforcement of the Access to Information Law, strategic engagement with the National Department for Iraqi Women, and organisational capacity assessments and recommendations for both the Iraqi High Committee on Human Rights (IHCHR) and the Child Welfare Committee. Whilst some of this engagement has been successful (notably the Legal Aid Law being passed, and the IHCHR adopting some of the organisational capacity assessment recommendations and self-funding their implementation), IRC’s own mid-term evaluation noted that inconsistent government ownership and lack of commitment of resources can hamper impact.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There were no changes to this output, and there are no planned changes as a result of this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

There were no recommendations from the previous AR.

FCDO recommends a sharper targeting and higher threshold for deciding to develop and launch new policy papers. The barriers to Durable Solutions in Iraq are well understood, with several studies providing data and recommendations in recent years. To ensure value for money, policy papers should only be written where genuinely novel or concrete recommendations will be presented to a willing recipient audience, or where there is a genuine knowledge or policy gap, or where increased evidence or research would complement momentum on a specific issue. BPSI should continue to focus on delivery and supporting the Government to implement past (relevant) policy recommendations or initiatives (i.e. laws now adopted or findings of organisational capacity assessments) through its other programme activities.

Output Title	IOM: Establishment of policy dialogues with government counterparts to elevate identified issues and encourage policy making.
Output number:		3.2	Output Score:	A
Impact weighting (%):		4%	Weighting revised since last AR?	Yes – IOM was not reviewed in the last AR

Indicator(s)	Milestone(s) for this review	Progress
3.2.1: # Number of technical policy dialogues organized to identify solutions for recurrent barriers hindering the achievement of durable solutions	Phase II planned: 2	Phase II achieved: 2

Briefly describe the output’s activities and provide supporting narrative for the score.
A series of policy dialogues were delivered to strengthen reintegration efforts and improve collaboration and effectiveness of authorities.

IOM coordinated the Suleiman Beg Durable Solutions Dialogue in Tuz District, Salah-Al-Din. This discussed urgent challenges in the area including housing destruction, delayed financial compensation and a lack of basic services, identifying priority areas for next steps (compensation reform, infrastructure rehabilitation, increased police presence and civil documentation support).

IOM also co-organised a national-level policy dialogue titled “Conference on Internal Displacement and Human Rights in the Kurdistan Human Rights Plan” in Erbil. The conference explored the KRI’s legal commitments to IDPs, including women and minorities. It led to calls for legislative reform, strengthening of anti-discrimination policies and greater access to social services for vulnerable groups.

One policy dialogue was held with the Ministry of Migration and Displacement (MoMD), which focused on harmonising how IDPs and returnees are categorised when registering for services. 23 recommendations were put to the MoMD Minister, focused on how to harmonise central and branch offices to ensure consistent application of services.

Finally, a further dialogue took place in Ninewa, focused on the changing shape of the humanitarian/development landscape in the Governorate. It allowed local authorities to reflect and acknowledge contextual changes but highlighted growing concern over the international community’s diminishing presence and Iraq’s growing responsibility in leading reintegration efforts. One outcome of the meeting was an action taken away by participants to more concertedly lobby the Federal Government for funds relating to this file. Another action was to ensure shared spaces between different Ninewa institutions were used to develop joint messaging and asks that could be delivered to the Ninewa Governor, allowing for better coordination across strategy and delivery of services. IOM have also since developed a policy paper highlighting the challenges relating to compensation and provided recommendations for system reforms that would better facilitate the provision of compensation to victims. Whilst the policy recommendations are a product of discussions with local authorities, implementation and advocacy at the central level is often a challenge, and this means the impact of this policy paper has not yet been realised.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No recommendations from the previous AR.

A recommendation for this next reporting phase is to involve FCDO early, as policy papers are being developed, to ensure FCDO can support in sharing the recommendations and messages with key interlocutors to improve likelihood of adoption.

Recommendations from IRC output 3.1 also apply.

Output Title	UNDP: Funding for the Durable Solutions advisor to the UN Resident Coordinator
Output number:		4	Output Score:	A
Impact weighting (%):		9%	Weighting revised since last AR?	Yes – new output/activity for this reporting period

Briefly describe the output’s activities and provide supporting narrative for the score.
BPSI has funded the Durable Solutions Advisor (contracted by UNDP but based in the UN Resident Coordinator’s Office) in Baghdad. This role effectively complements UN global efforts to embed effective approaches to Durable Solutions across several priority countries, including Iraq, under an initiative led by Robert Piper, the Secretary-General’s Special Adviser on Solutions to Internal Displacement. This work is also supported by a central UN Internal Displacement Solutions Fund, which operates in Iraq and has received central FCDO funding. Therefore, funding to this role not only supports BPSI, but is aligned with and effectively supports central FCDO policy and programming efforts on durable solutions.

This component of BPSI does not have formal outputs, but the role holder has clear objectives:
Advise and support the development of UN programmes and activities in Iraq to ensure better join up between the Durable Solution approach, moving Iraq along the humanitarian-development continuum.

- Act as the focal point on internal displacement and coordinate across multiple stakeholders including the Government of Iraq, UN agencies, Operation Inherent Resolve, the international community and displacement-related platforms (e.g. Durable Solutions Technical Working Group)
- Effectively mobilise financial resources and coordinated advocacy points, to contribute to the improvement of conditions and return pathways for displaced communities in Iraq.
- Identify and address technical gaps on issues related to displacement, including the displacement of Yazidis, and the approach to Iraq repatriating its nationals from North East Syria (Al-Hol camp) back to Iraq.

Over the reporting period, the Durable Solutions Advisor has delivered several key pieces of work that have contributed to shifting the dial on this file, including the Durable Solutions Roadmap, the Sinjar Needs Assessment, and most urgently, the revised UN OnePlan – the guiding document for the UN’s approach to supporting the Government of Iraq in returning its nationals from North East Syria.

The Durable Solutions Advisor reported to FCDO regularly throughout the reporting period through ad-hoc meetings and briefings. The information provided allows the FCDO to maintain an accurate picture of this rapidly evolving file, which is vital to managing the UK’s broader equities including development, political and counter-terrorism risks. The role also gives FCDO excellent access and influence to the highest levels of the Durable Solutions/displacement ecosystem. This link and unique access to information allows the UK to play a leadership role on this file, such as being a central convener for likeminded donors on revised versions of the Oneplan and on donor messaging to the UN and government in UN Oneplan Steering Committee meetings.

The Durable Solutions Advisor was also a strong advocate for BPSI-related activities throughout the reporting period. The Advisor attended several workshops run by both IRC and IOM, and gave a number of speeches at them, calling for coordination of activity in this space and endorsing BPSI’s outputs.

Changing context in Iraq
The Durable Solutions Advisor has flexed his role based on the operating context. At the beginning of the reporting period, the Advisor focused on contingency planning and advocacy around the Government of Iraq’s announcement to close IDP camps by July 2024. This closure did not materialise, but the coordination of resources and advocacy was useful, and the Durable Solutions Advisor has since engaged on government recommendations and committees around ending displacement.

The second contextual change was the fall of the Assad regime in Syria and the subsequent decision by the Government of Iraq to expedite the repatriation process of Iraqis in Al-Hol Camp in Northeast Syria, and their returns journey in Iraq. In the last six months, more Iraqis have been returned from Al-Hol to Al Amal Rehabilitation Centre in Iraq than in the previous two years. The Durable Solutions Advisor took over drafting of the revised UN One Plan (already underway when accelerated returns began). The revised plan was formally launched on the 30th January in Baghdad, alongside Government of Iraq representatives, and has also played a critical role in convening donors, UN and government, and conducting advocacy with government on this file since.

Third, the Durable Solutions Advisor coordinated an assessment of budget gaps following the US review of Federal Foreign Assistance and worked to reprioritise support for the repatriation of Iraqis from Northeast Syria to Iraq. To mitigate funding shortfalls, the Durable Solutions Advisor coordinated strategic advocacy interventions and high-level engagements with senior interlocutors; strategic meetings with relevant Government of Iraq Ministries, and a concerted advocacy campaign to reinforce messages to the Government of Iraq around the urgency for domestic resource mobilisation on this file.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

This is a new output - there were no significant changes to the way in which the Durable Solutions Advisor operated over the reporting period, although as mentioned above, the role flexed according to the context and the latest priorities. The Terms of Reference for this role have been updated for the coming year to reflect the latest priorities in Durable Solutions in Iraq.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No recommendations from the previous AR.

It is recommended that the Durable Solutions Advisor continues to link closely with other BPSI implementing partners, including downstream consortium partners, to profile their work as appropriate. This will support FCDO’s commitment to the localisation agenda.

## D: VALUE FOR MONEY

Key cost drivers and performance

Value for Money in the original Business Case details that promoting stability, and minimising conflict, is better value for money over the medium-longer term than responding to the impacts of conflict. Promoting stability also enables BE Baghdad to achieve its other goals including promoting inclusive growth, and achieving security and migration objectives as set out in the Country Business Plan.

During this reporting period, the ODA budget for BPSI remained stable. The Integrated Security Fund added a further £3.3m funding to IOM, using BPSI’s business case. This enabled IOM to increase targets and add an extra Outcome to the results framework, although IOM reported that the process of accessing two separate ‘pots’ of funding was difficult to manage.

The primary way in which BPSI achieved value for Monday is by partners utilising their existing footprint in-country to stand up activity quickly and achieve economies of scale. IOM, IRC, the consortium partners and the Durable Solutions Advisor have all been operating in Iraq and have built existing relationships and structures through which they deliver. This means that a (relatively) small injection of funds through the BPSI programme can deliver impact beyond what we’d expect, and the multi-component approach compounds this impact as each partner benefits from the others’ presence.

Economy
BPSI achieves Economy in several ways:
Leveraging experienced staff. BPSI has relatively high staff input costs, which is expected given the programme relies on technical experts to deliver wide-ranging activities. Whilst this model does not yield the same input-to-results conversion as other programmes (including humanitarian programmes focussed more on delivery of assistance), it reflects the move along the humanitarian-development continuum in Iraq, where capacity building and advocacy make up a higher proportion of inputs. Further, the quality and quantity of technical experts combined with the partners’ large in-country footprint allows for economies of scale: many staff are working on multiple grants (funded through other sources), which they can leverage. Further, IRC reported that it benefits from engaging IRC staff that are not cost recovered through the BPSI grant. This would not be possible had we not been working with a large, experienced INGO.
Benefitting from partners’ long-held presence in Iraq. BPSI funded the same five local NGOs as part of the IRC-led consortium as last reporting period and therefore there were no new start-up costs this year. The five NGOs received the majority of budget (approx. 60%). Their travel, subsistence and salary costs are lower than international counterparts, and they often have long-standing relationships that are key to unlocking delivery (for example, securing or not needing access letters to communities) and impact. Funding local NGOs and developing their capacity by supporting them in partnership with an experienced iNGO also helps build sustainable local organisational capacity, especially important given the decrease in international funding and staffing witnessed in Iraq over the reporting period.
Low input costs and high reach/impact: The infrastructure prioritised in the reporting period delivered at a direct cost of approximately $47 per beneficiary. Justice Centre and Legal Clinics Network received approximately £680,000 and were able to deliver 14,774 individual interventions through both legal and livelihoods support, alongside broader monitoring and advocacy work. This represents a cost per intervention per person of £46. Given the complexity of the interventions delivered and the significant impact of legal assistance, livelihoods and basic services on reintegration outcomes, these costs are considered reasonable. Similarly, the Durable Solutions Advisor cost a relatively low proportion of the BPSI budget (approx. £210,000 during the reporting period) but had outsized, and effective impact. During this reporting period, there were significant external shocks to the development, durable solutions, and return/reintegration file in Iraq and without this role, it would be difficult to convene relevant stakeholders, update advocacy points at pace, and reprioritise efforts – the Advisor was also able to provide assurance that BPSI’s activities remained relevant and effective during this time.

Challenges: the IOM evaluation does, however, cite issues posed by exchange rate fluctuations and global events. For example, exchange rates affected grant transfer values and purchasing power of budgets for electricity infrastructure, reducing the scale of beneficiaries that were able to be reached by these interventions. Procurement of galvanised metals for electricity infrastructure was also negatively impacted by the war on Ukraine.
[note] Final Evaluation Report, Building Peace and Stability in Iraq (BPSI), Salah Al-Din, Anbar, and Diyala in Iraq, Progressive Resolutions of Displacement Situations, May 2025, written by ARFADA for Development and Consultations p45-46

Efficiency
BPSI’s delivery largely on budget and strong performance across almost all outputs and outcomes underlines the efficiency of the programme. Efficiency is also improved in the following ways:

Partnership with national NGOs, as well as ensuring staff on the BPSI programme are highly qualified and experienced, embeds political economy analysis. This is key to ensuring outputs are delivered efficiently in Iraq – directly into the programme - as these NGOs have accurate and up-to-date understanding of the social and political dynamics including power structures. This reduces the need for expensive surveys and stakeholder analyses. The Durable Solutions Advisor has worked in Iraq on this file for nearly a decade and has built strong relationships with key interlocutors: often, the Advisor will directly convene meetings with the right players in the room to obtain information or get necessary decisions.

Programme management requirements for FCDO are reduced by working through IRC as a consortium manager, and IOM as a well-established partner. Both are familiar with FCDO process and are able to ensure reporting is in line with expectations. Both have fast response rates to FCDO requests which makes for efficient programme management and FCDO has worked efficiently with partners to drive reporting standards, progress compliance requests and make changes to the programme in line with the context throughout the year, i.e. processing additional funding to IOM and IRC. Managing multiple local NGOs via IRC also allows for more efficient management of the programme for FCDO, allowing direct management via one interlocuter, whilst also offering local NGOs access to capacity building which will support them to better be able to work directly with donors in the future.
Effectiveness
The expected outcome of the programme is that the displaced are rehabilitated and returned to Daesh affected governorates. Doing this will, in the long term, require increased Government involvement and leadership of rehabilitation in collaboration with civil society. At the district level these are realistic objectives, and some of the work with IRC has made a tangible difference, for example in terms of adoption of inclusive decisions made by local justice institutions. We have also seen effective engagement and ownership at the local level in terms of involvement and engagement in infrastructure rehabilitation.

However, at the national level, the outcomes of the influencing work are less clear: more factors are involved, many of which are not under the control of FCDO or its partners. Success will be reliant upon the FCDO supporting the collection of strong evidence from the districts and the subsequent building of influencing networks. However, some evidence of success is starting to materialise, in terms of government adoption of recommendations from policy dialogues, capacity assessments and, critically, the legal aid law. Further sustained efforts are, however, needed to ensure implementation of recommendations.

The programme outcomes align with Government of Iraq (GoI) priorities on the Durable Solutions File. Our programming works closely, through both the IRC and the IOM components, with government at all levels in GoI (including local and district level). The programme design has ensured that our programme activities align closely with both governments’ own key priorities and strategies for durable solutions, and BPSI provides capacity and assistance in a way that supports and strengthens local responsibility, capacity, and accountability and leadership.

Activities were effective at contributing towards BPSI’s aims. However, there is still opportunity to improve on the sustainability of some interventions. For example, rehabilitated electricity and water infrastructure in Anbar (funded via ISF) has been performing well since project completion, and this has benefitted the community and improved confidence in public service provision. However, in Yankaja, the rehabilitated water plant has been faced with quality/service issues which means the intended benefits have not been felt by the community. Whilst not directly due to IOM’s delivery, it exposes the risk in handing over projects to local authorities, when resource allocation to public services from the Government is not guaranteed.

Social cohesion activities have been effective at bringing members of diverse communities together through grassroots initiatives, supported by IRC and the consortium partners. These activities certainly have positive impact, as highlighted through post-activity surveys. BPSI implementing partners have also included mechanisms to embed social cohesion initiatives within communities over the longer term. Whilst it is too early to say whether these are effective, it demonstrates a clear commitment to ensuring outputs are effective and sustainable. Further efforts should be focussed on embedding the peace committee model in the next phase of the programme and ensuring these committees are equipped to continue independently in future.

Equity
BPSI focuses on the most at-risk and most marginalised Iraqis and aims to reintegrate them into society through access to services, resources, and justice.

A key element of the community-led work that IRC and the downstream partners implement is recognising and valuing the contributions of different development actors. In addition to the local community members and leaders developing their own community action plans, the programme partners engage and empower communities and marginalised groups to advocate for themselves and each other, for example through specific youth and women’s advocacy initiatives.

By utilising IRC as a consortium manager, BPSI strongly contributes to the localisation agenda. IRC heavily supported the five NGO partners in strengthening their capacities and capabilities (on risk and financial management, project delivery etc). Given that some outputs fell behind schedule in the last reporting period, IRC has invested resource into supporting the NGOs on this. These benefits will be long-felt by both the NGOs who will be better equipped to source their own funding in the future, and by local communities who will have trusted partners that are less likely to cease operating in Iraq in a changing development landscape.
All partners have proactively focused on Gender Equality, Disability and Social Inclusion (GEDSI): IOM’s gender sensitive/balanced teams and delivery of activities at flexible hours that respect established gender norms in villages, has encouraged strong female participation in livelihoods interventions. However, more could be done to ensure greater engagement with women in community planning. IOM also managed to effectively engage people with disabilities in their livelihoods interventions – 4% of beneficiaries were those with disabilities – which provides an effective starting point for greater inclusion in future. IRC has continued to prioritise the most vulnerable and complex cases for legal assistance, successfully pushed for more equitable decisions by justice institutions at the local level and has supported consortium partners to develop more ambitious policies: this reporting period saw TAD and PFO agree new commitments on equitable participation. However, IRC has also noted a lesson learned from this year that protection and legal services should be more strategically tailored to meet the needs of particularly vulnerable groups and that partnerships with grassroots women’s organisations, disability rights groups, and local influencers should be expanded to ensure programming is inclusive, gender-responsive, and community-led.
IRC and IOM have also worked to embed conflict sensitivity across interventions. For example, IRC have ensured conflict sensitivity is embedded in social cohesion activities through pre-engagement consultations, peace committee mediation and coordination with local authorities, as well as taking into account strong awareness of local ethnic and sectarian dynamics when organising activities, to ensure representation and avoid exacerbating tensions.

Cost Effectiveness
The positive working relationship between IRC and IOM is a key driver of cost effectiveness in this programme. The complementary approaches, with IRC engaging well-established local downstream partners, and IOM as a UN agency with experience working with the IDP and returnee communities within Iraq, allow for a balanced approach with different types of activities contributing to the overall ToC. Strengthened collaboration between both partners and referrals between them under their livelihoods components have further contributed to cost effectiveness.
The programme continues to deliver closely to the Iraq Business and Country Plan. As well as being technically appropriate the activities delivered have contributed to the overall durable solutions work taking place with major international donors and development organisations across Iraq. The relationships which have been developed have, in turn, allowed us to engage on wider topics such as the GoI camp closure announcement, Government plans on ending displacement and Northeast Syria returns.

BPSI has proven effective in adapting to the changing context. IOM have also been able to prioritise additional cash support to returnees from Northeast over the course of the reporting period, as returnee numbers increased, and quickly absorb additional ISF funding to maintain and expand vital support to returnees in Al Amal Rehabilitation centre. As noted above, the Durable Solutions Advisor role has operated across a range of priorities and stakeholders throughout the year, adapting to the latest developments in the context. In terms of security, IRC partners were able to adapt to security and access challenges in Kirkuk, Diyala and Anbar, which jeopardised legal and livelihoods support, through flexible modalities, like mobile teams and enhanced engagement with local authorities. Overall, despite significant changes in the context affecting this file over the reporting period, delivery remained strong.

Assessment of whether the programme continues to represent value for money

The programme continues to represent value for money – delivering effective, coherent, and multi-faceted interventions that are appropriate to the needs of beneficiaries and, overall, target key changes at the local and national governmental level that could have positive impacts on reducing barriers to return and supporting reintegration. However, continued VfM of the programme would be maintained and improved by greater and earlier clarity on funding, longer funding timelines, continued flexibility and adaptation, and ensuring continued lesson learning, building on evidence of effectiveness from this year.

As per last year’s annual review, FCDO continues to note the value of the different partnerships implemented under this programme: UN, NGO consortium and technical advisor. As above, these different delivery modalities remain complementary, allowing FCDO to harness technical expertise, international and local experience in country, the scale of UN systems, access to government across various actors, and to support localisation in Iraq. Thus, this annual review continues to recommend a continuation of the current model, although noting that FCDO, IRC and local NGOs will need to work together over the next reporting period to prepare for the design of phase IV of BPSI.

E: RISK

Overview of risk management

Risks on the current risk register are actively managed and include consideration of programme risks and mitigations relating to all partners, and their components within the overall programme. Programme risks are regularly discussed and documented ahead of quarterly British Embassy Baghdad Programme Boards, within any risks outside of risk appetite escalated as appropriate.

Overall, the risk appetite for BPSI remains consistent, at ‘major’. Over this reporting period, the average residual risk rating has reduced from major to moderate, which is primarily down to an improved security environment in Iraq (despite a still-turbulent regional context), and a larger focus on capacity building of the consortium partners’ programme management, which has reduced fraud and safeguarding risks. This is also the first full reporting period where both the SRO and PRO are based in Iraq: this has enabled a much closer understanding of BPSI by FCDO staff, meaning risks are more actively managed in conjunction with implementing partners.

Fraud and safeguarding: Partners have robust mechanisms in place to mitigate the risks of fraud and safeguarding. This includes IRC’s robust monitoring and in-person training for downstream partners and ongoing support to strengthen their internal systems, IOM running a tailored package of trainings for all staff working on BPSI, and fraud and safeguarding letters being sent to implementing partners detailing their responsibilities in October 2024.

Gender equality: Anti-gender campaign: In mid-2023, the Government of Iraq banned the use of the term ‘gender’. BPSI has ensured all messaging is contextually-sensitive and has continued conducting tailored interventions for women and girls, as well as capacity building for government on the specific needs of women, girls, boys and men in reintegration activities, and providing support to implement the National Strategy for Iraqi Women.

Climate and environment: there is a link between climate and displacement, and both IOM and IRC deliver activities under different programmes that address this nexus. Therefore, both partners are well-equipped to deliver climate-sensitive programming, with IRC in particular including climate-related activities in social cohesion initiatives. IOM have ensured that the infrastructure rehabilitation projects they delivered are compliant with basic environmental standards, but more could be done here. We have agreed with IOM that for the next reporting period, more proactive effort will be placed on ‘greening’ infrastructure projects as appropriate, e.g. by including solar panels on the roof of a water treatment plant, but this will be subject to sufficient funding being available and local authorities having the skills to maintain this infrastructure.

Development context: As donor funding to Iraq reduces, it is increasingly important for service delivery and key reforms to transition to the Government of Iraq. This will ensure sustainability of interventions.
Due diligence of partners: A due diligence refresh was completed for IOM before the MOU for this reporting period was signed, and IRC provided updates to recommendations from the due diligence assessment conducted in 2023 to FCDO in May 2025. Both partners have delivered well and are trusted partners of FCDO. IRC has also developed the capacity of local partners through developing and updating SOPs and policies that will improve their capacity to apply for and manage donor funding in the future. Ahead of signing the agreement with UNDP in 2024, additional questions were asked relevant to the nature of the funding for the Durable Solutions Advisor role to complement an existing due diligence held by British Embassy Baghdad.

Recommendation: Given changes in context and priorities over the reporting period, greater national stability but upcoming elections, and the planned departure of IRC from Iraq, it is recommended that a risk refresh be undertaken in the coming reporting period. FCDO should also work with partners and the Durable Solutions Advisor to understand the potential impact of planned elections in November 2025 on project activities and government engagement/policy, document this in risk registers and ensure regular conversations on risk occur in the run up to, during and after the election period.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

IOM and IRC have both successfully submitted required reporting. UNDP (through the Durable Solutions Advisor component) worked with FCDO to deliver tailored narrative reporting on the Advisor’s key priorities and achievements. All have been receptive to FCDO reviews, including timely responses and collaborative discussions with FCDO. Generally, comments have been actioned, and this has led to tangible improvements throughout the reporting year. For example, FCDO provided feedback to IRC on the format of the narrative reporting, which was acted upon and significantly improved the following quarter.

During the reporting year, some short extensions were given to quarterly report submissions, and some follow-up was required when further documentation (such as policy papers or assessments) were required, but this did not impact delivery.

Documentation such as visibility statements and delivery chain maps have been kept up to date and submitted on time, with minimal revisions required because of FCDO reviews.

At times, risk registers could have been more detailed, however this was mitigated by consistent communication with partners both via ad-hoc meetings and email communications. Risk has been managed effectively by all partners throughout the reporting period: this can be attributed to the extensive field experience partners have in Iraq. For example, access to certain geographies (particularly Diyala) was restricted by increased requirements from the Department of NGOs, putting timely implementation of activities at risk. Given partners’ familiarity with the operating context and risk environment and relevant relationships across the Iraqi system, mitigating actions were implemented such as sharing workplans with the Department in advance and the adoption of flexible practices such as remote meetings or smaller gatherings where access was limited.

IOM and IRC (including the consortium) achieved full spend for this reporting period, which highlights excellent budget management across a complex programme. IRC supported the consortium partners with regular financial check-ins. FCDO thoroughly reviewed all forecasts and all queries were successfully responded to during quarterly reporting cycles.

IRC requested to reallocate underspend from Monitoring Evaluation and Learning (MEL) staff costs, and savings obtained due to exchange rate gains, to deliver a third-party mid-programme evaluation. This request was agreed in January 2024, showing the quality of communication between FCDO and the Partners in identifying and mitigating underspend risk early.

Overall, IRC have robustly managed downstream partners, providing tailored capacity building, and robust financial and results management, ensuring all partners were clear on results expectations and reporting these and coherently pulling together information across the consortium for FCDO in reporting. IRC also facilitated multiple meetings with consortium partners to ensure FCDO could engage directly.

Engagement between IOM and IRC has also improved significantly this year, with greater regular meetings and the implementation of livelihoods referrals. IOM and IRC have also collaborated on a lessons learned document detailing the reporting period. In preparing for the coming reporting period FCDO have further encouraged this coordination through joint planning and greater synergies in delivery locations where possible.

Financial reporting from UNDP experienced some delays and inconsistencies during the reporting period, primarily due to the specific contracting modality used for the Durable Solutions Advisor position, which was a secondment from another UN Agency. Under this arrangement, payments could only be processed upon receipt of invoices from the seconding Agency, which affected the timeliness of reporting. These administrative constraints have since been resolved and UNDP has taken steps to ensure smoother, more accurate and timely financial reporting going forward.

G: MONITORING, EVIDENCE AND LEARNING [1/2 - 1 page]

Monitoring and Evaluation

Monitoring visits: The improved security situation, and the movement of the SRO and PRO positions to Baghdad has enabled stronger monitoring from FCDO. FCDO undertook a field visit to Salah-Al-Din in October 2024. The location (Yankaja) had activities delivered by IRC, JC, LCN and IOM, allowing the FCDO team to see the full suite of BPSI initiatives in one place. The Ambassador also attended the field visit, allowing for comms to be developed and posted. The visit was successful and resulted in recommendations around greening the infrastructure rehabilitation projects IOM deliver, as well as a follow up conversation to understand IOM’s approach to ensuring their staff (and importantly their field staff) are trained on fraud and safeguarding policies and procedures. The visit also enabled discussions with beneficiaries to understand the impact of the interventions delivered (livelihoods) and community discussions to understand challenges faced by the community, including the loss of agricultural livelihoods.

Whilst not directly BPSI locations, the BPSI SRO and PRO conducted a visit to Khanke camp in Dahouk in December 2024 to better understand the needs and concerns of IDPs. The BPSI SRO conducted a visit to Al Amal rehabilitation centre in February 2024 to understand better conditions and needs in the centre, and the BPSI PRO also joined a visit to Sinjar with the Deputy Ambassador in March 2025. Whilst BPSI was not explicitly delivering activities in Sinjar during this reporting period, the visit provided a chance to understand the scale of needs in Sinjar, which has resulted in its inclusion in BPSI from the next reporting period. The PRO also met a future BPSI consortium partner (House of Coexistence) on the visit, to understand the value they can add as a hyper-local partner with a specific remit. Similarly, greater engagement on the NES returnees file has led to a focus on likely areas of high return from Al Amal in Anbar in BPSI in the coming reporting period.

BPSI’s programme staff continue to plan for more field visits in the next reporting period.

BPSI programme staff have engaged with all implementing partners throughout the reporting year, and also attended several BSPI-funded activities such as technical workshops, and conferences. This has allowed FCDO to engage with stakeholders and beneficiaries of BPSI, particularly at the political level in Baghdad. This allowed the team to QA outputs and understand the impact of advocacy. Most workshops were well attended and the audience were sufficiently engaged, but identifying whether the workshops have had long term impact has been difficult. A recommendation around advocacy has been included in relation to the relevant outputs earlier in this review.

Evaluation: both IRC and IOM conducted an in-programme evaluation submitted three months after the reporting period ended. Both partners also collaborated to discuss lessons learned after the reporting period and submitted a lessons learned document to FCDO documenting key issues raised.

Annual review: this annual review draws primarily on reporting from all three partners under this programme, complemented by discussions with partners throughout the year and both the IOM and IRC evaluations. The annual review was drafted by the programme PRO, with support from the SRO, with quality assurance from the British Embassy Baghdad Development Director, Conflict Advisor and Risk, Results and Assurance Manager.

Evidence

FCDO has worked with BPSI partners to gather robust evidence as part of monitoring. As part of this, FCDO has emphasised the importance of disaggregated data through quarterly reporting meetings, which has been heeded. Further work can be done next reporting period on disaggregating for, and focusing on, people with disabilities. An evaluation has been conducted by both IOM and IRC using their own data sets and monitoring methodologies included focus group discussions.

Evidence quality is generally strong, although the IRC evaluation notes limitations of data collection including difficulty in reaching individuals who participated in training in the earlier years of BPSI, or females feeling unable to participate in surveys due to social norms. However, mitigation strategies were put in place such as field visits at times that suited women so they could participate.

Learning
Several learning processes were followed over the reporting period, including quarterly meetings with partners to discuss the quarterly reports and adjust any activities. The team also used the development of proposals for FY25/26 as a learning opportunity, engaging with partners on the theory of change and proposing contextually-appropriate shifts to programming. This is, allowing BPSI to shift its focus to geographic priority areas and priority groups, plan for greater cohesion across IOM and IRC project sites, expand livelihoods support to MSMEs and further embed climate-sensitivity. Finally, BPSI partners contributed to other FCDO Iraq Network learning activities such as the ISF-funded review into livelihoods programming. Highlights and challenges from these learning processes were shared regularly across the embassy, including in formal governance processes such as Programme Boards.

Key lessons emerged from this reporting period, including the importance of balancing breath of activity over depth: this was highlighted by IOM in particular in their evaluation of the reporting period, and it has since been agreed with FCDO that partners will reduce the geographical scope of BPSI in order to increase targets (i.e. increased number of individuals benefitted).

Second, the programme tested its ability to pivot to focus on the highest need. This was successful, as demonstrated by delivering activities in Al-Amal in the latter part of the year to respond to the accelerated and increased volume of returns from NE Syria, and reductions/pauses in US funding following the Federal Foreign Assistance review
.
Third, BPSI took learnings from the wider context. For example, the ISF-funded review into livelihoods programming highlighted key areas of improvement for all Iraq Network programmes. BPSI took an action to ensure future livelihoods activities would deliver for the local economy and value chains (not just individuals), focus on influencing key stakeholders through better targeted advocacy and capacity building, and ensure that interventions are closely aligned with other FCDO programming in Iraq, including in CT and ISF teams.

Date of last narrative financial report	IOM – 18/05/25 / IRC – 14/05/25 / UNDP – 24/01/25	Date of last audited annual statement	IOM – 29/05/2025 / IRC – 29/05/25 / UNDP – 01/05/2025