## Annual Review Report

Title: Jordan Protection Programme (JPP) Support to Vulnerable Refugees and Jordanians
Programme Value £ (full life): 15,000,000		Review date: Nov 2025
Programme Code: 301237	AMP start date: 24/11/2021	AMP end date: 31/03/2026

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	B	A	B	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/90000343.odt
DevTracker Link to results framework:	Jordan Protection Programme Logframe 2025.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Jordan Protection Programme (JPP) encompasses two complementary components:

1. Core Protection Services: Strengthening protection systems for refugees and vulnerable Jordanians, including persons with disabilities, through targeted services and capacity-building.
2. Emergency Facility: A flexible mechanism activated to respond to emerging humanitarian needs, enabling the rapid deployment of resources for critical interventions.
Core Protection Services: Implemented by a consortium led by the Danish Refugee Council (DRC), with the Jordan River Foundation (JRF) and Humanity & Inclusion (HI). This component operated from January 2022 to March 2025. It aimed to reach 34,706[1] individuals with:
[1] The original programme target was 43,000 beneficiaries. This was later revised to 34,706 to reflect delays in programme start-up and the impact of a 52% ODA budget reduction.

- Case management for children at risk of exploitation and child labour;
- Support for survivors of gender-based violence (GBV) and individuals experiencing trauma;
- Rehabilitation and early intervention services for persons with disabilities;
- Prevention programming to address root causes of exclusion and protection risks; and
- Capacity-building for national and local entities.
Activities ran across eight governorates, including Azraq refugee camp. This Annual Review covers the fourth year of implementation, covering the period from October 2024 to September 2025. This represents the final year of core protection services activities. A full assessment of overall programme performance will be conducted upon the completion of the programme in March 2026.

Emergency Facility: As the protection component concluded, the emergency facility was activated to address urgent needs through two critical workstreams:
- Water, Sanitation and Hygiene (WASH) Intervention: a £1.5 million Memorandum of Understanding (MoU) was agreed with UNICEF to sustain life-saving water and sanitation services in Azraq and Za’atari camps, aiming to reach approximately 115,000 refugees.
- Refugee Return Assistance: a £1.5 million partnership with UNHCR was agreed to support safe, informed returns, including documentation assistance, counselling, legal aid, and a pilot cash support scheme for vulnerable cases. Aiming to reach approximately 150,000 refugees.
These additions demonstrate the programme’s flexibility and strategic responsiveness, ensuring the continuity of essential services and alignment with UK humanitarian priorities in Jordan.

Summary supporting narrative for the overall score in this review.

The programme scored an A overall, meeting expectations. Below is a summary of each output assessment and score.

	Output	Assessment	Output weighting	Score
1	Women, men, girls and boys at risk of Gender Based Violence (GBV), Child Protection (CP), and other protection concerns are provided with life-saving protection response and rehabilitation services.	Met expectations. Most milestones were met.	52%	A
2	GBV risks are mitigated through prevention programming	Met expectations. Most milestones were met.	19%	A
3	Child Protection risks are mitigated through prevention programming and specialised services	Moderately exceeded expectations. One milestone significantly exceeded expectations and others were met.	20%	A+
4	Capacity-building and strengthening of national and local structures providing protection, rehabilitation and early development services.	Met expectations. All milestones were met.	9%	A

In its final year, the programme delivered meaningful and impactful protection outcomes for vulnerable communities, overcoming earlier constraints of budget uncertainty through adaptive planning, collaborative delivery, and reallocating funding to JRF and HI. The consortium resumed full implementation with revised workplans and scaled-up activities ensuring services reached more individuals in need.

Core protection services implementation concluded in March 2025 having supported 33,868 unique individuals since they commenced. The programme sustained high-quality services and remained responsive to shifting needs. FCDO approved DRC’s request of a no-cost extension until September 2025 to allow for financial and administrative closure. Final evaluation of the overall programme will follow in 2026.

BE Amman’s Development Director approved a business case extension to March 2026, enabling the activation of the JPP emergency facility for emerging humanitarian needs. Under this facility, new interventions with UNICEF (WASH) and UNHCR (refugee return assistance) were launched late in the review period. As these activities began only in June–August 2025, they are not assessed in this Annual Review and will be evaluated in the Programme Completion Review in 2026.

Major lessons and recommendations for the year ahead

The final year of implementation of core protection services under the DRC-led consortium of the programme offers critical learnings to shape future protection programming in Jordan and other protracted displacement settings. These insights underscore the importance of embedding sustainability, inclusion, and strategic responsiveness in programmes.

Among the most impactful interventions were expressive arts for women, rehabilitation services for persons with disabilities, cash for protection (CfP) and helpline activities. These activities not only achieved strong quantitative outcomes but also demonstrated meaningful qualitative improvements in participants’ lives. Expressive arts sessions fostered emotional resilience and self-expression, rehabilitation services significantly enhanced functional independence for individuals with disabilities, CfP proved highly effective in mitigating immediate protection risks such as eviction and legal vulnerabilities and the helpline was seen as helpful or very useful.

Together, these interventions highlight the value of holistic, person-centred approaches that address both psychosocial and structural protection needs. They also reinforce the importance of flexible, locally grounded delivery models that can adapt to shifting contexts and reach underserved populations.
Strategic Recommendations for Future Programming:
- Build on successful interventions: Activities pursued under the programme were found to be effective in supporting Syrians and vulnerable Jordanians living in Jordan – notably using art for psychosocial support, rehabilitation services for people with disabilities, and helpline services. CfP was also found to be an impactful intervention and should be pursued where budgets allow. The programme also showed the merit in addressing multi-dimensional vulnerabilities in an integrated way in protection programming.
- Strengthen systems for sustainable impact: As funding becomes more constrained, future UK support should look to build on systems-strengthening efforts initiated under JPP. The programme successfully continued to embed inclusive protection approaches within national structures such as the Ministry of Social Development (MoSD) and Ministry of Health (MoH). It helped develop and institutionalise three national technical products and also formalise the Community Based Rehabilitation volunteer network. It combined this with effective training of Government and NGO staff to build capacities. Through these it successfully strengthened national systems to help sustainably maintain protection outcomes following the closure of core protection activities.
- Improve referral pathways and health access equity: Strengthen coordination between protection and health actors, and address documentation barriers that limit access for non-Jordanian children, including refugees.
- Strengthen strategies for targeting and engaging refugees: While the programme did reach a considerable number of refugees, (registered and non-registered) the overall reach was lower than expected, highlighting the need for strengthened strategies to target and engage the refugee population in future programming. That said, refugee reach improved slightly in the final year of implementation rising to 57% in Q3 indicating positive progress and the potential for stronger targeting with more consistent and adaptive approaches.
- Strengthen disability inclusion across all protection programmes’ components: Embed inclusive practices in GBV, child protection, and rehabilitation services through co-design with organisations of people with disabilities (OPDs), tailored outreach, and assistive technologies.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Jordan Protection Programme’s Theory of Change (ToC) remains valid, with minor adjustments following the inclusion of emergency funding for protection and WASH in its fourth year. The original ToC focused on reducing protection risks and strengthening the resilience of refugees and vulnerable Jordanians specifically persons with disabilities through integrated services and systems strengthening. It assumed that combining case management, psychosocial support, legal aid, rehabilitation, and cash assistance with community engagement and institutional capacity-building would lead to safer, more inclusive environments and long-term change.
Key outcome indicators demonstrated strong causal links between interventions and results:
Outcome Area	Total Recipients	Positive Outcome (%)	Positive Outcome (Count)	Description
Cash-for-Protection	314	97%	304	Reported mitigation of immediate protection concerns
Rehabilitation Support	3,150	90%	2,772	Demonstrated improved functional independence
Caregiver Support	1,170	94%	1,100	Reported improved access to early detection and intervention services
Government Staff Training	700	81%	567	Demonstrated increased capacity to deliver protection support

These results affirm the effectiveness of the programme’s integrated service model and validate core assumptions around the importance of local partnerships, multi-sectoral approaches, and institutional capacity-building. Services delivered through DRC, though concluded earlier, laid important groundwork in systems strengthening and service integration. Lessons learned include the need for flexible programme design, early exit planning, and coordination with national actors to ensure continuity.

On sustainability, several services initiated under the programme have continued beyond its original timeframe. For example, rehabilitation and early intervention services supported by HI have been sustained through alternative funding sources, and the JRF has retained components of its psychosocial support programming. In parallel, the emergency funding agreement with UNHCR and UNICEF established under the Emergency Risk Facility which was referenced in the programme’s Business Case was designed to address acute and time-sensitive humanitarian needs. While these interventions are time-bound and scheduled to conclude with the programme’s extended end date of 31 March 2026, they have played a critical role in bridging urgent gaps and complementing longer-term service delivery efforts.

JPP’s Monitoring, Evaluation, Accountability and Learning (MEAL) systems provided good evidence of impact, supported by disaggregated data across age, sex, disability, and geography. Tools such as Results Journals, Most Significant Change (MSC) stories, and beneficiary diaries captured nuanced shifts in attitudes and behaviours, particularly around GBV and child safeguarding. Regular engagement with beneficiaries through helplines, feedback mechanisms, and field visits ensured services remained responsive and accessible.

Persons with disabilities accounted for nearly 13% of the 33,868 individuals reached throughout the project’s implementation period. Tailored services including rehabilitation, early intervention, psychosocial support, and assistive technologies were designed and delivered to meet their specific needs.

Conclusion and Implications for Future Programming

The JPP’s ToC has proven resilient and effective. It provided a clear roadmap for achieving impact, and its assumptions were validated through evidence and experience. As the programme nears conclusion, its ToC offers a strong foundation for successor programming. The forthcoming multi-year humanitarian programme will likely retain JPP’s core protection logic while expanding, when possible, on system strengthening and resilience-building. It will continue to target the most marginalised, applying a holistic, adaptive approach that integrates protection services with broader development goals ensuring long-term sustainability and cohesion across refugee and host communities.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The JPP remains broadly on track to contribute to its expected outcomes and impact, despite operational and financial constraints which the programme experienced in earlier years. Outcome indicators reflect robust performance: 97% of Cash for Protection recipients reported reduced immediate risks, 90% of rehabilitation recipients showed improved functional independence, and 94% of caregivers reported better access to early detection services. These results affirm the programme’s effectiveness and the continued relevance of its ToC.

In the final months of implementation, the programme focused on consolidating impact and ensuring sustainability through the following actions:

1. Prioritising high-impact activities such as expressive arts and rehabilitation services due to their contribution to protection outcomes. Expressive arts, delivered as part of case management, supported emotional wellbeing particularly for children and women survivors of violence. Rehabilitation services for persons with disabilities, especially children, promoted functional independence and inclusion.
2. Strengthening referral pathways.
3. Consortium partners, mainly JRF and DRC, partnered with local CBOs to deliver protection services in remote areas, expanding outreach and promoting sustainable, community-based support.
4. Finalising capacity-building efforts with MoSD and MoH to support long-term service integration.
5. Preparing for an independent evaluation to assess cumulative impact and inform future programming.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio.

While JPP is scheduled to conclude in March 2026, it is strongly recommended that key protection activities such as; gender-based violence prevention and response, child protection, mental health services, disability rehabilitation, and legal support, prioritising at-risk groups including women, children, youth, and persons with disabilities; be sustained through their integration into the new multi-sector humanitarian programme. The programme has demonstrated relevance, effectiveness, and alignment with UK strategic priorities in Jordan. It has delivered meaningful protection outcomes and contributed to national systems strengthening. Building on JPP’s most successful components in the next phase where possible will ensure continuity, leverage proven models, and enable a more holistic response to emerging humanitarian needs.

## C. DETAILED OUTPUT SCORING

Output Title	Women, men, girls and boys at risk of Gender Based Violence (GBV), Child Protection (CP), and other protection concerns are provided with life-saving protection response and rehabilitation services.
Output number:		1	Output Score:	A
Impact weighting (%):		52%	Weighting revised since last AR.	No

Indicator(s)	Milestones for this Review[2]	Progress	%
1.1: # of vulnerable beneficiary households (HHs) assisted through case management	2,875	2,558	89%
1.2: # of women, men, boys and girls accessing sustained and structured psychosocial services	643	680	106%
1.3: # of calls received and served through JRF's helpline	9,026	9,493	105%
1.4: # persons with disabilities identified in need of assistance who are receiving specific support	3,150	3,150	100%
1.5: # of children screened positive for impairments enrolled in Early Intervention (EI) programmes	835	890	106%
1.6: # of beneficiaries of comprehensive rehabilitation services that are included in vocational trainings and/or employment opportunities	10	10	100%
1.7: # of refugees which UNICEF Jordan delivers continuous water and sanitation services in Za’atari and Azraq camps for to ensure safe, reliable, and dignified WASH access.	N/A – activity started in June 2025
1.8: # of refugees which UNHCR Jordan provides outreach and individualized counselling, legal support for vital documentation, transportation assistance, and pilot cash-based support to enable refugees who have voluntarily expressed their intention to return to Syria to do so in a safe, informed, and dignified manner.	N/A – activity started in August 2025
[2] The milestone and progress figures referenced are cumulative across the programme.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output delivered essential protection and rehabilitation services, with most indicators meeting their targets. Refugees reach however fell below expectations, with only 52% of beneficiaries being refugees, compared to the indicative 70% target under the Jordan Response Plan. Despite progress against the milestones, some challenges were encountered in delivery including complex and protracted protection needs requiring longer case durations, transportation fees, documentation barriers limiting access for non-registered refugees, high staff turnover and delayed recruitment, and the resource-intensive nature of individualized services such as vocational inclusion and rehabilitation.

Despite these challenges, many activities were highly impactful for beneficiaries. Cash for Protection activities under output 1.1 supported 314 individuals, with 97% reporting reduced protection risks. Rehabilitation services achieved a 90% improvement in functional independence, and the helpline provided critical support, with 94% of users rating it as helpful or very useful. These results demonstrate that while quantitative targets were missed, the programme delivered meaningful outcomes through adaptive, person-centred approaches.

### The services were designed to respond to urgent protection risks and promote long-term wellbeing, with a focus on refugees, persons with disabilities, and economically vulnerable Jordanians. Achievements made were:
  1. Case Management: Delivered by JRF and DRC, this service reached 2,558 individuals by the end of the reporting period, including children at risk of exploitation, survivors of GBV, and individuals facing legal risks such as eviction and documentation challenges. The overall cumulative achievement during the lifetime of this programme reached 89%. Case managers provided tailored support plans, legal counselling, and referrals to specialised services. CfP was delivered as a targeted financial intervention under Output 1.1. CfP aimed to mitigate acute protection risks such as eviction, legal vulnerability, and lack of adequate shelter by providing short-term economic assistance to individuals identified through case management. By the end of year four a total of 314 individuals received CfP, including Syrian refugees, Jordanians, and persons of other nationalities. The final external evaluation of JPP confirmed CfP as a key driver of positive protection outcomes, with 97% of recipients reporting that the assistance was sufficient to address their immediate protection risks. This intervention demonstrates the valuable role of economic support in reducing protection vulnerabilities and enhancing resilience among affected populations.
  2. Psychosocial Support: Delivered through DRC and JRF, structured counselling sessions reached 680 individuals, meeting expectations. These sessions targeted emotional distress, particularly among women and children affected by displacement, trauma, or uncertainty around potential returns to Syria. Delivered by trained counsellors, the sessions were designed to foster resilience and emotional stability.
  3. Family and Child Helpline: Operated by JRF, the helpline achieved the target of 9,493 calls out of 9,026 planned, offering confidential, real-time support and referrals. It served as a critical access point for protection services, especially for women and children in remote or high-risk areas. While the helpline exceeded its call volume target, only 59% of identified demand was fully met through direct counselling or successful referral. This reflects the complexity of cases received, limitations in external service availability, and operational constraints in scaling up response capacity. Despite these challenges, the helpline remained a vital entry point for protection support and demonstrated strong effectiveness, with 94% of users rating the service as helpful or very useful.
  4. Rehabilitation Services: HI met its target of providing rehabilitation to 3,150 individuals, including physiotherapy, occupational therapy, and assistive devices. Services were tailored to children and adults with physical and developmental disabilities. Rehabilitation services met 70% of identified demand due to budget cuts, staffing shortages, and the intensive nature of individualised care. Quality was measured through functionality assessments, with 90% of recipients showing significantly improved independence.
  5. Early Intervention: Through HI 890 children with developmental delays were enrolled in tailored therapy programmes, supported by caregiver engagement. Services included speech therapy, motor skills development, and early detection screenings. Early Detection services could not meet all the identified demand due documentation barriers for refugees, and limited access for non-Jordanian children at Primary Healthcare Centre (PHC) level.
  6. Vocational Inclusion: The community inclusion initiative led by HI, previously paused due to budget cuts, was resumed in late 2024. Individuals with functional limitations accessed vocational training and reintegrated into their communities, supported by HI and local service providers. While efforts were made, the scope and intensity of support required for inclusion in vocational training or employment was more complex and resource-intensive than initially anticipated.

Describe any changes to this output during the past year, and any planned changes because of this review.
### The final year of the programme was marked by a series of strategic adjustments aimed at restoring momentum after a challenging FY23/24. Following the confirmation of the FY24/25 budget, consortium partners revised their workplans, targets, and staffing structures to reflect both the lessons learned from the previous year and the realities of available funding. Recruitment and training resumed early in the year, enabling the reactivation of paused services and the expansion of activities into underserved areas such as Ma’an and East Amman.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.
In its final year, the programme made notable progress on key recommendations from the previous review. Recruitment and training efforts helped restore staffing levels, enabling the resumption of critical services. However, earlier gaps continued to affect case management throughout and closure rates.
The recommendation to reduce Output 1’s weighting was given careful consideration but not addressed to reflect the addition of new activities under output 1 under the emergency facility. Output 1.6 was reactivated which aimed to advance community inclusion for persons with disabilities through vocational training and functional assessments.
Despite some improvements in transportation support, systemic challenges in budgeting and payment mechanisms persisted, particularly for refugees facing documentation constraints.
The key approaches under Output 1 demonstrated strong impact and offer valuable direction for future programming:
- Integrated Protection Packages: Providing support for multidimensional vulnerabilities through psychosocial support, legal aid, and financial assistance proved especially effective for refugees and persons with disabilities, who often face intersecting protection and economic vulnerabilities. Institutionalising these packages would ensure holistic, person-centred service delivery that is responsive to complex needs.
- Community-Based Rehabilitation (CBR): CBR networks and peer-led support groups fostered local ownership, strengthened referral pathways, and ensured continuity of care—particularly in underserved and remote areas. The programme worked to embed these models within MoSD systems, supporting long-term sustainability.
Recommendations:
- In future programming to explore opportunities to integrate economic assistance within Protection Frameworks where there is sufficient budget: Future protection programming should continue to incorporate CfP as a targeted form of economic assistance within case management where budgets allow. CfP has proven effective in mitigating urgent protection risks such as eviction, legal insecurity, and lack of shelter by addressing financial vulnerabilities. This intervention should be clearly reflected in output-level planning, budgeting, and reporting, and linked to broader protection and resilience strategies.
- Support institutionalisation of inclusive practices: Building on existing programme achievements, future programming should continue to support the MoSD and MoH to institutionalise inclusive practices, strengthen referral pathways, and expand early detection and rehabilitation services. This will help ensure continuity, scale, and sustainability of inclusive protection services across Jordan.
Output Title	GBV risks are mitigated through prevention programming
Output number:		2	Output Score:	A
Impact weighting (%):		19%	Weighting revised since last AR.	No

Indicator(s)	Milestones for this review[3]	Progress	%
2.1: # of women and men attending Engaging Men through accountable practice programme	1,383	1,421	97%
2.2: # of women who received Expressive Arts workshops	1,193	1,193	100%
2.3: # community-based mechanisms/groups working on GBV prevention and response	5	5	100%
2.4 # of boys and girls attending GBV and gender programming for adolescents’ programmes	2,975	2,964	100%
[3] The milestone and progress figures referenced are cumulative across the programme.

Briefly describe the output’s activities and provide supporting narrative for the score.
### In its final year, Output 2 delivered a robust suite of GBV prevention services, meeting expectations across the indicators. These interventions targeted men, women, and adolescents with tailored approaches aimed at fostering behavioural change, emotional resilience, and community-level awareness around GBV prevention and reporting measures, enhancing protection and accountability mechanisms. Achievements made were:
  1. Engaging Men Through Accountable Practice (EMAP)- Delivered through DRC: The programme reached 1,421 men and women through structured sessions that promote gender-equitable attitudes and challenge harmful norms. The EMAP approach engaged women in initial sessions to identify community gender concerns, which then informed structured dialogues with men to promote gender equality and accountable behaviour change. Participants were primarily from underserved urban and peri-urban communities, where GBV risks are heightened. Feedback indicated increased self-reflection and peer accountability, suggesting strong uptake and relevance.
  2. Expressive Arts Workshops for Women Delivered through JRF: A total of 1,193 women participated in therapeutic arts-based sessions designed to support emotional healing and self-expression. Qualitative assessments showed high satisfaction and improved psychosocial well-being. Many participants reported new coping skills, improved self-expression, stronger social connections and enhanced emotional well-being safer and felt more empowered to speak out against violence.
  3. Community-Based Mechanisms Delivered through JRF: No new groups were formed during the final year of implementation, with the target of five groups having been met previously in the programme. This decision reflected a strategic shift from expansion to consolidation focusing on strengthening and sustaining the impact of existing community structures. It was also influenced by practical constraints, including significant budget reductions and the programme’s transition into its final phase, which prioritized sustainability, local ownership, and responsible closure over the launch of new initiatives.
  4. Adolescent GBV and Gender Programming Delivered through DRC: The programme reached 2,964 boys and girls through interactive modules on consent, healthy relationships, and gender roles. Delivered in schools and community centres, the sessions were well-received, with facilitators noting increased confidence and peer-led advocacy among youth.
### Progress on Recommendations and Lessons Learned:
### Last year’s recommendation to improve long-term tracking of prevention activities was implemented. DRC expanded the use of Results Journals, and JRF applied the Most Significant Change methodology to assess impact. Inclusion of persons with disabilities improved, though further work is needed to address participation barriers. The final year confirmed the value of creative and gender-transformative approaches, reinforcing their relevance for future programming.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

Targets were revised upward following the budget increase in April 2024. EMAP and adolescent programming were expanded to new locations, and monitoring tools were strengthened to capture behavioural outcomes.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

- Expressive arts sessions are considered a high-impact activity based on interaction and testimonies from beneficiaries of the programme. It offers a safe and creative outlet that supports emotional wellbeing and resilience, especially among children and survivors of violence. Continue supporting art as a protective and psychosocial support intervention in future programming, given its alignment with broader protection goals and the positive feedback from participants.
- Throughout the project, inclusion of persons with disabilities in GBV prevention and response was prioritised through targeted outreach, adapted facilitation methods, and collaboration with disability-focused organizations. A total of sixty-eight persons with disabilities participated in EMAP sessions, and eighteen adolescents with disabilities were engaged in GBV programming. To enhance accessibility, sessions were held in physically accessible venues, and facilitators received training on inclusive communication and disability-sensitive approaches. Additionally, HI supported the development of inclusive tools and referral pathways to ensure survivors with disabilities could access protection services without barriers. However, feedback from participants and implementing teams highlighted the need for further investment in assistive technologies, tailored psychosocial support, and stronger linkages between GBV and rehabilitation services. These lessons underscore the importance of embedding disability inclusion more systematically in future GBV programming, including through co-design with OPDs and disability advocates.

Output Title	Child Protection risks are mitigated through prevention programming and specialised services
Output number:		3	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicator(s)	Milestones for this review[4]	Progress	%
3.1: # of men and women attending parenting programmes	4,752	4,773	100%
3.2: # of boys and girls who participate in structured child protection activities	8,494	8,508	100%
3.3: # of children referred to PHCs for screening for developmental delays	300	418	139%
3.4: # of peer-led support groups established for family members/caregivers of children with disabilities	10	10	100%
[4] The milestone and progress figures referenced are cumulative across the programme.

Briefly describe the output’s activities and provide supporting narrative for the score.

In its final year, output 3 delivered a combination of prevention and specialised child protection services, with varied performance across indicators. The interventions targeted caregivers, children, and families of children with disabilities, aiming to strengthen protective environments and promote early identification of risks.

  1. Parenting Programmes: A total of 4,773 caregivers (men and women) participated in structured parenting sessions. These sessions focused on positive discipline, child development, and stress management. Facilitators reported strong engagement and behavioural shifts among participants, including improved parent-child communication and reduced use of punitive practices. These activities were delivered through JRF.
  2. Structured Child Protection Activities for Children: Through DRC and JRF the programme reached 8,508 children through age-appropriate activities designed to build resilience, awareness of rights, and coping strategies. While feedback from children and caregivers was positive, attendance was affected by seasonal migration, school schedules, and competing priorities in urban settings.
  3. Developmental Screening Referrals to PHCs: Through HI, 418 were referred to PHCs for developmental delay screening. The referrals reflect ongoing collaboration between child protection and health actors. These cases were identified through frontline worker observations and parent consultations.
  4. Peer-Led Support Groups for Caregivers of Children with Disabilities: The target of ten new support groups established by HI was reached, providing safe spaces for caregivers to share experiences, access resources, and advocate for inclusion. These groups were facilitated by trained peers and linked to local service providers.
Overall, Output 3 maintained a steady delivery of core child protection services, with notable strengths in caregiver engagement and cross-sectoral collaboration, demonstrating strong caregiver engagement, effective peer-led support models, and promising cross-sectoral collaboration with health actors. The parenting programme showed high completion rates and positive behavioural outcomes, while the establishment of caregiver support groups contributed to sustainability and community ownership. However, limited expansion of specialised services and some experiences of lower-than-expected child participation particularly in urban areas highlight the need for more adaptive outreach strategies, improved scheduling coordination, and strengthened integration with education and health systems to ensure broader and more equitable access for children.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

HI expanded outreach in Ramtha and Mafraq to address PHC access challenges, and JRF adapted parenting sessions to better engage male caregivers. These adjustments helped maintain service quality but did not significantly alter the trajectory of the output.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Output 3 advanced last year’s recommendations on integrating GBV and CP programming and engaging male caregivers. EMC sessions achieved strong participation and impact, with improved attitudes toward child marriage and labour. Parenting sessions also shifted to whole-family formats. However, male participation in peer-led support groups for caregivers of children with disabilities remained low, highlighting the need for tailored outreach. The final year reinforced the value of flexible, community-based delivery and stronger referral systems especially in contexts with documentation and access barriers.

Key Lessons and Recommendations for Future Programming
- Family Dynamics Are Central to Protection Outcomes: Parenting programmes and Engaging Male Caregivers (EMC) sessions revealed that shifts in family relationships and caregiving practices directly influence child protection outcomes. Participants reported long-term improvements in gender relations, emotional well-being, and decision-making within households. Future programme designs should better capture these interrelated dynamics and the influence of family systems on child well-being and help-seeking behaviour.
- Engaging Male Caregivers Works but Needs Scale and Flexibility: EMC sessions under Output 3.1 demonstrated strong behavioural change and high satisfaction among male participants. However, engagement levels varied due to competing responsibilities and limited flexibility in delivery. Future protection programmes should adapt delivery formats such as having evening sessions, mobile outreach, and peer-led models—to foster sustainability, community ownership, and broader participation.
- Disability Inclusion Requires Systemic and Community-Level Investment: Peer-led support groups for caregivers of children with disabilities proved effective in building confidence, knowledge, and advocacy skills. Future programming should institutionalise these models by linking them to Organisations of Persons with Disabilities (OPDs), local service providers, and national disability strategies. Disability-sensitive approaches should be integrated across all child protection and parenting activities to ensure inclusive outcomes.
- Referral Pathways Must Be Strengthened and Made More Equitable: The success of early detection referrals to Primary Health Centres (PHCs) highlighted the importance of strong coordination between protection and health actors. However, documentation barriers especially for non-Jordanian children-remained a challenge. Future programmes should invest in advocacy, administrative support, and inclusive service design to ensure equitable access for all children, regardless of legal status.
- Addressing Health Access Barriers: Access to PHCs remained uneven due to administrative complexities and documentation-related restrictions, particularly affecting Syrian refugees. Discrepancies between Ministry of Interior (MoI) card registration and actual residence often limited eligibility for free services. Continued collaboration with MoH and MoSD, alongside targeted awareness and inclusive protocols, is essential to mitigate these barriers.
- Designing Inclusive and Flexible Services: Future programming should prioritize mobile and flexible service delivery models, ensure financial accessibility, and address nationality-based disparities. This includes adapting session formats, expanding outreach to underserved areas, and embedding inclusive practices across all components.
- Integrated Programming Enhances Impact and Sustainability: Output 3 demonstrated that combining psychosocial support, parenting education, disability services, and child protection activities leads to more holistic and sustained outcomes. Future designs should prioritize cross-sectoral integration, ensuring that interventions reinforce each other and respond to the full spectrum of child and family needs.

Output Title	Capacity-building and strengthening of national and local structures providing protection, rehabilitation and early development services.
Output number:		4	Output Score:	A
Impact weighting		9%	Weighting revised since last AR?	No

Indicator(s)	Milestones for this review[5]	Progress	%
4.1: # of CBO and National Non-Governmental Organisation (NNGO) staff trained on child safeguarding and/or safe identification and referral	538	598	111%
4.2: # staff of governmental entities trained in the capacity building programme	660	700	106%
4.3: # of knowledge products and technical guidelines produced for government entities	3	3	100%
[5] The milestone and progress figures referenced are cumulative across the programme.

Briefly describe the output’s activities and provide supporting narrative for the score.

In its final year, Output 4 focused on strengthening institutional capacity across both civil society and government systems to deliver inclusive protection and early development services. This included extensive training of frontline staff, strategic engagement with government entities, and the development of nationally endorsed technical guidelines.

  1. CBO and NNGO training: A total of 598 staff from community-based organisations and national NGOs were trained in child safeguarding and safe referral practices. These sessions equipped frontline workers with practical tools to identify protection risks and respond appropriately, with several organisations integrating safeguarding protocols into their operations. This output indicator was delivered by DRC and JRF.
  2. Governmental training: In parallel, HI and JRF reached 700 government staff including social workers, health professionals, and education personnel tailored training programmes focused on rehabilitation activities, inclusive service delivery, early childhood development, child protection and GBV safe referral and online sexual exploitation. Post-training feedback highlighted the relevance and applicability of the content to their daily roles.
  3. Products for Governmental entities: To support institutionalisation, HI, developed and handed over three nationally validated technical products listed below across the programme:
- National standards for assistive products
- Early detection protocols for developmental delays
- Inclusive service delivery models for children with disabilities
These resources were co-developed with sectoral experts and validated through multi-stakeholder consultations, ensuring alignment with national priorities and service delivery realities.
The programme strategically invested in capacity building and logistical support to strengthen national and local service delivery systems, particularly rehabilitation centres, Early Intervention (EI) units, and PHCs. Through partnerships with MoSD and MoH, the project enhanced infrastructure, provided essential medical and assistive equipment, and trained government and health staff. These efforts ensured improved access to inclusive, high-quality services for children with developmental delays and persons with disabilities, while laying the foundation for sustainable, system-integrated care models across Jordan. Below is a summary of the key interventions implemented under the capacity building and logistical support activity for rehabilitation centres, EI units, and PHCs:
- Rehabilitation Centres: The programme provided targeted capacity building and logistical support to key rehabilitation centres across Jordan, including Prince Hamzah Hospital, Al-Basheer Hospital, Community Development Centre – Baqaa, and CDC Marka. Support included the donation of specialised equipment, infrastructure upgrades to improve accessibility, and the integration of psychosocial support into rehabilitation services. These efforts enhanced the quality and inclusiveness of care for persons with disabilities and contributed to the institutionalisation of multidisciplinary approaches.
- Early Intervention Units: Four new Early Intervention units were established in Amman, Jerash, and Mafraq, equipped with essential materials and supported by trained CBR volunteers. HI led the development of a standardized Early Intervention Model, which was formally handed over to MoSD for national replication. This model ensures consistent, high-quality service delivery for children with developmental delays and disabilities, and reflects a strategic shift toward sustainable, system-embedded care.
- Primary Healthcare Centres (PHCs): The programme strengthened 32 PHCs by training over 250 health professionals on early detection, disability inclusion, and child development. Twelve PHCs received medical equipment to enhance early childhood services, while national clinical pathways for DDH and CP were piloted in collaboration with MoH. These interventions improved access to inclusive health services and laid the groundwork for scalable, integrated early detection and rehabilitation systems.
Additionally, partnerships with national CBOs in Ma’an, Irbid, and Mafraq enabled the delivery of services in remote and underserved areas, particularly benefiting women and persons with disabilities. Despite budget constraints, the reactivation of these partnerships in the final year reaffirmed their critical role in community-led protection responses.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Following a budget increase, capacity-building activities were scaled up. Technical guidelines were finalised and disseminated, and coordination with MoSD and MoH was strengthened.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Last year’s recommendation to increase the weighting of Output 4 was not implemented, given the commencement of new emergency facility activities under output 1 increases the significance of output 1 and a corresponding decrease in its weighting was not seen as appropriate any longer. That said there was a greater focus on output 4 during the last six months of the DRC-led consortium activities, reflecting an enhanced emphasis on these activities in practice. Final evaluations confirmed improved capacity among trained staff and strong institutional uptake of tools and models. The programme’s investment in government partnerships and technical standardisation has laid a solid foundation for future programming.

Key learnings and recommendations for future programming:

The JPP programme demonstrated that system strengthening is both achievable and impactful when inclusive models and technical tools are co-developed with national institutions and embedded within them. The successful institutionalisation of the Early Intervention Model, National Early Detection Guidelines, and Assistive Products List endorsed by MoSD and MoH reflects sustainable systems-building. These efforts were reinforced by capacity-building for government staff, cascading training models, and digital innovations that improved service coordination and access. Further programming should seek to build on these successful systems strengthening work.

A compelling example of this systems approach was the integration of psychosocial support into rehabilitation services, piloted at Al-Bashir Hospital. This initiative, endorsed by the Ministry of Health, trained professionals in Problem Management Plus (PM+)[6] and disability inclusion, and established Jordan’s first Psychosocial Support (PSS) clinic at the secondary health level. It showcased how holistic, person-centred care can be embedded within public health systems.
[6] Problem Management Plus – a low-intensity psychological intervention developed by the World Health Organization (WHO), used to integrate psychosocial support into rehabilitation services.

D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case.

The programme made important progress in embedding Value for Money (VfM) principles, particularly in its final year. The consortium faced considerable challenges in developing a unified VfM framework due to evolving financial reporting systems and the complexity of multi-partner implementation. A structured methodology was only introduced in Year 3, limiting the ability to track VfM performance consistently across the programme’s lifecycle. Nevertheless, the final year’s framework provided a clearer picture of where the programme delivered well and where improvements are needed, against the 5Es VfM framework.

Economy: In Year 4 the programme introduced a structured VfM methodology that enabled clearer tracking of input costs and procurement practices. Despite earlier challenges, partners demonstrated sound economic management in sourcing and allocating resources.
Direct implementation costs accounted for 73% of total expenditure, slightly above the 70% benchmark. This reflects a deliberate effort to prioritise programme delivery over overheads and indicates prudent financial planning in resource allocation. At the partner level:

- JRF allocated 78% to direct costs (+11.4%), showing a strong emphasis on delivery-focused budgeting.
- HI reached 73% (+4.3%), maintaining alignment with VfM principles.
- DRC met the benchmark at 70%, reflecting consistent cost discipline.
These figures suggest that the programme maintained a cost-conscious approach to input sourcing and budget allocation, contributing to overall economic efficiency.

Importantly, while the programme maintained a commendable 73:27 programme-to-support cost ratio, this reflects a decline from last year’s 86:14 ratio, which was considered above benchmark and indicative of strong cost efficiency. This shift underscores the importance of early strategic cost planning and consistent financial reporting. It is also critical to note that the 27% support cost encompasses a wide array of enabling functions beyond administration, including security, MEAL, legal services, and staff support each essential to sustaining quality delivery.

Procurement savings were more notable reflecting good procurement practices:
- HI achieved a 20% reduction in procurement costs.
- JRF achieved an 8.5% reduction.
Efficiency: Efficiency was assessed through cost-per-beneficiary analysis across core activities. The final year of the programme showed several areas of cost-efficiency, with most activities delivered below market benchmarks. However, efficiency gains were not uniform across partners or activities, and in some cases, lower costs were offset by limited reach or equity gaps. The programme continued to track Non-Project Attributable Costs (NPAC) as a measure of efficiency, consistent with the business case and previous annual reviews. NPAC refers to indirect costs not directly linked to specific outputs but necessary for programme delivery. In the final year:

- DRC reported an NPAC rate of 7%.
- JRF reported 10%.
- HI reported 13%.
These rates fall within the historical range of 7–14% observed in previous protection programmes and are well below the benchmark of 30% used in earlier FCDO programmes. The overall programme ratio of 87:13 (programme to NPAC) reflects strong cost efficiency and effective cost attribution across the consortium.
Table: Key Efficiency Indicators
Activity	Partner	Cost/Beneficiary (GBP)	Benchmark (GBP)	% Change	Comment
Case Management	JRF	20.55	33.39	−38%	Efficient, but high dropout rate noted.
Individual PSS Counselling	DRC	42.95	54.65	−21%	Cost-effective with moderate reach.
Family & Child Helpline	JRF	5.18	6.26	−17%	High reach, but equity gaps (low disability).
Rehabilitation Services	HI	174.21	202.21	−14%	Efficient and impactful (90% improved).
EMAP Training	DRC	5.07	9.83	−48%	Strong efficiency and good reach.
Expressive Arts for Women	JRF	18.81	55.66	−66%	Highly cost-efficient, but limited inclusion.

The programme demonstrated that several activities could be delivered at lower-than-market costs, particularly those with standardised formats and lower operational complexity.

The absence of a VfM framework in earlier years means these gains cannot be assessed cumulatively or linked to strategic decisions. Efficiency must be interpreted alongside effectiveness and equity to ensure that cost savings do not come at the expense of inclusive and impactful programming.

Effectiveness: According to the business case, programme effectiveness was to be measured through agreed outcome indicators with selected partners, alongside efforts to strengthen relationships with government institutions to support more sustainable programming and reduce long-term reliance on humanitarian services. The programme made meaningful progress in this area, particularly through collaboration with the MoSD and MoH, with a focus on staff capacity building and technical support. The programme demonstrated strong effectiveness through its outcome indicators, with most partners meeting or exceeding expected results. This reflects the quality-of-service delivery and the relevance of interventions to community needs, even in a constrained operating environment.

Importantly, the programme contributed to positive attitudinal change among beneficiaries. Activities such as GBV prevention for adolescents, parenting sessions, and safeguarding awareness led to measurable improvements in gender-equitable attitudes, coping strategies, and family dynamics—key indicators of sustained effectiveness and behavioural impact.
These interventions also demonstrated strong delivery performance, with several activities achieving meaningful outcomes at lower-than-expected costs. For example:

- GBV prevention (DRC) achieved a 24–25% cost reduction.
- Parenting and expressive arts (JRF) recorded 13–66% cost reductions.
- Early Detection and Rehabilitation (HI) delivered services with 14–29% cost savings.
While these figures suggest a high degree of cost-effectiveness, the absence of consistent VfM tracking across all years limits the ability to fully assess whether these efficiencies were sustained throughout the programme’s duration. Nonetheless, the combination of attitudinal change and outcome achievement reflects a strong effectiveness profile across key components.

Equity: In the context of the Jordan Protection Programme (JPP), equity refers to how effectively the programme reached those most at risk, particularly refugees and persons with disabilities—in line with its protection mandate. Equity is not just about numbers; it reflects whether services are accessible, inclusive, and responsive to the needs of marginalised groups. Despite the consortium’s commitment to inclusive programming, equity performance varied across partners in the VfM assessment.

In terms of refugee inclusion, the programme aimed to reach at least 70% refugees across its activities. However, performance varied significantly by partner:

- DRC exceeded the benchmark, reaching 76% refugees, a positive change of +8.6%.
- HI was close to target at 68%, a minor shortfall of -2.9%.
- JRF, however, reached only 34% refugees, falling -51.4% below the benchmark.
Overall, the consortium reached 52% refugees, reflecting a -28% deviation from the target. While DRC and HI demonstrated effective outreach to refugee communities, JRF’s low refugee reach particularly in activities delivered through schools and community centres significantly impacted the consortium’s overall equity performance. This suggests that refugee targeting was not consistently embedded across all delivery models.

In terms of disability inclusion, the programme made substantial efforts to ensure persons with disabilities were reached and supported across all components. HI led the disability inclusion work, identifying and referring over 4,000 individuals to rehabilitation services, supporting 890 children through early intervention, and engaging 129 caregivers in peer-led support groups. Disability inclusion was also integrated into GBV and child protection programming, with persons with disabilities participating in EMAP, parenting sessions, and adolescent-focused activities. Across the consortium, over 4,400 persons with disabilities were reached, representing a meaningful step toward inclusive service delivery. However, similar to refugee inclusion, the level of disability inclusion varied by partner and activity type, highlighting the need for more consistent and intentional inclusion strategies across all delivery models.

Conclusion
The JPP delivered solid VfM in its final year, particularly in procurement and activity-level efficiency. However, the delayed framework, inconsistent equity performance in ability to reach refugees, and limited cumulative tracking mean that VfM was not fully measurable throughout the programme.

Recommendations
- Integrate VfM frameworks from inception, with partner-specific benchmarks and real-time tracking.
- Strengthen equity mechanisms, especially for refugee and disability inclusion, with clearer accountability.
E: RISK

Overview of risk management
Over the reporting period, the programme’s overall risk exposure was moderate, reflecting a dynamic operating environment and a significant programme transition. The closure of the protection component in March 2025 and the commencement of WASH and UNHCR return components in July/August 2025 led to a reduction in residual risk across several categories particularly operational and safeguarding risks associated with direct protection delivery.
However, the WASH start-up phase introduced new delivery and operational risks, including procurement delays, coordination challenges with local authorities, and uncertainties around the capacity of newly onboarded partners. These risks were identified early and are being managed through proportionate mitigation measures, including strengthened oversight, adaptive planning, and technical support. The following section provides a summary of key programme risks:
#### Strategy & Context
Status: Major
Description: The operating environment in Jordan continues to be shaped by regional instability, high refugee needs, and economic constraints. This creates ongoing political and contextual risks, particularly around coordination with national authorities and responsiveness to shifting government priorities. While these risks remain high, they are broadly in line with corporate appetite given the strategic importance of the programme. The programme’s ability to flexibly transition from protection to WASH (via UNICEF) and return support (via UNHCR) reflects its resilience and responsiveness to evolving needs.
Residual Risk: Within appetite
#### Policy & Programme Delivery
Status: Moderate
Description: The programme’s policy and delivery risk was assessed as moderate, with the risk profile evolving over the reporting period. In the final year of the protection programme delivered by the consortium and concluded in March 2025, early delays in procurement and mobilisation slightly elevated delivery risk above appetite. These challenges were mitigated through close donor–partner coordination, targeted technical support, and revised implementation timelines. Following the closure of the protection component, risks related to partner capacity, outreach to vulnerable populations, and safeguarding in frontline service delivery significantly diminished.
In the latter part of the year, new operational risks emerged in connection with the expansion of WASH services. The summary below outlines the key risks and corresponding mitigation measures.
- Environmental risks associated with WASH infrastructure such as groundwater depletion, waste management, and land degradation were reassessed in line with FCDO’s Operational Risk Framework. Mitigation measures, including environmental impact assessments and adherence to Jordanian and FCDO environmental safeguarding standards, are embedded in programme design. The risk remains within appetite and supports the UK’s Paris Agreement commitments.
- The programme continues to uphold FCDO’s safeguarding and inclusion standards, as well as the UK’s Gender Equality and Public Sector Equalities Duty. With the expansion of WASH services, new risks of exclusion particularly for women, children, and persons with disabilities were identified. These were mitigated through inclusive infrastructure design, community engagement, and strengthened monitoring. Services remain responsive to the needs of vulnerable groups, and residual risk is moderate but managed.
- While return programming remains a strategic priority, there is a risk that FCDO may face reputational challenges if support for refugee returns is perceived as premature, politically sensitive, or misaligned with international protection standards. These risks are heightened by the fluid political and humanitarian context in Syria and the region.
The programme team will be monitoring refugee intentions surveys outcomes and feedback through UNHCR’s protection monitoring and M&E systems. Ensuring Jordan’s return assistance alignment with UNHCR’s regional voluntary return framework and protection principles.
Residual Risk: Within appetite
#### Safeguarding
Status: Moderate
Description: Safeguarding risks were actively monitored throughout the protection component until its closure. The residual safeguarding risk is considered low. With WASH, safeguarding risks resurface in different ways, linked to labour standards, construction site safety, and engagement with communities in vulnerable settings. Mitigation includes integrating safeguarding requirements into all new contracts and providing refresher training for implementing partners.
Residual Risk: Within appetite
#### Financial & Fiduciary
Status: Moderate
Description: Fiduciary risk has remained within appetite, supported by routine financial monitoring and the timely submission of partner reports. Due diligence assessments (DDA) continue to provide proportionate assurance, with no major new concerns emerging during the year. The winding down of the protection component reduced exposure to fiduciary risk in that portfolio, while the onboarding of the new WASH partner was supported by strengthened due diligence processes. Some recommendations from DDA assessments remain under implementation, but progress is on track, and no refresh is required at this stage.
Residual Risk: Within appetite
#### Reputational
Status: Moderate
Description: Operational risks increased as the programme approached its end, particularly around ensuring continuity of service delivery and maintaining clear communication with stakeholders about the programme’s closure and transition. Transparent engagement with partners, donors, and beneficiaries helped mitigate reputational risks.
Residual Risk: Within appetite.
#### People
Status: Low
Description: Staff turnover during the transition period was managed through joint onboarding, coaching, and capacity-building efforts. No significant HR-related risks were reported during the WASH scale-up phase.
Residual Risk: Within appetite.
On balance, residual risk levels across most categories remain broadly in line with programme and corporate appetite, and no changes are proposed to the overall risk appetite at this stage. The addition of WASH services introduced temporary spikes in delivery and operational risk, particularly around infrastructure coordination, safeguarding, and environmental compliance. Assurances from due diligence remain proportionate, and mitigation measures are actively progressing.
Looking ahead, the programme will prioritise consolidating WASH delivery and voluntary returns support delivery, strengthen oversight of safeguarding and environmental risks, and ensure that equality, inclusion, and accessibility remain central to all programme decisions. Continued attention to delivery and operational risks will be essential throughout the coming year to maintain programme integrity and responsiveness.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Financial Management
The protection consortium, led by DRC, demonstrated strong financial adaptability in response to budget fluctuations. Following a reduction of the FY2023/24 budget from £4.6m to £2.5m, the consortium revised its scope, targets, and financial plans, leading to a 33% reduction in overall programme targets while maintaining alignment with core objectives. By April 2024, the FY2024/25 budget was confirmed at £5.5m, allowing a modest increase in targets. At programme closure, the total value reached £11.07m, representing 88% of the original AGA allocation (£12.54m).

Reallocations were used strategically to mitigate funding shortfalls and sustain critical services. In December 2024, £50,000 was reallocated from DRC to JRF to expand expressive arts interventions. In February 2025, £30,000 was redirected to HI to cover service gaps caused by the suspension of US funding, enabling continued rehabilitation for 368 patients, prosthetics provision for nine individuals, and visual aids for eleven children. A further £50,000 was reallocated in March 2025 to HI, ensuring continuity of home-based interventions, comprehensive rehabilitation services for 150 persons with disabilities, and procurement of essential assistive technology. These reallocations demonstrated responsive financial management and prioritisation of beneficiaries’ urgent needs.

Programme Extension and New Components
In February 2025, FCDO approved a one-year, no-cost extension to the JPP business case (to March 2026), retaining the £15m budget envelope, including the £4m risk facility. This extension aimed to preserve humanitarian readiness and allow flexible deployment of contingency funding in light of regional instability.

As part of this extension:

- The DRC Accountable Grant Agreement (AGA) was extended to September 2025, aligning with the Ministry of Planning and International Cooperation (MoPIC) approval, though protection activities concluded in March 2025. A final project meeting in August 2025 captured achievements and lessons learned, and a JORISS modification was approved by MOPIC.
- In July 2025, £1.5m from the risk facility was allocated to UNICEF to sustain life-saving WASH services in Syrian refugee camps (July 2025–March 2026). Risks were integrated into the programme risk register, AMP was updated, and new logframe indicators were introduced.
- In August 2025, a further £1.5m was allocated via MoU with UNHCR to support refugee returns from Jordan to Syria. A new AMP component was established, with risk register and logframe updates planned accordingly.
G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Throughout the review period, programme performance was monitored through quarterly partner reporting, indicator tracking (disaggregated by sex, age, disability, nationality, and location), and regular review meetings. FCDO and implementing partners also conducted joint field visits, ensuring direct engagement with beneficiaries and the inclusion of their feedback in programme decisions.

For the protection consortium, monitoring data was complemented by specialist frameworks. DRC and JRF applied the GBV Prevention Evaluation Framework, including community-level results journals and proxy indicators, to track shifts in knowledge, attitudes, and practices. HI maintained detailed monitoring of rehabilitation and assistive technology services, including functionality outcomes. These systems enabled timely course corrections, for example, reallocations to HI in early 2025 ensured uninterrupted rehabilitation services after external funding cuts. With the launch of the WASH component in July 2025, UNICEF established monitoring systems integrated into existing camp-based WASH coordination structures. Data on service delivery and access are reported monthly, supported by FCDO site visits and review meetings.

UNHCR Jordan will apply its established protection monitoring and identity management systems to ensure that refugee returns are voluntary, informed, and dignified. Through individualized counselling, legal documentation support, and transportation assistance, UNHCR will track refugee needs, barriers to return, and reintegration outcomes. Monitoring will be coordinated with UNHCR Syria and adapted to the fluid context, ensuring accountability and responsiveness to refugee feedback throughout implementation.

Evidence
The independent final evaluation of the protection consortium, completed in March 2025, provided robust evidence on programme performance. It confirmed that an integrated model, combining prevention, response, and capacity building, achieved meaningful protection outcomes and strengthened local capacity. It also reinforced earlier findings from the February 2024 FCDO audit and previous Annual Reviews, particularly regarding consortium governance, coordination, and sustainability challenges.
Evidence indicated that while programme activities reached intended beneficiaries, inequities persisted, especially for Syrian refugees and non-Jordanian beneficiaries who faced greater barriers to access.

The WASH component, though newly launched, is expected to generate operational evidence on sustainability of camp-based water systems and on the effectiveness of joint monitoring with UN partners.

Learning
Learning has been an integral part of the closure of the DRC led consortium protection activities and transition to programme closure. A final consortium meeting in August 2025 provided a platform to consolidate lessons and share best practice across partners. Key lessons included:

- The need for stronger consortium leadership and governance structures to reduce coordination inefficiencies.
- The value of flexible funding and budget reallocations in safeguarding critical services during funding shocks.
There is an opportunity to apply these lessons to WASH, and refugee return programming as well as future humanitarian programming. Embedding formalised coordination mechanisms with external actors, strengthening equity-focused strategies, and sustaining robust monitoring systems will be key learning aims in the year ahead.

Date of last narrative financial report	DRC: 14 July 2025	Date of last audited annual statement	DRC: 25 June 2025