## Template
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
PROJECT TITLE | Jordan Protection Programme (JPP) Support to Vulnerable Refugees and Jordanians
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
The protection environment for refugees and Jordanians at risk of violence, coercion and deliberate deprivation is strengthened through reduced protection threats and increased capacities to respond | % of beneficiaries who report an increase in attitudes and/or behaviors that support gender equity and child safeguarding | Planned | NA | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | NA
|  | Achieved |  | NA | NA | NA | NA | 0% | 66% | 65% | 64% | 65% | 64% | 77% | 79% | NA
Source
KAP Survey baseline and endline, EMAP, Adolescent Gender and GBV Programme, Engaging Male Caregivers, and Parenting programme pre- and posttests
| Impact Indicator 2 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| % of beneficiaries supported with direct protection services reporting improvement in their well-being | Planned | NA | 0% | 0% | 0% | 0% | 0% | 50% | 50% | 50% | 50% | 50% | 50% | 50% | NA
|  | Achieved |  | NA | NA | NA | NA | 0% | 71% | 72% | 72% | 72% | 67% | 72% | 69% | NA
Source
Post Intervention Monitoring (PIM), PSS counsellor assessment form, well-being assessment, case management and PSS exit surveys
OUTCOME | Outcome Indicator 1 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026 | Assumptions
Strengthened capacity of refugees and vulnerable Jordanians, communities, and local and national systems to prevent, respond to, and recover from immediate and longer-term protection risks. | % of CfP recipients who consider the assistance was sufficient to mitigate immediate protection concerns | Planned | NA | 0% | 0% | 0% | 0% | 0% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | NA | 1) COVID situation remains stable and beneficiaries are able to access services. 2) Targeted participants have the desire to participate in the activities, and are available to give their time. 3) Service providers are able to provide the referred services in a timely manner and with high quality, either from their initial expertise or following capacity-building from the consortium partners. 4) The needs for protection and rehabilitation remain at the same level as those observed during the project design phase.
|  | Achieved |  | NA | NA | NA | NA | 0% | 97% | 97% | 97% | 97% | 97% | 97% | 97% | NA
Source
Post distribution monitoring, CfP closure form
| Outcome Indicator 2 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| % beneficiaries who report increased positive parenting skills and coping methods | Planned | NA | 0% | 0% | 0% | 0% | 0% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | NA
|  | Achieved |  | NA | NA | NA | NA | 0% | 85% | 64% | 54% | 55% | 58% | 66% | 63% | NA
Source
DRC and JRF caregiver programme pre- and posttests
| Outcome Indicator 3 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| % of beneficiaries, among those who received rehabilitation services showing improvement in their functional independence | Planned | NA | 0% | 0% | 0% | 0% | 0% | 80% | 80% | 80% | 80% | 80% | 80% | 80% | NA
|  | Achieved |  | NA | NA | NA | NA | 0% | 89% | 88% | 88% | 88% | 88% | 90% | 90% | NA
Source
HI Beneficiary database
| Outcome Indicator 4 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| % of caregivers who report improved access to quality needed Early Detection and Early Intervention services | Planned | NA | 0% | 0% | 0% | 0% | 0% | 60% | 60% | 60% | 60% | 60% | 60% | 60% | NA
|  | Achieved |  | NA | NA | NA | NA | 0% | 96% | 96% | 94% | 94% | 94% | 94% | 94% | NA
Source
Post Intervention Monitoring (PIM)
| Outcome Indicator 5 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| % training participants (including government stakeholders) who demonstrate increased ability to provide protection related support | Planned | NA | 0% | 0% | 0% | 0% | 0% | 70% | 70% | 70% | 70% | 70% | 70% | 70% | NA
|  | Achieved |  | NA | NA | NA | NA | 0% | 100% | 100% | 94% | 85% | 81% | 81% | 81% | NA
Source
Training attendance sheets, pre- and posttests
| Outcome Indicator 6 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| Percentage of people with access to safe, equitable, and reliable water supply and sanitation in Azraq and Za’atari refugee Camps. | Planned | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 100%
|  | Achieved |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Source
UNICEF reporting
INPUTS (£) | FCDO (£) |  | Govt (£) | [10 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026 | Assumptions
Women, men, girls and boys at risk of GBV, CP, and other protection concerns are provided with life-saving protection response and rehabilitation services | # of vulnerable beneficiary households (HHs) assisted through case management | Planned | 0 | 0 | 0 | 289 | 597 | 947 | 1037 | 1127 | 1238 | 1584 | 1900 | 2411 | 2875 | NA | 1) COVID situation remains stable and beneficiaries are able to access services. 2) Service providers are able to provide the referred services in a timely manner. 3) The referred beneficiaries meet the criteria to benefit from referred services. 4) Targeted participants have the desire to participate in the activities, and are available to give their time. 5) Partner CBOs have acquired the experience and capacity to implement activities and a referral system related to social protection and have the willingness and capacity to expand its services to a larger number of beneficiaries. 6) There is an urgent need for protection, and a large number of abuse victims are not aware how to access help and support. 7) Cases in need of psychosocial support (PSS) will be referred through pathways to access appropriate service providers (internally and externally). 8) Refugees continue to have access to information, counselling, and documentation services necessary for informed decision‑making. 9) Essential WASH inputs including core infrastructure, operational consumables, and logistical support will remain reliably available, enabling the continuity of service delivery as planned.
|  | Achieved |  | 0 | 101 | 328 | 688 | 1131 | 1268 | 1406 | 1447 | 1584 | 1856 | 2235 | 2558 | NA
Source
DRC beneficiary database, case management case closure form, client satisfaction survey
| Output Indicator 1.2 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| # of women, men, boys and girls accessing sustained and structured psychosocial services | Planned | 0 | 0 | 0 | 117 | 146 | 171 | 196 | 221 | 291 | 393 | 501 | 549 | 643 | NA
|  | Achieved |  | 0 | 7 | 112 | 211 | 262 | 295 | 340 | 358 | 383 | 422 | 543 | 680 | NA
Source
DRC and JRF beneficiary databases, PSS exit survey
| Output Indicator 1.3 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| # of calls received and served through JRF's helpline | Planned | 0 | 0 | 0 | 1078 | 1966 | 2406 | 2846 | 3286 | 3726 | 4954 | 6181 | 7408 | 9026 | NA
|  | Achieved |  | 0 | 0 | 1078 | 1966 | 2308 | 2988 | 3606 | 4248 | 5222 | 7016 | 8531 | 9493 | NA
Source
Helpline tracking system and reports
| Output Indicator 1.4 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| # persons with disabilities identified in need of assistance who are receiving specific support | Planned | 0 | 0 | 0 | 0 | 1304 | 1500 | 1700 | 2000 | 2150 | 2350 | 2500 | 2500 | 3150 | NA
|  | Achieved |  | 0 | 0 | 412 | 991 | 1149 | 1243 | 1396 | 1540 | 1664 | 2060 | 2688 | 3150 | NA
Source
Signed invoices from beneficiaries and partners, transportation sheets and beneficiaries databases.
| Output Indicator 1.5 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| # of children screened positive for impairments enrolled in Early Intervention (EI) programmes | Planned | 0 | 0 | 0 | 0 | 0 | 264 | 350 | 500 | 550 | 650 | 700 | 700 | 835 | NA
|  | Achieved |  | 0 | 0 | 72 | 264 | 365 | 420 | 445 | 523 | 554 | 625 | 796 | 890 | NA
Source
HI beneficiary database
| Output Indicator 1.6 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| # of beneficiaries of comprehensive rehabilitation services that are included in vocational trainings and/or employment opportunities | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | NA
|  | Achieved |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 10 | NA
Source
VTC records, apprenticeship contracts, internship contracts, work contracts
| Output Indicator 1.7 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| # of refugees which UNICEF Jordan delivers continuous water and sanitation services in Za’atari and Azraq camps for to ensure safe, reliable, and dignified WASH access. | Planned | 115,000 individuals | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 115,000 individuals
|  | Achieved |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Source
UNICEF field monitoring reports. Contractors and other implementing partner reports. Community feedback, hotline, and partner’s monthly reports.
IMPACT WEIGHTING (%) | Output Indicator 1.8 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
52% | # of refugees which UNHCR Jordan provides outreach and individualized counselling, legal support for vital documentation, transportation assistance, and pilot cash-based support to enable refugees who have voluntarily expressed their intention to return to Syria to do so in a safe, informed, and dignified manner. | Planned | 150,000 individuals | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | 150,000 individuals
|  | Achieved |  | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA
Source
UNHCR reporting, NRC’s Protection Context Updates, Jordan Operational Durable Solutions Working Group Updates
INPUTS (£) | FCDO (£) |  | Govt (£) | [10 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026 | Assumptions
GBV risks are mitigated through prevention programming | # of women and men attending Engaging Men through accountable practice programme | Planned | 0 | 0 | 0 | 180 | 180 | 285 | 285 | 300 | 310 | 640 | 925 | 1263 | 1383 | NA | 1) COVID situation remains stable and beneficiaries are able to access services in person. 2) In-person group sessions of up to 20 are allowed by the government. 3) Communities accept the subject matter of prevention programs. 4) Targeted participants have the desire to participate in the activities, and are available to give their time. 5) Partner CBOs have acquired the experience and capacity to implement activities and a referral system related to social protection and have the willingness and capacity to expand its services to a larger number of beneficiaries. 6) Vulnerable women and men are in need of specialized training to empower them against protection threats. 7) Social workers are assumed to be able and willing to conduct the prevention sessions.
|  | Achieved |  | 0 | 0 | 93 | 423 | 595 | 595 | 611 | 626 | 641 | 803 | 1184 | 1421 | NA
Source
EMAP session attendance sheets, DRC beneficiary database, EMAP pre- and posttests
| Output Indicator 2.2 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| # of women who received Expressive Arts workshops | Planned | 0 | 0 | 0 | 153 | 306 | 353 | 400 | 447 | 494 | 614 | 850 | 938 | 1193 | NA
|  | Achieved |  | 0 | 0 | 153 | 306 | 350 | 413 | 466 | 496 | 624 | 854 | 941 | 1193 | NA
Source
JRF’s IM system, attendance sheets, facilitator’s observational journal
| Output Indicator 2.3 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| # community-based mechanisms/groups working on GBV prevention and response | Planned | 0 | 0 | 0 | 5 | 5 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | NA
|  | Achieved |  | 0 | 0 | 5 | 5 | 2 | 2 | 2 | 2 | 5 | 5 | 5 | 5 | NA
Source
JRF’s IM system, Committee’s members list & schedule of activities
IMPACT WEIGHTING (%) | Output Indicator 2.4 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
19% | # of boys and girls attending GBV and gender programming for adolescents programs | Planned | 0 | 0 | 0 | 440 | 605 | 770 | 935 | 1100 | 1450 | 1745 | 2225 | 2655 | 2975 | NA
|  | Achieved |  | 0 | 0 | 422 | 1054 | 1275 | 1596 | 1711 | 1727 | 1745 | 2175 | 2556 | 2964 | NA
Source
GBV and Gender Programming session attendance sheets, DRC IM system (Gamma), pre- and posttests
INPUTS (£) | FCDO (£) |  | Govt (£) | [10 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026 | Assumptions
Child Protection risks are mitigated through prevention programming and specialised services | # of men and women attending parenting programs | Planned | 0 | 0 | 0 | 215 | 978 | 1179 | 1574 | 1946 | 2228 | 2573 | 3768 | 4452 | 4752 | NA | 1) COVID situation remains stable and beneficiaries are able to access services in person. 2) In-person group sessions of up to 20 are allowed by the government. 3) Communities accept the subject matter of prevention programs. 4) Targeted participants have the desire to participate in the activities, and are available to give their time. 5) PHC accept and receive referrals of children. 6) PHC close the referral loop. 7) Caregivers of children are responsive and collaborative to support their children with disabilities. 5) Partner CBOs have acquired the experience and capacity to implement activities and a referral system related to social protection and have the willingness and capacity to expand its services to a larger number of beneficiaries. 6) Vulnerable women and men are in need of specialized training to empower them against protection threats. 7) Social workers are assumed to be able and willing to conduct the prevention sessions. 8) There are limited safe spaces available for children, adolescents, and youth.
|  | Achieved |  | 0 | 0 | 205 | 978 | 1178 | 1546 | 2022 | 2230 | 2585 | 3663 | 4482 | 4773 | NA
Source
Caregiver group session attendance sheets, DRC beneficiary database, caregiver programme pre/posttests
| Output Indicator 3.2 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| # of boys and girls who participate in structured child protection activities | Planned | 0 | 0 | 0 | 789 | 1397 | 2170 | 3256 | 4185 | 5116 | 6065 | 7180 | 8221 | 8494 | NA
|  | Achieved |  | 0 | 0 | 789 | 1397 | 2158 | 3247 | 4233 | 5159 | 6152 | 7408 | 8290 | 8508 | NA
Source
JRF’s IM system, attendance sheets, facilitator’s observational journal
| Output Indicator 3.3 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| # of children referred to PHCs for screening for developmental delays | Planned | 0 | 0 | 0 | 0 | 0 | 19 | 100 | 500 | 600 | 155 | 250 | 300 | 300 | NA
|  | Achieved |  | 0 | 0 | 0 | 19 | 26 | 77 | 124 | 149 | 162 | 185 | 410 | 418 | NA
Source
HI beneficiary database
IMPACT WEIGHTING (%) | Output Indicator 3.4 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
20% | # of peer-led support groups established for family members/caregivers of children with disabilities | Planned | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 4 | 6 | 8 | 10 | 10 | 10 | NA
|  | Achieved |  | 0 | 0 | 0 | 1 | 1 | 1 | 3 | 4 | 4 | 5 | 7 | 10 | NA
Source
HI beneficiary database, attendance sheets
INPUTS (£) | FCDO (£) |  | Govt (£) | [10 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026 | Assumptions
Capacity-building and strengthening of national and local structures providing protection, rehabilitation and early development services | # of CBO and NNGO staff trained on child safeguarding and/or safe idenitification and referral | Planned | 0 | 0 | 12 | 12 | 13 | 14 | 15 | 16 | 17 | 58 | 318 | 538 | 538 | NA | 1) Training curriculum meets participant needs and standards. 2) Attendance and retention rates at trainings are high. 3) government stakeholders are collaborative and engaged continiuously. 4) government stakeholders agree to assign staff to attend training sessions. 5) MoH agree to develop a dissemination startegy for the Endorsed clinical pathways. 6) Training effectively targets those most in need of capacity building (not those who are already experts). 7) COVID situation remains stables and in-person trainings of up to 20 participants are allowed
|  | Achieved |  | 0 | 0 | 12 | 37 | 52 | 56 | 56 | 58 | 58 | 272 | 598 | 598 | NA
Source
Trainings attendance sheets, pre- and posttests
| Output Indicator 4.2 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
| # staff of governmental entities trained in the capacity building program | Planned | 0 | 0 | 0 | 80 | 129 | 130 | 163 | 180 | 195 | 343 | 478 | 660 | 660 | NA
|  | Achieved |  | 0 | 0 | 44 | 124 | 124 | 162 | 174 | 243 | 291 | 446 | 575 | 700 | NA
Source
Trainings attendance sheets, pre- and posttests
IMPACT WEIGHTING (%) | Output Indicator 4.3 |  | Baseline | Milestone 6 months - June 2022 | Milestone 9 months - Sept 2022 | Milestone 12 months - Dec 2022 | Milestone 15 months - Mar 2023 | Milestone 18 months - Jun 2023 | Milestone 21 months - Sept 2023 | Milestone 24 months - Dec 2023 | Milestone 27 months - Mar 2024 | Milestone 30 months - Jun 2024 | Milestone 33 months - Sept 2024 | Milestone 36 months - Dec 2024 | Final target - March 2025 | Final target - March 2026
9% | # of knowledge products and technical guidelines produced for government entities | Planned | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 1 | 1 | 3 | 3 | NA
|  | Achieved |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 2 | 2 | 3 | NA
Source
Attendance sheets; invoices for refurbishment
INPUTS (£) | FCDO (£) |  | Govt (£) | [10 empty] | Other (£) | Total (£) | FCDO SHARE (%)
INPUTS (HR) | FCDO (FTEs)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
1 | Outcome | Outcome indicator #6 is added. | Programme team | 2025-07-01
2 | Output | Output 1 - indicator 1.7 is added | Programme team | 2025-07-01
3 | Output | Output 1 - indicator 1.8 is added | Programme team | 2025-09-01
4
5
6
7
8
9
10

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.