## Annual Review Template

Title: Empowerment and Development for Girls Education (EDGE)
Programme Value £ (full life): £12,000,0000		Review date: Sep 2025
Programme Code: 301240	AMP start date: Sep 2021	AMP end date: Apr 2026

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	A	A	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/90000395.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007280.xlsx

## A. SUMMARY AND OVERVIEW

Description of programme

The Empowerment and Development for Girls Education Programme (EDGE) is a 5-year (2021-2026) programme, aimed at improving access to quality secondary education to underserved populations. It works through an innovative model of cascading best practice from NGO-delivered services to government schools, paired with a ‘development diplomacy’ approach to support policy reform.

EDGE is integral to the BHC Lusaka country plan to facilitate the Government of the Republic of Zambia (GRZ) to fund and deliver effective social sector spending to increase human capital outcomes for poor, vulnerable, out-of-school girls, and those with disabilities. EDGE complements GRZ’s introduction of fee-free education in 2022 (“Education for All”, EFA) by (i) increasing capacity and quality in the secondary sector, and (ii) improving the capacity of the Ministry of Education (MoE) to monitor the quality of education services. This is key to mitigate risks associated with the strain on the sector due to increased enrolment following the introduction of the EFA policy.

The period under review (September 2024 to August 2025) is the fourth year of the EDGE programme’s implementation. EDGE has two components:

Component	Focus	Delivery Partner	Value
Support the implementation of Promoting Equality in African Schools (PEAS)	Scale network of rural secondary schools to increase access to the most marginalised students (at least 50% girls) and to reach school-level sustainability. / Strengthen the equity and quality of education in the PEAS network, develop school improvement tools and generate evidence on what works to improve inclusion, teaching quality and outcomes for girls to share with the Government.	PEAS (Promoting Equality in African Schools)	£10.1m
Development Diplomacy in the secondary education sector	Policy development and implementation with the MoE, the Teaching Service Commission (TSC) and Head Teachers Association of Zambia (HAZ).	British Council	£1.8m

During this reporting period EDGE was extended by eight months from the original end date (August 2025 to April 2026). PEAS received a costed extension (increase of £950,000, and extension of eight months, to April 2026). The British Council received a no-cost extension (of two months, to October 2025).

Summary supporting narrative for the overall score in this review

In this year EDGE has met the majority of its output level milestones. Of the five outputs, four have scored A and one has scored A+. At outcome level, EDGE has met the majority of milestones. Therefore, this Annual Review scores A overall. This continues the pattern from previous years with consistent strong performance.

There has been substantial progress in the past year across a number of different areas:
- Construction of schools and facilities: Construction and opening of two new secondary school in the PEAS network, bringing education opportunities to underserved populations, and providing boarding schools that enhance student safety, particularly for girls.
- System strengthening: Alongside this, the expansion of the PEAS TIEEZ (Targeted Improvement for Equitable Education in Zambia) programme has brought the lessons and experience from running schools to support government schools in school leadership and management, child protection and safeguarding, and enhanced teaching and learning.
- Reach: This year EDGE is directly reaching over 70,000 Zambian students through PEAS’s various interventions.
- School leadership: The British Council’s support to the Ministry of Education shifted toward provincial and district engagement. In collaboration with the Headteachers Association of Zambia (HAZ), orientation sessions reached nearly 1,800 school and system leaders, cascading to over 12,600 nationwide. PEAS complemented this by ensuring all network and partner schools implemented School Improvement Plans, strengthening leadership and management across diverse school settings.
- Technical Assistance to the Ministry of Education (MoE): British Council support at MoE HQ continued to be flexible and, in the past year, critical and timely support to the Curriculum Development Centre meant that Zambia’s new, competence-based curriculum could be validated and finalised on time for roll-out in 2025. Support to the Primary Education Directorate helped finalise a strategy document for this new directorate’s activities and priorities.
- Resourcing within FCDO: To date an EDGE programme-funded education advisor post has been vacant in the BHC Lusaka. This was filled temporarily during the reporting period, allowing the BHC to more deeply engage with the education sector writ large, and bringing lessons into the EDGE programme, and vice versa.

Major lessons and recommendations for the year ahead

Section C contains recommendations for the various outputs. Overarching recommendations for EDGE are here:
Extend the EDGE programme beyond April 2026 to 2029, shifting the focus to (i) deprioritise direct service delivery, and (ii) emphasise systems strengthening and foundational learning. This better aligns with MoE momentum, evidence-based impact, and the donor architecture in education in Zambia. It will also focus on VfM by strengthening existing public service delivery.

- Update the logframe to:
  - Reflect the new April 2026 end date. Including revising any targets where there is significant overachievement.
  - Account for further extensions to 2029.

Review and renew if necessary any Due Diligence Agreements (DDAs) due to new programme timelines.

Increase focus on improved teaching quality and learning outcomes, especially in PEAS partner schools, and especially in light of the new curriculum rollout.

Continue to further strengthen PEAS’s engagement with the MoE to ensure that PEAS’s impact continues to expand beyond their school network and partner schools into the wider Zambian education system. PEAS’s Top 10 Teaching Practices being adopted by MoE has been a good example of this, future opportunities exist by sharing experience from curriculum rollout in PEAS schools, and use of efficient systems for school monitoring.

Ensure that, with the extension to 2026, British Council leverages policy influence to embed EDGE learnings into national strategies and guidelines.

Complete and analyse pending evaluation data from the British Council elements, to provide a full picture of EDGE impact.

Some lessons from the past year include:
PEAS’s hub model (network schools as innovation centres) is effective for scaling best practices to government schools.

Grant-aided transition of PEAS schools has improved sustainability for the PEAS network, though some staffing and grant disbursement challenges remain.

Construction scale-up was successful but highlighted the need for stronger quality assurance and contract management. This was – in part – due to compressed timelines for delivering construction.

Improved boarding and sanitary facilities significantly improved safety and attendance, especially for girls.

The substantial shift of focus by the British Council – to concentrate some operations at the provincial and district level, rather than only the MoE HQ – made a positive difference. The orientation sessions for school leaders and education officials were impactful, especially when cascaded to wider audiences.

Teaching quality in PEAS schools has been maintained stable despite staff changes, thanks to strong CPD and oversight. But partner schools showed declines in teaching scores, there may be external factors at play (curriculum changes, staff shortages), but this is critical in delivering learning outcomes from Zambian students.

British Council’s flexible approach to supporting the MoE enabled timely contributions to curriculum validation and strategy development for key directorates (e.g., Primary), it also allowed support for MoE priorities which were more tangential to direct EDGE objectives (e.g., communications strategy).

Joint field assessments and learning dialogues strengthened MoE ownership and uptake of EDGE interventions.

FCDO engagement – alongside British Council – in EWF planning and attendance allowed for a well-structured programme which highlighted Zambia education strengths and allowed engagement with multiple UK stakeholders – including FCDO Ministers and senior staff.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The programme Theory of Change (ToC) was adjusted in January 2023, to explicitly articulate the British Council’s ToC within the overarching ToC. Each ToC is shown below.

The broad narrative of the Theories of Change is there is a two-pronged approach to achieving the overall impact – of improved education equity for vulnerable children, especially girls, in Zambia. One approach to achieving this impact is that through establishing schools (PEAS network) that are hubs for strong leadership, safeguarding and teaching and learning, and using these lessons and techniques across government schools (through TIEEZ), then access to education is improved, teaching quality in a safe environment is enhanced, and school leadership is strengthened. The second, complementary, approach, is that high quality support and provision of evidence (from British Council) that informs policy and can influence decision making, will enhance the ability of actors in the education system to think, act and plan strategically and use data to find evidence-based solutions: all of which will enhance quality, access and equity across the educational system.

The EDGE logframe has undergone a couple of revisions in the past two years. A review in March 2024 (described in the 2024 Annual Review) streamlined the logframe and better linked the two programme elements. A further revision in March 2025 clarified targets, added new indicators under various outputs, as well as adding one new output.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

EDGE has two programme outcomes, with indicators for each. The tables and discussion below provide detail on the outcome progress. Overall EDGE is on track to meet the expected outcomes.

Outcome 1	Improved access and learning outcomes in secondary education, generating evidence of cost-effective approaches that influence improvements in the sector, especially for girls and vulnerable groups
Indicator(s)		Milestone(s) for this review	Progress
1.1 Percentage children reaching a minimum proficiency level in English language at the end of i) G7, ii) G9 and iii) G12 (disaggregated by sex)		G7: 69% (F: 69%, M: 69%) / G9: 59% (F: 59%; M: 59%) / G12: 84% (F:84%; M: 84%)	G7: 56% (F: 58%, M: 55%) / G9: 79% (F: 82%, M: 76%) / G12: 89% (F: 91%, M: 86%) / (G7 – 81% of target) / (G9 – 134% of target) / (G12 – 106% or target)
1.2 % of PEAS school-level costs covered by sustainable school income		100%	77% / (77% of target)
1.3 % of girls completing lower secondary school[1] (in comparison to boys) in PEAS and PEAS partner schools[2]		PEAS: F: 100% (M: 100%) / Partner schools: F: 90% (M: 85%)	PEAS: F: 102% (M: 105%) / Partner schools: F: 89% (M: 87%) / Met targets
1.4 Total number of students accessing education through PEAS and PEAS partner schools		Total 56,217 (F: 26,991) / Of which: / PEAS Network: 5,126 (F: 2,563) / Partner primary schools: 10,072 (F: 5,053) / Partner secondary schools: 37,019 (F: 17,396) / Schools under teacher training colleges: 4,000 (F: 1,979)	Total 72,477 (F: 32,273) / Of which: / PEAS Secondary Network: 5,904 (F: 3,401) / Partner primary schools: 21,950 (F: 11,766) / Partner secondary schools: 33,855 (F: 17,106) / Schools under teacher training colleges: 10,768 (F: 5,348) / (Total is 129% of target, females is 120%)
[1] This indicator measures the percentage of children (girls/boys) completing lower primary (G9) compared with the number of children (girls/boys) who started lower primary school (G8). Therefore, a result over 100% means that a higher number of girls/boys finished G9 than started G8.
[2] ‘Partner’ schools refers to government schools that are part of PEAS’ TIEEZ programme – i.e. schools that are government funded and administered but benefiting from PEAS’ capacity-building support.

Outcome 2	MoE adopts and implements evidence-based policies and guidelines to expand quality secondary education, with a focus on girls and marginalised groups
Indicator(s)		Milestone(s) for this review	Progress
2.1 Number of MoE sub-sector strategies and programme documents/ guidelines developed		1	2
2.2 Number of events/meetings to disseminate findings of lessons learned		3	5
2.3 PEAS schools transition to grant-aided model		4 (cumulative)	6 / (150% of target)
2.4 Number and type of practices of institutional changes at central, provincial and district government levels attributed to EDGE interventions, categorised by practices around monitoring, teaching and learning, as documented in final stakeholder interviews		5	5
2.5 Proportion of central, provincial, and district government stakeholders/education partners indicating that EDGE created outcomes or changes in their institutions		80%	95%

Outcome 1 relates to the PEAS element of EDGE. Progress here is on track. The indicators show that:
- Learning outcomes are increasing in the PEAS network (outcome indicator 1.1). The Grade 9 and 12 results are taken from PEAS network schools (Grade 7 numbers are from national end-of-primary assessments). The proportion of children meeting the minimum proficiency level in English – whilst still quite far from 100% - is above targets.
- PEAS schools are increasingly self-financing (outcome indicator 1.2) (77% this year is up from 66% in the previous year) and the move to grant-aided status in 2024 was a large step in this direction. However, the network has not yet reached the point of being fully self-sustained, PEAS estimate that this will be achieved in 2028/2029.
- Targets on retaining children in lower secondary school are being met (outcome indicator 1.2), with boys and girls progressing through grades 8 & 9 are similar rates. This is true for PEAS network of schools and the partner (TIEEZ) schools, although – as expected – the numbers are lower for partner schools.
- There has been a substantial increase in the number of children directly benefitting from education through PEAS interventions (outcome indicator 1.4). In the PEAS network, the addition of two new secondary schools has increased enrolment by 15%. But the really large increases have come through the expansion of the TIEEZ programme, with the number of students being reached in partner primary schools increasing significantly (by 117%).
- It is notable, however, that whilst overall numbers of students in outcome indicator 1.4 have increased (by 29%), the rate is lower for girls (20%). This is likely due to the increased working through government schools.
Outcome 2 largely relates to the British Council-led element of the EDGE programme. Progress here is on track. The various indicators show that:
- The British Council TA to the MoE has been able to support specific directorates to develop two strategies or guidelines (outcome indicator 2.1). However, whilst the support to the Directorate of Primary Education to develop and finalise guidelines on primary education provision has been well-organised, had momentum, and successfully produced a valuable document, the support to the Directorate of Secondary Education stalled and has not been fully finalised. However, a new overarching education policy was passed in 2025 with little input from the EDGE TA, and it will be important to ensure that the key pieces of MoE policy work – such as the upcoming revision of the Education Act – are evidence-based.
- There have been various events to disseminate work from the EDGE programme in the past year (outcome indicator 2.2). The work with the Directorate of Primary Education yielded two well-attended and insightful workshops. The British Council’s support to the Teaching Service Commission on strengthening HR management committees was presented at the education sector Joint Annual Review (July 2025). A MoE communications strategy – developed with the support of the British Council – was launched, following approval by the Cabinet, in March 2025.
- Sustainability of the PEAS model is also part of this outcome (outcome indicator 2.3). All eight PEAS schools have now transitioned to a grant-aided model.[3]
  [3] The indicator shows six. This is because two of the earliest PEAS schools – George and Kawama were already covered by an agreement with MoE where they received government teachers, effectively making them “grant-aided” already.
- There are practices and changes which can be attributed – at least in part – to EDGE activities across different levels of the education system (outcome indicator 2.4). Some examples include:
  - Decentralisation of disciplinary case management. Previously managed at the district or provincial level, disciplinary case management is now done by direct supervisor of the individual at the school level.
  - Sharing Headteachers’ Individual workplans with all school staff of the school; thus improving accountability, collaborative planning and goal setting.
  - Improved delineation of roles and responsibilities within the school management teams; allowing for more autonomy and reduced conflict in schools
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the progress on specific activities and towards specific outcomes within the programme, there is a good argument for EDGE to continue. This is even more relevant given the wider BHC portfolio in Zambia. FCDO will be continuing a full development partnership in Zambia and education is a key contributor to UK priorities in the country – in particular reducing poverty and increasing human capital development – essential for inclusive growth. A key recommendation from this Annual Review is that FCDO should extend the EDGE programme, but with a shift of emphasis – in line with broader FCDO developments – to deprioritise direct service delivery, and focus on utilising technical expertise to (i) strengthen Zambian systems and (ii) support foundational learning, where there is government/MoE momentum, and strong evidence around the societal, economic and equity impacts.

## C. DETAILED OUTPUT SCORING

Output Title	Improved capacity of PEAS and PEAS network schools to deliver and scale up effective school management and safeguarding approaches
Output number:		1	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of PEAS secondary school places	Total: 5,596 / Day: 3,445 / Boarding: 2,151	Total: 6,025 (108% of target) / Day: 3,610 (105% of target) / Boarding: 2,415 (112% of target)
1.2 Number of partner primary and secondary schools and teacher training colleges supported through PEAS	Partner primary schools: 20 / Partner secondary schools: 90 / Teacher training colleges: 2	Partner primary schools: 40 (200% of target) / Partner secondary schools: 90 (100% of target) / Teacher training colleges: 5 (250% of target)
1.3 Average World Management Survey score in partner primary and secondary schools	Primary: 4.1 / Secondary: 4.2	Primary: 4.5 (110% of target) / Secondary (2022 cohort): 4.0 / Secondary (2023 cohort): 3.3 / Secondary (2024 cohort): 2.9 / (Range from 69% of target to 95% of target)
1.4 Number of schools with School Improvement Plans in place	PEAS network schools: 8 / Partner primary schools: 20 / Partner secondary schools: 90	PEAS network schools: 8 (100% of target) / Partner primary schools: 40 (200% of target) / Partner secondary schools: 90 (100% of target)

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is focussed on in increasing capacity in PEAS and TIEEZ schools. Of the four indicators, three have been met or exceeded (1.1, 1.2 and 1.4) and one has mixed results (1.3). This output scores A+.

Indicator 1.1 is about secondary school places in PEAS schools, indicators have been met and exceeded. In the past year PEAS constructed two new secondary schools (PEAS Pembele Secondary School in Chirundu and PEAS Tsogorolathu in Sinda), these both opened in January 2025. In addition, expansion works were completed at the six existing PEAS secondary schools. This work, in total, provides 1,760 additional classroom spaces and 1,440 additional boarding places across the eight schools. Risks existed (see Section E) around such a rapid scale-up of construction work and – whilst the schools were constructed and opened on time – there have been some concerns around quality of cosmetic construction and equipment (e.g., desks). There are not concerns around structural quality due, in part, to PEAS’s use of a supervision consultant.

Indicator 1.2 refers to PEAS’s work beyond their network of eight schools. The TIEEZ programme has expanded and is now working in 40 government primary schools, 90 government secondary schools and 5 teacher training colleges (up from 20, 50, and 2 respectively in the previous year). This programme is testing approaches to improve the wider education system. In the past year, the TIEEZ programme also expanded to Eastern Province, adding 15 secondary and 20 primary schools, while the pre-service teacher training programme was introduced to three more colleges of education (Solwezi, Mufulira and Kasama).

All of these TIEEZ schools – and the eight PEAS schools – have school improvement plans (SIPs) in place (indicator 1.4). The SIPs are key tools in helping schools focus on areas such as leadership, management, teaching, infrastructure, community engagement and safeguarding. Support and mentoring are focussed on monitoring SIPs, and they help schools prioritise scarce resources and advocate for change.

Indicator 1.3 assesses the management capacity of schools. For the partner primary schools, this indicator has been met. However, for all partner secondary schools the management score is below the target. Nonetheless, there is a clear pattern of improvement – those schools that entered the programme earlier have higher scores. This suggests that management is improving over time.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output over the period under review.

There is a need to update the logframe given the EDGE programme now runs to April 2026. Likely this will require small adjustments to milestones.

In the event that the EDGE programme is extended further, with more substantial changes to activities, then a refresh of the logframe will be necessary.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

(Summarised) recommendation from previous AR	Progress
PEAS will be expanding their work by merging with Impact Network (IN): a non-profit with strong evidence of delivering transformative education to some of the poorest children in Eastern Province. IN reach over 6,000 students each year across 42 primary schools. This merger offers PEAS the opportunity to package and share tried-and-tested approaches with another cohort of schools and learn from the IN programme.	In January 2025, PEAS formally merged with Impact Network, a non-profit with a strong track record of delivering transformative education to some of the poorest children in Eastern Zambia. This merger grew PEAS’s school network by adding eight primary schools and brought in system strengthening activities in an additional 80 primary schools in Eastern Province. Whilst the merger is fully completed, the schools formerly supported by Impact Network remain fully funded by other donors and, hence, are not included in the EDGE reporting in this Annual Review. Further work is ongoing within PEAS to fully align the workstreams and share learnings.
PEAS has begun preparatory work ahead of construction of two new secondary schools. The land has been secured, following council inspection of the lands. PEAS has also carried out engagement at Provincial, District and community level to build relationships with the community and encourage high levels of engagement when the schools open.	The two new secondary schools were constructed, opened and launched during the past year. Both schools received new government teachers and learners (Form 1 and Grade 10) joined in January/February 2025. PEAS have continued to work with a construction consultant to monitor and quality assure construction work. PEAS will undertake a review of the large-scale construction in the coming months to capture lessons learned.

Recommendations include:
- PEAS to consolidate systems to allow reporting of their whole set of activities, including those previously under Impact Network.
- PEAS to conduct health and safety inspections around new constructions and a review of procurement and quality assurance processes and procedures.
- Continue to focus on improving school management – there is a clear pattern of improvement over time through the TIEEZ programme as school move toward the targeted benchmarks in the World Management Survey.

Output Title	Teachers and school leaders are equipped to meet the needs of all students, particularly girls and the most marginalised
Output number:		2	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 Average teaching quality score in PEAS and partner schools	PEAS network schools: 2.4 / Partner primary schools: +0.05 (from previous year score of 2.6) / Partner secondary schools: +0.05 (from previous year of 1.8 for 2022 cohort and 1.9 for 2023 cohort)	PEAS network schools: 2.4 (100% of target) / Partner primary schools: 1.9 (a decrease of 0.7 from previous year) / Partner secondary schools: / 2022 cohort: 1.4 (a decrease of 0.4 from previous year) / 2023 cohort: 1.5 (a decrease of 0.4 from previous year) / (targets missed for partner schools)
2.2 Number of teachers reached through technical assistance interventions	PEAS network: 131 / Partner primary schools: 231 / Partner secondary schools: 618 / Teacher training colleges (trainee teachers): 200	PEAS network: 515 (393% of target) / Partner primary schools: 133 (58% of target) / Partner secondary schools: 542 (88% of target) / Teacher training colleges (trainee teachers): 250 (125% of target)
2.3 Number of School Leaders trained (in PEAS and partner schools)	PEAS network: 18 / Partner primary schools: 40 / Partner secondary schools: 120	PEAS network: 41 (228% of target) / Partner primary schools: 191 (478% of target) / Partner secondary schools: 291 (243% of target)
2.4 Improved welfare score in PEAS and partner schools	PEAS network schools: 2.3 / Partner primary schools: +0.05 / Partner secondary schools: +0.05	PEAS network schools: 2.4 (104% of target) / Partner primary schools: 2.6 (an increase of 0.1 from previous year) / Partner secondary schools: / 2022 cohort: 0.5 (a decrease of 1.2 from previous year) / 2023 cohort: 0.7 (a decrease of 1.5 from previous year) / (for partner schools data is not comparable between years)

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is focussed on the quality of teaching, school leadership and welfare in PEAS and TIEEZ schools. Of the four indicators, one has not met the target (2.1), two have exceeded milestones (2.2 and 2.3), and one is hard to assess due to methodological changes (2.4). This output scores A.

Indicators 2.2 and 2.3 have, in general, been met and exceeded targets. These indicators refer to teachers and school leaders trained in PEAS schools, partner schools and via teacher training colleges. Within their own network of schools (and through teacher training colleges) PEAS have exceeded teacher and school leader training targets. Teacher training in partner schools has been under target likely because – as set out in the previous Annual Review – primary schools in particular are understaffed. For the school leaders, targets have been greatly surpassed. Monitoring and support visits to all TIEEZ Schools, along with Ministry of Education officials, shared results of the 2024 Annual School Assessments with school leaders. These leaders were supported to review their School Improvement Action Plans (SIAPs) and develop their 2025 plans. School leaders also reviewed their child protection policies and all TIEEZ secondary schools completed their finalised child protection and SIAPs ready for the new school year.

Indicator 2.1 captures the effectiveness of teaching happening in PEAS schools and partner schools. The index is between 0 and 3. The eight PEAS schools have met the target, but for partner schools the targeted year-on-year increase of 0.05 has not been achieved. For partner primary schools and both cohorts of partner secondary schools teaching quality score is lower than in the previous Annual Review. This is in part encouraging and in part concerning. PEAS schools moved to grant-aided status (from 2024) and were allocated government teachers. It is encouraging, therefore, that even with a new cohort of teachers, the teaching quality score in PEAS schools has been met through implementation of the Top 10 teaching practices, and strong oversight on teaching and learning in schools. More concerning is the fall in teaching scores in partner schools. It is possible that much of this may have been caused by the changes generated by the introduction of the new school curriculum in 2025.

For indicator 2.4 – the welfare score in schools – the PEAS network schools have met the target. Various activities contributed to this:
- At the start of the 2025 academic year all teachers in PEAS schools received comprehensive training on safeguarding and positive discipline strategies.
- New handbooks were introduced to strengthen the operation of Child Protection Committees and Disciplinary Committees.
- All students had inductions on PEAS’s safeguarding policies and procedures, and the PEAS Students’ Top 10 (a framework for behaviour and conduct in PEAS schools).
- Construction of 12 new boarding and sanitary blocks for boys and six for girls across the eight PEAS schools, along with additional sanitary blocks for day students at three schools. These facilities help girls manage menstrual hygiene safely and privately, encouraging school attendance, while boarding options reduce long, unsafe commutes – especially for female students.

However, the Child Protection assessment – used to calculate this welfare score in partner schools – was redeveloped during the year. The new method has a larger focus on the school environment – based on learning from PEAS own school network – and gives a more evidence-based assessment of child protection standards in partner schools, however this makes it hard to assess progress over time.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

There have been no changes to this output over the period under review.

There is a need to update the logframe given the EDGE programme now runs to April 2026. Likely this will require adjustments to milestones, especially where targets have been significantly exceeded.

In the event that the EDGE programme is extended further, with more substantial changes to activities, then a refresh of the logframe will be necessary.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

(Summarised) recommendation from previous AR	Progress
Classroom delivery was one area in which learning walk[4] scores have not improved over the past year. There is a need to focus upcoming teacher coaching on classroom delivery.	The target on teaching quality has been met in PEAS schools in this Annual Review. However, the target for partner schools has not.
[4] Learning walks are structured, but non-evaluative, visits to classrooms. They are for a short period (5-15 minutes) and used to observe and gather a snapshot of teaching practices and student engagement. They are used to support and inform continuous professional development plans and to identify trends for school improvement, rather than forming judgements on individual teachers.

Recommendations include:
- PEAS should continue to conduct regular CPD sessions for staff across their network schools, supported by lesson observations, coaching, support and supervision visits and learning walks. However, these practices need to feed into classroom delivery in partner schools.
- PEAS should make the most of opportunities to share learning from their network of schools with TIEEZ schools and with the government school system more widely. One opportunity is to share how the new curriculum has been implemented and tested in PEAS network of schools, and share this with the Curriculum Development Centre in the MoE.

Output Title	Stakeholders and decision-makers in the GRZ are provided with timely syntheses of data, learning and evidence to support policy development and implementation
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Number of a) collaborative research reports completed and b) policy papers completed	N/A
3.2 Number of joint MoE field assessments undertaken	2	5 / Exceeded target
3.3 Number of reflective learning meetings conducted with stakeholders in districts and provinces (DEBs and PEOs)	Unique: 10 / Cumulative: 24	13 meetings by British Council / 4 meetings by PEAS / Exceeded target
3.4 Number of participants in meetings and training organised by EDGE (School Leaders orientations, Code of conduct, professional conduct, roles and responsibilities, safeguarding)	7 orientation meetings / 140 individuals per session	9 orientation meetings across 7 provinces / 1795 school leaders in total (~200 per session) / Exceeded target
3.5 % of education leader orientation session* participants (School Leaders, Ministry of Education Officials, District Education Officials, and HRMC Members) reporting improved knowledge of roles & responsibilities, safeguarding and protection, code of conduct resulting from session / (*sessions related to policy implementation - safeguarding/professional standards)	80%	99.2% (or 56% for high levels) / Exceeded target
3.6 % of education leader orientation session participants (School Leaders, Ministry of Education Officials, District Education Officials, and HRMC Members) who identify minimum: / - one key practice learned in the session implemented in their setting / - one key action taken to share the knowledge with colleagues	80%	96% / Exceeded target
3.7 Number of follow-on programmes, interventions, and activities developed or launched based on results of research, results, consultation, lessons learned to-date in EDGE Programme	3	2 launched / Multiple activities in development / Target met
3.8 Number of provinces supported to pilot new interventions	7	9 / Exceeded target

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is focussed on providing government officials with data and evidence to support policy and implementation. Both British Council and PEAS work contributes to this output. There are 8 indicators (although one (3.1) has no target for this year[5]). Of the remaining seven indicators, six have exceeded targets (3.2, 3.3, 3.4, 3.5, 3.6 and 3.8), and one has not met the target (3.7). This output scores A.
[5] The four research reports for indicator 3.1 – Cost of Education; Education Dashboard; Safeguarding; and Non-Educational Barriers – were completed last year.

Whilst the research reports (indicator 3.1) were completed in the previous year, they have continued to be discussed with MoE, who consider them high quality and relevant. Directorates of Planning, Curriculum, and Secondary Education have expressed interest in using the findings to inform ongoing policy development. For example, the cost of education study was instrumental in informing the introduction of school grants. The study continues to inform the planning and budgeting processes within the MoE’s Planning Directorate. However, it is worth noting that the research did not come up in discussions with MoE stakeholders as part of this Annual Review (whereas training – described below – did).

Joint working with the MoE has been key to the British Council approach, including joint field visits (indicator 3.2). Field assessments were completed with HAZ (who are not technically part of the MoE) in four provinces (Lusaka, Northwestern, Copperbelt and Southern) and Teaching Service Commission (in Copperbelt).

Indicator 3.3 helps to track learning meetings and discussions with officials at provincial and district levels. The cumulative target for this year had already been surpassed at the last Annual Review, nonetheless the target for this year (ten meetings) has been exceeded (17 in total). Thes include meetings held after orientation trainings with DEBS and PEOs, and in locations where PEAS operates.

Indicators 3.4, 3.5 and 3.6 are all largely related to work done by the British Council in collaboration with the HAZ. These orientation sessions for systems and school leaders reaching a total of 1,795 participants, including representatives of the Provincial Education Office, District Resource Centre Coordinators, District Education Standards Office as well as school leaders from both primary and secondary schools. These sessions have been further cascaded by the Ministry of Education to an additional 12,626 participants. Evaluation of these sessions find that over 99% of participants reported “some level of improved understanding of roles and responsibilities, safeguarding and codes of conduct”, which exceeds the milestone target (80%). However, “some levels” is quite a low bar, and only 56% report “high levels of improvement”. Subsequent fieldwork has shown that the training has become well embedded in some provinces/districts, whereas in others there has been minimal impact on behaviour change.

Indicator 3.7 assesses the impact of EDGE work on development and launch of new programmes, initiatives and activities. Two key activities were launched during this period:
- The integration of the HAZ school leader orientation into Zambia’s national teacher development framework via the Teaching Council of Zambia (TCZ), marking a significant milestone for sustainability and formal recognition.
- EDGE’s support to HAZ in developing a concept paper in response to a UNESCO regional office request to pilot the school leader orientation in five countries—Ghana, Tanzania, Kenya, Uganda, and Zambia. Interest in this initiative was sparked by HAZ’s presentation at a regional school principals meeting in Uganda.

The absence of a programme-funded FCDO education adviser for much of the programme, has limited the role that FCDO could play in helping to drive forward progress with partners on new initiatives. Despite this, some progress includes:
- PEAS has been engaging the MoE on piloting best practices for effectively monitoring the newly rolled-out 2023 curriculum. This has started with adapting lesson plan templates and piloting across PEAS schools. In discussion with Curriculum Development Centre PEAS are looking to pilot approaches to curriculum monitoring and review across PEAS and TIEEZ schools.
- PEAS has been in discussion with FCDO and partners to design a follow-on scaled up model based on the school improvement cycle developed under the TIEEZ programme. This is being considered for funding (for a “test-learn-adapt pilot”) under FCDO’s Scaling Access and Learning in Education (SCALE) programme.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicator 3.5, 3.6 and 3.8 were added since the previous Annual Review to reflect EDGE’s increasing focus on sustainability, influence on policy and practice, and local ownership.

There is a need to update the logframe given the EDGE programme now runs to April 2026. Likely this will require small adjustments to milestones.

In the event that the EDGE programme is extended further, with more substantial changes to activities, then a refresh of the logframe will be necessary.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

(Summarised) recommendation from previous AR	Progress
While it is important to remain flexible and adaptive to new opportunities to influence key stakeholders, the British Council must also ensure that activities are selected strategically, and aligned with the EDGE outcomes and impact statements. Whilst learning events have responded to MoE demands, they have not in all cases had a clear line of sight to policy influencing objectives. For example, the strategic policy objectives of the Education World Forum and Global Schools Conference were not articulated in advance of those events (although, for example, the EWF was valuably used by BC to facilitate meetings between the Minister of Education and PEAS). The British Council has improved its recording of outputs (e.g. in ‘Activity profiles’ for EWF and in its ‘Stories of Change’ for support to directorates. However, these records tend to focus on outputs rather than outcomes. It is recommended that in the final year of the programme, the BC maps out the learning events/stakeholder engagement events that correspond to its policy and advocacy priorities, and develops a specific advocacy plan for each event.	The British Council developed a strategic workplan for this year, and their evaluation partner – Thuso – have developed a set of tools to better capture outcomes.
In the final year of the programme, it will also be important to produce final versions of the research reports and policy briefs that have now been validated, so that they can be widely disseminated and used by both the EDGE programme and external stakeholders to identify best practice and policy reform and implementation priorities.	In March 2025, an EDGE exit strategy meeting took place (between PEAS, British Council and FCDO) took place where ideas on producing, using and disseminating final briefings were discussed and a plan was devised.

Recommendations include:
Ensure that the British Council focusses on embedding existing work, rather than starting new initiatives. Expanding school/system leader training to have nationwide coverage and/or embedding this training into existing systems would be good examples of this.

Output Title	The Ministry of Education has improved capacity to use data and evidence to shape and implement policy
Output number:		4	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
4.1 Number of government officials trained through a) primary and b) secondary school system strengthening	Trained through primary school level system strengthening: 4 / Trained through secondary school level system strengthening: 28	Trained through primary school level system strengthening: 8 (200% of target) / Trained through secondary school level system strengthening: 44 (157% of target)
4.2 Number of school inspection visits conducted jointly with MoE in PEAS partner schools	PEAS network schools: 8 / Partner primary schools: 20 / Partner secondary schools: 90	PEAS network schools: 8 (100% of target) / Partner primary schools: 40 (200% of target) / Partner secondary schools:75 (83% of target)
4.3 a) MoE validation of revised Education Dashboard and b) completion of orientation on Education Dashboard for MoE M&E staff	Validation sessions:2 / Orientation sessions: 2 / Capacity Building sessions: 2	Validation achieved: 2 sessions conducted / (target not met)
4.4 Number of multi-country policy dialogues, events, learning dialogues attended by supported MoE officials.	Learning events: 2	Two multi-country education learning dialogue attended by MoE officials. / (100% of target)

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is focussed on the capacity of the MoE to use data and evidence. Both British Council and PEAS work contributes to this output. Of the four indicators, two have exceeded targets (4.1 and 4.2), one has met the target (4.4), and one has not met targets (4.3). This output scores A.

Indicators 4.1 and 4.2 reference work through PEAS’s TIEEZ programme. Throughout the year PEAS has deepened working relationships with MoE officials, especially at Provincial and District levels. TIEEZ is jointly implemented in partnership with MoE teams in target districts, including co-designing and rolling out the TIEEZ model, conducting joint inspection visits and training government officials. PEAS staff are embedded in MoE offices and have established provincial-level MoE-PEAS working groups which oversee implementation.

Indicator 4.3 concerns the further embedding of the Education Dashboard, developed by the British Council, into MoE work. This experienced some delays and challenges. Whilst the MoE is showing growing interest in embedding and using data systems, the main focus is on reforming the existing EMIS. This is being supported by the World Bank and the EU. As such, the orientation and capacity building sessions on the education dashboard did not take place. It is possible that the findings of the education dashboard study will inform these broader EMIS reforms.

Indicator 4.4 is about MoE officials learning from attendance at international fora. In October 2024 MoE officials were sponsored to attend the South–South dialogue and learning exchange in Nairobi. A number of post event actions were identified by the MoE delegation, in particular aimed at enhancing inclusion within Zambia’s education system. In May 2025 British Council sponsored MoE officials (the Minister of Education and others) to attend the Education World Forum (EWF) in London (accompanied by an FCDO official from BHC Lusaka). Further details on the EWF are in output 5.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicators 4.4 was added this year to reflect growing emphasis on support to the MoE that draws from research and multi-country policy dialogue events and knowledge exchanges.

There is a need to update the logframe given the EDGE programme now runs to April 2026. Likely this will require small adjustments to milestones.

In the event that the EDGE programme is extended further, with more substantial changes to activities, then a refresh of the logframe will be necessary.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

(Summarised) recommendation from previous AR	Progress
PEAS has developed a real-time dashboard which enables data-driven decisions to be taken by schools, PEOs and DEBs. This dashboard captures the type and frequency of support provided to schools, scores on teaching quality, conversations with school leaders, and planned action points. As a source of actionable data for conversations with schools, and for decisions regarding program direction, this will be an important reference point in PEAS-MoE joint implementation of school support activities. PEAS School Improvement Leads and the School Improvement Specialist have been given training on how to use the tool. Training for MoE officials is planned for the coming year. It is recommended that PEAS engages in wider sectoral discussions regarding the MoE’s Education Management Information System (EMIS) strengthening. PEAS’ experience and expertise in developing digital and real-time data tools is valuable and there is the opportunity to influence development partners’ policy and practice.	It is notable that in any visits, interviews or discussions as part of this Annual Review process there was no mention of a dashboard (by PEAS staff, education officials or staff at schools). PEAS have not engaged on the EMIS debates, which are progressing nationally, mainly through World Bank and EU programming. There is certainly scope for PEAS to share learning from their real time systems and data management systems. For example, through the Directorate of Standards who have expressed interest in PEAS methods of school inspections. More generally, PEAS are looking to set up – at national level – a MoE-PEAS working group which will further institutionalise collaboration and provide strategic oversight to PEAS’s work.
The British Council develops clear outcome-oriented objectives for its activities under this output. The British Council should develop a plan for joint policy monitoring (or capacity building) with the MoE that: / Is informed by and responds to Directorates’ own strategies (developed through BC support); / Has specific objectives related to building MoE capacity to deliver tasks related to that Directorate’s mandate, or related to the development or adaptation of specific MoE policies. / Includes a clear summary report of lessons learned from the policy monitoring and next steps.	In the past year MoE staff have been trained on the dashboard, this is aligned with tracking MoE performance, however it has somewhat been overtaken by other work (on EMIS). British Council has focussed on helping Directorates deliver their mandates – examples include supporting the Primary Education Directorate with developing a comprehensive guideline document, and supporting the Curriculum Development Centre with validation of the new curriculum. Alongside these kind of efforts, some capacity has been built in these directorates.

Recommendations include:
- Ensuring the PEAS work on system strengthening, being advanced through EDGE and also the FCDO SCALE programme, is well-evidenced and the distinction between work delivered under the different programmes is clear.
- As EDGE will, on current timelines, run until before the next EWF, British Council and FCDO should establish the plans for Zambia attendance and engagement at the event in 2026.
Output Title	Increased FCDO engagement and UK visibility in education sector
Output number:		5	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
5.1 Number of meetings between Ministry of Education senior officials (Directors General/Ministry of Education) and FCDO Zambia seniors focused on education policy and delivery priorities	MoE/FCDO meetings: 4	5 / (125% of target)
5.2 Number of social media posts and/or press releases related to FCDO Zambia’s education portfolio	Posts: 4	Posts on X (twitter): at least 12 / MoE facebook posts: at least 5 / Press releases: at least 5 / (target exceeded)
5.3 EDGE supported MoE participants at EWF indicating attendance resulted in improved relationships with UK-based partners, colleagues, or stakeholders	3 individuals	Data being collected as part of final evaluation. Not yet completed.
5.4 Proportion of stakeholders indicating 'positive' or 'very positive' view of the United Kingdom due to participation on FCDO funded EDGE / *Stakeholders refer to government staff that have worked/engaged with the EDGE 2 project	80%	85% / Target met

Briefly describe the output’s activities and provide supporting narrative for the score.

This output is focussed on increasing the UK’s visibility and engagement in the education sector in Zambia.[6] Of the four indicators, two have exceeded targets (5.1 and 5.2), and two (5.3 and 5.4) do not yet have collected data. This output scores A.
[6] In part this is achieved by using EDGE programme funds for a programme funded education advisory post in the BHC Lusaka.

Indicator 5.1 is about engagement with the senior levels of the MoE by BHC Lusaka officials. There have been at least five substantial meetings with Minister/PS in the past year.[7] There have been a wide range of other engagements with the Minister throughout the year at different events – some directly related to the EDGE programme[8], others less so[9]. There have also been multiple engagements with Director-level MoE officials by FCDO staff throughout the year at different events, and specific meetings,[10] as well as with senior officials in Provinces and Districts[11]. All of this engagement seeks to keep the UK well situated as a partner in the Zambian education sector.
[7] Meetings between Human Development Team and the (previous) PS in January and February 2025. Introductory meeting between the British High Commissioner and Minister of Education (February 2025). A meeting with EDGE programme partners and the (new) PS (March 2025). A set of preparatory meetings for EWF with the Minister of Education and his team, and attendance at the EWF (April/May 2025).
[8] Breaking ground on the new PEAS secondary school in Chirundu (in September 2024), and opening the same school (in June 2025). Celebrating British Council’s 90th anniversary (December 2024).
[9] For example, at the expansion of the Kansanshi mine (August 2025).
[10] Engagement and discussions with Directors of ICT, Primary, Secondary, TESS, CDC, Standards, and Planning at various times related to EDGE work (BC and PEAS), the education Joint Sector Annual Review, CP coordination meetings, GPE planning, etc.
[11] For example, engagement with PEOs in Copperbelt and Lusaka through the JAR and EDGE field visits, and with various DEBS and DEBS offices.

Indicator 5.2 measures public messaging around the UK’s engagement in Zambia’s education sector. The target for this indicator has been exceeded. There have been multiple posts on X from the UKinZambia account referencing EDGE work[12], the broader UK education work in Zambia[13], and UK-Zambia links on education[14]. In addition, facebook posts by the Ministry of Education[15] and various press releases – generating stories in local newspapers – have added to the UK visibility.
[12] For example, groundbreaking at PEAS Chirundu school, and PEAS students meeting the UK Minister for Development.
[13] For example, through Keeping Girls in School, and marking international day of the boy child. In addition, there are multiple posts advertising and celebrating scholars and scholarships as well as links with UK higher education institutions (e.g., the Wallace Group) – all of which are important elements of the UK education portfolio.
[14] Meetings between the High Commissioner and Minister, and the Minister of Education’s attendance at EWF are examples.
[15] For example, on PEAS Chirundu boarding school.

Through the British Council EDGE sponsored the MoE participation at the Education World Forum (EWF). This yielded concrete relationship gains, with feedback from participants highlighting enhanced links with UK-based policy institutions and FCDO partners. In addition, the EWF provided an opportunity – at a UK-hosted roundtable on school violence and in an APPG-hosted Ministerial roundtable on foundational learning – for the Zambian Minister of education to highlight Zambia’s progress, and engage with UK Ministers and politicians. The Minister spoke on Zambia’s experiences on girls’ education, refugee education, foundational learning and signed up to a new ministerial taskforce on ending violence in and around schools. In a bilateral with the Pakistani delegation – organised by FCDO and the British Council – the Minister shared Zambia’s experience of teaching at the right level (TaRL, or “Catch Up” in Zambia). Data to report against the specific indicator (5.3) however, has not yet been collected.

Data collected for indicator 5.4 demonstrates a high degree of positive views of the UK from those stakeholders engagement in the EDGE programme. This was backed up by the interviews conducted for this Annual Review, which also gave general positive feedback on the relevance and usefulness of EDGE activities (across both PEAS and British Council components).

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicators 5.3 and 5.4 have been added to the logframe in the past year to ensure it is possible to capture stakeholder feedback on programme activities.

There is a need to update the logframe given the EDGE programme now runs to April 2026. Likely this will require small adjustments to milestones.

In the event that the EDGE programme is extended further, with more substantial changes to activities, then a refresh of the logframe will be necessary.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations in the previous Annual Review, and progress, are shown below.

(Summarised) recommendation from previous AR	Progress
Ensure that opportunities for FCDO engagement and advocacy are reflected in BC’s strategic workplan for the final year of the programme	The British Council work for the past year has been instrumental in many of the FCDO engagements described above. This applies to senior engagement (High Commissioner, Minister, EWF) and at a working level (e.g., FCDO engagement in HAZ training and primary directorate guideline development)
Ensure that FCDO attendance in Education Cooperating Partners meetings is regular and informed by policy objectives	The FCDO Education Lead from BHC Lusaka has been attending the Cooperating Partner Coordination Committee (CPCC) throughout 2025, as well as engaging in wider strategic sector discussions (e.g., JAR, GPE planning).
BHC Lusaka develops a proposal for funding to the new Centrally Managed Scaling Access and Learning in Education (SCALE) programme that builds on lessons learned from EDGE	There have been ongoing discussions between BHC Lusaka, the central SCALE team and PEAS throughout the year, building strongly on TIEEZ work through EDGE. A piece of research (functional review of the middle-tier) has been completed, but a full pilot has not yet been agreed.
Integrate lessons from EDGE within the development of wider BHC Lusaka cross-sectoral poverty reduction programming	Lessons from EDGE, particularly around systems strengthening and successful ways to support MoE priorities have been crucial in formulating the UK’s future education plans in Zambia.

Recommendations include:
- FCDO to remain engaged in the education sector, through CP discussions.
- As in output 4, FCDO and PEAS to continue to work on developing a pilot for the SCALE programme.
- Ensure that BHC Lusaka’s planned poverty reduction programme has an element under the pillar of improving public service delivery that relates to education.
## D: VALUE FOR MONEY

Key cost drivers and performance
The key cost driver for EDGE remains staff costs. In the past year staff costs have accounted for around 60% of programme costs. In the EDGE model – for both PEAS and British Council elements – staff input time is a key delivery mechanism. Staff provide support to the MoE for strategic planning, prioritisation and advice through the British Council. For PEAS’s TIEEZ programme, PEAS staff providing mentoring, guidance and monitoring to schools – alongside MoE officials – in at the heart of the model to support government schools.

In the past year construction costs were a much more significant share than in previous years. The additional funds to PEAS to build two new secondary schools means that construction costs accounted for 18% of spending. The construction has been delivered (a) to standard, and (b) to time, allowing the schools to be ready, open and operational for the start of the 2025 school year. Given that the decision to fund this construction, and the groundbreaking, only happened in 2024, this is an admirable pace – certainly faster than other secondary school building programmes currently ongoing in Zambia.[16]
[16] For example, the World Bank’s ZEEP programme – which has a large element, over $150m, for constructing secondary schools – has faced delays. ZEEP has had to be extended by 18 months to ensure the construction can be completed.

VfM performance compared to the original VfM proposition in the business case

VFM in the original Business Case focussing on the PEAS element of EDGE proposed that delivering through PEAS would achieve significant economy gains in education provision compared to government provision – in both construction and non-construction costs. On the British Council side, the original Business Case suggested that VfM would come from leveraging the British Council’s expertise in supporting the MoE to make good use of its own existing resources. Evidence was cited that the EDGE programme would, over the longer-term, support FCDO’s efforts in Zambia to reduce fertility rates and boost human capital.

The original Business Case highlighted the importance of delivering VfM in education by moving beyond considerations of only access, and the need to raise learning outcomes. It states: “the key to achieving VfM in the education system is to increase access and improve the quality of education whilst keeping control of the costs: this is a key reason why EDGE focuses on raising learning outcomes”. Quality of education is a key outcome of this programme and therefore efficiency and effectiveness measures are integrated into the logframe. Various indicators in the logframe, which are reported on in Sections B and C are indicative of VfM. Whilst they are not always directly comparable to costs, so are not true VfM indicators, they are measures of efficiency (e.g., outcome 1.4, outputs 1.3, 2.1, 2.2, & 2.4), effectiveness (e.g., for example, outcome 1.1, 1.2, outputs 3.2 & 3.6) and equity (e.g., outcome 1.3). Full reporting on these is provided in Section B & C, the discussion below brings out some key points.

Economy (i.e. cost of inputs)

The Business Case articulated an aim to progress from a “cost to FCDO Zambia” unit cost of £69 per student to £4 per student throughout the PEAS element of EDGE programme. There has been some progress on this, with the benchmark coming down from £26.50 August 2023 to £5.84 in June 2024. However, in the past year, this has risen again – to £7.34 in June 2025. There are a few reasons for this rise in per-student costs, despite the rise in students reached in the past year:
- For the newly opened PEAS schools the overhead costs (support, supervision, school support visits, finance support visits, CPD, school inspections, IT support, etc.) are equivalent to that of a full school, however, the schools begin with only one or two grades enrolled. The schools will grow the enrolment to be full over 3-4 years.
- Additional operational expenditure for the new schools (ground-breaking, school launch activities, enhanced operational oversight from PEAS).
- The transition to grant-aided status has required additional training for all staff in schools – including new teachers provided by MoE – to build skills.
- Expanded system strengthening activities – such as the validating the Top 10 Teaching Practices for use in for pre-service training – does not directly led to an increase in the number of students reached, although the VfM impacts over the long term are substantial.
This indicator still has further progress to reach its long-term targets of £4 per student.

On the British Council element of EDGE there are two main aspects contributing to economy (i.e. the price of “inputs”) VfM:
- Co-delivering and cost sharing activities with the MoE. As well as providing VfM this helps enhance government ownership and sustainability. For example, orientation sessions with the HAZ were jointly designed and delivered by British Council and MoE and, whilst the direct sessions reached around 1,800 people, the wider education system was able to expand this to an additional ~12,600 people across the country.
- Consistent procurement practices, which always sought three quotations for goods and services enabled competitive prices for inputs. For example, in supporting the CDC to validate the new curriculum quotes were received from three venues. The lowest price venue (~£159k) was significantly (~£34k) less than the highest bid. By running this activity in collaboration with UNESCO and British Council shared costs and contributed around £57k towards the event.

Efficiency (i.e. turning inputs into outputs)
Many of the EDGE outputs show that – for the given budget – numbers of outputs being achieved are being met or exceeded. The target for the number of students directly accessing education is being reached. Across other elements of the programme teachers are being trained, colleges of education are receiving support for pre-service training, school leaders are being oriented and are receiving training.

Specific actions delivering efficiency include:
- Using PEAS network schools as hubs for innovation (testing approaches) means that tools and ideas have been shared with PEAS partner schools and the wider government system in the same regions. This drives efficiency by establishing a wider indirect reach for PEAS’s activities.
- Use of communities of practice, through WhatsApp groups, to share best practice and maintain contact has been crucial given the remote locations of many TIEEZ schools.
- The British Council (and HAZ’s) orientation was delivered in a way to enhance efficiency – training system leaders (as well as school leaders) allowed many thousands more people to be reached through cascade training. In addition, of those training, nearly 100% reported improved knowledge on their roles and responsibilities, safeguarding and professional conduct.

Sustainability is key to the programme, and its effectiveness:
- For PEAS, the shifting to a grant-aided model will allow investments to be sustained by the government beyond EDGE’s lifetime. This has been a major change in delivering VfM in the past year. Measured through the proportion of PEAS school-level costs covered by sustainable school income. The shift to grant-aided status, combined with expanded school-based income-generating activities, has increased the proportion of PEAS school-level costs covered by sustainable school income from 66% (June 2024) to 77% (June 2025).
- For the British Council, groundwork with new directorates in the MoE to develop guidelines and strategy documents will stand these organisations in good stead as they establish priorities.

Effectiveness (i.e. turning outputs into outcomes)

Section B shows that – for the given budget – outcomes are being achieved. In particular the data on learning outcomes in PEAS schools demonstrates effectiveness of the model. This was the eighth consecutive year in which PEAS students performed higher than the national average for Grade 9, despite often starting with lower learning levels than their peers in other schools.[17] The PEAS network average pass rate at Grade 9 was 61% (63% for girls, 59% for boys). This is especially notable because – since the transition to grant-aided status – this has been achieved by the PEAS network staffed with government-assigned teachers.
[17] https://www.peas.org.uk/resources/peas-zambia-programme-evaluation/

There is some evidence that the TIEEZ programme is making progress on outcomes. Students at TIEEZ partner schools have made more progress than average across their districts, for example, in TIEEZ schools in Northern Province, the pass rate for Grade 7 exam results was 90%, 19-percentage points higher than the national average, and 15-percentage points higher than the provincial average. Whilst TIEEZ schools began above the national average, the performance gap between TIEEZ primary schools and the national average has widened from 6.3 percentage points (2021) to 19 percentage points (2024).

Equity

The British Council element of EDGE has focused on reaching rural provinces where access to quality secondary education remains a challenge due to resource constraints. Orientation sessions with a strong focus on roles and responsibilities around safeguarding have been a key activity in the past year. That these sessions (delivered to 1,800 people) have been cascaded to a further 12,600 demonstrated some VfM in rolling out important information and training.

Over half (58%) of PEAS’s network school places are taken by girls – directly providing more girls with access to a quality education. Whilst boarding facilities primarily house girls (and an additional 480 girls boarding spaces were added this year) the construction of 12 boys’ dormitories provides an additional 960 boarding spaces for boys. All these boarding spaces provide increased support for girls and boys in rural locations to access and complete secondary schools.

However, the data in outcome 1 shows that as the number of students reached grows through the working with government schools through the TIEEZ programme this is proportionately faster for boys. This is something to continue to address through the programme.

One concrete example of improved outcomes for students in rural areas is from PEAS Kafula Musungu school. At this rural school performance was high in 2024: 94% of students achieved Grade 9 certificates (38-percentage points above the national average), showing an increase of 31-percentage points compared to 2023. On gender: at Grade 12, girls in the PEAS network performed 5-percentage points better than boys, marking a widening of the gender gap compared to 2023 when the gap had nearly closed.

Assessment of whether the programme continues to represent value for money
The programme continues to represent VfM. The outcomes are on course to be achieved within the programme budget.

Any potential extension of the programme should consider how best to enhance VfM of UK spending in the education sector in Zambia. This would likely involve: reduced focus on direct service delivery, increased focus on maximising value from the public expenditure on education (i.e., systems strengthening), and refocussing on foundational learning where returns to education are high and equitable.

E: RISK

Overview of risk management

Individual risk registers are maintained by the implementing operating (British Council and PEAS), and an overall EDGE risk register is reviewed regularly by the programme team in BHC Lusaka – the most recent update was in August 2025. The overall risk for the programme is moderate. A brief summary by risk category is shown below.

People
EDGE faces challenges due to the absence of a dedicated FCDO Education Adviser. This limits the provision of consistent technical and strategic guidance. To mitigate this, during the reporting year, a temporary Education Lead has been deployed, and recruitment for a permanent adviser is underway. The EDGE programme includes funding for this essential role.

Safeguarding
Safeguarding risks are particularly acute for adolescent girls in PEAS and government schools. Many come from marginalized communities and may be vulnerable to sexual exploitation, abuse and harassment. EDGE – through both PEAS and British Council elements – has responded with robust institutional safeguards, including comprehensive training for staff and students, clear reporting mechanisms, and a zero-tolerance policy for abuse. PEAS has designated safeguarding officers at each school, and FCDO conducts regular spot checks to ensure compliance and safety.

Financial & Fiduciary
Given the scaled-up construction activity in the past year and the speed of delivery, there has been a high risk of financial mismanagement or diversion of funds which could jeopardize both construction progress and overall programme delivery. To address this, the programme employs rigorous due diligence, disburses funds only for approved activities, and conducts regular spot checks. Annual financial reviews have so far not identified any major issues, indicating that the mitigation measures are effective.

Policy & Programme Delivery
This captures a wide range of systemic and operational risks that could significantly affect the EDGE programme’s effectiveness. One major concern is the potential duplication or misalignment with other development partners (e.g., USAID, World Bank, GPE). This could overburden an already fragile education system in Zambia. To mitigate this, the programme emphasizes coordination through mechanisms like the Cooperating Partner Coordination Committee (CPCC) and leverages technical advisors to align efforts and avoid redundancy. Additionally, the programme faces challenges in ensuring that the MoE Education can absorb and apply the technical assistance provided. This is being tackled through capacity-building initiatives, development diplomacy, and support for senior officials to engage in global learning forums.

Another critical issue is the inconsistency in government grant aid to PEAS schools, which can lead to resource gaps and increased administrative burdens. This has been addressed via an MOU with the MoE, ongoing lobbying, and the recruitment of volunteer teachers to fill staffing gaps when government support falls short.

Construction quality is another risk area (see Section F for some further detail). Substandard work could endanger students and compromise value for money. During a period of increased capital development funding, construction risks were heightened due to the scale and pace of building activities. To mitigate these, PEAS hired a consultant to review technical drawings and bills of quantities and provided quality assurance support. Two clerks of works were stationed at each new school site to supervise construction, and contractors were inducted on PEAS’ Anti-Corruption and Child Protection policies. Payments were made in instalments via bank transfer to ensure financial control.

Coordination between the British Council and PEAS components has also been flagged as a risk, with the potential to undermine programme coherence and value for money. In response, monthly coordination meetings and a consolidated logframe have been introduced to align efforts and improve delivery.

Strategy & Context
The programme is vulnerable to strategic shifts, particularly changes in UK ODA. This has not materialised during the EDGE programme to date, and – as the UK will maintain a full development partnership with Zambia – this is a minimal risk to the current end date of the programme (April 2026).

There are also broader risks to the education sector, some of which materialised in 2025. A substantial USAID programme – Let’s Read – operating in the early primary grades was discontinued, and planned funding from the Global Partnership for Education (GPE) was halved – also reducing external support to the early grades of primary school.

Reputational
There is a reputational risk that the EDGE programme could be perceived as politically biased, especially if it is seen to support a particular party. This concern is being addressed through diplomatic engagement with political stakeholders, community sensitisation efforts to clarify the programme’s objectives, and ongoing support from the British Council to maintain neutrality and transparency.

Public Service Delivery & Operations
Changes in FCDO could shift funding and policy priorities. However, the programme’s focus on universal access to education aligns with the UK’s broader international development goals.

Some additional, minor, risks are monitored by British Council and PEAS include:
- Fraud and Operational Risks associated with procurement and financial management within the British Council’s component of the programme. One potential risk involves the potential for British Council staff to provide inside information to preferred consultants in exchange for facilitation fees. This is mitigated by procurement processes which are managed entirely outside the country (in Zimbabwe), thereby reducing the risk of undue influence.
- Staff could be bribed to approve substandard work. To counter this, a multi-disciplinary teams review all deliverables before payments are approved, ensuring quality and compliance with contract terms. These are effective mitigations.
- Partners may fail to comply with British Council or FCDO fraud policies. Addressed through strong performance monitoring.
- There are risks around the impact of currency devaluation on project budgets. Mitigated through close tracking of exchange rates
- Risks around payments being made to partners lacking sound financial systems is addressed by rigorous due diligence processes.
- Risks of staffing levels in PEAS schools following transition to grant-aided model. To mitigate shortages, PEAS used volunteer and private teachers.
- Delays in grant disbursements also meant that PEAS had to use contingency funds to support schools temporarily. In both cases (teachers and grants) a signed MoU with the MoE has provided greater certainty.
- High operational costs (e.g., fuel) requires cost-saving measures, such as remote coaching via WhatsApp, consolidating travel logistics, and closely monitoring expenditures through monthly finance reports.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

EDGE is implemented by PEAS since 2021 and the BC since 2022, with a scheduled end date of April 2026. The programme is progressing according to the planned timelines.

Delivery

PEAS
PEAS supports schools in Zambia by expanding access to secondary education and improving educational outcomes for girls, especially in rural areas. This is achieved by increasing the number of secondary school places and enhancing teaching quality. PEAS has addressed recommendations from the previous EDGE Annual Review and has strengthened several internal operational policies this year.

Despite a challenging economic context PEAS has been able to operate within the allocated funds delivering all the planned programmes. This has been achieved through extensive financial management, effective negotiations during procurement processes and a focus on identifying cost-efficiencies during implementation (e.g. sharing vehicles for school support trips, holding training in PEAS schools, selecting cost-effective accommodation during trips).

During the year an internal PEAS audit spot check was undertaken. This raised some systemic gaps, and some areas of non-compliance on procurement, quality linked to construction (not structural, but on snagging issues and furniture), weaknesses in contract management, and oversight of consultants. PEAS are conducting further investigations, critically related to health and safety of learners, and have put in place a detailed response plan to address the issues identified.

The Accountable Grant with PEAS ends in April 2026. The programme is on course in terms of programme delivery timelines.

British Council
The British Council continues to provide technical support to Zambia’s Education Policy Reform, with a focus on expanding access to secondary education for vulnerable girls in a way that is effective, safe, and sustainable. Over the past year, BC has successfully acted on recommendations from the previous annual review, delivering planned activities within budget and with minimal changes to the original scope.

However, some activities faced delays or were removed from the workplan altogether. This was mainly due to misaligned timelines between the British Council and the MoE, which affected coordination and implementation of certain components.

Quality and Timeliness of Reporting

PEAS
PEAS consistently submits timely monthly and quarterly reports that integrate technical, financial (both forecasts and actuals), and administrative updates on programme progress and use of funds. During regular programme update meetings, PEAS also presents “spotlight” topics to share recent research, solicit feedback from FCDO, and provide comprehensive updates on project activities, risks, and financial performance.

This regular and structured reporting has helped PEAS to proactively address concerns and supports FCDO in effectively managing identified risks. The narrative and financial reports submitted quarterly allow FCDO to monitor progress, identify challenges, and assess emerging risks.

British Council
The content of British Council’s reports generally meets the required standards for accuracy and detail. There has been a notable improvement in the timeliness of report submissions since the last Annual Review. This has enhanced FCDO’s ability to assess project progress promptly and address arising issues more effectively.

Performance

FCDO
During the period under review, FCDO had a temporary deployment of education technical expertise which significantly strengthened the capacity of the new team, enabling the completion of key recommendations from the previous year.
In addition, the education expertise provided through the temporarily deployed Education Lead has contributed to improved internal capacity, enhanced support to the SCALE programme, and increased FCDO’s presence and engagement within the Education Cooperating Partners Group.

The programme is overseen by the SRO and PRO (the lead Social Development Adviser), supported by the temporarily deployed Education Lead and the Programme Officer, who manages day-to-day operations. Performance, finances, risks, and due diligence are reviewed in regular meetings with implementing partners. Internally, regular meetings and deep-dive sessions with the Team Leader are held to address outstanding issues. Updates are also shared across BHC Lusaka during office-wide Portfolio Steering Board meetings

PEAS
A due diligence assessment of PEAS was conducted in 2021, highlighting the need to adhere to internal control policies and update the child protection policy. These recommendations have been progressively implemented, leading to strengthened internal operational policies. In August 2024, a refreshed due diligence assessment was completed, identifying no major risks, although some ongoing recommendations will be tracked until the programme concludes.

Despite budget constraints and a challenging economic context, PEAS has delivered all planned objectives within its allocated budget through effective programme and financial management, with consistent consultations with FCDO.

British Council
The British Council’s implementation of the project began in June 2022 and is scheduled to conclude in 2025. The downstream partners include local and international consultants. Currently, the British Council is collaborating with a consultancy (CSK Consortium) to deliver on the safeguarding research and works with local consultants.

A due diligence assessment of the British Council was conducted in April 2022, and the recommendations have been largely implemented, although some are ongoing until the programme ends. Despite initial delays, this element of the programme is now aligned with its delivery schedule.

Financial Management

PEAS
PEAS has consistently submitted timely financial reports, with expenditure remaining within the variance limits specified by FCDO. During the reporting period, PEAS received a costed amendment to their accountable grant, which included an additional £950,000 in funding.

PEAS manages foreign exchange (FX) gains in accordance with FCDO’s ProF rules and the terms of the accountable grant agreement. The gains are reinvested into the project at the end of the financial year to offset any potential losses during the financial year. However, in the case of PEAS, exchange gains are ploughed back into the programme quarterly with approval from SRO because most programming activity was contracted in Kwacha and funds received from FCDO are transferred by PEAS to a local currency account to hedge against currency fluctuations and thus realizing the FX gains immediately. As a result, these gains are reinvested into the project within the same financial year.

British Council
Overall, the British Council demonstrated significant improvement in financial management and reporting during this reporting period. This progress is largely attributed to regular finance meetings held between the FCDO programme team and the British Council finance team. Similar engagement with PEAS also contributed to timely reporting and effective financial oversight.

Expenditure generally remained within the agreed variance limits. For any variances exceeding 10%, both partners provided advance commentary and raised issues proactively during monthly update meetings with FCDO.

The programme closed the year (October 2024 – September 2025) with total expenditure of £2,294,734, achieving 100% of the planned budget. Of this, 18% was directed towards the completion of two new PEAS schools and related expansion works, 59% covered staff costs including technical assistance to development diplomacy. Of the total spending in the past year, 23% is eligible as International Climate Finance (ICF), this is the CDEL funding (and some associated RDEL) for school construction.

Annual Expenditure Summary
Component	Annual Budget (GBP)	Actual Expenditure (GBP)
CDEL/Non-ICF (PEAS)	407,102	407,102
CDEL ICF (PEAS)	477,345	477,345
RDEL/Non-ICF (PEAS and British Council)	1,363,530	1,363,530
RDEL/ICF (PEAS)	46,757	46,757
Total	2,294,734	2,294,734

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Programme performance has been monitored regularly over the course of the reporting year. Internally, the FCDO team held monthly meetings to review progress and reported to the BHC Lusaka Programme Steering Board. Critical issues are discussed as they arise and escalated to the Development Director where appropriate (e.g., issues on gains from foreign exchange movements). The FCDO team also held monthly and quarterly progress meetings with PEAS and the British Council to review programme delivery, financial management, risk management, and to discuss progress made with implementing recommendations from Annual Review and due diligence assessments. British Council and PEAS held monthly joint meetings and submitted meeting meetings to FCDO. Both partners reported that these joint meetings have strengthened their coordination and facilitated joint learning.

To consolidate programme monitoring, staff from BHC Lusaka also undertook regular field trips throughout the year to engage with the EDGE partners in three provinces:
- In February 2025 two visits to Ndola in Copperbelt Province were undertaken. The first (by the Education Lead and the Programme Officer) visited PEAS network schools. The second (by the British High Commissioner and the Education Lead) also visited a PEAS school, and attended the British Council and HAZ orientation training for school leaders.
- At Chirundu, in Southern Province, FCDO participated in the groundbreaking ceremony (BHC Lusaka staff included the acting Development Director in September 2024,) and official opening of PEAS Pembele school (BHC Lusaka staff included the British High Commissioner in June 2025).
- Further, in July 2025 the Education Lead conducted a joint monitoring trip to one PEAS schools and three TIEEZ schools in the Southern Province to inform this Annual Review.
- Finally, BHC Lusaka’s new Development Director visited a PEAS school in Northern Province in August 2025.
This Annual Review was conducted by the Education Lead and Programme Officer, with oversight from the EDGE SRO and the Human Development Team Leader in BHC Lusaka. In addition to the field visits mentioned above, the Annual Review has been informed by interviews and discussions with: implementing partners, MoE officials – at HQ level (various directors and organisations), provincial level (e.g., provincial resource centre coordinators), and district level (officials from DEBS offices).

Further, monitoring and evaluation have been key to British Council’s flexible and responsive programming. During the review period, several activities were carried out to support learning and make timely adjustments. These included regular school visits by British Council staff and partners like Keeping Girls in School (KGS) in Kalumbila, Mushindamo, Chingola, and Luanshya Districts. Feedback sessions were also held with school leaders and teachers, in partnership with the Headmasters Association of Zambia.

In June 2025, an external evaluation of the British Council’s part of EDGE began, with data collection starting in July. The evaluation uses a mix of methods—document reviews, interviews, and school visits in seven provinces. The goal is to assess how relevant, effective, and sustainable the EDGE’s work has been, especially in building capacity, influencing policy, and promoting evidence-based decision-making within the Ministry of Education.

Evidence

British Council

The British Council work continues to generate and apply robust evidence to inform policy influence and strengthen programme implementation. Its learning outputs, research studies, monitoring data, and uptake metrics have been instrumental in identifying effective strategies for enhancing school leadership and safeguarding girls in secondary education.

A key milestone during the review period was the analysis of Output 3.5, which examined how the project supported tools and research have been adopted by the Ministry of Education and other stakeholders. The analysis found that provincial education planners in North-Western and Copperbelt Provinces have begun incorporating the project data into their quarterly planning meetings—an encouraging sign of early institutional uptake.

Additionally, the four research studies commissioned under Output 2—focusing on the Cost of Education, Non-Education Barriers, Safeguarding, and the Education Dashboard—were completed. These findings have informed both internal programming decisions and external engagement strategies, including revisions to the school leadership orientation toolkit.

PEAS

In 2024, PEAS drew valuable insights from the DevTech evaluation of the USAID-funded EduFinance programme, which focused on PEAS network schools and partner primary schools. The evaluation included a desk review of PEAS-collected data, student exam results, surveys with school leaders, and key informant interviews (KIIs) and focus group discussions (FGDs) with parents, teachers, Ministry of Education representatives, and project staff.

Findings from the school surveys indicated perceived improvements in teacher performance across lesson planning, delivery, assessment, and classroom management. The evaluation also concluded that the programme contributed to a safer learning environment through safeguarding training and the promotion of child rights awareness. Teachers and school leaders reported increased awareness of child protection among learners and community members. PEAS’ holistic approach was highlighted as a core strength, with the evaluation recognising the programme’s focus on multiple areas—school leadership, teaching, safeguarding, and community engagement—as key to its relevance and effectiveness.

In line with its commitment to continuous learning and evidence-based programming, PEAS Zambia is currently collaborating with independent evaluators on several studies, including:
- Endline evaluation in PEAS network schools (funded by the Sir Ernest Cassel Educational Trust);
- Baseline study for a quasi-experimental evaluation in partner primary and comparison schools (funded by the Hempel Foundation);
- Baseline study in PEAS network and comparison schools for a longitudinal alumni tracking study (funded by the Sir Ernest Cassel Educational Trust);
- Baseline for a quasi-experimental quantitative study in PEAS partner secondary and comparison schools (conducted and funded by the American Institute for Research (AIR), in partnership with PALM Associates);
- Formative qualitative study in partner secondary schools (conducted and funded by AIR, in collaboration with the University of Zambia).

Findings from these studies will be used to inform and strengthen PEAS programming across all intervention areas.

Learning

Learning has been continuously through regular meetings, field visits and studies such as the outcome harvesting workshop by British Council. Key lessons and recommendations have been captured in Section A of the review.

Date of last narrative financial report	PEAS: Y5Q1 Quarterly Report shared on 31/07/2025 / BC: Y4Q1 Quarterly Report shared on 30/07/25	Date of last audited annual statement	PEAS: 2024 annual audited accounts shared with FCDO on 20/07/2025 / BC: 2023/24 annual audited accounts shared with FCDO on 23/04/25.

 Asset Management

FCDO has actively monitored the asset registers of both the BC and PEAS. In August 2025, FCDO conducted an asset spot-check on the BC, confirming that the BC maintains an inventory of assets (above the £500 cost threshold, procured using FCDO funds) with clear records on location, condition, purchase value, and asset lifespan.

PEAS maintains an inventory of all its assets. During the annual spot check visit in May 2025, a physical verification was conducted for assets located at the two PEAS schools in Copperbelt Province and at the PEAS head office. Additionally, a virtual check was carried out for the remaining schools through their designated asset leads, confirming that all assets are in working condition.