## CIFPAK High Level Logframe
Please refer to the Guidance Notes tab for advice on completing the various fields in the logframe.
Please refer to the Results Framework Prof Guide for broader information on the logframe approach
Climate Investment Fund Pakistan Logframe
IMPACT | Impact Indicator 1 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date) | Assumptions
Increased climate resilience of Pakistan's economic development and low carbon growth pathway. | Climate finance investment as a share of GDP. | Planned | To be determined with MEL support. | CIFPAK MEL ToRs Finalised and Tender issued by April-25. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | To be determined with MEL support. | Assumes a stable macroeconomic environment for both investments and the wider operations of the programme, particularly noting the important of a MEL partner for baselining the programme's operations and analysing activity. Assumes it will be possible to discern how UK ODA has effected the wider market too. In the absence of MEL, other sources will be utilised, but measuring CIFPAK's impact may not be possible in the programme's first year(s).
Achieved
Source: MEL with inputs from delivery partners.
| Impact Indicator 2 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
| Volume of private climate finance (with % split of adaptation and mitigation) available in Pakistan. | Planned | To be determined with MEL support. | CIFPAK MEL ToRs Finalised and Tender issued by April-25. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | To be determined with MEL support.
Achieved
Source: MEL with inputs from delivery partners.
OUTCOME 1 | Outcome Indicator 1.1 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date) | Assumptions
Volume of public and private finance mobilised as a result of CIFPAK transactions. | Public and private mitigation finance mobilised (ICF 11 & 12). | Planned | Up to 1 investment committed within year one. | IFC pipeline development commenced, with 4-6 investments initially targeted including with climate resilient projects. With at least one potential investment tagged for adaptation and resilience. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Overall target of £420m mobilised by CIFPAK by the end of the programme (2031). | Assumes 1 investment made within the first few months of the programme's operation, due to the pre-existing IFC pipeline, but over time, for the programme to gradually move towards it's own, developed pipeline, in line with the adaptation targets.
Achieved
Source: IFC with MEL support.
| Outcome Indicator 1.2 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
| Public and private adaptation finance mobilised (ICF 11 & 12). | Planned | 0 - for year one. Any figures provided will be indicative and verified later in the programme lifecycle. | IFC pipeline development commenced, with 4-6 investments initially targeted including with climate resilient projects. With at least one potential investment tagged for adaptation and resilience. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Overall target of £420m mobilised by CIFPAK by the end of the programme (2031).
Achieved
Source: IFC with MEL support.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | [5 empty] | FCDO SHARE (%)
90m GBP
FCDO (FTEs)
4.75
OUTCOME 2 | Outcome Indicator 2.1 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date) | Assumptions
Number of people with improved climate resilience as a result of CIFPAK (ICF 4). | Jobs generated as a result of CIFPAK transactions (gender disaggregated). | Planned | 0 - CIFPAK investments or TA activity are not yet able to report at this time. Estimations may be provided. | Investment pipeline development commenced, with first investment made. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | 100K jobs created by the last year of programme. | Assumes CIFPAK projects and TA will be able to report. IFC will be able to estimate the total jobs created, including direct, indirect and induced jobs, at ex-ante. But at ex-post, we will only be able to report on direct jobs. For the AR, all figures for this outcome will be indicative.
|  | Achieved |  | 0
Source: MEL with inputs from IFC and BCG
| Outcome Indicator 2.2 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
| Number of people with improved climate resilience (gender disaggregated). | Planned direct beneficiaries | 0 - CIFPAK investments or TA activity are not yet able to report at this time. Estimations will be provided for the AR. | Delivery partner agreement to report on resilience aligned with ICF KPI 4. MEL to support baselining. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | 250K beneficiaries (direct and indirect) by the last year of programme. MEL to support baselining once procured.
|  | Achieved |  | 0
|  | Planned indirect beneficiaries | Source: IFC/delivery partners with MEL support.
|  |  | 0 - CIFPAK investments or TA activity are not yet able to report at this time. Estimations will be provided for the AR. | Delivery partner agreement to report on resilience aligned with ICF KPI 4. MEL to support baselining. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | 250K beneficiaries (direct and indirect) by the last year of programme. MEL to support baselining once procured.
|  | Achieved |  | 0
Source: IFC/delivery partners with MEL support.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | [5 empty] | FCDO SHARE (%)
108m GBP
INPUTS (HR) | FCDO (FTEs) 4
OUTCOME 3 | Outcome Indicator 3.1 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date) | Assumptions
Extent to which the CIFPAK intervention is likely to lead to transformational change (ICF 15). | Government of Pakistan (Federal and Provincial) and regulators report an increased capacity to deliver climate finance projects. | Planned | 0 - MEL partner needed to fully develop methodology, and subsequent assessment. | Key personnel for Federal Government intervention(s) and correct forums for engagement identified. Structures for engagement notified with government. MEL partner will finalise methodology once onboarded. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | To be determined (alongside methodology) for intervention with MEL partner. | Assumes "buy-in" and support from government and private sector for actions. Plus a stable environment for interventions to take place within.
Achieved
Source: BCG and IFC - MEL coordinating
| Outcome Indicator 3.2 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
| Investors (development and private finance) report that environment for climate finance investment and mobilisation has improved. | Planned | 0 - MEL partner needed to fully develop methodology, and subsequent assessment. | Key partners identified, and structures for engagement notified with relevant partner organisations. Correct forums for engagement identified. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Methodology for intervention to be finalised with MEL partner.
Achieved
Source: BCG and IFC - MEL coordinating.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | [5 empty] | FCDO SHARE (%)
35m
INPUTS (HR) | FCDO (FTEs)
OUTPUT 1 | Output Indicator 1.1 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date) | Assumptions
Adaptation Finance Mobilised through the blended finance facility (direct). | % of total volume of finance and % of total number of projects adaptation tagged (disaggregated by volume and number). | Planned: | 0 - for year one. | Investment pipeline development commenced, with initial investment made. At least one project identified to have resilience benefits (by IFC adaptation tagging standards). | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | 30% of total capital deployed will be for Adaptation and Resilience focussed projects. IFC will aim to achieve 50%. 50% of the number of projects will be adaptation and resilience focussed. | Assumes an economic environment where private investment is feasible. Also assumes a high level of additionality for CIFPAK investments that can be attributed to UK investments.
Achieved
Source: IFC
| Output Indicator 1.2 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
| Volume of public and private finance mobilised for adaptation purposes (disaggregated). | Planned: | 0 - for year one. | Investment pipeline development commenced, with initial investment made. At least one project identified to have resilience benefits (by IFC adaptation tagging standards). | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Overall aim to mobilise £420m of investment by conclusion of the programme (2031).
Achieved
IMPACT WEIGHTING (%) |  | Source: IFC
30%
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | [5 empty] | FCDO SHARE (%)
70m GBP
INPUTS (HR) | FCDO (FTEs)
OUTPUT 2 | Output Indicator 2.1 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date) | Assumptions
Mitigation Finance Mobilised through the blended finance facility (direct). | Tonnes of greenhouse gas emissions reduced or avoided due to CIFPAK. | Planned | 0 - in year one we do not expect to be able to accurately measure any emission reductions associated with CIFPAK. For any investments completed within this window, we will provide indicative numbers. | Delivery partner agreement to report on Greenhouse Gas Emissions reductions aligned with ICF KPI 6 when appropriate in reporting cycle. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | To be determined with support from the MEL partner and input from IFC and other delivery partners. | Assumes an economic environment where private investment is feasible. Also assumes a high level of additionality for CIFPAK investments that can be attributed to UK/CIFPAK finance, due to robust criteria for project selection. For capital market projects, assumes the private sector recognise the benefits of CIFPAK bond issuances (e.g. green or catastrophe). Lastly, for GHG emission reductions, assumes that private capital mobilised will go towards transformational projects that lower GHG emissions.
Achieved
Source: IFC (Climate Business Team) with MEL support.
| Output Indicator 2.2 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
| Volume of public and private finance mobilised for mitigation purposes (disaggregated). | Planned | 0 - in year one. We expect for project(s) to be invested in, but we are not able to provide a baseline. | Investment pipeline development commenced, with potential initial investment made. Innovative mitigation projects identified for potential future investment. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Overall aim to mobilise £420m of investment by conclusion of the programme (2031). Mitigation and adaptation respectively will be approximatelt £210m. This will be refined further with MEL support.
Achieved
Source: IFC (Climate Business Team) with MEL support.
IMPACT WEIGHTING (%) | Output Indicator 2.3 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
30% | Number of deals leading to an amount of FX savings. | Planned | 0 - this task will need to be completed with the support of a MEL provider. | Not able to assess this indicator at this point in the programme cycle. We will be collaborating with a MEL partner on this indicator at a future date. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Delivery partner agreement to report on resilience aligned with ICF KPI 4. MEL to support baselining.
Achieved
Source: IFC Blended Finance Team with MEL support.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | [5 empty] | FCDO SHARE (%)
70m GBP
INPUTS (HR) | FCDO (FTEs)
OUTPUT 3 | Output Indicator 3.1 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date) | Assumptions
Project Preparation (Advisory Facility), capital market development and inclusive finance practices. | Pipeline (No.) of projects supported and x% transitioned to investment/deal signing stage (disaggregated on type and sector). | Planned | 0 - for year one. | Number of projects at this stage is not applicable. But scoping for future pipeline commenced. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Overall aim to mobilise £420m of investment by conclusion of the programme (2031). Mitigation and adaptation respectively will be approximatelt £210m. This will likely be refined further with MEL support. | Assumes finance will be available for investments if projects are developed. Assumes also that firms are actively engaged in the advisory services' recommendations make relevant change, including to benefit marginalised groups/women.
Achieved
Source: IFC Advisory with MEL support.
IMPACT WEIGHTING (%) | Output Indicator 3.2 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
15 | 25% of blended finance projects supported by the Facility meet the IFC "Gender Flagging standard". | Planned | 0 - for year one. | Project pipeline development commenced, building gender tagging investment into the process for potential future investment. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | 25% of projects by meet IFC's Gender Tagging Standards.
Achieved
Source: IFC Advisory with MEL support.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | [5 empty] | FCDO SHARE (%)
20m
INPUTS (HR) | FCDO (FTEs)
OUTPUT 4 | Output Indicator 4.1 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date) | Assumptions
Technical Assistance Deployment, improvement in the enabling environment, and the wider climate finance ecosystem. | Market barriers identified and interventions held in response. | Planned | 0 - for year one. | Key barriers identified with the identification process commenced. Mitigation interventions commenced in close coordination with key stakeholders. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | To be agreed with MEL Partner support. | Assumes Government of Pakistan (and relevant other actors) recognise the importance of the regulatory and policy environment to catalyse private climate finance. Risks that TA support develops policies or regulation which has limited market wide impact.
Achieved
Source: IFC with MEL support
| Output Indicator 4.2 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
| BCG improves Federal Government capacity on climate risk visualisation and project prioritisation, building on past interventions. | Planned | 0 - for year one. | Influencing structure agreed with government. Risk visualisation tool design completed. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | By the end of the 2025/6 FY, BCG to have embedded the climate risk assessment tool into the Government of Pakistan's operations.
|  | Achieved | Deliver
IMPACT WEIGHTING (%) |  | Source: BCG reporting and FCDO exchange of letters.
15 | Output Indicator 4.3 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
| BCG improves Provincial Government capacity for climate risk visualisation and project prioritisation, building on past interventions. | Planned | 0 - for year one. | Project pipeline developed and private sector engagement commenced. Structure for supporting provinicial government notified. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | By the end of the 2025/6 FY, BCG to have successfully developed a series of bankable climate resilient projects in Sindh, alongside supporting the Sindhi administration in increasing it's capacity to improve Pakistan's climate reslience.
Achieved
Source: BCG reporting.
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | [5 empty] | FCDO SHARE (%)
35m
INPUTS (HR) | FCDO (FTEs)
OUTPUT 5 | Output Indicator 5.1 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date) | Assumptions
Monitoring Evaluation and Learning | Number of evidence and learning products generated and disseminated (disaggregated by topic especially gender and climate adaptation) | Planned | Tendering for, then securing a MEL partner and beginning the baselining process. | CIFPAK MEL ToRs Finalised and Tender issued by April-25. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | TBD with MEL once fully procured. | Assumes environment for procuring a MEL partner remained stable, with few internal or external changes to disrupt this.
Achieved
Source: MEL
IMPACT WEIGHTING (%) | Output Indicator 5.2 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
10% | Evidence of effective collaboration between CIFPAK implementing partners including effective use of data and evidence to improve delivery and knowledge sharing. | Planned | Tendering for, then securing a MEL partner and beginning the baselining process. | CIFPAK MEL ToRs Finalised and Tender issued by April-25. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | TBD with MEL once fully procured.
Achieved
Source: MEL
| Output indicator 5.3 |  | Baseline | Milestone 1 (March 2025) | Milestone 2 (March 2026) | Milestone 3 (March 2027) | Milestone 4 (March 2028) | Milestone 5 (March 2029) | Milestone 6 (March 2030) | Milestone 7 (March 2031) | Target (date)
| Frequency and quality of engagement with the international community and relevant global initiatives (e.g. the Adaptation and Resilience Investors Collaborative) to standardise international best practices and validate CIFPAK approaches. | Planned | Tendering for, then securing a MEL partner and beginning the baselining process. | CIFPAK MEL ToRs Finalised and Tender issued by April-25. | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | Needs to be completed | TBD with MEL once fully procured.
Achieved
Source: MEL
INPUTS (£) | FCDO (£) |  | Govt (£) | Other (£) | Total (£) | [5 empty] | FCDO SHARE (%)
3m GBP
INPUTS (HR) | FCDO (FTEs)

## Change frame
Use this change log to record all changes to the logframe over the life of the project.
ID | LOGFRAME SECTION | DETAILS OF CHANGE | AUTHOR | DATE
E.g. | Output 1, Indictor 2 | Indicator amended from 'No of children enrolled in primary schools' to 'Number of children enrolled in UNICEF supported primary schools (disagregated by sex) | Joe Bloggs | 2022-01-01
1
2
3
4
5
6
7
8
9
10

## Guidance Notes
Logframe Template Guide
Teams should use the guide below to complete the logframe template.
PROJECT TITLE
The name of the programme to which this logframe applies, from the business case
IMPACT
Long term goal to which the project will contribute towards achieving. When drafting the impact statement, consider how your project fits with other efforts from FCDO and partners to achieve the impact, ie is your project nested within a broader undertaking? This will often be the Impact indicator from the Theory of Change in the Business Case.
OUTCOME
The outcome should link through to the outcome level in the programme Theory of Change as stated in the Business Case. The outcome of your project identifies what will change, who will benefit and how it will contribute to reducing poverty, including contributions to the Sustainable Development Goals (SDGs) or Climate Change.
Ongoing monitoring of progress against outcome milestones takes place as an assessment of whether you expect to achieve the Outcome by the end of the programme in the programme Annual Reviews. An assessment of whether your project achieved the Outcome will be included in the Project Completion Review (PCR) based on the target milestone for the programme completion.
OUTPUTS
Outputs are the specific, direct deliverables of your project. These will provide the conditions necessary to achieve the Outcome. The logic of the chain from Output to Outcome therefore needs to be clear. Outputs should reflect the Theory of Change as set out in the Business Case for the programme.
Progress towards the outputs will be assessed and scored at the Annual Review, using output indicators and milestones. Achievement of the outputs will be assessed at project completion, using output indicators and targets.
IMPACT WEIGHTING
Once you have defined your Outputs, assign a percentage for the contribution each is likely to make towards the achievement of the overall Outcome.
The impact weights of all the Outputs will total 100% and each are rounded to the nearest 5%.
Impact weightings for Outputs are intended to:
1. Promote a more considered approach to the choice of Outputs at project design stage; and
2. Provide a clearer link to how Output performance relates to project Outcome performance.
INPUTS
Clarification of inputs is a key part of results-chain thinking. Inputs are specified at the country-level in country operational plans and the project information contained in logframes should feed up into these.
The input-level boxes show the amount of money provided by FCDO and any partners (£) including, where relevant, the government’s own contribution. This only relates to monetary (not in kind) contributions. At Outcome level this is equal to the sum of Inputs for all Outputs. The FCDO share at Outcome Level is a simple, pro rata calculation of FCDO’s contribution in monetary terms for all outputs.
Information should also be provided for the total number of Annual FCDO Full-Time Equivalents (FTEs) allocated to this project, based on the time individual staff members will spend on the project. It is understood that this may change through the project cycle, and is intended as a management tool.
INDICATORS
Indicators are performance measures, which tell us what will be measured not what is to be achieved. Avoid including elements of the baseline or target.
What makes a good indicator?
Specific – what will be measured? And how?
Measurable - data can be collected
Relevant - to the results chain
Useful – for management decision making
Does not include any element of the target
Can be disaggregated if relevant (especially when the indicator relates to number of beneficiaries reached with an intervention)
A mix of qualitative and quantitative
Already defined - if relevant include indicators which towards the FCDO Outcome Delivery Plan / ICF KPIs / SDGs.
Consider using standard indicators / best practice indicators / learning from other projects
The basic principle is that “if you can measure it, you can manage it”.
Top Tip – select indicators based on relevance to the Theory of Change and the availability of data.
Best Practice suggests a maximum of three Indicators per Output.
Some example indicators for a WASH project are shown below.
BASELINE
Baselines set the starting point and provide a measure of the situation before your project starts (could be zero if a new project).
The baseline is used to measure change and monitor progress.
Include a baseline for each of your indicators. The first 6 months of a project may exceptionally be used for assembling baseline data at output level if agreed by your PRO.
Use existing data where possible, but check reliability and seek assurances regarding the data quality eg use data from national statistical systems / Management Information Systems.
If you need to collect your own data - collect baseline data early – as soon as beneficiaries have been identified but before any results are expected.
MILESTONES
Milestones are the desired trajectory from baseline to target, helping you to track progress and make changes to underperforming areas.
Will depend on sequencing of activities and data availability.
Include REALISTIC milestones given resources and capacity.
At the output level include annual milestones for each year of the project (or monthly if short term). At outcome & impact level data may not be available annually and you should record the expected frequency of data availability.
TARGET (DATE)
Targets set the desired point, showing what is achievable within the timeframe available.
The target is often the last year of the project (or month if its short term).
Include realistic targets given resources and capacity, the baseline situation, funding available and country/operational context. Project targets might be informed by evidence about what has worked in the past and take into account lessons learned from other projects.
Include targets dissaggregated by sex/geography/income etc where appropriate.
Consider using government targets although if they are too ambitious then make a more realistic estimate.
Top Tip - A good Theory of Change will help you think about what is realistic and achievable as it will enable critical reflection of context, external influences & assumptions.
SOURCE
Each Indicator will have a data source to verify the results achieved.
List the specific data sources i.e. give the specific data collection e.g. named survey / report and avoid just naming the organisation.
State the frequency of the data source and ensure consistency with milestones and targets.
Check the source can provide disaggregated data as required.
Consider and specify the data collection and reporting responsibilities to ensure the results planned and forecast rows in the logframe are updated on a regular basis.
Top Tip - Before using a data source, assess its quality and seek assurances from data providers where needed ie consider its validity, reliability and availability. Use the Data Quality Prof Guide to help you consider the quality of your data.
ASSUMPTIONS
Define any assumptions which are linked to the realisation of your project's individual outputs, as well as those which are critical to the realisation of the outcome and impact: these will not all be the same. If you are carrying out any evidence gathering to check your assumptions then make reference to this as part of this section.
VALUE FOR MONEY
Ensure the outputs and outcome projected represent good value for the invested resources, at the beginning of the project, and through its life.
Consider including VfM metrics in the logframe (or other documents such as the Delivery Plan) to allow VfM to be measured through the life of the project and to provide assurance at Annual Review.
VfM is achieved at different stages of the results chain. Thus for each result we seek to achieve we should aim to have metrics for each of the following:
Economy - Are we (or our agents) buying inputs of the appropriate quality at the right price?
Efficiency - How well are we (or our agents) converting inputs into outputs? (‘Spending well’)
Effectiveness - How well are the outputs produced by an intervention having the intended effect? (‘Spending wisely’)
Cost-effectiveness - What is the intervention’s ultimate impact on poverty reduction, relative to the inputs that we or our agents invest in it?
Equity - Is the intervention meeting the needs of all beneficiaries?
FCDO’s Approach to Value for Money (PrOF Guide) provides further advice on ensuring VfM.