## CIFPAK Annual Review 2025
(Review Period: November 2024 – March 2025)

Title: Climate Investment Fund Pakistan (CIFPAK)
Programme Value £ (full life): £108m		Review date: / 12/10/2025
Programme Code : 301242	AMP start date: / 01/08/2024	AMP end date: / 31/03/2031

Summary of Programme Performance

Year	2025
Overall Output Score	A
Risk Rating	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-301242/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-301242/documents

A. SUMMARY AND OVERVIEW

Description of programme

Pakistan ranks among the most climate vulnerable countries worldwide. With increasing temperatures, Pakistan has already experienced an increase in the frequency and intensity of extreme climate events such as floods, droughts, cyclones, heavy rain spells, extremely high temperatures etc. As the climate changes, the number of people affected by flooding in Pakistan is projected to increase, with a likely increase of around 5 million people exposed to extreme river floods by 2035–2044, and a potential increase of around 1 million annually exposed to coastal flooding by 2070–2100. Pakistan faces a $348 billion gap in adaptation financing by 2030. This means that crowding investment from the private sector for climate action is essential.

CIFPAK (2024-2031) is a £108m UK-funded initiative implemented by IFC and through the Centres of Expertise to mobilise private investment in climate adaptation and resilience in Pakistan. It combines blended finance with technical assistance (TA) to develop bankable projects, strengthen regulatory frameworks, and build institutional capacity. Overall, the programme aims to mobilise £420m of climate finance in Pakistan.

CIFPAK has four components. This AR focuses on the mobilisation and early-stage implementation of the programme.

CIFPAK will:
  1. Mobilise investment towards climate adaptation and mitigation. CIFPAK uses blended finance to de-risk investments and attract private capital into climate-vulnerable sectors. It aims to crowd in both domestic and international investors by offering concessional support alongside IFC’s own financing.
  2. Develop a pipeline of bankable climate resilient projects through technical assistance, particularly in sectors like agribusiness, water, and sustainable infrastructure that are tagged for climate adaptation. This includes feasibility studies, climate risk assessments, and project documentation. Many of these projects will go on to receive investment from the blended finance component.
  3. Strengthen regulatory and policy framework reforms to enable climate finance, including the development of green taxonomies, ESG standards, and climate risk disclosure frameworks.
  4. Build institutional capacity for climate risk management, providing tools, training, and advisory support to financial institutions and regulators to assess and manage climate-related risks. This includes integrating climate risk into financial supervision, portfolio management, and investment decision-making.
  5. Embed gender positive approaches, including in investment structures and helps companies implement Environmental Social and Governance (ESG) action plans.

In response to the reduction in UK ODA to 0.3%, we adopted a rigorous approach to ensure all ODA programming aligns with UK government priorities and responds to Pakistan’s evolving development context. This approach also reflects the UK’s comparative advantage, enabling a shift towards a more rationalised and coherent portfolio that maximises impact for the most vulnerable communities we aim to support.

As implementation continues, FCDO is using this shift to refine a forward-looking plan for CIFPAK’s technical assistance (TA). This includes consolidating TA delivery, deepening partnerships with Pakistani institutions, prioritising private sector mobilisation, and sharpening the programme’s theory of change. We acknowledge that the Boston Consulting Group (BCG) led TA has faced challenges, particularly around limited in-country demand and presence. These lessons are informing our thinking on how future TA will be structured across the portfolio to ensure relevance, responsiveness, and sustainability.
Summary narrative for the review’s score
This review focuses exclusively on the programme’s first four months of implementation, from November 2024 to March 2025. Initially scheduled for completion in June, the review was formally postponed to October following due approvals however, logical framework and review period wasn’t feasible to be extended over this extended period. The delay was necessitated by the India/Pakistan Pahalgam Crisis, which disrupted regional operations, and by the strategic need to align the review with the reporting timelines of the programme’s primary delivery partner, the IFC. This revised schedule ensures a more coherent and contextually informed assessment of early progress and operational foundations.

In the review period, CIFPAK made significant strides towards successful mobilisation and transition from inception to implementation. The Blended Finance (BF) facility made its first investment, the project development pipeline commenced, and Component 3s TA began implementation, with the structures for this influencing set up.

Summary supporting narrative for the overall score in this review
In its first year of implementation, CIFPAK demonstrated early momentum across its core components, blended finance, technical assistance, and enabling environmental reforms. The programme successfully mobilised its first investment, unlocking over $115m in climate finance with just $10m of concessional support. This transaction, into SAFCO (Sustainable Aviation Fuel), embeds both adaptation and gender-responsive features, validating CIFPAK’s blended finance model and setting a precedent for future investments. Technical assistance interventions have also commenced, with IFC launching advisory engagements in green buildings, geothermal energy, and infrastructure resilience, each contributing to a growing pipeline of investable climate projects.

Despite the absence of a MEL partner during the review period, foundational steps were taken to prepare for its onboarding, including the finalisation of ToRs and procurement approval. Coordination between delivery partners has improved, with joint planning underway to align upstream reforms with downstream investment readiness. Three outputs Adaptation Finance Mobilised, Mitigation Finance Mobilised, and Project Preparation—scored an A, reflecting strong delivery against early milestones and strategic alignment with CIFPAK’s theory of change. While Output 5 (MEL) scored a B due to procurement delays, the programme remains well-positioned to build robust evidence base and validate its delivery trajectory. CIFPAK’s strategic relevance, early successes, and adaptive management approach justify an overall score of A.
Major lessons and recommendations for the year ahead
CIFPAK’s blended finance and de-risking model works. The SAFCO investment demonstrates CIFPAK’s ability to mobilise significant private capital for climate mitigation and adaptation. It validates the programme’s blended finance approach and sets a precedent for future investments that embed resilience and gender inclusion.

But Technical Assistance (TA) must be sharply aligned with investment mandates[1]. While advisory activities have begun across multiple sectors, some risk being too broad or mitigation focused. To maximise impact, TA must be more explicitly targeted toward preparing adaptation investment-ready projects, especially in sectors prioritised by the programme’s business case.
[1] The programme team’s approach to future TA is being shaped by the strategic direction set out in the Spring 2025 CIFPAK TA Strategy, which emphasises locally led, resilience-focused interventions that prioritise adaptation finance, or climate resilience focussed reforms. At the same time, contemporary events, particularly recurring floods and the growing urgency around disaster risk finance are reinforcing the need for scalable, replicable models that can attract blended finance and deliver tangible development outcomes. These factors are guiding our approach to future TA, with a focus on provincial-level capacity, financial innovation, and deeper engagement with public and private stakeholders.

Monitoring Evaluation and Learning (MEL) will be crucial for the programme’s long-term success. The lack of a dedicated MEL partner during the review period constrained CIFPAK’s ability to baseline activities, track progress, and generate evidence. Rapid onboarding and operationalisation of MEL is essential to validate delivery and support adaptive management.

ODA Cuts Require Strategic Prioritisation but not a structural overhaul. The reduction in UK ODA has not derailed CIFPAK, but it has introduced a need for more prioritisation. The programme’s pre-existing alignment with UK strategic objectives is a strength, but delivery must now focus on high-impact sectors and ensure coherence across components to maintain momentum under constrained resources.

Partner coordination is improving, but work is still needed. Initial collaboration between IFC, FCDO, and BCG is promising, particularly in aligning enabling environment reforms with project-level delivery. However, formal mechanisms for joint planning, learning, and reporting are needed to ensure strategic alignment and coherence across the programme.

Governance structures must be clarified and strengthened. IFC proposed that the Climate Finance Working Group be used to steer CIFPAK’s strategic direction. While this offers a useful platform, its effectiveness will depend on IFC’s active and consistent engagement. If this cannot be guaranteed by December 2025, a dedicated governance structure, such as a programme steering committee, should be established by March 2026 to ensure strategic oversight, partner accountability, and alignment with UK ODA priorities.

1. Major recommendations for the programme include:
  1. Secure and operationalise the MEL partner. CIFPAK must rapidly onboard its Monitoring, Evaluation, and Learning partner at latest by Jan-2026 to enable baselining, performance tracking, and evidence generation. This will be essential to validate delivery, support adaptive management, and ensure coherence across programme components. Owner: CIFPAK SRO and PRO.
  2. Closer align technical assistance with investment goals outlined in the administration agreements. IFC’s advisory work should be more tightly focused on preparing investment-ready projects for the blended finance facility. Broad sectoral TA should be deprioritised with a final cut-off date of March-2026 unless clear adaptation co-benefits are demonstrated, and joint planning between FCDO and IFC should be strengthened. Owner: CIFPAK SRO and Advisors in Coordination with all CIFPAK Implementing Partners.
  3. Strengthen adaptation focus and sector prioritisation. CIFPAK should ensure investments are clearly focused on adaptation and resilience, prioritising sectors such as agribusiness, water, and sustainable infrastructure. FCDO and IFC should jointly review how adaptation is defined and tracked to maintain clarity and coherence at latest by December-2025. Owner: CIFPAK Advisor and IFC.
  4. Promote inclusive and gender-responsive investments. All CIFPAK investments should embed gender and inclusion, with delivery partners supporting companies to implement gender-smart policies. Owner: CIFPAK Advisor and IFC.
  5. Improve value for money reporting. IFC and BCG should submit semi-annual VfM assessments reports aligned with programme outputs and cost-effectiveness indicators. This will improve transparency, support accountability, and strengthen the evidence base for future investment decisions. Owner: CIFPAK Team with all CIFPAK Implementing Partners.
  6. Enhance partner presence and coordination. BCG should establish a more consistent in-country presence to improve stakeholder engagement, responsiveness and sustainability of programme reforms. Joint planning and reporting mechanisms across delivery partners should be formalised to ensure coherence and accountability. If BCG are unable to be present themselves, they must meaningfully work through their local partner (Adam Smith International) to ensure this gap is covered suitably. Owner: Respective CIFPAK Advisors and BCG.
  7. Strengthen communications and visibility. CIFPAK should develop a proactive communications strategy by December 2025 to highlight its activities, investments, and achievements. Regular updates, press releases, and stakeholder briefings will help build awareness and position the programme within the global climate finance landscape. Owner: CIFPAK Team with all CIFPAK Implementing Partners.
  8. Strengthen programme governance. Effectively utilise the Climate Finance Working Group to ensure progress and robust contextualising of CIFPAK activity. If necessary, create a programme advisory panel or steering group at latest by March 2026. Owner: CIFPAK Advisor and IFC.

## A 1: List of Acronym
A&R	Adaptation and Resilience
AAs	Administrative Agreement
ADB	Asian Development Bank
AMP	Aid Management Platform
AR	Annual Review
ASI	Adam Smith International
BC	Business Case
BCG	Boston Consulting Group
BFF	Blended Finance Facility
BHC	British High Commission Islamabad
BTEPL	Bio Techn Energy Pte Limited
BVI	British Virgin Islands
CDEL	Capital Delivery
CIAP	Climate Impact Assessment Portal
CMP	Centrally Managed Programme
CO2	Carbon Dioxide
CoE	Centre of Expertise
COI	Cost of Inaction
DC	District of Columbia
DDA	Due Diligence Assessment
DFI	Development Finance Institutions
DFW	Department of Forestry and Wildlife
DoA	Department of Agriculture
DoI	Department of Irrigation
DoL	Department of Livestock
EAD	External Assistance Department
ESG	Environmental Social and Governance
EV	Electric Vehicle
FCDO	Foreign Commonwealth and Development Office
FX	Foreign Exchange
FY	Financial Year
GCISC	Global Change Impact Studies Centre
GG	Growth Gateway
GHG	Green House Gases
GIZ	Deutsche Gesellschaft für Internationale Zusammenarbeit
HEO	Head Executive Officer
ICF	International Climate Fund
IFC	International Finance Corporation
INT	Integrity Vice Presidency
IPs	Implementing Partners
KPI	Key Performance Indicator
MEL	Monitoring, Evaluation and Learning
MoCC	Ministry of Climate Change
MoF	Ministry of Finance
NAPs	National Adaptation Plans
NDC	National Determined Contributions
NDMRF	National Disaster Risk Management Fund
ODA	Official Development Assistance
PAC	Public Accounts Committee
PC	Planning Commission
PCD	Procurement and Commercial Department
PN	Promissory Note
PPP	Public Private Partnership
PRO	Programme Responsible Officer
PrOF	Programme Operating Framework
QPRs	Quarterly Progress Reports
RDEL	Resource Delivery
RISE MEPA	Resilience, Inclusion, Sustainability, and Empowerment in the Middle East, Pakistan, and Afghanistan
SAB	Sindh Abadgar Board
SAF	Sustainable Aviation Fuel
SAFCO	Sustainable Aviation Fuel Company
SMEs	Small Medium Enterprises
SRO	Senior Responsible Officer
TA	Technical Assistance
TCFD	Task Force on Climate-related Financial Disclosures
ToC	Theory of Change
ToRs	Terms of References
TWG	Technical Working Group
VfM	Value for Money
WBG	World Bank Group

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

CIFPAK is designed to catalyse transformational change in Pakistan’s climate finance landscape by mobilising private and development finance for climate mitigation and adaptation. The programme addresses systemic barriers, such as a weak pipeline of investable projects, underdeveloped capital markets, and policy and regulatory gaps, through a dual approach: a blended finance facility and targeted technical assistance.

The theory of change assumes that by de-risking high-impact, frontier climate investments (particularly in adaptation), and by strengthening the enabling environment, CIFPAK will unlock significant volumes of private capital. This will be achieved through concessional finance, project preparation support, and capital market development, alongside policy reform and institutional capacity building.

CIFPAK’s outputs include increased volumes of climate finance mobilised, improved ESG and gender standards in investments, and enhanced government and investor capacity. These are expected to lead to outcomes such as a more resilient financial ecosystem, increased access to green finance, and improved livelihoods for vulnerable populations. The ultimate impact is a more climate-resilient, inclusive, and low-carbon growth pathway for Pakistan, aligned with its National Adaptation Plan and 2030 climate goals.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

CIFPAK remains broadly on track with its foundational activities, showing encouraging early signs of progress toward intended outcomes. Given the limited mobilisation and implementation window of just five months, the programme’s milestones have understandably focused more on establishing key processes than delivering measurable, sustainable impact at this stage. Nonetheless, critical outputs including the mobilisation of initial investments, the development of the IFC pipeline, and the launch of early technical assistance have been successfully initiated. These achievements have laid the groundwork for meaningful progress toward the programme’s core outcomes, particularly Outcomes 1 and 2, which are now advancing with promising momentum

Many indicators are not yet baselined; we also note that the methodology for Outcome 3 (transformational change) will need to be developed. This is reflective of the programme’s need to successfully onboard a MEL partner. See table below for progress against key outcome indicators:

Outcome Indicator	Milestone	Progress
Indicator 1.1: / Public finance mobilised for climate change purposes (ICF 11).	IFC pipeline development commenced, with 4-6 investments initially targeted including with climate resilient projects. With at least one potential investment tagged for adaptation and resilience.	IFC has developed a pipeline of over 6 investment opportunities under CIFPAK, including at least one adaptation and resilience-tagged project. / One investment, into the sustainable aviation fuel company SAFCO, has been committed to, marking early progress in mobilising climate finance, with up to c. $115m being mobilised from CIFPAK’s $10m. / Score: A (Outcome Indicator Met Expectations)
Indicator 1.2: / Private finance mobilised for climate change purposes (ICF 12).
Indicator 2.1: / Jobs generated as a result of CIFPAK transactions (gender disaggregated).	Investment pipeline development commenced, with first investment made.	This milestone has been achieved, demonstrated through the SAFCO investment announcement. SAFCO is expected to create 200 jobs, with the developer working with the IFC to ensure an amount of these are allocated for women. / Score: A (Outcome Indicator Met Expectations)
Indicator 2.2: / Number of people with improved climate resilience (gender disaggregated).	Delivery partner agreement to report on resilience aligned with ICF KPI 4. MEL to support baselining.	Delivery partners agreed to report on ICF KPI 4. MEL procurement postponed initially due to ODA/commercial pause and lately due to HR constraints. / Score: B (Outcome Indicator moderately did not meet Expectations)
Indicator 3.1: / Government of Pakistan (Federal and Provincial) and regulators report an increased capacity to deliver climate finance projects.	Key personnel for Federal Government intervention(s) and correct forums for engagement identified. / Structures for engagement notified with government. MEL partner will finalise methodology once onboarded.	Key personnel successfully identified, with forums successfully commenced. / Federal Adaptation and Resilience Technical Working Group agreed with the Government. One meeting held. However, overarching programme governance forum remains under review for finalisation during MEL component inception phase. / Score: B (Outcome Indicator moderately did not meet Expectations)
Indicator 3.2 / Investors (development and private finance) report that environment for climate finance investment and mobilisation has improved.	Key partners identified, and structures for engagement notified with relevant partner organisations. Correct forums for engagement identified.	Key personnel successfully identified, with forums successfully commenced. / Sindh Adaptation and Resilience Technical Working Group agreed with the Government of Sindh. Two meetings held. / Score: A (Outcome Indicator Met Expectations)

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on current progress and the programme’s strategic relevance, CIFPAK should continue. While the programme has not yet reported full progress on climate finance mobilisation or resilience outcomes, early engagement with government and private sector stakeholders has laid the groundwork for future delivery. CIFPAK addresses a critical gap in Pakistan’s climate finance ecosystem and is one of the few UK-funded initiatives explicitly focused on mobilising private capital for both mitigation and adaptation. Indeed, it is a prototype in both the FCDO and World Bank networks. The successful start for the blended finance facility and IFC led components generally position the programme well in the longer term for its outcomes. For the demand led- technical assistance workstream, it is showing signs of early ownership and buy-in from the government and has the potential for more sustainable achievements.

While early delivery has faced some operational challenges and delays, some outside of the programme team’s control, there is strong evidence that the programme’s early activities align with its theory of change and initially represent good value for money.

Its blended finance model, technical assistance, and policy engagement are well-positioned to deliver systemic impact, provided implementation accelerates, and is more specifically targeted. Within the wider FCDO and departmental portfolio, CIFPAK contributes directly to climate resilience, inclusive economic growth, and gender-responsive development: priorities under the UK’s International Development Strategy and Pakistan’s Country Business Plan. While restructuring is not currently warranted, enhanced programme management, clearer accountability for delivery partners, and strengthened MEL systems will be essential to ensure that outputs translate into outcomes and impact within the planned timeframe and budget. Outside of the programme itself, further integration with Goal 4 – Climate and Humanitarian portfolio will also help CIFPAK to navigate the ODA changes.

Programme management has remained compliant and generally effective, despite some disruption caused by personnel changes and occasional inconsistencies towards internal processes (such as documentation and reporting). These issues have not compromised delivery but have, at times, affected continuity and slowed operational efficiency. Going forwards, CIFPAK requires consistency with both personnel, and robust programme management.

In the year ahead, CIFPAK will finalise MEL procurement, deepen pipeline development, and initiate further targeted technical assistance. These steps are essential to course-correct and ensure outcomes, such as £420m mobilised and 250,000 people with improved resilience, remain achievable within the current timeframe and adjusted ODA environment.

## C. DETAILED OUTPUT SCORING

Output Title	Adaptation Finance Mobilised
Output number:		1	Output Score:	A
Impact weighting (%):		30	Weighting revised since last AR?	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.
Indicator(s)	Milestone(s) for this review	Progress
% of total volume of finance and % of total number of projects adaptation tagged (disaggregated by volume and number).	Investment pipeline development commenced, with initial investment made. At least one project identified to have resilience benefits (by IFC adaptation tagging standards).	IFC Blended Finance (BF) team have already commenced sifting projects for investment. Some, from an existing Pakistan pipeline, but teams across project development, Islamabad based colleagues, and DC teams have working relationships, with FCDO being regularly informed. / The SAFCO investment also will contain resilience benefits. / Score: A (Output Indicator Met Expectations)
Volume of public and private finance mobilised for adaptation purposes (disaggregated).		Successful investment made (SAFCO) and incorporates resilience benefits. / Pipeline for further investments exceeds the available capital, with multiple potential projects having Adaptation and Resilience potential. / Score: A (Output Indicator Met Expectations)

Output 1 tracks the mobilisation of adaptation finance through CIFPAK’s IFC-managed blended finance facility by de-risking investments in sectors such as agriculture, disaster risk financing, and climate-resilient infrastructure. This finance will also support innovative solutions, such as nature-based approaches, invest inclusively. FCDO and IFC have committed to ensuring that at least 50% of projects are focused on adaptation and resilience (A&R). In this first year, Output 1 primarily reflects the early implementation of the facility, with investment pipeline development and sifting commenced, and initial investment made during the review period. Based on this, the output warrants an “A” rating.

1. At this implementation stage for CIFPAK, early success was most clearly demonstrated by the Sustainable Aviation Fuel Company Investment[2] (SAFCO). The project’s inclusion and resilience key points are detailed below:
  [2] Detailed in Output 2 too.
  1. The SAFCO Project contributes to climate adaptation by integrating water reuse and climate risk management into its operations. Located in a region prone to heatwaves, droughts, and flooding, the project includes a wastewater treatment and reuse system to address water scarcity. The company has implemented climate risk mitigation measures across its value chain and committed to incorporating climate projections and scenarios into its risk assessments. These steps align the project with the adaptation and resilience goals of the Paris Agreement and demonstrate how industrial investments can be designed to withstand and respond to climate hazards.
  2. The SAFCO Project also demonstrates IFCs commitment to gender inclusion. In a sector and location where female participation is traditionally low, the Company has set ambitious targets to increase women’s employment from 0% to up to 25% over the life of the IFC investment. To support this, SAFCO has adopted Equal Employment Opportunity and Respectful Workplace policies and is exploring gender-smart solutions such as remote and hybrid work options for administrative roles. IFC is also considering a gender advisory engagement to help build the Company’s capacity for inclusive hiring and workplace practices. These efforts align with the WBG Gender Strategy (FY24–30) and aim to address Pakistan’s acute gender gap in manufacturing, where female workforce participation stands at just 14%.

Cumulatively, these factors demonstrate how the SAFCO investment marks an early success for the programme. Proving the concept behind CIFPAK demonstrating its ability to mobilise capital into high-impact, climate-tagged projects in a challenging market. The investment validates CIFPAK’s blended finance model, catalyses private sector engagement in climate innovation, and sets a precedent for future adaptation and mitigation investments in Pakistan.

In terms of project development[3] enabling eventual mobilisation of capital for adaptation, the link between the development and investment teams is becoming clearer. CIFPAK has successfully initiated several adaptation-focused advisory engagements that laid the foundation for a robust investment pipeline. These early-stage efforts demonstrate CIFPAK’s ability to identify and de-risk adaptation opportunities, positioning the programme to mobilise capital into climate-resilient sectors.
[3] Detailed more thoroughly in Output 3.

Lastly, the evolving relationship between IFC and FCDO has been characterised by its openness. Highlight in monthly meetings between FCDO and IFC, where consensus enables the steering of the direction of CIFPAK, with the pipeline openly discussed. This has enabled the programme team to better understand the direction of the facility.
Describe any changes to this output during the past year, and any planned changes as a result of this review

There have been no changes to this output relative to the CIFPAK business case and overall objectives. CIFPAK team extensively engaged with the IFC in finalising the Logframe, accentuated by the lack of a MEL partner for this year. This review has highlighted the similarities between Outputs 1 and 2, as such, from this review FCDO will explore merging Outputs 1 and 2 to make future reviews shorter and more focussed.

Being the first review, CIFPAK has no recommendations to address. However, the following recommendations have been developed for the adaptation aims of the blended finance component.
Recommendation and Suggested Owner
Further prioritise pipeline development in high-risk sectors outlined in the CIFPAK administration agreement. Particularly noting agriculture, water, urban infrastructure to maximise adaptation impact. Owner: IFC – Blended Finance Facility Team
Clarify and align IFC’s adaptation tagging system with the UK ICF methodology, ensuring consistent categorisation of CIFPAK investments into Adaptation & Resilience (A&R), Mitigation, and Mixed. This should include joint technical workshops, development of a shared tagging framework, and agreement on reporting metrics. Owner: IFC & CIFPAK Technical Adviser and Programme Manager.
Expand outreach to private sector actors, especially Small Medium Enterprises (SMEs) and developers, through targeted advisory and concessional finance tools. Where this is already being done, clarity on the narrative, actions taken, and results. Owner: IFC (MEL partner to support once procured)
Promote Public Private Partnerships (PPP) models for adaptation and resilience investments, especially in infrastructure, by working with state actors to identify bankable opportunities and enable policy frameworks. IFC should lead technical structuring and transaction support, while FCDO facilitates government engagement and policy dialogue. Owner: IFC & CIFPAK Technical Advisers
Secure a MEL partner and develop learning partnerships to generate evidence on effective means to mobilise the private sector for adaptation and support the overall programme narrative. Owner: CIFPAK SRO and PRO.

Output Title	Mitigation Finance Mobilised (Direct)
Output number:		2	Output Score:	B
Impact weighting (%):		30	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Tonnes of greenhouse gas emissions reduced or avoided due to CIFPAK.	Delivery partner agreement to report on Greenhouse Gas Emissions reductions aligned with ICF KPI 6 when appropriate in reporting cycle.	IFC agreed to report on emissions reductions, with information given to FCDO as: / Ex-ante. At the investment stage potential reductions would be reported. / Ex-post. At a later date (c.2 years from investment) IFC will be able to provide a more comprehensive figure of impact. / However, further discussions are required for complete alignment with the UK’s ICF methodologies. / Score: B (Outcome Indicator moderately did not meet Expectations)
Volume of public and private finance mobilised for mitigation purposes (disaggregated).	Investment pipeline development commenced, with potential initial investment made. Innovative mitigation projects identified for potential future investment.	SAFCO represents a significant mobilisation milestone for CIFPAK. With FCDO’s $10m derisking contribution enabling $115m of climate finance to be committed for the project. / Score: A (Output Indicator Met Expectations)
Number of deals leading to an amount of FX savings.	Not Applicable in absence of MEL partner.	In principle, IFC are willing to provide this information needed for assessment but are unable to do it themselves. MEL partner once on boarded will lead assessment for this indicator. / Not Marked

Briefly describe the output’s activities and provide supporting narrative for the score.

This output aims to increase investments in innovative and frontier climate mitigation solutions, including innovative/frontier technologies alongside underserved sectors such as nature-based solutions, agriculture, forestry, and land use: reducing Pakistan’s greenhouse gas emissions trajectory. Overall, the CIFPAK programme will also achieve scale by deepening Pakistan’s capital markets, enabling innovative finance that supports climate and growth objectives.

In line with this objective, CIFPAK’s first investment into SAFCO Venture Holdings represents a major milestone. The project supports the development of Pakistan’s first large-scale Sustainable Aviation Fuel (SAF) facility, expected to reduce 546,640 tons of CO₂ annually. It is 100% climate-tagged and aligns with both IFC and UK ICF mitigation standards, demonstrating the programme’s ability to mobilise capital into high-impact, low-carbon technologies. Despite this success, and IFCs agreement on ICF reporting this output scored of “B” due to delay in programme mobilisation.

In terms of finance mobilisation, the investment is a significant success. CIFPAK’s $10m is catalysing $85 million from ADB and other lenders, alongside $30 million from IFC. This demonstrates the facility’s core aim: using concessional finance to unlock private and DFI capital for high-impact climate projects. The investment structure showcases how CIFPAK can de-risk frontier mitigation technologies and mobilise capital at scale and makes a meaningful contribution towards our overall outcome aim of mobilising £420m of climate finance (£86m committed so far).

Beyond SAFCO, CIFPAK has initiated a broader set of mitigation-relevant activities through its advisory work. Under Output 3, the programme is supporting project development and pipeline building for industrial decarbonisation, resource efficiency, and green building certification. These efforts are laying the groundwork for future innovative mitigation investments.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

A key refinement to the mitigation finance mobilisation outputs, compared to the original business case logframe, was the clarification of how mitigation-related capital mobilisation will be tracked, specifically in terms of private finance leveraged per dollar of concessional funding and anticipated GHG reductions. However, as part of this year’s review findings and recommendations, CIFPAK team will consider merging Outputs 1 and 2 to better reflect the integrated nature of upstream project development and transaction support, streamlining delivery and reporting across the blended finance pipeline.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

As this is CIFPAK’s first annual review, there were no prior recommendations to assess. However, a key lesson emerging from the mitigation work to date (also highlighted under broader programme learnings), is the critical importance of strategic alignment with the sectors outlined in the Administration Agreement. In light of an increasingly constrained financial operating environment, future success in mitigation will hinge on targeted efforts in nature-based solutions, agriculture, forestry, land use, and capital markets. To maximise impact and maintain consistency, it is recommended that IFC adopt a clear and robust screening process for future mitigation investments, ensuring sector alignment is verified at the concept stage. This will safeguard envisaged programme impact, optimise the use of concessional finance, and ensure resources are directed toward priority mitigation areas. Additionally, this annual review process has surfaced specific recommendations for mitigation finance listed below that should be actively pursued to further strengthen delivery.
Recommendation and Suggested Owner
Ensure future mitigation focussed investments are closely aligned with priority sectors identified in the Administration Agreement, notably capital markets. Owner: IFC & CIFPAK Technical Adviser
Strengthen CIFPAK’s capital markets integration by continuing exploring support for green bond frameworks, ESG disclosure reforms, and sustainable finance product development. Owner: IFC & CIFPAK Technical Adviser

Output Title	Project Preparation (Advisory Facility), capital market development and inclusive finance practices.
Output number:		3	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Pipeline (No.) of projects supported and x% transitioned to investment/deal signing stage (disaggregated on type and sector).	Not applicable - Number of projects at this stage of first AR are not feasible to assess.	Project-level delivery is not yet applicable at this stage, but foundational scoping has begun to identify potential investment opportunities aligned with CIFPAK’s adaptation and resilience objectives. / Score: A (Output Indicator Met Expectations)
25% of blended finance projects supported by the Facility meet the IFC "Gender Flagging standard".	Project pipeline development commenced, building gender tagging investment into the process for potential future investment.	Pipeline development is underway, with gender tagging being incorporated into project scoping and advisory processes to support inclusive climate investment in future phases. / Score: A (Output Indicator Met Expectations)

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 3 focuses on IFC led technical assistance for project preparation, capital market development and inclusive financial practices which remain crucial for the long-term success of CIFPAK. IFC TA primarily supports the development of a pipeline of projects for CIFPAK’s blended finance facility, with a secondary objective focussed on the enabling environment for climate finance in Pakistan. It supports regulatory reform, institutional capacity building, and market development to unlock private sector participation in climate-resilient infrastructure and nature-based solutions. This work complements other CIFPAK components by laying the groundwork for scalable investment models and facilitating the uptake of blended finance instruments.

The programme’s ambitious aims in adaptation finance mean projects will need to be accordingly tailored to ensure this technical assistance translates into sustained impact, it is essential to establish a clear pathway that links short-term project support to long-term systemic change. As, in the absence of a comprehensive and agreed technical assistance workplan, there remains a risk that this critical strand may drift from its intended trajectory.

Between November 2024 and March 2025, IFC led technical assistance under CIFPAK advanced seven projects, with several now transitioning from development to investment potential. Four of these projects were initiated during the review period, marking a strong start to the programme’s technical assistance component[4].
[4] Green and Resilient Buildings saw engagement with regulators and developers, with 15 projects entering the EDGE certification pipeline and investment discussions underway; Surface Geothermal / Ground Source Heat Pumps advanced with feasibility procurement scheduled for August and post-AR workshops involving 150+ stakeholders; Pakistan E-Mobility moved forward with regulatory frameworks and EV standards under development, alongside plans for a national EV portal and model city pilot; and Infrastructure Climate Resilience became active by June, with climate risk assessments completed for five infrastructure projects and client engagement initiated.

Of the four technical assistance projects initiated, three - Green Buildings, Geothermal, and Infrastructure Climate Resilience, demonstrate clear alignment with CIFPAK’s adaptation and resilience objectives, as outlined in the Administration Agreement. While other projects, such as E-Mobility and RISE MEPA, lean more toward mitigation, the overall portfolio remains directionally sound and consistent with CIFPAK’s Theory of Change. Continued refinement in project selection and sectoral alignment will be key to maintaining programme integrity and maximising impact. To safeguard this alignment and ensure coherence across the TA portfolio, an overarching technical assistance plan should be developed and agreed with IFC. This plan would serve as a strategic anchor, ensuring that CIFPAK’s pipeline of projects and TA activities remain tightly linked to its core objectives.

Despite this progress, the Administration Agreement between IFC and FCDO places explicit emphasis on adaptation and resilience, alongside capital market development. It stipulates that all advisory activities under this component must demonstrate high potential for enabling private sector investment in climate adaptation, building resilience across sectors, or accelerating Pakistan’s sustainable capital markets. While some early activities reflect these priorities, the portfolio has not yet fully met this standard, indicating a need for stronger alignment in future project selection and design. Further, within the review period, gender and inclusion were not substantively explored during the review period, representing a gap in CIFPAK’s early implementation. However, IFC has since initiated a dedicated gender workstream aimed at embedding inclusive practices across its initiatives.

To further strengthen delivery and responsiveness to the programme’s evolving context, the technical assistance workplan should be reviewed annually. This would allow for adaptive management and continuous improvement, ensuring that CIFPAK’s TA remains relevant, impactful, and strategically aligned.

Given that this assessment covers only the first five months of mobilisation and implementation, Output 3 has nonetheless made commendable progress against agreed logframe milestones, justifying an “A” rating for its performance.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
No key changes have been made this year. Aside from the below recommendations, FCDO is will maintain Output 3s focus on project development.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
Early implementation of CIFPAK’s project preparation TA has underscored the need for tighter alignment between advisory services and the investment facility’s pipeline with a proper workplan agreed for the life of programme and reviewed annually. While the initial portfolio shows promise, there is a growing risk of the TA becoming overly dispersed, potentially diluting its strategic focus. To meet CIFPAK’s overarching goals, particularly the 50% adaptation finance target, TA efforts must be more explicitly directed toward preparing adaptation-focused, investment-ready projects.

Strengthening partnerships with local actors presents a valuable opportunity to diversify and deepen the pipeline, ensuring relevance and contextual fit. To enhance impact and accountability, the adoption of a standardised tagging framework and clearer prioritisation of climate-vulnerable sectors will be essential. Recognising these risks early, the CIFPAK programme team is in process of a strategic review of CIFPAK’s collective TA portfolio, helping to course-correct and reinforce alignment with the programme’s core objectives.

The work conducted in the review period, is wider in scope than what will be the case for CIFPAK in the long term as specific projects are not yet fully identified. Future annual reviews will take a detailed approach to the link between the IFC TA, and the project pipeline for the blended finance facility.
Recommendation and suggested Owner
Develop and agree on an overarching technical assistance workplan that is strategically aligned with CIFPAK’s objectives and Theory of Change. This workplan should serve as a guiding framework to ensure coherence, prioritisation, and impact across the TA portfolio. It should explicitly prioritise key sectors outlined in the Administration Agreement including agribusiness, water, sustainable infrastructure, nature-based solutions, and biodiversity finance, while allowing for adaptive refinement based on evolving programme needs. The workplan should be reviewed annually to ensure continued relevance and alignment with CIFPAK’s delivery context. Owner: IFC (particularly Sector Leads) with CIFPAK Programme Team.
Explore technical assistance partnerships with local partners like InfraZamin and Acumen to support smaller, high-impact, adaptation and gender-inclusive projects. Owner: IFC Blended Finance and Advisory Services Teams.
Further focus IFC TA on investment-ready projects for the CIFPAK blended finance facility, with less emphasis on broad sectoral work. Owner: IFC Advisory Services Team.
Ensure all TA projects are tagged using MDB Adaptation Finance Type 2 or 3 methodology and tracked against supporting CIFPAK’s 50% adaptation investment target. Owner: IFC with CIFPAK MEL partner support.
Deprioritise mitigation-only sectoral TA (e.g. EV support) unless adaptation co-benefits are clearly articulated and agreed with FCDO. Owner: IFC Advisory Services and CIFPAK Technical Adviser.
Strengthen technical engagement between FCDO and IFC through thematic workshops and joint planning to shape TA workstreams and ensure strategic alignment. Owner: CIFPAK Programme Team (FCDO), with IFC Advisory and Sectoral leads.

Output Title	Technical Assistance Deployment, improvement in the enabling environment, and the wider climate finance ecosystem.
Output number:		4	Output Score:	A
Impact weighting (%):		15	Weighting revised since last AR?	N/A

Indicator(s)	Milestone(s) for this review	Progress
Indicator 4.1 Market barriers identified, and interventions held in response	Key barriers identified with the identification process commenced. Mitigation interventions commenced in close coordination with key stakeholders.	IFC demonstrated strong market engagement practices with key barriers identified and respective interventions commenced in close coordination with all stakeholders. / Score: A (Output Indicator Met Expectations)
Indicator 4.2 BCG improves Federal Government capacity on climate risk visualisation and project prioritisation, building on past interventions.	Influencing structure agreed with government. Risk visualisation tool design completed.	Federal Adaptation and Resilience Technical Working Group agreed with the government. One meeting held. Prototype of the risk visualisation tool completed. / Score: A (Output Indicator Met Expectations)
Indicator 4.3 BCG improves Provincial Government capacity for climate risk visualisation and project prioritisation, building on past interventions.	Project pipeline developed and private sector engagement commenced. Structure for supporting provincial government notified.	Project pipeline development initiated, and private sector engagement commenced. / Sindh Adaptation and Resilience Technical Working Group agreed with the government. Two meetings held. / Score: A (Output Indicator Met Expectations)

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 4 focuses on deploying strategic technical assistance to strengthen the enabling environment and broader climate finance ecosystem for private sector engagement. Under Output 4.1 during the review period, IFC initiated targeted advisory activities addressing key market failures. Notably, collaboration with the Securities and Exchange Commission of Pakistan advanced ESG disclosure standards, aligning them with international norms to improve transparency in corporate climate risk reporting. At the firm level, IFC supported clients in overcoming barriers such as limited capacity to assess climate risks and weak adaptation pipeline demonstrating a structured approach to unlocking private sector investment in adaptation.

Output 4.2 and 4.3 are being delivered by the UK Centre of Excellence (CoE) through the Boston Consulting Group (BCG). Under Output 4.2, a Federal Adaptation and Resilience Technical Working Group was formally established with the Government of Pakistan to institutionalise climate risk analysis and cost-of-inaction methodologies within public investment processes. CIFPAK team played a central role in convening this group, co-chairing with the Planning Ministry, drafting the agenda, and providing secretariat support. A climate risk visualisation tool, developed by the Boston Consulting Group (BCG) deployed through the Centre of Expertise – Growth Gateway contract, was prototyped through extensive stakeholder engagement (NDMRF, ADB, GCISC, MoF, EAD, IFC, GIZ) and tested with over twenty representatives. The tool enables risk mapping, project prioritisation, and tracking of adaptation finance, though feedback from the first TWG meeting highlighted the need for further refinement in data integration, ownership and sustainability. The working group will also work to enhance federal systems to create a more conducive environment for international and private sector investment in climate resilience and adaptation efforts.

In Sindh, under Output 4.3, BCG initiated efforts to identify and mobilise investment into a pipeline of adaptation and resilience agriculture projects. Consultations with government departments, development partners, and private sector actors led to a long list of over 100 projects, narrowed down to a prioritised portfolio of 10 through technical workshops and feasibility assessments. Concept notes were developed, incorporating cost-of-inaction analysis and financial viability. Three projects are now being prioritised for investor engagement, with strong endorsement from both public and private stakeholders.

To support these efforts, a formal Technical Working Group was established in Sindh, chaired by the Planning and Development Department and backed by key provincial stakeholders including Public Private Partnership (PPP) unit, Public Accounts Committee, Department of Agriculture, Department of Forestry and Wildlife, Department of Irrigation, Department of Livestock and Sindh Abadgar Board. FCDO and BCG collaborated to draft and vet the Terms of Reference, informed by political economy analysis and local insights. The TWG meets quarterly, with BCG serving as Secretariat and FCDO providing strategic support. Two meetings have been held to date, marking a significant step toward institutionalising adaptation planning and investment mobilisation at the provincial level.

While BCG brings strong technical expertise to CIFPAK, its relatively limited footprint in Pakistan and a delivery model primarily focused on product delivery presented significant challenges for sustainability of CIFPAK’s intended reforms and required CIFPAK team to step up and engage beyond feasible levels. These included slower progress in securing government buy-in and achieving traction on both engagement and sustainable implementation fronts. CIFPAK team worked closely with BCG to support a deeper understanding of Pakistan’s political economy, sustainable delivery approaches, and private sector investment mobilisation. Nonetheless, discussions around value for money remained ongoing and required continued coordination between FCDO, Growth Gateway, and BCG.

1. An additional delivery risk emerged when the Growth Gateway business case, which governs BCG’s contract, concluded in March, and the Gateway team was unable to secure a no-cost extension in time. This led to a temporary pause in technical assistance provision to the Federal government, resulting in BCG’s further reduced presence on-ground engagement and delays in planned activities. In response, CIFPAK team stepped in to maintain momentum on policy engagement and advance key agenda items.
2. CIFPAK team maintained close engagement with the Gateway team to manage risks and explore alternative delivery mechanisms. These decisions were guided by commitments to the Government of Pakistan, the viability of proposed deliverables, value for money, and alignment with CIFPAK’s strategic ambitions. Certain workstreams were deprioritised to enable a responsible and sustainable wind-down, with efforts focused on handing over projects and interventions to relevant stakeholders.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
As highlighted above, the federal and provincial interventions under CIFPAK’s demand-led technical assistance, delivered through BCG, have faced limited buy-in from government and sector stakeholders. This challenge has largely stemmed from the constrained in-country presence of the TA delivery teams, which has affected engagement and ownership. In response, FCDO, GG, and BCG collaboratively revisited the original scope of work, shifting toward a more focused and streamlined approach. This revised strategy aims to enhance delivery effectiveness while ensuring stronger government ownership, critical for the sustainability and institutionalisation of the reforms being supported.

Recommendations and Suggested Owner
Federal Technical Working Group Leadership: It is recommended that BCG formally assume ownership of the secretariat and co-chairing responsibilities for the Federal Adaptation & Resilience Technical Working Group. While FCDO has previously led these efforts, BCG’s increased involvement will ensure continuity, operational efficiency, and stronger institutional engagement in future TWG meetings. Owner: BCG Team
Climate Tool Refinement and Stakeholder Engagement: BCG, in collaboration with the CIFPAK Policy Lead, should convene targeted workshops with key stakeholders including NDMRF, ADB, and the Planning Commission to refine the climate risk visualisation tool. These workshops should focus on critical areas such as data architecture, ownership, and integration. Final refinements should be reviewed and endorsed at the next Federal TWG meeting to ensure stakeholder alignment and tool sustainability. Owner: BCG Team with CIFPAK Policy Lead
Sindh A&R Project Pipeline Consolidation: The Sindh pipeline should prioritise three high-impact adaptation and resilience projects, jointly endorsed by government and private sector partners. BCG is advised to develop a comprehensive handover and sustainability plan for these projects by end-October 2025. This milestone will serve as a trigger for continued engagement and support for this work. Owner: BCG Team
Strengthening Local Partner Role: Given BCG’s limited in-country presence, it is recommended that the role of local partners be strategically enhanced. BCG should leverage their partners on-ground networks and contextual knowledge to support stakeholder engagement, represent the programme in key forums, and proactively address delivery bottlenecks. Owner: BCG and CIFPAK Team
Strengthening the CIFPAK TA Offer: With the current phase of TA activities under the Growth Gateway Business Case concluding on 31 March 2026, the programme team should begin developing forward-looking Terms of Reference for the next phase of enabling environment support that aligns with the Pakistan Network’s Climate Cooperation Strategy to sustain momentum beyond the current implementation window. Owner: CIFPAK Team

Output Title	Monitoring Evaluation and Learning
Output number:		5	Output Score:	B
Impact weighting (%):		10	Weighting revised since last AR?	N/A

Briefly describe the output’s activities and provide supporting narrative for the score.
Indicator(s)	Milestone(s) for this review	Progress
Number of evidence and learning products generated and disseminated (disaggregated by topic especially gender and climate adaptation)	CIFPAK MEL ToRs Finalised and Tender issued by April-25.	The procurement for the CIFPAK MEL component was significantly delayed due to ODA and human resource constraints with the contract now expected to be in place by January 2026. / Score: B (Outcome Indicator moderately did not meet Expectations)
Evidence of effective collaboration between CIFPAK implementing partners including effective use of data and evidence to improve delivery and knowledge sharing.		Initial collaboration between BCG and IFC has begun, with joint planning underway to align enabling environment and project-level delivery across Components 2 and 3. / Score: A (Output Indicator Met Expectations)
Frequency and quality of engagement with the international community and relevant global initiatives (e.g. the Adaptation and Resilience Investors Collaborative) to standardise international best practices and validate CIFPAK approaches.		A climate finance working group has been launched with the World Bank Group and other partners, supporting global engagement and positioning CIFPAK within broader climate finance dialogues. This met after the review period, but the underlying work was commenced within this period. / Score: B (Outcome Indicator moderately did not meet Expectations)

Output 5 focuses on CIFPAK’s independent Monitoring, Evaluation, and Learning (MEL) function, designed to generate credible evidence across geographies and components to inform climate finance, adaptation, and mitigation efforts in Pakistan. Despite delays in procuring a dedicated MEL partner due to the ODA prioritisation, the programme team made notable progress in laying the foundation for MEL delivery.

Key achievements include the development of programme briefs to build external understanding of CIFPAK’s strategic direction and spread awareness of the project’s investment goals, initial collaboration between BCG and IFC to align workstreams, and the launch of a climate finance working group with the World Bank and other partners to support global engagement.

While the absence of a MEL partner has slowed progress, particularly in baselining and impact tracking, FCDO successfully finalised the MEL ToRs and developed the programme logframe. With ToRs currently with central Procurement and Commercial Department, a MEL supplier is now expected to join CIFPAK by Jan-2026, enabling full implementation of MEL activities and strengthening programme accountability and learning.

Describe any changes to this output during the past year, and any planned changes as a result of this review

There have been no changes to this output or its milestones, however, this output and milestones will evolve once the MEL partner is onboard.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

MEL is a critical enabler for CIFPAK’s success, particularly in tracking progress against adaptation, gender, and capital mobilisation goals. While the programme has made strong initial efforts for programme mobilisation, partner engagement and fostering collaboration, the absence of a dedicated MEL partner during the review period has limited deeper analysis and baselining. The following recommendation outline priority actions to strengthen MEL delivery and ensure the programme is equipped to generate evidence, support adaptive management, and contribute to departmental and even global learning.
Recommendations and Suggested Owner
Accelerate MEL Partner Onboarding and Implementation: Finalise tendering requirements and expedite onboarding of the MEL partner to enable timely initiation of MEL activities, including: / MEL Delivery and Coordination: The MEL partner should immediately initiate programme baselining, with a focus on adaptation finance, gender inclusion, and capital mobilisation. Regular MEL coordination meetings should be established between the MEL partner, FCDO, IFC, and other delivery partners to ensure alignment and integration across components. / Develop and Disseminate Learning Products: The MEL partner should lead the development of a structured pipeline of learning products including case studies, thematic briefs, and quarterly learning notes, disaggregated by gender and adaptation. These outputs should be used to inform programme decisions and shared through platforms such as the climate finance working group to support global engagement and validation. / Owner: MEL Partner, with CIFPAK Programme Team

## D: VALUE FOR MONEY
In its first year, CIFPAK has demonstrated partial but encouraging signs of Value for Money (VfM), with strong performance in financial leverage, adaptive delivery, and inclusive design. The programme aligns well with FCDO’s VfM framework across all 5 E’s including economy, efficiency, effectiveness, equity, and cost-effectiveness, but a full assessment is constrained by gaps in monitoring, evaluation, and lack of structured reporting.

Economy and Cost Drivers: Key cost drivers during the review period included blended finance allocations, consultant deployments, travel logistics, and partners overhead charges. While CIFPAK demonstrated cost-consciousness such as pausing federal-level engagement and redirecting resources to Sindh, the reliance on BCG consultants flying in from overseas significantly increased travel costs and carbon emissions. This model also limited local responsiveness and stakeholder familiarity. Transitioning to more locally embedded delivery models could reduce costs, improve contextual relevance, and enhance impact. Leveraging existing modalities and networks helped reduce mobilisation timelines, but further localisation is needed to align with Pakistan’s TA benchmarks and VfM expectations.

Efficiency: CIFPAK has shown commendable efficiency, delivering several outputs ahead of schedule and adapting delivery in response to stakeholder engagement levels. The SAF biodiesel refinery project mobilised $115 million against a £10 million CIFPAK grant, achieving a mobilisation ratio of 1:11.5, well above the business case target of 1:5. This includes $30 million from IFC and $85 million from ADB and other lenders, demonstrating effective use of concessional finance to de-risk a first-of-its-kind facility. These results reflect strong operational agility and strategic use of public funds to catalyse large-scale climate investment.

Effectiveness: Effectiveness remains difficult to verify due to the absence of structured output-based reporting, baseline data, and KPI tracking. Outputs milestones lacked reporting during the limited review period, and there is no documentation tracking progress against key indicators such as GHG emissions avoided, private finance mobilised, or number of people supported to adapt to climate change. These gaps hinder the ability to link spending to outcomes and assess programme impact. Addressing these MEL deficiencies is critical to enable robust VfM assessments and inform future programme decisions.

Equity: CIFPAK has embedded equity considerations throughout its design. Gender and inclusion are central to project prioritisation, with initiatives like mechanised rice transplantation reducing women’s labour burden and enabling access to education. Eight out of ten pipeline projects target low-income farmers, ensuring climate resilience benefits reach vulnerable populations. The SAFCO Project also demonstrated IFCs commitment to gender inclusion, SAFCO has set ambitious targets to increase women’s employment from 0% to up to 25% over the life of the IFC investment.

Overall, CIFPAK has delivered partial VfM in its first year, with strong performance in financial leverage, adaptive delivery, and inclusive design. However, the lack of structured MEL systems and no formal partner commitment and reporting on VfM limits the ability to fully assess cost-effectiveness and impact. To strengthen VfM in future years, the programme must prioritise development of a VfM framework, baseline establishment, and systematic KPI tracking. These steps will enable more rigorous assessments, support strategic improvements, and justify continued investment.
Recommendation and Suggested Owner
Develop and Operationalise a Programme-Level VfM with Strengthened Partner Reporting: By March 2026, CIFPAK team and the MEL partner should co-develop a comprehensive VfM framework aligned with the programme logframe. This should include structured output-wise reporting templates, measurable indicators, and timelines for each component. Owner: CIFPAK Team and MEL Partner

## E: RISK

Overview of risk management
CIFPAK has maintained a structured, responsive, and compliant approach to risk management, aligned with the Pakistan Network’s Risk Appetite and the programme-specific appetite agreed as part of the Business Case in October 2024. The overall risk rating remains moderate, with risk registers managed and updated in accordance with the Programme Operating Framework (PrOF).

CIFPAK’s risk appetite remains eager for strategy and policy delivery, receptive to fiduciary and operational risks, and cautious regarding reputational, safeguarding, and people risks; a balanced approach that supports adaptability while maintaining strong controls. As of March 2025, the CIFPAK Risk Register includes 27 active risks across all seven FCDO categories.

The programme has embedded risk ownership and escalation protocols within delivery frameworks, promoting transparency and accountability. Partners are required to report risks aligned with FCDO categories, which are reviewed and updated regularly to reflect emerging challenges. Risks are discussed in weekly progress meetings and ad hoc sessions, with escalation supported through formal channels including direct reporting to BHC and integration into programme governance.
Key Risks and Mitigation Measures
Despite good progress on investment mobilisation and technical assistance offer, several risks continue to affect delivery. Within Strategy and Context, macroeconomic volatility, limited investible opportunities, and constrained private sector risk appetite have challenged mobilisation efforts particularly for IFC. These are being mitigated through diversified portfolios, concessional finance, and close monitoring of IFC’s investment behaviour. On programme delivery and operations front, varying reporting requirement, approaches and timelines affected the decision-making. On BCG’s front in particular, limited contextual awareness, presence and federal engagement have impacted continuity in technical assistance, particularly around project prioritisation and sustainability.

To address these challenges, CIFPAK team and partners have implemented targeted mitigation strategies. IFC has deployed blended finance tools, ESG advisory services, and sector-specific TA to de-risk investments. BCG along with CIFPAK team has institutionalised engagement through federal and provincial Technical Working Groups, enhancing government buy-in and policy traction. Tools like the Climate Impact Assessment Portal (CIAP) and a high-quality pipeline of adaptation projects have strengthened the enabling environment and attracted investor interest. Risks related to stakeholder commitment, financial uncertainty, and reputational exposure are being actively managed through adaptive planning, embedded advisors, and structured engagement.

On the financial and fiduciary front, CIFPAK remains the flagship programme within the Pakistan Network delivering CDEL. However, delays in the delivery of demand-led technical assistance (TA) and the project preparation facility pose a potential risk to annual spending plans, which could result in forecast variances exceeding tolerance thresholds. To proactively mitigate this, the CIFPAK team has developed an initial demand-led TA strategy paper with a clearly defined timeline to accelerate delivery. Furthermore, following successful engagement with the IFC team, a comprehensive project pipeline has been secured to provide greater assurance around CIFPAK’s investment commitments and forward planning. However, at a portfolio the risk remains for appropriate cover to deliver CDEL in case of lag in CIFPAK delivery and needs to be though through.

More broadly on financial management front, IFC follows a formal integrity risk management process through the World Bank Group’s Integrity Vice Presidency (INT), including anti-corruption provisions and investigation protocols, as outlined in the Administrative Agreement with FCDO. However, as outlined above, emerging concerns include the lack of periodic Value for Money (VfM) reporting by both partners IFC and BCG, which limits transparency and weakens the programme’s ability to assess cost-effectiveness.

Additionally, delays in implementing due diligence recommendations and irregular updates on risk mitigation progress have been noted. To strengthen oversight, it is recommended that IFC provide quarterly (or at minimum bi-annual) VfM reports aligned with programme outputs, share updates on actions taken following the September 2024 DDA, and enhance visibility on ESG performance. For Centre of Expertise – Growth Gateway strand, formalising engagement between BCG and the CIFPAK Programme Team, through quarterly joint sessions and structured progress reporting, will help surface risks early and improve delivery coordination.

During the reporting period, several key ‘People’ risks materialised that were outside the programme’s risk appetite and were escalated to the Development Director. The absence of leave cover for the Green Growth Adviser resulted in a temporary gap in climate finance expertise at a critical juncture for the programme. This was compounded by the departure of both the Private Sector Team Leader and the CIFPAK Programme Responsible Owner (PRO), which significantly constrained programme delivery capacity. In response, a new Senior Responsible Owner (SRO) was appointed to provide strategic leadership and enable the Lead Adviser to focus on technical oversight. Recruitment for the PRO role is now underway, supported by a strengthened job description, and the programme is expected to be fully resourced by January 2026.

Other risk including reputational and safeguarding largely remained unchanged and manageable. The programme has “cautious” risk appetite for Reputational risks and “minimal” risk appetite for Safeguarding risks.

Climate and Environmental Risk
CIFPAK programme team reassessed climate and environmental risks in line with the Paris Agreement. Investments face both physical and transition risks. IFC’s climate strategy, aligned with Task Force on Climate-related Financial Disclosures (TCFD), and BCG’s Climate Impact Assessment Portal (CIAP) support climate-informed decision-making. The pipeline prioritises adaptation and resilience, targeting high COI reduction and vulnerable populations.
Recommendation and Suggested Owner
CDEL Assessment for Pakistan Network Portfolio: Given CIFPAK’s central role in delivering CDEL within the Pakistan Network, and the limited CDEL allocations projected for future years, it is important to proactively assess and risk-adjust CDEL utilisation across the broader portfolio. The CIFPAK team, in collaboration with Goal 3 and Goal 5 teams and the Operational Excellence (OpEx) unit should lead this assessment to ensure strategic alignment, optimise resource allocation, and mitigate potential underspend risks and have it agreed by Development Director by December 2025. Owner: CIFPAK, Goal 3 and 5 teams and OpEx.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Commercial Performance
Following its approval in Summer 2024, CIFPAK swiftly initiated contracting with its implementing partners, demonstrating a flexible and adaptive delivery approach in response to emerging priorities and results.

For two core components, Blended Finance Facility (BFF) and Project Preparatory Support, Administrative Agreements (AAs) were signed with the International Finance Corporation (IFC) after completion of the Due Diligence Assessment (DDA). The AA for BFF totals £74.9 million, comprising £70 million for programme activities and £4.9 million in administrative fees. The AA for Project Preparatory Support amounts to £15 million, bringing the total CIFPAK commitment with IFC to £89.9 million. Implementation of DDA recommendations is underway, with updates pending from IFC.

For the Federal and Provincial Enabling Environment Technical Assistance, CIFPAK signed a Dual Lock Agreement[5] with the centrally managed programme - Growth Gateway (GG) programme at FCDO’s Centre of Expertise. This agreement, valued at £6.4 million, leveraged GG’s existing delivery partner, Boston Consulting Group (BCG), engaged through the Option 2a buy-in process under FCDO’s guidance where the contract management remains with the central team.
[5] A Dual Lock arrangement is an agreement upfront between two parts of the organisation -usually a country post and a team managing a centrally managed programme (CMP) or Centre of Expertise (CoE). A Dual Lock arrangement details: • Roles and responsibilities of both parties for management and oversight of the programme. • Internal and external governance and reporting arrangements and key ways of working. • Expectations on levels of staff resource and input needed from both parties to manage and oversee the programme. • How both parties will work/interact with the delivery partner(s) to ensure effective delivery.

Procurement for the Monitoring, Evaluation, and Learning (MEL) component is currently in progress via a competitive commercial process. With a total allocation of £3 million, the MEL function will provide independent oversight, learning, and adaptive management support across all components. As mentioned earlier, contract is expected to be in place by January – 2026.
Financial Performance
From a financial management perspective, the table below summarises programme outputs, implementing partners, delivery routes, budget types, and to-date expenditure:
Output	Implementing Partner	Delivery Route	Budget Objective Type	Lifetime Budget	Reporting Year Spend (till Mar-25)	Spend to Date (till Sep-25)
1 & 2	Adaptation & Mitigation Finances mobilised through Blended Finance Facility – IFC	Administrative Arrangement with Multilateral	ICF CDEL	70,000,000	30,000,0001	30,000,000
			ICF RDEL	4,900,000	2,100,0002	2,100,000
3 & 4.1	Project Preparation (Advisory Facility) – IFC	Administrative Arrangement with Multilateral	ICF RDEL	15,000,000	183,0884	573,125
4.2 & 4.3	Technical Assistance Deployment for Climate Finance Ecosystem – BCG under GG Programme/CoE	Dual Lock Centrally Managed Programme (CMP) Agreement	ICF RDEL	13,600,0003	1,525,000	1,655,000
4.4	Technical Advisory and Delivery Support	Programme Funded Positions	ICF RDEL	1,500,000	39,280.78	160,247
5	MEL - TBC	Commercial contract under procurement	ICF RDEL	3,000,000	-	-

1-this is the total amount of CDEL in PN-1 out of which only £10m has been encashed.
2-this is the total amount of RDEL in PN-1 out of which only £700k has been encashed against 7% administration fee.
3-this is the total amount of component-3/output-4. For BCG/GG TA contract total amount is £6.4m
4-IFC monthly spend report is generated with a delay of one month therefore March-2025 spend was reported in April-2025.

For the BFF component, payments to IFC are managed through Promissory Notes (PN). In accordance with the AA, the first PN was issued for £32.1m, with one encashment of £10.7m to date. Of this, £10m was committed to a green energy initiative aimed at producing biodiesel and sustainable aviation fuel (SAF) to support Pakistan’s transition to cleaner energy sources. The SAF project is being developed by SAFCO Venture Holdings Limited BVI through its subsidiary, Bio Tech Energy Pte Ltd.

Under the Advisory Services AA, a pre-payment of £1m was made to support IFC in building a pipeline of innovative investment projects. The implementation of the UK-IFC CIFPAK Programme has continued to build up, with a current total of 7 projects.

IFC’s financial management is aligned with the central administrative arrangements however the team has been successful in agreeing monthly reporting for the TA component to meet FCDO monthly resource accounting requirement. IFC team has also been helpful in sharing anonymised pipeline commitments for planning BFF tranche disbursements.

BCG’s financial management of the intervention is aligned to the wider Growth Gateway programme financial management and reporting. Invoicing is against milestones, with spending fully aligned with forecasts. BCG received £1.53m for the delivery of three output-based interim deliverables. Due to challenges in engaging with the Government stakeholders initially, and following close consultation with CIFPAK team, the final deliverable was split. Following extensive engagement with local government stakeholders, investors, and private sector partners, these funds supported the preparation of a pipeline of 10 projects from a total of 73 priority projects. Of these, three are scheduled for delivery in FY2025–26.
Delivery
Despite early staffing constraints, CIFPAK successfully onboarded its two core delivery partners and demonstrated strong performance across four key outputs. To bridge capacity gaps during mobilisation, the programme team secured interim support, including a 10% time allocation from a previous SRO and 50% from an HEO, ensuring strategic alignment of Outputs 3 and 4 with the Business Case and initiating the MEL partner procurement process.

Weekly engagements with implementing partners helped steer delivery and address emerging challenges. Although onboarding of the Climate Advisor and Policy & Engagement Lead was delayed, both contributed meaningfully to stakeholder engagement and programme visibility. In Sindh, consistent liaison with government departments led to the formation of a Technical Working Group (TWG) for agriculture-focused adaptation projects, formalising provincial government support and strengthening institutional buy-in.

At the federal level, BCG conducted a detailed political economy analysis, engaging key officials across ministries and development institutions to introduce CIFPAK’s approach—including the Cost of Inaction concept and the Climate Impact Assessment Portal (CIAP). This engagement helped identify critical friction points in A&R planning: limited integration of climate risks in National Adaptation Plans (NAPs), underuse of climate modelling, and weak tracking of adaptation finance. In response, the CIAP tool was developed and refined to support project prioritisation, funding strategies, and gender-responsive planning.

While delivery momentum was strong, several operational challenges emerged. The absence of quarterly reporting mechanisms weakened programme assessments, transparency and accountability. Staff turnover at BHC further complicated sustainable delivery. Although BHC maintained steady engagement with partners, management and coordination remains difficult to modalities and partners constraints and requires improvement, particularly through clearer reporting structures and defined engagement protocols.
Recommendation and Suggested Owner
Introduce Quarterly Progress Reports (QPRs) to Complement Milestone Narratives: Starting Q4 2025, all CIFPAK implementing partners should submit structured QPRs alongside milestone-based progress narratives. This will enable more consistent performance tracking, improve accountability, and support adaptive management. These reports must include: / Progress against logframe indicators / Value for Money (VfM) analysis / Financial and Risk management updates / Stakeholder coordination updates / Lessons learned and corrective actions / Owner: CIFPAK Team and all Implementing Partners
Strengthen the Formal Coordination Framework Across Delivery Partners: By March 2026, CIFPAK team along with the MEL and other implementing partners co-develop and adopt a formalised “Ways of Working” document including, defined roles and responsibilities, quarterly coordination meetings, and coordination protocols and escalation pathways. This framework will build synergies, strengthen alignment, and ensure timely decision-making across partners. / Owner: CIFPAK Team and all Implementing Partners

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
During the review period, CIFPAK in absence of Monitoring, Evaluation and Learning (MEL) partner, relied on MEL activities carried out by implementing partners. Tetra Tech, the MEL partner for Growth Gateway, led internal monitoring for CIFPAK-funded activities, delivered through BCG. This included reviewing project outputs, conducting interviews with stakeholders, and gathering feedback from the British High Commission in Islamabad. IFC used its own internal systems to monitor progress on advisory projects such as ESG Pakistan, Green Buildings, and RISE MEPA.

Weekly planning sessions with FCDO, Technical Working Group meetings, and one-to-one engagements, provided further opportunities for feedback and reflection. Stakeholder feedback and political economy analysis, conducted by BCG with Adam Smith International, identified limited engagement from the federal government. This led to a strategic pause in federal-level activities and a shift in focus to provincial implementation in Sindh.

The evaluation studies will examine the broader impacts of the programme and progress towards transformational change. This will include environmental and social effects, impact of building resilience on livelihoods, and the effect on women, youth, and disadvantaged groups. This will allow the assessment of the programme’s progress to meeting strategic objectives, expected results, and the recommend any changes to the programme’s theory of change.

The MEL supplier will also support the production and dissemination of learning materials. This will include at least 5 case studies of CIFPAK investments. There will also be a focus on learning the impact of linking climate finance flows to livelihoods, gender, and community uplift.

The Annual Review process was led internally by CIFPAK team included inputs from BCG, IFC and broader programme stakeholders.

Date of last narrative financial report		BCG: 12 July 2025 / IFC: TA - 30 July 2025; BFF - 08 Aug 2025	Date of last audited annual statement	TBC Reports are anticipated to be submitted by mid-October 2025