## Logframe 2024
Project Title: | Kenya Anti-Corruption Programme 2021-2024
IMPACT | Impact Indicator 1 |  | Baseline (Oct 2021) | Milestone 1 ()ct 2022) | Milestone 2 (Dec 2023) | Target (Oct 2024) | Assumptions
Reduction in the levels of corruption in Kenya, and public perceptions of it. | Change in public perceptions and attitudes owing to improved public service delivery of public goods and services including increased public confidence and citizen trust | Planned | TI 2021 CPI Index puts Kenya at 30/100, Rank 128/180 | No 2022 milestone | - Reduced incidences of procurement fraud in Kenya’s public sector - Private sector empowered to respond and prevent corruption at institutional level | Positive change in public perception compared to previous year. | While the programme is focussed a prevention approach, its assumed that Weak coordination in the oversight, prevention, law enforcement and criminal justice will be strengthened through ensuring that programme engages actors within the entire Anticorruption Chain to ensure there is no weak link. Addressing business integrity blocks without addressing cost of doing business, or safety and security will not unlock additional FDI or Capital flows. As such, improvement in business intergrity will not transform to Kenya increasing business if other factors noted are not addressed; thus Programme success is underpinned by systems approach, ensuring it coordinates with other FCDO programmes including the Kenya Devolution Programme, Reducing Insecurity and Violent Extremism in Norther Kenya Programme; Sustainable Economic development programmes and others to realize improved governance wth greater accountability to allow for positive development outcomes. Donor coordination will ensure donors interact across the anti-corruption chain and influence weak coordination in the public sector. Assumption that we will have adequate data sources to measure progress and achievement of results.
|  | Achieved |  | TI 2022 CPI Index in January 2023, indicated that Kenya had moved from 30 to 32 points and ranked position 123 out of the 180. | There is evidence of reduced incidence of procurement fraud as measured under the Ibrahim Index where Kenya’s Anti-corruption score has improved from 38.9-41.4 2020-2021.
Source TI Kenya Perception Index and Mo Ibrahim Governance Index,
| Impact Indicator 2 |  | Baseline | Milestone 1 - Oct 2022 | Milestone 2 - oct 2023 | Target (Oct 2024)
| Improved enforcement of norms, standards, and laws, and further legal reform. | Planned | Laws and legislative amendments enacted in the last ten years (e.g. Leadership and Integrity, Access to Information, and Elections Campaign Financing laws) yet to be fully implemented. |  | - Strengethened procurement reform for improved accountability and transparency. - Institutionalization of OGP through development of long-term better open government results | Evidence on enhanced implementation of norms, standards, and laws, and further legal reform
|  | Achieved |  |  | PPRA is drafting a 5-year plan to improve public procurement processes. An OGP action plan drafted, including a commitment on beneficial ownership transparency.
Source TI Kenya Perception Index and Mo Ibrahim Governance Index
OUTCOME 1: | Indicator 1 |  | Baseline | Milestone 1 - Oct 2022 | Milestone 2 Oct 2023 | Target (Oct 2024)
GoK and businesses anti-corrupion and illicit finance practices are stronger. | Instances of strengthened anti-corruption & illicit finance practices in areas HMG has supported | Planned | - Transparency International Kenya and Global Financial Integrity notes that Kenya loses KES 270 billion (US$ 2.5 billion), amounting to 25% - 30% of the government’s annual budget. - EACC Annual Report of 2020/21 recovered KES 6.2 billion of public stollen assets and averted a possible loss of public funds estimated at KES 6 billion. - EACC survey in 2021 noted national average bribe increased considerably from KES. 3,833.14 in 2018 to stand at KES. 5,889.89 in 2021. - 2020/21 report by Office of Auditor General: ‘lack of action and sanctions contributed to fiscal indiscipline including misallocations, wastage of resources, lack of value for money in implementation of projects and loss of public funds... | No 2022 milestone | - GoK use the Public Procurement Risk Index database - PPRA strategic plan completed - Open Government Partnership Action Plan on beneficial ownership completed. - GoK accepts support on implementing FATF recommendations - Private sector engaged in dialogue with the public sector (GoK) on buisness integrity. | 1.Measures to improve business integrity, to progress the OGP and improve the transparency in public procurement are institutionalised by GoK. 2. LSK is using a risk based approach to managing AML CFT across the sector.
|  | Achieved |  |  | On track: PPRA uses the PP Risk Index Database. • On track: PPRA strategic plan review due to be completed by end of 2023 • On track: Open Government Partnership Action Plan, including beneficial ownership commitment, set to be completed by end of 2023. • Achieved: GOK accepted support on implementing FATF recommendations. • Achieved: one public-private dialogue event held by BBCK
Source - Partner reports, EACC Annual Report, OAG Reports, CBK reports, FRC reports NGO Coordination Reports,Mutual Evaluation Reports by FATF, ESAAMLG Report
OUTPUT 1 | Output Indicator 1.1 |  | - | Milestone 1 - Oct 2022 | Milestone 2 - oct 2023 | Target (Oct 2024) | Assumptions
GOK and business associations supported to strengthen anti-corruption and illicit finance practices | Support to government and/or business associations on tackling integrity issues in the private sector Weight: 10% | Planned | Business Intergrity Initiative Pilot | No 2022 milestone | • Refreshed MOU between BCCK and MoT under discussion • 4 Events/discussions with Business Associations on key topics as per recommendations from the Study • 1 Public/private dialogue events held | Three priority reform areas are identified, well defined, and agreed with BCCK,BHC and MITI. | There is GoK buy-in and ownership of interventions. Businesses will have the appetite and interest to promote fair business environment leading to collaborations with civil society, media and government working on their challenges. Partners identified to deliver the work will have the requisite skills, experience and social license to do the work effectively.
|  | Achieved |  | • Publication of the 2022 BCCK Integrity Market Study (the Study) • MOU signed with the Outgoing Administration [date] | a) Met expectation: Discussions held with 4 business associations. b) Exceeded expectation: MOU between BCCK and GOK signed in Sept 2023. c) Met expectation: 1 public/private dialogue held.
Source- Mutual evaluation reports, Partner Reports , BCCK Documents, EACC Surveys, TI Surveys
| Output Indicator 1.2 |  | Baseline | Milestone 1 - Oct 2022 | Milestone 2 - oct 2023 | Target (Oct 2024) | Assumptions
| GOK and/or business associations supported to implement FATF recommendations Weight: 20% | Planned | • No regular engagement between HMG and GOK on FATF | No 2022 milestone | • 5 Discussions held with GOK and private sector on FATF process • Agreed and signed security compact includes UK support on FATF • GoK acceptance of provision of support | LSK structures and systems improved to better respond to AML recommendations as a supervisory entity of the legal proffession in Kenya | Enough key political actors engage to effect change at system level Donors willing to work together to deliver change on public procurement and Beneficial Ownership
|  | Achieved |  | • TI Report on NPO Sector Engagement • Report on High Risk Sectors | a) Met expectation: With UK engagement, GOK's OGP Action Plan (V) due to be published by end of 2023, including a commitment on beneficial ownership. b) Met expectation: FCDO facilitated BRS’ engagement with the Africa Beneficial Ownership Transparency Network.
Source- Mutual evaluation reports, Partner Reports , BCCK Documents, EACC Surveys, TI Surveys
| Output Indicator 1.3 | Planned | Baseline | Milestone 1 - Oct 2022 | Milestone 2 - oct 2023 | Target (Oct 2024) | Assumptions
| GOK supported to improve beneficial ownership practice Weight: 20% |  | • Not currently supporting | No 2022 milestone | • Engagement in the development of GOK’s OGP Action Plan V on Beneficial Ownership • Implement support to BRS and/or PPRA in line with need and other donor offers | 1. 80% increase in awareness amongst target BCCK members on beneficial ownership. 2. Increase in no. of information requests to BRS during investigations on Beneficial Ownership (Mzalendo). 3. Completed workplan and budget developed for BO cluster | Focus on strengthening government institutions without public engagement will lead to improvements in the government systems which the public are unaware Strategic comms will be deployed to strengthen public engagement
|  | Achieved |  | • Report provided to BRS on how to align data collection practices with Beneficial Ownership data standard. • Feedback submitted to BRS on beneficial ownership legislation and sharing of data with Public Procurement Regulatory Authority (PPRA) • Advice submitted to PPRA on how to update their beneficial ownership consent and disclosure forms. • Delivery of IT tools for utilising beneficial ownership data in Government processes including public procurement | At least 20 engagements have been held with GOK and the private sector. (More than can be accurately quantified ) Security compact communique includes UK support. GOK accepted UK support, and technical assistance has started with the Central Bank of Kenya.
Source- Mutual evaluation reports, Partner Reports , BCCK Documents, EACC Surveys, TI Surveys, Mzalendo reports, BCCK Survey
| Output Indicator 1.4 (NEW) |  | Baseline | Milestone 1 - Oct 2022 | Milestone 2 - oct 2023 | Target (Oct 2024)
| Awareness of the OGP in Kenya increased Weight: 20% | Planned |  |  |  | 1. Back-end metrics of at least 1500 clicks per month on OGP website. 2. Half all OGP countries from Africa & the middle-east attend the NAP 5 launch. 3. GoK increases representation at OGP multi-stakeholder forums
Achieved
Source OGP website, Partner reports, NAP 5
| Output Indicator 1.5 |  | Baseline | Milestone 1 - Oct 2022 | Milestone 2 - oct 2023 | Target (Oct 2024) | Assumptions
| GOK supported to develop Public Procurement Risk Index Weight: 25% | Planned | No early warning mechanism | No 2022 milestone | • Update the Public Procurement Risk Index (PPRI) scores. • #2 Disseminate findings and learning from the PPRI to GOK •#1 Convene regular engagement fora with the Kenya Editors Guild to publicise key findings of the PPRI | 1. A tangible commitment to adopt at least 1 policy recommendations from PPRI made by each benefiting institution (PPRA, National Treasury, OAU). 2. Action plans developed by 3 CSO networks on use PPRI findings in counties | Improved accountability in public procurement processes Increased public awareness of the incidences of public procurement fraud GOK Commitments to address procurement fraud by relevant institutions
|  | Achieved |  | • IEA PEA on Public Procurement in Kenya • Comprehensive record of public procurement transactions included in the Public Procurement Information Portal. • Development of a Public Procurement Risk Index using the public procurement transactions record data. | a) Met expectation: PPRI scores updated. b) Met expectation: Dissemination of PPRI findings to GOK entities (PPRA, Treasury and EEAC) completed in 2023. c) Met expectation: One engagement with Editors Guild held. Another planned after PPRI data is updated.
Source -IEA through survey, generated PPRI reports, partner narrative reports, CSO reports
IMPACT WEIGHTING: | 90 (%)
INPUTS (£) | (£) 350,000 |  | Govt (£) |  |  | Other (£)
INPUTS (HR); | DFID (FTEs) 50%*B2 prog manager; 100%*B2 Gov adviser; 20%*G7 Illicit Finance adviser; 10%*G6 Team Leader; 10%*SEO Deputy Team Leader