ADDENDUM TO BUSINESS CASE INCLUDING FOR BRIDGE FUNDING AND SCALE-UP COST EXTENSIONS

SUMMARY INFORMATION
Programme Name	Kenya Anti-Corruption Programme
Country or region targeted	Kenya
Type of cost extension (if applicable)	Theory of Change Refresh
Original Programme budget	£3 Million
Original Programme start and end dates	04 October 2021 – 04 October 2025
Cost extension value (if applicable)	Not applicable
New reduced budget (if applicable)	Not applicable
New Programme end date (if applicable)	Not applicable
Business Case Quest Document No.	301247

INFORMATION
What is the programme’s purpose?
The purpose of this programme as set out in the business case is to seek to ensure the Kenyan government uses effective processes to prevent corruption in the public and private sectors, focussing on the prevention angle. The programme envisages strong Kenyan systems and processes to reduce and respond to corruption. It seeks to realise a more open, transparent, and accountable government and stronger and engaged civil societies which strengthen resilience to corruption, illicit finance, and human rights violations and ensure citizens benefit from stronger, more accountable, and inclusive institutions. / The original programme set out 4 outputs - three of which we propose closing as part of this business case amendment. notably: / Improved evidence, data and analysis of corruption and innovation in programming (To be closed) / Strengthened efforts to prevent corruption in the public and private sectors, and delivery of the Kenyan government’s anti-corruption commitments. / Strengthened institutions deliver criminal justice and accountability through effective prosecutions and asset recovery. (To be closed) / Strengthened regional institutions and cooperation to counter illicit financial flows. (To be closed) / We propose closing Output I, III, and IV following the outcome of the Kenya Anti-Corruption Programme Annual Review that recommended the need for a refresh of the programme’s theory of change and logframe.
What is the objective of the cost extension or other changes?
	The objective of this addendum is to update the Business Case with the new changes made to the Theory of Change and Outcome Statement: / Original Business Case (Approved Oct 2021) Previous TOC New TOC in the Amended Business Case (May 2023) / Theory of Change The original theory of change focussed on: / Contributing to improving better outcomes across the breadth of the UK-Kenya Strategic Partnership. At the outcome level the programme aimed at contributing to further improvements across the spectrum of anti-corruption efforts, maintaining momentum and results through the 2022 election cycle through: enhancing prevention of corruption in both the public and private sectors and enhancing accountability through the criminal justice system. The refreshed theory of change posits: / If we can build the capacity of Kenyan institutions charged with tackling illicit financial flows, anti-money laundering and prevention of corruption in the public and private sector; then the institutions will be strengthened to reduce opportunities for corruption and realise savings through reduced wastage in corruption, illicit financial flows, and anti-money laundering. Kenya will be able to unlock additional Foreign Direct Investment and capital flows into the country as business integrity blocs will incrementally reduce and citizens’ perceptions and confidence increase. / Outcome Statement Prevention of corruption in the public and private sectors. Improved processes to prevent corruption in the public and private sectors. / The programme's ToC has been revised to focus on prevention and drops the focus on output (1, 3 and 4) as it is not feasible to continue or start new activities under them. The shift to prevention was informed by the changes in the following areas: / Need for a clear logframe and milestones to guide in the implementation of the programme. / Change in political context in Kenya following the 2022 general election that led to the end of term of the Jubilee administration led by President Uhuru Kenyatta (2013-2022) and entry of the Kenya Kwanza Government which pledged to focus on promoting institutional independence and oversight as a means of enhancing accountability and transparency. / Recognition of the changing context in the UK, leading to reduced Overseas Development Assistance (ODA). KAP programme experienced 70% cut on its total budget for FY 2023/2024 / Evidence from the donor matrix revealed criminal justice and law enforcement were highly funded with less focus on prevention and civic engagement. / Need for clear UK offer that adds value and complements other donors’ interventions in the context of reduced ODA. / An opportunity to innovate and trial new ways of working through collaborations, coordination, increased UK-Kenya-Donor partnerships, and use of influence and UK strategic leadership to achieve results. / The new refreshed theory of change recognises Kenya’s new priorities on: / Promoting accountability and openness in the management of public affairs, institutionalising open governance in all State organs and agencies. / We will be progressing with output 2 which focusses on ‘Strengthened efforts to prevent corruption and illicit financial flows, in the public and private sectors, and delivery of the Kenyan government’s anti-corruption. Under this output we will focus on the following output indicators: / Support to government and/or business associations on tackling integrity issues in the private sector / GOK and/or business associations supported to implement FATF recommendations. / GOK supported to improve beneficial ownership practice. / Public Procurement Regulatory Authority supported to develop a strategic plan on public procurement. / GOK supported to develop Public Procurement Risk Index / Finance, Commercial and Management / The original business case budget was £3M, envisaged as approximately £1M per programme year for 3 years. This will also change as follows: / FY 21/22 ( FY 22/23 FY 23/24 FY 24/25 Total / Original business case budget (£) Approx £500,000 to 1M 1,000,000 (reduced to £634,000 in Dec 2022 budget cuts) 1,000,000 / (Reduced to £300,000 in March 23 ODA allocations exercise) £500,000 – 1M. £3M / Actual spend (£) and proposed budget for this addendum 358,591 636,136 300,000 £1.7M £3M / To align with the funding available in FY23/24, we will focus only on output 2 which has 5 indicators, with four implementing partners. One of the 5 indicators will be delivered through influencing owing to limited funds and will receive funding in the final year of the programme 2024/2025. / We also note that while in previous years we did four outputs with much smaller budgets; the final FY 24/25 will have an uplift to 1.7m. We justify this uplift using the following reasons: / Given output 2 has 5 indicators, with four implementing partners. The final year will focus on scaling and sustainability which will require more resources. The partners will also be in their third year of completion and would have established trust with their partners, and built good relations, as such, will not have mobilisation challenges.
What is the additional and total support the UK will provide?
The Programme will be leveraging on staff expertise to include influencing as part of delivering its outputs. / We recognize the following risks and opportunities: / While the programme adopts a prevention-focused approach, its effectiveness depends on strengthening coordination across the entire anti-corruption chain including oversight, prevention, law enforcement, and criminal justice. To avoid gaps that could undermine progress, the programme seeks to engage relevant actors across these areas, promoting a comprehensive and integrated response to corruption. / Addressing business integrity blocks without addressing cost of doing business, or safety and security will not unlock additional Foreign Direct Investments or Capital flows. As such, improvement in business integrity will not translate to Kenya increasing business if other factors noted are not addressed; thus, success is underpinned by a systems approach, ensuring it coordinates with other donors, and XHMG programmes like the Devolution Programme, Reinvent, Prosperity, to realise improved governance with greater accountability to allow for positive development outcomes. / We assume that donor coordination will ensure donors interact across the anti-corruption chain and improve coordination in GOK. In addition, we also assume that we will have adequate data sources to measure progress and achievement of results. / In recognition of these risks and opportunities we will undertake the following mitigation strategies: / Staff time to complement programme delivery through strategic influencing to enhance implementation effectiveness. / Ensure the programme output includes a public engagement component to mitigate poor public perception of improvements in government systems. / Strategic communications will be deployed to strengthen public engagement. / Strengthen donor coordination to enable GOK interactions across the anti-corruption chain and improve coordination in GOK. / Overall, these risks will be reflected and managed through the FCDO and partners' risk registers. Implementation of mitigating actions will be closely monitored.
What are the expected results?
The programme will seek to realise the following results: / Deliver GOK owned action plan on improving business integrity / Support Public Procurement Regulatory Authority to develop a strategic plan that will catalyse funding and enhance long-term institutional changes. / GOK supported to implement FATF recommendations.
What is the approach to implementation?
As set out in the original business case, we anticipate that the remaining output will be delivered through accountable grants with qualified not-for-profit organisations. A limited number of small-scale procurements may be undertaken where essential. Prior to awarding grants, we will conduct due diligence assessments in line with the FCDO standards. / It is envisioned that workstreams on output 2 will be transitioned to a new programme on strengthening institutions (currently in design), therefore potential implementing partners will be assessed based on their capacity to propose innovative, sustainable ways to deliver this output to deliver the intended outcomes, with a clear exit strategy. / The logframe has been amended to reflect the revised programme, and targets for the end of the programme.
Describe any key changes to the original business case including the theory of change or new evidence from ongoing monitoring, evaluation or learning work?
The programme has made changes to its outcome statement and output indicators. Outputs I, III, and IV have now closed following the outcome of the Kenya Anti-corruption Programme Annual Review which recommended the need for a refresh of the programme’s theory of change recognising the shifts in context, reduced funding as well as some technical issues with how things were measured. / The programme previously focussed on a criminal justice approach and has now shifted towards prevention as informed by evidence, learning from the annual review and our support to criminal justice actors for the last 8 years. / The new theory of change is now clearer and recognises the shifts in context and learnings from our AR, the ToC states that: if we can build the capacity of Kenyan institutions charged with tackling illicit financial flows and corruption in the public and private sectors; then the institutions will be strengthened to reduce opportunities for corruption and realise savings through reduced wastage. Kenya will be able to unlock additional foreign direct investment and capital flows into the country as business integrity blocks will incrementally reduce and citizens perceptions and confidence increase. / This programme would broadly contribute to these priorities owing to the following mutual interests HMG has with Kenya.
[note] This will require robust prioritization of investments to ensure clear results, working with stakeholders across a wide spectrum of engagement (from prevention to accountability) combined with enhanced efforts to maintain the public profile of the anticorruption agenda, through diplomatic engagement, the media and close working with other missions.