## All Annual Review Template

Title: Justice and Stability in the Sahel Programme
Programme Value £ (full life): £19milllion		Review date: June 2025
Programme Code: [AMP ID#] 301252	AMP start date: 31/08/2021	AMP end date: 31/03/2026

Summary of Programme Performance
Year	21/22	22/23	23/24	24/25
Overall Output Score	A	A	B	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case and addendum:	Business Case and Summary (90000470) 301252 (Published - February 2022)
DevTracker Link to Business Case Addendum	https://iati.fcdo.gov.uk/iati_documents/D0003892.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0003891.xlsx

A. SUMMARY AND OVERVIEW

This Annual Review covering the period August 2024 to July 2025 and has been conducted by an external FCDO team and edited by the FCDO JASS team. The reviewers went to Niamey to participate in the JASS Steering Committee in May 2025, conducted group feedback sessions with participants of the programme and partners in Niger in person and in Mali (virtually).

Description of programme

The JASS programme has three components taking place in Mali and Niger:
Improved conflict management capacity and collaboration among communities divided by conflict, and between them and state institutions, to mitigate and resolve conflicts over land and natural resources. This work addresses conflicts between land and water users (both pastoralists and farmers) which are likely to evolve into violence as they are vulnerable to being exploited by armed groups to fuel instability in the Sahel. JASS ensures both nomadic and seminomadic pastoralist and farmers are included in land governance structures and are empowered to reduce resource-based conflicts by influencing land use and allocation outcomes.

Strengthened resilience to climate shocks among affected communities in the target areas. The Sahel is one of the planet’s worst affected regions by climate change and biodiversity loss. Land and water scarcity accelerated by climate change, spiralling population growth, and entrenched social inequalities are core structural drivers of conflict in the region. JASS injects more resources in climate resilience and adaptation for vulnerable rural communities, helping reduce pressures on land and water through innovative, climate and gender/GESI-sensitive investments contributing to conflict reduction as pressure on resources is reduced.

Improved evidence base for effective delivery of stabilisation programmes, working with international and national actors to articulate lessons to achieve growth, stability, and poverty reduction. JASS Phase II will galvanise interest from other donors and donor networks in the Sahel to either contribute funding for its delivery or to adopt successful practices piloted by the programme, thus leveraging additional results and value for money of UK investment.
Summary supporting narrative for the overall score in this review

Overall, the programme has scored ‘A’ for the reporting period.

JASS has performed well across all outputs, and the team has responded well to the recommendations made in last year’s Annual review (see Annex A).

JASS has delivered tangible benefits to some of the most vulnerable and hardest to reach communities in Niger and Mali through cash assistance, improved access to productive land, improved yields, diversified incomes, improved services. Also has enabled policy changes in Mali and Niger, through JASS’s advocacy efforts bridging the gap between formal and customary justice systems and resorting trust amongst communities in the justice system. These impacts can be seen through the level of engagement in the external Steering Committee and the Resilience Forum where the JASS team brought communities, stakeholder and Ministries together to share experiences and build off the learning from the JASS programme.

During the Annual Review interviews and focus groups, there was positive feedback on the programme’s approach from a range of beneficiaries and local partners, including community members, technical services, local authorities and central ministries. Feedback highlighted the strength of JASS in responding to needs of the communities in a flexible and comprehensive way, with strong community engagement and reinforcement of their existing capacities and structures from the outset.

The programme in the future will need to consider more stretching targets in the logical framework to score higher by improving stronger evidence on what has been achieved not just on each activity level, but the impact for individuals, communities and wider, with stronger targets on gender and learning.

Table 1 summary of output performance and weighting
Output Description	Impact Weight (%)	Output Performance
Improved conflict management capacity and collaboration among communities divided by conflict, and between them and institutions, to mitigate and resolve conflicts linked to land and natural resources.	40%	Outputs met expectation (A)
Strengthened resilience to climate shocks and stressors to reduce frequency and impact of resource and land-based conflict in the Sahel.	40%	Outputs met expectation (A)
Improved evidence base for more effective stabilisation programme design, delivery and coordinated action among key stakeholders.	20%	Outputs met expectation (A)

Major lessons and recommendations for the year ahead
For the remaining year of the JASS programme, the key recommendations from this year’s Annual Review include:
Recommendation 1: Mercy Corps should develop a clear exit strategy, consisting of 3 pillars:
1. Responsible engagement and plan for ending the programme at community level. Ensuring clear communications with the communities, open conversation on next steps and ensuring the good functioning of community structures (COFOs - les Commissions Foncières) so that they continue after the end of the programme.
2. Discussion on the ‘handover’ of the programme to national governments at the upcoming External JASS Steering Committee, in Niamey in August 2025.
3. Review potential alternative sources of funding to continue JASS’s most impactful elements, looking at appropriation within governments, International Financial Institutions as well as wider bilateral donors.
4. The JASS team will work with FCDO to identify any support needs to ensure a responsible exit over the next year.

Recommendation 2: Mercy Corps should produce a consolidated evidence review, summarising the most significant pieces of evidence produced by JASS and to identify those which could be strategically used for national and international advocacy efforts and to institutionalise reforms and scale proven approaches.

Recommendation 3: At the final JASS Steering Committee, Mercy Corps should hold a learning workshop to present key evidence and learning from the JASS programme to a wider set of stakeholders, including other development partners operating in Niger and Mali.

Recommendation 4: During the next year JASS should assess further the impact of the programme both for communities and what strategic lessons can be taken for FCDO’s future programming.

Recommendation 5: JASS is great example of an integrated programme working at the nexus of humanitarian, development, peace and climate. FCDO should champion this programme and ensure that learning is captured and shared within FCDO, relevant networks, and build off the existing dissemination approach.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

The theory of change is based on the three outcomes of the programme:

1. Conflict Management and Land Governance: Supporting inclusive and legitimate land use in target localities and improving conflict management between communities and communities and institutions
2. Climate Adaptation: Mitigating structural drivers, including climate shocks, behind land conflicts, and
3. Policy Influence and Coalition Building: Strengthening the evidence-base for mitigating and resolving land and resource-based conflicts and building partnerships to deliver and scale up efforts to address fragility and support stability.
Impact: If these Outcomes are achieved then JASS will be able to prevent conflict turning violent in target localities while supporting sustainable livelihoods. More inclusive and legitimate use of land and of governance over land will help to reduce structural drivers of conflict, leading to improved stability and security in the Sahel.

Amendments to the Phase 1 original Theory of Change following an approved Business Case Addendum were documented in detail in the previous annual review; and reflected the geographic expansion of the programme to Niger and the inclusion of a more explicit reference to climate shocks and stressors as a structural driver and trigger for resource and land-based conflict.

The mid-term evaluation supported JASS's Theory of Change, with 94% of respondents now believing their community is peaceful and secure, an increase from 58% at baseline. The combination of logical framework results and qualitative data from key informant interviews and focus group discussions provide evidence to support the theory of change that “enhancing equitable land governance, strengthening climate resilience, and developing evidence-based policy approaches collectively contribute to improved security in the Sahel”. As such no proposed changes to the programme Theory of Change and Outcome and Impact indicators are proposed.

A study based on mid-term perception surveys of JASS participants provides some further confidence of the Theory of Change and the merits of focusing on strengthening inclusive context-specific conflict resolution systems, increasing community’s knowledge of these systems, and supporting bridging between locally legitimate dispute resolution mechanisms and formal legal and justice institutions.
[note] Perceptions of justice actors and conflict resolution mechanisms in Mali and Niger, April 2025.

The programme is on track to contribute to the expected outcomes and impact.

JASS has been operating within a challenging context in FY24/25; and has had to adapt to major challenges during the reporting period, including: Intensifying security threats in both Mali and Niger restricting movements in JASS programme areas and increase logistic costs, a deteriorating humanitarian situation across the region, which has increased pressure on JASS’s humanitarian activities such as recent major flooding, wider economic and political challenges.

Despite these challenges, JASS has been able to deliver good results; demonstrating the programme’s relevance in its focus on addressing multiple shock and stresses; and its continued ability to adapt its implementation strategies to changing contexts; a result of JASS’s flexible and adaptive programming approach.

JASS is contributing well to the 3 outcomes of the programme:

Outcome 1: Conflict Management and Land Governance: JASS has empowered communities to manage land disputes locally, with increased inclusion of women and marginalized groups. Respect for migratory routes and legal awareness has improved transparency and relations with authorities. It was reported in the last Steering Committee meeting that 95% of participants in JASS felt that use of natural resources was fairer and more equitable.

Outcome 2: Climate Adaptation: The programme contributed to improving resilience to climate shocks through climate-smart practices, diversified livelihoods, and cash-for-work initiatives, boosting food security and income. Total 5517 people were supported to better adapt to the effects of climate change.

Outcome 3: Policy Influence and Coalition Building: In Mali, JASS strengthened advocacy through research, leading to actions on women’s land rights and local governance. In Niger, coalition-building is emerging, with early steps toward coordinated advocacy. JASS has worked with stakeholders to develop guidelines and advocated for their buy-in for inclusive land governance, access to land and conflicts resolution. Particularly changes in policies are increased participation of women in COFOs and other decision-making bodies, improved women’s access to land, allocation of land to women by the municipalities, standardized agreements for COFOs homologation minutes, and secured municipal funding for COFOs operations.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

During this reporting period, JASS has delivered good results, despite a challenging security context. JASS’s triple nexus approach contributed to addressing the underlying causes of conflict and instability, which are either derived or exacerbated from climate change related impacts. This integrated approach has showed promising results according to programme reports and the Mid Term Evaluation (MTE), and the ongoing research generated under Output 3.

In a period of shrinking aid budgets, and as climate change and global insecurity continue to increase, it is pertinent that the UK using JASS as a model to learn from and build off in future programmes.

## C. DETAILED OUTPUT SCORING

Output Title	Improved conflict management capacity and collaboration among communities divided by conflict, and between them and institutions, to mitigate and resolve conflicts linked to land and natural resources.
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review / (March 25)	Progress / Source JASS Annual Report Annex 1
1.1: (Building trust) Percentage of men, women, adolescent boys and girls living in target communes who believe that those responsible for land conflict management in their commune are able to prevent and resolve conflicts in their community	89%	98.07% / (Mali 96% Niger 100%)
1.2: (representation) Percentage of people who report women and minority group are effectively represented and empowered in decision making institutions	73%	90.98%
1.3: (respect) Proportion of target communities that respect migration routes	77%	84.90%
1.4: (capacity building) Percentage of community members and leaders surveyed having knowledge of existing texts and laws on natural resources and land ownership	28%	42.64% / (Mali 26%, Niger 57%)
1.5: (state relations) Percentage of people living in target communes who believe that relations with the State and its designated local and technical authorities have improved as a result of the intervention	65%	85.80%
[note] NB: these are pastoral communities tradition seasonal migration paths.

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has met expectations and is scored A based on the activities contributing to the indicators in the table above and the activities summarised below:

Indicator 1.1 building trust: Through 76 participatory theatre performances across 24 communes, JASS reached over 11,000 people—51–57% of whom were women and 52% youth—raising awareness of how exclusion fuels instability. The Model Husband’s initiative trained 290 men from diverse ethnic and livelihood groups, linking gender norms to women’s roles in agriculture and fostering more equitable household and community dynamics.

Indicator 1.2 representation: JASS also strengthened local peace infrastructure through 146 community peace forums (120 in Mali, 26 in Niger) and 30 targeted peace initiatives, engaging 6,061 participants—41% of them women. These efforts have fostered inclusive dialogue and proactive conflict resolution, with communities increasingly turning to COFOs (les Commissions Foncières), CRCs, and traditional leaders rather than courts or security forces. The credibility of village chiefs has been revitalized, and 24 GESI action plans (20 in Mali, 4 in Niger) have raised women’s representation in COFOs and SCAP/RUs from 16% to 34%, embedding gender inclusion in local governance. This has led to a perception that women and minorities groups are better represented and empowered with 91% feedback that they felt it was better.

Indicator 1.3 respect: In addressing transhumance-related conflicts, JASS reached 3.16 million people through radio campaigns in Mali and Niger, promoting awareness of pastoral laws and mobility rights. In Mali, 5,739 km² were placed under community-agreed governance through pastoral conventions developed with government departments. Additionally, 37 km of transhumance corridors were physically demarcated, visibly reducing tensions over land use.

Indicator 1.4 capacity building: Strengthening COFO Capacities: JASS has trained 1,245 COFO members (1,028 in Mali, 217 in Niger), achieving 249% of the annual target and 415% of the programme-to-date target (2,075 trained vs. 500 planned), with participant knowledge scores on land legislation, mediation and inclusive decision-making rising from 30% to 83%. A key innovation has been shifting COFOs from project-dependent to state-owned structures. In 10 communes, COFO financing is now embedded in Social, Economic and Cultural Development Plans (PDSECs), complemented by community-led financing models. This has led to an average of a 42.6% of community members having understanding of key texts and laws on land ownership. Greater progress has been made in Niger due to the strength of the COFOs.

Indicator 1.5 state relations: JASS also strengthened vertical linkages between local COFOs and national institutions (Permanent Secretariat of the Agricultural Orientation Law (SP/LOA) in Mali, Permanent Secretariat of the Rural Code (SP/CR) in Niger), enabling grassroots experiences to inform national reforms and ensuring frameworks respond to local realities. Advocacy efforts, particularly around women’s and youth land access, have leveraged these ties to foster coherent governance ecosystems. Again, these efforts have led to a reported improvement in relations between the State and local authorities.

Strengthening land dispute resolution institutions and inter-institutional collaboration: JASS has worked to strengthen collaboration between COFOs and other conflict resolution mechanisms while enhancing the integration between informal and formal justice systems. A key pillar has been the expansion of the Early Warning and Early Response System (EWERS), which registered 330 alerts in Mali (188 from new communes) with an 84% resolution rate. Together, these initiatives have built inclusive, locally owned mechanisms for land management and conflict resolution, directly addressing exclusion and enhancing regional stability. Linking community mechanisms to courts, boosting legal legitimacy.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

No specific recommendations on this Output last year.

Recommendation for next year: JASS should focus on consolidating the support provided to COFOs and further strengthening the community financing models to ensure their sustainability and operational budgets beyond the life of the programme.

Output Title	Strengthened resilience to climate shocks and stressors to reduce frequency and impact of resource and land-based conflict in the Sahel.
Output number:		2	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review / (March 25)	Progress / Source JASS Annual Report Annex 1
2.1 (climate sensitive practices) Support climate sensitive, agricultural intensification on existing productive land and facilitate off-farm livelihood diversification to increase sustainable job-growth and reduce natural resource trigger points for conflict (MC)
2.1.1 Number of farmers and herders (MWBG) targeted across programme activities.	3500	6280
2.1.2 Percentage of farmers and herders surveyed who believe that the pressure on natural resources has been allayed by the intervention of the program.	65%	72.89% ((Mali 87%, Niger 58%)
2.1.3 Percentage of farmers whose positive change in agricultural production is attributed to the implementation of JASS II	65%	83.8%
2.1.4 Number of individuals (MWBG) targeted with support across livelihood diversification and market systems activities	800	960
2.2 (resilience to shocks) Support rural communities to access resources and knowledge needed to plan, act and cope to build resilience to climatic shocks and stressors
2.2.1 Number of hectares of natural resources restored in the context of climate change adaptation	80	889.05
2.2.2 Number of vulnerable households supported with cash to improve resilience against climate disaster	450	1350

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has achieved an A. There has been a significant progress in the delivery of this output as represented in the table above and the activities summarised below. To highlight some of the gains: there has been more efficient use of funding leading to greater number of people targeted (2.1.1). Scaling up of the Cash for Work Activities (CfW) has also led to a significant increase to number of hectares and number of households receiving cash (2.2.1 & 2.2.2).

Indicator 2.1: climate sensitive practices:

Intensifying Climate-Sensitive Agriculture and Pastoral Resilience:

In Mali, market gardening participation rose by 208% (from 300 to 625), offering sustainable livelihoods and reducing land encroachment in areas like Koutiala, M’Pessoba, and San. Climate-resilient techniques cut chemical input use by 85% without reducing yields. In San, local seed production increased by 70%, and seven cooperatives became certified seed producers, reintroducing resilient crops like groundnuts.

In Niger, 600 farmers (26% women) were trained in climate-resilient practices and received inputs. As a result, 75.3% reported improved soil fertility, 93% noted increased climate resilience, and 74.4% saw yield gains. Additionally, 45.3% diversified crops, 38.1% expanded arable land, and 23.3% improved land access for women and youth. JASS also rehabilitated 26 water points in Mali and 27 in Niger, easing pressure on pastoral resources.

Supporting Off-Farm Livelihoods through Value Chains:

JASS’s value chain support boosted off-farm livelihoods, especially for women, youth, and persons with disabilities. Incomes rose by 148% (from £303 to £752), and jobs increased from 26 to 35, with 16 apprentices trained. Knowledge scores rose from 25% to 84% in Mali and 40% to 85% in Niger.

Group revenues grew by 89% (from £1,805 to £3,406), creating 22 new jobs. In Bla and Touna, women-led groups-built market linkages in food and textiles. In Niger, 400 group members (including 199 women and 174 youth) generated incomes ranging from £523 to £781 per group.

Indicator 2.2: Resilience to shocks

Building Climate Resilience in Rural Communities: JASS significantly advanced climate resilience in Mali and Niger through integrated interventions. In Mali, 125 hectares of degraded land were rehabilitated using sustainable techniques like half-moons and zaï pits. In Niger, 600 participants, including 200 women and 212 youth, restored pastoral lands in conflict-prone areas. These efforts were embedded in formal governance structures, with state technical services overseeing design and implementation.

Cash-for-Work (CfW) activities: 500 participants in Mali (48% women) and 600 in Niger (35.3% women) used earnings to meet basic needs and stimulate local markets. In 2024, 436 hectares were recovered for restoration, involving 1,850 households and contributing to flood risk reduction.

Improving Natural Resource Management: In Mali, 20 associations (five women-led) received 42.5 million FCFA for reforestation and rainwater management. In Niger, eight CSOs received grants (~£2,872 each), engaging 2,216 people (62% women), promoting inclusive governance and reducing gender-based exclusion.

Strengthening Disaster Preparedness: JASS established 20 Community Early Warning Systems and 4 Village Monitoring Observatories, equipping them with tools and income-generating plans. Municipal multi-risk emergency plans were developed and validated, restoring trust in local institutions.

Humanitarian Response and Impact: Following 2024 floods, JASS supported 430 vulnerable households in Tahoua and Maradi with non-food items and emergency stock systems. These holistic efforts improved social cohesion and resource management.

Resilience Outcomes: Mid-term evaluation shows 47% of households now feel able to cope with future shocks, up from 13% at baseline. Among programme participants, this rises to 53%, compared to 37% for non-participants.

This holistic approach working across a range of different entry points has helped improve social cohesion, resource management, and restore faith in local systems. The mid-term evaluation found that 47% of households feel able to cope with future shocks (Economic, Environmental, and Conflict related), up from 13% at baseline. Among programme participants, this figure rises to 53%, compared to 37% for non-participants.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

The scale-up into Niger required additional resource allocation and partner onboarding processes. Mercy Corps applied VfM principles to harmonise tools, streamline coordination across country teams, and ensure consistency in partner management, cost monitoring, and reporting. Based on the recommendations from the Mid-Term evaluation, minor adjustments were made to the programme log frame and indicator framework (such as the addition of new conflict incident tracking indicators, reclassification of indicators within the results chain) to strengthen the measurement of outcomes, improve consistency, and ensure data remains relevant for adaptive management and VfM analysis.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

See Annex A for recommendations from previous AR (Recommendations 4,5,6 and 7 pertain to this Output. For next year:

Recommendation: Mercy Corps should look for opportunities to reduce the reliance on cash for work as a model, to transition to more community engagement, demonstration sites, and behaviour change strategies, with facilitation done increasingly by technical services.

Output Title	Improved evidence base for more effective stabilisation programme design, delivery and coordinated action among key stakeholders.
Output number:		3	Output Score:	A
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review / (March 25)	Progress / Source JASS Annual Report Annex 1
3.1 (evidence) Develop the evidence base for action among key local, national, and international stakeholders in relation to land and natural resource governance/conflicts and resilience to climate shocks
3.1.1 Number of research products produced and disseminated	10	17
3.1.2 Number of pilot initiatives launched by program during implementation	1	1
3.1.4 Number of climate change adaptation tools, technologies and methodologies developed, tested and/or adopted as a result of program assistance	3	9
3.2 (coalition building) Support inclusive coalition building and effective platforms for knowledge sharing, scalable action, and advocacy in relation to land and natural resource governance/conflicts and resilience to climate shocks
3.2.1 Number of relevant organisations participating in coalition building actions initiated by JASS by the end of intervention	30	47
3.2.2 Number and type of joint outputs (position papers, advocacy campaigns, events) delivered by coalition(s)	3	9

Briefly describe the output’s activities and provide supporting narrative for the score.

This output has met expectation and is scores as A. In the reporting period, JASS published above the expected number of publications, addressing evidence gaps, including in the climate-conflict-governance nexus, and stabilisation field, and has formed a number of strategic partnerships, and joint research products. Output 1 comprises two areas:

Indicator 3.1 (evidence): JASS advanced evidence-based action by producing influential research to guide interventions. A flagship study in Niger (April–August 2024) assessed 25 years of environmental change, revealing that agricultural expansion is accelerating vegetation and water degradation, heightening conflict risks. These findings directly informed Cash-for-Work activities and supported local authorities in making more sustainable land management decisions.

In Mali, research focused on inclusive governance. A participatory workshop in Bamako (September 2024) highlighted how exclusion of women and marginalized groups from land governance fuels instability. Recommendations from this workshop shaped JASS’s programming to improve women’s land access and participation in decision-making.

Surveys across seven communes in both countries showed that JASS interventions have increased trust in community-based justice systems like COFOs and CRCs, reducing pressure on formal courts. A quasi-experimental study (March 2025) confirmed that communities prefer inclusive, local governance models over centralized systems, viewing them as more equitable and climate resilient.

Indicator 3.2 Coalition Building: In Mali, JASS partnered with the National Judicial Training Institute (INFJ) to address inconsistencies in land conflict resolution. A new training module on land law led to the certification of six trainers and training of 95 judicial and local actors. A Guide for COFO Homologation was finalized in February 2025, standardizing court validation of local agreements.

JASS also co-developed a Guide for Women’s and Youth Access to Developed Agricultural Lands, validated by national ministries in December 2024.

In Niger, JASS supported the launch of the National Rural Code Committee’s web portal and helped establish a multi-stakeholder land governance consultation framework via ministerial decree, enhancing transparency, coordination, and inclusive policy implementation.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation: Mercy Corps would continue to ensure that evidence is being strategically used for national and international advocacy efforts and to institutionalise reforms and scale proven approaches.

D: VALUE FOR MONEY

Throughout the lifetime of the programme, Mercy Corps, in consortium with the downstream partners, have been committed to efforts that enhance value for money and maximize the impact of FCDO funding.

Economy

Key Findings: With a budget of £6,014,666, the programme reached 37,500 participants at an average cost of £160 per beneficiary, covering 485 villages across 24 communes in Mali and Niger. Operating cost rose from 29% to 46% of the budget due to expansion into Niger and inflationary pressures. Expansion required onboarding new partners, conducting context analysis, and establishing frameworks with local authorities. Mercy Corps secured long-term agreements for key services to stabilise costs and in part mitigate inflation pressures.

Economy Indicators:

The operations costs have increased to 46% of the total programme budget, from 29% last year, an approximate 50% increase as the expansion in Niger added new areas of operation in Maradi and Tahoua. While this expansion has allowed for greater reach and programme scale-up, it has also required additional investment in partner onboarding, context analysis, security risk management, and the establishment of new operational frameworks with Cercle Dev and local authorities.
In addition, inflation, fuel shortages, electricity cuts, currency fluctuations and supply chain disruptions have continued to drive higher than anticipated operational costs, longer procurement lead times, and increasingly complex logistics compared to the situation assessed in 2022.

To manage these increasing costs Mercy Corps proactively strengthened internal cost reviews and secured long-term/master agreements for key expenses such as lodging, supplies, catering and vehicle rentals. This ensured that best prices were being obtained despite challenges.

Efficiency

Key Findings: Despite instability, the programme scaled up delivery, working with two downstream partners under a single management structure reduced overhead. JASS adapted input distribution based on actual farmer needs, increasing reach and reducing waste.

Efficiency gains:
- Seed allocation adjustment: The programme has carefully reviewed the actual needs of farmers before the distribution of inputs resulting in an increased number of participants and efficient distribution of available climate-smart inputs. In Mali, seed costs per farmer reduced from £40 to £26 allowing support to 500 farmers instead of 300.
- Staff restructuring: Discontinuing certain international roles and nationalising others saved £68,777, which was reinvested in project-dedicated roles like Learning Specialist and Climate Resilience Manager. The savings have been strategically reallocated to establish/strengthen positions that are 100% dedicated to the project, such as the Learning Specialist, Climate Resilience and Adaptation Manager, Communication and Research Officers. This has also resulted in increased cost allocation to programme activities versus support cost.
Effectiveness

Key findings: The JASS programme has been making a concerted effort to deliver in a complex context, adapt the programme to the constraints and manage to keep delivery going despite increasing delivery risk. JASS's transformative work on land conflicts was successful in both preventing conflict by strengthening the underlying rules, laws and frameworks governing land, whilst encouraging and enabling the use of non-violent judicial means to resolving continued land disputes. The effectiveness of the programme can be seen through building trust between communities and authorities. This has led to better management of the negative external effects related to access to land and natural resources, climate effects and improved living conditions through the creation of economic opportunities.

Effectiveness indicators:
- Gender and youth inclusion: 43% of participants were women; youth participation was also significant.
- Economic empowerment: Improved livelihoods and resilience through market linkages and value chain development.
- Land restoration: Despite rising costs (£1,920/ha), more land was restored using efficient Cash for Work and seed distribution.
- Training scale-up: 830 COFO members trained (vs. 500 planned) by increasing session sizes and hosting them locally.
- Revenue growth: As part of the training and sensitisation delivered through the programme vendor revenues rose by 275% (£225 to £617). Producer groups revenues in Mali increased by 89% (£1,805 to £3,406). Animal feed banks stocked with 60 tonnes of wheat bran which could help reduced conflict along transhumance routes.
- Women-led IGAs: In Niger, 20 farmer groups (50% women) generated £523–£781 per group, reviving previously inactive groups.

Equity

The targets set out in the Gender Action Plan include addressing social norms and practices, promotion of more inclusive land and natural resources governance and other outlined in the plan are being reached. It has been reported that 91% of the expected targets in the Gender Action Plan have been met. In addition, 45% of livelihood diversification and agricultural intensification support is going to marginalised groups (including women or older adolescent girls). This demonstrates that the programme is making good progress towards its inclusion objectives.

JASS Programme has helped communities mitigate and resolve conflicts by improving equitable and inclusive land, natural resource governance and justice outcomes for marginalised groups (women, young people, people living with disabilities, IDPs, allochthones).

The programme also expanded inclusivity (women’s representation reached 30.43%, youth 49.67%), standardised land documentation, and introduced formal conciliation procedures. All these activities have helped JASS transform what were often ad hoc bodies into credible and effective governance institutions.

In collaboration with the Norwegian Refugee Council (NRC) a guide for the allocation under the 15% law has been developed and validated. In the third year of the project, JASS will support the implementation of this guide with the commitment of three ministries (Agriculture, Women's Promotion, and Youth) for the issuance of an inter-ministerial circular.

The Mid-term evaluation shows there is a positive impact from these economic opportunities, with 91% of youth participating in programme activities reporting improved life prospects as a result of JASS interventions. In both Mali and Niger, 216 Gender Champions, Guardians and Focal Points engage directly with communities to promote participant rights and safe reporting. Both countries have fully operational Community Accountability and Reporting Mechanisms (CARM), with multiple reporting channels available, including toll-free hotlines, WhatsApp numbers, suggestion boxes, and field-level committees or ambassadors who collect and escalate feedback.

VfM performance compared to the original VfM proposition in the business case

A strength of the JASS’s inclusive approach in Mali and Niger is engaging women, youth, ethnic minorities, and displaced communities in governance and resource decisions. JASS has fostered legitimacy, trust, and collaboration, with women’s representation increasing from 16% to 33%, and 80% of respondents affirmed effective inclusion. Economic alternatives empowered vulnerable groups, with 91% of youth reporting improved economic prospects. These outcomes demonstrate strong VfM through equity-driven interventions even in a context of rising costs and increasing insecurity.

Assessment of whether the programme continues to represent value for money

The JASS team has also made efforts to improve delivery over this reporting period. It is critical to monitor the increasing input cost due to inflation including increasing transport costs, currency fluctuations and disruption of supply chains. The fact there are positive signs of the programme delivering towards Outcomes and meeting the Outputs within budget. During the latter stages of this phase of the programme learning from the approach should be used to help define other programme particularly the integrated nature of the programme, the community level conflict management approaches and the impact of the evidence papers. Also, it would be worth while having a strong monitoring and reporting of agreed VFM indicators.

E: RISK

The programme risk appetite remains in-line with the risk appetites for 4SD. The overall risk appetite for the programme remains moderate. The FCDO programme team actively monitors risks and mitigating measures through regular discussions with Mercy Corps, quarterly progress reports and steering committee meetings.

The mains risks during this reporting period were:

Strategy and Context - Growing unpredictability in operating context in both countries, including the temporary suspension of Mercy Corp’s operations in Niger in August 2024. To mitigate against this, several measures were introduced including, “Niger Contingency Plan2 which was updated to enhance crisis preparedness, including revised travel protocols, organisational profiling, and communication strategies.

Public Service Delivery and Operations – Security continues to be a key risk and events, such as attacks on gendarmerie camp, Bamako’s Modibo Keita International Airport, are exacerbating the risk and leading to: movement restrictions, including requirements for armed escorts or state accompaniment, complicating logistics and inflating operational costs and timelines. However, the impact on JASS operations remained limited as Mercy Corp’s has demonstrated adaptability enabling planned activities to continue without major delays or slippages.

Public Service Delivery and Operations – The USAID budget cuts have impacted on partners’ operations and staffing numbers. This poses a risk on their ability to deliver, manage and monitor activities and downstream partners. FCDO Sahel team has worked closely with partners to understand the impact on FCDO funded programmes and ensure that there are mitigation measures in place to manage the risks.

Operations: In Mali there is an emerging risk of the proposed 10% levy that could impact on all NGOs operating in Mali. FCDO is working with partners/stakeholders (UN and other donors) to highlight the proposed risks of such a levy on NGOs being able to implement activities.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Adam Smith International (ASI), Mercy Corps’ subrecipient for certain components during the initial phase of JASS was replaced at the start of Phase 2 (April 2023) based on value for money (VfM) considerations and a strategic decision to enhance the programme localisation approach by partnering with and strengthening national capacities. This change allowed for more direct programme ownership and capacity building of downstream partners.

Mercy Corps (lead), AMEDD (Mali) and Cercle Dev (Niger) continued to collaborate well during this reporting period. To ensure close collaboration between the two countries, a Programme Management Unit (PMU) was set up, with the objective to ensure the sound technical, administrative and financial management of the programme, ensuring its proper implementation, compliance with donor procedures and the achievement of the results set. For instance, a review of the workplan by all partners ensured relevance and alignment in delivery, and day-to-day communication between partners ensured smooth technical and operational delivery. Quarterly meetings with FCDO team also helped add in regular review points to check on progress and project alignment.

Partners AMEDD in Mali and Cercle Dev in Niger have also been fully integrated into Mercy Corps’ safeguarding framework. Both organisations have undergone joint safeguarding assessments, and their staff have received safeguarding training, while Mercy Corps maintains regular monitoring to ensure compliance and continuous capacity strengthening where needed. Mercy Corps has also signed a protocol with AMEDD for Community Accountability Reporting Mechanism (CARM) information sharing.

In Niger, three new roles were created and filled in 2024, partner liaison, gender and social inclusion, and Research/MEL. MEL activities were consolidated under a more senior person resulting in efficiency gains. In Mali, new cross-country roles were created, including Climate Adaptation and Research Managers, reflected the programme’s integrated focus. Additional hires—a Community Accountability Assistant and Coalition Building Officer—strengthened participatory governance. The promotion of a Finance Assistant to Officer, strengthened financial capacity. In addition, Mercy Corp’s engaged interns to cover short-term staffing gaps.

In October 2024, Mercy Corp’s elevated JASS was to a complex programme under the supervision of a Complex Programme Support Board. This translated into increased support and oversight from Mercy Corps HQ and global support functions. Following USAID cuts, in April 2025, as part of Mercy Corps’ broader organisational realignment across West and Central Africa, both Mali and Niger transitioned to a nationalised country leadership structure. While the nationalisation of leadership positions ensures greater cost effectiveness, it also translates into contextual expertise, stronger field presence, and closer relationships with local authorities and stakeholders.

Finance

JASS’s overall spend for 2024-2025 financial year was £6 million against an initial budget of £5.7 million with a 105% burn rate. During this reporting period JASS absorbed an additional £600,000 for a Resilience and Adaptation Fund (RAF) JASS leverages this RAF funding to strengthen community resilience and stability in Central Mali and the Tarka Valey in Niger, enabling us to directly support 4,634 people (reaching 2,006 women) to better adapt to the effects of climate change.

During this reporting period, financial management improved, with timely submission of advance fund requests, and close management of the budget against a backdrop of high inflation and increasing costs related to the security situation. Disbursement arrangements are structured around quarterly advances, based on approved workplans and detailed financial forecasts submitted by the partners. There were some discrepancies between forecasts and quarterly expenditures, but the differences were not significant as they remain around 10%. Each disbursement request was accompanied by a status of funds report detailing previous expenditures, reviewed and approved in line with Mercy Corps’ authority matrix prior to release of funds.

As inflation, currency fluctuations, and logistics disruptions increased in both Mali and Niger, Mercy Corps implemented stricter procurement planning, enhanced budget monitoring with close support from HQ, and closely coordinated supply chains to minimise cost overruns while preserving delivery quality.

Operational flexibility and cost optimisation

Mercy Corps has implemented cost management and continuous analysis of operational efficiency within the project and within our wider country structures. Efforts have been made on cost structure and targeted adjustments to maximise impact with available resources without compromising quality or impacting the activities/support ratio. As discussed with FCDO, country team structures for the Sahel region was adapted as a result of donor budget cuts, and the staffing changes have been reflected in the latest JASS budget resulting in cost savings. The initial March 2023 budget for JASS presented a Program to Support cost ratio of 62%/38%. Through subsequent adjustments, FY24/25 effectively achieved an overall ratio of 67%/33%.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

During this period, a mid-term evaluation was conducted, providing insights into the relevance, coherence, effectiveness, efficiency, and sustainability of the programme. In response to the MTE recommendations, JASS has made a number of adjustments to the programme logical framework to enhance clarity, consistency, and alignment with available data. These adjustments including strengthening conflict incident tracking in Niger, realignment of several indicators between the “Results” and “Outputs” levels to better reflect their position within the programme’s results chain, an impartial review of International Climate Finance Key Performance Indicators.

Evidence and Learning

JASS has invested heavily in research efforts, findings from which were used to inform programming. Evidence is shared within the programme through Quarterly steering committees, publications and dedicated learning events. Learning also takes place through regular updates and joint problem-solving. In addition, research findings have been successfully leveraged for advocacy and used in support of other stakeholders' interventions (see Output 3 for more detail).

Key lessons learnt over this reporting period include:
The JASS programme shows working on climate adaptation can help reduce conflict triggers: 88% report lower water tensions post-rehabilitation, down from 78% citing water as a conflict trigger. Respect for pastoral paths rose from 57% to 80%, showing land-use improvements ease pressure on contested areas and revive traditional norms, supporting the hypothesis that adaptation addresses conflict’s root causes.

Building Coalitions for Lasting Change: Over the past year, JASS has refined its advocacy strategy, recognizing that sustained policy influence depends more on trusted institutional relationships than on technical research dissemination alone. Initial efforts focused on outputs proved limited without strong stakeholder engagement. JASS has since learned that aligning with institutional champions and building strategic coalitions significantly accelerates policy change. In this final year of the programme, JASS should continue to build on these efforts.

Anticipating Seasonal Conflict Hotspots: Analysis of JASS’s Early Warning and Response System (EWER/SAP) data has revealed clear seasonal conflict patterns, enabling more targeted and timely prevention. This insight now guides initiatives such as expanding land mediation in high-risk areas, pre-emptive conflict resolution during peak months, improved flood preparedness in vulnerable communes, and stronger coordination between authorities and local mediators.

Planned learning for 25/26
This is a list of planned learning activities as part of the JASS activities will be carried out as part of the implementation of the final stage of the programme:

- Perceptions of justice actors and mechanisms and understanding of the concepts of "justice" and "equity";
- Role and narrative of women in decision-making bodies, particularly within the COFO, and what "participation" means in theory and practice.
- Types of disabilities and barriers to better access natural resources by PLWD in Mali and Niger in partnership with the national federations of people with disabilities (FEMAPH and FNPH, respectively).
- Financing mechanism for Niger's Rural Land Policy
- Updating the institutional framework of the SP CNCR (Niger), enabling the empowerment of land commissions and understanding their impact.
- JASS will also support the research work of partner research institutions (Universities of Niamey, Tahoua, and Maradi in Niger - IPR/IFRA and the EMP - Peacekeeping School in Mali) and will support publications in the EMP journal, in addition to supporting the production of 10 policy briefs and scientific articles related to stability and climate resilience in the Sahel.
- For the final year of the programme the JASS team and FCDO will work together to better capture learning and strategic impact of the programme using the key research papers, organising learning sessions as part of the steering committees and jointly develop a plan / final learning workshop.
Date of last narrative financial report	30 April 2025	Date of last audited annual statement	08 November 2024

Annex A Updates on last year recommendations

Recommendation	Status
Recommendation 1: Finalise evaluation of and reporting against the outputs as much as possible in time for the next annual review.	Completed – In the past year JASS has reviewed and finalised reporting of outputs and aligned to FCDO annual reporting periods.
Recommendation 2: Differentiate in reporting between Mali and Niger to reflect the difference in the nature of the conflict, the applicable legislative framework, and the difference in the maturity model of the programme in the two countries.	Completed – Over the reporting period, the global MEL team at Mercy Corps worked with the JASS team to review and refresh the reporting structure to report on each country specifically to reflect the local contexts, and different levels of maturity of the programme.
Recommendation 3: While formal additional research should not expose implementing partners to unnecessary risks, the mid-term evaluation could test perceptions of VEOs and the pull factor that violent extremism has in the communities subject to JASS interventions. Such research could be used to make recommendations for delivery of Results 1 and 2.	Completed – The mid-term evaluation questionnaire was expanded to include bout perceptions of violence and security (qualitative and quantitative tools). Additionally, JASS conducted three studies (on perceptions of VE, perceptions of justice, and a quasi-experimental study). Findings from which have been used to inform programming.
Recommendation 4: As per Recommendation 1 of last year’s annual review, the mid-term evaluation should test whether the new climate adaptation activities, including the Cash for Work element, are contributing to the results and outcome of the programme, how to create synergies with Output 1 (conflict management) and Output 3 (evidence), and that those activities improve climate security in the target regions.	Completed - The mid-term evaluation tested whether the new climate adaptation activities, including the Cash for Work element, are contributing to the results and outcome of the programme.
Recommendation 5: Work should continue to identify suitable International Climate Finance Key Performance Indicators and reflecting those in the log frame.	Completed – Through the CLEAN helpdesk, an assessment was conducted to identify activities which could be included under ICF KPIs. Four appropriate ICF KPIs were identified, but it was determined that given where the programme was, reporting against ICF KPI 11 and 17 was most appropriate. These indicators have been incorporated into the log frame.
Recommendation 6: At the mid-term evaluation, consideration should be given to how Output 2 can include measurement of GESI outputs.	Completed – The mid-term evaluation terms of reference included this need and provided subsequent recommendations. The activity reports now provide disaggregated information
Recommendation 7: As activities for this programme and specifically under the CFW scheme are expanded, the potential negative unintended consequences of these expanded activities need to be monitored and mitigated. A conflict sensitivity lens should be applied to the choice of beneficiaries, the activities, and the outputs from those activities.	Completed - Ongoing monitoring of results and activities to prevent social or environmental tensions. Furthermore, a community feedback system is in place to adjust actions and ensure positive and sustainable effects.
Recommendation 8: For activities going forward, especially as the programme is rolled out in Niger, it is important to ensure that implementation considers the competencies and remits of the local and central institutions.	Completed – The implementation of activities considers the existing capacity of institutions and through output 3 looks at how coalitions can help strengthen capacity.
Recommendation 9: Future research under Result and Output 3, should include a study of what, if anything, increases people's trust in formal justice systems and any impactful approaches for achieving this.	Completed - JASS has conducted three studies (on the perception of Violence, the perception of justice, and a quasi-experimental study), the reports of which have been shared with the annual report.
Recommendation 10: Mercy Corps and partners should clarify the segmentation approach and its communication strategies vis-à-vis the different stakeholder groups and leverage on popular and widely accessible channels to further share good practices on innovative climate resilience activities and social inclusion.	Completed – Throughout this reporting period, JASS has used a range of approaches to inform communication. For instance, before the herder/pastoralist movement south, JASS recorded radio programmes to sensitise communities which has helped reduce conflict.
Recommendation 11: Mercy Corps and partners should tailor and strengthen the institutional advocacy and policy engagement to advocate for granting of 15% of land developed by the State for women and youth communities.	Completed - In collaboration with NRC, a guide for the allocation under the 15% law has been developed and validated. In the third year of the project, JASS will support the implementation of this guide with the commitment of three ministries (Agriculture, Women's Promotion, and Youth) for the issuance of an inter-ministerial circular.
Recommendation 12: Mercy Corps should improve internal communication on finance management and enhance programme delivery, ensure diligent execution and timely reporting especially for FYII when Mercy Corps aspires to receive a potential additional financial envelope from the RAF.	Completed - Monthly meetings were organized starting from July 2024. The classification of the JASS as a complex program was approved in September 2024. A board of directors was established and now meets monthly bringing together key colleagues from MC HQ, Mali, Niger and regional colleagues to improve internal communication on finance
Recommendation 13: For contractual arrangement on pre-payment, Mercy Corp should transmit fund advance request alongside quarterly financial reports and forecast and share more accurate/realistic forecasts and timely QPR and responses to FCDO’s feedback	Completed - The director of international finances helped the team to coordinate the revision of the budgets for fiscal year 2 and fiscal year 3. More accurate and realistic budget forecasts were organized. General information and the financial report were sent at the same time as the quarterly report.