## Annual Review Template

Title: Demographic Transition in Iraq Programme (DTIP)
Programme Value £ (full life): up to £35m		Review date: 19 August 2025
Programme Code: 301255	AMP start date: 19/08/2021	AMP end date: 31/03/2026

Summary of Programme Performance
Year	August 2022	August 2023	August 2024	August 2025
Overall Output Score	A	B	A	A
Risk Rating	Moderate	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business Case and Summary
DevTracker Link to results framework:	Logframe March 2024

A. SUMMARY AND OVERVIEW

Programme summary
Summary
The Demographic Transition in Iraq Programme is a five-year programme implemented by the UN Population Fund (UNFPA). The programme aims to increase access to, quality of and demand for voluntary family planning services, whilst also tackling early marriage and violence against women and girls. The programme does this by providing support, primarily to the Ministry of Health, on policies and systems, improving quality of training and facilities for training for healthcare staff, conducting awareness raising and providing support to the most vulnerable in humanitarian settings.

Objectives and programme logic
Overall, the programme will support Iraq’s demographic transition, reinforcing wider development gains and political stability by addressing the barriers which prevent women and men from utilising voluntary family planning (VFP) services. The programme will:
- tackle the bottlenecks in VFP service delivery;
- increase awareness of VFP services; and
- improve the evidence base for the efficacy of VFP services in Iraq.

This will enable individuals and couples to take control of their reproductive choices, and therefore:
- improve health outcomes for women and infants;
- increase financial resilience of households;
- reduce some of the barriers that prevent adolescent girls from staying in education;
- increase fiscal space for public services (oil revenue dependent); and
- contribute to Iraq’s resilience against climate change impacts on population growth.

The reduction in ODA has resulted in key changes to this programme. This Annual Review reflects that the programme has had to refocus resources and so will deliver against a new plan with new results targets. As a result, the findings of this Annual Review reflect on a programme in transition.

About changes to UK ODA
- At this time of profound change, with conflicts overseas undermining security and prosperity, the UK Prime Minister has taken the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027, to help smooth the transition.
- The UK remains fully committed to playing a globally significant role in humanitarian aid and development. The transition to spending 0.3% of GNI on ODA will require significant shifts, building on those already underway as the government implements its modernised approach to development, which centres on establishing long-term partnerships based on mutual interests and respect.
- ODA allocations and the impact on programmes are being worked through based on various factors, including impact assessments. We will be taking a rigorous approach to ensure all ODA delivers value for money and maximises the impact of our work to best support the people it benefits, including those in humanitarian crises.
- We remain committed to spending 0.7% of GNI on ODA when the fiscal circumstances allow.
Programme context and key changes
The context in which DTIP was delivered over the reporting period (1st April 2024 – 31st March 2025) was characterised by several key trends and events:

- UN and UNFPA strategy: Over the reporting period the UN has developed a new Sustainable Development and Cooperation Framework (UNSDCF) (2025-2029), which emphasises the transition away from humanitarian support in Iraq and an increased focus on technical assistance. In early 2025, UNFPA launched its new country programme document (CPD), which, in line with the UNSDCF, emphasises a shift from service delivery to systems strengthening and providing technical support at the national level to enable government service delivery. The outcomes under the CPD are: 1) institutional strengthening; 2) service quality and integration; and 3) harmful norms and social behaviours.
- Census: In November 2024, Iraq conducted its first full census in 37 years. The census noted a total population of Iraqis of 46.1m, with an equal balance between men and women. Approximately 70% of Iraqis live in urban areas and 35.9% are aged 0-14. Although the census demonstrates shrinkage in the youngest age groups in comparison to the 1987 census, it underlines the significant proportion of working age Iraqis (approx. 60% aged 15-64). The annual population growth rate remains 2.3%. UNFPA provided technical support to the census, including on the census design, implementation and follow-up.
- Expedited returns from Syria: Following the fall of the Assad regime in December 2024, the GoI has expedited returns of Iraqis from Al Hol and Al Roj camps in Northeast Syria to Al Amal Rehabilitation Centre in Nineweh, Iraq. Expedited returns, whilst welcomed by the international community, have put pressure on infrastructure and services in Al Amal Rehabilitation Centre.
- US funding: In January 2025, the US announced a review of Federal Foreign Assistance. In February, the US defunded UNFPA globally[1].
  [1] Statement by UNFPA Executive Director on the United States Government funding cuts

Key results
Over the reporting period the following key results were achieved:
- UNFPA supported a conference in Baghdad where the results of the census were launched. The conference secured high-level attendance from the Government of Iraq and profiled experts from the UK and Saudi Arabia.
- UNFPA secured government buy-in for the rollout of the Adolescent Girls’ Toolkit, a manual containing life skills information that can be used by social workers, school health facilitators and others to disseminate key messages to adolescent girls. 20,404 girls were reached with this messaging.
- 1,660,000 people were reached with family planning messages on UNFPA’s social media and 248,084 people were reached through a collaborative online campaign with the Ministry of Health.
- 318,872 reproductive health beneficiaries were reached by graduates of UNFPA-supported centres of excellence[2].
  [2] Centres of excellence are public healthcare facilities that have been upgraded to offer maternal and reproductive health training and comprehensive service provision.
- 80,272 young people received counselling, including family planning and reproductive health messages and referrals through primary healthcare centres.
- Preparatory work to digitalise the contraceptive commodity supply chain was completed, training on the digital system rolled out and the system made pre-operational in 46 districts, 40 district warehouses and 6 governorate warehouses.
- Critical maternal and reproductive health, and VAWG services were maintained and delivered in Al Amal Rehabilitation Centre.

Results continued to be underpinned by strong collaboration with, and technical support to, the Ministry of Health and wider government ministries and committees, as well as a comprehensive approach to behaviour change communication and training to support the results noted above.

Summary supporting narrative for the overall score in this review:

Across the board, UNFPA delivered an impressive range of interventions, whilst adapting to the context. A more comprehensive results framework refresh, alongside iterative updates as required, would have helped better evidence programme performance this year. A full refresh is underway for the next reporting period which should help better reflect plans and performance over the coming reporting period. Nevertheless, performance this year has led to an overall score of A.

Across the various outputs UNFPA’s expertise and interventions have:
- Secured Government support for and increased prioritisation of family planning, as evidenced in increased budget allocations;
- Increased quality of family planning service provision through support to guidelines, government staff training, and provision of training facilities;
- Developed and implemented an evidence-based, culturally-sensitive behaviour change communications strategy via digital media and in-person communication methods;
- Provided tailored messaging and training to support youth via the adolescent girls’ toolkit and youth counselling services;
- Supported the digitalisation of supply chains, which will enable more efficient and evidence-based procurement and supply management;
- Delivered critical services to women and girls in Al Amal.
Major lessons and recommendations for the year ahead

Major Lessons learned:
- The coming year will be the final year of the DTIP business case. As such, FCDO and UNFPA have worked together to define a prioritised list of activities for FY 25/26 that build on DTIP’s successes to date, finalise key activities and respond to the latest priorities in the current context.
- Stronger and continued coordination with national institutions, particularly the Ministries of Health, Education and Planning, is critical. Earlier buy-in and defined roles could have improved ownership and accelerated policy integration. Training frontline workers (e.g. health workers and school educators) yielded strong results, but sustaining these outcomes requires systemic support from national institutions/MOH and long-term domestic investment. The key to the sustainability of DTIP interventions is supporting the government to embed activities, policies and practices within their systems, whilst enabling them to make the case for funding for this.
- Socio-Cultural sensitivity enhances programme acceptance. Community engagement and culturally sensitive messaging were crucial for programme acceptance, particularly in youth and reproductive health interventions. This approach should be deepened in future designs to ensure inclusive and trusted service delivery.
Recommendations for year ahead:
- Prioritise Core Activities: DTIP should focus its remaining resources on high-impact, scalable, and sustainable activities, as well as on developing systems and evidence that will support the government beyond the lifetime of the programme. Additionally, the programme should seek to support high priority issues for the Government, i.e. the census and support to Al Amal.
- Formalise the Exit Strategy: UNFPA should develop a clear exit and sustainability plan by Q3, in collaboration with FCDO and MoH, including handover timelines, methodologies, and documentation to be shared with national counterparts.
- Leverage the 2024 Census Results to Drive Policy and Programming: The results of Iraq’s census are expected to significantly enhance data availability and demographic analysis. FCDO and UNFPA should advocate for the integration of census insights into national planning, including future national reproductive health and youth development strategies, to ensure investments are evidence-based and geographically targeted.
- Institutionalise Successful Models within Government Systems: Finalise and embed DTIP-supported tools, including the eLMIS, Adolescent Girls Toolkit and BCC materials, into formal Ministry of Health and Education systems.
- Resolve the issue of the DTIP-funded intrauterine device (IUD) consignment held at Baghdad airport: DTIP previously procured a consignment of IUDs, which were held at Baghdad International Airport due to bureaucratic challenges. As part of exit planning, efforts should be increased to find a solution for this issue.
- Capture and share Legacy Knowledge and Learning: Produce a final DTIP report (Programme Completion Review), including beneficiary insights and government feedback. Host a national-level dissemination event in collaboration with MoH and other partners to formally close the programme (Closure Ceremony) and ensure visibility of its contributions. Ensure tools, training materials, and M&E resources are available digitally and archived with the MoH for long-term use and internally for audit.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

According to the business case the theory of change can be summarised as follows:
If FCDO supports VFP in Iraq by (a) capacity building, (b) technical assistance, (c) provision of VFP in humanitarian contexts, (d) increased knowledge of VFP services, and (e) increased willingness to access these services in Iraq (programmatic outputs). FCDO will empower more households to make informed decision about their reproductive choices. Which will (a) improve the health of women and children, (b) increase the likelihood that girls can stay in education, (c) increase household financial resilience, (d) increase fiscal space for public service provision, and (e) reduce environmental degradation.

The theory of change from the DTIP business case is below:

The ToC logic still holds and there have been no changes to the theory of change during the reporting period. The outcome and impact statements remain relevant to the intervention being delivered. The assumptions underpinning the theory of change are also still relevant, with the exception of the assumption that supply-side constraints are effectively mitigated by the programme. Ongoing work to digitalise contraceptive commodity supply chains should help support this, but the programme is no longer actively procuring contraceptive supplies or managing supply chains directly.

Since the programme started, humanitarian interventions have decreased, reflecting the broader transition from humanitarian to development in Iraq. During the reporting period, the programme retained a small humanitarian intervention in Al Amal. Funding for the programme has also been much reduced since the original business case, which has necessitated a prioritisation of activities.

Over the reporting period, UNFPA and FCDO have sought to maximise programme impact through engagement with stakeholders, engaging government counterparts, including on programme design for the coming reporting period, to support buy-in for current and future programme activities, and ensure these were tailored to needs and priorities.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

A full assessment of impact and outcome indicators has been hindered by the lack of available data at the national level. Where available, or alternative data has been able to be sourced, progress has been assessed below. At the time of writing, the annual report from the Ministry of Health was yet to be released, which affects data for impact indicators 2-7. Once, received, this data will be assessed against targets with UNFPA to: a) define reasonable targets for 2026, b) assess whether any adjustments to the programme are needed to help better address areas where progress has been limited.

2025 targets have also not been set at impact and outcome level for every indicator in the results framework. This reflects the high-level nature of impacts and outcome indicators, as well as expected timeframes for progress and monitoring. Progress against indicators is expected to evolve gradually over time, given the number of underlying factors contributing to these, and the longer-term impacts we expect DTIP to have.
Overall, this does make it difficult to assess the extent to which the theory of change is being validated by programme delivery at this stage. However, some positive trajectories can be assessed from the data available:
- Since programme inception, the Government has now assumed full responsibility for public sector contraceptive commodity procurement.
- Government spending on family planning has increased beyond stated targets (see output 1.1).
- The % of modern contraceptive prevalence provided for by the public sector has increased, already far exceeding 2026 targets.
On the last point, while the trend is encouraging, UNFPA note that this is an estimate derived from available public service delivery data but there has not been a dedicated survey or assessment to directly measure this indicator. They attribute the estimated progress to expansion of family planning services in the public sector (supported by UNFPA training, guideline updates and support to supply chain mechanisms), a relative decline in contraceptive services through non-public providers (though this could also affect the proportional calculation without reflecting an overall increase in contraceptive use), and improvements in public sector reporting systems, underpinned by the UNFPA-supported electronic logistics management information system (eLMIS) training.

In summary, although some positive improvements have been noted at outcome and impact level over the lifetime of the programme, data availability poses an issue in fully assessing progress, and change is likely to be incremental and long-term, given the nature of the interventions and changes targeted. Further progress on early marriage linked to this programme is likely to be limited, due to the refined scope in the final year, which will limit early marriage interventions to UNFPA technical advice and integrated messaging in wider awareness-raising interventions. As more data becomes available, UNFPA and FCDO will further assess progress, and whether any changes can be made in the next reporting period that are likely to help further contribute to potential gains against these indicators.

Indicator number	Indicator name	Target	Achieved	Data source or explanation of data constraints
Impact indicators
Impact indicator 1	Modern Contraceptive Prevalence Rate	45% (2024) / No target (2025) / 47% (2026)	43% (2024) / No data (2025) / 28% (all) / 41% of women married or in union	IWISH2 survey 2020 – no new data available for 2025 / UNFPA State of the World Population report 2025
Impact indicator 3	Unmet need for family planning	12% (2024) / No target (2025) / 10% (2026)	12% (2024) / No data (2025) / 8% (all) / 12% of women married or in union	Iraq Ministry of Health annual report – due for publication in summer 2025 / UNFPA State of the World Population report 2025
Impact indicator 7	Early marriage below 18 years old (women)	22% (2024) / No target (2025)	25.5% (2024) / No data (2025) / 28% (2006-2024)	Iraq Ministry of Health annual report – due for publication in summer 2025 / UNFPA State of the World Population report 2025
Outcome indicators
Outcome indicator 1.1	% of increase in the domestic budget allocated for contraceptive procurement (at national and governorate levels) annually	No target – procurement cycles are every 2-3 years	No data – but the objective of this outcome indicator is fulfilled as MoH fully fund their own contraceptive procurement for public sector services	UNFPA reporting
Outcome indicator 1.2	Number of government policy and regulations modified with UNFPA support that apply evidence from research and study papers related to FP	7	4 – of which 2 achieved this year (updated FP guidelines and work on the eLMIS)	UNFPA reporting
Outcome indicator 1.3	Percentage of modern–method contraceptive prevalence that is / accounted for by the public sector	10% (2024) / 15% (2026)	27%	https://www.unfpa.org/ar/data/world-population/IQ
Outcome indicator 2.1	Percentage of the targeted population who know of at least three modern methods of contraception and where to obtain them.	21% (2024)	21% (2024) / No data (2025)	The last data point was collected in 2023 as part of the formative research for the national FP messages and BCC materials. This type of indicator is typically assessed every 2–3 years to allow time for measurable change and cost-efficiency in data collection.
Outcome indicator 2.2	Percentage of facilities that have stock-out by method offered in the past 90 days in the targeted governorates	33% (2024)	33% (2024) / No data (2025)	No data available pending the rollout of the eLMIS. Data collection planned in the coming reporting period.
Outcome indicator 2.3	Percentage of primary SDPs that have at least 3 modern methods of contraception (other than condom) available in targeted governorates	22% (2024)	55% (2024) / No data (2025)	No data due to lack of structured, digital monitoring system. Some manual data collection but not sufficiently structured or comprehensive. Data will be collected via an MoH field-based assessment in the coming reporting period.
Outcome indicator 2.4	Percentage of girls 15-19 years old who are currently married (disaggregated rural and education level)	25% (2024)	26.5% (2024) / No data (2025)	Data reported last year was based on the Multiple Indicator Cluster Survey conducted in 2018.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on contextual evidence, there is a strong rationale to continue working on demographic transition in Iraq – population growth remains at 2.3% and 35.9% of Iraq’s population are aged 0-14. As of 2025, the population is set to double in the next 33 years (compared to an average of 30 years for least developed countries and 36 years for Arab states) and the fertility rate is 3.2 births per woman (in line with Arab states, and slightly lower than the least developed countries’ average of 3.8).4 The modern contraceptive prevalence rate remains low at 28% (in line with other Arab states, but also in line with least developed countries)5 and the proportion of demand satisfied with modern methods is at 60% (again in line with least developed countries and lower than the average for Arab states of 65%)6.

Continued high population growth in Iraq will increase pressure on job markets, services, infrastructure, the climate and the oil-dependent economy, exacerbating existing challenges. UK objectives to support Iraq’s stability, limit the recurrence of violent insurgency, tackle serious organised crime and migration, and support inclusive societies and economic growth will be compromised if demographic transition is not supported. Supporting voluntary family planning also represents a major return on investment given the role it plays in supporting demography as well as the health, socio-economic and political benefits it generates.

DTIP has also performed well over the programme lifecycle, making significant progress in improving the quality of family planning services by supporting government policies, systems, strategies and guidelines, supporting training to government staff with amplified effect via digital methods and training of trainers models, and supporting enhanced training facilities and integration of family planning services in healthcare facilities. In terms of demand creation, the programme has delivered multi-faceted behaviour change and awareness, using both digital and in-person methodologies to target youth, adolescent girls, educators, health workers, social workers and other key groups. On access to services, this is both being supported by work to improve service quality and expand centres of excellence, where integrated services are delivered to further governorates, and work to digitalise supply chains, which will improve commodity forecasting and evidence-based procurement. Over the longer-term, this combination of interventions should, if coupled with sustained government commitment and permissive social norms, start to enable shifts against the targeted impacts and outcomes of the programme.

However, due to reduced funding, UK development objectives in Iraq will need to be tightly prioritised in future years. As DTIP approaches the end of its programme lifecycle, the FCDO will consider how to sustainably transition from DTIP. Subject to budgets, we will consider whether to retain some specific aspects and activities of DTIP that best support Iraq’s future stability and security, including from an economic perspective, whilst leveraging change achieved under DTIP to sustain engagement with GoI on continued progress.

## C. DETAILED OUTPUT SCORING

NB: A full results framework refresh will be conducted in the coming reporting period to effectively capture the reduced and prioritised activities that will be delivered in the last year of the programme. This is ongoing at the time of writing and may result in substantial changes to output indicators or the removal or addition of indicators. This is not reflected under each individual output

Output Title	Improved national policies, and regulations on access to rights-based family planning with a focus on young people and vulnerable groups
Output number:		1.1	Output Score:	A+
Impact weighting (%):		20%	Weighting revised since last AR?	Yes – up from 15%

Indicator(s)	Milestone(s) for this review	Progress
1.1.1 Number of national policies improved that address the access to rights-based family planning information and services	12% of the annual health budget allocated to family planning	Exceeded expectation - 17% of the annual health budget allocated to family planning according to Gensis analysis.

Briefly describe the output’s activities and provide supporting narrative for the score.

The increase in health budget allocated to family planning builds on previous gains made under this indicator and broader institutional and policy-level progress achieved under outcome 1.2. During the previous reporting period 19 governorates adopted family planning action plans and UNFPA developed a national position paper on advocacy of family planning from an economic development perspective. MoH produced various recommendations following on from this paper, including to dedicate budget specifically for family planning services, and the recommendations were being taken forward with support from UNFPA.

UNFPA also attribute progress on policies and regulations to strategic alignment with national health sector priorities, strong government buy-in from MoH who have endorsed and adopted several UNFPA-supported policy outputs, continuity of technical assistance support over the lifetime of DTIP and effective leveraging of partnerships and evidence-based advocacy. Under outcome 1.2, UNFPA have supported amendments to the following polices and regulations:

- Procurement procedures (Kimadia) – Changes adopted to facilitate registration of new medical items, including contraceptives, through online processes. (Amended in 2022)
- National Essential Medicines List – IUDs were introduced (though later removed due to low uptake). (Amended in 2022-2023)
- Digital health and supply chain system (eLMIS) – Phase 1 implemented, with continued rollout planned. (Ongoing since 2024) (see also output 2.2.5)
- FP Guidelines – Updated with an accompanying eLearning module to support distance learning. (2024–2025) (see also output 2.2.1)
- Contraceptive Procurement Policy – MOH demonstrated commitment to cover contraceptive needs despite challenges with supplier participation. (Achieved) (see also output 2.2.4)

Future work is planned or ongoing on a women, child and adolescent health costed action plan and service package update and a third-party procurement agreement between UNFPA and the MoH. There are also potential plans to integrate maternal and FP services under universal health insurance schemes and to expand the eLMIS.

During the reporting period (April 2024 – March 2025), UNFPA also engaged two national consultants to develop the Minimum Initial Service Package (MISP) and to complete the digitalisation of the national family planning training curriculum.
The MISP document, finalised and approved by the Iraqi Minister of Health, was integrated into Iraq’s Women, Children, and Adolescent Health (WCAH) Costed Action Plan. This institutionalised MISP-aligned emergency preparedness and unlocked potential domestic and donor funding. The digitised training curriculum significantly improved the Ministry of Health’s capacity to train health personnel by transitioning from in-person sessions to a cost-effective, accessible online format.
Over the past year, there was a strategic shift from policy-level groundwork to institutionalisation and implementation. The development of the MISP and its formal integration into a national costed action plan marked a significant operational advancement. Similarly, the digitisation of the training curriculum reflects a transition toward scalable and sustainable capacity building within the health system.
Looking ahead, the programme will continue to build on these outputs by ensuring full operational rollout of the e-training platform.
In parallel, UNFPA supported Iraq’s launch of the Global School-Based Student Health Survey (GSHS) in collaboration with WHO, UNICEF, and the Ministries of Health and Education. This milestone provides a critical evidence base to inform policies and interventions focused on adolescent health and well-being.
In addition to these activities, in early 2025 FCDO agreed to reallocate some funding towards follow-up on the 2024 Iraq census. This funding supported a conference to launch the results of the census, a post-enumeration survey and the procurement of GIS equipment for the Government. The conference was well attended at the highest levels of government and heavily publicised in Iraqi media. UK expertise from the Office for National Statistics was also profiled at the conference. The post-enumeration survey is critical for verifying the quality and reliability of the census results and the GIS equipment will enable the census results to be used for national planning. Given their late addition to the programme, these activities were not captured in the results framework. However, the results and their effective use and dissemination, have the potential to drive better allocation of resources towards government service delivery.
These achievements build on earlier work, including the development and dissemination of policy briefs on family planning and population dividends, and demonstrate a strong trajectory of progress.
Describe any changes to this output during the past year, and any planned changes as a result of this review.

N/A

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendation from the last annual review: The UK should engage with high-level government officials to press for implementation of adopted FP action plans to ensure sustainability and monitor adoption at a governorate level during project visits.

Update: There has been varied implementation of the FP action plans at governorate level. During the reporting period, FCDO staff have visited three centres of excellence in Baghdad, Dahouk and Mosul where they have been able to monitor family planning services directly but have not directly held focussed discussions on this with MoH. A dedicated discussion on this should be planned for the coming reporting period.

Lessons learned this year:
- Institutional integration (e.g., embedding MISP into national frameworks) is essential for sustainability and resource mobilisation.
- Digital tools can rapidly scale training but require strong MoH ownership and IT infrastructure.
- Cross-sector collaboration (with MoH, MoE, WHO, UNICEF) enhances programme visibility and leverage.
Recommendations for the year ahead:
- Monitor the implementation of governorate-level family planning action plans and track progress against national targets.
- In the final year of DTIP, the programme should continue strong advocacy and work with the MoH to ensure adequate budget provision for family planning services.
- Building on previous successes, in the coming reporting period, the programme should assess progress against Iraq’s national birth spacing strategy and ensure findings and recommendations are shared with MoH.
- Given the strong transformative potential of effective use of the census results and UNFPA’s strong technical relationship with GoI on this area, DTIP should continue to support census follow-up activities.

Output title	Increased awareness of decision-makers, community leaders, influencers about family planning and reproductive rights, (including early marriage and its negative consequences) in the context of the demographic dividend
Output number:		1.2	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR?	Yes. Up from 10%

Indicator(s)	Milestone(s) for this review	Progress
1.2.1 Number of decision-makers, community leaders, influencers who express support for Family Planning and Reproductive Rights of women and girls. / Number of school students and teachers benefited from awareness sessions on early marriage. / Number school teachers/head masters benefit from early marriage training. / Number of beneficiaries received essential VAWG services	Youth Scorecards Report is available and used for evidence-based advocacy. / Adolescents Girls Vulnerability Index is available and used for evidence-based advocacy. / 10,000 of community members sensitized in FP and early marriage with communication materials / 30 media reports where Family Planning is mentioned. / Students 500. / Teachers/Headmasters: 75 / 700 beneficiaries accessing VAWG services	Not met / Not met / Partially met - A total of 192 community leaders were sensitized on strategies to combat early marriage. / Partially met expectations - More than 15 posts were made on UNFPA's social media platforms. / Partially met expectation - 356 school students benefited from sessions designed to raise awareness about early marriage and encourage active participation in community issues. / Outputs substantially exceeded expectation - 107 teachers and headmasters participated in specialised training sessions focused on early marriage awareness. / Outputs substantially exceeded expectations - 966 beneficiaries accessed comprehensive VAWG services during this period.
1.2.2 Number of research and study papers produced and used for awareness-raising on Family Planning and Reproductive Health. early marriage and demographic situation	An assessment report on MISP readiness is available in Iraq.	Outputs exceeded expectation - MISP Readiness Assessment was finalised in Q3 / Early School Dropout and Early Marriage: A study investigating the link between leaving school early and early marriage has been finalised. The findings have been shared with key stakeholders

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall outputs partially met expectations (score B). During the reporting period (April 2024 – March 2025), progress made in advancing Output 1.2 was focussed on raising awareness and strengthening national systems related to early marriage and activities relating to violence against women and girls (VAWG). Partway through the year, focussed shifted onto the provision of services in Al Amal, including VAWG services. This shift, alongside some contextually driven changes in the approach to awareness-raising, have led to some underachievement against targets originally set for this year.
UNFPA led wide-reaching initiatives targeting community leaders, educators, and students to enhance awareness on early marriage. Between April and September 2024, 192 community leaders and 107 teachers/headmasters were trained, and 356 students participated in awareness sessions. These engagements built local capacity to address marriage and embedded prevention messaging within educational institutions.
UNFPA also facilitated 22 legal and educational awareness sessions for 1,262 students and 216 parents across 21 schools in Erbil. In the Kurdistan Region of Iraq (KRI), eight-day awareness training sessions for 65 educational instructors were conducted to address early marriage at the community level.
UNFPA sustained high-level coordination with the Secretariat of the Council of Ministers (COMSEC) on the formal adoption of early marriage recommendations from the 2022 National Conference. Further, UNFPA finalised a study linking school dropout to early marriage to inform national response strategies. UNFPA’s engagement with the Ministry of Planning and the Iraqi Women Department also led to the integration of a dedicated output on women’s empowerment into the national population policy.
These activities demonstrate strong alignment with programme objectives and contribute directly to national policy advancement and system strengthening in areas of child protection and women’s empowerment. Over the past year, Output 1.2 evolved from an initial focus on community awareness and service provision to a more integrated approach combining grassroots engagement with national-level policy influence. This strategic shift is expected to yield longer-term impact by embedding planning that is sensitive to the needs of women and girls into national frameworks.
In Autumn 2024, FCDO and UNFPA agreed to support services in Al Amal under DTIP, reallocating funding away from planned activities on an early marriage campaign, including public awareness campaigns on early marriage, community workshops on early marriage and school-based education programmes on children’s rights and early marriage. To mitigate the impact of this change in focus, UNFPA proposed integrating messaging on early marriage into broader initiatives and emphasising education and economic empowerment for girls. This realignment, agreed with FCDO reflects a strategic pivot to address more immediate VAWG -related needs, particularly in Al-Amal camp, and explains some of the under-achievements against this output.

The expansion of VAWG service delivery and training, reflects a shift toward inclusive and survivor-centred support. UNFPA-supported VAWG services reached 966 beneficiaries during the first half of the reporting year. In the second half (October 2024 – March 2025), the scale-up of VAWG services became evident, with 67 individualised case management sessions taking place and over 10,000 displaced women and girls (returnees from Al Hol Camp in Syria) accessing referral services. In addition, more than 2,300 women and girls participated in targeted VAWG awareness sessions, and 204 awareness sessions addressed women’s rights, mental health, empowerment, and integration. (See also output 2.3).
Describe any changes to this output during the past year, and any planned changes as a result of this review.
In addition to the inclusion of services in Al Amal and reduction in activities focussed specifically on early marriage awareness raising, UNFPA adapted methodologies throughout the year to suit local contexts and emerging opportunities for impact. Whilst some changes were made to the results framework during the year to capture changes, i.e. the inclusion of VAWG targets and targets for students/headteachers reached, the targets above were not fully updated in line with real-time programme adaptations. Initially proposed indicators such as the development of “youth scorecards” and an “adolescent girls vulnerability index” were not pursued. Instead, the programme adapted its methodology to better reflect the operational realities and emerging opportunities for impact, while continuing to focus on its core objective of addressing early marriage and violence against women and girls (VAWG).
Increasingly over the year, attention was redirected toward VAWG interventions in Al-Amal camp where immediate needs were greater.
Despite the shift, the programme-maintained momentum through activities focused on:
- Strengthening the medico-legal response to violence against women and girls (VAWG)
- Empowering youth with legal knowledge, fostering their ability to understand and claim their rights in a protective and informed environment.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR:

- Strengthen partnerships with local community organisations and leaders to ensure broader outreach and sustained advocacy efforts. While local implementing partners have continued to play an important role in outreach and awareness raising, sustainable progress requires stronger government ownership. UNFPA has equipped the MOH with training, tools, and behaviour change communications materials, but implementation varies across governorates. Moving forward, the MOH is expected to lead on community engagement using these resources. Robust coordination between the MOH and the local leaders is needed to strengthen advocacy and outreach efforts.
- Explore alternative advocacy platforms, such as digital campaigns, to reach a wider audience, especially in areas where more traditional methods, such as face-to-face meetings or printed materials, face resistance. Digital campaigns yielded strong results under output 2.1. Digital campaigns will be prioritised further in the coming reporting period, alongside an assessment of the Government’s Behaviour Change Communication strategy.

Lessons learned this year:
- Localised actions, such as community mobilisation and school engagement, are most impactful when paired with national policy action and legal reform.
- Data and research (e.g. the school dropout study) are powerful tools in shaping policy dialogues and supporting advocacy.
- More strategic engagement is needed at central government level to ensure accountability on delivering against action plans.
Recommendations for the year ahead:
- FCDO and UNFPA to agree how FCDO engagement and advocacy can best help sustain momentum and progress on previous activities around early marriage as we shift our focus away from direct community interventions in the coming reporting period.
- UNFPA to continue integrating early marriage messaging into other DTIP activities in the coming reporting period, where feasible.
- FCDO and UNFPA to regularly review programme progress and any adaptations needed, ensuring these are effectively captured in the results framework (a full refresh is underway at the time of writing).

Output title	Increased access to age-appropriate reliable information and education on FP, rights and life-skills among women and young people, especially the most vulnerable.
Output number:		2.1	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1.1 Number of community members reached with Information Education Communication on FP disaggregated by location and profile.	30,000 community members reached with Religious Leaders messages on Birth Spacing. / 150,000 reached with FP messages through Mass media	Substantially did not meet expectation- The activity related to community members through religious leaders was not started. / Substantially exceeded expectation- 1,660,000 people reached via media messages on UNFPA's social media platforms in 2024.
2.1.2 Number of young people who have accurate knowledge and self-efficacy to adopt a positive behavioural change to practice family planning	20,000 of people have increased knowledge and skills through MOH, outreach activities to raise awareness on RH/FP in the provinces of CoEs. / 20,000 adolescent girls in target areas have increased knowledge and skills by Adolescent Girls’ Tool Kit (AGTK) Education. / Develop the capacities of 550 MoE staff to provide skills education using AGTK in 10 governorates initiative of "integration of AGTK into school education"	Substantially exceeded expectations – 248,084 through an online outreach campaign conducted by UNFPA and MoH. This is the number reached through UNFPA platforms – UNFPA report the reach of MoH platforms is higher. / Met expectations - 20,404 / Met expectation - 525 MoE staff
2.1.3 Number of youth centres in the targeted governorates that are provide age-appropriate and life-skills based education on RH /FP (including messages around the negative consequences of early marriage)	337 Schools regularly delivering messages on family planning and reproductive health and rights for youth	Met expectation- 428 schools
2.1.4 Number of youth centres in the targeted governorates that are providing age-appropriate and life-skills based education on RH/FP (including messages around the negative consequences of early marriage)	15 Youth centres that are providing information on reproductive rights, family planning, empowerment and VAWG / 4500 young people reached with life-skills education integrated with FP/RH rights and VAWG prevention	Met expectation- 13 Youth Centres / Moderately did not meet expectations - 3370 young people reached

Briefly describe the output’s activities and provide supporting narrative for the score.
Overall, across the output, indicators met expectations. During the reporting period (April 2024 – March 2025), DTIP made strong progress in the areas of Behaviour Change Communication (BCC) and adolescent outreach. In 2022-23 UNFPA, in partnership with the Ministry of Health (MoH), developed a national BCC strategy and costed action plan to enhance awareness and uptake of reproductive health services. Many of the activities delivered under this output constitute efforts towards the rollout of that strategy.

Key achievements include:
- Completion of a Knowledge, Attitudes, and Practices (KAP) study, forming the basis for national family planning messages.
- Development of a national booklet and multimedia materials for the family planning campaign.
- Launch of a coordinated social media campaign with regular content dissemination by MoH and UNFPA, amplified by the British Embassy – which allowed targets to be significantly exceeded compared to originally planned outreach activities.
- Two BCC Training-of-Trainers (TOTs) were held for 85 MoH staff, and 72 social and healthcare workers were trained on integrating family planning into community outreach.
- 533 healthcare providers across 10 governorates received training in counselling services.
- Significant scale-up of the Adolescent Girls Toolkit (AGTK)[3]: 525 Ministry of Education staff trained; 18,572 adolescent girls received life skills education in schools; and 622 were reached in host communities.
  [3] he Adolescent Girls Toolkit for Iraq is a manual designed to support adolescent girls focal points embedded in schools to discuss key issues such as life skills, health, violence against women and financial education with adolescent girls. The toolkit was produced by UNICEF and UNFPA.
- 3,370 youth were reached in youth centres with reproductive health (RH), FP, and VAWG -related education.
- 13 youth sports centres are now delivering information on family planning and VAWG.
These activities demonstrate a comprehensive and coordinated approach to increasing awareness and demand for reproductive health services across Iraq, while embedding adolescent-appropriate content into education and community systems.
During this reporting year, the output expanded its reach significantly. Notable changes included the successful scale-up of the AGTK from pilot areas to broader implementation in Federal Iraq, alongside a more formalised and structured national media campaign for family planning. Engagement with the Ministry of Health elevated from departmental heads to Director General level, which improved coordination and accountability.
While most indicators met or exceeded expectations, engagement with religious leaders was unable to progress as planned. MoH developed unified guidelines on messaging for awareness raising activities with technical support from UNFPA, however, these guidelines have not yet been approved.

The slight underachievement in young people reached via youth centres is due to the limited number of youth centres targeted and school holidays affecting the timing and scale of the roll-out.

Describe any changes to this output during the past year, and any planned changes as a result of this review

Targets for those reached through MoH outreach activities were amended from 30,000 to 20,000, but achievements exceeded both targets. An original target to work with 20 adolescent girls focal points was removed and replaced with the target of training MoE staff on the AGTK. The target under 2.1.3 was amended to measure the number of schools, rather than the number of districts. The target under output 2.1.4 was amended from 15,000 young people to 4,500 young people due to revised geographical targeting and messaging on early marriage was removed from this target.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR:

- FCDO and UNFPA should work together to ensure communication strategies adequately address and are adapted to cultural sensitivities. FCDO and UNFPA should work together to monitor risks and discuss mitigation strategies that will allow programme work to continue as far as is possible during the next reporting year. UNFPA has ensured communication strategies are adapted to the cultural sensitivities in Iraq and has been able to maintain delivery on behaviour change communications during the reporting period.
- UNFPA should continue to strengthen their own relationship and support the new FCDO team’s relationships with the Ministry of Health to help underpin programme delivery. The relationship between UNFPA and MoH has strengthened, with engagement now elevated to the Director General level, enabling stronger alignment and oversight of programme delivery. UNFPA has also supported the new FCDO team in deepening its engagement with key MoH stakeholders, including supporting joint engagement and coordination for a planned meeting between HMA and the Health Minister (the latter of which took place after the reporting period).
- The Adolescent Girls Toolkit should be rolled out in Federal Iraq. The Adolescent Girls Toolkit (AGTK) has already been introduced in Federal Iraq and is being further expanded. Training of Federal Ministry of Education staff has taken place across 7 governorates (Baghdad, Basra, Anbar, Diywanya, Salah Al-Din, Kirkuk and Ninewa), reaching thousands of adolescent girls with life skills education, with plans for continued rollout in the next phase.
Lessons learned this year:
- Effective behaviour change requires sustained, multi-channel communication grounded in national systems and tailored to local sensitivities.
- Investing in capacity building at scale particularly through government institutions ensures ownership and sustainability.
Recommendations for the year ahead:
Continue adapting communication content and delivery to reflect cultural sensitivities.
Maintain strong coordination mechanisms with MoH and MoE to sustain BCC and AGTK activities at scale.

Output Title	Increased capacity of the health care system to deliver family planning services for young people and women, especially among vulnerable populations.
Output number:		2.2	Output Score:	A
Impact weighting (%):		30%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.2.1 % of service delivery points that have integrated FP services into the basic package of health services	130,000 RH beneficiaries serviced by graduates of centre of excellence -75,000, Popular clinics -15,000, private - 15,000, MOLSA -10,000, CSOs -15,000 / 20,000 beneficiaries received Immediate Post-Partum FP counselling & Services / Monitoring & accreditation system for CSOs’ clinics providing FP service is available / Guidelines, standard & training manuals for integrating provision of “Immediate Post-Partum/- FP” services in maternities are available / Orientations/regulations to integrate FP services into “Popular Clinics” is approved / 10 popular clinics received FP commodities / Report with mapping of private clinics and pharmacies is available / 25% of Private clinics & maternities that signed PPP with DoH to promote FP services / governorate / 50% of CSOs clinics that offer FP services in existing medical services	Substantially exceeded expectation - 318,872 of RH beneficiaries serviced by graduates of centre of excellence, MOLSA - 10,000. No reports available from Private facilities. / Substantially exceeded expectation -154,164 mothers received Immediate Post-Partum FP counselling & Services at MOH services according to MOH annual report (23% of 670,282 mothers) / Met Expectation / Met Expectation- Guidelines, and protocols for integrating provision of Immediate Post-Partum services in maternities are available. / Not met - Popular Clinics do not provide FP services yet / Not met – due to contextual developments / Not met / Not met / Not met – due to contextual developments
2.2.2 Number of young people who received youth-friendly counselling on FP	20,000 adolescent beneficiaries received FP counselling within PHC facilities / 5000 youth received FP, RH and VAWG counselling and referrals though the helpline	Substantially exceeded expectations - 80,272 young people received counselling services through PHCCs in 2024 till end of March 2025. / Partially exceeded expectations - 5355 young people received counselling through the helpline in 2024 till end of March 2025.
2.2.3 Management & coordination, supervision, accountability and operations of FP programme is enhanced	FP Technical committee held meeting and provide technical feedback and recommendations / Inter-ministerial/ Pop/FP Committee reviews FP Action Plans and provide feedback & recommendations / FP Quality assessment & improvement system is place / 50% implementation of M&E plans at governorate level	Met Expectation / Met Expectation / Met Expectation / Met Expectation
2.2.4 National RH Commodity Security (RHCS) system is strengthened	75% of Forecasted Commodities procured by KIMADIA (preferably by each approved FP method) / Functional supervisory system to monitor RHCS functions at all levels is available	Exceeded expectation - KIMADIA procures more than 75% of the forecasted commodities, but this didn't happen this year as KIMADIA already purchased for year (2023-2024). / Met Expectation
2.2.5 % of health facilities with functional LMIS	All storage facilities are renovated and equipped / 36 of targeted districts have operational LMS/LMIS / 10 monitoring visits conducted to support supervision of supply chain	Not met / Partially met – eLMIS pre-operational across 46 districts, 40 district warehouses and six governorate-level warehouses / Met Expectation

Briefly describe the output’s activities and provide supporting narrative for the score.
Despite some variation in achievements across the output, delivery met expectation across the various indicators, and progress was made to strengthen Iraq’s healthcare system in delivering high-quality, youth-friendly family planning (FP) services through enhanced training, technical support and supply chain interventions.

Family planning service quality and training: Good progress was made on integrating family planning services into government healthcare services. There were substantial overachievements on reproductive health services provided by graduates of centres of excellence and post-partum family planning counselling provided through MoH services. The latter was underpinned by appropriate guidelines and protocols. Strong progress on these indicators was supported by the Centres of Excellence model. Over the course of the programme 11 PHCCs were upgraded into reproductive health Centres of Excellence with medical furniture and equipment, offering improved infrastructure and staff training facilities, and integrated services (antenatal, postnatal, maternal-foetal medicine, and counselling), alongside behaviour change communication. During the reporting period, funding was reallocated to enable expansion work at the Maternity Hospital in Halabja and in Khormal primary healthcare centre (PHCC), including infrastructure improvements and staff training spaces to support service delivery in the surrounding areas. Additional funding was allocated to procure equipment for Kirkuk’s Centre of Excellence.

Achievements in this area were further supported by training innovations. A new FP e-learning module was developed by UNFPA in partnership with the MOH. The module is hosted on Canvas and blends theoretical e-learning with a shortened one-week in-person practical component. Teachers were trained through a training of trainers model, and MOH now certifies successful participants. Overall, these achievements and efforts will support increased and expanded quality of family planning service provision through government services.

Unfortunately results reported above do not capture results delivered through civil society organisations or the private sector as these clinics are not integrated into the national health information system.

Indicators around popular clinics (public sector (semi-)urban outpatient clinics run by MoH providing a basic package of health services) and CSO clinics (which largely provide services in humanitarian settings) were not achieved. This was largely due to the shift in focus from humanitarian to development assistance over the lifetime of the programme. Accordingly, UNFPA has largely stopped direct support to services, commodity provision and operational support. Provision of contraceptives to popular clinics is now done in line with MoH national supply chain protocols and the MoH has recently approved the integration of FP services into popular clinics, which will in turn increase access to FP. Indicators relating to these activities will be removed in the final year of the programme to accurately reflect the programme’s revised focus.

Public-private partnership: Work is ongoing on private sector mapping and public-private partnerships. UNFPA and the Ministry of Health are currently in discussions regarding the mapping of private hospitals and clinics. They are also evaluating the potential for public-private partnerships, beginning with private hospitals, to enhance family planning services considering the support that UNFPA can offer in this initiative.

Adolescent/youth counselling: Significant progress was also made in terms of adolescent counselling training and provision, with substantial overachievements against original indicators. This was made possible by an expansion of training for healthcare providers. Original plans to conduct one training of trainers for 26 healthcare providers from seven governorates were expanded to deliver three five-day trainings of trainers across Federal Iraq and KRI. Training equipped staff to deliver counselling and referrals on health matters, including family planning and reproductive health. DTIP funding facilitated the continuation of a youth counselling and referrals hotline staffed by MoH, with both activities enabling the public healthcare system’s ability to support youth understanding in these areas across Iraq.

National technical engagement: To complement the support to increase quality service provision, UNFPA has engaged with the Inter-Ministerial Population Committee, a coordination platform composed of representatives from key ministries and public institutions. During the reporting period, UNFPA participated in two committee meetings. This led to key achievements in securing endorsement of the draft family planning guidelines for religious leaders (see also output 2.1). It also led to approval of the unified national family planning awareness messages, which will ensure consistent messaging on family planning across government ministries and platforms.

UNFPA has also engaged effectively with technical oversight and quality management at the national level. The Family Planning Technical Committee is a technical body consisting of supply chain and reproductive health experts from MoH and partners. The committee reviews national contraceptive forecasts, approves the national contraceptive supply plan and maintains oversight of the national drug list (playing a role in evaluating and approving the inclusion of family planning commodities). It also standardises product specifications for contraceptive methods. When requested, UNFPA provides technical support to the reproductive health department at the MoH to support and inform the work of this committee. Although the committee is led by KIMADIA, the medical procurement body for the government, MoH provides inputs on the standard list of commodities KIMADIA will procure via this committee.

Supply chain strengthening: This technical engagement at the committee-level is linked to, and complements, outputs 2.2.4 and 2.2.5. These outputs concern government contraceptive procurement and DTIP’s efforts to support the digitalisation of the contraceptive commodity supply chain. Although UNFPA does not support KIMADIA directly, work to support national capacity and systems, for example training on logistics management information systems, and engagement at the policy and systems level, have supported achievements under 2.2.4. In 2024 the MoH procured 100% of the forecasted quantities of contraceptives. For certain contraceptives, the small quantity of commodities required led to difficulties attracting suppliers and delays or unavailability of commodities. UNFPA continues to advocate for a third-party supplier agreement with the Government so they can procure commodities for national health systems using their global supply chains, mitigating this supply issue.

Although varied progress was made against indicators in output 2.2.5, activities conducted during the reporting period have laid the groundwork for the rollout of an electronic logistics management information system (eLMIS). This will digitalise the contraceptive commodity supply chain and enhance data-driven forecasting and supply planning moving forward. The supervisory system to monitor RH Commodity Security (mentioned under output 2.2.4) will also be digitalised.

During the reporting period, following a national supply chain assessment, UNFPA supported the development of a technical framework for the electronic Logistics Management Information System (eLMIS). This used the Digital Health Information System (DHIS2) platform, supported by WHO. A formal UN-to-UN agreement has been signed with WHO to support the pilot implementation of the eLMIS, with system requirements, SOPs and training plans prepared in coordination with MoH. By the end of the reporting period, training on the eLMIS had been done in Federal Iraq and KRI, and laptops procured. The eLMIS system was then pre-operational across 46 districts, 40 district warehouses and six governorate-level warehouses, with the system currently operating on demo data for training purposes. This exceeds plans to target 36 districts, which UNFPA attribute to strong collaboration with MoH and strong readiness at the subnational level. Further rollout of the system is planned for the coming reporting period.

These myriad efforts contributed directly to improving access to quality FP services and capacity building at all levels of the healthcare system.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicator targets for output 2.2.2 were revised down from 22,500 to 22,000 for PHC facilities and down from 7,500 to 5,000 for the hotline, the latter to more accurately reflect hotline usage previously and the lack of hotline in Kurdistan.

During the year, the original plan to introduce a new warehouse management software for supply chains was revised due to delays. Instead, the team shifted to a more feasible Plan B, which focused on integrating FP LMIS into the national DHIS2 platform. This approach aligns better with existing national systems and is expected to be more sustainable.

A further change involved modernising FP provider training through an e-learning module to reduce in-person training time, lower costs, and reach more healthcare providers. This digital transformation is expected to continue in the next year, with further scale-up across additional regions.

Additionally, the expansion of the CoE model to Halabja represents a geographical and infrastructural shift, improving coverage in underserved areas and reflecting a commitment to reaching peri-urban areas with quality FP services.

Looking ahead, implementation of the eLMIS pilot, and expansion of CoEs in other underserved areas are planned as part of continued investment in health system resilience and quality FP services. Given the shift in context outlined above, future targets around CSOs and popular clinics will be removed.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations from the previous AR:
- UNFPA provides technical support to MoH to digitalise the paper-based LMIS forms to digital forms, and WHO to integrate these form into the DHIS2. The paper-based system has been transformed into a digital form. The work to pilot this will take place in the next reporting period.
- UNFPA to support the MoH to continue the rollout and operationalisation of the LMIS in collaboration with the Ministry of Health, focusing on targeted governorates. Ongoing – detail above.
- UNFPA should lead the digitalisation and delivery of training courses for healthcare providers, ensuring they have the skills needed for effective service deliver. Complete.
Lesson learned this year:
- National system alignment such as integrating LMIS into DHIS2, ensures better uptake, reduces fragmentation, and increases government ownership.
- Shifting to digital training platforms can significantly reduce cost and increase scalability, especially in resource-constrained settings.
- Close coordination with MOH in both Federal Iraq and KRI is essential for the rollout and sustainability of upgraded services.
Recommendations for the year ahead:
- Implement the pilot of the eLMIS and begin rollout based on lessons learned.
- Expand access to the e-learning module and consider making it available beyond MOH-nominated staff to scale training.
- Continue expanding Centres of Excellence, prioritising underserved regions and building local training capacity.
- UNFPA and MoH to work together to identify next steps on public-private partnerships and how UNFPA can support this work.

Output Title	Support life-saving humanitarian services strengthen (including returnees)
Output number:		2.3	Output Score:	C
Impact weighting (%):		10%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.3.1 Number of targeted women and girls in need received RH and VAWG services in humanitarian settings, through UNFPA supported SDPs	209,106 women and girls received RH and VAWG services in humanitarian settings through UNFPA supported SDPs	10,184 women and girls received VAWG referral services. 1,103 gynaecological consultations, ante-natal care visits, post-natal care visits and cases of family planning counselling and services were delivered in the second half of the reporting period.
2.3.2 Number of targeted women and girls in need received Dignity kits in humanitarian settings, through UNFPA in targeted areas	5,000 women and girls received Dignity kits	958 procured and distributed in Al Amal

Briefly describe the output’s activities and provide supporting narrative for the score.
Although targets were not met this year, this primarily reflects a lack of comprehensive updates to the results framework, rather than underperformance of the programme. Initially, no humanitarian activities were planned during the reporting period. However, in Autumn 2024, FCDO agreed to fund UNFPA-supported maternal and reproductive health, and VAWG activities in Al Amal Rehabilitation Centre, reallocating budget from the planned early marriage campaign to facilitate this. UNFPA later reallocated further funding from the programme’s budget line for this humanitarian output to support activities in Al Amal. These activities were delivered and verified by FCDO staff during a visit to Al Amal in February 2025.

UNFPA met expectations in sustaining the provision of critical lifesaving services in Al Amal Rehabilitation Centre throughout the latter part of the reporting period with FCDO funding (and prior to that with other funding). Between April 2024 and March 2025, RH and VAWG services were regularly delivered to vulnerable women and girls, including antenatal and postnatal care, skilled birth attendance, family planning counselling, STI prevention, and RH awareness sessions. A referral system is also in place to ensure cases of complicated pregnancies, obstetric emergencies and other critical RH conditions can be transferred to the nearest hospital. UNFPA-funded services also support VAWG case management, VAWG services, provision of dignity kits (NB: the dignity kits themselves were not UK funded), VAWG referrals and VAWG awareness-raising sessions.

In early 2025, services in Al Amal faced two simultaneous challenges: 1) the US Federal Foreign Assistance review which led to the termination or pause of some services; 2) the expedited return of Iraqi nationals from Northeast Syria to Iraq. Since January, the UNFPA-supported clinic has been the sole internationally-supported healthcare provision in Al Amal and UNFPA is the sole provider of RH services. Given this, and the increased population of Al Amal, UNFPA services have been under increasing pressure. This sustained presence during a period of significant humanitarian contraction demonstrates UNFPA’s critical role in safeguarding women’s health and rights and the critical role UK funding has played in maintaining consistent services for the most vulnerable.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicator 2.3.1’s target was revised down from 600,000.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Recommendations from the previous AR:
- UNFPA and the UK should work together and use UK diplomatic levers to engage with customs and local authorities to help streamline the import process for essential medical supplies. Ongoing
- UNFPA should encourage MoH funded third-party supply chain processes to ensure timely and consistent import of necessary supplies. Ongoing
- FCDO and UNFPA should ensure workplans and targets for the coming year reflect the reality of import challenges. Done – imports were not factored into planning for the reporting period.
Recommendations for the year ahead:

- UNFPA and FCDO to continue discussions on potential continuity of or other sources of funding for Al Amal humanitarian services beyond March 2026 to mitigate any potential gaps.
- UNFPA to consider whether community volunteers/outreach methods can be used to complement strained services in Al Amal and support awareness raising activities.
- To date, UNFPA services in Al Amal are focussed on women and girls. UNFPA to consider whether and how to support VAWG and Prevention of Sexual Exploitation and Abuse (PSEA) awareness sessions for men and boys to mitigate protection risks in the centre.
- The FCDO, UNFPA and the wider UN system should continue to advocate for increased government-funded health services in Al Amal.

## D: VALUE FOR MONEY

The overarching VfM statement for the programme contained in the business case still holds: the Iraqi state remains dependent on oil revenue and therefore a faster demographic transition will have higher returns in terms of creating fiscal space than in a non-oil dependent country. The interventions delivered remain economic and efficient – with the exception of humanitarian interventions, activities are designed to ensure systems strengthening, and to yield benefits beyond to the programme lifetime.

Key cost drivers and performance
- As in 23/24 a significant proportion of the programme budget in 24/25 has been spent on delivering technical assistance, capacity building and systems strengthening in country. The activities with the largest expenditure were the design of and training on the eLMIS, the rollout of the Adolescent Girls Toolkit (AGTK) and the census follow-up (conference, post-enumeration survey and procurement of GIS equipment).
- These activities have the potential to drive significant return on investment in terms of: 1) optimising evidence-based contraceptive procurement and improving contraceptive availability; 2) enhancing awareness of family planning and embedding awareness-raising structures in national systems; 3) supporting the Government of Iraq to better understand and plan for its population and their needs.
- Costs per beneficiary for key interventions with defined numbers of beneficiaries remain reasonable. The AGTK activities had a cost of $18.36 per girl in the reporting period. However, by embedding knowledge and skills in national systems these activities will yield much greater economy over the longer term.
- Despite its humanitarian nature, delivery costs in Al Amal are low. Even if only accounting for beneficiaries of VAWG GBV referral services, activities in Al Amal were delivered at a cost of $10.27 per beneficiary. Multiple other services were also provided (see output 2.3).
- UNFPA administrative costs remain at 8% with a coordination levy of 1% and are comparable with broader UN cost recovery rates.
- UNFPA also continued to deliver economy by providing effective expertise to deliver the programming in country (a key economy measure identified in the business case). UNFPA retains a number of highly qualified staff who have been integral to the delivery of DTIP in the reporting period, and who have provided expertise to wider government work, i.e. on the census.
- UNFPA also continues to harness the expertise of local NGO delivery partners and other UN agencies. For example, UNFPA sub-granted work on the eLMIS to WHO, given their existing ownership and expertise on the Digital Health Information System (DHIS), which the eLMIS needed to integrated into.
Efficiency
The business case notes that efficiency will be delivered by ensuring that: (1) an adequate choice of VFP services (including actual commodities), are available to women, girls, boys, and men where and when they need them and that this access is sustainable; it also means, (2) that though information and behaviour change campaigns an increasing number of Iraq citizens are better informed and empowered to take control of their reproductive rights. The work started on the eLMIS during the reporting period is a critical first step to achieving the former efficiency measure, whilst the continued focus on behaviour change communications via the AGTK, digital media and youth services supports the latter.

Over the reporting period:
- The programme has effectively converted inputs into outputs, successfully delivering against many key activities as evidenced in the output scoring above. Throughout the reporting period UNFPA flexed budget within internal budget categories for reproductive health, VAWG and youth activities to scale up impactful activities, such as the AGTK and services in Al Amal.
- The programme has delivered various outputs that should enhance the efficiency of family planning services in Iraq by building government systems and capacity, enhancing the reach and scale of these outputs.
  - By training healthcare providers and government employees to improve service quality, this should help drive trust in and demand for public services on voluntary family planning, ensuring better usage of public healthcare facilities.
  - Digitalising supply chains to ensure these better deliver supply against demand should help reduce stockouts and wastage.
  - Supporting work on the census, which should allow for more efficient allocation of government resources, if the results are harnessed effectively, allowing government revenue to be more effectively used.
- The methods by which UNFPA have delivered interventions have also improved efficiency. Delivering training via a “training of trainers” model or disseminating behaviour change messages via digital means have helped cost-effectively scale interventions, whilst, in the case of the ToT model, embedding knowledge in national systems to support sustainability.
- UNFPA’s technical inputs to government committees and policies, for example inputs on commodity lists and support on post-natal RH guidelines, should support government regulations and policies to better enable targeted objectives of the programme.
Effectiveness
Although it is difficult to assess at this stage how effectively the programme is translating outputs into outcomes due to the long-term nature of the interventions’ intended effects and the lack of annual outcome targets (see also outcomes section), the following evidence of effectiveness is observed:

- The programme results framework notes a significant increase in estimated modern method contraceptive prevalence accounted for by the private sector – increasing from 8% in 2021 to 27% in 2025. Outcomes around reducing stockouts and % of service delivery points with multiple methods of contraception achieved or exceeded targets last year – this should continue to translate into further progress in the final year of the programme. Over the longer-term, the rollout of the eLMIS should help further increase access to FP.
- Similar in 2025, 17% of the health budget was allocated to family planning, exceeding the stated target of 12%. This should contribute to driving quality and availability of service provision.
- UNFPA’s continued focus on behaviour change communications, which support the uptake of family planning and birth spacing approaches, constitutes an efficient preventative approach that should help support effective achievement of outcomes around knowledge of modern methods of contraception.
Cost-Effectiveness
Again, given the lack of impact level data, it is difficult to assess the extent to which the programme is effectively driving change at the impact level at this stage. However, the theory of change still stands and the programme is delivering multiple interventions that address the myriad of underlying factors that should contribute to impact-level progress over the longer-term.

Equity
- DTIP successfully pivoted to support interventions for displaced women and girls returning from Northeast Syria, providing access to maternal and reproductive health services and delivering VAWG awareness-raising and referrals that support the health of, access to family planning for and protection of women and girls in Al Amal.
- The programme promotes equity in reproductive health information by targeting youth.
- The expansion of centres of excellence, started this year, will help ensure better access to family planning in underserved communities.
- By supporting national strategies and policies, for example the humanitarian minimum integrated service package and the integration of an output on women’s empowerment into the national population policy, UNFPA is ensuring systems are established to better ensure women’s empowerment and to account for the needs of the most vulnerable women and girls in humanitarian need.
Assessment of whether the programme continues to represent value for money
Despite some changes to activities over the course of the year and some under-achievements, overall the programme continues to represent value for money. DTIP’s continued focus on driving systemic change at the national level to enhance access to, quality of and demand for family planning services should yield results beyond the lifetime of this programme, if sustained by national actors. For example, embedding the rollout of the AGTK into the education system is a catalytic step that should yield lasting impacts, as should the rollout of the eLMIS (planned for the coming year following preparatory work in the reporting period).

Delivering through UNFPA also offers value for money due to their convening power and expertise. The programme has enhanced national engagement in the issue of demography and family planning via this strong expert engagement with the Government, which facilitated contributions to the census, policy, regulatory and systems support, and training for national actors. These activities should also enhance the sustainability of the programme by increasing national capacity.

FCDO will keep tracking VfM through scrutiny of UNFPA reporting on results and performance, alongside continued engagement with key government stakeholders and programme beneficiaries.

Recommendation: To further increase the equity of the programme, consideration should be give to how the programme can further expand to areas of Iraq with lower family planning uptake and how the programme can better embed disability inclusion best practices.

Recommendation: Conduct a final value-for-money assessment, FCDO to work with UNFPA to document cost effectiveness and delivery efficiency across the programme’s main components to inform FCDO programmes in similar contexts.

E: RISK

Overview of risk management
The overall programme risk level remains moderate. DTIP’s overall risk profile remains within FCDO Iraq’s risk appetite and within appetite for all seven risk categories. Risk is managed and monitored regularly by the FCDO programme team and key risks are discussed with UNFPA and escalated as appropriate. The implementation of a programme steering committee has introduced an additional layer of oversight, which will help ensure that risks are promptly addressed and that adaptive strategies are in place. A greater focus on risk management will be embedded in steering committee meetings in the coming reporting period.

DTIP continues to operate within a complex and fluid context shaped by bureaucratic obstacles and institutional capacity limitations. This sits alongside a constrained donor funding landscape and a shift from humanitarian to development approaches in Iraq. These factors have influenced programme delivery during the reporting period and are likely to intensify as the programme enters its final year of implementation, especially given planned elections in Federal Iraq in November 2025. Some of the key contextual challenges and shifts experienced during the reporting period are summarised at the top of this review.

Institutionally, national ownership of the programme has gradually increased, particularly within the Ministries of Health. However, there remain challenges related to government financing, limited human resources in some PHCCs, frequent staff turnover, and uneven capacity at sub-national levels. These factors have affected the pace of implementation and transition to government systems in several areas. The reduction in internationally supported services following the US Federal Foreign Assistance review, alongside challenges faced by the government-run PHCC in Al Amal in a context of increased returns from Northeast Syria, have increased pressure on the UNFPA clinic at Al Amal. Lessons from the past year highlighted the need for sustained capacity support at the local level and the importance of embedding ownership not only at senior policy levels but also among MOH's operational staff who lead day-to-day implementation.

Safeguarding remains a cross-cutting risk, especially in community-level programming managed by UNFPA and local NGOs. During the reporting period, FCDO shared a letter with UNFPA emphasising our expectations on safeguarding (and fraud) and conducted a due diligence refresh which assessed progress against safeguarding standards. Ensuring recommendations from the due diligence are actioned will be a priority in the coming year.

Similarly, the risk of fraud and corruption is a cross-cutting risk in Iraq. This risk is mitigated by channelling funding through UNFPA financial systems. As noted above, UNFPA Iraq has undergone a due diligence refresh in 2025 and conducted assessments on its downstream delivery partners. Each year FCDO also sends partners a letter emphasising our expectations on fraud and safeguarding risk management and expectations on reporting.

Risks for the Year Ahead
As DTIP enters its final year, several strategic and operational risks must be carefully managed to ensure successful closure and transition. There is a heightened potential risk of implementation delays linked to the November 2025 elections, which may result in shifting priorities within government and reduced availability of key interlocutors.

Based on previous experience, such periods can lead to reduced engagement from government counterparts, ministerial reshuffles, and delays in decision-making. The programme has learned from similar political shifts in the past and has already taken steps to front-load high-level engagements and secure necessary approvals early in the year. Strong relationships with technical staff have also proven vital in maintaining implementation momentum during periods of political uncertainty.

The programme budget is significantly less than envisaged in the original business case and financial constraints are expected to persist during the coming year. This will require a sharper focus on prioritisation and efficiency, and consistent monitoring of the context, budget utilisation and implementation to identify any opportunities for budget reallocation between activities to ensure full programme spend against the highest impact activities by the end of the financial year.

Finally, the potential loss of institutional memory both within UNFPA and among national stakeholders could undermine the sustainability of DTIP’s achievements. There is a recognised risk that without a well-coordinated transition strategy, key tools, systems, and community-level initiatives developed under DTIP may not be institutionalised or sustained. To mitigate this, the programme will work closely with government counterparts (MOH) and UNFPA to develop a formal exit plan, which includes the handover of technical materials, training packages, and demographic data systems. Early planning in this area is vital, as previous years have shown that system transition and institutional integration require time, consistent follow-up, and clear responsibilities. Some of this work may need to continue beyond the life of the programme, in terms of engagement and coordination with the government.

In addition, there is a potential reputational risk if services are abruptly discontinued or if community engagement platforms established under the programme outputs are not maintained. Ensuring transparent communication with stakeholders and a phased approach to transition will be essential to mitigate this.

Recommendations:
- Prepare for impacts on programme activities ahead of November elections: Finalise high-level approvals and critical engagements by early Q2, and prepare contingency plans to avoid delays in programme implementation. Increase focus on relationships with technical government stakeholders to maintain momentum during any political transition.
- Develop a Knowledge Management and Legacy Plan: To mitigate risks related to institutional memory loss and ensure continuity, prepare final technical packages, toolkits, and reports to be handed over to ministries and, where possible, published on open-access platforms.
- [Continue Strengthening Safeguarding and Accountability Mechanisms: Ensure UNFPA and their partners complete any safeguarding strengthening recommendations identified in the due diligence receive Fraud and Safeguarding letters from FCDO.
F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Delivery Performance:
Overall, DTIP has delivered a multifaceted set of interventions over the reporting period that remain well aligned with the programme objectives.

UNFPA’s overall technical performance in delivering DTIP during the review period was strong. UNFPA demonstrated effective coordination with government stakeholders and flexibility in shifting priorities. UNFPA remains a respected partner of choice for the Government on reproductive and maternal health and demography, evidenced by significant technical support from UNFPA on the census and in key areas of government policy and decision-making.

Reporting and communication with the FCDO were regular and constructive. The programme’s adaptive implementation approach, led by UNFPA, allowed it to respond effectively to contextual shifts and operational constraints. Although engagement with FCDO was regular and constructive, greater communication between UNFPA and FCDO on changes made and the granularity of progress against targets could have been improved, alongside a more thorough and realistic review of the logframe after the last annual review. Learning has been drawn from this and will be implemented for the coming reporting period.

UNFPA have provided two six monthly narrative reports which have informed this annual review. These reports cover overall performance, progress against outputs, key successes and challenges, a risk update, an update on contextual, security and operational issues, monitoring and evaluation, and recommendation suggestions. Narrative reports are accompanied by a financial report and an updated results framework.

Reporting has been strengthened by including more detail about feedback from the programme’s key beneficiary, the Minister of Health (MoH). DTIP has received consistent commendation from the Ministry of Health (MOH) for its impactful role in addressing systemic challenges in the health sector. The MOH views the programme as a vital complement to its strategic vision, especially in overcoming financial and bureaucratic obstacles to implementing key health initiatives such as providing commodities (contraceptives) and increasing resources in some primary health centres in some areas of need. The MOH has repeatedly advocated for the programme’s continuation and expansion and particularly highlighted the need for increased investment in digital health transformation, sustained behavioural change communication (BCC), expansion of the Adolescent Girls Toolkit (AGTK) rollout in federal Iraq and the Centres of Excellence (COEs) model, and continued funding of the youth counselling helpline.

FCDO Programme Management Performance:
The FCDO team (SRO and PRO) in Baghdad provided effective programme oversight, maintaining strong engagement with UNFPA and government counterparts, particularly the Ministry of Health. Key contributions included establishing the first DTIP steering committee meeting and multiple subsequent meetings with the MoH on priorities and planning for the coming reporting period, field visits to observe implementation and support to resolve financial bottlenecks. The team responded to challenges, supported flexible reallocation of funds, and maintained alignment with UK strategic priorities. A continued focus on proactive risk management and coordination with UNFPA and MoH will be essential. The FCDO team have instituted regular meetings with the UNFPA programme team, which allows for increased programme oversight, and will increase the frequency of programme meetings with government in the coming reporting period.

However, it should be noted that both the programme SRO and PRO changed during the reporting period. This necessitated a greater focus on building relationships with key stakeholders this year and adapting management processes, alongside ensuring strategic prioritisation for the coming reporting period. Consistency in the SRO and PRO roles for the coming reporting period will help strengthen FCDO management of this programme.

Commercial Performance:
UNFPA continued to deliver DTIP through a mixed model of direct implementation and collaboration with vetted implementing partners. These include Together NGO, which played a key role in mobilising community actors and delivering the Adolescent Girls Toolkit training in KRI and Federal Iraq, and Zhian NGO, which is delivering services at Al-Amal camp. The Third-Party Procurement agreement was discussed with MOH and drafted in line with UNFPA’s established financial and safeguarding standards but has not yet been signed.

Financial Performance:
Over the reporting period, following issues with the reporting available from UNFPA financial systems, FCDO developed a programme-specific financial reporting template, which required UNFPA to report against forecasted spend line by line. This helped better evidence where spend was on or off track, where budget had been flexed across programming lines and budget utilisation. Overall, UNFPA achieved almost full budget utilisation across the reporting period, with only a 2% underspend.

There remains, however, room for improvement in the timeliness of financial reporting and payments on the programme, to mitigate risks of delays in delivery. The FCDO programme team will work closely with UNFPA to improve this in the coming reporting period.

Steering Committee meetings
The first FCDO initiated DTIP Steering Committee was held on 30 June 2024 and documented. UNFPA and MoH officials were in attendance (FCDO were unable to attend on this occasion) and discussed key components of the programme, the challenges and specific action points to help move the programme forward.

Recommendations:
Programme meetings involving FCDO, Government of Iraq stakeholders and UNFPA should continue on a quarterly basis.
- Strengthen exit and sustainability planning with stakeholders, working closely with MOH and relevant directorates to help support ownership and continuity of key activities beyond the programme’s lifetime.
- FCDO and UNFPA to work together to plan effectively for future payments, to mitigate any delays.
- FCDO and UNFPA to plan effectively for programme financial closure, ensuring UNFPA are prepared to provide documentation evidencing spend against activities and all required financial reporting in a timely manner.
- Continue to proactively reallocate any unutilised funds throughout the coming reporting period, identifying areas where unspent budget can be reallocated to other activities to maximise programme impact.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation
Throughout the April 2024 – March 2025 review period, DTIP was monitored through a combination of field-level observations, structured partner reporting, and engagement with national and community-level stakeholders.

Field Visits:
The FCDO Development team conducted periodic monitoring visits, including a field visit to attend and observe the Adolescent Girls Toolkit training in Erbil and Baghdad, visit to Centres of Excellence in Baghdad, Mosul and Dahouk, and a visit to Al Amal. These visits allowed FCDO staff to observe activities supported by UNFPA and those implemented by downstream partners “Together” and “Zhian”. The latter visit facilitated direct engagement with the Zhian field team, allowing FCDO to verify the scope of services provided, and discuss ongoing challenges. Similarly, witnessing the Adolescent Girls’ Toolkit training allowed FCDO staff to monitor the range of topics covered and engage directly with participants on their experience of the training, and visits to centres of excellence allowed FCDO staff to discuss challenges at the subnational level directly with those working in healthcare facilities.

UNFPA also monitors programme quality through various mechanisms, including:
- Quarterly Progress and financial reports from implementing partners
- Employing a qualified civil engineer to monitor, oversee and supervise the construction maintenance and improvement of CoEs
- Enforcing standard operating procedures for CoEs
- Arranging meetings between implementing partners and MoH to track progress

UNFPA maintains two dedicated Monitoring and Evaluation Officers who supported systematic tracking of outputs and outcomes across DTIP components. These officers played a central role in compiling quarterly progress reports, coordinating with implementing partners, and facilitating data collection to assess performance against the programme logframe. There is no external M&E supplier attached to DTIP; however, internal monitoring was strengthened this year through the use of an FCDO-developed financial management template, which improved visibility on expenditure linked to specific activities and enhanced accountability.

The Annual Review was led by the DTIP SRO and PRO, both based in British Embassy Baghdad. UNFPA provided full cooperation, submitting narrative, financial and results documentation, as well as conducting discussions on progress since the last review and providing clarification on reporting. Feedback from MoH was also integrated into this review, especially on sustainability planning and the need for continued behavioural change and digital health efforts beyond the life of the programme. As no formal external evaluation was conducted, this Annual Review will serve as the primary performance assessment tool, and will inform the programme closeout and future UK engagement in Iraq’s health and population sectors.

Evidence:
- UNFPA conducted a study to investigate early marriage's tie to school dropout in Iraq, revealing marriage was a dominant reason for girls dropping out of school before the age of 14. Solutions proposed include raising awareness about early marriage impacts, and enhancing curricula. Economic aid and fostering open parent-child dialogue on health topics are recommended. For girls who have dropped out, financial support and education re-entry programmes are crucial. The study emphasises the necessity of addressing this issue to improve girls' educational prospects in Iraq.
- UNFPA, jointly with WHO and UNICEF, developed a dashboard that shows the emergency obstetric and newborn care (EmONC) indicators in hospitals and PHCCs at national and sub-national levels. These indicators are crucial for monitoring and improving the quality of care provided to mothers and newborns during emergencies related to pregnancy and childbirth. The dashboard allows progress to be tracked, helped identify gaps and enable informed decisions to enhance maternal and newborn health outcomes.

Learning: Points of learning are embedded throughout the document.

Due Diligence: A refreshed UNFPA Due Diligence was completed in early July 2025.

Recommendation: In the coming year the programme should conduct an assessment of the birth spacing and behaviour change communication strategies and the AGTK to capture outcomes, lessons learned and successes.

Date of last narrative financial report	May 2025	Date of last audited annual statement	Official Financial Statement for 2024 received on 22/07/25

List of Acronyms
BCC	Behaviour Change Communication
CoE	Centre of excellence
DoH	Directorate of Health, governorate health authority
FP	Family Planning
GoI	Government of Iraq
KRG	Kurdistan Regional Government
LMIS	Logistics Management Information System
MoH	Ministry of Health
MOLSA	Ministry of Labour and Social Affairs
MoP	Ministry of Planning
MoYS	Ministry of Youth and Sports
PHCC	Primary Health Care Centre
RH	Reproductive Health
ToT	Training of Trainers
VFP	Voluntary Family Planning