## Annual Review
Title: Data for Foundational Learning
Programme Value £ (full life): £27,000,000		Review date: 25/02/2026
Programme Code: 301259	AMP start date: 01/04/2022	AMP end date: 31/03/2027

Summary of Programme Performance
Year	2024	2025	2026	2027
Overall Output Score	A	A	A
Overall programme risk rating	Minor	Minor	Minor

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Results Framework

## A: SUMMARY AND OVERVIEW
Description of programme
1. With over 270 million children estimated to be out-of-school, and some 70% of children in low- and middle-income countries unable to read and understand a simple sentence by the age of ten, there is a global education crisis. In this context, the UK is committed to improving foundational learning for all and driving progress against Sustainable Development Goal (SDG) 4 to ensure inclusive and equitable quality education for all. The range of investments supported under the Data for Foundational Learning (D4FL) programme is critical to achieving these objectives.
2. The D4FL programme (£27m, 2022-2027) aims to contribute to more countries reporting progress against SDG 4.1.1[1] and reducing learning poverty[2] in lower- and lower-middle-income countries (LICs and LMICs) by supporting high quality assessments, data generation and state capacity to use data. Programme activities deliver against the following three objectives:
  [1] SDG 4.1.1 measures the proportion of children and young people: (a) in grades 2/3; (b) at the end of primary; and (c) at the end of lower secondary achieving at least a minimum proficiency level [MPL] in (i) reading and (ii) mathematics, by sex.”
  [2] Learning poverty is the share of children being unable to read and understand a simple text by the age of ten. The indicator was developed by the World Bank in coordination with UNESCO Institute for Statistics (UIS) in 2021 to highlight the global learning crisis.
  1. Track global learning outcomes to enable reporting for SDG 4 numeracy and literacy reporting and G7 girls’ education targets (Track)
  2. Generate more quality data through learning assessment tools, support with technical assistances and promoting citizen led assessments (Generate)
  3. Ensure data is used to improve the planning, design and implementation of foundational learning initiatives (Use)
3. The programme supports a range of priority interventions through various partners including the UNESCO Institute of Statistics (UIS), the Global Education Monitoring Report (GEMR), the People’s Action for Learning (PAL) Network, the Australian Centre for Education Research UK (ACER UK), the World Bank, UNICEF, and the National Foundation for Education Research (NFER).

Summary supporting narrative for the overall score in this review
1. This is the third Annual Review for this programme, covering March 2025 – February 2026. Overall, the programme has scored an A, reflecting very good progress against the outputs with ongoing work to support capacity building for better quality assessment and reporting. The Mid-Term review (MTR) of the D4FL programme highlighted it has responded well to the need of the global education community to demonstrate that countries can generate globally comparable data through a range of pathways. And that there is a high level of coherence with other global and national effort to strengthen foundational learning data.
2. Key achievements during the reporting period include:
1. National assessments in several countries being strengthened, through timely FCDO support, working closely with partner governments
2. The PAL network[3] completed the ambitious simultaneous generation and publication of their International Common Assessment of Numeracy and International Common Assessment of Reading (ICAN-ICAR) common assessment in 12 countries
  [3] The PAL Network is a South-South partnership of 17 member organisations working across 15 countries in Africa, South Asia, and the Americas to advance foundational learning.
3. Increasing collaboration across development partners, despite significant institutional change for most organisations.

Major lessons and recommendations for the year ahead

1. This section sets out key lessons and recommendations from the past year. However, in the context of the UK significantly reducing its Official Development Assistance (ODA), their implementation for the year ahead is dependent on the outcome of the Spending Review budget decisions and transition to FCDO’s new operating model. The recommendations therefore highlight where impact and value for money can be maximised, subject to these constraints.
2. Important lessons from this review include:
  1. D4FL funded efforts to enable countries to report against national assessments aligned with global standards remains important, with increasing ambition from partner governments to find local solutions, shared in 2025.
  2. The programme is on track to lead to new, high quality foundational learning data being generated and more tools being available. However, there is limited evidence to date that the programme is on track to improve the design and monitoring of foundational learning interventions. Evidence of support going beyond national learning assessment units, to include and inform curricula and instruction, will be important. Coherence with the wider FCDO education portfolio of programmes, and development partners, provides a route to better leverage high quality learning data to improve foundational learning outcomes.
  3. While there is growing information on reporting requirements and global methodologies, the extent to which these are well understood by different stakeholders is mixed. More outreach should be undertaken with national Ministry of Education staff and local stakeholders by D4FL partners, to ensure their needs are being met by activities. Capacity building of FCDO Education Advisers, alongside development partner staff, to better understand issues related to data and the D4FL offer should also be prioritised.
  4. Marginalised children are still at risk of being excluded from comparable learning data collection efforts globally. Comparable household assessments pioneered by the PAL Network and the strengthening of the foundational learning module by UNICEF will continue to play an important opportunity to enhance inclusions in comparable learning assessment.
  5. Plans to reduce ODA and change FCDO’s operating model mean that once spending review outcomes and staffing are confirmed in 2026, a clear programme and policy plan will be required, to maximise value for money and the sustainability of investments under D4FL going forward.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES
Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.
1. The D4FL programme theory of change is designed to deliver against the following impact: Contribute to progress against SDG 4.1.1 and learning poverty reduction in lower- and lower-middle-income countries (LICs and LMICs). The theory of change was revised in the formative evaluation, published in January 2025. No changes have been made since then.
2. The Mid-Term evaluation, which was completed in November 2025 included a red, amber, green (RAG) rating for the pathways set out in the theory of change, highlighting which outcomes are likely to be achieved, and which are at risk of only being partially achieved. The RAG-rated theory of change diagram can be found at Annex B.
3. The 2025 Annual Review recommended a comprehensive logframe review to ensure the outputs, indicators and weighting reflect the activities and intended outcomes of the programme against the revised Theory of Change agreed in early 2025. Progress: This was completed, in consultation with all partners in July – August 2025, and all changes recorded. These mostly related to the number and weighting of outputs, exact wording, and grouping of indicators, to better reflect the agreed Theory of Change. No changes were made at outcome/impact level or in contrast to what was set out in the original Business Case.

The evaluation also tested the validity of the assumptions underpinning the theory of change. Some of the assumptions relating to the pathways from outputs to outcomes have not held during implementation. Notably that there would be more opportunity for partners to support learning data in emergency contexts. During the final year of the programme, working with partners to maximise ways learning data can be more inclusive will be essential. The evaluation also challenges the assumption that improving learning data for SDG4 will improve learning for all. The assumptions will be revisited ahead of the final summative evaluation, given the changes in the global education context since the design in 2022.
Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?
While there has been good performance against the output indicators as set out in the programme logframe, the evaluation concluded that not all the programme outcomes are on track.
Outcome 1: Global learning data gaps filled, including in emergency contexts	Likely to be partially met
Outcome 2: More disaggregated learning data available that can be used to design and monitor foundational learning interventions	Likely to be met
Outcome 3: Increased capability in priority countries to use learning data to design and monitory foundational learning interventions	At risk of not being met

1. Under outcome 1, while more internationally comparable data from LICs and LMICs will be generated, it is not yet clear if the data will be accepted for SDG 4 reporting, as the processes are still not finalised. In addition, gaps in Education in Emergency (EiE) settings remain and marginalised groups including out-of-school children, children with disabilities, children residing in rural settings, and refugees are at risk of being excluded from data collection efforts.
2. Through support for national assessment and data collection processes under output 2, high quality data on foundational learning is being generated. This data will have the potential to inform the design and monitoring of education policy and programming. Technical assistance provided by ACER UK has helped respond to national demand, ensuring alignment of national assessments with UIS criteria and global standards.
3. For output 3, there is limited evidence that the act of reporting against SDG 4 will create accountability for improved learning outcomes and/or capability to use the data. Indeed, little D4FL resource has been allocated specifically to the use objective. In the final year of the programme, FCDO and partners should highlight contexts/programmes where data is being used to inform policy and programming and where FCDO programming and influencing across the portfolio are enabling better use of learning data and tools generated.
4. While the evaluation included an assessment of progress against outcomes, not all the impact and outcome indicators in the logframe include targets. These should be finalised as soon as possible to ensure a formal assessment of progress in the Project Completion Review in the first half of 2027.
Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio
The D4FL programme should continue through to the end of March 2027, as it remains highly relevant. This may require adjustments following ODA reductions and changes to the FCDO operating model. Foundational learning for all is a top UK priority and is increasingly recognised as a priority by partner governments across the Global South. Hence the need to more effectively measure learning outcomes. Through strategic investments, the programme has promoted alignment of assessments with SDG 4 reporting requirements and demonstrated that countries can produce globally comparable data using strengthened national assessments and citizen led assessments, not only regional or global assessments. Progress against outputs is on track.

## C. DETAILED OUTPUT SCORING
Output Title	Coordination and publication of comparable learning data using quality assessments (Track)
Output number:		1	Output Score:	B
Impact weighting (%):		15%	Weighting revised since last AR?	Yes, down from 40%

Indicators	Milestones for this review	Progress
1.1: Interventions supported to generate learning data that is feeding into the UNESCO Institute for Statistics (UIS) database	Assessment for Minimum Proficiency Level (AMPL) implemented in 12 LICs and/or LMICs countries and used for reporting 4.1.1, including % of girls reaching minimum learning proficiency in reading by the end of primary school. / Microsite on learning updated.	Partially off track: AMPL implemented in four countries (Gambia, Zambia, Kenya and Lesotho) and used for SDG 4.1.1. reporting. Activities underway in 8 additional countries to varying degrees of completion and due to be completed by 2026. / Learning Data Resource Centre updated in 2025
1.2: Number of Global Education Monitoring Reports contextualising global and regional SDG4 progress published, using diverse sources of assessed quality	Third benchmarks report / Third Spotlight report / At least one regional report edition	Exceeded: Third benchmarks report and Scorecard launched in June 2025. Four regional editions launched since February 2025, including the third Spotlight report launched in October 2025. See links to report below.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 1 is aligned with the track objective, focusing on the publication of comparable learning data using quality assessments. The main implementing partners for this output are the UNESCO Institute for Statistics (UIS) and the Global Education Monitoring Report (GEM-R). While the number of GEMR reports contextualising progress against SDG 4 exceeded expectations (indicator 1.2), fewer countries implemented the Assessment for Minimum Proficiency Level (AMPL)[4] than expected. This output therefore scores a B.
[4] AMPL refers to a set of assessment tools used to measure if children are achieving foundational skills/ Minimum Proficiency Levels (MPLs) in reading and math. The tools complement the Monitoring the Impact of Learning Outcomes (MILO) study, originally carried out in 2021, during the COVID-19 pandemic as a rapid way to measure learning levels. MPLs serve as a global reference point for basic skills that should be acquired in reading and math by grades 2/3, end of primary and end of lower secondary.

1. Indicator 1.1 14 countries in total are being supported to pilot/administer AMPL. This includes the following Low and Middle Income Countries: Rwanda, Bangladesh, Cambodia, Nepal, Sri Lanka, Lebanon, and Tunisia. However, as of December 2025, only four countries had submitted data to UIS to report against SDG 4.1.1 using AMPL results. This is significantly lower than the target of 12. AMPL implementation has faced several challenges, including delays in retendering the implementing partner, and aligning timelines with national readiness and school calendars. UIS focus on AMPL over other tools being designed, while also not widening the range of implementing partners that can implement AMPL, is creating an unnecessary bottleneck for SDG4 reporting and carries risks of fragmentation and cost.
2. Indicator 1.2 tracks the number of GEM reports contextualising global and regional SDG4 progress. During the reporting period, GEM exceeded the target. This includes: The Benchmarks report[5] and the subsequent 2025 edition of the SDG 4 Scorecard[6], in partnership with UIS; Four regional editions launched including; the third continental spotlight report [7] for Africa, Lead for foundational learning; Lead for inclusion on Central and Eastern Europe, the Caucasus and Central Asia, Lead for democracy on Latin America and Lead for technology on East Asia. GEM completed preparatory work for its Countdown to 2030 series report on access and equity. This included a concept note and 30 country case studies. The report will be launched in Paris in March 2026.
  [5] Benchmarks refer to the targets countries have set themselves against the SDG 4 indicators
  [6] Scorecard tracks countries’ progress against their own 2025 and 2030 national education benchmarks. As of 2025, 164 countries (80%) have submitted at least one benchmark indicator
  [7] The Spotlight report series focuses on basic education completion and foundational learning
3. As of December 2025, there have been 350,000 downloads of the GEM Global report, plus 150 events, launches and presentations, including with over 170 senior officials. There have also been nearly 20,000 blog views per month, and over 1.3 million views of all GEM report websites.
Describe any changes to this output during the past year, and any planned changes because of this review.
1. This output was reduced in weighting as planned in 2025, to better reflect the proportionately of these activities, in terms of number of partnerships and percentage of spend, within the wider D4FL programme.
2. In August 2025, Output 1.1’s 2027 indicator has been revised with UIS to ensure the milestone reflects all innovations, new methodologies, and reporting pathways for SDG 4.1.1, not only the AMPL tool. Instead, the indicator will focus on the number of countries successfully processed by the UIS vetting mechanism[8]. The vetting mechanism is the process to unlock national learning data, and household data, aligned with SDG4.1.1 criteria and submitted by national governments, to be considered for SDG 4 reporting.
  [8] The UIS vetting mechanism aims to promote standardised learning assessments and a process to evaluate the quality and alignment of national assessments with SDG 4 reporting standards. The ultimate objective is to validate country assessment data, enabling them to report on SDG 4.1.1.
Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead
There were two recommendations under this output from the last AR: to work coherently with development partners to improve comparable learning assessments at national level; and to ensure efforts to drive comparable learning assessments are incentivising use of learning data nationally.
1. Progress: Partners have continued to use existing coordination mechanisms throughout 2025, with the Global Coalition for Learning’s Learning Data Coordination Pillar[9] meeting at least every two months. This has enabled joint work on the upcoming Global Partnership for Education (GPE‑) topup mechanism on learning assessment, recommendations to UIS to accelerate progress towards tracking against ‑SDG4, and shared approaches for countrylevel engagement. In some contexts, FCDO, World Bank and UNICEF are coordinating more regularly at country level to respond coherently to national requests, including sharing quarterly reports to increase visibility of ongoing assessment activities between development partners at country level.
  [9] The Global Coalition for Foundational Learning is made up of FCDO, the Gates Foundation, Global Partnership for Education, UNESCO, UNICEF and World Bank.
2. Progress: D4FL partners’ activities on learning data use were mapped following an evaluator‑led workshop on 23 April 2025. All D4FL partners aligned their actions to their respective grants. The mid‑term review indicates that strengthening learning‑data use requires continued attention. Where possible tracking and generation of data must be use led. This needs to underpin UIS processes going forward.
Lessons learned and recommendations for the year ahead
1. There are three headline lessons and recommendations for Output 1.1 this year:
    1. SDG 4 reporting remains off track. SDG 4 reporting data remains exclusively from regional assessments. The UIS vetting global mechanism will play a key role in enabling more countries to report against SDG 4 using data from national and household assessments, that are aligned with global standards. However, the mechanism is not yet piloted, which will be necessary to confirm the process and guidance for all countries.
    2. While the UIS learning microsite has been updated to include more resources and guidance, the extent to which they are being understood and used by countries to generate and use learning data is not known. Development partners, implementing partners, national governments, and non-government stakeholders report it is difficult to find the latest information, tools, or processes to effectively report on SDG4.1.1.
    3. Although partners share goals, coordination gaps risk incoherence or competing approaches to data generation. These key risks are fragmentation and parallel efforts; institutional incentives that can pull partners in different directions; coordination and coherence relying on individual efforts
2. The recommendations are:
Recommendation 1. Request UIS to share an action plan for implementing the vetting mechanism, including piloting, monitoring and scaling to meet national demand to report. This should also include clear timelines for key milestones and reflect a commitment to transparency and utility for partner countries [FCDO, UIS, ongoing]
Recommendation 2. UIS to select and implement recommendations from the vetting mechanism pilot to ensure the UIS microsite better reflects all available learning data aligned with SDG 4, and that the process, tools and guidance are easily understandable and accessible. Consider carrying out a survey or evaluation to test whether national governments and partners can access what they need. [UIS, FCDO and partners, ongoing]
Recommendation 3. FCDO to develop an engagement plan for global and local support to strengthening learning data leading up to 2030. [FCDO, April 2026]

Output Title	Development and implementation of global methodologies to track foundational learning for all internationally (Track)
Output number:		2	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	No

Indicators	Milestones for this review	Progress
2.1: Publication of new methodology technical papers or tools by partners	UIS: 5 / PAL: 1	Met: UIS: 5 (Annual release of SDG 4 Scorecard report and four new outputs produced and promoted; Criteria for use of an assessment to report on SDG 4.1.1; Buyer’s Guide to International Student Assessment; SDG 4.1.1 Minimum Proficiency Levels: Definition and Blueprint for Assessment; National Education Statistical Capacity Assessment / PAL: 1 (The State of Foundational Learning in the Global South: 2025 Report, November 2025)
2.2: Number of Member States provided with training sessions on setting benchmarks, reporting on learning (4.1.1) and data collection tools (including training on data collection and disaggregation by gender and disability)	70 Member States (30 in Sub-Saharan Africa)	Exceeded: 95 countries (29 in Sub-Saharan Africa)
2.3: Number of validated Multiple Indicator Cluster Survey (MICS) modules developed and made available	Lower primary module validated and made available	Met: Module currently being administered in Zimbabwe

Briefly describe the output’s activities and provide supporting narrative for the score.
1. Output 2 activities contribute to the track objective by supporting the development and implementations of global methodologies to track learning. Activities were delivered by UIS, GEM, the People’s Action for Learning (PAL) Network and UNICEF. This output met expectations and scores an A.
2. Indicator 2.1 tracks the number of new methodology technical papers or tools published by UIS and the PAL Network. This indicator met expectations with six reports/papers being published in line with the target (five from UIS and one from the PAL Network).
3. The headline achievement was The State of Foundational Learning in the Global South: 2025 Report published by the PAL network and launched in Kenya in November 2025 as part of their ten year anniversary celebration. This included representatives across their global network, from South Asia, Latin America and Africa, and for the first time, national government representatives from several countries and parliamentarians from the host country. This launch was hailed as an historic moment, demonstrating how communities across the Global South are generating and using their own high‑quality learning data, aligned with global standards, to understand children’s foundational skills. Overall, the report highlighted that learning levels remain low across low and lower middle-income countries, however it also highlighted the range between countries. Each country is now working to generate their own country specific report. There is more on this in Output 3.
4. The ICAN/ICAR common assessment tool developed by the PAL Network, is open access and is now being adopted and disseminated via several networks, including the What Works Hub for Global Education, who have included it in their recently developed Learning Assessment Guidance. In addition, this support to PAL network is being leveraged by additional support from Education Cannot Wait to adapt the ICAN and ICAR tools for best application in emergency settings, and for children with disabilities.
5. Indicator 2.2 measures the number of countries provided with training sessions to support capacity building in education data generation, with an emphasis on SDG 4 monitoring. In 2025, UIS supported 95 countries (including 29 in Sub-Saharan Africa) with training and support on setting benchmarks, reporting on learning in line with SDG 4.1.1, and data collection tools. This exceeded the overall target of 70 because UIS shifted from isolated support to a coordinated regional approach and will ultimately help deliver Output 1.1.
6. Indicator 2.3 tracks UNICEF’s strengthening of the Foundational Learning Module (FLM) for the Multiple Indicator Cluster Survey (MICS)[10], co-funded with the Gates pFoundation. The updated FLM is intended to strengthen the measurement of learning outcomes within the MICS, through aligning with global standards. This indicator is on track with the lower primary module validated by UIS and being administered in Zimbabwe, due to be completed in January 2026. Zimbabwean Ministry of Education officials are actively engaged in implementation to help build trust in the module, uptake for policy applications, and support to nationally led learning assessment efforts. Following this success, discussions are ongoing with other countries to support a further rollout.
  [10] The MICS is a household survey designed to generate data on the status and wellbeing of children capturing data on a wide range of indicators including education, health, child protection, nutrition and sanitation
7. UNICEF are working to combine these efforts on improving foundational learning data with their efforts on advocacy and prioritisation of foundational learning via the Foundational Learning Action Tracker at country level, to ensure conversations on policy priorities are combined with the available learning data.
Describe any changes to this output during the past year, and any planned changes because of this review.
This output was amended following last year’s review to capture all activities related to the implementation of global methodologies. As a result, indicator 2.2 on training was added to this output (it was previously under Output 3).
Progress on recommendations from the previous AR
1. Last year, there were three recommendations under output 2, they were to disseminate clear guidance to FCDO for reporting on SDG4.1.1; channelling feedback from country to those developing global methodologies and guidance; and increasing an intentional focus on education in emergencies:
  1. Progress: Guidance has been developed in May 2025 and shared internally. This will be updated following progress in the development of global methodologies, increased demand from national governments, and confirmation of UIS guidance, following their change in leadership in 2025.
  2. Progress: Engagement across D4FL partners has strengthened, with biannual meetings taking place and joint representation on panels at major conferences (e.g. UKFIET 2025, ADEA 2025, and an accepted panel for CIES 2026). Partners have collaborated with UNESCO to share practical insights from working directly with governments and in country, helping ensure that guidance, processes, and support to countries are aligned with real in‑country needs and reality.
  3. Progress: Constraints around mandate, clarity, and opportunity mean that generating comparable learning data in emergency contexts falls largely outside the scope of this programme, a challenge heightened by geopolitical and institutional shifts in 2025. Nonetheless, several D4FL partners, including the World Bank, PAL Network, and ACER UK (supporting UNRWA directly), are contributing to efforts in emergency settings but may or may not be reaching the most marginalised in these contexts. The mid‑term evaluation concludes that the programme is unlikely to significantly reduce global learning data gaps for emergency contexts
Lessons learned this year and recommendations for the year ahead
1. D4FL has invested in some relatively low-cost tools and solutions which are potentially scalable and replicable across a range of contexts, and some that are more costly but more effective to build country assessment capacities.
2. Recommendation 4: Use the Centre of Expertise for Education to clearly and coherently communicate the options to track foundational learning in country, including in emergency contexts. This includes application of available learning data, which can be brought into policy conversations and for used for SDG4.1.1 reporting.
Output Title	Generation of comparable learning data using quality assessments (Generate)
Output number:		3	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	n/a

Indicators	Milestones for this review	Progress
3.1: Number of countries in which the PAL Network common assessment is scaled	12	Met: 12 / (Asia: Nepal, Bangladesh and Pakistan / Africa: Kenya, Uganda, Tanzania, Mozambique, Senegal, Mali, and Botswana / The Americas: Mexico and Nicaragua)
3.2: Number of (i) national large-scale, (ii) regional, and/or (iii) international assessments aligned with SDG 4 reporting requirements administered with World Bank ALMA support	2	Met: 2 / Djibouti administered the Programme d'Analyse des Systèmes Éducatifs (PASEC)[11]. / The Organisation of Eastern Caribbean States (OECS) completed the Grade 2 National Learning Assessment (NLA) in reading and maths
[11] PASEC is a CONFEMEN programme and an international assessment focusing on reading and math skills in primary grades, primarily in Francophone Africa

Briefly describe the output’s activities and provide supporting narrative for the score.
1. Output 3 contributes to the overall objective to generate high quality national level learning data by supporting the creation of comparable learning data using quality assessments. Good progress was made against both indicators and this output scores an A.
2. Indicator 3.1 In 2025, the PAL network met their ambitious target of, scaling the ICAN-ICAR assessment[12] model in 12 countries[13] across three continents, reaching 89,185 children aged five to 16. This indicator is also on track to meet the end-of-programme target of 15. This unique effort has resulted in locally rooted but internationally comparable assessments meeting the criteria for MPLs required for SDG 4 reporting. This does not mean it will be automatically included (see more on the role of the UIS vetting mechanism in Output 1, paragraph 23).
  [12] These simple tools are administered by volunteers, one to one in the household, and are adaptable across languages.
  [13] Bangladesh, Botswana, Kenya, Mali, Mexico, Mozambique, Nepal, Nicaragua, Pakistan, Sengal, Tanzania, and Uganda
3. This round includes Botswana, where the assessment was implemented at the school level for the first time, while maintaining the key features of the model i.e. one-on-one, child-centred administration. This may be relevant for children benefitting from non-formal education (NFE) provision not included in national assessments and result in high quality, UIS-aligned, and comparable data for previously excluded groups. The next ICAN-ICAR cycle in 2027/28 will be essential to measure progress, contribute to the evidence base on what works and enhance accountability for foundational learning. For this to happen, the PAL network needs to diversify and increase funding from partners.
4. Indicator 3.2 focuses on the World Bank’s Accelerating Learning Measurement for Action (ALMA) programme which aims to build country capacities to implement national, regional, and international assessments aligned with SDG requirements. ALMA is currently supporting 12 countries at various stages, following requests from World Bank teams in country, and this year supported the implementation of two assessments, meeting the milestone for this review.
5. The ALMA follows a catalytic approach, providing small grants to unlock larger investments in assessment system reform. According to the World Bank, ALMA grants have leveraged a total of US$116,322,635 in World Bank lending. There are indications that assessment efforts are starting to inform policy and programming. For example, in Mali with the development of Grade 1 scripted lesson plans and training materials.
Describe any changes to this output during the past year, and any planned changes because of this review.
Output indicator 3.1 (countries where ICAN-ICAR is scaled) was moved from Output 1 to better reflect the outputs in line with the revised theory of change. Output 1 now focuses on coordination and publication of learning data (track) while Output 3 focuses on generation of learning data (generate).
Lessons learned this year and recommendations for the year ahead
1. There are three lessons and three recommendations for this output this year:
  1. The PAL network has successful initiatives in generating quality data, and delivering cost effective interventions in the community, via their My Village pilots in Tanzania and Nepal. The PAL Network could consider ways to maximise learning across their activities, to leverage the ICAN/ICAR investments, and identify ways to contribute towards the Education Great buy (providing information on the benefits, costs and quality of education).
  2. The PAL network should continue to raise the profile and awareness of the ICAN/ICAR tools themselves to maximise impact. The ICAN/ICAR data continues to potentially be an important option for national governments to report on SDG4.1.1, while the tools are also cost effective and could be applied in emergency contexts, and efforts to generate comparable learning data (even if not to report on SDG4.1.1). Raising the profile and sharing the value will also assist in the necessary funding they need to raise for the next round in 2027/28.
  3. ALMA countries respond to needs as identified by World Bank Task Team Leaders, which has benefits in leveraging wider bank financing. The Mid-Term evaluation highlighted some risks in government ownership and buy-in in some contexts, limiting potential cost effectiveness and sustainability.
2. Recommendations for the year ahead:
1. Recommendation 5. Engage with the PAL Network, as they develop their country reports, to encourage them to share best practice amongst the membership for how to best include governments in ICAN-ICAR assessments/data and to provide information on the benefits of education to local communities. (FCDO/PAL Network, April 2026)
2. Recommendation 6. Disseminate options to use the open access ICAN/ICAR tools to track programming, including in emergency contexts including via the Centre of Expertise and What Works Hub for Global Education guidance on learning assessments.
3. Recommendation 7. Request WB to document concrete examples of data funded by ALMA interventions generating national ownership and thereby informing policy and programmes sustainably and cost effectively. Ensure this is documented in the Project Completion Review. (FCDO/ALMA, March 2027)
Output Title	Adaptation / implementation of rigorous regular primary learning assessments (Track)
Output number:	4 (previously 3)	Output Score:	A
Impact weighting (%):	15%	Weighting revised since last AR?	No (compared to the previous output 3)

Indicators	Milestones for this review	Progress
4.1: Number of ACER UK supported LICs and LMICs with appropriate assessment instruments (and refreshment plans, if required) to support ongoing regular assessment	2	Met: 2 / (Ghana and Rwanda)
4.2: Number of ACER UK supported organisations with appropriate assessment instruments (and refreshment plans, if required) to support ongoing regular assessment	1	Met: 1 / (PAL network)

Briefly describe the output’s activities and provide supporting narrative for the score.
1. Output 4 focuses on capacity building for countries and organisations to strengthen national assessment practices, in line with the track objective. It is exclusively implemented by ACER UK. Both indicators met expectations, ultimately supporting more accurate, relevant and comparable data, and this output scores an A.
2. Indicator 4.1 tracks ACER UK’s support to national governments to strengthen their ongoing national learning assessment systems. This technical support is demand-led, responding to specific requests from partner governments where there is an FCDO Education Adviser. As of the end of 2025, this includes support to Ghana, Rwanda, Malawi, Somalia, and Sierra Leone, with requests from several more countries in the pipeline. In 2025, ACER UK completed its support to two countries (Ghana and Rwanda), in line with the target set out in the D4FL programme logframe. In both instances, the data generated from the supported assessments is being used to monitor and design interventions to improve learning, and as the potential to be used for SD4.1.1 reporting. See example from Ghana below.
3. Ghana: ACER UK provided support to Ghana’s national assessment authority, the National Council for Curriculum and Assessment (NaCCA), to integrate the UIS criteria into its standardised large-scale national assessments and support submission of documents to report against SDG 4.1.1. The support included capacity building of the assessment authority through workshops to review items for the 2023 Primary 4 National Standardised Test (NST), following which NaCCA produced the 2025 Primary 2 NST. The scope of ACER UK’s assistance was extended in April 2025 to support the development of the kindergarten 2 (K2) NST.
4. The evaluation highlights how the output activities have contributed to increased use of reliable data on foundational learning. In Ghana, the Ministry of Education, NaCCA, and partners are using NST data to inform teacher development, school grants, and programme monitoring. In Rwanda, the Learning Achievement in Rwandan Schools (LARS) data is being used to inform curriculum and system reforms, and further early-grade assessments and disaggregation is planned.
5. Indicator 4.2 tracks ACER UK’s support to organisations on assessments. During the reporting period, ACER UK supported the PAL Network to quality assure the PAL Networks efforts to ensure the ICAN-ICAR met UIS eligibility criteria. ACER UK support to UNRWA is ongoing and will be completed in 2026.
Progress on recommendations from the previous AR (if completed)
Partners to apply political economy tools as they plan for and implement TA in specific countries. D4FL partners should share political economy learning with D4FL partners, where appropriate. Progress: Partners have strengthened stakeholder mapping and management, with ACER UK and NFER demonstrating increased adaptability to change. FCDO has shared political‑economy tools to support this work. FCDO Education Advisers continue to play a critical role to deepen partners’ political economy understanding in country, while the World Bank is reflecting on this as part of their focus on developing in-country impact narratives.
Lessons learned this year and recommendations for the year ahead
1. Lessons learned for this output:
  1. ACER UK’s demand-driven model provides both relevant and effective support, with the initiatives funded under output 3.1 contributing to sustained capacity building.
  2. There is evidence that D4FL may have contributed to increased demand for foundational learning data in some supported countries. However, this demand remains fragile, and although timely technical assistance has proved effective, as it stands, available expertise risks seeming scare and costs remaining high.
2. Recommendations for the year ahead:
1. Recommendation 8. options for FCDO’s Centre of Expertise for Education to build on best practice under D4FL (e.g. via ACER UK) to support the supply of technical support to strengthen national learning assessments that prioritise a cost effective and use led approach. This should have a clear strategy alongside for engaging with informed customers at country level to ensure coherent and sustainable uptake of any draw down offers.
2. Recommendation 9. Work towards leveraging the D4FL support to household and national government assessments to date, to get behind a growing Community of Practice in Africa, informed by country demand and building on local expertise.

Output Title	Strengthened mechanisms for use of learning data in national decision making, policies and reforms. Strengthened use of simple foundational learning assessments in classroom and community interventions. Strengthened curricula teacher development, pedagogy and teaching materials to support foundational learning. (Use)
Output number:		5	Output Score:	A
Impact weighting (%):		20%	Weighting revised since last AR?	Yes – up from 15%

Indicators	Milestones for this review	Progress
5.1: Number of supported projects introducing/enhancing elements of the foundational learning instructional core during key influence points in the dialogue or project cycle.	10	Exceeded: 12 (Central African Republic, Cote d’Ivoire, Eswatini, Ghana, Liberia, Madagascar, Malawi, Republic of Congo, Rwanda, Senegal, Sierra Leone, and Tanzania)
5.2: Regional Education Assessment Resource Centre (EARC) established as a centre of excellence on assessment design, delivery, analysis and use.	8 core modules developed	Met: Seven core modules developed and the final one being finalised by March 2026.

Briefly describe the output’s activities and provide supporting narrative for the score.
1. Output 5 is the only output linked to the programme’s use objective. It met expectations and scores an A.
2. Indicator 5.1 focuses on support provided via the World Bank Accelerator Programme to enhance the ‘instructional core’ in policy and programming. The instructional core refers to classroom-level interactions between teachers, students, and learning content. As such, it is key to improving learning outcomes. In 2025, 12 countries were supported through the Accelerator, exceeding the target of 10. Of the 12 countries, eight have been able to provide reporting on the number of children benefiting from interventions to enhance learning. According to the World Bank, nearly 34 million children have benefitted. Two of the countries are classified by the World Bank as fragile/conflict affected.
3. Like ALMA, Accelerator grants are used to leverage additional funding to support the implementation of World Bank foundational learning programmes. At the global level, support provided by the Accelerator includes two consultants to support World Bank country teams with expertise on foundational learning to ensure countries are spending effectively. An internal Community of Practice on foundational learning has also been established for World Bank teams.
4. Indicator 5.2 tracks the establishment of the Regional Education Assessment Resource Centre (EARC) by the Kenya National Educational Assessments Council (KNEC) with support from the National Foundation for Educational Research (NFER). KNEC’s vision for the EARC is for it to serve as a regional and country level hub for training and materials, and to provide support for countries on assessment and use of assessment data through technical assistance and peer-to-peer learning. NFER support is focused on capacity building, including through a Trainer of Trainers model. In 2025, seven modules were developed and delivered and the eighth is due to be finalised by March 2026.
Progress on recommendations from the previous AR (if completed)
1. Three recommendations from last year covered efforts to collectively strengthen capacity building in global south; working horizontally across the FCDO portfolio to improve foundational learning in the classroom; and identifying Accelerator 2.0 case studies to demonstrate links between assessment and policies on curricula and teaching.
  1. Progress: EARC, with NFER support, co‑hosted a Gates‑supported convening with ADEA in Nairobi in August 2025. Attendance included representation from ACER UK, NFER and the PAL Network, to explore how to strengthen Global South leadership in assessment, including access to resources, training and support. This work will continue in 2026, leveraging D4FL investments.
  2. Progress: There are emerging examples of stronger FCDO cross‑programme collaboration. For example, in Malawi, the Scaling Access and Learning in Education (SCALE) TaRL pilot and ACER UK jointly engaged in government workshops. In Kenya, the British Council has linked EARC to the new teacher education technical working group established through the What Works Hub for Global Education (WWHGE). In January 2026, UNRWA, supported by an FCDO adviser, brought together TA from SCALE, EdTech and D4FL to share activities. WWHGE is also integrating selected D4FL tools into its guidance for the research community on learning assessments. However, the evaluation notes that such collaboration remains uneven and requires more systematic strengthening.
  3. Progress: Accelerator grants are strengthening remedial and targeted instruction activities in three countries (Ghana, Eswatini, and Rwanda), for which assessment is a critical component of the approach. Additionally, in the past year, the Accelerator held a community of practice event specifically focused on remedial programme design and implementation, featuring work from the Science of Teaching Program. Impact and coherence across investments in the FLC will continue to be monitored by FCDO.

Lessons learned this year and recommendations for the year ahead
Lessons learned for this output:
1. The EARC could serve as a critical, cost-effective and sustainable model to support the capacity building of LICs and LMICs on assessment. The outcomes/longer-term impact should be monitored (beyond the final year of D4FL implementation) to test the feasibility of the model and whether it could be replicated in other areas.
2. The World Bank Accelerator Team recognises the need to upskill staff on issues related to learning and assessment and has established a network to support them. Having this technical support to complement funding and programming is essential and should be replicated more widely.

Recommendations for the year ahead:
1. Recommendation 10. Ensure the D4FL Project Completion Review includes a plan for ongoing engagement and monitoring of EARC outputs, either through the Centre of Expertise for Education or from regional FCDO Education Advisers. (FCDO/NFER, April 2027)
2. Recommendation 11. 11. Explore whether sessions held by the World Bank Community of Practice could be expanded to technical counterparts from implementing countries and other donor agencies. (FCDO/Accelerator, April 2026).
Output Title	Evaluate programme
Output number:		6	Output Score:	A
Impact weighting (%):		5%	Weighting revised since last AR?	Yes – down from 10%

Indicators	Milestones for this review	Progress
6.1: Adaptive evaluation of programme to improve effectiveness	Final Mid-term review submitted	Met; rated ‘good’ by EQUALs.

Briefly describe the output’s activities and provide supporting narrative for the score.
Output 6 focused on the programme evaluation delivered through a contract with Mokoro and Oxford MeasureEd. This output scores an A. The evaluation was structured across the six OECD‑DAC evaluation criteria: relevance, coherence, effectiveness, efficiency, impact, and sustainability. This has resulted in 30 important findings, followed by five major recommendations, focussing on data use and ownership, as well as inclusion and sustainability. The findings were shared with the FCDO programme team, and with all FCDO partners in December 2025. The FCDO’s Evaluation Quality Assurance and Learning Service (EQUALS) gave the evaluation an overall rating of good in January 2026.
Describe any changes to this output during the past year, and any planned changes because of this review.
As part of the overall logframe revision of number of outputs and weighting, the output weighting was revised as planned in 2025. There are no planned changes for 2026.
Progress on recommendations from the previous AR (if completed) and lessons learned this year and recommendations for the year ahead
1. Prepare for the Mid-Term Review and the Summative Evaluation well in advance, including scheduling country case studies. Prioritise workshops with partners in advance, to help secure participation from participants. Progress: The evaluation was organised and timely. They have used their reflections on participation and case studies to feed into the plans for the summative assessment to drive the best possible results and value for money.
2. Looking ahead, the examples and evidence of data use are currently limited as are efforts to ensure more children affected by emergencies and protracted crises are reached.
3. Recommendation 12. Ensure implementing partners and FCDO advisers encourage and track examples of data use, inclusion and sustainability, supported by the programme, to share with the evaluation team.

D: VALUE FOR MONEY
Key cost drivers and performance
The main cost drivers of this programme are staff time, reports, developing assessment tools, conducting workshops, and travel.

The independent Mid-Term Evaluation concludes that the D4FL programme continues to provide good value for money. The programme objectives are relevant to the global education sector and LICs and LMICs. In most cases funded activities are likely to achieve their intended results efficiently and in a synergistic way, complementing and not duplicating other efforts. There are also positive signs of sustainability in several supported countries. In addition, the programme crowds in and leverages additional funding, furthering its aims. The evaluators flag that sufficient support for data use is needed to realise the programme’s full potential and maximise value for money.

Economy: Accountable grants follow sound procurement and cost control, aligned with the Business Case VfM indicators (e.g. consultant fee rates, admin cost ratios). ACER UK provides favourable rates to FCDO to deliver support to LICs/LMICs, while the PAL Network, used trained volunteers to deliver assessments globally for 90,000 children in 2025.

Efficiency: The evaluation finds that D4FL activities fill gaps and complement other assessment efforts, with no duplication identified. There are potential strong efficiency gains from integrating the new UIS SDG 4 criteria into national assessments, yielding simultaneous benefits for both national systems and SDG reporting. The efficiency is potentially weaker where partners run parallel assessments to generate data, as this risks limited national capacity building or ownership.

Effectiveness: There is strong evidence of strengthened national assessment systems through support from ACER UK, creating a dual‑benefit investment improving both domestic utility and global comparability. In addition, there is effective production of replicable global methodologies (e.g. ICAN/ICAR), which provide low‑cost, scalable models for LMICs, including those with limited capacity to carry out national learning assessments.

Equity: D4FL supports gender-disaggregated reporting aligned to UIS criteria, and household surveys (PAL Network, MICS) include out of school children and remote learners. ACER UK raises equity issues with governments in their initial meetings to test scope for maximising support to inclusive assessments. For non-government interventions, the PAL Network has mobilised additional resource to adapt the tools under this programme to apply better to children with disabilities and EiEPC contexts.

Cost-‑effectiveness: D4FL is on track to produce new or betterquality foundational learning data in 16 of 24 supported settings, with 27 additional quality foundational learning data in 16 of 24 supported settings, with 27 additional‑ countries potentially able to report by 2027. As outlined in the original business case, robust and reliable learning assessments are critical for targeting education reforms effectively and equitably. The costs of developing high-quality assessments are minimal relative to the overall broader costs of education systems and the long-term consequences of not addressing foundational learning gaps. When done well, improving learning assessments can be the least expensive but most effective education reform[14]. Currently, there are data-use pathways (policy uptake, instructional shifts) evident in only 8 of 24 cases. In the last year of the programme, there will be a focus on coherence with governments partners and within FCDO, to ensure data generated through the programme is used to improve foundational learning for all.
[14] UNESCO (2018) – Making the Case for Learning Assessment

Overall VfM Assessment
D4FL continues to represent good value for money, especially in its catalytic financing, contribution to global public goods, and strengthening of national assessment systems. The programme objectives to enhance the breadth, depth, quality and use of data to enhance learning outcomes, particularly foundational learning, remain highly relevant.

E: RISK
Overview of risk management
1. The overall risk rating for the D4FL programme remains minor, with the programme operating comfortably within FCDO’s corporate risk appetite across all categories. Risks are regularly reviewed through monthly team discussions and updates to the programme’s Risk Register on AMP. Where necessary, risks are escalated to the Girls’ Education Programme Team (GEPT) Leader for advice and mitigation planning.
2. Over the past year, the programme experienced stable risk exposure in most categories, with minor areas of pressure linked to change of leadership in UIS, and in UNICEF as part of UN80. Mitigation strategies have proven effective in maintaining delivery within risk appetite. A brief update on three institutional risks highlighted in the 2025 Annual Review are:
1. UIS: Risks remain that UIS will not have developed nor delivered a clear and inclusive approach to accept the national governments and household data, supported via this programme. UIS, under new leadership as of summer 2025, is committed to ensuring they have the right staff in place, and an effective prioritisation and delivery plan. They are engaging closely with development partners, including FCDO, to support this. Continued monitoring remains essential.
2. World Bank: The World Bank’s strategic push on improving jobs and skills for young people risks moving away from their previous priority of improving foundational learning outcomes. This risks limiting the leveraging of investments via the World Bank to increase a focus on learning outcomes through their programming and to provide support to national governments’ education reforms. The FCDO team continues to work with the World Bank education teams to press for investments in the global practice to benefit the broader World Bank IDA portfolio to deliver learning outcomes. Continued monitoring remains essential.
3. PAL Network: The Network managed their risks effectively this year, collecting data in 12 countries and delivering on the common assessment report to time. Looking ahead they will need to secure financing to support the management of risks beyond 2027.
A key risk looking ahead relates to the reduction in ODA and changes in the FCDO operating model. This will potentially result in changes to this programme in the final year. FCDO will continue to keep partners closely informed on plans. Once Spending Review outcomes and staffing are confirmed in 2026, a clear programme and policy plan will be developed to maximise value for money and sustainability of investments under D4FL.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
Summarise the performance of partners and FCDO, notably on commercial and financial issues
D4FL has had eight active project components implementing through the year, with payments being made to all eight related organisations during this review period. The final arrangement (with UNICEF) was signed in late February 2025 - and the first payment made from the related component in April 2025.

The 24/25 budget allocation was £7.7m and the actual spend was £7.76m. The 25/26 original budget allocation was £7.96m and actual spend expected to be around £7.5m

At the end of 25/26, the forecast total spend of the D4FL programme will be around £18.5m against the approved BC value of £27m. The final financial year of the programme is 26/27. The final budget will be confirmed before the start of FY26/27.

The programme continues to monitor performance through regularly scheduled reporting against logframes, results frameworks, milestones and budgets, in line with the various Memoranda of Understanding, Accountable Grants, contracts, WB arrangements, and FCDO framework arrangements. For this reporting period, the narrative and financial reporting has been extremely timely and of very good quality across the programme.

Partners’ outstanding due diligence recommendations (all minor) continue to be threaded into updates via scheduled reporting. On financial accountability, the audit reports of the multilateral organisations’ external auditors are public documents and available to view on all their Executive Board’s website when published. The latest Annual Audited Accounts for the Accountable Grant partners are the filed appropriately.

G: MONITORING, EVIDENCE AND LEARNING
In its third full year of delivery, the programme underwent an independent Mid-Term Evaluation, summarised in Output 6. The recommendations have been incorporated into this Annual Review and will be taken forward by the D4FL team, with actions integrated into the programme workplan. The FCDO D4FL programme team meets partners quarterly, and in some cases monthly, including joint sessions with relevant partners and co-funders. Internally, the programme team convenes quarterly Steering Committee meetings with programme leads and cross-cutting advisers to guide strategic decisions.

Country monitoring missions were conducted in Ghana in October 2025 and Kenya in November 2025. These visits included engagement with government officials partnering with ACER UK, PAL Network members representing 15 organisations, World Bank country teams, the UNICEF regional office, and the British Council Kenya as NFER’s downstream partner.

Externally, D4FL partners continue to promote the generation and use of learning data by sharing evidence with governments and sector organisations. The programme co-curated sessions at the UKFIET Conference (September 2025), the ADEA Triennale (October 2025), and the PAL Network Conference (November 2025), and has been accepted to present at the Comparative and International Education Society (CIES) conference in 2026. Partners will continue to seek opportunities to disseminate learning jointly to maximise global impact.

ANNEX A; List of recommendations for the coming year
Lesson from AR 2026	Recommendations for 2026/27
SDG 4 reporting remains off track. SDG 4 reporting data remains exclusively from regional assessments. The UIS vetting global mechanism will play a key role in enabling more countries to report against SDG 4 using data from national and household assessments, that are aligned with global standards. However, the mechanism is not yet piloted, which is necessary to confirm the process and guidance for all countries.	1.Request UIS to share an action plan for implementing the vetting mechanism, including piloting, monitoring and scaling to meet national demand to report. This should also include clear timelines for key milestones and reflect a commitment to transparency and utility for partner countries [FCDO, UIS, ongoing]
While the UIS learning microsite has been updated to include more resources and guidance, the extent to which they are being understood and used by countries to generate and use learning data is not known. Development partners, implementing partners, national governments and non-government stakeholders report it is difficult to find the latest information, tools or processes to effectively report on SDG4.1.1.	2. UIS to select and implement recommendations from vetting mechanism pilot to ensure UIS microsite better reflects all available learning data aligned with SDG 4, and that the process, tools and guidance are easily understandable and accessible. Consider carrying out a survey or evaluation to test whether national governments and partners can access what they need. [UIS, FCDO and partners, ongoing]
Although partners share goals, coordination gaps risk incoherence or competing approaches to data generation. These key risks are fragmentation and parallel efforts; institutional incentives that can pull partners in different directions; coordination and coherence relying on individual efforts	3. FCDO to develop an engagement plan for global and local support to strengthening learning data leading up to 2030. [FCDO, April 2026]
D4FL has invested in some relatively low-cost tools and solutions which are potentially scalable and replicable across a range of contexts, and some that are more costly but more effective to build country assessment capacities.	4. Use the Centre of Expertise to clearly and coherently communicate the options to track foundational learning in country, including in emergency contexts. This includes application of available learning data, which can be brought into policy conversations and for used for SDG4.1.1 reporting.
The PAL network has successful initiatives in generating quality data, and delivering cost effective interventions in the community, via their My Village pilots in Tanzania and Nepal. The PAL Network could consider ways to maximise learning across their activities, to leverage the ICAN/ICAR investments, and identify ways to contribute towards the education great buy (“providing information on the benefits, costs and quality of education”).	5. Engage with the PAL Network, as they develop their country reports, to encourage them to share best practice amongst the membership for how to best include governments on ICAN-ICAR assessments/data and to provide information on the benefits of education to local communities. (FCDO/PAL Network, April 2026)
The PAL network should continue to raise the profile and awareness of the ICAN/ICAR tools themselves to maximise impact. The ICAN/ICAR data continues to potentially be an important option for national governments to use to report on SDG4.1.1, while the tools are also cost effective and could be applied in emergency contexts, and efforts to generate comparable learning data (even if not to report on SDG4.1.1). Raising the profile and sharing the value will also assist in the necessary funding they need to raise for the next round in 2027/28.	6.Disseminate options to use the open access ICAN/ICAR tools to track programming, including in emergency contexts including via the Centre of Expertise and What Works Hub for Global Education guidance on learning assessments.
ALMA countries respond to needs as identified by World Bank Task Team Leaders, which has benefits in leveraging wider bank financing. The mid-term evaluation highlighted some risks in government ownership and buy in some contexts, limiting potential cost effectiveness and sustainability.	7. Request WB to document concrete examples of data funded by ALMA interventions generating national ownership and thereby informing policy and programmes sustainably and cost effectively. Ensure this is documented in the Project Completion Review. (FCDO/ALMA, March 2027)
ACER UK’s demand-driven model provides both relevant and effective support, with the initiatives funded under output 3.1 contributing to sustained capacity building	8.Explore options for FCDO’s Centre of Expertise for Education to build on best practice under D4FL (e.g. via ACER UK) to support with the supply of technical support to strengthening national learning assessments that prioritises a cost effective and use led approach, with a clear strategy for engaging ‘informed customers’ at country level to ensure coherent and sustainable uptake of any draw down offers.
There is evidence that D4FL may have contributed to increased demand for foundational learning data in some supported countries, though this demand remains fragile, and though effective, available expertise risks seeming scare and costs remaining high.	9.Work towards leveraging the D4FL support to household and national government assessments to date, to get behind a growing continental Community of Practice in Africa, informed by country demand and building on local expertise.
The EARC could serve as a critical, cost-effective and sustainable model to support the capacity building of LICs and LMICs on assessment. The outcomes/longer-term impact should be monitored (beyond the final year of D4FL implementation) to test the feasibility of the model and whether it could be replication in other areas.	10. Ensure the D4FL Project Completion Review includes a plan for ongoing engagement and monitoring of EARC outputs, either through the Centre of Expertise or from regional FCDO Education Advisers. (FCDO/NFER, April 2027)
The World Bank Accelerator Team recognises the need to upskill staff on issues related to learning and assessment and established a network to support them. Having this technical support to complement funding and programming is essential and should be replicated more widely	11. Explore whether sessions held by the World Bank Community of Practice could be expanded to technical counterparts from implementing countries and other donor agencies. (FCDO/Accelerator, April 2026)
The examples and evidence of data use is currently limited as is efforts to ensure more children affected by emergencies are reached.	12. Ensure implementing partners and FCDO advisers encourage and track examples of data use, inclusion and sustainability, supported by the programme, to share with the evaluation team. programme, to share with the evaluation team.

ANNEX B – RAG RATED THEORY OF CHANGE