## Annual Review Template

Title: Green Growth Nepal (GGN)
Programme Value £ (full life): 38 million		Review date: 27th June, 2025
Programme Code: 301260	AMP start date: 28/06/2023	AMP end date: 31/03/2031

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Major	Major

DevTracker Link to Business Case:	https://iati.fcdo.gov.uk/iati_documents/D0003513.odt
DevTracker Link to results framework:	https://iati.fcdo.gov.uk/iati_documents/D0007301.xlsx

A. SUMMARY AND OVERVIEW

Description of programme

The Green Growth Nepal (GGN) programme aims at promoting green economic development in Nepal. It does so through three components:

- Component 1: National Green Growth (NGG) provides technical assistance (TA) to federal and provincial governments (around economic projects) to enhance policy, strategy, and regulatory frameworks for green economic, industrial and investment-led growth, while also strengthening the Office of the Investment Board Nepal (OIBN), to attract foreign direct investment (FDI) and promote the adoption of public-private partnerships (PPPs).
- Component 2: Green Growth for Provinces and Cities (GGC) focuses on improving urban development and green infrastructure in Madhesh, Lumbini, and Karnali provinces by building local government capacity and attracting investments into city clusters.
- Component 3: Financial Sector Deepening (FSD) supports regulatory reforms and capacity building in financial institutions to improve access to international and green finance for infrastructure projects. GGN is designed to align with both Nepal’s national priorities and the UK’s development strategy, and it aims to leverage UK partnerships by drawing on British expertise, institutions, and financing mechanisms to support climate-resilient infrastructure, inclusive economic growth, and improved investment environments.
The components, in tandem, aim to: support in Nepal’s bid to attract foreign direct investment including green private and concessional finance; build green and resilient transformative infrastructure; and support dynamic urban growth by combining project development and financing of cluster level projects.

Summary supporting narrative for the overall score in this review

The overall score for the programme is A.

The programme underwent a 5-month inception period July-December 2024, and has had a short implementation period of 3-months for the period of this Annual Review (AR). GGN has established good working relationships with key counterpart agencies including Office of Investment Board of Nepal (OIBN), Ministry of Finance (MoF), Electricity Regulatory Commission (ERC), Ministry of Urban Development (MoUD), Nepal Rastra Bank (NRB) and Securities Board Of Nepal (SEBON). The GGN Steering Committee met on 21st February 2025, and fed in and endorsed the GGN annual workplan. An urban thematic working group was also formed, co-chaired with MoUD. The thematic committee endorsed GGN’s urban approach, and will be an important vehicle for influencing national urban policies.

Under Component 1, positive progress has been made towards understanding the policy gaps for green economic investments including on PPP and to a lesser extent on industrial policies. These are being used to troubleshoot specific GGN-supported project policy bottlenecks. The support for the sustainability of OIBN has been initiated through development and endorsement of a new 5-year Strategy and Business Plan, which provides a framework to work on Human Resources and Independent Fund sustainability. GGN made a tangible contribution to getting 1 cable car project to the next stage in project development, with the aim to reach final close as per the Theory of Change (ToC). Collaboration has also begun with ERC that will increase energy sector competitiveness.

Progress has also been made in Component 2 (Cities), which has developed a robust working relationship with MoUD. The ministry has been in a process of reviewing its long-standing policies where GGN was able to provide its expert opinion. The city cluster approach note – a forward-looking policy note that could speed-up urban growth, and get mainstreamed into the larger Urban strategy – has been endorsed by MoUD. GGN identified high-potential cluster level projects, which will be reviewed further for their potential to be developed into green or climate resilient PPPs. Component 2 has also been able to leverage the UK’s Centre of Expertise (Green Cities, Infrastructure and Energy) funding, which will review the Lumbini province City Master Plan, and see which projects can be taken forward.

Component 3 (Financial Sector) has established crucial relationships to leverage green finance and operationalise derisking policies, partnership and instruments. Work is underway with Nepal Electricity Authority (NEA) to support them in raising funds for projects, which includes a potential energy bond and in refinancing. Beyond the government, the programme has progressed conversations with The Currency Exchange Fund, NORAD, Invest for Impact Nepal (IIN), Nepal Bankers Association (NBA), and International Finance Corporation (IFC). The component has progressed discussions for establishing a dedicated debt fund and green bonds in collaboration with NMB Bank Ltd, with the latter committing to an initial anchor tranche of USD 40-50 million.

The country operating context while still fraught with political instability has become more conducive with the Government of Nepal bringing forth two rounds of business and investment enabling reforms. This shows that the operating context has become more conducive to delivering programme impact. However, ODA reductions for the current financial year and beyond have resulted in some changes to this programme. This AR reflects that the programme has had to spend time refocusing resources and so will deliver against a new plan with new results targets. As a result, the findings reflect on a programme in transition. A key shift has been a reduction in ambition on provincial work within Component 1 and 2, and also with increased focus on bringing mature infrastructure projects to fruition, over new project development. The focus on green and resilient remains integral.

Even though early signs of progress towards outcome have been satisfactory, this has been achieved with inefficient and slow programme management practices. The inception period was slow. This is especially due to the time it took to mobilise the full team. Additionally, GGN’s hiring process was initially slow, reporting deadlines missed, and it took time to align to standard programme practices. Careful planning is required going forward to maximise the use of scarce programme resources.

Major lessons

To have a holistic impact on reforming the project development and investment landscape, it is important to look at the whole of political economy to understand interdependencies across the system and work around them. Working too narrowly with only one agency limits the extent to which different perspectives of multiple Ministries, Departments and Authorities (MDAs) and private sector is incorporated. Technical interventions with only one agency have yielded incomplete results, hence require broader engagement both from program and counterpart agencies.

GoN is actively working on complimentary areas of GGN’s work and appreciates early engagement - as reflected in MoUD’s ownership of the programme. Otherwise, this risks a negative response. It is important to be proactively seek out counterpart agencies and key staff perspective early, to bring them along, contribute, and develop a mature partnership.

Given anticipated changeover in the government coalition next year, GGN needs to lead and work with OIBN and other key agencies to strengthen institutional relationships with staff at MoF and other relevant ministries, and in particular Joint Secretaries and Under-Secretaries. This is important for maintaining momentum and for safeguarding GGN’s strategic priorities amidst political transition.

A focused approach to human resource sustainability for OIBN will be necessary. This element of OIBN is crucial for impact. However, the incentive to fix this has thus far elapsed political priorities. Even with a legal framework in place and commitment from senior officials, this might delay owing to more incentives being tied in project development and approval mandates over institution building.

Unclear mandates under Federalism for GGN’s objectives make engagement at sub-national level tricky. There is overlapping mandates between the three tiers of government on infrastructure development, leading to inefficiencies and overtime a curtailed role of sub-national government.

The ODA commitments are still being worked out and it is still unclear how it will affect specific programmes and portfolios. It is important for the programme to plan for different scenarios to avoid shocks. GGN will need to be flexible and adaptable, and working as a portfolio programme helps.
Recommendations for the year ahead

Continue prioritisation of transformative economic green infrastructure projects - across GGN but specifically Component 2 – as well as addressing related policy bottlenecks. This should come in front of, but not exclusive of, broader green growth enabling environment support. GGN to set out a comprehensive approach to FCDO by start of August.

Partnerships are vital for the success of GGN outcomes. GGN to prioritise establishing meaningful partnerships where large sources of funds can be leveraged (ABD, World Bank, TDF, etc.), as a nimble TA programme. GGN to either influence at least two MDB operations, or have agreed and started implementing at least two partnerships within a year.

FCDO to support GGN outcomes. The FCDO team will need to foster greater collaboration and synergies among BEK and other Development Partner (DP) activities, given FCDOs role as a key DP. To happen immediately, and FCDO to coordinate at least monthly with GGN.

Transition GGN operation and administrative costs to a leaner size, reflecting reducing budgets. GGN to submit an options proposal to SRO by mid-July.

Prioritise and expedite work on OIBN sustainability: particularly operationalisation of hiring OIBN’s own staff and its independent funds. Everything should be in place to start implementing these by March 2026. Additionally, given the risk on multilateral financing materialising, GGN to take all necessary steps and provide clarity on multilateral commitments by October 2025.

Establish working relations with MOICS and DOI: To enable GGN to have a 360 overview and offer for FDI facilitation and approval systems. It will offer opportunities to solve the political economy (coordination) bottlenecks e.g. between MoICS and OIBN on investment approvals. GGN to do this immediately.

Have a strategic and coordinated approach to sub-national engagement: Leverage BEK’s sub-national initiatives, and align well with institutions like OIBN, TDF and NIFRA, as well as international partners such as ADB and the World Bank. Reframe the approach in the context of ODA reductions. All of this will ensure meaningful impact at the sub-national level. GGN and FCDO to clarify this by September 2025.

Better reflect ambition and ODA reductions in workplans, logframe and ToC. Revise these items reflecting two aspects: firstly, increase ambition in Components 2 and 3, given this was possibly too low in this years AR; and secondly due to ODA reductions. GGN to complete with FCDO by end-August 2025.

Make further improvements in programme management: As per Section F, and in summary; strengthen internal controls and protocols; improved efficiency in use and costing of staffing, particularly Short-term Technical Assistance (STTA); and strict compliance with GGN programme manuals. FCDO to explore qualitative Key Performance Indicators by July. GGN to implement these changes by October 2025.
## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

GGN’s ToC has focused on promoting green/sustainable development by increasing FDI flows to new green infrastructure projects, and supporting the government to adopt greener polices and provide significant improvements in environmental and social safeguards (primarily in OIBN). This is to be done through a combination of project development, institution strengthening (via capacity-building) and helping set up enabling policies and leveraging investments. The three components and overall programme approach are mutually reinforcing, and aim to have tangible impact on FDI flows towards new infrastructure projects which has been identified as a structural bottleneck to Nepali economy.

FDI is still a structural bottleneck and GGN is still set-up to have an impact on this, however the implications of ODA reductions still need to be further worked out, with potential implications for the ToC. The inception period did validate the existing ToC to date. Time will potentially be a challenge for GGN, with institutional strengthening, the development of infrastructure projects, and development of innovative financing instruments all requiring significant time. Additionally, the programme neatly brings together mutually reinforcing components and approaches, and therefore amendments will need to consider these dependencies.

After years of different programmes attempting to bring FDI enabling reform and strengthening the capacity of various institutions, the GoN has been proactive in pursuing necessary reforms (via two different set of ordinances which were later passed through the parliament). This shows increased commitment to attracting FDI and closing large infrastructure projects on paper. Despite this, it has not been able to demonstrate a step-change on both fronts. As such, GGN should keep as its primary aim the development of FDI ready projects. The programme should focus on a problem-driven iterative approach to generating impacts at the project (development and financing) level, and bring policy and institutions-building goals in to compliment this.

Similarly, from the point of view of the country context, the second component –Green Growth for Provinces and Cities – needs a closer look. At face value, the component is less concerned with attracting FDI which is the programmes primary aim. However, from a developmental perspective, the urban sector is the largest driver of growth and provisioning of urban infrastructure remains one of the binding constraints to continue this growth. The local governments have a high favourability in comparison to other institutions due to their positive contributions in local infrastructure and administering public services (education, and health among others). Inclusive growth in Nepal is more likely to emerge from the dynamism at the local level more than anywhere else (including through attracting FDI). This is a difficult tension within country context and programme priorities that should be addressed in case of any scaling down decisions.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

The programme appears on track to contribute to the expected outcomes and impact, based on ToC and progress highlighted during this review. However, it is too soon to say with certainty. Additionally, the impact of ODA reductions will require a revision of the programme ambition and potentially further re-prioritisation. So far, GGN has prioritised key elements of the programme and committed to expedite the mature and well-developed activities which have a high level of government counterpart commitment and ownership which can be completed in relatively shorter period.

For the year ahead, success would be a whole of programme approach to attracting green FDI, with Component 1 and 3 supporting Component 2 projects and financing, Component 3 developing a financial product and required reforms to make more finance available green infrastructure projects, and OIBN in place where it is ready on paper to stand on its own two feet. Failure would be a lack of buy-in to OIBN from Government and the MDBs, zero projects reaching maturity in Component 2, and a failure to move from intention to concrete steps in developing a financial product in Component 3.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

Based on the merits of the programme, GGN should continue. On the context of the wider Embassy portfolio, the programme will require a relook, and potentially a redesign if the programme needs to be scaled down from its three components and multi-pronged approach to attracting FDI and spurring urban growth through increased investment in green infrastructure.

## C. DETAILED OUTPUT SCORING

Output Title	National Green Growth (NGG)
Output number:		1	Output Score:	B
Impact weighting (%):		50%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1. Progress of green economic investment, including Public Private Partnerships (PPP) and industrial policies and guidelines (both new and amendments)	1.Review of investment regulations completed/ Identification of key issues in FDI and industrial policies (Stage 1) / 2. Paper on development and implementation of PPPs developed / 3.A draft report on policy ecosystem submitted.	Moderately did not meet expectations. B / A review of 8 investment related Acts related to investment climate was completed. The assessment report was useful and helped GGN identify possible areas of policy intervention, such as harmonising FDI approvals, structuring PPP project concessions and transactions, and capacity improvement. A paper on PPP project development and implementation was received. / The draft paper ‘PPP Delivery Structures – Key Issues and Considerations’, was delivered with minor delay, and is under review. / The policy ecosystem report is a work in progress, requiring significant rewrite.
2.Progress of green energy policies and guidelines against (both new and amendments)	1. Intervention ToR for Electricity Regulatory Commission (ERC) support finalised and work commenced. / 2. Intervention ToR for hydropower generation cost benchmarking finalised and commencement of work.	Met expectation. A / ToRs for ERC support and hydropower generation cost benchmarking were received. The ToRs were good. However, work could not commence by March end 2024 due to FCDO budget uncertainty.
3.Provincial green economic policies, laws and guidelines (Madesh, Lumbini, Karnali)	1. Provincial project bank work commenced	Not assessed - Put on hold due to budget reductions.
4.OIBN capacity development and OIBN Business Plan implementation	1. OIBN Business Plan developed (incl. implementation plan) / 2. Initial GGN staff support for OIBN mobilised / 3. Review of legislations and recommendations completed / 4. GGN's Staffing plan for OIBN project support & sustainability developed / 5. OIBN Transition Plan submitted. / 6. Capacity building plan for OIBN approved	Met expectations, although capacity building plan for OIBN still under review. A / OIBN's 5-year Strategic and Business Plan (SBP) was developed and submitted to OIBN on time. This SBP was approved from the OIBN board on 27 April 2025. / Six transitional thematic experts have been mobilized to support OIBN. However, the mobilization process took longer than anticipated. Additionally, support staff were not yet mobilised to work on the sustainability aspects of OIBN (beyond the Business Plan). / Review of legislation and recommendations was covered in the above assessment report of 8 investment related Acts. / Draft OIBN sustainability plan, including staffing and transition plans, and draft OIBN capacity development plans were developed. FCDO provided comments and feedback, awaiting final versions.
5. Ministries, departments and agencies (MDAs) collaborating effectively for green investments	1.Report on identification and engagement plan of MDAs (Ministries, departments and agencies) / 2.ERC initial support defined and initiated	Moderately did not meet expectations. B / A GGN-wide engagement plan was created instead. Deeper MDA engagement options still need to be explored. Moderately did not meet expectations. / ERC support plan was developed in consultations with ERC, sectoral experts and senior governance experts. Slight delay in initiating support over programme budget uncertainty in March 2024.
6.Provincial governments strengthened to deliver green investments	Capacity Needs Assessment designed	Moderately did not meet expectation. B / A ToR for subnational capacity needs assessment was submitted, but work on the design was not started. The delay is partially linked to budget uncertainty.
7.Progress of green infrastructure projects against the project maturity scale, including PPP projects and supported for implementation and monitoring of projects ensuring ESG.	Techno financial/commercial assessments for 2 projects submitted to OIBN (Stage 1)	Moderately did not meet expectations. B / A techno-financial assessment of the Birethanthi--Muktinath Cable Car project has been prepared and submitted to OIBN. This work has helped advance the project with the government’s intent to approve it. / While no detailed assessment was carried out for a second project, GGN did assess 19 projects at various maturity stages including West Seti hydropower project, ICT project, Risen Grid Solar Project, Agrivoltaics project, industrial parks, and fertilizer, and provided feedback to the OIBN and the respective project developers.

Briefly describe the output’s activities and provide supporting narrative for the score.
NGG component receives a score of “B” overall for its work and achievement last year, due to a mix of delays and strong ambition. The main priority last year, as GGN came out of inception in December, were: i) development of OIBN Business Plan and start of implementation, ii) providing embedded technical experts to work at IBN to progress project development, iii) starting technical support to the ERC, and iv) review and analyses of relevant policies and laws to inform prioritisation and implementation. NGG achieved most of its annual milestones, but resulted in only moderately not meeting expectations. Where milestones were not fully met, this was mostly due to: ODA budget uncertainty, GGN slow inception period and time to align expectations with Government.

GGN played an important role in assisting OIBN with the development of its Strategic and Business Plan (SBP), which received approval from the OIBN board on 27 April 2025. This comprehensive plan outlines OIBN’s organizational and management frameworks, including a revised organogram, a human resource (HR) staffing plan, financial and budget projections, core service definitions such as investment promotion, public-private partnerships (PPP), and investor support, as well as a detailed delivery plan. Additionally, the GGN team formulated OIBN’s workplan, detailing activity-specific budgets and key performance indicators (KPIs) for all organizational units.

During the SBP development, a misalignment arose between OIBN's expectations and GGN's deliverables. GGN addressed this by changing the component lead for OIBN, enhancing communication, and accelerating the finalization of the SBP. As a sign of OIBN’s growing credibility, supported by GGN, the CEO’s designation was recently elevated to that of the level of a Minister.

GGN mobilized six transitional support staff, including four cross-cutting specialists (Environmental, Safeguards and Community Engagement, Economist, and Financial), a Legal and Institutional Development Specialist, and a One Stop Service Centre (OSSC) Specialist. These specialists are supporting OIBN in evaluating 19 projects within its pipeline, offering feedback for project development enhancement. The Legal and Institutional Development Specialist ensures project compliance with legal standards, while the OSSC Specialist is developing Standard Operating Procedures (SOPs) and strengthening the OSSC at OIBN.

GGN also provided a short-term high-level cable car expert to assess the Detailed Project Report (DPR) of the Birethanthi-Muktinath cable car project. The expert, along with cross-cutting specialists, produced a techno-financial assessment report, which OIBN and the developer found valuable and have begun implementing. The OIBN approved the cable car investment recently, June 2025. There were delays in mobilizing these specialists due to a lengthy recruitment process which GGN is working to expedite future hires.

GGN has also drafted the OIBN sustainability plan, including staffing and transition plans, and capacity development plans, aiming to ensure OIBN can effectively manage its mandates in the next few years. The amended PPP and Investment Act (PPPIA) empowers OIBN to hire its own staff, as well as external staff at market rates. GGN is providing transitional support until OIBN's experts are operational.

NGG also developed ToRs for support to ERC in 3 areas: institutional strengthening (as a still new agency) around institutionalisation of mechanisms to improve coordination with the Ministry of Energy and Water Resources and Irrigation (MoEWRI), NEA, and SEBON; generation of evidence on cost of hydro generation; and two consultants to help with digitisation, policy influencing and technical support. Two GGN staff have started at the ERC, as of April end 2025.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
The planned reduction of the FCDO ODA budget has impacted GGN planned support to the OIBN. Considering this budgetary constraint, GGN will prioritize the institutional sustainability of OIBN, focusing on both human resources sustainability and the OIBN fund sustainability. Additionally, GGN will focus its support on green projects within the project pipeline that are at a higher maturity scale. Consequently, GGN will reduce support for investment promotion and projects that are at a lower maturity scale. ERC work will continue given the importance of the energy sector and the role of the regulator. Green policy work will continue in an opportunistic way, and mostly driven by project policy issues. Provincial work has had to be largely paused, with the remainder tied to project policy issues, and the rolling out of PPPs.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Progress on recommendations:

Recommendation	Progress
1. [GGN programme wide] Collaboration: there are many areas of potential collaboration for GGN with other development partners and external organisations (multilaterals, business groups. i.e. National Investment Policy) as well as across BEK and UK funded regional programmes.	Ongoing. Leveraging on GGN’s support envelope, OIBN and cities component have reached out to multilateral agencies (WB, ADB) for garnering complementary support. See Green Cities Component for additional detail. Within BEK, GGN has also discussed potential collaboration with the Local Infrastructure Support Programme (LISP), Resilience, Adaptation, and Inclusion in Nepal (RAIN), and Nepal In Business (NIB).
2. [GGN programme wide] Research and adaptive programming: to make the most of all the research agendas in BEK, the SRO and Supplier will need to establish an engagement mechanism to ensure that latest evidence and knowledge feeds into implementation and is coherent with BEK’s new evidence programme, EDIT. / SRO to determine most suitable approach, including the next phase of SOAS work [by December 2025]	Ongoing. SRO is working with the BEK Governance Adviser and GGN to explore a potential deeper partnership. Several workshops have taken place amongst BEKs research partners and GGN has taken up learnings from previous programmes as well as part of inception, for example what constitutes a green project, and approaches institution building. A mechanism is being explored but delayed due to ODA reduction uncertainty.
3. [GGN programme wide] Government engagement: strong and regular engagement with Government of Nepal (GoN), in addition to GGN Steering Committee, across all relevant agencies/Ministries for successful GGN implementation.	Ongoing. GGN and BEK team has been engaging with the relevant GoN bodies, as noted in the AR. GGN has an engagement plan.

Lessons:
- Building on existing work or of predecessor programme: APPIIC had developed several key documents, including SOPs, an O&M survey, draft OSSC guidelines, a roadmap for VGF, and operations fund mobilization guidelines. However, most of these documents have not been approved by the relevant authority and therefore have not been implemented. Similarly, other development partners, such as the UNDP, EU, USAID have supported the OIBN and other government institutions in developing documents and guidelines to enhance the investment environment in Nepal.
- Continuous engagement and ensuring GGN deliverables address stakeholder expectations: Understanding beneficiary/client expectations is crucial when engaging with government agencies. GGN encountered challenges during OIBN’s SBP preparation due to misaligned expectations but addressed them by replacing the component lead, improving communication and accelerating the drafting process.
- Greater integration between the government OIBN staff and GGN consultants: improved working relationship and integration between GGN consultants and seconded civil servants at OIBN is essential for timely issue resolution, enhanced policy implementation, and sustainable long-term outcomes. Presently, integration challenges persist.
- Energy sector: There is much that needs to be done in the energy sector, including influencing for the passage of the Electricity Bill to capacity enhancement of the relative new ERC. With the closure of USAID and now likely pull out of MCC support, there is a major gap in support.
- Importance of buy-in across Government: For OIBN to succeed the wider institutional ecosystem needs to function as well. MoF is key for financially empowering OIBN to operate effectively. Ministry of Industry is crucial as the approver of foreign investment, and has an existing OSSC. Other Line Ministries and Sub-national governments are key clients of OIBNs that it needs to support and be seen of value.

Recommendations:
- GGN to maximise leveraging existing resources and developments under the APPIIC programme rather than initiating new processes, focusing instead on finalizing and securing approval for timely and effective implementation. On-going.
- GGN to work more closely with OIBN and have a clear engagement plan for MDAs to enhance the overall investment environment (by end-July 2025). Additionally, GGN should obtain consent from the respective ministries on the guidelines and SOPs being developed for OIBN, while also prioritizing capacity building of ministry representatives nominated to OIBN’s OSSC to strengthen inter-agency coordination and improve investment-related service delivery.
- GGN to support OIBN in preparing necessary documents, advancing the recruitment process, and advocating MoF increase OIBN’s budget. GGN and OIBN to also work jointly on setting a renumeration package that is on market rates/attractive to get the right skills and experience. By March 2026.
- GGN to proactively foster collaboration by encouraging transitional support staff to engage constructively with their civil service counterparts to improve working relationship. Additionally, organizing joint meetings and events will help build mutual understanding, strengthen rapport, and promote a cohesive working relationship conducive to achieving shared objectives. Immediately revisit the delivery model.
- GGN to provide an options paper to FCDO on TA and transitional support staff options for OIBN, and other MDAs, given ODA reductions and providing a suitable balance of resources. By mid-July 2025.

Output Title	Green Growth for Provinces and Cities (GGPC)
Output number:		2	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
Progress of policies, regulations, plans related to urban development developed/amended for federal government, provincial governments, cities against the policy maturity scale	Assessment of federal level urban sector policies initiated	Met expectations. A / Review of National Urban Development Strategy 2017, Town Development Fund (TDF) Business Plan 2025, Town Development Fund Act 1996, and Nepal Infrastructure Bank (NIFRA) Prospectus have been initiated. / Brief note prepared on Green Growth for cities and shared with GoN.
	Approach note for city cluster endorsed by the urban thematic committee	Met expectations. A / Approach note on city clusters endorsed by Urban Thematic Committee at Ministry of Urban Development.
No of cities & city cluster with improved economic management (project planning and financing	Capacity assessment methodology outline developed / Integrated Solid Waste Management (Madhesh) and Lumbini Capital City Master Plan – LPCC - (Lumbini) shortlisted as potential projects for cluster mechanism.	Met expectations. A / Capacity assessment currently paused (to review priority activities going forward) / Projects shortlisted. UK Centre of Expertise (Green Cities, Infrastructure and Energy Programme - GCIEP) – has approved funding for the Lumbini Review. GGN ToR for Madhesh not yet approved.
Climate Smart infrastructure project mechanisms (clustering & partnerships)	Review of cluster mechanisms initiated	Met expectations. A / Cluster mechanism approach note developed. It was recently approved on 6th May (after this AR reporting period). The ToR for rolling out cluster mechanism was developed with delay.
Progress of Climate smart aligned project pipeline development against the project maturity scale	Review of long list of potential projects initiated.	Moderately did not meet expectations. B / ToR only approved and initiated in May 2025. Lost list from GCEIP study in 2023 was reviewed during the inception period and is now short-listed to 7 projects as part of the GGN ToR to start reviewing.

Briefly describe the output’s activities and provide supporting narrative for the score.
The overall output score of “A” is validated for this output as most targets were achieved. Several positive developments have been achieved. Key foundational elements, such as the planning and design of sub-outputs and the drafting of ToRs, have been successfully completed. Notably, a joint GGN and BEK field visit to all the three provinces and select municipalities happened in November 2024 and the first meeting of the Thematic Urban Committee at the Ministry of Urban Development endorsed both the approach note on the cities cluster strategy and a brief note on green growth for cities, marking significant milestones. The recent government budget has also seen MoUD approval to allocate some finance towards GGN-linked activities: demonstrating significant buy-in. Additional resources from Green Cities, Infrastructure and Energy Programme (UK’s Centre of Expertise) has been mobilized to support urban work in Lumbini Province. Despite the challenges of FCDO’s resource uncertainty, the output remains on track overall.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
Due to the need to prioritise and ensure maximum value for money and limited alignment to UK International Climate Finance (ICF) eligibility, provincial capacity self-assessment has been deprioritised and paused. Additionally, the scope of review of investment projects, including Lumbini Province Capital city Master Plan and Birendranagar municipal land pooling project, has been reduced.

Progress on recommendations from the previous AR, lessons learned this year and recommendations for the year ahead.

Progress on recommendations:

Recommendation	Progress
1. Coordinate and develop BEK’s urban strategy and approach.	Ongoing. Draft BEK urban strategy was discussed in economic development team in September last year. Since urban is an evolving area in Nepal, it requires regular review and reiteration to remain relevant and responsive to changing urban dynamics and FCDO’s strategic priorities.
2.GGN team will need to align with the Palika selection framework being developed in BEK	Completed. GGN’s City cluster approach note used BEK’s Palika selection criteria and framework.
3. GGN to ensure consistency on GGN’s clustering approach with BEK’s Palika selection approach and develop a robust approach to cluster local governments around investments as agreed in the GGN steering committee.	Completed. GGN has developed a City Cluster Approach Note, drawing on key insights from BEK’s intervention projects -notably the Local Infrastructure Support Programme and Palika prioritisation framework. This city cluster approach note has received formal endorsement from the Urban Thematic Group under the Ministry of Urban Development (MOUD), the lead governmental body represented in the GGN Steering Committee. This endorsement reinforces the alignment of the approach with Nepal's urban development priorities and strengthens its potential for scalable implementation.

 The lessons learned in the past year and recommendations for the year ahead:

Lesson: (i) Due to ODA reductions, as well as the BEK Urban Feasibility Study that highlighted a lack of mature bankable projects at sub-national level, the Cities component will significantly scale back our ambition for project development at this level. We will work to develop just a few promising projects, particularly those where the majority of funding is secured from public sources or Multilateral Development Banks. (ii) Clarification on what constitutes “urban system” is required as GGN progresses. Recent Nepal Urban Policy (2024) increasingly emphasizes the importance of urban systems. However, this systems-based approach is not yet fully understood or consistently applied across the three spheres of government. "Urban systems" can easily be confused with "city clusters", especially in policy discussions where terminology isn't always clearly defined.

Recommendations:
- GGN urban component needs to prioritize building strong partnerships and collaborations with like-minded organizations such as the ABD and WB to enhance technical support, policy alignment, and for financing potential infrastructure projects. There is a strong MDB urban development presence which GGN needs to explicitly reinforce. Additionally, GGN will also need to explore project financing partnerships with institutions like the TDF and Nepal Infrastructure Bank (NIFRA) to ensure long-term sustainability and scalability. These partnerships can unlock critical funding for green infrastructure projects. GGN to update FCDO monthly, and carry out a deep dive on partnership after the 7 PINs are completed.
- GGN urban component to continue its primary focus on transformative green and urban infrastructure projects, and related urban policy bottlenecks. GGN to immediately test this with FCDO.

Output Title	Financial Sector Deepening (FSD)
Output number:		3	Output Score:	A
Impact weighting (%):		25%	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.Progress of key steps in the development of green finance policies, instruments and partnerships	1. ToR for one green instrument developed with identification of target institution / 2. Initial scoping to ascertain feasibility has been completed	Moderately exceeded expectations. A+ / 1. ToR of good quality approved, and additional progress made: ToR for stakeholder engagement and ecosystem mapping for options assessment in fund creation and Green Bond issuance, with NMB Bank Ltd. as the key institution. A memorandum of understanding (MoU) will be signed based on the mandate letter provided by NMB Bank. Additionally, NMB Bank committed the initial tranche of USD 40-50 million / 2. An initial scoping to ascertain the feasibility of proposed interventions was completed which included wide stakeholder consultations resulting good potential partnerships. / Additionally, a potential partnership with Nepal Electricity Authority (NEA) on transaction advisory is at a mature stage.
2.Progress of efforts to operationalise derisking policies, partnerships and instruments against defined milestone criteria	1. ToR for two de-risking instruments have been developed and submitted to the FCDO / 2. Partnership discussions for operationalization of instruments have initiated	Met expectation. A / 1.ToR on developing i) credit guarantee mechanism, and ii) currency risk hedging solution aimed at reducing investment risk in Nepal’s infrastructure sector were developed and submitted. The ToRs of good quality covering the main areas and identifying next steps to advance this work. / 2. Discussions on forming partnership for the operationalisation were initiated with national stakeholders, MoF, Public Debt Management Office (PDMO), NRB, and commercial banks, as well as international partners like The Currency Exchange Fund (TCX), the NORAD Credit Guarantee scheme, and others.
3.Progress in banking sector policies and institutional partnerships for green project financing against defined milestone criteria	1. Stakeholders have been identified / 2. A partnership has been established for one intervention aimed at greening the banking sector / 3. Demand assessment of interest from collaborators	Met expectation. A / 1. Stakeholders including Invest for Impact Nepal (IIN), Nepal Bankers Association (NBA), and the International Finance Corporation (IFC) were identified. / 2. Partnership with National Banking Association (NBA) was discussed and agreed but a MoU was not signed because this work was paused due ODA reductions. / 3. Demand assessment for IIN, NBA and IFC was done to ascertain interest, and identify synergies, and plan collaboration.
4.Progress of capital markets policies institutional mechanisms for issuance of green instruments against defined milestone criteria	1. ToR for policy and institutional intervention have been developed and submitted to the FCDO / 2. Initial discussions with SEBON and NEPSE have been initiated	Met expectation. A / 1. A holistic ToR for scoping initial engagement for capital market development was developed and submitted. It focused on strengthening the bond market through assessment of regulatory frameworks, engagement with key stakeholders for identification of areas of strengthening market capacity. / 2. Policy and institutional intervention have been identified, and initial discussions with SEBON and NEPSE were initiated to strengthen domestic capital markets for issuance of green instruments.

Briefly describe the output’s activities and provide supporting narrative for the score.
FSD scores an “A” overall for the good progress made against the output milestones for the year, fully achieving 8 deliverables while 1 was put on hold because of budget uncertainty, although significant progress had been made. Work on establishing a dedicated debt fund and green bonds in collaboration with NMB Bank Ltd. has made notable progress with NMB Bank committing the initial tranche of USD 40-50 million. Engagement with NEA was at an advanced stage, but delayed to appointment of a new CEO.

Describe any changes to this output during the past year, and any planned changes as a result of this review.
This year inception and implementation started. At the moment as the outer year budget is uncertain due to ODA budget reduction, FSD (and GGN). Greening of the financial sector, and policy work on foreign currency hedging legislation have been paused for now.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead.

Progress on recommendations:
Recommendation	Progress
1.Collaboration across other FCDO programmes and other development partners: there are many areas of potential collaboration for FSD with other development partners and external organisations.	Ongoing. GGN is collaborating with IFC on domestic bond market development. It is working with NMB Bank on creation of fund for green financing. In addition, GGN is also engaging with bilateral donors such as the Swiss Agency for Development and Cooperation (SDC), KfW, and the Norwegian Embassy for project preparation facilities.
2. British Investment Partnerships (BIPs) are central to increase scale and impact across GGN across all components. / The Supplier will set out a BIPs engagement plan and allocate resource for implementing the most promising partnerships. [Inception phase]	Partially met. No plan exists, however FSD component has been very strongly engaging with various BIPs since the beginning, including British International Investment (BII), Private Investment Development Group (PIDG) and GuarantCo on potential collaboration on guarantees for green project financing.
3. Government engagement: strong and regular engagement with Government of Nepal (GoN), in addition to GGN Steering Committee, across all relevant agencies/Ministries for successful GGN implementation. / GGN may need some additional layers of regular government coordination e.g. for finance stakeholders [Inception phase to propose options]	Ongoing. GGN and BEK team has been engaging with the Ministry of Finance (MoF), SEBON, Nepal Banking Association (NBA). / FSD component has been in discussion with the Financial Sector division at MoF for a financial sector working group.

Lessons Learned:
Buy in of key government institutions: A key lesson this year is the importance of early engagement and buy in of anchor government institutions like PDMO and NRB. Their involvement is essential not only for ownership but also for anchoring regulatory changes and policy reforms needed for financial innovations.
- Capacity gap on technical aspects: Given the early stage of the financial sector in Nepal and the technical nature, there is a significant capacity gap around the various financial innovations (e.g, foreign currency hedging, guarantees, green bonds) that FSD is working on.
- Concessional financing is crucial given high interest rates around major economies: Successful de-risking instruments require a combination of market demand, regulatory preparedness, and concessional finance backing to lower transaction costs and increase uptake. Currently, US treasury yields (interest rate) are high and adding transactions costs and other fees make the transactions commercially unviable vs. domestic interest rate.
- Challenges of limitations of TA alone to mobilise finance, and the importance of partnership to overcome this: Mobilising finance is very challenging in Nepal, more so just with TA. Thus, partnership with development finance institutions (DFIs) and financial institutions is necessary, and is a key risk to GGNs ToC.
Recommendations:
- Continue early and regular engagements withy anchor government institutions in the financial sector so that there is ownership and support for FSD’s various interventions. On-going.
- Incorporate building awareness and capacity-building into the design of innovative financial instrument interventions, given strong need for these. GGN to do immediately.
- GGN to develop a more systematic approach to partnership with an increased focus on partnerships building activities, given their criticality of a TA programme like GGN in mobilising finance. Specifically, on derisking instruments, a multi-pronged approach (creating market demand, regulatory preparedness, and concessional finance) is necessary to make progress. Immediate, and GGN to share a renewed approach with FCDO by end-July 2025.
## D: VALUE FOR MONEY

GGN is a TA programme therefore the main costs are experts, consultants, and GGN delivery team, as well as some programmatic costs such as the office and flights. Cost drivers are related to availability of expertise, domestic inflation, and global conditions affecting flights.

Economy
GGN has sought to bring a balanced delivery team with a mix of international and local experts, as well as experienced and more junior staff, and short and longer-term staff. International staff (including short term) days is 26% of total days charged in the period. While this breakdown is consistent with the overall days for 5-year period, given this year included the inception period the use of international staff could be considered above average (916 days international compared to 2,579 days of local staff). More involvement of international staff would be expected when the programme is in full delivery mode.

GGN has also utilised more experienced staff day rates than expected. This partially reflects the upfront effort required in reform and drafting, as well as high stakeholder expectations, and positively a window of real reform with OIBN. Going forward this will be more balanced. GGN is to revisit the longer-term model of TA to provide a better solution that continues to deliver quality with greater consideration of input costs.

To reduce costs administratively, framework purchase agreements with repeat suppliers such as hotels, travel agents, office supplies, cleaning services, and car hire services have been set up.

Efficiency
Of the total staff and external consultant fees, 80% is on frontline delivery, including programme leadership, and 13% on programme management, and 6% on admin and programme support (see table below). Overall programme costs are on the higher side due to two key reasons: first, GGN is a complex TA programme with very limited logistics aspects (reducing frontline delivery); and second, GGN predominantly operates out of Kathmandu raising fixed costs. In the changing context of reduced ODA, GGN will look for ways to reduce overall management cost and drive VfM.

Cost Category	Share of total Staff Cost
Programme Leadership	3%
Programme Management	13%
Programme support and Administration (Admin)	6%
Technical Expert (Frontline Delivery)	77%

In addition to the core programme staff, GGN also draws on STTA when more specific or additional expertise is needed. GGN has utilised a blended approach when it comes to frontline delivery of activities, to utilise the strengths of the core team while complementing them with targeted technical inputs. FCDO should better understand how such decisions are taken.

Effectiveness
GGN has prioritized interventions that are aligned with the country’s priorities and ToC. The agreed logframe reflects the objectives of the GGN programme. Performance-based funding has been adopted to incentivise progress and clarify accountability, maintaining that resources are deployed judiciously and fostering a cost-effective and result-oriented project implementation. Various social, economic, and environmental impact assessment tools have been used to carry out impact assessments of interventions.

Equity
GGN has maintained gender and ethnic diversity during the selection of consultants where possible. The core team has a good gender mix and diversity, with a strong presence of women in both leadership positions (e.g., the provincial engagement lead and programme manager) and in supporting positions, with a higher proportion of women in the component technical support teams. A GEDSI internal ToR has been approved by FCDO and is being implemented to ensure high standards.

GEDSI has been embedded as one of the qualitative parameters to be assessed for every intervention that GGN implements. A safeguards and community engagement specialist has been placed at OIBN to undertake social impact assessment, analyse the social and political risks of proposed projects and prepare resettlement action plans and community development plan. On the Muktinath Cable Car Project, a thorough, social safeguards and socio-economic analysis was conducted to help the project be socially responsible.

Assessment of whether the programme continues to represent value for money
GGN should continue—it is a flagship FCDO programme working to support green and sustainable growth in Nepal, by improving investment climate for green growth and infrastructure projects, urban development, and deepening of the financial sector. It is therefore well aligned to BEK and FCDO outcomes, as well as the priorities of the government of Nepal.

GGN came out of its inception phase at the end of December and entered implementation. Over that period, GGN has made good progress on identification of key priorities and developed work plans, all while factoring in an uncertain ODA future. While there are areas where economy and efficiency could be improved (e.g., better use of core staff on delivery, and greater balance of levels of expertise in frontline delivery), overall GGN is likely to represent good VFM. It is too early to say with certainty at this stage given there has only been 3 months of implementation.

E: RISK

Overview of risk management
GGN has overall risk rating of Major, within the "Receptive" overall FCDO risk appetite. The programme team and the partner regularly review, discuss and update the programme risks.

Strategy & Context: There is a risk that weak government coordination, unclear institutional roles, political instability, and frequent turnover of officials may disrupt GGN implementation and increase the likelihood of political capture, especially in the absence of a municipal clustering mechanism.
To address this, GGN regularly updates its Political Economy Analysis (PEA), design interventions with clearly identified government counterparts, and maintain strong networks to manage turnover and identify reform champions. Ongoing engagement with officials and collaboration with key agencies such as MoF, NRB, OIBN, and MoUD will help ensure alignment and continuity. There is also a strong assumption around MDB financing of OIBN, that may impact OIBN’s transition to a sustainable organisation. We are engaging the MDBs to mitigate this.

Financial & fiduciary: Weak financial systems, slow programme delivery, and limited internal controls within the Government of Nepal may lead to financial mismanagement, underspending, and reduced accountability of UK funds. FCDO has decided to pause Financial Assistance (FA) in the wake of ODA reductions and uncertainty. For GGN, these risks are managed through Fiduciary Risk Assessments (if the decision is for FA to go ahead), implementing Financial Management Improvement Plans, and ensuring that fund disbursements are made on an actuals basis following approval of financial monitoring reports. Oversight will be reinforced through intervention trackers, monthly forecasts, spot checks, and annual independent audits.

Programme Policy and Delivery: Limited technical capacity within GoN institutions and the implementing partner, along with shifting FCDO priorities and budgets may hinder effective delivery and achievement of programme objectives. GGN will respond to this challenge by strengthening counterpart capacity through targeted interventions, coordinating with development partners, and ensuring quality through continuous monitoring and consultant vetting. Clear communication and adaptive management, including annual logframe updates, will help align expectations and maintain delivery momentum.

Public Service Delivery and Operations: Delays in procurement and government approvals may disrupt timely implementation of GGN, creating delivery gaps and limiting the ability of government counterparts to engage effectively. Over-reliance on international expertise may also reduce value-for-money and limit sustainability. GGN will manage this risk by securing timely approvals, maintaining regular communication with government counterparts, and preparing contingency plans to address delivery disruptions. Value-for-money will be embedded in ToRs and budgets, with a focus on prioritising national expertise to strengthen local ownership and long-term impact.

People: Inadequate staffing or advisory capacity within the BEK and GGN teams may hinder effective delivery, particularly given the complexity of large-scale investment projects. To reduce this risk, GGN will embed a specialist advisory role to monitor and manage investment-related risks, conduct regular field visits for oversight, and leverage the consortium’s broad technical expertise. The STTA pool will be maintained and expanded as needed, and all ToRs and personnel will be carefully reviewed to ensure suitability for the programme’s needs.

Reputational: There is a risk that relationships with key government counterparts—such as the Ministry of Finance, provincial and city governments, and OIBN—may deteriorate due to perceived poor delivery or lack of responsiveness, potentially damaging the programme’s credibility and future influence. GGN will safeguard against this through proactive and consistent engagement by the SRO and advisers to maintain transparency and alignment with expectations. If issues escalate, the SRO will raise them with the Senior Leadership Team (SLT) for timely resolution and strategic intervention.

Safeguarding: among project staff, as well as potential adverse environmental, social, or economic impacts from infrastructure projects. GGN will address this risk by ensuring the BEK team monitors safeguarding policies and reporting mechanisms of implementing partners, and by delivering induction sessions to all staff. Environmental and social safeguards will be integrated into project agreements, with regular monitoring to ensure compliance and uphold ethical standards across all activities.

Update on Partnership Principles
A Financial Aid budget of £1.74 million has been allocated under the GGN contract to support OIBN and clusters of city governments in growth corridors. No FA expenditure has been recorded during this reporting period, and FCDO has taken the decision to pause any FA for the time being.

A MoU was signed between the FCDO and the Government of Nepal (GoN) on 20 February 2024, outlining the principles of the partnership.

In November 2024, BEK updated its Partnership Principles Assessment. The assessment concluded that Nepal demonstrated a “medium commitment” across all four thematic areas of the Partnership Principles. This reflects a stable trajectory, with some areas showing improvement and others presenting increasing risks that require close monitoring. Notably, improvements have been observed in domestic accountability and the management of fiduciary risk. This marks a positive shift from previous years, where a medium commitment with stable progress was noted across all principles. The stable trajectory in domestic accountability is attributed to the peaceful and orderly completion of the first electoral cycle at the local, provincial, and federal levels, as well as recent by-elections. The emergence of new political actors presents both opportunities and risks for democratic strengthening, though it is not currently seen as a significant threat to the overall trajectory.

Fiduciary performance has improved across all levels of the GoN, as evidenced by internal Fiduciary Risk Assessments (FRAs) and the latest Public Expenditure and Financial Accountability (PEFA) assessment. These findings suggest that fiduciary risks are now better managed. However, significant risks remain in public sector effectiveness and service delivery, which must be closely monitored for their impact on VfM.

Progress has also been consistent in other areas of the Partnership Principles. Human rights continue to improve gradually, particularly in the planning, enactment, and implementation of legal frameworks. Despite positive developments—such as the adoption of the Citizenship Bill and the Transitional Justice (TJ) Act—implementation challenges persist. These include the appointment of individuals to the TJ commissions who inspire public confidence in the process. A widespread and credible perception remains that the Federal Government’s commitment to human rights is politically driven and uneven across population groups, as reflected in the TJ process. Similar concerns are now emerging in relation to proposed digital governance legislation, where political and cultural considerations appear to outweigh sound legal principles.

The British Embassy Kathmandu will continue to assess and monitor performance against the Partnership Principles through its ODA portfolio and strategic risk registers.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE
To ensure better VfM and maximize complementarity and cohesion between components, the three components NGG, GGC and FSD were combined into a single contract. Though GGN was approved as a seven-year programme, with a total budget of £38 million, the initial contract is for 5 years, with the contract value of up to £22,490,382. PricewaterhouseCoopers LLP (PwC) - in partnership with Triple Line - was selected through a competitive bidding process under the GDD framework.
Total actual spent of GGN for this reporting period as follows:
Components	Spent (GBP) as of March 2025
Green Growth Nepal	1,337,670.11
MEL	193,548.97
Insourced Role	21,794.66
Total	1,553,013.74

GGN’s implementation commenced in July 2024. The inception phase concluded on 22 December 2024, with the implementation phase beginning shortly thereafter. There was a contract amendment after the inception phase to reflect to reflect minor changes to team structure and use of expertise and move to implementation. The AR assesses the programme’s commercial and financial performance from 22 July 2024 to 31 March 2025.
While there were some initial delays in meeting deadlines for deliverables e.g. invoices and forecasts, these were largely due to early-stage onboarding staffing challenges. It affected the timely setup of internal systems and project management tools. Despite these hurdles, the team has shown strong commitment and adaptability. Progress has steadily improved as the team structure has solidified, and efforts are now underway to streamline internal processes and strengthen project coordination.
The lack of an overall workplan early on made it hard to track overall portfolio progress and alignment both the logframe, and budget. This has now been resolved.
The current approach to STTA recruitment could benefit from a more strategic and portfolio-based perspective to better align with programme needs and ensure efficient use of resources – balancing across all areas of work demand. While the programme is still in its early stages, a notable portion of expert-category STTA days has already been utilized. This is explained in the VfM section (above), and has now been resolved with a stricter process for use of senior experts.
GGN took time to shift flight purchases to a local vendor, but this has been resolved. Exploring more cost-effective office space could help further optimize operational expenses. It's encouraging to see GGN’s proactive approach to improve cost efficiency. GGN has faced longer delays than expected in consistently applying standard financial management practices, such as using petty cash for local procurements instead of bank transfers. Encouragingly, GGN has committed to resolving the remaining cases, and work is already underway, including the finalisation of Local Transfer Agreements (LTAs).
FCDO conducted two spot checks this year. The first identified areas for improvement, while the second showed clear progress, particularly in asset tracking and procurement awareness. Recommendations have been shared separately.
The total forecast for the reporting period from July 2024 to March 2025 was £1,382,660.36, while actual spending amounted to £1,337,670.11—resulting in only a small variance of approximately 3% under budget. Submitting forecasts closer to the end of each financial quarter played a role in improving accuracy. More precise forecasting and clearer intervention planning could have further minimized this.
ICF reporting was not carried out this year, given there was only three months of implementation, and it is too early to report results. This will take place as part of the next AR.
Overall, while the GGN project reflects a positive intent to meet FCDO expectations, some further alignment is needed to fully comply with updated standards.
The table below provides a breakdown of the actual spend against the forecast for the reporting period.

Budget Category	Forecast 2024/25	Actual Spent 2024/25	Spend vs. forecast	Justifications
Programme Staff Cost (including NPAC and Profit)	£1,206,002.28	£1,183,146.76	98%	Minor underspend, due to programme and staffing delays, and lower intervention budgets that originally proposed.
Capital expenditure	£20,044.05	£27,293.86	136%	Temporary budget overage due to earlier furniture purchases than planned. The overall budget remains within limits.
Programme Activities	£63,545.03	£53,456.20	84%	Most of the planned interventions was significantly delayed. As a result, certain activities, such as consultation meetings, workshops, and training sessions weren’t carried out as planned. Provincial offices were also not set up as originally intended.
Travel	£40,300.00	£24,850.06	62%	Underspend to the reduced implementation of programme activities resulting in less travel.
Accommodation	£39,780.00	£33,530.23	84%	Underspend linked to travel, and reduced amount of international experts.
Subsistence	£12,989.00	£15,395.00	119%	Similar to the above, but resulted in a slight overspend due to workshops that should’ve been planned for.
Total	£1,382,660.36	£1,337,672	97%

Date of last narrative financial report	March 2025	Date of last audited annual statement	To be carried out after a full year of activity, as per good practice

Recommendations for the year ahead
- GGN is encouraged to develop and submit a revised, detailed implementation workplan and budget for FY 2025/26, fully aligned with the programme’s logframe outputs by end-July. This will support more effective progress tracking and ensure coherence between planned activities and financial allocations. FCDO to support, particularly on handling ODA reduction uncertainty.
- GGN to immediately finalise the transition to standard financial procedures—such as direct bank transfers—will strengthen internal controls, documentation, and adherence to financial protocols remains a priority.
- GGN can benefit from setting up LTAs with frequently used vendors, such as travel agencies and hotels, to streamline procurement and reduce reliance on PwC India. This is to be finalised immediately. Travel costs must be monitored on an on-going basis to ensure they remain within approved unit rates.
- More experienced STTA to be used sparingly, with clear justification, and combined with greater use of lower band (but still highly effective) STTA to greater benefit. Emphasizing VfM through competitive selection and rate benchmarking is essential. Internal resources should be considered first to reduce costs and build long-term capacity. GGN to implement immediately, and present a plan to FCDO for areas such as OIBN transitional support (see Component 1).
- Ensure strict compliance with the established operations manual, financial manual, and programme manual. On-going.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Progress Tracking
GGN holds weekly team-wide meetings that serve as a key monitoring mechanism. These meetings are instrumental not only in tracking progress against logframe milestones but also in identifying opportunities for collaboration and addressing emerging challenges. Additionally, GGN has been consistently updating the context tracker on a monthly basis. This tool helps monitor the evolving context, shifts in stakeholder needs and interests, and their implications for GGN’s strategic direction. BEK advisers regularly engage with GGN component leads through scheduled catch-up meetings to monitor the progress of each component. In addition to these individual check-ins, a consolidated monthly progress update meeting is held with the entire BEK GGN team, covering all components of the GGN project, as well as separate monthly BEK-GGN programme management meetings.

Learning and Reflection Mechanisms
GGN has institutionalized monthly ‘pause and reflect’ sessions involving both GGN team members and embedded staff within OIBN. These sessions provide a platform to engage with learning agenda questions, such as:
- Integration of climate and GEDSI (Gender Equality, Disability, and Social Inclusion) lenses,
- Strengthening collaboration across components and with external stakeholders,
- Adaptation and course correction,
- Capacity transfer strategies and future planning,
- Value for Money.
Collaboration, Learning, and Adaptation (CLA) Approach
GGN’s CLA approach goes beyond tracking outputs. It emphasizes learning from implementation experiences to inform evidence-based decision-making. Learning agenda themes such as collaboration, adaptation, and value for money are regularly explored. For example, insights from OIBN have been used to systematize communication and feedback loops with clients, enhancing responsiveness to evolving priorities and strengthening relationships.

Fostering a Learning Culture
To promote a learning organization, GGN has initiated brown bag sessions and thematic talk programmes. These cover diverse topics relevant to GGN’s work. GGN is also engaging in internal discourse on defining what constitutes “green” and is developing a concept note on the subject. It has reached out to stakeholders such as ADB, TDF, and the Climate Finance Accelerator for cross-learning and knowledge exchange.

GGN also plans to develop learning products, through the learning and takeaways generated from OIBN work, and other pertinent works so that these can be shared with wider audience. While concept notes for several research themes have been developed, these activities are currently on hold due to resource constraints.

Monitoring Capacity Transfer through Embedded Staff
GGN is capacity transfer to OIBN through its embedded staff, promoting peer-learning processes, as well as on the job training and mentoring as mechanisms for capacity transfer. GGN has also planned learning sessions in the form of brown bags and talk programs in pertinent thematic areas that are relevant for OIBN. It will intensify learning initiatives and foster learning culture also through cross-departmental collaboration within OIBN.