## PeaceRep Annual Review 2024-5

Title: Peace and Conflict Resolution Evidence Platform (PeaceRep)
Programme Value £ (full life): £19m total – (£18.5m official development assistance (ODA) funds, £0.5m non-ODA)[1]		Review date: July - August 2025
Programme Code: 301263	AMP start date: 01/10/2021	AMP end date: 30/09/2027
[1] The programme also received supplementary funding in 24/25 from outside the business case: non-ODA under the umbrella RED Mission Driven Research; ODA under CSSF Myanmar. Details are set out in 2024’s Annual Review.

Summary of Programme Performance
Year	2022	2023	2024	2025
Overall Output Score	A+	A+	A++	A++
Risk Rating	Minor	Moderate	Moderate	Moderate

DevTracker Link to Business Case:	Business Case
DevTracker Link to results framework:	Log-frame

A. SUMMARY AND OVERVIEW

Description of programme

The Peace and Conflict Resolution Evidence Platform (PeaceRep) is a £19 million research investment over seven years from 2021/22 to 2027/28, bringing together a research consortium of universities and research institutions, non- and inter-governmental organisations, and local research teams led by the University of Edinburgh (UoE) Law School. This team of 50+ researchers, mediation practitioners, lawyers, data scientists, managers, and communications professionals are dedicated to reimagining peace and transition processes.

PeaceRep is comprised of:

(i) interdisciplinary research on peace and transition processes: data-driven, comparative research examining the major trends and shifts in the post-1990 peace and transition process landscape to support innovation and adaptation to changing conflict contexts;

(ii) PeaceTech: the PA-X Peace Agreements Database contains over 2,000 peace agreements signed since 1990 and PA-X data underpins digital tools to support research and practice, including visualisations, dashboards, interactive timelines, and infographics;

(iii) peace process support: comparative evidence on peace and transition processes, and active peace and transition support to in-time issues, including for example on Afghanistan, Syria, Yemen, Iraq, Ethiopia, Sudan, South Sudan, Somalia, Myanmar and Ukraine; and

(iv) teaching and training: equipping professionals and students with the cutting-edge evidence and tools required to understand and rethink today’s peace and transition processes.

The UoE-led consortium includes LSE IDEAs, LSE Middle East Centre, Conciliation Resources (CR), International IDEA, Coventry University, University of Stirling, Queen’s University Belfast, and University of St Andrews who work together with other downstream partners comprising local researchers in case study contexts.

This review covers the period July 2024 to June 2025.

Budget per year to current FY

FCDO Financial Year	Annual Allocation (GBP)
1 April 2021 – 31 March 2022	£884,714
1 April 2022 – 31 March 2023	£3,757,836
1 April 2023 – 31 March 2024	£3,370,000
1 April 2024 – 31 March 2025	£4,591,000
1 April 2025 – 31 March 2026	£4,500,000

Some activities conducted under PeaceRep’s ODA grant – specifically, in Myanmar – have again received supplementary funding from the UK’s Integrated Security Fund (ISF) totalling £160,932 during this review period, for more focused work in-country.

Summary supporting narrative for the overall score in this review

PeaceRep scored A++ in its fourth full year of operation. The programme is moderately exceeding expectations against its Outcome milestones and is on track to ensure that conflict resolution processes are better informed by evidence: the outcome case studies demonstrate that PeaceRep’s research and advice continues to be highly valued across a range of contexts and peace processes, and reflects the trust and reputation that PeaceRep has built through its long-term engagement with a variety of stakeholders. Frequently, we heard in stakeholder interviews conducted for this review how the gains from investing in these relationships in previous programme years grow as the programme progresses.

PeaceRep has substantially exceeded output targets on producing quality products on peace and transition processes (Output 1) that are relevant to and informed by stakeholders like policy makers and mediators (Output 2) while moderately exceeding targets on enhancing research capacity, particularly in the Global South (Output 3).

The programme’s overall A++ score reflects the fact that the programme is continuing to deliver strongly against its objectives. A conclusion from last year’s annual review was that its A++ score indicated a mismatch between the ambition in the programme’s log frame, and what it had shown itself to be capable of delivering; but also reflected an unsustainable level of delivery and responsiveness to high policy demand which needed recalibrating. PeaceRep has since revised its milestones in response to that Annual Review’s recommendation. This year’s rating of A++ demonstrates that demand for PeaceRep’s expertise continues to be high both within and outside of FCDO, which combined with the volatile conflict context globally, has meant that the programme has continued to surpass targets. It also indicates that there remain some milestones which need to be further increased to reflect expected delivery (see below).

FCDO and PeaceRep leadership have agreed that key priorities for the fifth year of the programme will be to: further develop core concepts with a focus on drawing out policy implications in conjunction with practitioners; maximise opportunities for cross-consortium collaboration as the programme develops its synthesis outputs; and formalise a sustainability plan to ensure the programme’s lasting impact. These are set out in more detail in the findings and recommendations below.

Key achievements this year include:

Research and publications: Christine Bell’s book ‘PeaceTech’ had strong uptake over Y4, having been accessed a total of 22,000 times since it was published 18 months ago. Based on this success, Palgrave have now commissioned a second edition in Y5, which will be published Open Access, helping to sustain PeaceRep’s conceptual contribution to a rapidly changing field. PeaceRep further contributed to the understanding of contemporary peace and transition processes by publishing conceptual and empirical journal articles, including on ‘disaggregated mediation’ (Adhikari, Hodge, Bell, Siwa) in the highly ranked European Journal of International Relations. PeaceRep delivered a range of new publications on peacemaking and fragmentation in its ten country case studies (e.g. Somalia, Ethiopia, and South Sudan) as well as on emerging themes such as climate change (Epple and D’Amico). PeaceRep introduced a new annual product, a data report providing an annual overview of new peace agreements worldwide, to support policy audiences to engage with and interpret trends in PA-X data. For the first time, PeaceRep also published country-level key findings, synthesizing the main takeaways from country case study research. The section was launched with insights from South Sudan, Syria, and Somalia, and additional countries are in development for publication in the future. PeaceRep’s research is widely cited (see Outcome 1.2), underscoring its growing contribution to the field.

Peace process support and policy impact: PeaceRep’s pro-active peace and transition support and advice has informed international and domestic actors’ policies and operations in various contexts, including Myanmar, Somalia, South Sudan, Sudan, Syria, and Ukraine (see Outcome case studies). PeaceRep engaged the UK Special Representative for Syria, the UK Special Representative for South Sudan, and the EU Special Representative for the Horn of Africa, among other senior diplomats. PeaceRep’s research on multimediation, fragmentation, and peace process actors has been discussed and taken up in a range of policy circles (See for example, outcome case studies on Myanmar and Sudan for more detail). In addition, In November 2024, PeaceRep hosted Catherine West MP, Parliamentary Under-Secretary of State (Indo-Pacific), and colleagues from FCDO for a visit to Edinburgh Law School.

The UN Secretary-General’s 2024 annual report on the women, peace, and security agenda cites PeaceRep research to highlight the stagnation of women’s participation in peace processes, noting that none of the peace agreements in 2023 included women’s representatives as signatories. The report informed the Security Council’s meeting on advancing women’s roles in peacebuilding amid rising global conflicts.

In September 2024, PeaceRep hosted the FCDO Conflict Resolution Department (CRD) away day, with PeaceRep researchers offering a tailored session providing insights on mediation patterns and peace agreements trends using PA-X data and emerging findings from country case studies and the joint UoE-St Andrews Mediation Event and Negotiators Database (MEND). PeaceRep was then invited to deliver training to approximately 25 staff of the FCDO Conflict Resolution Department as part of their pilot internal Core Conflict Course which received excellent feedback.

In December 2024, PeaceRep responded to the overthrow of Bashar al-Assad with expert commentary and evidence-based analysis with researcher appearances on global news outlets including CNN, Sky News, and BBC News to offer insights into the Syrian conflict and what might lie ahead. Researchers including Kaldor, Turkmani, Mehchy, and Gharibah held a rapid response public roundtable, ‘The End of the Assad Regime? What Happens Now?’, which was attended by over 100 people, mostly from FCDO, with others from across HMG, LSE colleagues, and the general public. PeaceRep published a collation of PeaceRep research insights into the history of the Syrian conflict and key findings on transitional governance and power-sharing, alongside a list of PeaceRep media appearances on Syria. The Programme then pivoted its research agenda to account for the changed context. More detail on the impact of PeaceRep Syria’s policy engagement is included in the outcome case studies.
Data analytics, artificial intelligence (AI), and tools to track conflict resolution: PeaceRep has continued to develop innovative datasets and their application in research. The flagship dataset, the PA-X Peace Agreement Database and Dataset, has been updated to its 9th version since initial release in 2018, now containing 2144 peace agreements signed since 1990. The update also encompassed the PA-X Local and PA-X Gender sub-databases. In addition to the new data, PA-X now features a new and streamlined search page, to make access to information about peace agreements more efficient and effective. PA-X has seen an update on the data production side, with new data entry interfaces and database structure that ensures the database's sustainability. The uptake of PA-X data by external actors in research and policy, without PeaceRep’s involvement, (see Outcome 1.2) indicates the growing popularity of the dataset, and how the initial investment is growing in impact.
The programme also completed and updated the Peace Agreement Actors Dataset (PAA-X), as well as its expansion that focuses on Third Parties in Peace Agreements, and the Amnesties, Conflict and Peace Agreement database and codebook. These resources allow the tracking of specific actors, such as governments, armed groups, NGOs, religious organisations, international organisations, and others, to better understand the commitments made by these different actors at various stages of peace processes. PA-X and PAA-X are both core data resources for the PA-X Tracker, which continues to be regularly updated to provide an overview of key events, actors, and political and social indicators for countries in conflict. Another innovation this year has been the launch of the PA-X Tracker Globe that presents a global and regularly updated overview of conflict and peace agreement activity.

PeaceRep researchers have also completed the first stage of data collection for MEND, which collects systematic data on recent mediation events related to the most intense armed conflicts. MEND allows for a tracing of the mediation landscape, and its methodology that combines official sources and web-scraped news text ensures wide reach, beyond the most prominent peace talks, and beyond peace talks that result in a formal agreement. Taken together, these three complementary data resources – PA-X, PAA-X and MEND - provide a more comprehensive overview of the landscape of conflict mediation. They are also at the heart of the programme’s work with Large Language Models (LLMs) and Natural Language Processing (NLP): LLM and AI-driven projects to improve the efficiency of data production are now being implemented for PA-X and MEND, while PAA-X is an example of a data production process that relies on NLP.

Visibility and external recognition: PeaceRep researchers were awarded a number of additional funding grants during the review period, both offering notable added value to PeaceRep but also evidencing the value of PeaceRep’s research agenda and early research findings. These include: collaboration with FES (Ukraine and South Sudan), the British Academy’s Global (Dis)Order programme, the British Academy Talent Development Award, and the Scottish Peace Programme. Visibility highlights included being asked to host the 2024 Conflict Research Society Conference at Edinburgh Law School, and providing seven participation scholarships to participants from ODA-recipient countries. A record-breaking 137 institutions attended this flagship three-day conference that significantly contributed to PeaceRep’s visibility in peace and conflict studies.
Gender: PeaceRep delivers research to inform policymaking and practice on gender and Women, Peace and Security (WPS). PeaceRep advocates for greater inclusion of gender perspectives in peace processes, and for the support of women's full, equal, meaningful and safe participation in peace negotiations, particularly at early stages. It complies with the Gender Equality Act. This year, PeaceRep provided updated data and analysis on gender and peace agreements to inform the UN Secretary General’s Report reviewing the UN Security Council Resolution (UNSCR 1325) (see case Outcome case study). PeaceRep continues to maintain the PA-X Gender database and the PeaceFem mobile application on women’s inclusion in peace mediation. The consortium runs an annual Women Constitution-Makers joint analysis event, using this to inform a report relating to gender, peace processes and constitution-making – this year the focus was on the importance of women’s inclusion and insights in independent institutions. In 2024-25, PeaceRep also published reports on the WPS agenda in Afghanistan and the gender dynamics of the agri-food sector in northwest Syria and blogs on brideprice and conflict in South Sudan and gender and fragmentation in peace agreements.

PeaceRep has continued to consider gender in the design of the research into Y4 by:

- Including high-quality gender expertise in the programme’s research team. This continues into 2024-5. For example, Wise is a member of the Advancing Women in Peace Processes (AWIPP) Working Group, hosted by the Harvard Kennedy School’s Women and Public Policy Program, and of the governing committee of the UoE’s GENDER.ED which informs cross-University research and teaching on gender and sexuality from intersectional and interdisciplinary perspectives. This ensures PeaceRep’s approach to gender and inclusion remains current and abreast of developments in the broader academic field, thus informing good practice.
- Authoring and submitting evidence to the International Development Committee’s (IDC) Parliamentary Inquiry on Women, Peace and Security. Wise, Doby and Wilson (UoE) submitted evidence from PeaceRep's comparative research, focusing on the ‘participation’ pillar of WPS, particularly women’s full, equal, meaningful and safe participation in peace and transition processes at all stages.
- Delivering the second iteration of the online short course, Gender and Peace Processes in a Changing World, which introduces students to the women, peace and security agenda, inclusive peace processes in theory and practice, and gender perspectives in peace agreements alongside an opportunity to experiment with PeaceTech tools on gender perspectives in peace processes.
- Taking account of gender dimensions of conflict and peace and transition processes, both in terms of dedicated global data, and in each case study site. For example: (i) the South Sudan peace perception survey disaggregates all questions for gender; (ii) a gender focus guides the dowry and conflict project, which focuses on the conflict-triggering dimensions of excessive dowry payments on conflict-related countries; and (iii) researching the gender dimension of conflict in case study countries, including through analysis of post-Assad Syria which will continue into next year’s review cycle.
- Designing comparative and in-country research events through a gender lens. This is in order to evolve methodological thinking and approaches, and to deliver research focused on improving gender sensitivity and inclusion in peace and transition processes. For example, CR facilitates discussions among women mediators from Afghanistan, Ethiopia, and global network members on barriers, priorities and possibilities for more gender inclusive meditation. The Women’s Constitution-Makers Network and annual dialogue provides a platform for past and current women constitution-makers to build learning and share lessons and experiences with peers from other constitutional reform processes worldwide, which is disseminated through an annual research report.
- Monitoring and assessing the gender balance of researchers. The majority of PeaceRep’s core research team at the University of Edinburgh are women (56%), and women hold the majority of senior leadership roles (83%).
- Including gender sensitivity as a part of the remit of research peer review for PeaceRep outputs.

Supplementary funds:
PeaceRep received an ODA uplift in autumn 2024 of £91,959 to facilitate additional research as part of the Ukraine and Myanmar case studies. These additional funds were spent in full by year end with additional outputs delivered. PeaceRep received further additional funding (beyond RED) during this period, which is detailed as part of Section D.

Major lessons and recommendations for the year ahead

Lesson 1: The sustained relationships that PeaceRep has built with policymakers and practitioners over the lifetime of the programme is at the heart of much of its impact. These relationships are mutually beneficial, providing policymakers and practitioners with credible, expert and grounded insights whilst providing researchers with real time feedback on the feasibility of their recommendations from those who have an understanding of political realities which may not be immediately accessible to academics. There is potential to leverage these relationships further as the programme seeks to advance its core concepts in its final major year of delivery, to sensitise policymakers and practitioners to these concepts whilst providing researchers with insights on how well the theory lands amongst those engaged with peace processes in practice.

Lesson 2: PeaceRep’s conceptual research is valued by policymakers for helping them to understand and respond to the complexities of the current geo-political context. This conceptual work has most impact when research outputs present informed, actionable policy recommendations.

Lesson 3: Interaction between the conceptual analysis and the case study research strengthens both. In a consortium of this size, this interaction can happen organically but needs to be deliberately facilitated to ensure it happens comprehensively. This means facilitating opportunities for collaboration between those leading on conceptual development and those leading local research, as well as between academic and non-academic partners. The planned synthesis work on multimediation and the cross-consortium workshop in Jordan that will bring together researchers and practitioners from conflict-affected countries and the UK, both planned for Year 5, are good opportunities for this kind of interaction.

Lesson 4: The programme is reaching the point where more concrete plans are required to ensure the sustainability of the programme beyond the lifetime of its current grant, including its PA-X and MEND ‘public good’ data. This should be a priority for PeaceRep Senior Leadership and FCDO in Year 5.

Lesson 5: In a programme such as PeaceRep where results are not always predictable at the outset, longer-term positive outcomes of the investment that build over several reporting years risk being missed – for example, the networking impacts of regular convening activities, or the capacity building impacts of the programme’s engagement with local researchers and its professional development courses. Harvesting and capturing these outcomes and impacts will become more important as the programme seeks to demonstrate its overall impact against its agreed impact indicators towards the end of the grant.

Lesson 6: Whilst some milestones now more accurately reflect what the programme can reasonably expect to achieve, others are still being substantially exceeded. In several cases, the rates of delivery over the past two years are now a stronger indicator of what the programme can be expected to deliver, than the output milestones themselves. This suggests that some milestones are still not ambitious enough to fairly reflect what we now know the programme can reasonably deliver in the current programme year. One exception to this is Output 2.2 on in-time oral advice, which does reflect efforts from the consortium that went above and beyond what the programme can be expected to sustain. Where new outcome indicators were added for Year 4, the baseline data now available within this annual review can be used to reassess how far the milestones for these new indicators can be raised.

Recommendation 1: Conceptual development on multimediation and fragmentation: By the end of September 2025, PeaceRep to kick off a process of interviews and workshops that engages a range of policymakers and practitioners in the multimediation concept, to allow researchers to test and refine the concept, and to identify policy implications and recommendations for how practitioners can respond to the realities of multimediation and fragmented peacemaking.

Recommendation 2: Policy impact and uptake: Ensure the visibility and accessibility of PeaceRep outputs that address how conflict resolution practice needs to adapt to the changing geo-political context by:
(i) Combining Year 5 conceptual outputs, including synthesis and legacy products, with practical and informed policy recommendations. This should extend to academic outputs such as the special issue, e.g. by supplementing these outputs with policy briefs written for a practitioner audience. To be completed by end of March 2026.
(ii) By the end of October 2025, PeaceRep to develop a plan for strategic engagements on the big picture ideas and capstone synthesis / legacy outputs of the programme. The FCDO Lead Adviser can support by convening key FCDO stakeholders to consult on what types of engagements would be most strategic to align with FCDO objectives and priorities across the year on this theme.

Recommendation 3: Cross-consortium collaboration: Review cross-consortium coordination mechanisms to ensure that PeaceRep is maximising the benefits of the diversity of expertise within the consortium in this crucial year for synthesis and conceptual development. PeaceRep SLT to work with consortium partners to elaborate and strengthen plans for cross-consortium collaboration including in relation to planned synthesis pieces, and particularly those being led by downstream consortium partners. A refreshed plan for cross-consortium collaboration to be finalised by end of September 2025.

Recommendation 4: Sustainability planning: PeaceRep, by the end of December 2025, to formalise concrete sustainability plans to enable the sustainability of the programme beyond the lifetime of its current grant, including its PA-X and MEND ‘public good’ data. This should involve a presentation and discussion with the International Advisory Board at its bi-annual meeting in November 2025. On financial sustainability, the plan should set out what work PeaceRep proposes to continue beyond the lifetime of the grant across its four pillars (1. Research; 2. PeaceTech; 3. Peace Process Support; 4. Teaching and Training) and its capacity building work with Global South researchers and practitioners. The plan should be clear about the financial model(s) that will underpin this proposed work, with viable options for funding streams identified. On data sustainability, the plan should outline what steps PeaceRep’s will be taking to further integrate data from across the consortium.

Recommendation 5: Monitoring, evaluation and learning: By the end of March 2026 PeaceRep should develop a plan for a specific piece of work that will assess and capture the programme’s impact. This work should draw on impact and evaluation expertise either from within UoE or from external sources, depending on budget availability. It should focus on the programme’s networking and capacity building impact, as well as its conceptual and instrumental impact. Initial impact case studies to be developed by the next annual review (end of June 2026).

Recommendation 6: Log frame revisions: All output and outcome milestones which were substantially exceeded in this reporting year should be reassessed and amended to reflect a reasonable level of ambition for the programme, drawing on the evidence of previous years’ delivery and bearing in mind differences in annual budgets, to present a fair expectation of what the programme will deliver in Year 5 (PeaceRep, by end of December 2025.)

Progress summary of 2023/24 recommendations

R1. PeaceRep, in conjunction with the SRO and PRO, should review the milestones for Year 4, Year 5, and Year 6 to ensure they are reflective both of what the programme can be expected to deliver, and what would demonstrate a sustainable pace of delivery with emphasis on empirical and conceptual quality for the final years (by October 2024).

Partially met. Completed and signed off in December 2024 with log frame approved. This is considered partially met as it was completed outside of the recommended timeframe. Additionally, while PeaceRep did raise output milestones as recommended, the extent to which some of these milestones have again been exceeded raises the question of whether they were raised enough to reflect what the programme could be expected to deliver.

R2. PeaceRep to fully revise the programme’s impact indicators to create measures that are relevant to a research programme, reflective of the programme’s impact ambition and potential, and that are measurable during the lifetime of the programme. PeaceRep to adjust the Theory of Change and log-frame accordingly, including adding relevant indicators at outcome level, in agreement with FCDO (by January 2025).

Met. Completed and signed off in January 2025 with log frame approved.

R3. In future programme years, outcome case studies should go beyond demonstrating that practitioners have engaged with PeaceRep research, and set out more clearly how that research or advice has been utilised, such as by capturing what has changed as a result of PeaceRep’s work.

Met. Over the course of this review period, PeaceRep crafted a set of possible outcome case studies, collecting evidence from key stakeholders and discussing these with the SRO and PRO periodically. The PRO then triangulated with stakeholders to evidence outcome stories, including through interviews.

R4. PeaceRep to continue developing the concepts of ‘multimediation’ and ‘fragmentation’ and new work on governance and constitutionalism including by engaging in conversation with FCDO practitioners to test these concepts in different contexts and to draw out their implications for policy and practice, and by publishing to seek peer academic review (by June 2025).

Met. Concepts have continued to be developed as part of the work towards the fragmentation special issue. FCDO staff were engaged on core concepts of multimediation and fragmentation through a plenary panel discussion at the annual FCDO conflict conference, and through PeaceRep participation in preparations for the Sudan conference. Individual country case study leads have engaged both HMG and non-HMG stakeholders on how these concepts are playing out in contexts such as Sudan and Myanmar.

As a next step, PeaceRep will be working in Y5 towards refining and synthesising the multimediation concept and on drawing out policy implications. This review’s recommendations propose a way to structure this work to have the strongest impact.

R5. Given HMG demand for PeaceRep’ bespoke evidence and advice outstrips possible supply, RED and PeaceRep to jointly consider strategies for ensuring that PeaceRep’s workload is sustainable and that proportionate time and resource is spent on advisory work and research delivery respectively, with a focus on the highest priority, highest impact research and advisory outputs. This should include identifying priority areas for policy engagement, reviewing approaches to managing in-time advice requests, and assessing whether certain types of research outputs can be de-prioritised to protect time for core research (by November 2024).

Met. PeaceRep and FCDO established quarterly meetings for assessing proposals for engagements and in time advice requests and agreeing priorities for the coming quarter. This has also been monitored through regular monthly meetings. Clearer criteria have been applied for assessing and agreeing priority engagements and responses, such as the extent to which a response or engagement will draw on PeaceRep’s specific expertise, the influence of the audience/requester and the capacity within the consortium. The consensus at quarterly catch-ups between FCDO and PeaceRep is that the workload is now more manageable and sustainable, whilst the programme continues to deliver on high impact requests. Strategies are in place for continuing to manage this balance into Y5.

R6. PeaceRep to implement its PA-X Tracker socialisation plan to support iterative development of the Tracker through continued end-user engagement. RED to assist with socialisation of the Tracker with FCDO teams and PeaceRep to develop and document specific Tracker use cases (by June 2025).

Met. PeaceRep has engaged research and policy audiences on the PA-X Tracker through a number of engagements, including:

- A presentation to FCDO Conflict Resolution Department (CRD) in Edinburgh in September 2024.
- A keynote presentation and a workshop presentation on the Tracker at the September 2024 Conflict Research Society (CRS) Annual Conference.
- Engagement activities at the International Studies Association (ISA) March 2025 annual conference, including researcher presentations, a reception event and an information booth, which collected evidence from academic end-users on the uptake of the Tracker particularly in teaching.
- A presentation at the March 2025 FCDO Conflict Conference in Glasgow, featuring the Tracker’s Scrollytelling work.
- A presentation to FCDO Myanmar as part of their visit to Edinburgh in March 2025.
- Development of new Globe Map to provide an updated point of entry to the Tracker’s country profiles. This was undertaken as a direct result of end-user feedback.

The Tracker has received positive feedback through these engagements, particularly from the research community. Practical Tracker use cases to date include:
- FCDO CRD using the Tracker’s interactive country timelines of peace or transition agreements, coup d’états, amnesties, elections and constitutional events since 1990, in its analysis of peace and transition processes.
- In mid-2025, a member of the PeaceRep UoE team used PA-X and the Tracker to advise stakeholders in an intra-state armed conflict with a long-standing peace process, helping parties overcome a key obstacle in their peace process.
- The United Nations Systems Staff College (UNSSC) using the Tracker as an example of a tool that can provide historical information in the context of evidence-based programming, as part of its ‘Integrated Data Analytics for Conflict Prevention Intermediate Boot Camp’ (June/July 2024).

R7. PeaceRep to make specific plans for programme synthesis across research strands in Year 5. PeaceRep to update its key findings page and products, and to add country key findings (by March 2025).

Met. PeaceRep has developed a plan for programme synthesis in Year 5, which was captured in the Year 5 workplan presented to the FCDO in February 2025, and further elaborated in the revised Research Uptake Strategy (June 2025). Cross-consortium exchanges on thematic and geographic areas will identify and collate top-line evidence from the breadth and depth of the programme’s research. These findings will be published in a range of synthesis outputs drawing together key insights and analysis from across the consortium, together capturing PeaceRep’s central contributions to the field. Each synthesis output is aimed at different audiences across policy, practice, and academia, and will be socialised in a programme of activities designed to maximise uptake and impact among key audiences. Data synthesis will form an important element of this work, bridging the gap between raw data from PA-X and end users who rely on secondary analysis to interpret the data for maximum uptake.

Indicative synthesis outputs include:
- A second edition of Christine Bell’s monograph, PeaceTech: Digital Transformation to End War
- A cross-programme multimediation synthesis paper
- A series of thematic and country synthesis papers planned by partners
- A compendium of thematic and geographic key findings
- A synthesis paper on ‘peace analytics’ in Year 6
PeaceRep’s key findings products form an important pillar of programme synthesis. Year 4 saw the publication of new thematic findings on fragmentation, environment and climate, and violent extremism; and the launch of a new country findings page with Myanmar, Somalia, South Sudan, Sudan, and Syria. Additional findings on Ukraine, Afghanistan, Ethiopia, and Iraq are in development.

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

PeaceRep has exceeded delivery of outcome and output targets and its theory of change remains valid. The theory of change is that PeaceRep will provide world class research and in-time expertise to FCDO and partners on the design and timing of peace processes and that this will enable negotiators, mediators and those engaged in peace and political processes to improve efforts to end war and conflict.

Diagram 1: PeaceRep’s Theory of Change

£19M and RED staff time

Outcomes

Impact

Output

Intervention

Input
Intervention Work Strands

Data analytics & AI to aggregate conflict data and research and illustrate this through new tools.

 Tools to track Peace & Conflict Resolution through data and research.

In-country research and data to understand how conflict resolution works in specific contexts.

Output Components.

Public good research: a new research platform to track conflict resolution.

Tools to aid process and intervention design that track how processes and interventions adjust to opportunities and risks.
Policy engagement including:

Rapid advice: to inform time critical response.

Convening & leadership: Engage with actors involved in conflict resolution to improve evidence based response.
Products, events, outputs include:
Dashboards
Website
Research Papers
Policy Briefs
Blogs
Rapid Expertise
Events
Prospects of peace reports

Conflict Resolution processes and practice are better informed by evidence’
Demonstrated through the evidence -informed practice of UK, UN and other actors involved in Conflict Resolution
Fewer, less deadly and shorter conflicts around the globe.

This theory of change, is based on the assumptions that:
- Policy makers make more use of evidence because of having better data, better presented data and improved institutional memory on what has and has not worked before.
- Improving knowledge on precedent will make conflict resolution efforts more successful and durable, e.g. by providing options to break deadlock, understanding of red lines and sticking points, and solutions to technical and political disputes.
- Improving data on the timing and sequencing of conflict resolution will improve interventions, as the timing of interventions related to peace processes has been highlighted as essential to success. PeaceRep will identify time-sensitive ‘critical junctures’ for engagement and indicate where interventions could be better adjusted.
- Practitioners will take up intervention design choices that maximise benefits for conflict resolution (e.g., in economic development, essential services, support to civic actors). PeaceRep will examine where resolution efforts are working and where they are going off track to determine how interventions should be adapted.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact progress:

PeaceRep’s intended Impact is ‘Fewer, less deadly, and shorter, conflicts globally’.

The impact indicators were changed following a recommendation from the 2023-24 Annual Review, which found that the previous impact indicators were too distant from the programme’s Theory of Change to present a meaningful measurement for understanding how this research fits into the global conflict research context. The impact indicator below reflects the new indicator as agreed between PeaceRep and FCDO in December 2024.

Impact Indicator 1	Progress
Number of cases of conceptual impact (changing ways of thinking at scale or at a significant level, leading to significant peace actors adopting PeaceRep thinking in strategies or approaches); OR instrumental impact (where PeaceRep has influenced an actor in a peace and transition process as a result of which there was a positive change in the process/context); OR networks and connectivity impact (eg, evidence of impact from building and strengthening networks etc); OR capacity building impact (evidence of impact from building researchers' capacity to conduct research or socialise their research, or practitioners' capacity to use PeaceTech etc) / (Target date 2027, to be assessed annually against narrative impact stories)	PeaceRep has made progress in conceptual innovation, continuing to develop concepts including ‘multimediation’ and ‘fragmentation’, and initiating new work on governance and constitutionalism in (post-)conflict contexts. There are indications of uptake of these concepts in both academic and practitioner fields, including citations in scholarly articles and policy documents, invitations to key international fora, the ongoing demand for PeaceRep advice, and stakeholder feedback. PeaceRep has designed a series of outputs for 2025-6 to consolidate conceptual learning and demonstrate its contribution to the field.

Outcome progress:

PeaceRep’s intended Outcome 1 is ‘The new knowledge, evidence and PeaceTech produced by the programme influences conceptual thinking on contemporary peace and transition processes’.
Outcome Indicator 1.1		Baseline	Jun-22	Jun-23	Jun-24	Jun-25	Jun-26	Jun-27	Sep-27	Cumulative
Number of cases where PeaceRep is invited to speak at a multi-stakeholder event convened by scholarly or policy-focused actors in peace and transition processes, with subsequent evidence of uptake.	Planned	/	/	/	/	8	8	1	/	17
	Achieved	/	/	/	/	12
Outcome Indicator 1.2		Baseline	Jun-22	Jun-23	Jun-24	Jun-25	Jun-26	Jun-27	Sep-27	Cumulative
Number of instances of PeaceRep research findings and recommendations taken up and referenced in published scholarly work, recommendations, official reports, and/or Southern & Northern media outputs.	Planned	/	/	10	15	22	24	8	/	79
	Achieved	/	29	21	54	121
Outcome Indicator 1.3		Baseline	Jun-22	Jun-23	Jun-24	Jun-25	Jun-26	Jun-27	Sep-27	Cumulative
Number of PA-X citations, as per Google Scholar; supplemented by short narratives of the most impactful cases of PA-X uptake.	Planned	/	/	/	/	8	12	16	/	36
	Achieved	/	/	/	/	37

PeaceRep is on track to contribute to the expected outcomes. It substantially exceeded its Outcome 1 targets this year.

Outcome 1.1

PeaceRep researchers were invited to contribute to or deliver a series of high-profile engagement opportunities. These included:
- An invitation to present at the WTO Public Forum 2024 on sustainability standards in global supply chains, including supply chains for critical minerals (Lang, UoE). The invitation was received as a result of Lang publishing a report with the British Standards Institution (BSI) on sustainability standards. Lang has since spoken at further invitations from Queen Mary University and HMG’s Department for Business and Trade.
- Workshop in Myanmar
- An invitation to deliver opening remarks to the 2025 British Academy/Carnegie Institute for Peace opening conference on 'Global (Dis)Order'. Wise (UoE) was one of three individuals invited to deliver opening remarks for a roundtable on prospects and pathways for regalvanising accountability for violations of the laws of war, during which she focused on accountability gaps for conflict-related sexual violence. The roundtable was attended by around 30 senior members of the FCDO, the ICRC, international human rights lawyers, peacebuilders, and academics and was chaired by Christine Chinkin, LSE. The impact of this will be realised through the forthcoming invited publication, which PeaceRep researchers will be contributing authors.
- PeaceRep UoE was asked to host the Conflict Research Society 2024 conference at Edinburgh Law School.
- PeaceRep UoE was asked to host the FCDO Conflict Resolution Department (CRD) away day at Edinburgh Law School, and subsequent invitation to deliver a bespoke training session.
- Epple (UoE) was invited to deliver an opening talk on his PeaceRep research at a workshop on ‘Assessing the Challenges & Chances of Climate Change for Peace Mediation Processes’ hosted by the German Center for International Peace Operations (ZIF) in Berlin on 18 September 2024. After delivering the talk, Epple was invited to co-author a policy brief with the ZIF on climate-sensitive mediation.
- International IDEA was invited to present in the first session of a two-day workshop on Navigating Uncertainty: The Case for Interim Constitutions in Syria and Palestine, held at the University Sciences Po in Paris on 15-16 May 2025, on ‘Transitions and Interim Constitutions’ – the theme of the first Edinburgh Dialogue and follow-up policy paper. The entire workshop, but in particular the presentation prepared by International IDEA, received excellent evaluations from the attendees. As a result, the organisers intend to turn the workshop into a permanent course.
- a series of invitations to present on the South Sudan Peace Perceptions Survey (Pospisil, Coventry) including at a South Sudan Heads of Mission meeting in Juba. 15 Heads of mission (or representatives) were present, including UN DSRSG/RC/HC, UNMISS Civil Affairs, and delegations from the EU, USA, Canada, Norway, Switzerland, United Kingdom, Netherlands, Germany, Japan, and Egypt. Early uptake from this is evidenced by subsequent in-time advice requests and media requests.
- the publication of the PeaceRep report on the economic balance of power between Ukraine and Russia in the war (Cooper, LSE IDEAS) received a number of mentions in news media (39 separate outlets), and resulted in an op-ed by Cooper in The Guardian on the US-Ukraine Critical Minerals Deal. Cooper has been invited to present the research at a series of opportunities including as part of an expert roundtable organised by the Ukraine Recovery and Reconstruction team at FCDO.
- Navigating Protracted Conflicts in a Multi-Aligned World: Closing the Chatham House XCEPT Research Programme: PeaceRep (Kaldor, LSE IDEAS) was invited to contribute to a plenary entitled Multialignment and transnational conflict: policy challenges and implications. The high-level session brought together policymakers and experts to discuss how governments are adapting to these evolving dynamics and consider the strategic, diplomatic, and security implications of multi-alignment in today’s interconnected conflicts.
- following her public inaugural lecture, Mallinder (QUB) was invited to write an article summarising the arguments from her PeaceRep research for the April 2025 issue of the Northern Ireland political magazine, Fortnight. The article was part of a series of pieces intended to be relevant to forthcoming Supreme Court hearings on the NI Legacy Act.
- following a series of in-country engagements focusing on PeaceRep research, Adhikari (Stirling) was approached as a ‘noted expert’ to discuss Malaysian chairmanship of ASEAN and its ongoing engagement in Myanmar by Frontier Myanmar, one of the most-read outlets in the country. The interview referenced data from PA-X Peace Agreement Actors Dataset which has mapped Malaysia to be one of the most prolific signatories in peace agreements from the Global South.

Outcome 1.2
PeaceRep was cited in 20 scholarly works, recommendations, and official reports; and at least 46 media appearances. Key citation examples included:
- The 2024 United Nations Secretary-General's annual report on Women, Peace and Security (S/2024/671) cites Wise (“None of the peace agreements reached in 2023 included a women’s group or representative as a signatory”) and a graph from PA-X showing the percentage of peace agreements with provisions referring to women, girls, and gender, 1990-2023 (see details in Outcome 2.2 case study).
- Developing from the sustained relationship with UN Women, the UN Committee on the Elimination of Discrimination against Women (CEDAW) references PeaceRep statistics in its October 2024 General Recommendation No. 40 (2024) on the Equal and Inclusive Representation of Women in Decision-making Systems (CEDAW/C/GC/40). In the report’s Peace and political stability section, CEDAW referenced PA-X Gender versions 7 and 8 data which shows that “[i]n 2023, none of the peace agreements reached included representatives of women’s groups as signatories” (p. 4).
- PA-X data and analysis provided by the UoE PeaceRep team supported the UN Special Rapporteur on Human Rights of internally displaced persons to better understand the dynamics around the provisions and lack of provisions relating to IDPs in peace agreements. The Special Rapporteur team reported that this data analysis helped them to formulate conclusions and recommendations on the need for more attention in peace processes to internal displacement. These recommendations, and a citation to PA-X data, appear in the 2024 Report of the Special Rapporteur on the human rights of internally displaced persons (A/79/334), which was presented to the UN General Assembly in October 2024.
- The OECD States of Fragility Report 2025 cites several PeaceRep works, including ‘Non-Western approaches to peacemaking and peacebuilding: State-of-the-art and an agenda for research’ by Peter and Rice; ‘Security Sector Governance and Reform in Ukraine’ by Beliakova and Detzner; and ‘The spaces of local agreements: Towards a new imaginary of the peace process’ by Bell and Wise.
- Bell’s (UoE) book was cited in an article in Data & Policy exploring the role of AI in promoting peace. The piece acknowledged Bell’s work as part of "an ecosystem of scholars, research institutes, civil society organizations, public institutions, private companies, philanthropic institutions, and venture capitalists working on technology for peace, including AI for peacebuilding.”
- Peter’s (St Andrews) Global Transitions series report, ‘Non-Western approaches to peacemaking and peacebuilding: State-of-the-art and an agenda for research’, was cited in two articles in Contemporary Security Policy, including ‘Children of their time: The impact of world politics on United Nations peace operations’ and ‘Making peace by fighting war: competing visions of conflict management and African agency in the “new scramble for Africa”’.
- Epple’s (UoE) work on climate change and peace agreements, and PeaceRep’s key findings on the environment and climate, were cited in Berghof Foundation’s November 2024 report on ‘Climate, peace and conflict: Mapping linkages and a path forward’ (p. 13).
- In the media, PeaceRep research was cited in The Guardian (Pospisil), The Independent (Conciliation Resources)and PeaceRep researchers appeared in global mainstream media outlets including the BBC, The Times, CNN, TRT World, and more (see narrative under Output 2 below).
- PeaceRep’s media engagements well exceeded anticipated levels. This is explained by demand due to world events, particularly in South Sudan and Ukraine. For example, one PeaceRep report on Ukraine was covered by 39 media outlets in Q1 alone due to the popular relevance of critical mineral rights, which could not have been foreseen. This resulted in a piece by Cooper (LSE IDEAS) being commissioned by The Guardian, awarding significant (and broad) research uptake to the programme.

Outcome 1.3

PA-X has been cited a cumulative total of 237 times since 2018 for the codebook and 2019 for the data feature article, across:
- the data feature article (Introducing PA-X: A new peace agreement database and dataset, C Bell, S Badanjak. Journal of Peace Research 56 (3), 452-466).
- the PA-X Codebook (Bell, Christine, Sanja Badanjak, Adam Farquhar, Juline Beaujouan, Tim Epple, Robert Forster, Astrid Jamar, Kevin McNicholl, Sean Molloy, Kathryn Nash, Jan Pospisil, Robert Wilson, Laura Wise. (2025). PA-X Codebook, Version 9. Peace and Conflict Resolution Evidence Platform (PeaceRep), University of Edinburgh).
The data and technology tools produced by the PeaceRep teams, particularly the PA-X and MEND data suites, have been cited in widely read policy reports and official documents (see Outcome 1.2, e.g. by the UN and OECD). In academic research, PA-X has served as a source of original peace agreement texts and as a quantitative dataset. As can be seen from the citations of PA-X outputs collected from Google Scholar, there have now been more than 100 articles, books, theses, and reports that have cited the data. The data, the data-based PA-X Tracker, and the key findings from the data-driven PeaceRep research have been presented in multiple academic and practitioner venues (see Outcome 1.1 for examples). The UNSSC uses PA-X data in its assignments for UN staff and non-UN participants in data analytics training. Feedback from end users has also highlighted how PA-X data acts as a resource for supporting those involved in negotiations to understand and develop options to resolve particular issues at the centre of talks.

PeaceRep’s intended Outcome 2 is ‘Conflict resolution processes and practice are better informed by evidence’.

Outcome Indicator 2.1		Baseline	Jun-22	Jun-23	Jun-24	Jun-25	Jun-26	Jun-27	Sep-27	Cumulative
Number of cases where PeaceRep research influences UK policy or operations on conflict resolution.	Planned	/	/	3	3	3	3	/	/	12
	Achieved	/	/	4	5	4
Outcome Indicator 2.2		Baseline	Jun-22	Jun-23	Jun-24	Jun-25	Jun-26	Jun-27	Sep-27	Cumulative
Number of cases where PeaceRep research influences policy or operations of international or domestic actors involved in conflict resolution such as UN, regional bodies, parties involved in conflict resolution	Planned	/	/	3	3	3	3	/	/	12
	Achieved	/	/	5	8	8

PeaceRep is on track to contribute to the expected outcomes. It moderately exceeded its Outcome 2 targets this year. A selection of outcome case studies are included below.

Outcome Indicator 2.1: Number of cases where PeaceRep research influences UK (Government) policy or operations on conflict resolution (assessed through case studies of evidence use in specific conflicts and processes).
Case	Outcome
FCDO: Ukraine	As part of its regular preparation for the annual Ukraine Recovery Conference, the PeaceRep Ukraine team, in collaboration with Clingendael Institute, Kyiv School of Economics and Friedrich Ebert Stiftung, hosted an expert roundtable attended by a range of stakeholders, including staff from the Ukraine Early Recovery and Reconstruction Department and British Embassy Kyiv. FCDO officials later commented on the value of the roundtable noting that it challenged assumptions (such as on approaches to addressing unemployment); it built staff knowledge base and understanding of key issues (such as on critical minerals); it provided opportunities for networking in the margins and subsequent relationship building (such as with the Clingandael institute, which has since led to closer engagement with the Netherlands on recovery and reconstruction); and facilitated engagement with Ukrainian policy makers who provided insights on a Ukrainian perspective that staff may not have otherwise been exposed to. / In addition to the support on the URC, the PeaceRep Ukraine team also engaged FCDO staff on dedicated piece of research on Ukraine-China relations, produced using FCDO uplift funding in Q4. FCDO staff valued PeaceRep’s collaborative approach in developing the research questions, and commented that these early discussions on the areas of research focus were useful in themselves for supporting internal FCDO thinking on the key issues.
FCDO: Myanmar	The PeaceRep Myanmar team continued to facilitate workshops with key stakeholders. The workshops held in this reporting year built on trusted relationships established through PeaceRep engagements in previous years. These activities have directly contributed to the British Embassy Yangon’s objectives in Myanmar.
FCDO: Syria	Following the fall of the Assad regime in December 2024, PeaceRep Syria research supported the FCDO response. For example: / PeaceRep’s existing thematic briefings and research reports on political transitions provided clear lessons on how transitions tend to evolve and what approaches tend to be successful. / PeaceRep Syria researchers provided a number of ad hoc briefings in the days and weeks following the change of regime. / PeaceRep research has continued to support UK longer-term thinking on Syria throughout the reporting period.
FCDO: Conflict Resolution Department / Lebanon	PeaceRep provided a rapid response paper on the history of ceasefires in Lebanon following a request from FCDO officials during the conflict between Israel and Lebanon in 2024. This paper was used as the basis for an internal roundtable discussion facilitated by the FCDO’s Conflict Resolution Department for officials working on the response to the crisis. One official commented that the paper was crucial for supporting staff to better understand the history of previous ceasefire arrangements and shaped subsequent work on the role of the United Nations Interim Force in Lebanon (UNIFIL).

Outcome Indicator 2.2: Number of cases where PeaceRep research influences policy or operations of international or domestic actors involved in conflict resolution such as UN, regional bodies, parties involved in conflict resolution (assessed through case studies of evidence use in specific conflicts and processes).
Case	Outcome
Somalia: / Informing ECHO funding and do-no-harm strategies and approaches	The PeaceRep LSE Somalia team has established a close working relationship with ECHO Somalia, who chair the Humanitarian Donor Group in the country and are dynamic members of the Humanitarian Country Team (HCT). ECHO have been a proactive partner, utilising new PeaceRep research as well as the historical knowledge of the PeaceRep team (and its networks) to drive reforms and innovations in the humanitarian system. Underlying this relationship has been an appreciation for the political economy of aid in Somalia, that PeaceRep analysis brings, as well as the ‘activist’ approach that it articulates. / The success of this collaboration has been evident in a number of ways including: facilitated in-person presentation of key research – on corruption and aid diversion – to the humanitarian donor group; ongoing dissemination of blogposts and other outputs to the HCT; invitations to speak at EU/ECHO regional and global events (DG ECHO Regional Seminar (June 2024) and the EU Humanitarian Forum (March 2024). In addition, the Head of ECHO spoke as a panelist at an online session, organised by PeaceRep (Somalia) on corruption in the global humanitarian sector, at the Humanitarian Networks and Partnerships Week (April 2025). / One of the specific focuses of these engagements has concerned risks related to aid diversion and on ensuring a ‘do-no-harm’ approach to humanitarian aid. / ECHO Somalia reported that PeaceRep’s research and advice has informed the asks that ECHO make of their funded partners to ensure they are not inadvertently contributing to the negative aspects of the aid economy. In addition, PeaceRep’s written and oral advice has contributed to improved mitigation measures along with and as part of the advice of other humanitarian experts working in Somalia, with whom PeaceRep also actively collaborate.
South Sudan: / PeaceRep research informs domestic and international debates and electoral support strategies	Evidence from the South Sudan Public Perceptions of Peace Survey (PeaceRep – Coventry) has directly influenced national and international support for elections in South Sudan. / Conducted in six annual waves since 2020, the surveys provide a unique and trusted evidence base of local perceptions. Recent surveys show that 80% of surveyed South Sudanese citizens support elections to be held at the earliest possible date, even among respondents who believe the likelihood of election-related violence is high or very high. The surveys have influenced bilateral electoral support strategies, including US strategy, and were also cited in domestic political debates by key stakeholders, including the Executive Secretariat of the Sudan People’s Liberation Movement, to advocate for holding elections. / The research has been influential in informing the work of the Joint Election Support Committee – comprising UN bodies, bilateral donors, and national stakeholders – on South Sudan’s National Elections Act and in identifying potential hotspots for election-related violence. Survey findings – in particular questions regarding confidence in voting, expectation from electoral bodies, and political and civic space – have been presented to members of the national legislature and the National Election Commission, and were integrated into scenario planning exercises around electoral outcomes in workshops conducted collaboratively with the Friedrich-Ebert-Stiftung. The survey data directly informed discussions on ballot sheets, for example. The survey data was also socialised with the coordinator of the South Sudan National Police Service, contributing to early-stage institutional preparedness for elections. / Although national elections have been postponed to December 2026, the evidence generated by PeaceRep continues to shape electoral planning.
Sudan: / Supporting multimediation in the current conflict	PeaceRep’s long-term engagement in Sudan exemplifies the programme’s overarching commitment to rethinking international peacemaking. Rather than endorsing time-bound transitions aimed at rapid liberal institutional reform, the programme promotes a long-term, adaptive model that works incrementally, through iterative engagement, sectoral entry points, and locally grounded solutions. / PeaceRep’s approach to multimediation in Sudan has been discussed with senior Swiss and German diplomats, the team of the European Union Special Representative for the Horn of Africa, and United Nations system actors, highlighting possible pathways for grounded meditation approaches in light of the stalled Track 1. / PeaceRep-Coventry also played a key role in supporting practical mediation efforts with an armed actor in Sudan.
Syria: / Informing UNDP Syria strategy and programming	In 2024-2025, the PeaceRep LSE Syria Team has contributed to shaping international approaches to Syria's economic and social development. For instance, building on evidence socialisation efforts at a conference in 2024 and cooperation with United Nations Development Programme (UNDP) Syria in Damascus regarding the economic and social role of the private sector, the LSE Syria team succeeded in engaging UNDP - after several months of discussions - to undertake and fund a project focused on the importance of reviving value chains across conflict lines, aiming to enhance social cohesion within the country. / Following the fall of the Assad regime, the team adjusted the project to focus more on the social and economic integration between different areas in Syria. The LSE Syria team completed a first report within this project, ‘Value Chain Development in Syria to Promote Economic Benefits and Social Cohesion’, that informed the strategic design of a second UNDP development phase, concentrating on sector-specific initiatives and thereby guiding the practical programming of UNDP Syria.
Ukraine: / Fostering and informing Ukraine-Russia civil society exchange and advocacy around negotiations	The PeaceRep Ukraine LSE team organised a workshop of civil society advocates from Ukraine, Russia and the wider international community in December 2024. The workshop engaged civil society networks in research produced by the Ukraine programme, including research on the situation in occupied territories and the political economy of the war, and also acted as a source of knowledge generation, drawing on insights from the civil society community to develop 31 priority areas of discussion for the Russia-Ukraine peace talks. Post-workshop, some of the participants went on to establish the “People First” advocacy coalition, which has been campaigning to release captives of the Russian invasion and advocating for prisoner releases to be central to negotiations. The formation of the People First advocacy coalition was a direct result of the organisation of the workshop by PeaceRep. The PeaceRep Ukraine team has provided informal research support to the development of this coalition that includes the Nobel prize winning organisation the Centre for Civil Liberties and Memorial. The call to release captives was already present in President Zelensky’s 10-point formula, though it is possible the People First campaign did influence the emphasis given to it in the subsequent 2025 peace talks - where it appeared as a central priority in the Europe-Ukraine peace proposal of late April 2025. However, the significance of the formation of People First lies in capacity building and strengthening links between civil society in Russia, Ukraine and the broader international community. While informal contacts between some Russian and Ukrainian civic actors continued in private after the full-scale invasion, and focused on practical issues such as humanitarian evacuation, the People First campaign is distinct in that Russians and Ukrainian civil society has taken a public initiative for the first since the full-scale invasion. This is a significant development given the general stigma towards any contact with Russians inside Ukraine. As the PeaceRep Ukraine team played an important role in persuading Ukrainian civil society representatives to attend the workshop, and building confidence around the cooperation, PeaceRep’s action-orientated research activity made a concrete and meaningful contribution to the strengthening of this democratic civic space.
UN Women: / PeaceRep WPS expert input into 2024 UNSG Report	UN Women emphasised the value of PeaceRep’s sustained relationship through inputs into the UN Secretary-General's (UNSG) annual reporting on the Women, Peace and Security (WPS), especially related to women’s meaningful participation in peace processes and gender-responsive peace agreements. The PeaceRep UoE team has continued to provide UN Women with data and research insights into gender provisions in peace agreements and women’s groups. / The UNSG’s 2024 report on WPS referenced PeaceRep’s research and cited PA-X data (S/2024/671, pp.9-11), showing, among other insights, that only 26% of peace agreements in 2023 “included explicit references to women, girls, gender or sexual violence.”
UN Women: / Contributing to the development of new ‘Women in Peace Processes Monitor’	The PeaceRep UoE team has continued to provide expert WPS conceptual and methodological advice to UN Women, directly contributing to the development of UN Women’s ‘Women in Peace Processes Monitor’. During the Monitor’s design phase, PeaceRep provided inputs through tailored calls and a closed-door expert meeting on 25 October 2024, offering advice on the tracking of women’s participation in peace processes, development of the new tool, data collection, and online questionnaire. Of particular use to UN Women were discussions about how to adapt and integrate the definitions and categories of different types of gender provisions as foundational components of the UN data.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue. PeaceRep has demonstrated continued clear value to FCDO, and other actors relevant to conflict resolution and conflict response in this second full year of operation. It has exceeded log-frame targets, refined its data platform, and responded well to FCDO priorities in Ukraine Sudan, Syria and Myanmar, whilst sustaining engagement with wider international peace actors and transition process stakeholders.

## C. DETAILED OUTPUT SCORING [aim for 1 page per output]

Output Title	High quality, relevant, timely and reliable research products on peace and transition processes.
Output number:		1	Output Score:	A++
Impact weighting (%):		40%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
1.1: / # of high-quality, policy relevant, scholarly outputs on peace and transition processes published (annual).	8	17 (15 journal articles, 1 book review, 1 book chapter) – substantially exceeded / Highlights this year included Adhikari, Hodge, Bell, Siwa’s article on disaggregated mediation in European Journal of International Relations; Epple’s article in Environment and Security on peace agreements in a changing climate; and Peter and Houghton’s article on the Dayton Peace Process in International Peacekeeping. / Most journal articles are published in specialist human rights and peacebuilding journals, and highly rated journals suited to PeaceRep’s PeaceTech offer.
1.2: / # of high-quality, policy relevant, reports or policy briefs on peace and political transition processes published (annual).	24	44 (29 reports, 14 policy briefs, 1 discussion paper– substantially exceeded / Highlights among the published reports include ‘Peace Agreements in 2023: Insights from the PA-X Database’ (375 downloads). The 10 policy briefs covered diverse issues including Abiy Ahmed’s ascent to power in Ethiopia (In a Widespread War of All against All, Can Ethiopia Survive the Storm? - 494 downloads).
1.3: / # of high-quality, policy relevant, short-form publications on peace and political transition processes published (e.g. blogs) (annual).	25	62 – substantially exceeded / (Including blogs cross-posted from other sites with permission) / This number was higher than anticipated because PeaceRep found it useful for dissemination to provide short versions of research. Rapidly evolving contexts demanded quick information which necessitated a short-form publication format, including blogs on the fall of Assad in December 2024, the ceasefire in Gaza in January 2025, and political escalation and violence in South Sudan in March and April 2025.
1.4: / # of new datasets capable of supporting ongoing research, including the PA-X annual update (annual).	4	7 – moderately exceeded / PeaceRep updated the Peace Agreements Database and Dataset to Version 9 (including three distinct datasets: the main PA-X dataset, PA-X Local, and PA-X Gender), with 89 new agreements and improved search functionality, accessibility, usability and analytical depth. / PeaceRep also released the MEND dataset, the Perceptions of Peace in South Sudan survey dataset, an expanded Peace Agreement Signatories dataset (available on request), and the PAA-X actors dataset.

On Output 1, PeaceRep substantially exceeded expectations, scoring A++.

Briefly describe the output’s activities and provide supporting narrative for the score.

In addition to the publications delivered, PeaceRep researchers have outputs currently under review with leading journals and which are likely to publish during Year 5. The continued effort to balance scholarly publications with shorter reports and policy briefs is evidenced by the figures. The programme did substantially exceed its target for reports or policy briefs (1.2) and short-form publications/blogs (1.3). The high number of reports and briefs is partly a result of researchers who have used PA-X data proactively approaching PeaceRep and seeking co-sponsorship. The in-year uplift from FCDO also increased the number of products under this output. The high number of blogs is partly explained by the turbulent global context for peace and transition processes during this review period, and the trusted voice that PeaceRep researchers provide in reaction to crises, including in Syria, Ukraine, and South Sudan and in external outlets including The Conversation and The Guardian. However, the high level of outputs for both indicators also raises the question of whether this milestone was ambitious enough, as it was also substantially exceeded in the previous reporting year.

The data and technology tools produced by the PeaceRep teams, particularly the PA-X and MEND data suites, have had considerable impact on the development of the study of peace processes, and have also been cited in some of the most widely read policy reports. In academic research, PA-X has served as a source of original peace agreement text and as a quantitative dataset. As can be seen from citations of PA-X outputs from Google Scholar, there have now been more than 100 articles, books, theses and reports that have cited the data.

Additionally, PeaceRep research based on the PA-X data has been further cited in a variety of venues. For instance, a prominent example is the citing of the work of Bell and Wise (2022, local agreements paper), based on the PA-X Local dataset, in the OECD States of Fragility 2025 report. In 2024, the PA-X data have again been cited in the Report of the Secretary-General on Women and Peace and Security. PeaceRep’s data work has been at the centre of PeaceRep team's contributions to the recent issue of Accord, entitled ‘Still Time to Talk’ and edited by Teresa Whitfield, with contributions by Christine Bell, and Mateja Peter and Sanja Badanjak. The data, the data-based tracker, and the key findings from the data-driven PeaceRep research have been presented in multiple academic venues, but have also been presented at the UN Mediation Support Unit (February 2025, Q4), the FCDO annual conference in Glasgow, and with the FCDO CRD team.

The 23/24 recommendation was: ‘PeaceRep, in conjunction with the SRO and PRO, should review the milestones for Year 4, Year 5, and Year 6 to ensure they are reflective both of what the programme can be expected to deliver, and what would demonstrate a sustainable pace of delivery with emphasis on empirical and conceptual quality for the final years (by Oct 2024)’.

This revision of milestones was completed on time in December 2024. While revisions for some indicators were more realistic, evidenced by the shift to moderately as opposed to substantially exceeded, several substantive indicators have continued to be exceeded by nearly or more than 100% – these should be revised for Y6.

Output Title	Stakeholders (policymakers, practitioners, researchers) take up PeaceRep research in their work.
Output number:		2	Output Score:	A++
Impact weighting (%):		30%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
2.1: / # of written in-time research advice engagements (pro-active and re-active), tailored to HMG and other peace and transition process stakeholders (e.g. memo, policy brief, long email). (annual)	10	Substantially exceeded. 22 / Consortium partners provided 22 written briefings and ‘rapid data reports’ (drawing on PA-X) to a wide range of HMG (mostly FCDO) stakeholders and others including the ICRC and domestic actors.
2.2: / # of oral/presentation-based in-time research advice engagements (pro-active and re-active), tailored to HMG and other peace and transition process stakeholders (e.g. meetings, ‘tailored engagements’). (annual)	50	Substantially exceeded. 105 / Consortium partners provided 105oral in-time research support included meetings/presentations to FCDO, international, and domestic actors, and 4 FCDO-specific CRD quarterly update sessions on forthcoming research. / PeaceRep provided advice to the UNSG envoy to Sudan, UNMISS, the UK Envoy Special Representatives to Sudan, the UK Cabinet Office on conflict scenarios, FCDO CRD teams on Ukraine-Russia talks and possible conflict / peace talk scenarios, and FCDO country teams for Syria, Somalia, Sudan, South Sudan, Ukraine. / Beyond UK Government and UN support, PeaceRep also provided briefings to European diplomatic stakeholders including the Danish, Norwegian and Swedish embassies, and a range of EU delegations.
2.3: / # of sustained relationships between PeaceRep researchers and HMG teams (policy and/or Embassy) or other peace and transition process stakeholders characterised by regular check-ins and sharing of relevant research (annual)	4	Moderately exceeded. 9 / PeaceRep built upon and deepened nine strong relationships with the FCDO Iraq, Myanmar, Sudans Unit (including the Special Envoy), and Syria teams, FCDO Migration and Conflict Directorate (MCD), UN Women, UN Afghanistan, South Sudanese Ministry of Peacebuilding, and domestic actors in Ethiopia. These relationships are characterized by ongoing and in-time provision of empirically and conceptually founded expertise and knowledge, combined with applied analysis of live peace and conflict transitional settings. This is provided by PeaceRep experts to FCDO teams through regular check-ins and sharing of relevant research.
2.5: / Relative change in the number of PeaceRep and PA-X website visitors (annual).	Upward trend / 6%	Not met. Data inadequate. / https://www.peaceagreements.org/44% decrease in total website visitors (compared to previous year). / The annual stats reflect an artificial decrease in unique visitors and traffic for both the PeaceRep and PA-X websites due to a previously reported gap in Google Analytics (GA) data from July-November 2025 (5 months). A new UoE-wide cookie policy has also made it easier to reject cookies, leading to many users being excluded from analytics across both websites.
2.6: / Relative change in the cumulative number of PeaceRep's social media followers and newsletter subscribers (annual).	Upward trend / 6%	Substantially exceeded. / 96% growth across social and email channels (compared to 26.8% previous year). / The monthly subscription email bulletin grew from 1088 to 1185 subscribers (a 15.5% increase). / The programme is no longer active on Twitter or Facebook and is instead focusing on LinkedIn, which saw followers grow from 1,226 to 3,230 (a 163% increase). This new focus on LinkedIn was not predicted at the start of the review period, and is responsible for the overall inflation of this metric. This is not expected to continue.

Changes from the 2023/24 Annual Review: Previous output indicator 2.4: # of instances of PeaceRep research taken up and referenced elsewhere (e.g. in scholarly outputs, policy reports, Southern & Northern media outputs) was removed as part of the log frame review.

On Output 2, PeaceRep substantially exceeded expectations. This Output scores A++. The programme substantially exceeded the target for oral in-time advice (target 2.2) due to several unexpected crises resulting in numerous in-time rapid reaction requests and engagements (e.g. regarding the continued fighting in Sudan and regime change in Syria). The programme’s ability to act responsively to these moments of crisis can have valuable impact, demonstrated by the fact that this rapid advice has led to outcome level change as captured, for example, in the outcome case study on Syria. The fact this target has been substantially exceeded reflects both the sudden changes in context, and the substantial efforts of the researchers who strove to meet demand beyond expectations. Other exceeded indicators under this output, such as 2.3 on the number of sustained relationships, were arguably more predictable and whilst the target was raised following the last annual review, the progress made this reporting year is similar to last year’s delivery, suggesting that the milestone revision was conservative.

Briefly describe the output’s activities and provide supporting narrative for the score.

PeaceRep’s network of experts were able to respond to critical moments and junctures in conflicts in Sudan, South Sudan, Syria and Ukraine. Given their connections into live processes and research networks in-country, PeaceRep experts were able to provide a range of process expertise as well as thematic expertise.

Through sustained engagement prior to and throughout these shifts, PeaceRep researchers were also able to advise FCDO teams on thinking and approaches to contexts in (1) Sudan, relating to Al-Fashir and the deepening displacement and humanitarian crisis as well as conflict scenarios for a future Sudan; (2) ongoing expert advice to South Sudan teams and in-country senior FCDO figures in a moment of further election and transitional delay and relapse into violence and arrest of the opposition leader; (3) Advice calls to FCDO Ukraine team on Ukraine-Russia talks and future scenarios of unfolding conflict in relation to peace talks; (4) Critical advice immediately following the take-over in Syria and fall of Bashar al-Assad, advising the UK special representative to Syria and other FCDO Syria colleagues on approaching transitional governance dynamics under the new regime. Advice in the wake of regime change in Syria and longer-term ongoing PeaceRep Syria advice to FCDO, was described by FCDO officials as invaluable and helping to shape FCDO’s approach to Syria.

Highlights under this output include:

- In November 2024, PeaceRep hosted a visit from Catherine West MP, Parliamentary Under-Secretary of State (Indo-Pacific) and colleagues from the UK Foreign, Commonwealth and Development Office (FCDO). Minister West spoke with PeaceRep researchers about PeaceRep’s ongoing research in Myanmar, and the team shared findings and recommendations from a new policy brief on pathways ahead for Myanmar. The Minister commented on the importance of PeaceRep’s research and data-driven insights which provide “an invaluable resource for researchers and peace practitioners alike”.
- PeaceRep delivered four quarterly update sessions with FCDO CRD, spotlighting recent thematic research findings and creating a space for informal discussion of synergies between forthcoming research and policy priorities.
- PeaceRep delivered tailored oral and written in-time advice as part of a range of high-level FCDO and non-HMG engagements, including: through a series a series of calls in the wake of the take-over in Syria, in which PeaceRep experts advised FCDO Syria teams including the UK Special Representative to Syria on broader conflict patterns, localised governance realities and broader fundamental judicial and constitutional challenges; personalise oral in-time advice and briefing to Special Representative for South Sudan; PeaceRep Syria expert briefed the EU mission to Syria discussing the latest developments following the take-over; PeaceRep South Sudan expert respectively debriefed the EU delegation to South Sudan on the conflict and peace process, and the EU Special Representative for the Horn of Africa team on the Sudan dialogue.
- PeaceRep continued to build and maintain strong and sustained relationships on priority geographies, including with FCDO Iraq, Myanmar, Sudans Unit (including the Special Representative for South Sudan), and Syria teams, FCDO Migration and Conflict Directorate (MCD), UN Women, UN Afghanistan, South Sudanese Ministry of Peacebuilding, and domestic actors in Ethiopia. These relationships are characterised by regular check-ins and sharing of relevant research. Feedback from FCDO stakeholders interviewed as part of the review underlined the value they place on these relationships, citing PeaceRep’s country-level expertise, local networks, academic credibility, openness to discussion, convening power and neutrality amongst other peace actors as key advantages of the programme, contributing to the quality of PeaceRep’s support.
- PeaceRep experts submitted written evidence to the 2024 UK Ministry of Defence Strategic Defence Review (PeaceRep LSE CCRG) and the 2025 UK International Development Committee’s Parliamentary Inquiry on Women, Peace and Security (PeaceRep UoE).
- PeaceRep researchers gave interviews to major media outlets including the BBC, TRT World, NPR, CNN, The Guardian, The Times, Sky News, ITV News, Washington Post, Al Jazeera, The National, Voice of Islam UK Radio, Syria TV, and more.

The data for indicator 2.5 suggests that visitors to the PeaceRep website have substantially decreased. However, when compared on a monthly basis (rather than annual), and excluding the months of missing Google Analytics (GA) data, traffic rates for visitors and page views have actually increased. As a crude statistical comparison:

Y3 = 7869 visitors over 12 months, averaging 656 per month.
Y4 = 6825 visitors over 7 months, averaging 975 per month (48% increase).

Y3 = 48,697 views over 12 months, averaging 4,058 per month.
Y4 = 32,741 views over 7 months, averaging 4,677 per month (15% increase).

The decrease in recorded traffic can be attributed to several factors, including the GA outage and new cookie policy mentioned above, as well as the switch to a new website, the systematic removal of bots (which it is now thought may have inflated the Y3 data) as part of the Version 9 launch, and the reindexing of the site with Google search. PeaceRep also recorded data for the old PA-X site until April 2025, logging an additional 10,713 visitors and 15,032 views not included in the total count due to potential overlap in recorded traffic.

The PA-X and UoE communications teams have invested significant effort into tracing and resolving these issues with UoE information Services, and going forward Y5 data should be a more reliable indicator of site visits. Data from outcome indicator 1.3 shows that PA-X has substantial uptake in policy publications and scholarly articles. The quality of impact outweighs the concerns regarding the number of visits to the website.

Output Title	Enhanced research capacity, particularly in the Global South
Output number:		3	Output Score:	A+
Impact weighting (%):		30%	Weighting revised since last AR?	N

Indicator(s)	Milestone(s) for this review	Progress
3.1: / # of Southern-based or displaced researchers involved in research projects, as evidenced by their active engagement, e.g. through co-authorship and presentations at events.(annual)	30	Substantially exceeded. 55 / Events: 21 / Co-authorship: 9 / Online learning: 25 / This year PeaceRep facilitated 5 co-authorships with researchers based in Syria, 4 with researchers based in Juba, South Sudan, 1 in Ecuador and 1 in Colombia. / PeaceRep facilitated 14 experts from the Global South to present at the high-level 2024 Edinburgh Dialogue on Independent Institutions and the Women Constitution Makers Dialogue. In September 2024, PeaceRep hosted the Conflict Resolution Society (CRS) Annual Conference and supported 7 scholarships for attendees from ODA countries. / PeaceRep welcomed 25 participants from the Global South across two PeaceRep online short courses, for peer-to-peer networking and knowledge exchange. (Conflict Transitions in the Eastern Mediterranean Region / Skills-building for Working in Conflict Transitions)
3.2: / # of new PeaceTech tools and visualisations for complex problems in FCAS, tested and disseminated, including as an advocacy tool (annual)	3	Moderately exceeded. 5 / PeaceRep launched the PA-X Tracker Globe, actor network mapping, and three tools on third parties to peace agreements: Russia and China and UK. / Additional tools are on track for delivery in Y5 including a gender scrollytelling visualisation of PA-X Gender and the Perceptions of Peace in South Sudan dataset for 2025.
3.3: / # of new PeaceTech tool methodology write-ups for complex problems in FCAS disseminated (annual)	2	Met. 2 / These reports focused on the research methodology underlying the programme’s PeaceTech innovations.

Briefly describe the output’s activities and provide supporting narrative for the score.

On Output 3, PeaceRep moderately exceeded expectations, scoring A+.

Highlights under this output include:

- At the 2024 CRS conference, PeaceRep funded scholarships for 7 participants from ODA countries (including Brazil, Ethiopia, Ghana, India, Mexico, Nigeria, South Africa), enabling scholars from underrepresented regions to attend and contribute to the conference. Based on feedback after the conference, recipients credited the scholarships for enabling them to travel to the conference; build their networks and make connections with other scholars; present their research; and exchange knowledge, approaches, and expertise with colleagues from diverse contexts across the globe.
- In November 2024, International IDEA welcomed participants from conflict-affected contexts to the eleventh annual Edinburgh Dialogue at Edinburgh Law School, and participants from conflict-affected contexts to the sixth annual Women Constitution-Makers' Dialogue in The Hague.
- The programme convenes a group of local researchers and transition process stakeholders in one of its focus countries to inform FCDO policy and interventions. In South Sudan and Syria, it runs complex data collection efforts, and co-publishes with local researchers.
- In addition to southern-based researchers involved in the programme in these ways, the programme’s online short course portfolio enrolled 15 southern-based participants during this review period.

## D: VALUE FOR MONEY

Key cost drivers and performance

The key cost drivers of the PeaceRep programme remain the same as captured in the Business Case, namely costs associated with staff salaries, data storage costs and duty of care for in-country researchers.

VfM performance compared to the original VfM proposition in the business case

The VfM performance, when compared to the original proposition in the business case remains consistently strong. The strategy for achieving value for money focuses on delivering high-quality research that has real-world impact, using realistic resources and ensuring effective, equitable delivery.

The following examples for each of the four VfM indicators provide a balanced analysis of the programme’s cost effectiveness.

Economy	Reduction in travel costs are made wherever possible across the programme. For example, Coventry researchers saved £3,000 in travel costs through participation in invited events where the hosts have covered international travel. / The PeaceRep Ukraine team has continued to collaborate with FES, Clingendael Institute and the Kyiv School of Economics to host the annual Ukraine Recovery Conference side event in May 2025. By working collaboratively, significant savings were generated, including support with travel and event costs, and the costs of producing two research papers on critical raw materials and lessons from Bosnia’s reconstruction, which increased the overall value of the event for the practitioners who attended (see outcome case study). / The University of Edinburgh secured free access to its ELM platform, enabling PeaceRep staff to use advanced language models for research and analysis without incurring additional costs. This arrangement saved approximately $1,500 for three staff members during the review period and ensured sensitive data was handled securely within the university’s infrastructure, reducing both financial and data security risks. / Potential costs around peer reviewing continues to be offset by drawing on PeaceRep’s wide network of expertise. UoE allocate up to 10 hours per output for the expert peer review, resulting in quantifiable savings of up to £2,000 per output for the PeaceRep programme, but also ensuring that PeaceRep partners receive critical analysis and feedback from highly qualified experts, including for gender sensitivity, without incurring any financial burden. / Open Access costs are usually £1,000 per article. Institutional agreements covered 11 articles this reporting year, saving £11,000, which could be used elsewhere in the programme.
Efficiency	Coventry University’s partnership with FES South Sudan, established now for three years, has brought experienced and specialist researchers to PeaceRep’s core team. This enabled £36,000 additional funding plus enabled closer collaboration with the UN Mission in South Sudan. It resulted in economy savings including £10,000 on the year’s local transportation costs as well as a continued focus on climate change and conflict. The partnership has improved the uptake of the research with national and multinational stakeholders and bilateral partners. / At LSE IDEAS, the Somalia team have worked to combine travel arrangements for PeaceRep research with those that can be funded from other collaborations. For example, the team undertook two combined visits to Nairobi for discussions held with FCDO, World Bank, ECHO, Danish, Swedish and Norwegian Embassies, thus avoiding multiple long-haul trips from the UK, which are significant in time and cost in real terms. By making these economic savings, efficiency is improved as savings can be repositioned into meeting direct research costs, and have the added benefit of wider collaborative engagement.
Effectiveness	The effectiveness of PeaceRep’s outputs are illustrated by the outcome case studies and the fact that the programme has moderately exceeded expectations of progress towards its intended outcome: “Conflict Resolution processes and practice are better informed by evidence’”. Examples of where outputs have been effective in delivering outcome level contribution include: / FCDO Ukraine collaboration - PeaceRep’s expert roundtable and research on reconstruction in Ukraine directly enhanced FCDO staff knowledge, facilitated international collaboration, and shaped strategic thinking on recovery and reconstruction. / FCDO Syria – Existing research and rapid in-time advice provided FCDO officials with evidence-based lessons and analysis following the fall of the Assad regime. These were effective in supporting both immediate to long-term thinking, with value for money through responsive expert support. / FCDO: Conflict Resolution Department / Lebanon - A rapid response paper on Lebanon ceasefires was crucial for supporting FCDO staff understanding and shaped subsequent work on UNIFIL’s role, demonstrating effective, timely support for crisis response and value for money through targeted expertise. / Somalia: PeaceRep research informs ECHO funding and do-no-harm strategies - PeaceRep’s research and collaboration with ECHO Somalia informed humanitarian funding strategies and anti-corruption mitigations. / South Sudan: PeaceRep research informs domestic debates and electoral support strategies - The Public Perceptions of Peace Survey provided an evidence base that shaped electoral support strategies and legislative preparedness, with continued impact on planning despite election postponement. / Sudan: Supporting multimediation in the current conflict -Long-term, adaptive engagement promoted multimediation and supported dialogue in Sudan’s transitional landscape. / Syria: Informing UNDP Syria strategy and programming - PeaceRep’s research and engagement with UNDP Syria shaped a funded project on value chain development, informing strategic design and programming for economic and social integration. / Ukraine - A workshop organised by PeaceRep led to the formation of the “People First” advocacy coalition, strengthening civil society links and advocacy around negotiations. / UN Women: PeaceRep WPS expert input into 2024 UNSG Report - PeaceRep’s data and research on gender provisions in peace agreements used in the 2024 UNSG’s annual report on WPS, supporting UN Women’s advocacy and monitoring of international progress on the WPS agenda.
Equity	PeaceRep hosted the 2024 CRS Conference at Edinburgh Law School in September, and distributed approximately £20,000 as ODA scholarships to speakers. Following the conference, the CRS committee contacted recipients to ask about their experience of being a 2024 Scholar and any ongoing benefits from being able to attend and present at CRS – such as new collaborations or new research avenues. Feedback from scholars was very positive, detailing new collaborations, authorship opportunities, and approaches to research that draw on PeaceRep’s concepts and data. / PeaceRep’s Myanmar research focuses on emerging modes of dialogue and peace talks in Myanmar, including understanding what such new modes mean for the Women Peace and Security agenda, both in terms of norms and practices. / The majority of PeaceRep’s core research team at the University of Edinburgh are women (59%), and women hold the majority of senior leadership roles (75%). / At LSE IDEAS, women comprise approximately 30% of the Syria partner Local Administrations Council Unit’s (LACU) in-country researchers and data collectors. All LACU activities, such as focus group discussions, workshops or key expert interviews have a minimum and mandatory 35% quota for participation of women. 20% of all LACU’s in-country staff are IDPs from different areas in Syria. / The authors of International IDEA’s key outputs from the Edinburgh Dialogues and Women’s Constitution Makers’ Network are all women. / The PeaceRep Ukraine team has built a participatory civic network of 118 activists spread across 40 different local territorial communities (‘hromadas’) feeding in data and analysis on local conditions. By focusing the research method on developing inclusive approaches to knowledge production, the underpinning approach of this work is so that it is ‘with’ and not simply ‘on’ communities, thus getting a more accurate picture, but also more equitable engagement into the communities and the applicable activists.

*Assessing cost effectiveness at Outcome level:

It was agreed in 23/4 that a revised approach to assessing cost effectiveness will be applied in future reviews from this year, using a qualitative rating to assess each outcome case study against a composite indicator:

“Peace research influences policy or operations of UK, other international or domestic actors involved in conflict resolution, such as UN, regional bodies, and parties involved in conflict resolution”.

An assessment of case studies for this current review is as follows:

Case study	Composite effectiveness rating 24/25
FCDO Ukraine	Met
FCDO Myanmar	Met
FCDO Syria	Moderately Exceeded
FCDO Conflict Resolution Department	Met
Somalia: PeaceRep research informs ECHO funding and do-no-harm strategies	Met
South Sudan: PeaceRep research informs domestic debates and electoral support strategies	Moderately Exceeded
Sudan: Supporting multimediation in the current conflict	Met
Syria: Informing UNDP Syria strategy and programming	Met
Ukraine: Fostering and informing Ukraine-Russia civil society exchange and advocacy	Met
UN Women: PeaceRep WPS expert input into 2024 UNSG Report	Met
UN Women: PeaceRep contributed to the development of new ‘Women in Peace Processes Monitor’	Met

Overall cost effectiveness

PeaceRep has consistently scored well against its outputs, which in turn have influenced the programme’s outcomes, which justify FCDO investment. It has been noted that PeaceRep has a ‘cumulative impact’- testimonials both externally and internally have spoken of the value of PeaceRep’s research and advice over the long-term, with the influence of the programme building over time. Several of the examples captured in the outcome-level case studies in Section B, such as on Syria, South Sudan, and Myanmar, support this.

The recommendation to begin gathering evidence of impact case studies will support PeaceRep to better capture the pathways from outcome to impact in next year’s Annual Review.

E: RISK

Overview of risk management

The current programme risk rating is moderate. This moderate rating has remained in place over this reporting year, and risks remain well managed through effective mitigation and tracking by the UoE, as well as regular engagement and correspondence on risk with FCDO, so that any risks indicated outside of appetite can be quickly mitigated to an acceptable tolerance.

The risk ratings post mitigation are:

Strategy & Context	Policy and Programme Delivery	Public Service Delivery and Operations	Reputational	Financial & Fiduciary	People	Safeguarding	Overall
Major	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate	Moderate

Strategy and Context (Major, stable trajectory) - PeaceRep operates in areas and environments that are often volatile. Sudden escalations, regime changes, or shifts in alliances can undermine research relevance, access to field sites, or the safety of partners and staff. Examples of this include PeaceRep researchers working in South Sudan. PeaceRep continuously monitor these risks and ensure that they have regular communication with staff working in these environments and that protocols are in place to ensure their safety. For example, when violence escalated in South Sudan, UoE were informed of the risk by the downstream partner, work was paused and the safety of researchers was made the primary concern while the respective situations were evaluated.

Policy and Programme Delivery (Moderate, Stable trajectory) A key risk to the programme in this reporting year was donor uncertainty and potential fluctuation of ODA funding. In 2024-25 the HMG Spending Review meant that the 2025-26 budget was not confirmed until after the start of the financial year. Regular communication between FCDO, UoE, and partners kept everyone informed and the budget has now been confirmed. Another risk to the programme’s policy and delivery impact is the potential weakening of its long-term legacy if synthesis work is not effectively completed before the end of the programme. Without robust synthesis, the ability to draw out and communicate cross-cutting insights from the programme’s research portfolio may be limited, reducing its usefulness for policymakers. This risk is being actively mitigated through ongoing synthesis activities and regular engagement with FCDO to ensure alignment on priorities and timelines. PeaceRep has a plan for programme synthesis in Year 5, with consortium partners sharing evidence and publishing key findings to highlight PeaceRep’s main contributions.

Reputational (Moderate, Stable trajectory): There are reputational risks associated with public accusations, disinformation or the misuse of data which may impact on the delivery of PeaceRep’s research. If the research outputs of the programme are misinterpreted, given the connection to conflict and peace building this may have a detrimental impact on FCDO and UoE’s reputation, and possibly have HMG implications given the political sensitivities around conflicts around the world. To mitigate this risk, UoE closely monitor news sources around the use of outputs and responds to correct them if required. The limitations of the research and data are also clearly stated, which limits the disinformation through clear articulation of capacity and use. Though UoE and FCDO go to great lengths to ensure the data use is clear, a degree of toleration has to be accepted, given the scope of PeaceRep’s work, especially interpretation of the PA-X Tracker, which may incur current and historical scrutiny, and thus reputational impact.

Financial & Fiduciary (Moderate, stable to descending trajectory): Uncertainty over budgets remained the major fiscal risk for the programme, with delayed budget confirmation from FCDO leading to a risk of underspend. Another fiscal risk is around partners underspending because of logistical contingencies or access issues associated with conducting field work in conflict-affected contexts. Management and financial teams are in regular contact with partners and FCDO to minimise the associated underspend risks. The programme has met its spending targets with accuracy over this reporting year, submitting forecasts and revisions in good time to mitigate potential underspend.

Safeguarding (Moderate, stable trajectory): A key risk for any research programme of this size is having inadequate safeguarding measures in place. Without suitable safeguarding protections, the risk of sexual abuse, exploitation and harassment (SEAH) increases, given possible power dynamics in conflict affected locations, as well as power imbalances between junior and senior academics. UoE has a named Safeguarding Officer for the entire PeaceRep consortium including downstream partners and considers safeguarding alongside duty of care responsibility, research ethics protocols, and risk assessments. PeaceRep is guided and supported by the Edinburgh Law School and UoE policies which include Protection of Children and Protected Adults, Modern Slavery and Whistleblowing as well as FCDO’s Reporting Concerns policy. UoE also holds all downstream partners to a high standard on safeguarding. Contact details are posted clearly on the programme website and each PeaceRep partner has similar robust measures in place. A recent Due Diligence Assessment on UoE, conducted by FCDO (completed August 2025), interrogated the communication between UoE and downstream partners on safeguarding, given no incidents had been reported to UoE from downstream partners in the last 3 years. A follow-up recommendation for UoE to restate and clarify expectations on safeguarding with downstream partners has been agreed and captured as part of the DDA report.

People (Moderate, stable trajectory): The primary risk in the people category is duty of care of researchers due to political instability and ongoing violent conflict in case study countries, such as Ukraine, Sudan and Myanmar. This includes both physical safety concerns, as well as wider security risks, such as a researcher becoming targeted through their association with the project. The PeaceRep staff working in these regions are sensitive to these risks and have taken action when needed. For example, in March 2025, violence in South Sudan led PeaceRep to immediately pause work, which was only continued when the safety of all researchers had been confirmed.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Over the course of this reporting year FCDO and PeaceRep teams have met monthly to discuss programme performance as well as a range of programme delivery topics such as the outputs/quarterly deliverables, key risks, downstream partners, and financial issues.

Forecasts and financial information are provided to FCDO swiftly when required, and accuracy between forecast and expenditure has been strong. Out of a total budget of £4.5 million in FY 2024/25, the programme spent £4,498,802. The programme had a small spend variance of 1% over the reporting year which is in line with FCDO requirements. This near-full utilisation indicates strong alignment between planned activities and delivery on the ground. Over the course of this reporting period the UoE has been quick to engage FCDO on a range of issues and topics to improve the delivery of the wider programme, as well as providing detailed and thorough cost analysis and reports, which were utilised in preparing this annual review.

Delivery Performance - The programme has maintained a strong delivery performance over the past year. In the previous reporting year, PeaceRep has consistently met or exceeded their Outcome and Output milestones set out in the log frame. The evidence shown across the Outcome and Output sections in this review demonstrates PeaceRep’s ability to produce research that directly or indirectly influences policymakers in FCDO, HMG and other key stakeholders beyond.

Financial Performance - The review period covers July 2024 to June 2025 with four payments processed throughout the year for ODA expenditure.  During the review period, UoE has responded constructively to in-year budget adjustments, working with partners to provide timely, revised forecasts within a reasonable margin of flexibility.

Quarterly and annual reports from UoE have been submitted on time, and to a high standard, giving FCDO a clear picture of the progress and fiscal implications of the programme. Expenditure has been in line with workplans and payment schedules.

Financial Statements and Budget Tracking:

The programme’s financial status remains in line with the approved budget. Where necessary to accommodate changes in direction of the research funded across the programme, PeaceRep has communicated this need to FCDO and provided full transparency, allowing FCDO to consider options and make decisions such as agreeing Accountable Grant Amendments or deciding that unfortunately it is not possible to make changes to the budget due to budget uncertainty.

UoE has confirmed programme information on the International Aid Transparency Initiative (IATI) is up to date: Details of income, expenditure and disbursement for Year 4 has been uploaded to IATI and can be located using IATI identifier: GB-UKPRN-100007790 and Transaction Receiver Organisation Activity ID: FCDO Peace and Conflict Resolution Evidence Platform (PEACEREP).

The programme has one asset, purchased in Y3: the Owl Labs video conferencing system, has a total value of £1,340.

ODA
	Q2 (Jul-Sep 24)	Q3 (Oct-Dec 24)	Q4 (Jan - Mar 25)	Q1 (Apr - Jun 25)	Total to date
Forecast	1,131,465	1,136,070	1,280,648	991,648	4,539,831
Actual spend	1,019,861	1,038,332	1,585,356	4,498,802	4,498,802
Variance	-10%	-9%	24%	-14%	-1%

** Q1 invoice has not been formally submitted at the time of this review.

Expenditure for the review period was 99% of the original forecast, with only a 1% variance. This reflects robust financial management and strong alignment between planned activities and actual delivery. Quarterly variances were mainly due to staff vacancies and sub-contractor contracts not being finalised in time to submit invoices.

Audited financial statements for UoE covering the year ending July 2024 were published in March 2025, with no issues highlighted. A programme specific audit has not yet been delivered. The absence of a programme specific audit was highlighted during the process of last year’s Annual Review. It was agreed between FCDO and UoE in September 2024 that UoE would commission a programme specific audit covering the period from the start of the programme to the end of March 2024. A subsequent annual audit would then be commissioned for each financial year that the programme is running, as per the requirements in the grant. However, at the time of writing this Annual Review in August 2025, a programme specific audit had not yet been received by FCDO. As a result, the programme is not currently compliant with audit requirements. UoE has advised that the programme specific audit is complete with the paperwork near finalised and is due to be submitted to FCDO imminently. Future annual audits should be kicked off at the end of the financial year and completed well ahead of the Annual Review.

G: MONITORING, EVIDENCE AND LEARNING

Monitoring and Evaluation

Regular engagement with delivery partners, quarterly Steering Committee meetings, and bi-annual International Advisory Board (IAB) meetings have been key features of the programme’s MEL approach. The IAB provides an independent monitoring mechanism to the programme, as well as an expert resource that the programme is able to draw upon. Regular meetings of the PeaceRep Senior Leadership Team (SLT) and between the FCDO and PeaceRep covering a range of topics provides space for focused discussion on progress, challenges, and emerging risks as well as substantive research ideas and concepts. These meetings have also provided space for discussion around strategic direction of research and the current state of play with ongoing projects, finances, and briefing of seniors in FCDO. Monitoring of programme delivery against the output milestones in the programme log frame is led by the PeaceRep programme management team at UoE. Monitoring of outcome delivery is also led by UoE, with support from the programme PRO, through structured interviews with key programme stakeholders. The institutional leads at consortium partner organisations beyond UoE additionally monitor outputs and outcome-level delivery. PeaceRep’s online short courses are subject to regulation by Edinburgh Law School’s Board of Studies and participant feedback loops, and all PeaceRep research is subject to rigorous institutional ethics approvals. All scholarly work published in academic journals undergoes rigorous and blind peer-review. There is no formal evaluation planned for this programme, however it will be part of institutional REF submissions and subject to the end of programme review.

Evidence

PeaceRep research is conducted by academics and practitioners who are governed by their institutional requirements and best practice in their fields. High academic standards underpin every aspect from research questions and design, to methods and ethics, to analysis and write up. Research is subject to rigorous peer review, both internal and as part of journal processes. Researchers are now in the middle of a REF cycle, so all their academic outputs are being graded which provides an additional level to this process.

The programme's outputs are designed and delivered with policy audiences in mind - as evidenced by the diversity of output types and, critically, engagement activities. The impact studies and in-time advice examples evidence how this is trusted, but how this is also changing approaches and informing actions.

PA-X is currently the most expansive collection of peace agreements data in the world. Now in Version 9, PA-X contains 2,144 peace agreements, found in more than 170 peace processes between 1990 and 2024.

Learning

PeaceRep keeps full records of the engagements different teams of FCDO and across HMG, UN (at Secretariat and field-levels), other governments/governmental organisations (such as the US State Department), and uses feedback from these meetings to inform future PeaceRep research and PeaceTech priorities. PeaceRep also provides dedicated briefing sessions to FCDO teams and contributes to FCDO events, such as the 2025 Conflict Conference, and provides bespoke training to FCDO teams on demand. Examples of engagements during this review period are included above and are provided in full as part of each quarterly report to FCDO.

PeaceRep regularly discusses and documents lessons learned across the consortium in SLT and Steering Committee meetings (September 2024, February 2025, May 2025). Research highlights and key concepts from the programme’s fourth year were shared with the International Advisory Board in November 2024 and May 2025, alongside significant discussion on plans for synthesising the programme’s research during year 5, and ongoing discussion of sustainability strategy. PeaceRep’s SLT regularly feeds lessons learned into the annual programming and consortium governance processes.

Quarterly catchups are held with a range of FCDO teams, as well as regular engagements with FCDO and non-FCDO stakeholders in conflict-affected countries. Key lessons identified over the course of the reporting year have been captured in Section A of this Annual Review and translated into recommendations as stated above.

Date of last narrative report	08/08/2025 (2025/26 Q1 report)	Date of last audited annual statement	** March 2025 (audit for year ending July 2024) (University of Edinburgh)

** A programme specific audit is underway but at the time of writing has not yet been received by FCDO.

This annual review was completed by the PRO and the Research Manager from June-August 2025 with supporting evidence provided by the UoE, and with oversight of the SRO. A total of 16 interviews were conducted to support this review: 11 interviews were conducted with FCDO stakeholders, including with UK-based policy teams, teams at Post, and FCDO research analysts. A further 5 external interviews (3 with downstream consortium partners and 2 with international organisations) were conducted as part of the triangulation process.