Annual Review

Title: Fighting Corruption Globally (FCG)
Programme Value £ (full life): £36,000,000 GBP		Review date: 26/07/2025
Programme Code: 301267	AMP start date: 24/07/2023	AMP end date: 30/06/2028

Summary of Programme Performance
Year	2024	2025
Overall Output Score	A	A
Risk Rating	Moderate	Moderate

DevTracker Link to Business Case:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-301267/documents
DevTracker Link to results framework:	https://devtracker.fcdo.gov.uk/programme/GB-GOV-1-301267/documents

 A. SUMMARY AND OVERVIEW

Description of programme

The FCG programme was launched in July 2023 and is a 5-year programme with a total value of £36m. FCG addresses transnational grand corruption by supporting efforts to put in place the tools and capabilities to prevent corrupt actors from stealing and moving significant financial resources around the world, and to hold them to account when transnational corruption does occur.

The programme does this by:
- Enabling governments, civil society, the private sector and law enforcement to use high quality beneficial ownership data to prevent or identify cases of grand corruption;
- Improving the effectiveness of international law enforcement to increase the volume of recovered assets; and
- Equipping the Foreign, Commonwealth and Development Office’s (FCDO) country networks, FCDO and other actors with evidence and learning for effective policy and programming on anti-corruption.

The programme funds seven partners to achieve these aims:
- The International Anti-Corruption Coordination Centre (IACCC) was established by the UK in 2017 and is hosted by the National Crime Agency (NCA). The IACCC is a collaboration of law agencies globally that work together to support developing countries to trace and recover stolen assets.
- The International Centre for Asset Recovery (ICAR) at the Basel Institute on Governance works with countries around the world to strengthen their capacities to recover illicit assets.
- Transparency International (TI) and the Organized Crime and Corruption Reporting Project (OCCRP) under a new joint grant which combines the unique strengths of investigative journalism and civil society advocacy in a consortium that exposes corruption and facilitates action by government, law enforcement, and international organisations. TI is a global movement working in over 100 countries against corruption, providing research and advocacy. OCCRP is a network of investigative journalists that seeks to spread and strengthen investigative journalism globally and expose crime and corruption so citizens can hold power to account. This project started February 2025.
- Open Ownership (OO) delivers evidence, expertise, technical tools, and tailored advice to countries implementing beneficial ownership transparency reforms to drive the global shift towards transparency and accountability in company ownership.
- The U4 Anti-Corruption Resource Centre is a web-based resource centre that studies the causes and effects of corruption on development. Through publications, training, workshops and a helpdesk, U4 supports development practitioners to address corruption challenges in their work.
- The International Monetary Fund (IMF) Anti-Money Laundering/Combatting the Financing of Terrorism (AML/CFT) Thematic Fund is a multi-donor trust fund led by IMF staff in the Legal Department that provides technical assistance training and related research to mitigate macro-relevant consequences of weak AML/CFT frameworks, helping countries address Money Laundering, Terrorism Financing and related financial integrity issues.
- The World Bank (WB) Governance & Institutions Umbrella Trust Fund (G&I UTF) is a multi-donor trust fund led by WB staff in the Global Governance Practice that seeks to bolster government effectiveness and accountability through facilitating knowledge and innovation, data and analytics, operational work and partnerships.

Partner	Funding provided from start of programme to March 2026 (£)
International Anti-Corruption Coordination Centre (IACCC)	7,614,835
International Centre for Asset Recovery (ICAR)	2,709,120 (core), 1,005,019 (project)
Transparency International (TI) and the Organized Crime and Corruption Reporting Project (OCCRP)	2,673,000
Open Ownership (OO)	2,760,246
U4 Anti-Corruption Resource Centre	690,000
International Monetary Fund (IMF)	2,000,000
World Bank (WB)	1,000,000

Until March 2025, FCG also provided funding for a specific project with OCCRP on professional enablers. This project is now closed but its valuable work is being taken forward in the new joint grant with Transparency International and OCCRP. Please see below for more detail.

During this reporting period, FCDO has been responding to the priorities of a new government. In November last year, the Foreign Secretary launched a personal campaign to tackle illicit finance. The primary aim is to strengthen the UK’s domestic defences and provide international leadership to ensure dirty money has nowhere to hide in the UK or overseas. As a centrepiece of the Foreign Secretary’s campaign, the UK will host a Countering Illicit Finance Summit. Priorities for the campaign cut across multiple projects under this programme, including beneficial ownership transparency, reducing development harms and accountability.

Over the past year, significant changes to the global landscape have occurred. In February, the UK Prime Minister took the difficult decision to increase spending on defence to 2.5% of GDP from 2027, funded by reducing the UK’s Official Development Assistance (ODA) and reinvesting it into defence. The ODA budget will be gradually reduced to the equivalent of 0.3% of GNI by 2027. Reductions in ODA spend in other countries have also been taking place within the last year, including some change in priorities. The UK’s decision to reduce its ODA took place soon after the new US administration’s decisions on USAID and international development, resulting in large-scale budget cuts across governance efforts, including on anti-corruption work. These cuts affected some of the partners in the programme, to varying degrees. FCG supported partners to readjust their budgets and programmes of work, providing flexibility to maintain impact.

Summary supporting narrative for the overall score in this review

We have scored the Fighting Corruption Globally (FCG) programme an A (met expectation) for this annual review. The programme continues to deliver excellent results through its various partners, with most moderately or substantively exceeding expectations. Two delivery partners are falling short of meeting expectations (IMF and World Bank), partly due to delayed timelines. We have selected this score as a midpoint between all partners, recognising progress on the impact and outcome indicators that has been achieved this year.

Open Ownership, U4, OCCRP, ICAR and IACCC continue to deliver impressive results. Open Ownership has successfully delivered further outputs following a grant uplift this calendar year. ICAR successfully completed a separate project under the same grant focusing on Zambia, following which discussions have begun about a new project in Bangladesh. U4 has completed its mid-term evaluation, a significant opportunity for U4 and all donors involved. One of our most innovative projects, delivered with OCCRP, closed in March with significant lessons being taken straight into a new joint grant with Transparency International and OCCRP. IACCC continue to display leadership in law enforcement, with expanded membership and clear impact.

Major lessons and recommendations for the year ahead

Since the completion of the last Annual Review, we have established coordination channels for each project, including regular internal and partner discussions; and proactive coordination between policy leads and programme managers. Programme management indicators have also been improved, especially the assessment of project-level risks. Following positive feedback from partners, this approach will be strengthened further over the coming year.

A key lesson reinforced this year is the value our partners place on FCDO flexibility in a dynamic, fast-changing world. Delivery partners can flex in response to changing needs and moving timelines, which ensures ODA funding remains strategic and targeted. Regular partner engagement is essential for this approach, with IFAC policy leads and programme managers fully appraised of risks, opportunities and lessons.

Recommendations for the year ahead

Recommendation 1 – Review the programme theory of change to ensure it remains valid (by the end of September 2025).

Recommendation 2 – As two-year log frame indicators expire, refresh log frame indicators for next three years of programme (by the end of September 2025).

Recommendation 3 – Ensure FCDO supports coordination with and between partners working on related issues to align delivery as much as possible.

Recommendation 4 – Work with the World Bank to strengthen programme management and improve delivery.

Recommendation 5 – Commission mid-term evaluation for the programme which will also consider how to take forward formal learning opportunities by programme partners (MTR contracted by Spring 2026).

Recommendation 6 – Explore closer coordination within FCDO where multiple departments or posts provide funding to the same partner (by the end of September 2025).

## B: THEORY OF CHANGE AND PROGRESS TOWARDS OUTCOMES

Summarise the programme’s theory of change, including any changes to outcome and impact indicators from the original business case.

The Theory of Change in the Business Case is set out below. While budget uncertainty has limited our ability to agree longer-term impact indicators, a review of the Theory of Change will be undertaken prior to the mid-term evaluation.

The overall impact statement for FCG is “Developing countries, affected states and global financial centres act more robustly to prevent and respond to transnational grand corruption”. This will be measured by an improvement (reduction) in Basel AML Index ranking for specific countries receiving FCG support.

The outcome statement is “Reduced incentives and opportunities for grand corruption through enhanced transparency and accountability measures (nationally & internationally), based on more robust evidence and enforcement of international standards”. This will be measured by two indicators: the number of suspects charged with the support of the IACCC; and the number of countries making commitments or progress in BOT reforms that are supported under this grant.

There are three outputs:
- Greater, better quality BENOT globally driven by better data standards, coordinated and tailored technical assistance and stronger evidence and policy.
- Greater capability amongst national agencies drives clear case progression in a stronger international policy environment.
- Stronger evidence base provides a platform for better policy and programming on effective responses to grand corruption.

Implementation experience of partners supports the original programme design, with the three outputs listed above remaining crucial steps to achieve the desired impact and outcome. However, as we near the mid-point of the programme, we will conduct a full review of the Theory of Change prior to the mid-term evaluation to ensure it is adequately responding to the changing world environment. This will be a recommendation of this Annual Review and will feature in the mid-term evaluation contract.

We will consider the ‘Leave no one Behind’ agenda for monitoring data, evidence and learning. We are unlikely to be able to disaggregate information by age and disability as the programme works with institutions rather than direct beneficiaries, however we are working with partners to develop indicators for equity which will provide some insight into the impact on protected characteristics.

Describe where the programme is on/off track to contribute to the expected outcomes and impact. What action is planned in the year ahead?

Impact and Outcome Log frame Indicators

Impact	Indicator	2025 Milestone	Progress
Developing countries, affected states and global financial centres act more robustly to prevent and respond to transnational grand corruption	Improvement (reduction) in Basel AML Index score for selected countries receiving FCG support, where data is available: / Countries / Malawi / Kenya / Moldova / Zambia / Nigeria	Of countries with available data, 50% see improvements in score from 2024-2025	From Dec 24 Basel data, 5 countries had available data on score changes and 3 countries (60%) had improved their score. / Countries FY24 FY25 Improve? / Malawi 5.63 5.45 Yes / Kenya 6.95 6.87 Yes / Moldova 4.59 4.65 No / Zambia 5.70 5.34 Yes / Nigeria 6.72 6.85 No
Outcome	Indicator	2025 Milestone	Progress
Reduced incentives and opportunities for grand corruption through enhanced transparency and accountability measures (nationally & internationally), based on more robust evidence and enforcement of international standards	Number of suspects charged with the support of the IACCC	2	1 suspect was charged in FY24/25. 2 suspects that were charged in FY23/24 were convicted during this financial year, however this is not tracked under the log frame. / Grand corruption cases typically take 5-7 years to come to fruition. The timeframe for these results assumes success in cases taken on by IACCC since it became operational in 2017 (based on long-term HMG funding). The outcome also relies on partner law enforcement agencies updating the IACCC on the outcomes of their investigations.
	Number of countries making commitments or progress in BOT reforms that are supported by OO	10	This is a two-year target: Ten countries have made commitments and tangible progress in advancing beneficial ownership transparency reforms under this grant since July 2023. Progress this year has been made in Zambia, Botswana, Mexico, Lesotho, Mauritius, Mozambique and Sri Lanka.

The impact indicator for the selected countries receiving cross-cutting support from FCG components is on track. Of the 5 countries selected for assessment, 5 now have available data on changes to their Basel AML Index and 3 (60%) have seen an improvement in their index for FY25.

The countries that did not see a reduction in their Basel AML Index (Moldova, Nigeria) saw minor increases in the AML Index which indicates the level of risk of Money Laundering/Terrorist Financing (ML/TF). The level of attribution to FCG is unknown and likely smaller at the start of the programme, however, we assume, particularly over the long run, that the programme will make some contribution to these scores.

The IACCC indicator measures the number of suspects charged on cases that the IACCC is directly supporting. The type of support provided is case dependent, but the dissemination of intelligence will nearly always be the foundational component. IACCC’s collaboration with international partners and initiatives is also case dependent.

FCDO has now signed fresh agreements for the coming financial year and will reassess the country list for this indicator as part of a broader log frame refresh.

Overall, the programme is likely to achieve its intended impact and outcomes given the momentum of delivery specifically via IACCC and Open Ownership. These indicators were only set up to Year 2, therefore a refresh of the log frame is needed for the following three years.

Justify whether the programme should continue, based on its own merits and in the context of the wider portfolio

The programme should continue. Impact and outcome indicators show that delivery is on track whilst individual project log frames display excellent progress made in Year 2 of the programme.

The programme will continue to contribute to the DOSD Business Plan and FCDO’s organisational delivery plan (ODP).

## C. DETAILED OUTPUT SCORING

Output Title	Greater, better quality BENOT globally driven by better data standards, coordinated and tailored technical assistance and stronger evidence and policy
Output number:		1	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
1.1 Number of tailored technical assistance projects delivered in ODA eligible countries through OO	12	OO have significantly exceeded their original target, delivering 26 tailored technical assistance projects in FY 24-25.
1.2 Number of research, evidence and guidance products to enhance global BO standards produced through OO	11	13 research, evidence and guidance products have been produced by OO.
1.3 Increased / evidence base for the / design and / implementation of BO / reforms by / governments and key / stakeholders, and in / WB operations	WB to have developed impact assessment and implementation toolkit for BO reforms	WB deliverables have been delayed, owing partly to changes in staff and unforeseen absences. The toolkit is expected to be delivered by end-2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicator 1.1: Open Ownership (OO) are engaged globally in delivering demand-led technical assistance on beneficial ownership transparency. OO significantly outperformed expectations this year, favouring a broad spread of engagements and a smaller number of deeper ones. The 26 tailored technical assistance projects supported16 countries to advance the implementation of beneficial ownership (BO) reforms. Of these, 10 made meaningful progress—either by initiating new reforms or strengthening existing ones, with Kenya, Lesotho, Mauritius, Botswana and Mexico demonstrating particular progress in Q4. This included actions such as introducing or amending legislation, or laying the groundwork for improving the quality and usability of BO data. This year has also seen a focus on collective action and peer-to-peer exchange through the Africa Beneficial Ownership Transparency Network, a forum for technical experts across the region to share best practice.

Indicator 1.2: In addition to technical support, Open Ownership provide a number of public research, evidence and guidance products. Recent policy briefs include "Detail: Collecting sufficient detail in beneficial ownership declarations", which provides high-level policy guidance and practical considerations for registrars, and "Using ownership information to flag vessels of interest" explores the potential for maritime security actors to utilise BO data.

Indicator 1.3: Beneficial Ownership Transparency deliverables under the World Bank trust fund have seen delays to timelines as originally set out, meaning the second tranche of funding has been withheld for over six months. Some delays were due to unforeseen and unavoidable personnel absences, which led to staff changes and slower team mobilisation.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicator 1.1: No major changes, but OO have significantly outperformed on this indicator. Part of this is explained by a small financial uplift in Q4 that supported the continuation of 4 in-country engagements. This is addition to managing a greater than expected resource requirement for AfBOTN, so is commendable.

Indicator 1.2: No major changes. OO have outperformed expectations, but more modestly than Indicator 1.1.

Indicator 1.3: No major changes. We have a list of milestones that we have requested to be completed before the release of the second tranche of funding, and we have used the one we deem most suitable for this AR.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Indicator 1.1: FCDO should consider setting higher milestones for OO next year that better reflect their capability to deliver, taking into account resource pressures and OO’s own new organisational strategy.

It is noted that TA takes time to generate visible policy outcomes, particularly when delivered through participatory and inclusive approaches. BO reforms are often complex and multifaceted, requiring time to build institutional knowledge, shift attitudes, and forge collaboration across government to deliver meaningful reforms.
Under their new organisational strategy (2025–2030), OO will be focusing its TA efforts on a smaller number of countries with the momentum and political will to drive real reform. Alongside this, they will continue to provide flexible, on-demand support through helpdesk-style engagement with other jurisdictions.
Learnings from this year highlighted by the partner include the importance of region-led approaches and a strong civil society as well as how to best capture the energy across the globe, particularly in Africa. Things that merit further work include accountability, measurement and cross-agency collaboration, all of which feature in the new grant.

Indicator 1.2: FCG may wish to consider asking OO for examples/cases of how their evidence and analysis is put to use, to help evidence which pieces of analysis are most impactful and widely consumed. This might help gauge where there is most interest in the broader BENOT space on new analysis products.

Indicator 1.3: No lessons learned or recommendations were identified for this output last year, so no progress to report. The World Bank is still adjusting to the FCDO’s annual funding cycle, which differs from its typical multi-year planning approach. Withholding the second tranche of funding to the Bank freed up funds for FCG to spend on other important projects in the previous financial year whilst providing an incentive for improved performance from World Bank colleagues. Creating a list of clear milestones that need to be achieved before releasing the second tranche has helped the Bank understand what FCDO expects of them and ensures funding is not provided in advance of need. Quarterly catch-ups have been useful for monitoring progress but given we have two separate projects with the Bank and there is often insufficient time to cover both projects within the hour, it is recommended that FCDO changes the frequency of its meetings with the Bank to monthly.

Output Title	Greater capability amongst national agencies drives clear case progression in a stronger international policy environment
Output number:		2	Output Score:	A
Impact weighting (%):		40	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
2.1 No. of countries where AML/CFT legal framework has been drafted with support from IMF and is in line with FATF standards	24	14 countries have made progress towards this indicator.
2.2 Number of legal instruments and investigative tools or procedures revised or introduced as a result of ICAR’s interventions	20	22 legal instruments and investigative tools or procedures were revised or introduced as a result of ICAR’s interventions, exceeding its annual target of 20 for the second year in a row.
2.3 Number of countries and global partners IACCC engages with	40	55 countries and global partners.

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicator 2.1: Over the past financial year, the IMF has supported the drafting of an AML/CFT legal framework for an additional 5 countries (Cote d,Ivoire, Nigeria, Yemen, Kosovo and Samoa) compared to the previous annual review. They have made progress on 36 projects reaching 50 countries, including 18 single-country projects, one multi-country project covering 4 countries, 10 thematic projects covering 29 countries and 2 analytical research projects. In South Sudan, a comprehensive AML/CFT law was approved, building on the work from the previous year. This work would not be captured in the output milestone as South Sudan’s legal framework was drafted last year. The team also helped develop an upgraded AML/CFT supervisory tool for the offsite risk-based supervision of banks in Bangladesh. Cote d‘Ivoire also made significant progress with its FATF International Corporation Review Group (ICRG) action plan. The current milestone targets may be overly ambitious and could create perverse incentives to prioritise AML/CFT legal drafting over practical work to address AML/CFT deficiencies. Therefore, it is recommended that milestone targets are adjusted downwards, and future annual reviews use the narrative section to report on other notable achievements beyond legal drafting. This will be captured during the update of the FCG logframe.

Indicator 2.2: The International Centre for Asset Recovery have had a very successful reporting period across all four of their key outputs, which cover training and mentoring, capacity building, production of asset recovery tools and international advocacy. Case-based assistance and mentoring continue to support deterrence, repurposing proceeds, restoring trust in citizens, and driving reforms. Technical Assistance continues to drive 80% of their impact, with learning and global advocacy making up the remaining 20%.

Highlights include:
- Over 100+ cases supported, with billions of illicit assets targeted
- 57 multi-jurisdictional operational/case-based meetings held
- 33 products disseminated to international audiences
- 45 training courses delivered, with 768 practitioners

ICAR’s role is best illustrated in several high-profile cases including the conviction of a former Peruvian president for bribery in the Odebrecht case, and support provided to Guernsey who confiscated nearly half a million dollars in criminal proceeds on behalf of Colombia.
Specifically in relation to the indicator above, ICAR are credited with playing an important role in the development of Zanzibar Economic Crime Centre. They have assisted with structured investigative plans, a proforma for asset declarations for ZAECA, a proforma for suspect profiles for ZECC and an agreement on the transmission of suspicious transaction reports. In Zambia, ICAR have supported updated legislation and institutional reforms which will improve the mutual legal assistance process and result in more efficient international cooperation. FCDO provided a well-received uplift to funding in Q3 and 4 to support additional, rapid response work to the Interim Government of Bangladesh, focused on legal advice to complement the operational support of the IACCC.

Indicator 2.3: Over the past year, IACCC has engaged with a wide range of countries and organisations to ensure the role of the IACCC is understood, and that requests for support continue to be channelled to the IACCC. Examples of engagement include meetings with, Colombia, Panama and Switzerland. The IACCC has successfully exceeded its target of 40 countries and partners to engage and intends to continue this effort. More broadly, IACCC is successfully embedded in Bangladesh, working collaboratively with other partners.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicator 2.1: No planned changes during the past year. There have been no milestones set for next year as funding was initially agreed for 2 years. Funding is now being agreed to enable us to continue to be part of the Trust Fund, so we will request an update to the log frame with milestones for both FY 25/26 and 26/27 (the latter year represents an extension to the IMF fund phase of one year).

Indicator 2.2: Specifically on the indicator above, the annual target for the 2025 work plan will increase to 24 (from 20), reflecting ICAR surpassing its own targets in both of the last two years.

Indicator 2.3: There have not been any reported major changes for this indicator in the past financial year, or for projected results. We expect IACCC to continue to find opportunities to engage with partners.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Indicator 2.1: There has been continued dialogue between IMF staff and FCDO PEA experts, and we have provided funds for external PEA analyses that have informed IMF assessments in Sri Lanka and Kenya. The mid-term evaluation of the programme will provide a series of lessons learned and it is recommended that donors and the IMF work together to implement recommendations from that report. More detail is outlined in the MEL section of this report.

Indicator 2.2: In their new Operational Strategy (2025-2028), ICAR will continue with the current delivery model, which focuses on demand-driven technical assistance to support case activity across all phases of case work, and flexibility to meet a range of intervention styles, which is enabled by core funding.

Learnings from the last Strategy include the importance of political economy analysis and risk assessments as well as regionalisation efforts for economic and environmental reasons. Another reflection is the value of a common policy agenda: asset recovery should be central in discussions around IFFs, kleptocracy and broader development challenges, and highlight best practice in the asset recovery field.

Over the next year, there will be opportunities to strengthen AML resistance further, with the new round of FATF evaluations creating new demand. In particular, ICAR will continue to promote non-conviction based forfeiture and respond to risks around cryptocurrency. There will likely be opportunities to promote the learnings of asset recovery in broader economic fields.

Indicator 2.3: The importance of remaining focused on the operational impact was highlighted as a key takeaway this year, as well as the importance of monitoring, evaluation and learning. A new focus in the coming year will be to review their current comms activity, taking advantage of the ten-year anniversary of the creation of the IACCC in 2026.

Since the last Annual Review, the Programme team has formalised quarterly meetings with the IACCC, which has improved collaboration, enabled a better understanding of their work, and identified more opportunities for FCDO to amplify IACCC’s work with diplomatic support. The Programme team is working closely with the IACCC on a risk register and a log frame to ensure it reflects progress on key objectives.

Output Title	Stronger evidence base provides a platform for better policy and programming on effective responses to grand corruption
Output number:		3	Output Score:	A+
Impact weighting (%):		20	Weighting revised since last AR?	No

Indicator(s)	Milestone(s) for this review	Progress
3.1 Total number of U4 helpdesk enquiries and total number of UK Government enquiries	5 enquiries, with at least 1 UK enquiry.	Significantly exceeded expectations. / 28 helpdesk enquiries between April 2024 and March 2025; 5 from FCDO (21%).
3.2 Number of publications on leading trends and policy implications emerging from investigative reporting on enablers through OCCRP work.	2	The first report was published in May 2025 with the Centre for Financial Crime & Security Studies (CFS) at the Royal United Services Institute (RUSI) "Disabling the Enablers of Sanctions Circumvention". We are still waiting for confirmation of publication timelines on the second report.
3.3 No. of working group meetings and learning events that showcase and advance discussions on corruption and IF data, measures and evidence (cumulative)	2	2 meetings have been convened by the Bank on illicit financial flows measurement. The first was last year and the second was conducted in June 2025.

Briefly describe the output’s activities and provide supporting narrative for the score.

Indicator 3.1: Over the reporting year, U4 have continued to build a strong research and evidence base for policy and programming on anti-corruption, as well as providing high quality training and a helpdesk service for donor partners. U4 also participated in numerous international fora.

U4 has completed 55 thematic research outputs across various anti-corruption themes, including blogs, briefs, issue papers, and topic pages. The subjects covered a diverse range of corruption issues including research on renewable energy in Mexico and Kenya, civil society in Cambodia, and in particular, a guide on corruption in prisons. The latter received substantial attention in the human rights field, notably from the UN Committee Against Torture, the Secretariat of the UN Human Rights Committee, and OHCHR, all of whom commended its timeliness and relevance. This research is complemented by the increasing body of work generated by the Helpdesk for donor partners. As well as exceeding the target number of enquiries required in indicator 3.1, Helpdesk responses have had positive feedback from FCDO staff on their responsiveness and their value for policy and programming work.

On training for donor partners, U4 expanded its course offerings over the reporting year. Seven self-paced courses are now accessible online and U4 also facilitated in-person courses, including Corruption in Fragile and Conflict-affected States, Corruption Risk Management and Corruption in the Justice Sector. In collaboration with donor partners, U4 also completed ten in-country engagements and five partner forums, the latter on areas such as evaluating anticorruption interventions in Ukraine, whistleblowing, and anti-corruption strategies.

Indicator 3.2: OCCRP published one publication instead of two, although the preparatory work and drafting of the second publication was largely completed in this reporting period. The second publication will be published soon.

OCCRP partnered with the Centre for Financial Crime & Security Studies (CFS) at the Royal United Services Institute (RUSI) to produce a cross-case analysis report titled "Disabling the Enablers of Sanctions Circumvention" which was published in May 2024. OCCRP and its partners exceeded the target of 6 presentations on the findings of the publications with 16 presentations including at the U.S. House of Representatives. With a subgrant issued under this project, Transparency International completed a near-final draft of a 23-page report entitled “Enabler Accountability: Assessing measures taken against enablers of illicit financial flows from Africa.” The report will be published later in 2025.

In addition, the University of Exeter's team developed a Language Learning Model (LLM)-powered solution designed to transform complex financial and regulatory documents into structured, accessible data, and used it to extract new datasets. This will provide a robust foundation for uncovering insights into service provider and enabler networks. For journalists to have manually reviewed all these filings would have been impossible. The model can also be used to extract structured data from other complex financial and regulatory documents in the future. The long-term benefits of this piece of work has been illustrated in the case study box below.

Indicator 3.3: The Bank organised a well-attended roundtable event on Measurement of Illicit Financial Flows in June 2025. There were 23 participants including representatives from the IMF, FATF, UNODC, OECD, UNCTAD, University of Sussex, Tax Justice Network, Utrecht School of Economics and EU Tax Observatory. The session was successful in bringing together a range of stakeholders to agree joint definitions of IFFs, share knowledge of activities and interventions that support IFF measurement and test ideas the Bank will take forward in measuring corruption-related IFFs. Participants recognised the value of having stakeholders meet to discuss these issues and another meeting will happen next year. Meanwhile, the Bank will develop a diagnostic framework for measuring corruption-related IFFs and enhancing the effectiveness of previous approaches.

NEW PROJECT Global Anti-Corruption Consortium (Transparency International and OCCRP): FCDO signed a new accountable grant with Transparency International (OCCRP constitutes an equal delivery partner) and the project began on 31 January 2025. This work aims to curb the movement of corruption proceeds and generate a stronger response to transnational grand corruption. The thematic priorities for this project are: (1) ownership transparency; (2) enablers of cross-border corruption and money laundering; (3) accountability for kleptocracy and high-level, grand corruption; and (4) reforms in global financial centres. This partnership leverages the distinct yet complementary strengths of investigative journalism and civil society advocacy to combat transnational corruption.

TI Secretariat have undertaken a broad range of advocacy initiatives, several of which resulted in positive progress towards intended outcomes, such as the TI-S and partners release of analysis on real estate ownership transparency and enablers, and OCCRP’s publication of 7 investigative stories from 5 countries. The GACC component of the project supported 4 national chapters in their advocacy and legal accountability efforts and finalised 7 legal submissions on cross border corruption.

This project does not yet have an agreed indicator on the overall log frame but will be included as part of the log frame refresh this summer.

Describe any changes to this output during the past year, and any planned changes as a result of this review.

Indicator 3.1: No changes were made during the past year, but changes are planned as part of this review, and U4’s external Mid-Term Review.

Indicator 3.2: There were two changes of note: firstly, the original target of 3 publications was revised down to 2. The innovative nature of this work meant that delivery was complex; a decision was made to reduce the original target.

Secondly, Journalists entering enabler data Output 2 Indicator 2.2 was not met. The idea was to support OCCRP to identify new ways to collect the data that journalists gather during the reporting process. The approach was intended to be flexible to reflect that this was an innovative and ambitious ask. After significant research, OCCRP decided it would be more effective and less risky to develop a tech solution for extracting enabler data from the hundreds of research answers written by the OCCRP research desk each year. OCCRP’s scoping work determined that a potential tool would be too costly. The work is on hold, therefore, but OCCRP hopes to pick it up when funding becomes available. The concept is ready to go, thanks to work done on this project.

The accountable grant with OCCRP for the enabler work came to an end on 31 March 2025.

Indicator 3.3: No changes were made to the original target. New milestones will be agreed as part of the FCO logframe update, building on previous plans and likely to include a piloted data-driven framework for corruption-related IFFs.

A new project component was agreed under this output, starting in Q4 25/26, providing funding to the Global Anti-Corruption Consortium (see above). The full scope of this component needs to be incorporated into the programme, particularly the logframe and Theory of Change, following this review.

Progress on recommendations from the previous AR (if completed), lessons learned this year and recommendations for the year ahead

Indicator 3.1: Over the years, U4 has been a consistently high performing partner, delivering high quality research, training and helpdesk responses. As a mature organisation, U4 is now in a position to become more than sum of its parts by a greater focus on its objective of developing a coherent global approach, and by planning for outcomes as much as outputs. This was confirmed in an independent Mid-term Review of U4 in 2024/5 (see MEL section below).
Other things to mention:
- The uncertainty of FCDO funding has been a concern to U4, and lead to a brief discussion about other funding partners; however, this is not being actively explored at present
- U4 have frequently mentioned that the support and leadership given by FCDO throughout the year, in its role as lead donor, has been very important and valued, both in hosting the Steering Committee in London; convening donors for key decisions; and in providing inputs throughout the year, including on the Mid-Term Review; and
- Aligning our log-frame and other programme documents as far as possible with U4’s own planning documents, has been immensely helpful.
Recommendations:
- That Indicator 3.1 is revised to reflect a more realistic level of Helpdesk enquiries in future years.
- That an additional indicator for U4 is developed to measure U4’s thought leadership on at least one area per year
Indicator 3.2: No specific recommendations for OCCRP but Recommendation 1 ‘Increase engagement and monitoring of partners through formalising regular discussions and communications products’ was implemented.

Case study: Impact beyond results / The grant’s legacy will continue for some time, expanding the quality, value and impact of OCCRP’s work. The project advanced at least four types of results beyond those tracked formally in the results framework, all of which will have a sustainable impact beyond the project’s completion. / Dedicated attention to Enablers at OCCRP and beyond. / Cross-case analysis. This project allowed OCCRP’s impact team to pilot the analysis of multiple investigations based around a common theme. / Impact partnerships with think tanks and universities. The project enabled OCCRP to experiment with partnering with think tanks and universities for the first time. OCCRP are now working to build a much wider initiative for how universities and investigative journalists can work together on data-intensive projects. / Data extraction and use of AI. This project allowed OCCRP to make tangible progress in addressing two of its top data priorities – relying less exclusively on leaks in its reporting and harnessing the power of AI to investigate corruption and illicit finance. The model developed by Exeter and shared with OCCRP will feed directly into wider processes to develop the next generation of investigative data tools and approaches, which OCCRP will use and make available to the wider journalism field.

Indicator 3.3: No specific recommendations for the Bank from last year for this indicator. For this year the suggested recommendation as laid out in output 1.3 is for FCDO to consider monthly meetings with the Bank to sustain momentum and allow for early detection and correction of delays in workstreams. The same applies to this output.
## D: VALUE FOR MONEY

Key cost drivers and performance

VfM performance compared to the original VfM proposition in the business case

Recommendation 6 in the previous Annual Review set out that the programme should aim to “develop a Value for Money (VfM) Framework for FCG with indicators covering economy, efficiency, effectiveness and cost-effectiveness in line with FCDO VfM best practice”. The in-house economist and programme managers have been working with partners to draft VfM indicators at project-level over the past year. These encompass the 5 Es of the FCDO’s value for money framework – economy, efficiency, effectiveness and equity (including gender equality, disability inclusion, LGBT+ and other equality considerations), and overall cost-effectiveness.

Value for Money indicators now exist for Open Ownership, U4, and IMF, whilst conversations with IACCC and WB are ongoing. TI/OCCRP and ICAR will be reporting on VfM, starting from Summer 2025. We will be monitoring over the next year and plan to report back in the next Annual Review once we are able to compare indicators with baseline figures for all projects.

Assessment of whether the programme continues to represent value for money

As per the previous Annual Review, findings from the previous programme (IACT) evaluation concluded that measuring impact and VfM of the programme at the outcome level was difficult due to the lack of a robust measure of corruption. Outcome and output attainment provide sufficient evidence that the programme continues to achieve impact. Funds will be allocated to a mid-year assessment of the FCG programme which will ensure VfM remains on track.

E: RISK

Overview of risk management

The FCG risk process is made up of three stages: individual project risk registers are maintained and discussed monthly with partners; risks out of appetite are then escalated to the programme risk register which is discussed at quarterly SRO meetings. In practice, emerging risks can be raised at any time with the SRO. Any risks out of appetite at programme level are then escalated to departmental level.

The FCG programme risk appetite for each of the seven risk categories was updated to align with the FCDO’s general risk appetite in Autumn 2024. This reflects a minor recommendation in the previous Annual Review. Strategy and context, and Policy and programme delivery sit at ‘receptive’, and all other categories are registered at ‘cautious’. There have been no risks out of appetite over the past year, apart from a risk associated with the impact of ODA decisions which has been escalated to departmental level for monitoring.

Risk exposure has been driven by strategy and context, including global events which could affect the pressure and workload of delivery for partners, and changes in partner countries’ circumstances which could impact delivery. Budget and staffing considerations have also factored into the overall risk assessment. The overall programme risk rating is classed as Moderate.

We have undertaken due diligence assessments on delivery partners, concluding that all risks are acceptable and within the project’s risk tolerance levels. In particular, we completed refreshed DDAs on IMF and WB projects this year, as well as new due diligence on Transparency International, the lead funding partner for the TI/OCCRP project. We continue to review due diligence recommendations regularly t and will undertake ongoing monitoring throughout the programme where appropriate to ensure risks are managed and remain within our risk appetite.

On environment and climate, we agree with the initial assessment within the business case that there continues to be no environmental or climate risks within the programme.

F: PROGRAMME MANAGEMENT: DELIVERY, COMMERCIAL & FINANCIAL PERFORMANCE

Summarise the performance of partners and FCDO, notably on commercial and financial issues.

Delivery of this programme is through seven different partners. Programme managers have organised quarterly meetings with partners at which programme issues, including finance, reporting and risks are standing agenda items.

Open Ownership - Forecasting and reporting has been efficient, timely and accurate. OO colleagues have worked closely with programme managers to develop a new reporting template this year, which has been successfully implemented.

U4 - U4 provides an annual (calendar year) report to its 8 partners. The report is detailed, outlining main achievements throughout the year. This year they have also provided a report covering January to May 2025, which ensures we have the latest updates for this Annual Review. The next reporting stage will be the Autumn donor meeting.

International Centre for Asset Recovery - ICAR provides six-monthly reports to its donors by way of annual Steering Committee Meetings and Core Donor meetings in Autumn and Spring respectively. Narrative reports are always high quality. FCDO colleagues will continue to work with ICAR to ensure reporting is proportionate.

Transparency International (and implementing partner: Organized Crime and Corruption Reporting Project) - This grant is held by Transparency International but OCCRP operate as an equal partner with an equal share of the funding. Although only running since February 2025, all programme management aspects are exceeding expectations, with regular meetings now arranged.

Organized Crime and Corruption Reporting Project – This project was completed in March 2025. Reporting was concise and suggestions for improvement were taken on board earlier in the year.

International Anti-Corruption Coordination Centre – IACCC provide detailed quarterly reports covering key progress on operational work and engagement undertaken. IACCC also provide quarterly finance reports outlining forecasts and actual spend across the financial year, as well as useful explanations on underspends and overspends for that period. NCA audited statements are available online and cover IACCC work. IACCC had a small underspend in FY24/25. The Programme team communicate with IACCC on an ad-hoc basis where necessary but have formally set up quarterly meetings to discuss progress, finances, and other key issues. As a PAG, IACCC own assets bought under the programme. However, the Programme team will carry out an asset review in FY25/26 to maintain oversight on purchases. The Programme team will also conduct a review of the risk register and logframe to ensure both teams are working to a single version.

IMF – The IMF provides good quality and comprehensive annual reporting. We have formal and regular update channels (quarterly meetings) as well as ad-hoc communications via email. We have access to Partners Connect – the IMF’s information management system – and detailed project-by-project financial reporting is provided in the Annual Report, including budget changes with accompanying rationale. Any proposed major changes to the budget of the programme require approval by the steering committee (donors) in advance. Programme management of the Trust Fund has exceeded expectations to date.

World Bank – The World Bank provides an annual report to its partners in advance of its Partnership Council meetings. The last PC meeting was held in June 2024, but this year it will be held in autumn. The annual report is due end of next month, which is misaligned with this Annual Review process, so we have relied on informal communication channels such as regular email discussions, and our quarterly catch ups to provide updates for this Annual Review.

G: MONITORING, EVIDENCE AND LEARNING

This annual review took place from late May to July 2025. We reviewed key documents and spoke with partners and stakeholders.

We will continue to monitor results, risks and strategic and technical issues but will also consider whether we need to dedicate more time to monitoring activities over the life of the programme, including increasing the amount of time contributing and working with partners to strengthen and improve the quality of data and use evidence and findings which will support decisions on resource allocation.

Throughout the year, informal feedback from partners has suggested we may wish to consider how we can optimise the links between activity delivered by FCDO and delivery partners, in particular when we have more than one partner operating in the same country. On a similar theme, IFAC should take account of other FCDO funding sources and how we can coordinate internally. We will seek to explore these areas and have listed both as formal recommendations.

We were a lead reviewer for U4’s external mid-term review of both their work and the organisation and which has identified multiple recommendations for U4 management and its donor partners. The principle recommendations are that: U4 should focus its original research on fewer themes to increase its impact; that they should move towards outcome-focused deliverables; and that they should increase U4’s engagement in international fora. At the U4 Steering Committee, donor partners expressed support for these changes, and U4 management has also accepted the recommendations.

The IMF has undertaken an externally led mid-term review of the third phase of the programme and the UK volunteered to be a member of the evaluation sub-committee, providing comments and feedback on the draft report. The report is due to be finalised in August and will be shared with all donors. The report highlighted a few areas, particularly that impact could be enhanced by more directly focussing on jurisdictions and sectors with macro-relevant ML/TF risks; coordination within IMF area departments could be improved; CD traction is sometimes affected by recipient capacity constraints, staff turnover and competing priorities; the IMF can and should conduct more analytical and research reporting; and donor reporting is comprehensive but administratively burdensome and could be further streamlined. At the June steering committee, donors agreed with this assessment and the IMF will take forward these recommendations to further strengthen strategic focus, delivery and impact of the programme.

We will undertake an external mid-term assessment of FCG in the coming year to inform the last two years of the programme. We will also organise a partner learning event as part of this process.
There have been no known changes in the evidence for this programme.

We have not had the resources to share best practice via community of practice fora but we will look to see whether there are any opportunities to join up with other parts of the organisation to undertake this.

Date of last narrative financial report	OO: April 2025 / U4: May 2025 / ICAR: April 2025 / TI/OCCRP: May 2025 / IACCC: May 2025 / IMF: June 2025 / WB: Due shortly	Date of last audited annual statement	OO: January 2025 / U4: June 2025 / ICAR: Due shortly / TI/OCCRP: New project / IACCC: August 2024 / IMF: N/A / WB: N/A